## Introduction
Renewable Energy Planning Database
Version: June 2020 (Q2)
Introduction
The Renewable Energy Planning Database ('REPD') is managed by Eunomia Research and Consulting Ltd (‘Eunomia’) on behalf of the Department of Business, Energy & Industrial Strategy ('BEIS’). The database tracks the progress of renewable electricity projects (including those that could also be used for CHP) and electricity storage projects from inception, through planning, construction, operation and decommissioning. The REPD is updated on a monthly basis, and contains information on all Renewable Electricity (and CHP) projects up to the end of the previous calendar month.
Table Headings
General Facility Details
| Heading | Explanation
| Old Ref. ID | The old reference ID associated with a project in a previous version of the database
| Ref. ID | Project reference ID number in REPD database
| Record Last Updated | Date a project record was last updated or checked
| Operator (or Applicant) | Name of operator or applicant
| Site Name | Name of development site
| Technology Type | Type of technology (e.g. solar photovoltaics, offshore wind etc.)
| Installed Capacity (MWelec) | Installed electrical capacity in megawatts (MW)
| CHP Enabled | Is the project capable of combined heat and power output
| Wind Turbine Capacity (MW) | For windfarms, the individual capacity of each wind turbine in megawatts (MW)
| No. of Wind Turbines | For windfarms, the number of wind turbines to be located on the development site
| Height of Turbines (m) | For windfarms, the height of the wind turbines in metres (m)
| Mounting Type for Solar | For solar PV developments, whether the PV panels are ground or roof mounted
Current Status
| Heading | Explanation
| Development Status | No Application Required - A project that does not require planning permission has been announced by the developer
Planning Application Submitted - Planning application validated by planning authority
Planning Application Withdrawn - Planning application has been withdrawn by the applicant
Planning Permission Granted - Planning permission granted by planning authority
Planning Permission Refused - Planning permission refused by planning authority
Appeal Lodged - An appeal has been lodged by the applicant following a refusal of planning permission
Appeal Withdrawn - An appeal agaisnt a refusal of planning permission has been withdrawn
Appeal Refused - An appeal has been refused (dismissed) by the planning inspectorate, such that the original refusal remains
Appeal Granted - An appeal against a planning refusal has been granted (upheld) and planning permission is therefore granted
Secretary of State - Called In - A planning application has been called in by the Secretary of State such that the Secretary of State will determine whether planning will be granted or refused
Secretary of State - Refusal - The Secretary of State has refused planning permission after calling-in a planning application for review
Secretary of State - Granted - The Secretary of State has granted planning permission after calling-in a planning application for review
Under Construction - A project is under construction
Operational - A project is operational
Decommissioned - A project has been decommissioned and is no longer operating
Abandoned - Project has been abandoned by developer
| Development Status (short) | This is a description of the current status of the development in a more succinct form. For example, where a facility has obained planning permission either directly from the Local Planning Authority, through an appeal, or from the Secretary of State, it is classified here as 'Awaiting Construction'. Where a development has been refused planning permission, either directly from the LPA, following an appeal, or from the Secretary of State, it is classified here as 'Application Refused'.
Location Details
| Heading | Explanation
| Address | Site address of the development
| District | District the development site is located within
| Region | Region the development site is located within
| Country | Country the development site is located within
| Post Code | Post code of the development site
| X-coordinate | X & Y coordinates for development site in British National Grid
Y-coordinate
Planning Details
| Heading | Explanation
| Local Planning Authority | The relevant local planning authority for the project
| Planning Application Reference | The reference number associated with the planning application
| Appeal Reference | The reference number associated with an appeal
| Secretary of State Reference | The reference number associated with a Secretary of State Intervention
| Type of Secretary of State Intervention | The type of Secretary of State of Intervention. This can be one of three types: recovery, call-in, or holding direction
| Judicial Review | The latest date of when a legal challenge has been launched to review the lawfulness of a planning application and/or appeal decision
| Offshore Wind Round | Leasing round in which an offshore wind project was established
Timeline
| Heading | Explanation
| Planning Application Submitted | Date planning application was validated
| Planning Application Withdrawn | Date planning application was withdrawn
| Planning Permission Refused | Date planning permission was refused
| Appeal Lodged | Date an appeal was lodged
| Appeal Withdrawn | Date an appeal was withdrawn
| Appeal Refused | Date an appeal was refused (dismissed)
| Appeal Granted | Date an appeal was granted (upheld)
| Planning Permission Granted | Date planning permission was granted by the planning authority
| Secretary of State - Intervened | Date of a project that is 'Called In' by the Secretary of State
| Secretary of State - Refusal | Date planning permission was refused by the Secretary of State
| Secretary of State - Granted | Date planning permission was granted by the Secretary of State
| Permission Expiration Date | Date a planning permission expires (as per the planning decision)
| Under Construction | Date construction on site has begun
| Operational | Date a project become operational

## Database
Public Database - June 2020 (Q2)
General Facility Details | [16 empty] | Current Status |  | Location Details | [6 empty] | Planning / Development Details | [6 empty] | Timeline (dd/mm/yyyy)
Old Ref ID | Ref ID | Record Last Updated (dd/mm/yyyy) | Operator (or Applicant) | Site Name | Technology Type | Storage Type | Storage Co-location REPD Ref ID | Installed Capacity (MWelec) | CHP Enabled | RO Banding (ROC/MWh) | FiT Tariff (p/kWh) | CfD Capacity (MW) | Turbine Capacity (MW) | No. of Turbines | Height of Turbines (m) | Mounting Type for Solar | Development Status | Development Status (short) | Address | County | Region | Country | Post Code | X-coordinate | Y-coordinate | Planning Authority | Planning Application Reference | Appeal Reference | Secretary of State Reference | Type of Secretary of State Intervention | Judicial Review | Offshore Wind Round | Planning Application Submitted | Planning Application Withdrawn | Planning Permission Refused | Appeal Lodged | Appeal Withdrawn | Appeal Refused | Appeal Granted | Planning Permission Granted | Secretary of State - Intervened | Secretary of State - Refusal | Secretary of State - Granted | Planning Permission Expired | Under Construction | Operational
N00053B | 1 | 2009-07-07 | RWE npower | Aberthaw Power Station Biomass | Biomass (co-firing) |  |  | 35 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Aberthaw Power Station , The Leys , Aberthaw Barry , Vale of Glamorgan | South Glamorgan | Wales | Wales | CF62 4ZW | 302219 | 166320 | Vale of Glamorgan Council | 04/00580/FUL | [5 empty] | 2004-04-16 | [6 empty] | 2004-09-03 |  |  |  |  | 2006-05-01 | 2007-05-01
AA110 | 2 | 2017-11-20 | Orsted (formerly Dong Energy) / Peel Energy | Hunterston - cofiring | Biomass (co-firing) |  |  | 170 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Hunterston, Fairlie, West Kilbride, Ayrshire | Strathclyde | Scotland | Scotland |  | 218740 | 652937 | Scottish Government (S36) | [6 empty] | 2010-06-02 | 2012-06-27
B0730 | 3 | 2020-06-04 | Scottish and Southern Energy (SSE) | Ferrybridge Multifuel 2 (FM2) | EfW Incineration |  |  | 70 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational |  | West Yorkshire | Yorkshire and Humber | England |  | 447490 | 424684 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2014-08-20 | [6 empty] | 2015-10-28 |  |  |  | 2020-10-28 | 2016-09-01 | 2019-12-20
1106000 | 4 | 2003-12-18 | Energy Power Resources | Thetford Biomass Power Station | Biomass (dedicated) |  |  | 38.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Thetford Power Station , Marley Building Materials Site , Two Mile Bottom, Mundford Road, Thetford , Norfolk | Norfolk | Eastern | England |  | 585300 | 286900 | Breckland Council | [6 empty] | 1994-06-23 | [6 empty] | 1995-05-05 | [5 empty] | 1998-10-02
2047000 | 5 | 2005-09-29 | Agrigen | Nunn Mills Road Biomass Plant | Biomass (dedicated) |  |  | 8.82 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Nunn Mills Road , Northampton , Northamptonshire | Northamptonshire | East Midlands | England |  | 476500 | 259700 | Northamptonshire County Council | [6 empty] | 1997-06-24 |  | 1999-02-01
70700000 | 6 | 2004-08-13 | Incetec / Border Biofuels | Kingmoor Marshalling Yard | Biomass (dedicated) |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Kingmoor Marshalling Yard, Carlisle, Cumbria | Cumbria | North West | England |  | 337200 | 559800 | Carlisle City Council | [6 empty] | 1999-01-14 | [6 empty] | 2000-03-16
9162000 | 7 | 2004-11-29 | NOVERA | North Wiltshire Biomass Power Plant | Biomass (dedicated) |  |  | 5.528 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | North Wiltshire Biomass Power Plant, Kingshill Farm, Cricklade, Wiltshire | Wiltshire | South West | England |  | 411500 | 192500 | Wiltshire Council | 00/01204/EIA | 34716010 |  |  |  |  | 2000-05-24 |  | 2001-09-11
100640000 | 8 | 2003-12-23 | Private Developer | Newbridge Power Station | Biomass (dedicated) |  |  | 15 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land adjacent to BSW Sawmills , Newbridge on Wye , Powys | Powys | Wales | Wales |  | 302400 | 256000 | Powys County Council | PR5332/02 | [6 empty] | 2003-12-23
11065000 | 9 | 2004-08-30 | Agricultural Energy Company Limited | Poole Biomass Plant | Biomass (dedicated) |  |  | 10.93 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Poole Biomass Power Plant, near Wellington , Adjacent to Brickworks and Waste Disposal Site , Near Wellington , Somerset | Somerset | South West | England |  | 314900 | 121800 | Taunton Deane Borough Council | [7 empty] | 2004-08-30
12076000 | 10 | 2012-01-04 | Yorkshire Environmental | Eggborough Biomass Power Station | Advanced Conversion Technologies |  |  | 10.62 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Eggborough Biomass Power Station Eggborough Near Selby North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 457200 | 424000 | Selby District Council | [6 empty] | 1996-05-21 | [6 empty] | 1997-01-15
A0047 | 11 | 2018-12-04 | Eastman Peboc Factory | Eastman Peboc Factory | Biomass (dedicated) |  |  | 31 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused |  | Gwynedd | Wales | Wales |  | 243260 | 376631 | Isle of Anglesey County Council | [6 empty] | 2011-01-15 |  | 2012-05-15 | 2013-07-15 |  | 2013-07-31
A0138 | 12 | 2012-01-04 | AHS Energy | AHS Energy (Combustion) | Biomass (dedicated) |  |  | 4.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | AHS Energy, Coppards Lane, Northiam, East Sussex | East Sussex | South East | England | TN31 6QP | 583577 | 125972 | Rother District Council | RR/2009/1283/P | [5 empty] | 2009-05-20 |  | 2009-11-19
A0186 | 13 | 2011-05-05 | Northern Energy Developments | Forestry Commission Depot | Biomass (dedicated) |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Invergarry, Highlands. | Highland | Scotland | Scotland | PH35 4HG | 229288 | 801062 | Highland Council | 09/00325/FULLO | [5 empty] | 2009-08-28 |  | 2011-02-22
A0331 | 14 | 2012-04-04 | Dalkia | Chilton Energy Plant | Biomass (dedicated) |  |  | 18 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Chilton Industrial Estate, Chilton, Ferryhill, County Durham | Durham | North East | England |  | 428049 | 530414 | Durham County Council | 7/2008/0522/DM | [5 empty] | 2008-09-17 | [6 empty] | 2009-11-24 |  |  |  |  | 2010-03-01 | 2012-03-12
A0420 | 16 | 2011-08-17 | Bronzeoak Thermal Processing | Bronzeoak Thermal | Biomass (dedicated) |  |  | 12.7 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Btpl, Acorn Industrial Park, Dimmer Lane, Castle Cary, Somerset, | Somerset | South West | England | BA7 7NR | 361823 | 131905 | South Somerset District Council | 02/01774/CPO | [5 empty] | 2002-06-07 | [6 empty] | 2002-08-22
AA395 | 20 | 2012-07-23 |  | Chilton Bros Biomass Plant | Biomass (dedicated) |  |  | 2.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | 19 Ladywell Avenue Girvan South Ayrshire | Strathclyde | Scotland | Scotland | KA26 9PF | 219921 | 600195 | South Ayrshire Council | 10/01397/APP | [5 empty] | 2010-09-18 | 2011-07-21
AA851 | 22 | 2012-08-10 | Double H Nurseries | Double H Nurseries Biomass Plant | Biomass (dedicated) |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Double H Nurseries, Gore Road, New Milton | Hampshire | South East | England | BH25 5NQ | 422804 | 94625 | Hampshire County Council | 12/98264 | [5 empty] | 2012-01-25 | [6 empty] | 2012-05-29 | [5 empty] | 2012-12-15
B0242 | 23 | 2016-10-25 | REACT Energy (Kedco) | Newry Biomass Phase 1 (Gasification) | Advanced Conversion Technologies |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Newry | Co. Down | Northern Ireland | Northern Ireland |  | 117392 | 488885 | Northern Ireland Planning Service | [19 empty] | 2012-06-27
B0376 | 24 | 2012-05-29 | Balfor Beaty | Beckton STW Biodiesel Power Plant | Biomass (dedicated) |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beckton Sewage Treatment Works Jenkins Lane East Ham London | Greater London | London | England | IG11 0AD | 545350 | 181950 | Newham London Borough Council | [19 empty] | 2010-12-01
B0461 | 26 | 2012-08-07 | Living Power (REG Bio-Power) | Buslingthorpe Power Station (Leeds North) | Biomass (dedicated) |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Penraevon Industrial Estate, Buslingthorpe Green, Leeds | West Yorkshire | Yorkshire and Humber | England | LS7 2HG | 430213 | 435435 | Leeds City Council | 10/04466/FU | [5 empty] | 2010-09-30 | [6 empty] | 2010-12-30 | [5 empty] | 2011-10-14
C0001 | 27 | 2013-10-08 | Surrey County Council | Redhill Road Biomass Power Plant | Biomass (dedicated) |  |  | 2.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | The Depot, 46 Redhill Road, Cobham, Surrey | Surrey | South East | England | KT11 1EQ | 508090 | 160261 | Elmbridge Borough Council | 2012/0423 | [5 empty] | 2012-02-06 |  | 2012-11-06
EN00001 | 28 | 2010-06-09 | Balcas | Invergordon Pellet Mill | Biomass (dedicated) |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Invergordon, Ross-shire | Highland | Scotland | Scotland |  | 271390 | 870450 | Highland Council | 06/00944/FULRC | [5 empty] | 2006-04-15 | [6 empty] | 2007-04-16 | [5 empty] | 2009-11-01
EN00118 | 32 | 2011-06-29 | Green Renewable Energy Company | Clean Renewable Plant at Old Llynfi Power Station | Biomass (dedicated) |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Old Llynfi Power Station, Aberkenfig, Bridgend | Mid Glamorgan | Wales | Wales |  | 288400 | 186900 | Bridgend County Borough Council | 05/364/FUL | [5 empty] | 2005-03-28 | [6 empty] | 2006-02-16
EN00121 | 33 | 2013-10-08 | Balcas Timber | Balcas Timber Biomass CHP Plant | Biomass (dedicated) |  |  | 2.45 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Balcas Timber Ltd, Laragh, Enniskillen, Co. Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT94 2FQ | 31750 | 505000 | Northern Ireland Planning Service | [6 empty] | 2003-06-01 | [6 empty] | 2004-06-01 | [5 empty] | 2005-11-14
EN00151 | 34 | 2011-06-29 | Caledonian Paper | Caledonian Papermill | Biomass (dedicated) |  |  | 26.043 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Meadowhead Road, Shewalton, Irvine | Strathclyde | Scotland | Scotland | KA11 5AT | 233710 | 634940 | North Ayrshire Council | 06/00479/PP | [5 empty] | 2006-05-05 | [6 empty] | 2006-07-11 | [5 empty] | 2009-06-04
EN00156 | 35 | 2016-05-10 | UK Wood Recycling | Wilton International | Biomass (dedicated) |  |  | 35.22 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wilton International, PO Box 1985, Wilton, Middlesbrough, Cleveland | Cleveland | North East | England | TS90 8WS | 458500 | 519500 | Redcar and Cleveland Borough Council | R/2006/0910/FFM | [5 empty] | 2006-09-06 | [6 empty] | 2006-11-07 |  |  |  |  | 2006-11-08 | 2007-03-26
EN00236 | 37 | 2009-12-04 | Bioflame | South View Farm | Biomass (dedicated) |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | South View Farm , Yatts , Pickering | North Yorkshire | Yorkshire and Humber | England |  | 480945 | 486785 | North York Moors National Park Authority | NYM/2005/0657/FL | [5 empty] | 2006-02-01 | [6 empty] | 2006-10-24 | [5 empty] | 2007-10-01
EN00351 | 38 | 2009-03-20 | G B Bio | Tansterne Straw-Burning Power Station | Biomass (dedicated) |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land East of Tansterne Grange, Tansterne Lane, Flinton, East Riding of Yorkshire | Humberside | Yorkshire and Humber | England |  | 522530 | 437505 | East Riding of Yorkshire Council | 06/09030/STOUT | [5 empty] | 2006-11-13 |  | 2007-08-06
EN00544 | 40 | 2014-12-02 | RWE Innogy | Stallingborough Biomass Power Plant | Biomass (dedicated) |  |  | 65 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Stallingborough, near the port facilities of Immingham | Humberside | Yorkshire and Humber | England | DN41 8 | 519000 | 411520 | DECC (S36) | [6 empty] | 2007-02-16 | 2008-06-16 | [5 empty] | 2011-05-16
EN00569 | 41 | 2010-06-09 | Norbord | Cowie Biomass Facility | Biomass (dedicated) |  |  | 15 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Norbord Ltd, Station Road, Cowie, Stirlingshire | Stirling | Scotland | Scotland | FK7 7BW | 284085 | 688685 | Stirling Council | 06/00005/DET | [5 empty] | 2006-01-06 | [6 empty] | 2006-07-27 | [5 empty] | 2008-02-01
EN00573 | 42 | 2011-08-18 | Private Developer | Brigg Renewable Energy Plant | Biomass (dedicated) |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | British Sugar Corporation Ltd, Access roads to power station, Scawby | Humberside | Yorkshire and Humber | England | DN20 9LT | 498860 | 406109 | North Lincolnshire Council | PA/2008/0793 | [5 empty] | 2008-05-22 | 2008-09-15
EN00601 | 43 | 2011-09-12 | Dingle Holdings | Kings Dock Biomass | Biomass (dedicated) |  |  | 49.9 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Kings Dock , Swansea | West Glamorgan | Wales | Wales | SA1 8QT | 267902 | 192506 | City and County Council of Swansea | 2007/2684 | APP/B6855/A/09/2111230 |  |  |  |  | 2007-11-27 |  | 2009-04-06 |  |  | 2010-12-14
ENA0003 | 44 | 2006-05-23 | TPS (UK) | Thornton Power Station | Biomass (dedicated) |  |  | 9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wyre | Lancashire | North West | England |  | 334526 | 443323 | Wyre Borough Council | [19 empty] | 2002-06-15
H0064 | 46 | 2016-09-02 | A C Shropshire Ltd | Green's Lodge Farm | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | A C Shropshire Ltd, Green's Lodge Farm, Forest Road, Huncote | Leicestershire | East Midlands | England | LE67 4UY | 446531 | 314260 | Leicestershire County Council | 2009/0564/01 | [5 empty] | 2009-09-09 | [12 empty] | 2013-05-14
IF1016 | 47 | 2013-07-04 | Iggesund Paperboard (Workington) | Iggesund Paperboard CHP Plant | Biomass (dedicated) |  |  | 49 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Siddick, Workington, Cumbria | Cumbria | North West | England | CA14 1JX | 300293 | 530977 | Allerdale Borough Council | 2/2010/0982 | [5 empty] | 2010-11-17 | [6 empty] | 2011-03-08 | [5 empty] | 2013-02-17
IF1019 | 48 | 2012-11-15 | Biossence | Cophall Wood (ATT) | Biomass (dedicated) |  |  | 19 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land adjoining Cophall Wood Transfer Station, Cophall Wood, Hailsham Road (A22), Polegate | East Sussex | South East | England |  | 557716 | 106875 | East Sussex County Council | WD/621/CM(EIA) | [5 empty] | 2009-12-17 | 2010-08-20
N00009M | 49 | 2010-04-30 | Ancillary Components | Goosey Lodge Industrial Estate | Biomass (dedicated) |  |  | 16 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Goosey Lodge Industrial Estate , Wymington , Rushden , Northamptonshire | Bedfordshire | Eastern | England | NN10 9LU | 496208 | 236736 | Central Bedfordshire Council | [19 empty] | 2000-12-31
N00027B | 50 | 2010-12-07 | Express Power | Express Park | Biomass (dedicated) |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Express Park (Land north of Express Road), Bristol Road, Bridgwater | Somerset | South West | England |  | 330660 | 136870 | Sedgemoor District Council | 1/09/03/004 | 1164386 |  |  |  |  | 2003-02-25 |  | 2004-04-15
N00029B | 51 | 2009-11-05 | Western Skip Hire | Limekiln Hill Quarry | Biomass (dedicated) |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Limekiln Hill Quarry , Mells , Somerset | Somerset | South West | England |  | 372500 | 149500 | Mendip District Council | 106744/010 | [5 empty] | 2000-04-04 | [6 empty] | 2000-12-11
N00032B | 53 | 2005-08-04 | Energy Power Resources | Grimethorpe Biomass Gasifiction Power Plant | Biomass (dedicated) |  |  | 42 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Ferrymoor | South Yorkshire | Yorkshire and Humber | England |  | 434700 | 406300 | Barnsley Council | B/02/0511HR | [6 empty] | 2005-08-04
N00036B | 54 | 2011-06-29 | Private Developer | The Yeld Biomass Project | Biomass (dedicated) |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | The Yeld, Lions Hall, Kingston, Herefordshire | Hereford and Worcester | West Midlands | England | HR5 3LY | 334983 | 256434 | Herefordshire Council | NW20052690/N | [5 empty] | 2005-08-11 | [6 empty] | 2005-09-19
N00050M | 55 | 2011-06-29 | Talbotts Heating | Talbotts Heating Ltd | Biomass (dedicated) |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Talbotts Heating Ltd , St Albans Road , Stafford | Staffordshire | West Midlands | England |  | 392500 | 323500 | Stafford Borough Council | 00/39093/FUL | [5 empty] | 2000-05-05 | [6 empty] | 2000-07-20
N00051B | 56 | 2006-04-27 | Peninsular Power | Winkleigh Biogas Generator | Advanced Conversion Technologies |  |  | 23 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Former RAF Airfield , Winkleigh , Devon | Devon | South West | England |  | 261685 | 109395 | Torridge District Council | 1/2149/2004 | APP/W1145/A/06/2026225 |  |  |  |  | 2004-10-15 |  | 2006-04-07 | 2006-11-01 | 2007-03-01
N00052B | 57 | 2011-06-29 | Western Bioenergy, affiliate of Western Log | Western Wood Energy Plant | Biomass (dedicated) |  |  | 14 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Longlands Lane, Margam, nr junction 38 of the M4. | West Glamorgan | Wales | Wales |  | 277930 | 186880 | Neath Port Talbot County Borough Council | P2004/0035 | [5 empty] | 2004-01-09 | [6 empty] | 2004-04-27 |  |  |  |  | 2006-11-01 | 2009-11-01
N00063B | 58 | 2010-02-05 | Eccleshal Biomass | Eccleshall Biomass | Biomass (dedicated) |  |  | 2.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land Adjacent to Raleigh Ind. Estate, Sturbridge , Eccleshal | Staffordshire | West Midlands | England | ST21 6JL | 383491 | 330826 | Stafford Borough Council | 03/00942/FUL | [5 empty] | 2003-08-05 | [6 empty] | 2003-10-29 |  |  |  |  | 2006-05-01 | 2007-09-12
N00064B | 59 | 2009-09-22 | Charlton Sawmills | Charlton Sawmill | Biomass (dedicated) |  |  | 7 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Charlton Sawmill , Bideland Dinham , Nr Frome , Somerset | Somerset | South West | England | BA11 2RH | 372288 | 151929 | Mendip District Council | 084186/009 | [5 empty] | 2004-06-01 | [6 empty] | 2006-03-31
S0026B2 | 61 | 2006-06-16 | Border Biofuels | Burnside Farm Biomass Plant | Biomass (dedicated) |  |  | 2.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Glen Cloy, Brodick, Isle of Arran, North Ayrshire | Strathclyde | Scotland | Scotland |  | 200700 | 635500 | North Ayrshire Council | [6 empty] | 2001-06-26 | [6 empty] | 2001-10-08
S0030L1 | 62 | 2011-06-29 | EPR Scotland | Westfield Biomass Power Station | Biomass (dedicated) |  |  | 12.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Westfield Development Centre, Fife | Fife | Scotland | Scotland |  | 319000 | 695100 | Fife Council | [6 empty] | 1994-03-03 | [6 empty] | 1995-12-05 | [5 empty] | 2000-08-21
C2329 | 64 | 2015-02-25 | Plymouth Hospital NHS Trust | Derriford Hospital | Biomass (dedicated) |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Derriford Hospital, Derriford Road, Derriford, Plymouth, Devon | Devon | South West | England | PL6 8DH | 249930 | 59564 | Plymouth City Council | 13/01783/FUL | [5 empty] | 2013-09-18 | [6 empty] | 2013-12-10 |  |  |  |  | 2014-07-10 | 2014-10-01
B1145 | 65 | 2015-01-06 | C J Day Associates | Gortahar Road | Biomass (dedicated) |  |  | 2.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | 54 Gortahar Road, Gortahar, Rasharkin | Co. Antrim | Northern Ireland | Northern Ireland |  | 114111 | 572716 | Northern Ireland Planning Service | D/2005/0882/F | [5 empty] | 2006-03-07 | [6 empty] | 2007-10-03 |  |  |  | 2012-10-03
B1064 | 66 | 2015-06-17 | Cofely | Rampton Hospital Energy Centre | Biomass (dedicated) |  |  | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Retford, Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 0PD | 477542 | 377676 | Bassetlaw District Council | 12/01799/FUL | [5 empty] | 2012-12-24 | [6 empty] | 2013-02-06 |  |  |  |  | 2015-02-01 | 2015-05-29
B0799 | 67 | 2018-11-21 | Forever Fuels | Upper Geiselittle Biomass Plant | Biomass (dedicated) |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Upper Geiselittle Farm, Thurso, Highlands | Highland | Scotland | Scotland | KW14 8YH | 312487 | 965579 | Highland Council | 12/00945/FUL | [5 empty] | 2012-03-09 | [6 empty] | 2012-08-14
AA619 | 68 | 2016-09-02 | Oak Grove Renewables | Oak Grove Biomass Facility | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Oak Grove, Scottow, Norwich, Norfolk | Norfolk | Eastern | England | NR10 4DU | 626522 | 324286 | North Norfolk District Council | PF/11/1426 | [5 empty] | 2011-11-24 | [6 empty] | 2012-09-25 | [5 empty] | 2014-03-01
B1054 | 69 | 2017-01-23 | Honda | Honda Energy Centre (biomass) | Advanced Conversion Technologies |  |  | 4.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Highworth Road, South Marston, Swindon | Wiltshire | South West | England | SN3 4TZ | 418528 | 187782 | Swindon Borough Council | S/13/1860 | [5 empty] | 2013-12-17 | [6 empty] | 2014-03-19 |  |  |  | 2017-03-19
C2071 | 70 | 2014-02-17 | BEL (NI) | Sankey Valley Industrial Estate | Biomass (dedicated) |  |  | 4.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Adj Unit 1, Sankey Valley Industrial Estate, Anglezarke Road, Newton Le Willows, Merseyside | Merseyside | North West | England | WA12 8DJ | 357592 | 394778 | St Helens Council | P/2013/0738 | [5 empty] | 2013-09-20 |  | 2013-12-12
EN00378 | 71 | 2011-08-08 |  | Roves Farm | Biomass (dedicated) |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Roves Farm, Roves Lane, Swindon, | Wiltshire | South West | England | SN6 7QF | 420401 | 190490 | Swindon Borough Council | S/06/1753 | [5 empty] | 2006-08-15 | [6 empty] | 2006-11-13
IF1368 | 72 | 2016-09-02 | Lockwood Estates | Land at Grange Farm | Anaerobic Digestion |  |  | 1.125 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cliff Road, Spridlington, Market Rasen | Lincolnshire | East Midlands | England | LN8 2DN | 497563 | 383132 | West Lindsey District Council | 129564 | [5 empty] | 2013-02-25 | [6 empty] | 2013-06-04 |  |  |  |  | 2013-12-01 | 2014-12-01
60210000 | 73 | 2006-06-16 | Border Biofuels | Consett Power Station | Biomass (dedicated) |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Hownsgill Industrial Estate , Consett , Durham | Durham | North East | England |  | 410700 | 549800 | Durham County Council | [6 empty] | 2000-01-20 | [6 empty] | 2000-04-25
70680000 | 75 | 2005-11-28 | Border Biofuels | Byreshield Grains Woodgen | Biomass (dedicated) |  |  | 6.085 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Byreshield Hill , Falstone , Northumberland | Northumberland | North East | England |  | 368000 | 583500 | Northumberland County Council | [7 empty] | 2005-11-28
60240000 | 76 | 2005-11-28 | Border Biofuels (DynaMotive Europe) | Hexham Biofuel Power Station | Biomass (dedicated) |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Bridge End , Hexham , Northumberland | Northumberland | North East | England |  | 383449 | 555741 | Northumberland County Council | [7 empty] | 2005-11-28
1045000 | 78 | 2011-06-29 | European Development Corporation | Elean Business Park Biomass Plant | Biomass (dedicated) |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Elean Business Park Sutton Cambridgeshire | Cambridgeshire | Eastern | England |  | 545000 | 279900 | East Cambridgeshire District Council | [6 empty] | 1995-11-08 | [6 empty] | 1996-02-22 | [5 empty] | 2000-09-22
H0077 | 79 | 2014-02-20 | Northern Energy Developments | Dyemill Forestry Plantation | Biomass (dedicated) |  |  | 5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Dyemill Forestry Plantation Lamlash Brodick Isle Of Arran | Strathclyde | Scotland | Scotland | KA27 8NL | 203352 | 629538 | North Ayrshire Council | 13/00313/PP | [5 empty] | 2013-05-22 | 2014-01-16
AA193 | 81 | 2012-02-01 | RPS Planning & Development - Money | Thetford Biomass Power Station 2 | Biomass (dedicated) |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land to East of A134, Mundford Road, Thetford, Norfolk | Norfolk | Eastern | England |  | 586251 | 285851 | Norfolk County Council | C/3/2010/3004 | [5 empty] | 2010-12-28 |  | 2012-01-13
1087000 | 82 | 2011-06-29 | South Western Power (NOVERA) | Eye Biomass Plant | Biomass (dedicated) |  |  | 14.316 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Eye Biomass Plant , Eye Airfield, Site A , Eye Suffolk | Suffolk | Eastern | England |  | 613200 | 275200 | Mid Suffolk District Council | [19 empty] | 1992-07-01
01014M5 | 84 | 2014-05-20 | Cemex | Rugby Cement Works | Biomass (dedicated) |  |  | 35 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Rugby Cement, Lawford Road, Rugby, Warwickshire | Warwickshire | West Midlands | England |  | 448650 | 275665 | Rugby Borough Council | S965/06CM028 | [5 empty] | 2006-10-03 | [6 empty] | 2007-03-17
2043000 | 85 | 2014-02-12 | EPR Corby / Aztec Energy | Corby Biomass Plant | Biomass (dedicated) |  |  | 14.25 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Corby Biomass Plant , Phoenix Parkway , Corby , Northamptonshire | Northamptonshire | East Midlands | England |  | 489800 | 290900 | Corby Borough Council | 00/00143DPA | [5 empty] | 2000-05-11 | [6 empty] | 2001-04-01
A0005 | 86 | 2016-03-18 | University Of East Anglia | University of East Anglia CHP | Advanced Conversion Technologies |  |  | 1.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | UEA, Norwich | Norfolk | Eastern | England | NR4 7TJ | 619497 | 307667 | Norwich City Council | 07/00236/F | [5 empty] | 2007-03-03 | [6 empty] | 2007-11-20 | [5 empty] | 2009-11-30
A0063 | 87 | 2013-04-29 | Suez Energy Services | King's Yard | Biomass (dedicated) |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Carpenters Road, London. | Greater London | London | England | E15 2JH | 538424 | 183769 | Hackney London Borough Council | 2008/0826 | [5 empty] | 2008-04-08 | [6 empty] | 2009-03-10 |  |  |  |  | 2009-05-01 | 2012-07-25
A0181 | 89 | 2012-12-06 | EQ Waste | EQ Waste, Appspond Lane | Biomass (dedicated) |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Potters Crouch, Hertfordshire | Hertfordshire | Eastern | England |  | 511079 | 205798 | Hertfordshire County Council | 5/1470-07 | [5 empty] | 2007-06-08 | [6 empty] | 2010-05-25
A0181b | 90 | 2017-03-21 | Navitas Environmental (EQ Waste) | Appspond Lane (resubmission) | Biomass (dedicated) |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Appspond Lane, Potters Crouch, St. Albans, | Hertfordshire | Eastern | England | AL2 3NL | 511079 | 205798 | Hertfordshire County Council | 5/2108-09 | [5 empty] | 2009-10-16 | [6 empty] | 2010-12-02 |  |  |  | 2013-12-02
A0201 | 91 | 2019-07-18 | Forth Energy | Rosyth | Biomass (dedicated) |  |  | 120 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Rosyth Port | Fife | Scotland | Scotland | KY11 | 310449 | 682063 | Scottish Government (S36) | [6 empty] | 2010-11-09 | [6 empty] | 2014-01-24 |  |  |  | 2019-01-24
A0202 | 92 | 2019-11-29 | Grangemouth Renewable Energy | Forth Ports Ltd 2 (Grangemouth) | Biomass (dedicated) |  |  | 85 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Grangemouth Port | Falkirk | Scotland | Scotland | FK3 8UH | 293466 | 682661 | Scottish Government (S36) | EC00005229 | [5 empty] | 2010-09-17 | [6 empty] | 2013-06-03 |  |  |  | 2018-06-03
A0204 | 93 | 2012-03-06 | Forth Ports | Forth Ports Ltd 4 | Biomass (dedicated) |  |  | 120 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Leith Docks | Lothian | Scotland | Scotland |  | 326333 | 677112 | Scottish Government (S36) | [6 empty] | 2011-01-28 | 2012-02-09
A0208 | 94 | 2012-03-05 | Drax Power and Siemens Project Ventures | Drax Ouse Renewable Energy Park | Biomass (dedicated) |  |  | 290 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Selby, North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 466649 | 428375 | DECC (S36) | [6 empty] | 2009-07-23 | [6 empty] | 2011-08-10
A0209 | 95 | 2012-12-18 | Drax Power and Siemens Project Ventures | Drax Heron Renewable Energy Park | Biomass (dedicated) |  |  | 290 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land to the North, Humber Road, Killingholme. | Humberside | Yorkshire and Humber | England |  | 518091 | 417285 | DECC (S36) | PA/2009/1269 | [5 empty] | 2009-10-27 | [6 empty] | 2011-08-10
A0233 | 96 | 2014-04-01 | Blyth Biomass Plant | North Blyth Biomass Power Station | Biomass (dedicated) |  |  | 100 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Bate's Colliery, Port of Blyth, South East Northumberland | Northumberland | North East | England |  | 431322 | 582456 | DECC (S36) | [6 empty] | 2012-08-15 | [6 empty] | 2013-07-24
A0330 | 97 | 2014-05-07 | Dalkia | Pollington Energy Park | Biomass (dedicated) |  |  | 53 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Pollington, East Yorkshire | West Yorkshire | Yorkshire and Humber | England |  | 431479 | 431846 | DECC (S36) | S36 | [5 empty] | 2009-12-16 | [6 empty] | 2011-12-22
A0421 | 98 | 2012-02-01 | Bishop's Castle Biomass Power Ltd | Bishop's Castle Biomass Power Project | Biomass (dedicated) |  |  | 13 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned |  | Shropshire | West Midlands | England |  | 332704 | 288228 | Shropshire Council | 08/20502/F | [5 empty] | 2008-03-07 |  | 2008-05-20 |  |  |  | 2009-09-04 | 2009-09-04
A0422 | 99 | 2013-02-06 | Boyndie Biomass | Boyndie Airfield Biomass | Biomass (dedicated) |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Boyndie, Banff, Grampian | Grampian | Scotland | Scotland | AB45 2LR | 361978 | 864118 | Aberdeenshire Council | APP/2009/2327 | [5 empty] | 2009-07-16 | [6 empty] | 2010-02-24
A0482 | 101 | 2014-12-18 | Hunt's Heat & Power (BioFlame) | Chequers Lane | Biomass (dedicated) |  |  | 2.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | 75 - 77 Chequers Lane, Dagenham, Essex | Greater London | London | England | RM9 6QT | 548533 | 183901 | Barking and Dagenham London Borough Council | 08/01120/FUL | [5 empty] | 2008-08-28 | [6 empty] | 2008-12-12 |  |  |  | 2013-12-12
A0484 | 102 | 2016-10-24 | Peel Energy | Corpach Biomass Energy Plant | Biomass (dedicated) |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Kilmallie Hall Corpach Fort William | Highland | Scotland | Scotland | PH33 7JH | 209648 | 776708 | Highland Council | 10/04344/FUL | [5 empty] | 2010-10-27 | [6 empty] | 2010-12-09 |  |  |  | 2013-12-09
A0488 | 103 | 2014-02-24 | Purepower Energy | Huntingdon | Advanced Conversion Technologies |  |  | 4.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Woodhatch Farm, Thrapston Road, Ellington, Huntingdon, Cambridgeshire | Cambridgeshire | Eastern | England | PE28 0AE | 515960 | 272020 | Cambridgeshire County Council | H/05009/07/CW | [5 empty] | 2007-03-20 | [6 empty] | 2007-06-25 |  |  |  | 2010-06-25
A0489 | 104 | 2016-03-30 | Kiveton Heat and Power | Kiveton Recycling Centre | Biomass (dedicated) |  |  | 2.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | The Old Kiveton Quarry, Dog Kennel Hill, Kiveton, Park Station | South Yorkshire | Yorkshire and Humber | England | S26 6NG | 450612 | 382646 | Rotherham Metropolitan Borough Council | RB2008/1653 | APP/P4415/A/09/2106347 |  |  |  |  | 2009-02-10 |  | 2009-04-24 |  |  |  | 2010-02-03 | 2010-02-03 |  |  |  | 2015-02-03
AA118 | 106 | 2016-04-18 | MVV Energie, Ridham Dock | Ridham CHP Plant | Biomass (dedicated) |  |  | 25 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ridham Dock, Iwade, Sittingbourne, Kent | Kent | South East | England | ME9 8SR | 592076 | 168421 | Swale Borough Council | SW/10/0774 | [5 empty] | 2010-06-29 | [6 empty] | 2012-05-28 |  |  |  |  | 2013-04-08 | 2016-04-18
AA136 | 107 | 2015-12-08 | Tesco | Tesco Distribution Centre (Livingston) | Biomass (dedicated) |  |  | 6.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Carnegie Road, Deans Industrial Estate, Livingston | Lothian | Scotland | Scotland | EH54 8TB | 301071 | 669021 | West Lothian Council | 0467/FUL/10 | [5 empty] | 2010-06-30 | [6 empty] | 2010-12-08 |  |  |  |  | 2012-04-01
AA146 | 108 | 2013-11-22 | R Plevin & Sons Ltd | R.Plevin & Sons CHP | Biomass (dedicated) |  |  | 1.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Crookford Hill, Elkesley, Retford | Nottinghamshire | East Midlands | England | DN22 8BT | 467235 | 375633 | Bassetlaw District Council | ES/1848 and 18/10/00008 | [5 empty] | 2010-07-15 |  | 2013-10-10
AA194 | 109 | 2014-02-24 | Bioflame | Cardiff Dock Heat and Power | Biomass (dedicated) |  |  | 2.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Cold Stores Road, Queen Alexandra Dock | South Glamorgan | Wales | Wales |  | 320241 | 174279 | Cardiff Council | 08/02653/C | [5 empty] | 2008-12-04 | [6 empty] | 2009-02-06
AA244 | 110 | 2019-12-04 | Glennmont Partners | Port Clarence Biomass Plant | Biomass (dedicated) |  |  | 40 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Port Clarence Road, Port Clarence, Middlesborough | Cleveland | North East | England |  | 449811 | 521670 | Middlesbrough Council | S/CON/0038/10/P | [5 empty] | 2010-01-14 | [6 empty] | 2010-02-23 |  |  |  |  | 2015-11-17
AA359 | 112 | 2019-07-23 | L&S Waste Management | Pegham Renewable Energy Facility | Advanced Conversion Technologies |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Units D and E, Pegham Industrial Estate, Laveys Lane, Titchfield, Hampshire PO15 6SD | Hampshire | South East | England |  | 455549 | 108834 | Hampshire County Council | 11/00136/HCS | [5 empty] | 2011-01-24 | [6 empty] | 2011-04-07
AA379 | 113 | 2018-10-03 | Glennmont Partners | Margam Green Energy Plant | Biomass (dedicated) |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Longlands Lane, Margam, Port Talbot | West Glamorgan | Wales | Wales |  | 278940 | 186385 | Neath Port Talbot County Borough Council | P2008/1409 | APP/Y6930/A/10/2135473/WF |  |  |  |  | 2008-11-13 |  | 2010-03-16 |  |  |  | 2011-03-08 | 2011-03-08 |  |  |  |  | 2015-02-15 | 2017-12-01
AA392 | 114 | 2020-03-19 | Merevale and Blyth Estates | Merevale & Blyth Estate (Biomass Plant) | Biomass (dedicated) |  |  | 2.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Merevale Lane, Atherstone, Warwickshire | Warwickshire | West Midlands | England |  | 428108 | 297173 | Warwickshire County Council | NWB/10CM033 | [5 empty] | 2010-12-06 | [6 empty] | 2011-03-28 |  |  |  |  | 2018-02-15
AA430 | 115 | 2018-11-21 | Lynemouth Power | Lynemouth Power Station | Biomass (dedicated) |  |  | 420 | No |  |  | 420 | n/a | n/a | n/a | n/a | Operational | Operational | Woodhorn Ashington Northumberland | Northumberland | North East | England | NE63 9YH | 429850 | 590374 | Northumberland County Council | [18 empty] | 2016-01-01 | 2018-11-21
AA431 | 116 | 2015-08-13 | Scottish and Southern Energy (SSE) | Ferrybridge Multifuel 1 (FM1) | EfW Incineration |  |  | 68 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ferrybridge C Power Station, PO Box 39, Stranglands Lane, Knottingley, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF11 8SQ | 447490 | 424684 | DECC (S36) | 09/02103/OHL | [5 empty] | 2009-10-29 | [6 empty] | 2011-10-31 |  |  |  |  | 2012-10-01 | 2015-08-03
AA725 | 117 | 2018-02-01 | UYE (UK) / Veolia | Holbrook Community Renewable Energy Centre | Biomass (dedicated) |  |  | 6.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Rear Of Hadee Engineering Co Ltd, Rother Valley Way, Holbrook, Sheffield | South Yorkshire | Yorkshire and Humber | England | S20 3GH | 444564 | 381752 | Sheffield City Council | 12/00752/FUL | N/A |  |  |  |  | 2012-03-29 | [6 empty] | 2012-09-25 |  |  |  |  | 2015-07-17 | 2017-04-24
AA742 | 118 | 2018-04-24 | Alternative Use Group plc & Alchemy Farms | Riverside Industrial Estate Gasification Plant | Advanced Conversion Technologies |  |  | 10.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land at Riverside Industrial Estate, Marsh Lne, Boston, Lincolnshire | Lincolnshire | East Midlands | England |  | 533578 | 341831 | Lincolnshire County Council | PL\0245\09 | N/A |  |  |  |  | 2009-12-14 | [6 empty] | 2010-09-07 |  |  |  | 2013-09-07 | 2016-04-04 | 2018-03-15
AA761 | 119 | 2014-02-05 | International Power / GDF Suez | Rugeley Power Plant Conversion | Biomass (dedicated) |  |  | 1000 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Rugeley | Staffordshire | West Midlands | England | WS15 1PR | 405971 | 317375 | Stafford Borough Council | CH/12/0270 | N/A |  |  |  |  | 2012-11-29 | [6 empty] | 2013-01-09
AA789 | 120 | 2020-06-04 | Enviroparks Operations | Enviroparks Hirwaun Generation Site | Advanced Conversion Technologies |  |  | 20 | No |  |  | 11 | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Fifth Avenue, Hirwaun Industrial Estate, Hirwaun, Aberdare, Mid-Glamorgan | Powys | Wales | Wales | CF44 9YN | 293857 | 206832 | Brecon Beacons National Park Authority | 08/02488/FUL | [5 empty] | 2008-12-19 | [6 empty] | 2010-12-21 |  |  |  |  | 2016-02-18
AA952 | 121 | 2018-03-23 | Estover Energy | Cramlington CHP | Biomass (dedicated) |  |  | 27.7 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Windmill Industrial Estate, Cramlington, Northumberland | Northumberland | North East | England | NE23 1JY | 424308 | 578123 | Northumberland County Council | 12/02699/RENE | [5 empty] | 2012-08-31 | [6 empty] | 2013-01-21 |  |  |  |  | 2015-09-01 | 2018-03-15
B0089 | 122 | 2012-07-23 | Private Developer | Tyrone Energy 1 | Biomass (dedicated) |  |  | 2.1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lands 3 Art Road Artigarvan Strabane | Co. Tyrone | Northern Ireland | Northern Ireland |  | 53147 | 564212 | Northern Ireland Planning Service | J/2008/0177/F | [5 empty] | 2009-02-03 | [6 empty] | 2009-12-08 |  |  |  |  | 2011-08-01 | 2012-08-06
B0204 | 123 | 2012-12-17 | Centrica | Roosecote Biomass | Biomass (dedicated) |  |  | 80 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Roosecote near Barrowin- Furness, Cumbria. Roosecote | Cumbria | North West | England |  | 322350 | 468350 | The Planning Inspectorate - National Infrastructure | [7 empty] | 2012-12-17
B0251 | 124 | 2015-11-03 | ERE Developments | Evermore Renewable Energy (CHP) / Lisahally Power Station | Biomass (dedicated) |  |  | 15 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Site between Temple Road and Maydown Road, Lisahally opposite location of former dwelling 38 Temple Road, BT47 6FL | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 6FL | 64627 | 583737 | Northern Ireland Planning Service | A/2010/0030/F | [5 empty] | 2010-01-19 | [6 empty] | 2010-07-09 |  |  |  |  | 2013-12-19 | 2015-07-23
B0294a | 125 | 2015-12-02 | E.ON UK | Ironbridge Power Station | Biomass (dedicated) |  |  | 740 | No |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Buildwas Road , Telford | Shropshire | West Midlands | England | TF8 7BL | 365432 | 303783 | Shropshire Council | 12/00032/MAW | [5 empty] | 2012-01-03 | [6 empty] | 2012-04-05 | [5 empty] | 2013-03-27
B0305 | 126 | 2014-01-03 | Kronospan | Kronospan Biomass | Biomass (dedicated) |  |  | 9.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Holyhead Road, Chirk, Wrexham | Clwyd | Wales | Wales | LL14 5NT | 328595 | 338816 | Wrexham County Borough Council | P/2012/0165 | [5 empty] | 2012-03-05 | [6 empty] | 2012-09-14
B0344 | 127 | 2012-05-01 | Markley Group | Markley Group (Premiere Kitckens) Biomass | Biomass (dedicated) |  |  | 2.1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Unit Q1, Quadrant Distribution Centre, Quadrant Way, Hardwicke, Gloucester | Gloucestershire | South West | England | GL2 2RN | 380652 | 212428 | Stroud District Council | S.10/1242/FUL | [5 empty] | 2010-06-25 | [6 empty] | 2011-08-03 | [5 empty] | 2012-04-19
B0356 | 128 | 2019-11-04 | REACT Energy (Kedco) | Clay Cross CHP | Biomass (dedicated) |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Bridge Street, Clay Cross | Derbyshire | East Midlands | England |  | 439487 | 364075 | North East Derbyshire District Council | CW4/1114/98 | [5 empty] | 2014-12-17 | [6 empty] | 2016-04-11
B0390 | 129 | 2015-01-09 | Heathrow Airport | Heathrow Airport Biomass CHP | Biomass (dedicated) |  |  | 1.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Heathrow, London | Greater London | London | England |  | 507124 | 174485 | Hillingdon London Borough Council | 66849/APP/2010/479 | [5 empty] | 2010-03-02 | [6 empty] | 2010-05-25 |  |  |  |  | 2012-06-01 | 2013-01-01
B0462 | 130 | 2013-11-04 | REG Bio-Power | Bentwaters CHP | Biomass (dedicated) |  |  | 4.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bentwaters Business Park, Suffolk | Suffolk | Eastern | England |  | 634882 | 253510 | Suffolk Coastal District Council | C/07/1897 | [5 empty] | 2007-10-11 | [6 empty] | 2007-11-23 | [5 empty] | 2010-11-01
B0662 | 132 | 2014-01-09 | GDF SUEZ ENERGY UK | SAICA Paper Mill | Biomass (dedicated) |  |  | 41.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Partington Wharfside, land off Manchester Road, Carrington | Greater Manchester | North West | England |  | 372220 | 392117 | Trafford Council | H/69865 | [5 empty] | 2008-12-30 | [6 empty] | 2008-12-30 | [5 empty] | 2012-03-16
B1023 | 133 | 2014-12-16 | REACT Energy (Kedco) | Plymouth Energy Park Biomass CHP | Biomass (dedicated) |  |  | 10.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Ernesettle Lane, Plymouth | Devon | South West | England | PL5 2TT | 244609 | 60273 | Plymouth City Council | 14/01637/FUL | [5 empty] | 2014-09-03 | 2014-12-01
C0011 | 134 | 2013-04-24 | James Barr Ltd | PONTRILAS BIOMASS POWER PLANT | Biomass (dedicated) |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | The Sawmills, Pontrilas, Hereford | Hereford and Worcester | West Midlands | England | HR2 0BE | 340403 | 228529 | Herefordshire Council | DCSW2006/3693/N | [5 empty] | 2006-11-23 | [6 empty] | 2007-01-29
C0213 | 135 | 2018-07-18 | Sunrise Renewables | Hudson Dock East Biomass | Biomass (dedicated) |  |  | 9 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land At Hudson Dock East Barrack Street Sunderland | Tyne and Wear | North East | England | SR1 2BU | 441417 | 557257 | Sunderland City Council | 08/04526/FUL | [5 empty] | 2009-01-30 | [6 empty] | 2009-05-01
C0229 | 136 | 2016-06-15 | Fluid Leader Plc | Tenax Road - Renewable Energy Biomass Plant | Biomass (dedicated) |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Demolition Direct, Tenax Circle, Tenax Road, Trafford Park, Manchester, Greater Manchester | Greater Manchester | North West | England | M17 1JT | 378641 | 397677 | Trafford Council | H/70807 | [5 empty] | 2009-01-21 | [6 empty] | 2009-06-29
C0348 | 137 | 2017-03-27 | Edgeley Green Power (EGP) | Shoreham Renewable Energy Generation project | Biomass (dedicated) |  |  | 32 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | E/O Shoreham Power Station, Basin Road, Southwick, Brighton, East Sussex | West Sussex | South East | England | BN41 1WF | 525420 | 104804 | Adur and Worthing Councils | AWDM/0868/12 | [5 empty] | 2012-07-13 | [6 empty] | 2013-05-07
EN00103 | 138 | 2014-05-20 | Green Park Energy | Former Parkside Colliery | Biomass (dedicated) |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Winwick Road, Newton-le-Willows | Merseyside | North West | England |  | 360121 | 394484 | St Helens Council | P/2005/1251 | [5 empty] | 2005-10-17 | [6 empty] | 2006-05-19
EN00247 | 139 | 2017-06-23 | Eco Sustainable Solutions | Eco Composting | Biomass (dedicated) |  |  | 3.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Chapel Lane, Parley, Christchurch, Dorset | Dorset | South West | England | BH23 6BG | 410184 | 98499 | Dorset County Council | 8/11/0268 | [5 empty] | 2011-05-26 | [6 empty] | 2011-07-26 |  |  |  | 2014-07-26 | 2016-10-28 | 2017-03-22
EN00292 | 140 | 2017-06-23 | Scottish Bio-Power | Rothes Bio-Plant | Biomass (dedicated) |  |  | 8.32 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rothes Distillery, Speyside | Grampian | Scotland | Scotland |  | 327767 | 849116 | Moray Council | 08/00577/FUL | [5 empty] | 2008-03-17 | [6 empty] | 2009-01-28 |  |  |  |  | 2011-05-01 | 2013-04-16
EN00478 | 141 | 2018-10-03 | Orthios Group | Port Talbot Renewable Energy Plant | Biomass (dedicated) |  |  | 350 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Port Talbot | West Glamorgan | Wales | Wales |  | 276305 | 189045 | DECC (S36) | [6 empty] | 2006-10-23 | [6 empty] | 2007-11-21
EN00596 | 142 | 2013-07-29 | E.ON UK | Royal Portbury Docks Renewable Energy Plant | Biomass (dedicated) |  |  | 150 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Port of Bristol, Bristol | Avon | South West | England | BS20 | 347787 | 175980 | DECC (S36) | 09/P/1479/F2 | [5 empty] | 2009-09-07 | [6 empty] | 2012-03-12
H0060 | 143 | 2015-05-07 | Icon, EEA Holdings & 2OC consortium | Beckton Gas Pressure Reduction Station | Biomass (dedicated) |  |  | 19 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beckton Sewage Treatment Works | Greater London | London | England |  | 545005 | 181988 | Newham London Borough Council | 10/00092/LTGDC | [5 empty] | 2010-01-15 | [6 empty] | 2010-08-26 |  |  |  |  | 2013-04-30 | 2015-03-30
IF1122 | 144 | 2016-03-30 | Climate Corporate Advisory Services LLP | Bolingbroke Road | Biomass (dedicated) |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | GBM Waste Management Ltd, Bolingbroke Road, Louth, Lincolnshire | Lincolnshire | East Midlands | England | LN11 0WA | 532992 | 389263 | Lincolnshire County Council | (E)N105\0336 \09 | [5 empty] | 2008-12-22 | [6 empty] | 2010-01-26 |  |  |  | 2013-01-26
N00028B | 145 | 2014-05-20 | DeMulder and Sons Ltd | Nuneaton Animal Waste Incinerator | Biomass (dedicated) |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Mancetter Road/Grange Road , Hartshill , Nuneaton , Warwickshire | Warwickshire | West Midlands | England | CV10 0TA | 433245 | 295175 | North Warwickshire Borough Council | MIN/2002/0028 | [5 empty] | 2002-10-24 | [6 empty] | 2003-06-03
N00033B | 146 | 2019-12-04 | Under tender | Bracknell Forest Biomass Centre | Biomass (dedicated) |  |  | 1.1 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | In the centre of the '3M roundabout', which is at the junction of A329 (Millennium Way), B3018 (Binfield Road), Bond Way and B3048 (Wokingham Road). | Berkshire | South East | England |  | 486663 | 169545 | Bracknell Forest Borough Council | 04/01129/OUT | [5 empty] | 2004-11-25 | [6 empty] | 2006-12-21
N00062B | 147 | 2013-12-03 | Biogen Power | Elswick | Biomass (dedicated) |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Gorst Farm, Lodge Lane, Elswick, Preston | Lancashire | North West | England |  | 342587 | 438278 | Fylde Borough Council | 05/0795 | [5 empty] | 2005-08-18 | [6 empty] | 2005-12-14
A0493 | 148 | 2018-06-04 | Cogen | Ince Bio Power | Advanced Conversion Technologies |  |  | 21.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Plot 9, Ince Marshes Ince Reso, Marsh Lane, Ince, Chester, Cheshire | Cheshire | North West | England | CH2 4N | 345500 | 376500 | Cheshire West and Chester Council | 11/00040/WAS | [5 empty] | 2011-01-07 | [6 empty] | 2011-09-09 |  |  |  |  | 2015-10-29 | 2017-04-30
AA094 | 149 | 2019-06-20 | Peel Energy | Barton Renewable Energy Plant | Biomass (dedicated) |  |  | 20 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | south side of the Manchester Ship Canal | Greater Manchester | North West | England |  | 375558 | 396941 | Trafford Council | 76153/FULL/2010 | [5 empty] | 2010-12-07 |  | 2011-11-11 |  |  |  | 2013-05-16 | 2013-05-16
AA440 | 150 | 2017-11-02 | Eco2 | Brigg Renewable Energy Plant (Re-submission) | Biomass (dedicated) |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | British Sugar Corporation Ltd, Access roads to power station, Scawby | Humberside | Yorkshire and Humber | England | DN20 9LT | 498860 | 406109 | North Lincolnshire Council | PA/2009/0334 | APP/Y2003/A/10/2133721/NWF |  |  |  |  | 2009-03-23 |  | 2010-04-07 |  |  |  | 2011-10-18 | 2011-10-18 |  |  |  |  | 2014-06-19 | 2016-02-23
C2592 | 151 | 2019-04-16 | Preva Power | Chalk Lane Business Park | Advanced Conversion Technologies |  |  | 4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Unit 1, Chalk Lane Business Park, Chalk Lane | Norfolk | Eastern | England |  | 600511 | 290670 | Breckland Council | 3PL/2014/0024/F | [5 empty] | 2014-01-09 | [6 empty] | 2014-03-07
EN00550 | 152 | 2018-11-27 | Tilbury Green Power | Tilbury Green Power | Biomass (dedicated) |  |  | 43 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Tilbury Docks, Essex | Essex | Eastern | England | RM18 7NU | 563330 | 176110 | DECC (S36) | [6 empty] | 2008-02-07 | [6 empty] | 2009-08-27 |  |  |  |  | 2015-04-15 | 2017-10-26
EN00583 | 153 | 2019-11-20 | Macquarie/ PKA/ MGT Power | Tees Renewable Energy Plant | Biomass (dedicated) |  |  | 299 | Yes |  |  | 299 | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Teesport, Teeside, Middlesbrough | Cleveland | North East | England | TS6 | 454280 | 523320 | DECC (S36) | [6 empty] | 2008-07-23 | [6 empty] | 2010-03-09 |  |  |  |  | 2016-08-01
N00054B | 154 | 2014-07-07 | Express Power | Express Power, Innovia Films Site | Biomass (dedicated) |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Bath Road , Bridgwater | Somerset | South West | England |  | 328310 | 135870 | Sedgemoor District Council | 08/05/00105 | [5 empty] | 2005-04-08 | 2005-09-14
N00061B | 155 | 2018-04-04 | RWE | Markinch Biomass CHP Plant | Biomass (dedicated) |  |  | 65 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Markinch, Fife | Fife | Scotland | Scotland |  | 327988 | 701561 | Scottish Government (S36) | [6 empty] | 2005-08-01 | [6 empty] | 2008-07-01 |  |  |  |  | 2009-06-01 | 2014-02-18
A0384 | 156 | 2016-02-10 | Private Developer | Briar Hill Farm | Biomass (dedicated) |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Low Levels Bank, Hatfield, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | DN7 6HA | 470309 | 408866 | Doncaster Metropolitan Borough Council | 09/00386/FULM | [5 empty] | 2009-02-17 | [6 empty] | 2010-06-22
AA109 | 157 | 2016-01-11 | Scottish Power Renewables | Longannet | Biomass (dedicated) |  |  | 25 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | West Fife | Fife | Scotland | Scotland |  | 293993 | 686259 | Fife Council | 07/01283/WEIA | [5 empty] | 2007-04-16 | [6 empty] | 2008-08-22
AA169 | 158 | 2016-02-10 | W4B (UK) | Bristol Liquid Biomass | Biomass (dedicated) |  |  | 50 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Former Columbian Chemicals (Sevalco), Severn Road, Avonmouth, Bristol | Avon | South West | England | BS11 0YU | 353367 | 181676 | Bristol City Council | 09/03235/F | 10/20036/REF |  |  |  |  | 2009-08-17 |  | 2010-02-24 |  |  |  | 2011-02-10 | 2011-02-10
AA445 | 159 | 2019-12-06 | DMG Ecological Ltd | Llynfi Biomass Power Station | Biomass (dedicated) |  |  | 25 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 4km south of Maesteg and 6km north of Bridgend | Mid Glamorgan | Wales | Wales |  | 288375 | 186946 | Bridgend County Borough Council | P/11/21/FUL | [5 empty] | 2011-01-14 | [6 empty] | 2015-05-08 |  |  |  | 2020-05-08
AA563 | 160 | 2019-11-26 | Real Ventures | Reality Energy Centre, Immingham | Biomass (dedicated) |  |  | 49.9 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Immingham Docks, Immingham, Lincolnshire | Humberside | Yorkshire and Humber | England |  | 520097 | 415561 | North East Lincolnshire Council | DC/999/11/IMM | [5 empty] | 2012-01-12 | [6 empty] | 2012-04-12 |  |  |  | 2015-04-12
AA687 | 161 | 2019-11-05 | Greencoat Capital | Templeborough Biomass Power Plant- Rotherham | Biomass (dedicated) |  |  | 42 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Former Firth Rixson Ickles Works, Sheffield Road Templeborough, Rotherham, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | S60 1DP | 441740 | 391937 | Rotherham Metropolitan Borough Council | RB2010/0668 | [5 empty] | 2010-06-07 | [6 empty] | 2010-11-09 |  |  |  |  | 2015-11-26 | 2019-02-28
AA850 | 162 | 2020-04-21 | Real Ventures | Reality Energy Centre (Hull) | Biomass (dedicated) |  |  | 49.9 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Saltend, Land To The East Of King George Dock And South Of Hedon Road With Access From South Of Somerden Road Roundabout Kingston Upon Hull | Humberside | Yorkshire and Humber | England | HU12 8ED | 515477 | 428432 | Kingston upon Hull City Council | 12/00715/FULL | [5 empty] | 2012-07-27 | [6 empty] | 2012-11-16
B1308 | 163 | 2015-06-17 | Port Clarence Energy (Eco2) | Teeside Renewable Energy Plant | Biomass (dedicated) |  |  | 49 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land At Clarence Works, Off Port Clarence Road, Port Clarence, Middlesborough | County Durham | North East | England |  | 450957 | 521558 | Stockton on Tees Borough Council | 14/1106/EIS | [5 empty] | 2014-04-23 | [6 empty] | 2014-07-23
B0005 | 164 | 2019-12-05 | Bester Generacion | Pulse Park, Wellingborough | Biomass (dedicated) |  |  | 5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Pulse Park Business Park, Wellingborough, Northamptonshire | Northamptonshire | East Midlands | England |  | 489000 | 271500 | Wellingborough Borough Council | WP/2008/0060 | [5 empty] | 2008-01-17 | [6 empty] | 2015-03-20 |  |  |  | 2020-03-20 | 2014-11-24
B0086 | 165 | 2019-11-04 | REACT Energy (Kedco) | Enfield Biomass CHP Project | Advanced Conversion Technologies |  |  | 12 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Yard, Gibbs Road, Edmonton | Greater London | London | England | N18 3PU | 535169 | 192804 | Enfield London Borough Council | TP/09/1862 | [5 empty] | 2010-03-10 | [6 empty] | 2013-04-08
EN00529 | 166 | 2017-11-02 | E.ON UK | Blackburn Meadows Biomass Plant | Biomass (dedicated) |  |  | 30 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Blackburn Meadows in Sheffield, South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 440075 | 391650 | Sheffield City Council | 08/01225/OUT | [5 empty] | 2008-03-01 | [6 empty] | 2008-07-15 |  |  |  |  | 2011-11-01 | 2014-07-07
EN00580 | 167 | 2015-12-08 | Tesco | Tesco Distribution Centre, Goole | Biomass (dedicated) |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Tesco Distribution Centre, Capitol Park, Rawcliffee Road, Goole, South Yorkshire | Humberside | Yorkshire and Humber | England | DN14 6XL | 472715 | 423710 | East Riding of Yorkshire Council | 11/02623/STPLFE | [5 empty] | 2007-08-22 | [6 empty] | 2008-07-17
B1428 | 169 | 2018-11-14 | Warwick International Ltd | Warwick International Biomass CHP | Biomass (dedicated) |  |  | 8.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Coast Rd, Holywell, Mostyn | Clwyd | Wales | Wales | CH8 9HE | 316158 | 380495 | Flintshire County Council | 051924 | [5 empty] | 2014-04-01 | [6 empty] | 2014-07-28
AA041 | 170 | 2015-01-28 | Dow Corning | Barry Docks (Resubmission) | Biomass (dedicated) |  |  | 9 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land off Woodham Road, Barry | South Glamorgan | Wales | Wales |  | 312625 | 167514 | Vale of Glamorgan Council | 2010/00240/FUL - 2008/01203/ful | APP/Z6950/A/09/2114605 |  |  |  |  | 2008-09-08 |  | 2009-07-31 | 2010-01-08 |  |  | 2010-07-02 | 2010-07-02
AA535 | 171 | 2019-07-23 | Charlesfield First LLP & Biogas Power | Charlesfield Biomass CHP Plant | Advanced Conversion Technologies |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land East Of G A White Motors, Charlesfield Industrial Estate, St Boswells | Borders | Scotland | Scotland |  | 358892 | 629839 | Scottish Borders Council | 09/01020/OUT | [5 empty] | 2009-08-04 | [6 empty] | 2009-11-26 |  |  |  |  | 2015-05-01 | 2015-06-30
A0127 | 172 | 2014-12-02 | Diageo | Diageo Biomass Energy Project | Biomass (dedicated) |  |  | 5.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cameronbridge Distillery, Cameron Bridge, Leven, Fife | Fife | Scotland | Scotland | KY8 5RL | 334567 | 700177 | Fife Council | 08/00744/CEIA | [5 empty] | 2008-04-11 | [6 empty] | 2008-11-04 |  |  |  |  | 2009-08-01 | 2013-05-08
H0065 | 173 | 2019-09-25 | Burmeister & Wain Scandinavian Contractor (BWSC) | Discovery Park | Biomass (dedicated) |  |  | 16 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ramsgate Road, Sandwich, Kent | Kent | South East | England | CT13 9ND | 633403 | 159180 | Dover District Council | 13/00701 | [5 empty] | 2013-08-23 | [6 empty] | 2013-10-18 |  |  |  |  | 2016-06-23 | 2018-09-28
EN00567 | 174 | 2018-06-04 | Drax Power | Drax Biomass Power Station - Unit 1 | Biomass (co-firing) |  |  | 645 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Near Selby in North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 466650 | 427050 | DECC (S36) | [18 empty] | 2013-04-01 | 2013-07-30
EN00567b | 175 | 2018-06-04 | Drax Power | Drax Biomass Power Station - Unit 3 | Biomass (dedicated) |  |  | 645 | No |  |  | 645 | n/a | n/a | n/a | n/a | Operational | Operational | Near Selby in North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 466650 | 427050 | DECC (S36) | [18 empty] | 2017-04-01 | 2017-07-20
A0203 | 176 | 2014-09-03 | Forth Ports | Port of Dundee | Biomass (dedicated) |  |  | 120 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Port of Dundee | Tayside | Scotland | Scotland | DD1 | 340600 | 730752 | Scottish Government (S36) | [6 empty] | 2010-08-17 | 2014-04-01
AA069 | 177 | 2016-06-10 | East Yorkshire Power | Gameslack Farm | Biomass (dedicated) |  |  | 17.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Beverley Road, Fimber Nr Wetwang, Driffield, Humberside | Humberside | Yorkshire and Humber | England | YO25 9LT | 491171 | 459820 | East Riding of Yorkshire Council | 10/01123/STOUTE | [5 empty] | 2010-03-19 | [6 empty] | 2011-04-08
IF1040 | 179 | 2018-07-18 | Sunrise Renewables | King George Dock | Biomass (dedicated) |  |  | 9 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kingston Upon Hull | Humberside | Yorkshire and Humber | England | HU9 5PR | 513307 | 428707 | Kingston upon Hull City Council | 12/00949/FULL | [5 empty] | 2012-10-22 | [6 empty] | 2013-02-05 |  |  |  |  | 2016-04-15 | 2018-04-15
AA243 | 180 | 2014-09-01 | Eco2 | Mendlesham Renewable Energy Plant | Biomass (dedicated) |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | immediately north-west of Mendlesham Airfield Industrial Estate, near the village of Mendlesham, Suffolk | Suffolk | Eastern | England |  | 612132 | 264013 | Mid Suffolk District Council | 0759/12 | APP/W3520/A/14/2211941 |  |  |  |  | 2012-03-09 |  | 2013-07-18 |  | 2014-07-21
B0015 | 181 | 2016-06-24 | Welsh Power/ Pwer Cymru (Carron Energy) | Nevis Power Station | Biomass (dedicated) |  |  | 49.9 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | South Dock, Newport, Gwent | Gwent | Wales | Wales | NP20 | 331387 | 184150 | Newport City Council | 08/1257 | [5 empty] | 2008-09-30 | [6 empty] | 2009-01-07
C3218 | 182 | 2016-03-23 | Northampton General Hospital | Northampton General Hospital | Biomass (dedicated) |  |  | 1.9 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Northampton General Hospital Trust, Cliftonville, Northampton, Northamptonshire | Northamptonshire | East Midlands | England | NN1 5BD | 476449 | 260399 | Northampton Borough Council | N/2014/0546 | [5 empty] | 2014-05-12 | [6 empty] | 2014-06-30 |  |  |  | 2017-06-30 | 2015-03-01 | 2016-03-01
NEW2000 | 183 | 2020-06-04 | Peterborough Renewable Energy | Peterborough Energy Park (Green Energy Parks - Gasification) | Advanced Conversion Technologies |  |  | 81 | No | 2 |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Peterborough Renewable Energy Ltd, Land off Storey's Bar Road Peterborough | Cambridgeshire | Eastern | England | PE1 5YS | 521611 | 299282 | DECC (S36) | [6 empty] | 2009-01-30 | [6 empty] | 2009-11-04
AA032 | 184 | 2020-01-24 | W4B | Portland Dock Green Energy Plant | Advanced Conversion Technologies |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Portland Port, Castletown, Portland, Dorset | Dorset | South West | England | DT5 1PP | 369701 | 74257 | Weymouth and Portland Borough Council | 09/00648/LBC (09/00646/FULES) | [5 empty] | 2009-10-23 | [6 empty] | 2010-01-24
AA396 | 185 | 2017-11-02 | Burmeister & Wain Scandinavian Contractor A/S (BWSC) | Snetterton Biomass Plant | Biomass (dedicated) |  |  | 44.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Snetterton Heath, near the A11 in Snetterton | Norfolk | Eastern | England | NR16 2JU | 600731 | 290906 | Breckland Council | 3PL/2012/0029/F | [5 empty] | 2012-01-19 | [6 empty] | 2012-07-18 |  |  |  | 2015-07-18 | 2015-01-20 | 2016-12-13
AA931 | 186 | 2016-10-31 | Speyside Renewable Energy Partnership | Speyside Biomass CHP Plant | Biomass (dedicated) |  |  | 12.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Craigellachie Wood, Craigellachie, Aberlour, Grampian | Grampian | Scotland | Scotland |  | 327641 | 845585 | Moray Council | 12/01490/APP | [5 empty] | 2012-08-27 | [6 empty] | 2013-03-08 |  |  |  |  | 2014-11-26 | 2016-06-24
AA947 | 187 | 2015-07-21 | Estover Energy | Stoneywood Paper Mill | Biomass (dedicated) |  |  | 22 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land at Stoneywood Paper Mill, Bucksburn, Aberdeen, Grampian | Grampian | Scotland | Scotland | AB21 9AB | 389708 | 811181 | Aberdeen City Council | 121281 | [5 empty] | 2012-09-12 | [6 empty] | 2013-07-10
B0717 | 188 | 2020-01-14 | Renewable Developments Wales | Trecwn Biomass Plant | Biomass (dedicated) |  |  | 25 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | former Royal Naval Armament Depot in Trecwn | Dyfed | Wales | Wales |  | 197995 | 232045 | Pembrokeshire County Council | 14/0300/PA | [5 empty] | 2014-07-01 | [6 empty] | 2015-04-14 |  |  |  | 2020-04-14
A0339 | 189 | 2014-08-11 | Biogen Power | Twinwoods CHP | Biomass (dedicated) |  |  | 11 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Twinwoods Business Park, Thurleigh Road, Milton Ernest, Bedford, Bedfordshire | Bedfordshire | Eastern | England | MK41 6AE | 503240 | 256004 | Bedford Borough Council | 09/01258/FULWME | 10/00040/REF |  |  |  |  | 2009-06-10 |  | 2010-05-27 |  |  | 2012-02-09
IF1113 | 190 | 2017-08-31 | Burmeister & Wain Scandinavian (BWSC)/ Bioenergy Infrastructure Group | Widnes 3MG Biomass/Mersey Bioenergy (CHP) Plant | Biomass (dedicated) |  |  | 20 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Stobart Park/3MG Multi Modal Gateway (formerly known as West Bank Industrial Estate) approximately 1 kilometre (0.6 miles) west of Widnes Town Centre | Merseyside | North West | England | BT79 9HH | 350091 | 384450 | Halton Borough Council | 12/00458/FULEIA | [5 empty] | 2012-10-22 | [6 empty] | 2013-04-04 |  |  |  |  | 2015-02-01 | 2017-02-06
A0218 | 191 | 2019-12-04 | Orthios Group | Anglesey Biomass Power Station | Biomass (dedicated) |  |  | 299 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Anglesey Aluminium Metal Renewables Ltd, Penrhos Works, Near Holyhead, Anglesey | Gwynedd | Wales | Wales |  | 225594 | 381320 | DECC (S36) | S36 | [5 empty] | 2009-10-20 | [6 empty] | 2011-09-16
EN00567a | 192 | 2018-06-04 | Drax Power | Drax Biomass Power Station - Unit 2 | Biomass (dedicated) |  |  | 645 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Near Selby in North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 466650 | 427050 | DECC (S36) | [19 empty] | 2014-05-30
AA099 | 193 | 2014-09-24 | New Park Management | Georgmas CHP | Biomass (dedicated) |  |  | 4.7 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Georgmass Junction, Georgemas, Halkirk | Highland | Scotland | Scotland |  | 315251 | 960032 | Highland Council | 10/02997/FUL | [5 empty] | 2010-07-07 | [6 empty] | 2010-09-03 |  |  |  | 2013-09-03
C3303 | 194 | 2017-01-24 | Greenham Common Community Trust / Torftech Energy | New Greenham Park (gasification) | Advanced Conversion Technologies |  |  | 6.3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | S/O Buckner-Croke Way, Greenham Business Park, Greenham, Thatcham, Berkshire | Berkshire | South East | England | RG19 6HW | 449587 | 164281 | West Berkshire Council | 14/01735/COMIND | [5 empty] | 2014-07-24 | [6 empty] | 2015-08-12 |  |  |  | 2018-08-12
C3366 | 195 | 2019-11-21 | PdP Solutions Limited | Plot Q Kiln Lane | Advanced Conversion Technologies |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Plot Q Kiln Lane Industrial Estate, Europa Way, Stallingborough, North East Lincolnshire | Humberside | Yorkshire and Humber | England |  | 521100 | 414050 | North East Lincolnshire Council | DM/0848/14/FUL | [5 empty] | 2014-08-22 | [6 empty] | 2016-04-01 |  |  |  | 2021-04-01
N0040B | 196 | 2014-09-25 | E.ON (formerly Powergen). Agent Environmental Planning and Management | Stevens Croft | Biomass (dedicated) |  |  | 50.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 4km North of Lockerbie adjacent to the A74m | Dumfries and Galloway | Scotland | Scotland |  | 312100 | 585100 | Dumfries and Galloway Council | 05P40012 | [5 empty] | 2003-07-07 | [6 empty] | 2005-04-01 |  |  |  |  | 2006-06-01 | 2007-12-15
EN00577 | 197 | 2015-01-06 | Rose Energy | Rose Energy (Glenavy) Incinerator | Biomass (dedicated) |  |  | 30 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Glenavy, near Lisburn | Co. Antrim | Northern Ireland | Northern Ireland |  | 125000 | 525000 | Northern Ireland Planning Service | S/2008/0630/F | [5 empty] | 2008-06-06 |  | 2012-12-21
IF1228 | 198 | 2017-02-01 | Kelda Water Services | Riccall Mine | Biomass (dedicated) |  |  | 20 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Selby Road, Riccall, York, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO4 6QR | 390823 | 421809 | Selby District Council | [6 empty] | 2013-01-14 | 2017-01-11
A0099 | 199 | 2015-03-30 | Helius Energy | Bristol Port / Avonmouth | Biomass (dedicated) |  |  | 100 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Bristol Dock, Avonmouth | Avon | South West | England | BS11 9 | 352459 | 177491 | DECC (S36) | 09/005/06 | [5 empty] | 2009-04-15 | [6 empty] | 2010-03-26 |  |  |  | 2015-03-26
A0142 | 200 | 2019-09-16 | EQTEC (Gaia Power) | Billingham Biomass Power Station | Biomass (dedicated) |  |  | 49.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Haverton Hill Road, Billingham, Teeside, Cleveland | County Durham | North East | England | TS23 1PX | 447834 | 521669 | Stockton on Tees Borough Council | 09/1562/EIS | [5 empty] | 2009-06-24 | [6 empty] | 2009-10-14
AA217 | 201 | 2016-04-06 | GB-BIO | Tansterne Straw-Burning Power Station - Resubmission | Biomass (dedicated) |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | near Aldbrough, East Riding of Yorkshire | Humberside | Yorkshire and Humber | England |  | 522778 | 438754 | East Riding of Yorkshire Council | 10/04639/STREM | [5 empty] | 2010-11-03 | [6 empty] | 2011-02-14
AA762 | 202 | 2016-06-13 | RWE Innogy | Stallingborough Biomass Power Plant (Resubmission) | Biomass (dedicated) |  |  | 65 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Stallingborough, near the port facilities of Immingham | Lincolnshire | East Midlands | England | DN41 8 | 519000 | 411520 | DECC (S36) | [6 empty] | 2010-02-23 | [6 empty] | 2012-05-16 |  |  |  | 2015-05-16
B0545 | 203 | 2016-02-10 | Energy Park Sutton Bridge Ltd | Sutton Bridge Renewable Energy Park | Biomass (dedicated) |  |  | 48 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Wingland Enterprise Park, Centenary Way, Sutton Bridge, Spalding, Lincs | Lincolnshire | East Midlands | England | PE12 9TF | 548880 | 320385 | South Holland District Council | H18-0723-12 |  |  |  | 41795 |  | 2012-09-07 |  | 2015-04-28
EN00466 | 205 | 2011-09-02 |  | Macphie of Glenbervie | Biomass (dedicated) |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Macphie Of Glenbervie Ltd, Glenbervie, Stonehaven | Grampian | Scotland | Scotland | AB39 3YG | 376500 | 780500 | Aberdeenshire Council | APP/2007/2897 | [5 empty] | 2007-07-13 | [6 empty] | 2007-09-27 | [5 empty] | 2008-09-01
EN00486 | 206 | 2017-08-31 | Glenmont Partners | Sleaford Renewable Energy Plant | Biomass (dedicated) |  |  | 40 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Boston Road, North Kesteven, Sleaford | Lincolnshire | East Midlands | England |  | 508635 | 345855 | North Kesteven District Council | 08/0844 | [5 empty] | 2008-08-20 | [6 empty] | 2008-11-04 |  |  |  |  | 2012-05-10 | 2014-11-28
11022A4 | 209 | 2012-01-04 | Holsworthy Biogas Company ( North Tamar Business Network) | North Tamar Environ Project - Holsworthy (Farm AD) | Anaerobic Digestion |  |  | 1.43 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land north-east of Higher Manworth Holsworthy , Devon | Devon | South West | England |  | 234450 | 105800 | Torridge District Council | [6 empty] | 1998-12-21 | [6 empty] | 1999-05-14 | [5 empty] | 2002-07-18
A0137 | 210 | 2012-01-04 | Scottish Water Solutions | Deerdykes Composting and Organics Recycling Facility (Waste AD) | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dunswood Road, Cumbermould, Glasgow, Strathclyde | Strathclyde | Scotland | Scotland | G67 3EN | 277924 | 676998 | North Lanarkshire Council | [18 empty] | 2009-08-01 | 2010-09-28
A0210 | 211 | 2012-01-04 | Shanks Group | Cumbernauld BioPlant (Waste AD) | Anaerobic Digestion |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Shanks Landfill Site Meikle Drumgray Road Greengairs Airdrie Lanarkshire | Strathclyde | Scotland | Scotland |  | 277924 | 676998 | North Lanarkshire Council | 04/00316/AMD | [5 empty] | 2004-03-05 | [6 empty] | 2004-12-20 |  |  |  |  | 2010-09-01 | 2011-10-05
A0428 | 212 | 2014-12-02 | Farmgen | Carr Farm (Farm AD) | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Carr Farm Cottage, Lodge Lane, Warton, Lytham St Annes, Lancs | Lancashire | North West | England | FY8 5RP | 338850 | 428420 | Fylde Borough Council | 08/0974 | [5 empty] | 2008-01-28 |  | 2009-05-06 | [9 empty] | 2009-06-01 | 2010-01-01
A0498 | 213 | 2012-01-04 | Severn Trent Water | Stoke Bardolph energy crop (Farm AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Stoke Bardolf, Nottinghamshire | Nottinghamshire | East Midlands | England |  | 464588 | 342496 | Gedling Borough Council | 2008/0928 | [5 empty] | 2009-02-18 | [6 empty] | 2009-03-11 | [5 empty] | 2010-07-10
AA045 | 214 | 2013-10-08 | BV Dairy | BV Dairy (Farm AD) | Anaerobic Digestion |  |  | 1.539 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wincombe Lane, Shaftesbury, Dorset | Dorset | South West | England |  | 387275 | 123550 | North Dorset District Council | [6 empty] | 2009-05-27 | [6 empty] | 2009-07-28 | [5 empty] | 2011-01-05
AA173 | 216 | 2012-02-27 | Future Biogas | Stonepit Hill (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Plum Lane, Gresham | Norfolk | Eastern | England |  | 614994 | 337994 | North Norfolk District Council | PF/10/1185 | [6 empty] | 2012-02-27
AA176 | 217 | 2013-02-13 | Viridor | South Manchester Resource Recovery Centre (AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Longley Lane, Sharston | Greater Manchester | North West | England |  | 383732 | 388642 | Manchester City Council | 083953/FO/2007/S2 | [5 empty] | 2007-07-23 | [6 empty] | 2007-12-20 |  |  |  |  | 2010-11-01 | 2012-01-01
AA178 | 218 | 2013-01-23 | Viridor | Reliance Street Mechanical Biological Treatment Facility (MBT) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Reliance Street, Newton Heath, Manchester | Greater Manchester | North West | England | M40 3EZ | 388115 | 400842 | Manchester City Council | 084335/FO/2007/N1 | [5 empty] | 2007-08-30 | [6 empty] | 2008-10-09 |  |  |  |  | 2010-11-01 | 2011-04-07
AA354 | 219 | 2013-01-02 | Future Biogas | Westwell Leacon Renewable Energy Facility (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | 1km west of Westwell Leacon & 1.5km south of Charing, Kent | Kent | South East | England |  | 594993 | 147457 | Ashford Borough Council | 10/01491/AS | APP/E2205/A/12/2174758 |  |  |  |  | 2010-10-28 |  | 2011-10-26 |  |  | 2012-10-10
AA437 | 220 | 2013-01-21 | Local Generation | Fenmarc Fenland AD Plant (Waste AD) | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wisbech Road, March, Cambridgeshire | Cambridgeshire | Eastern | England | PE15 0BA | 539857 | 298688 | Cambridgeshire County Council | F/02007/09/CW | [5 empty] | 2009-05-27 | [6 empty] | 2009-06-22 |  |  |  |  | 2011-12-01 | 2012-11-01
AA441 | 221 | 2012-03-21 | Bowmans Waste | Bowmans Business Park (Waste AD) | Anaerobic Digestion |  |  | 4.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Mill Road, Addlethorpe | Lincolnshire | East Midlands | England |  | 554858 | 367352 | East Lindsey District Council | S/002/01344/11 | [5 empty] | 2011-07-21 |  | 2012-01-16
AA462 | 222 | 2013-01-23 | Staples Brothers | Marsh Farm (Farm AD) | Anaerobic Digestion |  |  | 1.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sea Lane, Wrangle, Boston, Lincolnshire | Lincolnshire | East Midlands | England | PE22 9HE | 544727 | 350655 | Boston Borough Council | B/09/0209 | [5 empty] | 2009-05-21 | [6 empty] | 2009-08-03 | [5 empty] | 2011-02-24
AA530 | 223 | 2012-04-19 | Global Renewables Lancashire | Thornton Waste Recovery Park (Waste AD) | Anaerobic Digestion |  |  | 1.9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fleetwood Road North, Thornton | Lancashire | North West | England |  | 333392 | 444767 | Lancashire County Council | 02/08/1133 | [5 empty] | 2009-10-29 | [6 empty] | 2010-01-28 | [5 empty] | 2010-05-01
AA531 | 224 | 2012-04-19 | Global Renewables Lancashire | Farington Waste Recovery Park (Waste AD) | Anaerobic Digestion |  |  | 1.9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational |  | Lancashire | North West | England |  | 351423 | 423205 | Lancashire County Council | 07/06/0821 | [5 empty] | 2006-07-17 | [6 empty] | 2006-11-22 | [5 empty] | 2010-09-01
AA591 | 225 | 2011-12-14 | Northwest Biogas | North West Biogas Anaerobic Digestion Plant (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | West Road, Hillhouse International Business Park, Thornton Cleveleys, Lancashire | Lancashire | North West | England | FY5 4QD | 334315 | 443459 | Wyre Borough Council | 09/00787/LCC | [5 empty] | 2009-09-30 | [6 empty] | 2009-10-29
AA684 | 226 | 2012-03-12 | Fernbrook Bio Limited | Fernbrook AD Plant (Waste AD) | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rothwell Lodge Farm, Rothwell, Kettering | Northamptonshire | East Midlands | England | NN16 8XF | 484016 | 280041 | Northamptonshire County Council | 09/00033/WAS | [5 empty] | 2009-05-08 | [6 empty] | 2009-10-22 | [5 empty] | 2010-09-01
AA768 | 227 | 2012-05-23 | Barfoots of Botley | Sefter Farm AD Plant (Farm AD) | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sefter Farm Pagham Road Pagham | West Sussex | South East | England |  | 489102 | 99582 | Arun District Council | P/92/08/ | [5 empty] | 2008-07-10 | [6 empty] | 2008-10-02 | [5 empty] | 2010-06-01
AA773 | 228 | 2012-05-24 | Private Developer | Brookfield Farm AD Plant (Farm AD) | Anaerobic Digestion |  |  | 1.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lower Reule, Church Eaton, Stafford | Staffordshire | West Midlands | England |  | 384502 | 319762 | Staffordshire County Council | S.09/05/4004 W | [5 empty] | 2009-02-09 | [6 empty] | 2009-05-01 | [5 empty] | 2010-05-01
B0272 | 229 | 2018-10-03 | Severn Trent (formerly Agrivert) | Cassington AD (Waste AD) | Anaerobic Digestion |  |  | 2.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Worton Farm, Worton, Witney, Oxon | Oxfordshire | South East | England | OX29 4FL | 446279 | 211425 | Cherwell District Council | 08/01781/CM | [5 empty] | 2008-07-30 | [6 empty] | 2008-08-29 | [5 empty] | 2010-09-01
B0465 | 230 | 2012-09-11 | Blakiston Houston Estate Company | BH Energy - Biogas (AD) | Anaerobic Digestion |  |  | 2.126 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 99 Ballymiscaw Road, Dundonald, Belfast | Co. Down | Northern Ireland | Northern Ireland | BT16 1TX | 155489 | 531504 | Northern Ireland Planning Service | [19 empty] | 2012-04-04
B0469 | 231 | 2018-10-03 | Bio Capital Limited | Energen biogas cumbernauld | Anaerobic Digestion |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dunnswood Road, Wardpark South Industrial Estate, Cumbernauld, Glasgow | Strathclyde | Scotland | Scotland | G67 3EN | 277889 | 676918 | North Lanarkshire Council | 08/01376/FUL | [5 empty] | 2008-09-17 | [6 empty] | 2008-11-05 | [5 empty] | 2011-06-22
B0569 | 232 | 2012-12-05 | GENeco | Bristol STW (Waste AD) | Anaerobic Digestion |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kings Weston Lane, Avonmouth, Bristol | Avon | South West | England | BS11 0YS | 353600 | 179530 | Bristol City Council | 10/02511/F | [5 empty] | 2010-06-11 | [6 empty] | 2010-12-14 | [5 empty] | 2012-12-04
B0738 | 233 | 2015-12-21 | PROjEN | A C Shropshire (Farm AD) | Anaerobic Digestion |  |  | 2.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Green Lodge Farm, Forest Road, Huncote, Leicester | Leicestershire | East Midlands | England | LE9 3LE | 451758 | 298963 | Blaby District Council | 09/0564/1/CX | [5 empty] | 2009-09-18 | [6 empty] | 2010-01-11 | [5 empty] | 2013-05-14
C1355 | 234 | 2013-09-20 | M S Power Projects Limited | Mapledurham farm AD (Farm waste) | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Pond Lane (North of Park Wood) Mapledurham | Oxfordshire | South East | England | RG4 7TY | 467916 | 176874 | South Oxfordshire District Council | P13/S1290/FUL | [5 empty] | 2013-05-13 | 2013-07-19
EN00085 | 235 | 2012-01-04 | Biogas Nord | Lowbrook Farm Anaerobic Digester (Farm AD) | Anaerobic Digestion |  |  | 1.336 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lowbrook Farm, Belchalwell, Okeford Fitzpaine, Blandford Forum, Dorset | Dorset | South West | England |  | 378836 | 109350 | North Dorset District Council | 2/2006/0363 | [5 empty] | 2006-04-12 | [6 empty] | 2006-06-06 | [5 empty] | 2006-06-26
H0078 | 236 | 2013-08-16 | Private Developer | Harp Road (Farm AD) | Anaerobic Digestion |  |  | 1.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land at (2), Harp Road, Brent Knoll, Highbridge | Somerset | South West | England | TA9 4HQ | 334777 | 149380 | Sedgemoor District Council | 07/13/00015 | [5 empty] | 2013-06-04 |  | 2013-06-24
IF1101 | 237 | 2012-12-04 | Geo E Gittus and Son | Symonds Farm Power Ltd (Farm AD) | Anaerobic Digestion |  |  | 1.415 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Orchard Piggeries Symonds Farm Newmarket Road Risby Suffolk | Suffolk | Eastern | England |  | 580088 | 265389 | St Edmundsbury Borough Council | SE/09/0806 | [5 empty] | 2009-07-09 | [6 empty] | 2009-09-07 | [5 empty] | 2012-03-01
IF1282 | 238 | 2013-02-13 | Hallwick Energy | Buttermilk Farm | Anaerobic Digestion |  |  | 1.067 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Baldock Road, Buntingford | Hertfordshire | Eastern | England | SG9 9RH | 534209 | 229393 | East Hertfordshire District Council | 3/10/1598/FP | [5 empty] | 2010-09-03 | [6 empty] | 2011-01-12 |  |  |  |  | 2011-03-30 | 2012-05-01
IF1285 | 239 | 2013-02-13 | Private Developer | Spring Farm (biomass) | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fir Covert Road,Taverham | Norfolk | Eastern | England |  | 615969 | 316308 | Broadland District Council | 20090884 | [5 empty] | 2009-07-16 | [6 empty] | 2009-12-15 | [5 empty] | 2011-08-01
IF1287 | 240 | 2013-10-08 | Hallwick Energy | Trinity Hall Farm | Anaerobic Digestion |  |  | 1.063 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Watling Street, Hockliffe, Leighton Buzzard | Bedfordshire | Eastern | England | LU7 9PY | 498750 | 225450 | Central Bedfordshire Council | CB/10/03200/FULL | [5 empty] | 2010-09-15 | [6 empty] | 2011-03-02 | [5 empty] | 2012-11-01
H0053 | 241 | 2013-10-17 | St Nicholas Court Farms Ltd | St Nicholas Court Farm (AD) | Anaerobic Digestion |  |  | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | St Nicholas At Wade, Birchington, Kent | Kent | South East | England |  | 625751 | 167136 | Thanet District Council | F/TH/13/0247 | [5 empty] | 2013-04-03 |  | 2013-08-13
AA349 | 242 | 2014-01-03 | Prosper Demulder / ReFood | Prosper Demulder Limited Anaerobic Digestion Plant (Waste AD) | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ings Road, Bentley, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | DN5 9SW | 457265 | 404820 | Doncaster Metropolitan Borough Council | 08/02575/FULM | [5 empty] | 2008-08-27 | [6 empty] | 2009-02-17 |  |  |  |  | 2011-04-01 | 2011-09-09
C2035 | 244 | 2013-12-10 | Private Developer | Marsh Farm (Farm AD) | Anaerobic Digestion |  |  | 1.4 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Marsh Farm Vange By-Pass Basildon Essex | Essex | Eastern | England | SS16 4QG | 571785 | 186629 | Basildon Borough Council | 13/00963/CC | [5 empty] | 2013-09-25 | 2013-11-13
AA400 | 245 | 2014-03-03 | GWE Biogas | Sandhill Anaerobic Digestion Plant (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land North East Of Battleburn Cottages Garton Road Kirkburn East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 498538 | 456147 | East Riding of Yorkshire Council | 09/00511/STPLF | [5 empty] | 2009-03-03 | [6 empty] | 2009-05-06 | [5 empty] | 2011-01-01
C1606 | 246 | 2014-03-06 | Welland Waste Management | Pebble Hall Farm - Food Waste AD | Anaerobic Digestion |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Pebble Hall Farm, Theddingworth Road, Marston Trussell, Northamptonshire | Northamptonshire | East Midlands | England | LE17 6NJ | 466125 | 284563 | Daventry District Council | DA/2013/0489 | [5 empty] | 2013-07-03 | 2013-10-01
AA299 | 247 | 2013-10-04 | Private Developer | Abbots moor Farm Anaerobic Digester (Farm AD) | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Haughton, West Felton, Shropshire | Shropshire | West Midlands | England |  | 337451 | 327233 | Shropshire Council | 11/00421/MAW | [5 empty] | 2011-02-02 | [6 empty] | 2011-09-26 | [5 empty] | 2012-11-30
C1605 | 248 | 2013-12-16 | Black Bridge Energy | Land at Oulton Street (Farm AD) | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Oulton Airfield, The Street, Oulton | Norfolk | Eastern | England |  | 614742 | 326962 | Broadland District Council | 20130860 | [5 empty] | 2013-07-01 |  | 2013-11-07
AA398 | 249 | 2012-01-04 | Biffa | Poplars Anaerobic Digestion Facility (Waste AD) | Anaerobic Digestion |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Poplars Landfill Site, Lichfield Road, Cannock | Staffordshire | West Midlands | England |  | 399422 | 309599 | East Staffordshire Borough Council | CH.09/03/721 MW | [5 empty] | 2009-07-13 | [6 empty] | 2010-01-15 |  |  |  |  | 2011-06-01 | 2011-07-31
IF1027 | 250 | 2013-05-21 | Clean Power Properties & Network Rail Infrastructure | Wheldon Road | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Castleford Wakefield | West Yorkshire | Yorkshire and Humber | England | WF10 2PP | 444005 | 426240 | Wakefield Council | 12/01966/FUL | [5 empty] | 2012-10-05 | 2013-01-16
AA281 | 251 | 2012-08-15 | Material Change | Reepham Road (Waste AD) | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Near Felthorpe, Norfolk | Norfolk | Eastern | England |  | 616498 | 316273 | Broadland District Council | 20101565 | [5 empty] | 2010-10-28 | [6 empty] | 2011-05-25 |  |  |  |  | 2011-07-31 | 2012-04-30
B0147 | 252 | 2013-01-28 | Waste Recycling Group | PwllfaWatkin AD Plant (Waste AD) | Anaerobic Digestion |  |  | 2.3 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Pwllfawatkin/Abernant Colliery, Pontardawe | West Glamorgan | Wales | Wales |  | 269721 | 208068 | Neath Port Talbot County Borough Council | P2011/1063 | [5 empty] | 2012-04-11 | 2012-09-10
IF1175 | 253 | 2018-03-02 | Biogen (formerly Tamar Energy) | Bonby Lane | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Bonby, North Lincolnshire | Humberside | Yorkshire and Humber | England | DN20 0PJ | 501545 | 416448 | North Lincolnshire Council | WD/2012/1438 | [5 empty] | 2013-01-02 | 2013-05-01
C1236 | 255 | 2016-09-22 | Kelda Organic Energy | Cardiff Waste Water Treatment Works (Waste AD) | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Cardiff Waste Water Treatment Works, Tide Fields Road, East Moors, Cardiff | South Glamorgan | Wales | Wales | CF14 2RX | 321166 | 175969 | Cardiff Council | 13/00686/DCO | [5 empty] | 2013-04-16 | [6 empty] | 2013-07-17
B1338 | 256 | 2015-11-27 | Severn Trent Water | Coleshill STW (Waste AD) | Anaerobic Digestion |  |  | 2.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Coleshill STW, Lichfield Road, Coleshill, Warwickshire | Warwickshire | West Midlands | England | B46 1DA | 419664 | 291273 | Warwickshire County Council | NWB/13CM021 | [5 empty] | 2013-06-27 | [6 empty] | 2013-11-13 |  |  |  |  | 2014-03-03 | 2015-04-15
C1870 | 257 | 2017-05-03 | Bio Dynamic | Colwick Industrial Estate (Farm and Food waste) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Eurobait Company Road, No 4 Colwick, Nottinghamshire | Nottinghamshire | East Midlands | England | NG4 2JT | 463399 | 339854 | Gedling Borough Council | 2013/0890NCC | [5 empty] | 2013-08-02 | [6 empty] | 2013-09-02 |  |  |  |  | 2014-03-01 | 2014-09-30
AA362 | 258 | 2014-05-22 | Shanks Group | Frog Island AD Plant (Waste AD) | Anaerobic Digestion |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Creek Way, Frog Island, Rainham | Greater London | London | England | RM13 8EN | 551017 | 180976 | Havering London Borough Council | P0530.11 | [5 empty] | 2011-04-06 | [6 empty] | 2012-03-29
C0149 | 259 | 2014-06-02 | Barfoot Energy Projects | Green Waste Composting Facility (Waste AD) | Anaerobic Digestion |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Green Waste Composting Facility, Bushywarren Lane, Ellisfield, Newbury, Berkshire | Hampshire | South East | England | RG20 | 465377 | 146817 | Basingstoke and Deane Borough Council | BDB/76333 | [5 empty] | 2012-05-02 | [6 empty] | 2012-07-09 | [5 empty] | 2014-05-20
B1283 | 260 | 2014-11-04 | Singleton Birch | Singleton Birch (Farm AD) | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Brigg Road, Melton Ross, Croxton | Humberside | Yorkshire and Humber | England | DN38 6AE | 508839 | 411734 | North Lincolnshire Council | WD/2012/1429 | [5 empty] | 2012-12-12 | [6 empty] | 2013-03-11 |  |  |  |  | 2013-07-27 | 2014-03-21
C1960 | 261 | 2017-05-03 | Ancala Bioenergy (formerly Biogen) | Bryn Pica AD / Tomorrow's Valley (Waste AD) - resubmission | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bryn Pica Landfill and Recycling, Merthyr Road, Llwdcoed, Aberdare | Mid Glamorgan | Wales | Wales | CF44 0BX | 300938 | 205377 | Rhondda Cynon Taff County Borough Council | 13/0880/10 | [5 empty] | 2013-08-23 | [6 empty] | 2013-10-07 |  |  |  |  | 2014-04-01 | 2015-09-15
01037A4 | 262 | 2014-05-20 | Infinis (previously NOVERA) | Suffolk Anaerobic Digestion Scheme (Waste AD) | Anaerobic Digestion |  |  | 1.05 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Eye Airfield , Eye , Suffolk | Suffolk | Eastern | England |  | 613200 | 275000 | Mid Suffolk District Council | 679/00 | [5 empty] | 2000-06-30 | [6 empty] | 2000-12-12
07082M4 | 263 | 2013-02-26 | Greater Manchester Waste | Bredbury Park Way - AD Stockport (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bredbury Park Industrial Estate, Bredbury, Stockport | Greater Manchester | North West | England | SK6 2SN | 392500 | 392300 | Stockport Metropolitan Borough Council | DC/027369 | [5 empty] | 2007-08-06 | [6 empty] | 2007-11-02 |  |  |  |  | 2010-07-01 | 2011-10-03
A0050 | 264 | 2014-05-20 | Chelveston Renewable Energy | Chelveston Renewable Energy Park (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Wellingborough, Northamptonshire | Northamptonshire | East Midlands | England | NN9 6AU | 499560 | 268037 | East Northamptonshire Council | 08/00194/NCC | [5 empty] | 2008-01-29 | [6 empty] | 2008-05-13
A0381 | 265 | 2017-04-20 | Future Biogas | Stud Farm, Rufford (Farm AD) | Anaerobic Digestion |  |  | 2.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rufford, Newark, Nottinghamshire | Nottinghamshire | East Midlands | England | NG22 9HB | 465057 | 362789 | Nottinghamshire County Council | F/1695 | [5 empty] | 2009-09-28 | [6 empty] | 2010-07-05 |  |  |  |  | 2016-09-01 | 2017-03-30
A0456 | 266 | 2016-11-01 | Scottish and Southern Energy (SSE) / William Tracey Ltd | Barkip Anaerobic Digestor (Waste AD) | Anaerobic Digestion |  |  | 2.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Barkip Landfill Site, Dalry | Strathclyde | Scotland | Scotland | KA24 4JJ | 229333 | 650530 | North Ayrshire Council | [6 empty] | 2009-09-02 | [6 empty] | 2009-10-15 |  |  |  |  | 2010-09-01 | 2012-05-11
AA017 | 267 | 2011-12-20 | Kirk Environmental | Dryholme Farm (Farm AD) | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dryholme Farm, Silloth, Wigton, Cumbria | Cumbria | North West | England | CA7 4PZ | 312882 | 552124 | Allerdale Borough Council | 2/2009/0864 | [5 empty] | 2009-12-02 | [6 empty] | 2010-06-16 |  |  |  |  | 2011-02-01 | 2011-11-04
AA100 | 268 | 2014-01-27 | J Pointon & Sons Ltd | John Pointon And Sons anaerobic digestion facility (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Felthouse Lane, Cheddleton, Staffordshire Moorlands | Staffordshire | West Midlands | England | ST13 7BT | 397144 | 350648 | Staffordshire Moorlands District Council | 10/00343/FMAJEI | [5 empty] | 2010-04-19 | [6 empty] | 2010-09-06
AA285 | 269 | 2014-05-15 | Fife Council | Lochhead Landfill CHP | Anaerobic Digestion |  |  | 1.7 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dunfermline, Fife | Fife | Scotland | Scotland |  | 308683 | 690319 | Fife Council | 11/01206/FULL | [5 empty] | 2011-03-07 | [6 empty] | 2011-08-18 |  |  |  |  | 2012-04-01 | 2014-03-31
AA393 | 270 | 2017-05-03 | Ancala Bioenergy (formerly Biogen) | Merevale & Blyth Estate (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Merevale Lane, Atherstone, Warwickshire | Warwickshire | West Midlands | England |  | 428111 | 297109 | Warwickshire County Council | NWB/10CM033 | [5 empty] | 2010-12-06 | [6 empty] | 2011-03-28 |  |  |  |  | 2013-05-28 | 2015-09-15
AA405 | 271 | 2017-05-03 | Ancala Bioenergy (formerly Biogen) | Bygrave Lodge Farm Anaerobic Digestion Facility (Farm AD) | Anaerobic Digestion |  |  | 2.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Nr Baldock, Hertfordshire | Hertfordshire | Eastern | England |  | 527584 | 235416 | Hertfordshire County Council | 1/0333-11 | [5 empty] | 2011-02-03 | [6 empty] | 2013-05-01 |  |  |  |  | 2013-05-02 | 2014-09-20
AA413 | 272 | 2017-05-03 | Ancala Bioenergy (formerly Biogen) | Westwood AD Plant (Farm AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Higham Park Farm, Bedford Road, Rushden, Northamptonshire | Northamptonshire | East Midlands | England |  | 498144 | 263639 | East Northamptonshire Council | 08/00056/CRA | [5 empty] | 2008-01-11 | [6 empty] | 2008-05-15 | [5 empty] | 2009-06-30
AA461 | 273 | 2014-01-03 | Barway Farms /Shropshire Energy | May Farm Anaerobic Digester (Farm AD) | Anaerobic Digestion |  |  | 2.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | May Farm, White House Road, Littleport, Ely, Cambridgeshire | Cambridgeshire | Eastern | England | CB7 4TF | 559921 | 286678 | East Cambridgeshire District Council | 11/00447/FUM | [5 empty] | 2011-06-09 | [6 empty] | 2012-11-29 | [5 empty] | 2013-12-12
AA544 | 274 | 2012-08-15 | Greenshoots Energy | Kenninghall Renewable Energy Facility (Waste AD) | Anaerobic Digestion |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Garboldisham Road, Norfolk | Norfolk | Eastern | England | NR16 2DU | 602618 | 284869 | Breckland Council | 3PL/2010/1372/F | [5 empty] | 2010-12-30 | [6 empty] | 2011-11-09
AA668 | 275 | 2018-03-02 | Biogen (formerly Tamar Energy) | Carousel Dairy AD Plant (Farm AD) | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Manor Farm, Farleigh Lane, Farleigh Wallop | Hampshire | South East | England | RG25 2HR | 460867 | 146936 | Basingstoke and Deane Borough Council | BDB/75034 | [5 empty] | 2011-08-30 | [6 empty] | 2012-03-12 |  |  |  |  | 2013-06-04 | 2013-12-10
AA733 | 276 | 2019-07-31 | Vale Europe | Clydach Refinery | Advanced Conversion Technologies |  |  | 10.3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Clydach Refinery, Ynys Penllwch Road, Clydach, Swansea | Swansea | Wales | Wales | SA6 5QR | 269551 | 201355 | City and County Council of Swansea | 2012/0452 | [5 empty] | 2012-03-27 | [6 empty] | 2012-10-09
AA769 | 277 | 2015-01-21 | Cannington Bioenergy | Cannington Cold Stores | Anaerobic Digestion |  |  | 3.296 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cannington, Bridgwater | Somerset | South West | England | TA5 2NJ | 323366 | 138920 | Sedgemoor District Council | 45/07/00022 | [5 empty] | 2008-01-25 | [6 empty] | 2008-12-22 | [5 empty] | 2009-07-29
AA774 | 278 | 2012-11-29 | McCain Foods | McCain Foods AD Plant (AD) | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Funthams Lane, Whittlesey, Peterborough, Cambridgeshire | Cambridgeshire | Eastern | England | PE7 2PG | 523801 | 297290 | Fenland District Council | F/YR08/0282/F | [5 empty] | 2008-03-12 | [6 empty] | 2008-04-09 | [5 empty] | 2010-05-01
AA847 | 279 | 2013-11-15 | Greenshoots Energy | Kenninghall Renewable Energy Facility (Resubmission) (AD) | Anaerobic Digestion |  |  | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Garboldisham Road, Norfolk | Norfolk | Eastern | England | NR16 2DU | 603151 | 284969 | Breckland Council | 3PL/2012/0737/F | [5 empty] | 2012-07-05 | 2013-09-19
AA872 | 280 | 2016-05-23 | Emerald Biogas | Preston Road AD Plant (Waste AD) | Anaerobic Digestion |  |  | 2.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | land at Preston Road, Aycliffe Industrial Estate, Newton Aycliffe | Durham | North East | England |  | 427211 | 523486 | Durham County Council | CMA/7/74 | [5 empty] | 2010-03-29 | [6 empty] | 2012-07-06 |  |  |  |  | 2013-01-01 | 2013-10-28
AA882 | 281 | 2014-03-17 | Lynton Development / Teg Environmental | East Dagenham Docks AD (AD) | Anaerobic Digestion |  |  | 1.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Plot 7A, Off Choats Road, Dagenham | Greater London | London | England | RM9 6 | 548394 | 182415 | Barking and Dagenham London Borough Council | 11/00460/FUL | [5 empty] | 2011-06-08 | [6 empty] | 2012-03-16 |  |  |  |  | 2012-10-01 | 2014-03-04
B0004 | 282 | 2018-03-02 | Biogen (formerly Tamar Energy) | Manor Farm (Farm AD) | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Manor Farm, Holbeach Hurn, Spalding, Lincolnshire | Lincolnshire | East Midlands | England | PE12 8LR | 540324 | 328455 | South Holland District Council | H09-0203-11 | [5 empty] | 2011-03-17 | [6 empty] | 2011-05-05 |  |  |  |  | 2013-06-04 | 2013-12-31
B0090 | 283 | 2018-04-05 | Olleco | Westcott Venture Park | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | High Street, Westcott, Buckinghamshire | Buckinghamshire | South East | England |  | 470457 | 217300 | Aylesbury Vale District Council | 10/20001/AWD | [5 empty] | 2010-05-24 | [6 empty] | 2010-07-09 |  |  |  |  | 2011-08-01 | 2013-11-07
B0317 | 284 | 2013-12-04 | Shanks Group | New Inn AD (Waste AD) | Anaerobic Digestion |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Pont-y-felin Industrial Estate, New Road, Panteg, Pontypool | Gwent | Wales | Wales | NP4 0SH | 330110 | 198710 | Torfaen County Borough Council | 12/P/00100 | [5 empty] | 2012-02-28 |  | 2013-04-16
B0359 | 285 | 2013-07-31 | Private Developer | Swancote Farm AD (Farm AD) | Anaerobic Digestion |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Swancote Farm, Swancote, Bridgnorth, Shropshire | Shropshire | West Midlands | England | WV15 5HB | 374201 | 293951 | Shropshire Council | 10/03881/MAW | [5 empty] | 2010-09-01 | [6 empty] | 2010-12-20 |  |  |  |  | 2012-04-01 | 2012-05-31
B0457 | 286 | 2018-01-30 | Viridor | Glasgow Renewable Energy and Recycling Centre (Waste AD) | Anaerobic Digestion |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Polmadie Disposal Complex, 425 Polmadie Road, Glasgow | Strathclyde | Scotland | Scotland | G42 0PJ | 259509 | 662366 | Glasgow City Council | 12/01631/DC | [5 empty] | 2012-08-14 | [6 empty] | 2013-01-29 |  |  |  |  | 2013-11-18 | 2017-12-15
B0511 | 287 | 2020-02-28 | Eco Sustainable Solutions | Parley Renewable Energy Park (AD) | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Chapel Lane, Parley, Christchurch, Dorset | Dorset | South West | England | BH23 6BG | 410161 | 98525 | Dorset County Council | PL\1363\12 | [5 empty] | 2012-08-23 | [6 empty] | 2013-09-25 |  |  |  | 2016-09-25
B0575 | 288 | 2017-06-23 | Wyke Farms | Wyke Farms Biogas (Farm AD) | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | White House Farm, Bruton | Somerset | South West | England | BA4 6NX | 366362 | 134820 | Somerset County Council | PL\2138\12 (2012/1085) | [5 empty] | 2012-03-01 | [6 empty] | 2012-11-01 |  |  |  |  | 2012-11-30 | 2013-09-19
B0631 | 289 | 2019-06-13 | Shanks Group | South Kirkby Business Park (Waste AD) | Anaerobic Digestion |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | South Kirkby, Wakefield | West Yorkshire | Yorkshire and Humber | England | WF9 4DG | 443726 | 411990 | Wakefield Council | 08/01633/FUL | [5 empty] | 2008-06-19 | [6 empty] | 2008-11-27 |  |  |  |  | 2013-07-17 | 2015-12-01
B0664 | 290 | 2018-03-15 | Energy Works / The Spencer Group | Energy Works Hull - AD (Waste AD) | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cleveland Street (former Adm Cocoa Plant), Dalton Street, Kingston Upon Hull | Humberside | Yorkshire and Humber | England |  | 510170 | 430424 | Kingston upon Hull City Council | 11/00615/CM | [5 empty] | 2011-06-27 | [6 empty] | 2011-10-20 |  |  |  |  | 2016-07-05 | 2018-03-01
C0005 | 291 | 2013-05-22 | Staples Brothers | Staples Anaerobic Digestion CHP Plant (Waste AD) | Anaerobic Digestion |  |  | 1.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Staples Vegetables Limited, Station Farm, Station Road, Sibsey, Boston, Lincolnshire | Lincolnshire | East Midlands | England | PE22 0SE | 536298 | 350519 | East Lindsey District Council | S/152/01385/10 | [5 empty] | 2010-07-08 | [6 empty] | 2010-07-19 | [5 empty] | 2011-10-01
IF1008 | 292 | 2013-09-20 | Clean Power Properties | Brierley Hill Energy Recovery Centre (Waste AD) | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Brierley Hill Freight and Steel Terminal, Moor Street, Brierley Hill, West Midlands | West Midlands | West Midlands | England | DY5 3SN | 391166 | 286880 | Dudley Metropolitan Borough Council | P12/1287 | [5 empty] | 2012-10-08 |  | 2013-08-29
IF1172 | 293 | 2014-04-22 | Northamptonshire County Counci | West Lodge Farm | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Blisworth Road, Courteenhall | Northamptonshire | East Midlands | England |  | 475087 | 253122 | South Northamptonshire Council | S/2008/1430/PCC | [5 empty] | 2008-10-13 | [6 empty] | 2008-10-30
N00050B | 294 | 2014-02-12 | Viridor / Wyvern Waste Services | Dimmer Anaerobic Digestor (Waste AD) | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dimmer, Castle Cary | Somerset | South West | England |  | 361141 | 131346 | South Somerset District Council | 04/02208/CPO | [5 empty] | 2004-08-13 | [6 empty] | 2004-12-10 | [5 empty] | 2013-10-01
A0173 | 295 | 2017-02-23 | Pro-Active Energy | M74 Central Coalburn (Waste AD) | Anaerobic Digestion |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Coalburn, Lanark. Strathclyde | Strathclyde | Scotland | Scotland | ML11 0NJ | 283383 | 635612 | South Lanarkshire Council | CL/09/0272 | [5 empty] | 2009-07-01 | [6 empty] | 2009-11-05 |  |  |  | 2012-11-05
AA581 | 296 | 2015-10-15 | Renewable Power Systems | Pineham AD Plant (Waste AD) | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land To The Right of Portway Pineham Milton Keynes | Buckinghamshire | South East | England |  | 488703 | 240458 | Milton Keynes Council | 10/01181/MIN | [5 empty] | 2010-06-22 | [6 empty] | 2011-10-12
B0343 | 297 | 2018-10-03 | Severn Trent (formerly Agrivert) | Wallingford (Waste AD) | Anaerobic Digestion |  |  | 2.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wallingford AD, Benson Lane, Preston Crowmarsh, Wallingford Oxfordshire | Oxfordshire | South East | England | OX10 6SL | 461566 | 190948 | Oxfordshire County Council | MW.0090/10 | [5 empty] | 2010-06-04 | [6 empty] | 2011-03-30 | [5 empty] | 2013-05-17
B0599 | 298 | 2017-01-16 | Peel Environmental | North Clyde Recylcing Centre (Waste AD) | Anaerobic Digestion |  |  | 1.6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Rothesay Dock, Clydebank | Strathclyde | Scotland | Scotland | G81 1LX | 250440 | 669070 | West Dunbartonshire Council | DC12/143 | [5 empty] | 2012-06-25 | [6 empty] | 2012-12-05 |  |  |  | 2015-12-05
B1115 | 301 | 2018-02-02 | Granville Ecopark | Granville Ecopark | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lands to the immediate West of Linden Foods, Granville Industrial Estate, Dungannon | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 1NJ | 88500 | 521293 | Northern Ireland Planning Service | M/2008/0063/F | [5 empty] | 2009-03-25 | [6 empty] | 2010-02-02 |  |  |  | 2015-02-02 | 2013-09-01 | 2014-06-10
C2252 | 302 | 2020-06-04 | Resourceful Earth | Queen Charlton Quarry Renewable Energy Facility - food waste | Anaerobic Digestion |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Parcel 5319, Charlton Field Lane, Queen Charlton, Bristol, Bath And North East Somerset | Somerset | South West | England | BS31 2TN | 363395 | 165868 | Bath and North East Somerset Council | 13/04126/MINW | [5 empty] | 2013-09-25 | [6 empty] | 2014-05-19 |  |  |  |  | 2016-05-01
B0150 | 304 | 2019-07-02 | SITA UK | Mitcham Eco Park (Waste AD) | Anaerobic Digestion |  |  | 6.2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Benedict Wharf Off Hallowfield Way, Mitcham, Surrey | Greater London | London | England | CR4 5BQ | 527064 | 168315 | Merton London Borough Council | 08/P2724 | [5 empty] | 2008-10-16 |  | 2011-10-12 |  |  |  | 2011-10-12 | 2011-10-12
B0216 | 305 | 2015-09-24 | AeroThermal Group (AAD (South West)) | Lee Moor AD (Waste AD) | Anaerobic Digestion |  |  | 3.25 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Lee Moor China Clay Refinery, near Plympton, Devon | Devon | South West | England |  | 256301 | 61291 | Devon County Council | DCC/3245/2011 | [5 empty] | 2011-07-19 | [6 empty] | 2011-12-05 |  |  |  | 2014-12-05
B0547 | 306 | 2016-08-11 | ReFood UK | Granox Biogas Plant | Anaerobic Digestion |  |  | 5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Desoto Road, Widnes | Cheshire | North West | England | WA8 0PB | 350392 | 384214 | Halton Borough Council | 12/00156/FULEIA | [5 empty] | 2012-03-21 | [6 empty] | 2012-10-19 |  |  |  |  | 2013-01-01 | 2014-06-18
B1052 | 307 | 2015-06-22 | Prosper Demulder / ReFood | Prosper Demulder Limited Anaerobic Digestion Plant (Waste AD) - extension | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ings Road, Bentley, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | DN5 9SW | 457265 | 404820 | Doncaster Metropolitan Borough Council | 13/01843/FULMC | [5 empty] | 2013-08-30 | [6 empty] | 2013-11-20 |  |  |  |  | 2014-03-18 | 2015-06-02
B1246 | 308 | 2018-10-03 | Severn Trent (formerly Agrivert) | Trumps Farm (AD) | Anaerobic Digestion |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Long Cross, Chertsey, Surrey | Surrey | South East | England | KT16 0EF | 499459 | 165739 | Runnymede Borough Council | RU.10/0872 | [5 empty] | 2010-09-15 | [6 empty] | 2011-05-12 |  |  |  |  | 2013-05-30 | 2014-02-28
A0126 | 309 | 2014-11-20 | Whites Renewable Energy | Selby Renewable Energy Park | Anaerobic Digestion |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Former Tate & Lyle site, Denison Road, Selby, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO8 8EF | 462309 | 431934 | North Yorkshire County Council | NY/2009/0038/FUL | [5 empty] | 2009-01-10 | [6 empty] | 2009-07-17
A0375 | 310 | 2017-07-28 | Viridor | Beddington AD Facility (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Beddington Lane, Beddington | Greater London | London | England | CR0 4TH | 530006 | 166069 | Sutton London Borough Council | D2010/62424 | [5 empty] | 2010-03-02 | 2017-07-07
A0494 | 311 | 2018-03-02 | Biogen (formerly Tamar Energy) | Ratty's Lane Sustainable Energy Facility (Waste AD) | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ratty’s Lane, Hoddesdon | Hertfordshire | Eastern | England | EN11 0RG | 538126 | 209495 | Hertfordshire County Council | 7/0510-10 | [5 empty] | 2010-06-28 | [6 empty] | 2012-03-26 |  |  |  | 2015-03-26 | 2014-03-31 | 2016-07-04
AA134 | 312 | 2017-01-20 | Biffa/West Sussex County Council | Brookhurst Wood (Waste AD) | Anaerobic Digestion |  |  | 4.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Horsham, West Sussex | West Sussex | South East | England | RH12 4QD | 517281 | 135056 | West Sussex County Council | WSCC/055/09/NH | [5 empty] | 2009-07-31 | [6 empty] | 2010-10-01 |  |  |  |  | 2013-06-20 | 2015-07-01
AA617 | 313 | 2018-03-02 | Biogen (formerly Tamar Energy) | Halstead Renewable Power Project (Waste AD) | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land Adjoining Fifth Avenue Bluebridge Industrial Estate Halstead Essex | Essex | Eastern | England |  | 582782 | 230400 | Braintree District Council | 10/00998/ECC | [5 empty] | 2010-07-16 | [6 empty] | 2010-08-20 |  |  |  |  | 2013-06-04 | 2014-07-01
AA856 | 314 | 2014-07-23 | Clean Power Properties & Network Rail Infrastructure | Washwood | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Washwood Heath Energy Recovery Centre, Washwood Heath Freight Yard No, Common Lane, Washwood Heath, Birmingham, West Midlands | West Midlands | West Midlands | England | B8 2U | 410878 | 289562 | Birmingham City Council | 2012/05409/PA | [5 empty] | 2012-08-08 | [6 empty] | 2012-11-23 |  |  |  | 2015-11-22
AA871 | 315 | 2019-06-26 | SITA UK | Packington AD Plant | Anaerobic Digestion |  |  | 1.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Packington Lane Landfill Site, Packington Lane, Little Packington, Meriden Warwickshire CV7 7HN | Warwickshire | West Midlands | England | CV7 7HN | 420921 | 285739 | Warwickshire County Council | NWB/12CM001 | [5 empty] | 2011-12-23 | [6 empty] | 2012-08-22 |  |  |  | 2019-07-02
AA888 | 316 | 2019-12-20 | Clean Power Properties & Network Rail Infrastructure | Willesden | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Willesden Junction Freight Terminal Site, Channel Gate Road, Willesden, London | Greater London | London | England | NW10 6UQ | 521310 | 182908 | Ealing London Borough Council | PP/2012/3267 | [5 empty] | 2012-08-03 |  | 2019-12-10
B0321 | 317 | 2014-07-23 | Viridor | Walpole Landfill AD (Waste AD) | Anaerobic Digestion |  |  | 1.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pawlett, Bridgwater, Somerset | Somerset | South West | England |  | 331400 | 143200 | Sedgemoor District Council | 41/10/00007 | [5 empty] | 2010-04-28 | [6 empty] | 2010-05-17 |  |  |  |  | 2012-03-01 | 2014-02-02
B0564 | 318 | 2017-05-03 | Ancala Bioenergy (formerly Biogen) | Waen Biogas (Waste AD) | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Former Abattoir, Holywell Road, Rhuallt, St Asaph, Denbighshire, LL17 0DS | Clwyd | Wales | Wales |  | 304959 | 374970 | Denbighshire County Council | 47/2012/1120 | [5 empty] | 2012-08-20 | [6 empty] | 2012-11-21 |  |  |  |  | 2013-06-01 | 2014-08-04
B0879 | 319 | 2018-03-02 | Biogen (formerly Tamar Energy) | Swanley (Waste AD) | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Tamar Organics Ltd- Swanley, Cookham Road, Swanley | Greater London | London | England | BR8 7QP | 549090 | 169697 | Bromley London Borough Council | 09/03618/FULL1 | [5 empty] | 2009-12-21 | [6 empty] | 2012-03-30
B0881 | 320 | 2014-07-17 | Peel Environmental | Fletcher Bank Quarry (Waste AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Fletcher Bank Works, Manchester Road, Ramsbottom, Bury | Lancashire | North West | England | BL0 0DD | 380250 | 416825 | Bury Metropolitan Borough Council | 57118 | [5 empty] | 2014-01-20 |  | 2014-03-18
B0882 | 321 | 2019-09-04 | Biogen (formerly Tamar Energy) | Wardley (Waste AD) | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Wardley Colliery, Wardley Lane, Felling, Gateshead | Tyne and Wear | North East | England | NE10 8YE | 431341 | 560661 | South Tyneside Metropolitan Borough Council | ST/0995/13/FUL | [5 empty] | 2013-09-03 | [6 empty] | 2014-12-01 |  |  |  | 2017-12-01
C0151 | 322 | 2015-10-29 | Clean Power Properties & Network Rail Infrastructure | Micheldever Rail Sidings EFW | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Micheldever Rail Sidings, Overton Road, Micheldever Station, Winchester | Hampshire | South East | England | SO21 3AN | 451868 | 143268 | Hampshire County Council | 12/02013/HCS | APP/Q1770/W/14/3001572 |  |  |  |  | 2012-12-13 |  | 2014-06-10 | 2015-01-26 | 2015-10-29
AA928 | 323 | 2020-06-16 | Peel Environmental | North Selby Anaerobic Digestion & Horticultural Glasshouse Project (AD) | Anaerobic Digestion |  |  | 2.75 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | New Road, Escrick, Deighton, York, North Yorkshire, YO19 6EZ (lies south of York, between the villages of Escrick and Wheldrake, Northy Selby Mine) | North Yorkshire | Yorkshire and Humber | England | YO19 6EZ | 464904 | 443729 | York City Council | 12/03385/FULM | [5 empty] | 2012-11-07 | [6 empty] | 2014-04-28
C2647 | 324 | 2017-01-19 | Welland Waste Management | Pebble Hall Farm - resubmission - Food Waste AD | Anaerobic Digestion |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pebble Hall Farm, Theddingworth Road, Marston Trussell, Northamptonshire, LE17 6NJ | Northamptonshire | East Midlands | England | LE17 6NJ | 466125 | 284563 | Daventry District Council | DA/2014/0045 | [5 empty] | 2014-01-17 | [6 empty] | 2014-01-31 |  |  |  |  | 2015-01-15 | 2015-12-15
C2684 | 325 | 2015-11-25 | St Nicholas Court Farms Ltd | St Nicholas Court Farm (AD) - resubmission | Anaerobic Digestion |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | St Nicholas At Wade, Birchington, Kent | Kent | South East | England |  | 625958 | 166890 | Thanet District Council | F/TH/13/0587 | [5 empty] | 2013-07-25 | [6 empty] | 2013-09-26 |  |  |  |  | 2014-03-31 | 2014-12-01
H0076 | 326 | 2016-12-15 | Earthly Energy Group | Wilton Centre (Waste AD) | Anaerobic Digestion |  |  | 5.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Land at Wilton International, Trunk Road, Redcar, Cleveland | Cleveland | North East | England | TS10 5BW | 458500 | 519500 | Redcar and Cleveland Borough Council | R/2013/0369/FFM | [5 empty] | 2013-05-21 | [6 empty] | 2013-07-24 |  |  |  | 2016-07-24
H0116 | 327 | 2016-05-10 | Wight Farm Energy | Gore Cross - AD | Anaerobic Digestion |  |  | 2.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land opposite Gore Cemetery and near to Arreton Cross Arreton Newport Isle of Wight PO30 | Isle of Wight | South East | England | PO30 3A | 452924 | 86485 | Isle of Wight Council | P/00198/13 | [5 empty] | 2013-07-05 | [6 empty] | 2013-12-20 |  |  |  |  | 2013-12-21 | 2014-12-20
B1031 | 328 | 2017-07-31 | ReFood UK | Dagenham Docks Biogas (Waste AD) | Anaerobic Digestion |  |  | 1.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Plot 5 London Sustainable Industries Park North Choats Road Dagenham Essex | Greater London | London | England | RM9 6LF | 548310 | 182740 | Barking and Dagenham London Borough Council | 13/00649/FUL | [5 empty] | 2013-08-01 | [6 empty] | 2013-11-11 |  |  |  |  | 2016-04-01 | 2017-07-07
B1128 | 329 | 2017-03-21 | B and D Property Services | Reservoir Road (Farm AD) | Anaerobic Digestion |  |  | 1.14 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 40m west of No.31 Reservoir Road Banbridge | Co. Down | Northern Ireland | Northern Ireland | BT32 4LD | 121174 | 500121 | Northern Ireland Planning Service | Q/2010/0585/F | [5 empty] | 2010-12-13 | [6 empty] | 2011-08-04 |  |  |  | 2016-08-04 | 2015-08-04 | 2016-08-04
B1282 | 330 | 2016-09-22 | JFS Biogas | Leeming Bar (Waste AD) | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land to rear of Clapham Lodge, Dere Street, Leeming, Northallerton | North Yorkshire | Yorkshire and Humber | England | DL7 9LY | 429880 | 488497 | North Yorkshire County Council | NY/2013/0237/FUL | [5 empty] | 2013-07-30 | [6 empty] | 2015-04-02 |  |  |  |  | 2015-07-15 | 2016-01-15
B1429 | 331 | 2017-04-20 | Future Biogas (Blankney Estate) | Metheringham Heath (Farm AD) | Anaerobic Digestion |  |  | 6.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Heath Farm, Metheringham Heath, Lincoln, Lincolnshire | Lincolnshire | East Midlands | England | LN4 2AJ | 502320 | 360674 | North Kesteven District Council | 13/1426/FUL | [5 empty] | 2014-01-21 | [6 empty] | 2014-06-11 |  |  |  |  | 2016-02-15 | 2017-03-30
C2311 | 332 | 2020-06-17 | Clean Power Properties | Eastleigh | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Chickenhall Lane, Eastleigh Central, Eastleigh | Hampshire | South East | England | SO50 6RQ | 446272 | 118254 | Hampshire County Council | S/13/73507 | [5 empty] | 2013-10-25 | [6 empty] | 2014-03-31 |  |  |  | 2017-03-31
C2334 | 333 | 2016-05-16 | Pure Malt Products Limited | Pure Malt Products AD | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pure Malt Products Ltd Whittingehame Drive Haddington East Lothian | Lothian | Scotland | Scotland | EH41 4BD | 351977 | 674000 | East Lothian Council | 13/00845/P | [5 empty] | 2013-10-30 | [6 empty] | 2013-12-20 |  |  |  |  | 2015-12-31 | 2016-01-01
C2873 | 335 | 2015-09-25 | Greener for Life Energy | Bearley Lane | Anaerobic Digestion |  |  | 1.3 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land Os 0002 Bearley Lane, Tintinhull, Yeovil, Somerset | Somerset | South West | England | BA22 8PE | 349663 | 122127 | South Somerset District Council | 14/00230/FUL | [5 empty] | 2014-03-19 | [6 empty] | 2014-11-21 |  |  |  | 2017-11-21
IF1086 | 336 | 2014-07-21 | J M Stratton & Co | Codford Biogas (Waste AD) | Anaerobic Digestion |  |  | 3.7 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | East Farm Church Lane Codford Wiltshire | Wiltshire | South West | England |  | 399036 | 141476 | Wiltshire Council | W/11/00745/WCM | [5 empty] | 2011-03-01 | [6 empty] | 2011-06-03 |  |  |  |  | 2013-03-01 | 2014-03-31
C2907 | 337 | 2017-12-12 | Pigeon Investment Management | Banningham Road | Anaerobic Digestion |  |  | 1.6 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land at Banningham Road, Aylsham | Norfolk | Eastern | England | NR11 6FD | 620476 | 327900 | Broadland District Council | 20140630 | APP/K2610/W/15/3053067 |  |  |  |  | 2014-04-15 |  | 2014-12-19 | 2015-07-30 |  |  | 2015-11-16 | 2015-11-16
AA887 | 338 | 2016-10-31 | PandaGreen | Blaise Farm (Farm AD) | Anaerobic Digestion |  |  | 5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Blaise Farm Quarry Kings Hill West Malling Kent | Kent | South East | England | ME19 4PN | 566208 | 156263 | Tonbridge and Malling Borough Council | 12/02549/WAS | [5 empty] | 2012-08-13 | [6 empty] | 2013-04-16
AA646 | 339 | 2015-07-15 | Shanks Group | Bolton Road Waste Treatment and Renewable Energy Facility (Waste AD) | Anaerobic Digestion |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Off Bolton Road, Manvers, Rotherham, South Yorkshire, S60 | South Yorkshire | Yorkshire and Humber | England |  | 445484 | 401479 | Rotherham Metropolitan Borough Council | RB2011/1539 | [5 empty] | 2011-10-25 | [6 empty] | 2012-05-08 |  |  |  |  | 2012-09-10 | 2015-07-13
C2889 | 340 | 2018-03-28 | Grocontinental/ Whitchurch Biogas | Broughall Fields Farm | Anaerobic Digestion |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Broughall Fields Farm, Ash Road, Whitchurch, Shropshire | Shropshire | West Midlands | England | SY13 4DE | 355602 | 340776 | Shropshire Council | 14/01398/MAW | [5 empty] | 2014-03-28 | [6 empty] | 2014-12-19 |  |  |  | 2017-12-19 | 2016-08-01 | 2017-03-30
C2705 | 341 | 2016-03-04 | Clean Power Properties | New Lodge Farm - AD | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | New Lodge Farm, Pontarulais Road, Cwmgwili, Llanelli | Dyfed | Wales | Wales | SA14 6PW | 257192 | 209823 | Carmarthenshire County Council | S/29559 | [5 empty] | 2014-02-05 |  | 2016-02-05
B0308 | 342 | 2016-12-15 | Willen Biogas & Xergi | Cattlegate Farm Biogas (Farm AD) | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | The Slip, Cattlegate Farm, Cattlegate Road, Enfield | Hertfordshire | Eastern | England | EN2 8AU | 530613 | 201383 | Hertfordshire County Council | 6/1795-11 | [5 empty] | 2011-08-24 | [6 empty] | 2013-06-20 |  |  |  |  | 2014-08-01 | 2015-12-01
B1511 | 343 | 2016-05-25 | GlaxoSmithKline | GlaxoSmithKline (Waste AD) | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Shewalton Road Riverside Business Park Irvine Ayrshire KA11 5AP | Strathclyde | Scotland | Scotland |  | 234362 | 636566 | North Ayrshire Council | 14/00036/PP | [5 empty] | 2014-01-21 | [6 empty] | 2014-02-21 |  |  |  |  | 2014-07-08 | 2015-03-15
C3231 | 344 | 2016-05-31 | JFS Biogas | Gravel Pit Farm | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Gravel Pit Farm, Sand, Hutton, York | North Yorkshire | Yorkshire and Humber | England | YO41 1LN | 468377 | 458725 | Ryedale District Council | 14/00709/MFUL | APP/Y2736/A/14/2226293 |  |  |  |  | 2014-06-26 |  |  | 2014-12-18 |  |  | 2015-05-26 | 2015-05-26 |  |  |  | 2018-05-26
C2598 | 345 | 2017-07-20 | Greener for Life Energy | Great Hele Farm AD farm waste | Anaerobic Digestion |  |  | 1.3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Great Hele Farm, Great Hele Lane, South Molton, Devon, EX36 4LB | Devon | South West | England |  | 272135 | 124437 | North Devon District Council | 56827 | APP/X1118/W/14/2226565 |  |  |  |  | 2014-01-09 |  | 2014-07-09 | 2014-10-09 |  |  | 2015-01-15 | 2015-01-15 |  |  |  |  | 2015-04-15 | 2017-01-25
IF1115 | 346 | 2014-11-26 | Andigestion | Harlington Quarry | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | N/O Cranford Lane, Harlington, Hayes, Middlesex | Greater London | London | England |  | 509450 | 178120 | Hillingdon London Borough Council | 2373/APP/2012/2011 | [5 empty] | 2012-11-02 |  | 2014-08-29
C2069 | 347 | 2020-06-04 | J H Willis & Son Ltd | Holme Farm | Anaerobic Digestion |  |  | 1.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Holme Farm, Marsh Lane Ince, Chester, Cheshire | Cheshire | North West | England | CH2 4NR | 345687 | 377142 | Cheshire West and Chester Council | 13/04187/WAS | [5 empty] | 2013-09-23 | [6 empty] | 2014-07-10
C3250 | 348 | 2017-04-20 | BioConstruct | Imperial Park | Anaerobic Digestion |  |  | 5.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | LAND OFF IMPERIAL AVENUE SOUTH BANK TS6 6BA | Cleveland | North East | England |  | 452775 | 521083 | Redcar and Cleveland Borough Council | R/2014/0435/FFM | [5 empty] | 2014-07-08 | [6 empty] | 2014-10-16 |  |  |  | 2017-10-16 | 2015-12-01 | 2016-12-05
IF1412 | 349 | 2016-05-31 | Hallwick Energy | Land Adjacent to Thomas Swan and Co Ltd. | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rotary Way, Consett, Co. Durham | Durham | North East | England |  | 412017 | 551124 | Durham County Council | CMA/1/84 | [5 empty] | 2013-02-26 | [6 empty] | 2013-07-03 |  |  |  |  | 2014-04-23 | 2014-12-15
AA849 | 350 | 2015-10-15 | Rockscape Energy | North Moor Farm AD Plant (Farm AD) | Anaerobic Digestion |  |  | 4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | North Moor Farm, Belton, DN17 4DA | Humberside | Yorkshire and Humber | England |  | 479949 | 409327 | North Lincolnshire Council | WD/2012/0901 | [5 empty] | 2012-07-30 | [6 empty] | 2012-10-19 |  |  |  |  | 2013-03-01 | 2014-04-01
C3254 | 351 | 2015-10-05 | JFS Biogas | Park Shield | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land North Of Fourstones Substation Fourstones Northumberland | Northumberland | North East | England |  | 389596 | 568832 | Northumberland County Council | 14/02186/RENE | APP/P2935/W/14/3001690 |  |  |  |  | 2014-07-03 |  | 2015-01-07 | 2015-02-20 |  | 2015-09-15
01002M5a | 352 | 2020-01-20 | Gent Fairhead Environmental Services | Wren Power and Pulp (Rivenhall Airfield) | Anaerobic Digestion |  |  | 1.786 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Woodhouse Farm, Near Braintree, Essex | Essex | Eastern | England |  | 582400 | 220500 | Essex County Council | ESS/37/08/BTE | [5 empty] | 2008-09-08 | [6 empty] | 2010-03-02 |  |  |  | 2015-03-02 | 2016-04-11
AA658 | 353 | 2014-09-02 | Fred Walter & Sons Ltd | Sutton Grange AD Plant | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sutton Cum Lound, Retford, Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 8SB | 469299 | 385640 | Bassetlaw District Council | 47/11/00019 | [5 empty] | 2012-01-11 | [6 empty] | 2012-05-10 |  |  |  |  | 2013-01-01 | 2014-03-20
C2881 | 354 | 2016-02-05 | Greener for Life Energy | The Old Dairy | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | The Old Dairy, Chavenage, Tetbury | Gloucestershire | South West | England | GL8 8XU | 385467 | 195975 | Stroud District Council | S.14/0673/FUL | APP/C1625/W/15/3032550 |  |  |  |  | 2014-03-25 |  | 2014-11-13 | 2015-06-19 |  | 2016-01-22
C2640 | 355 | 2014-09-03 | Clean Power Properties & Network Rail Infrastructure | Wheldon Road - resubmission | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Castleford Wakefield WF10 2PP | West Yorkshire | Yorkshire and Humber | England |  | 443976 | 426218 | Wakefield Council | 13/03470/FUL | [5 empty] | 2014-01-09 |  | 2014-07-17
B1032 | 356 | 2016-09-23 | Grundon | Wingmoor Farm (Waste AD) | Anaerobic Digestion |  |  | 1.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wingmoor Quarry And Landfill Stoke Road Bishops Cleeve Cheltenham Gloucestershire GL52 7DG | Gloucestershire | South West | England | GL52 7DG | 394374 | 227514 | Gloucestershire County Council | 13/0094/TWMAJW | [5 empty] | 2013-12-13 | [6 empty] | 2014-05-20 |  |  |  |  | 2014-06-01 | 2014-11-30
C2753 | 357 | 2016-05-17 | Beeswax Farming (Rainbow) | Carrington Farm AD | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | LAND TO THE NORTH OF BEECHES LANE, CARRINGTON, BOSTON, LINCOLNSHIRE | Lincolnshire | East Midlands | England | PE22 7JD | 530540 | 354400 | East Lindsey District Council | S/029/00231/14 | [5 empty] | 2014-02-26 | [6 empty] | 2014-07-31 |  |  |  |  | 2014-11-15 | 2016-01-07
C3084 | 358 | 2014-12-05 | Peel Environmental | Houghton Main Renewable Energy - AD | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land off Houghton Main Colliery Roundabout, Park Spring Road, Houghton Main, Barnsley | South Yorkshire | Yorkshire and Humber | England |  | 441799 | 406582 | Barnsley Council | 2014/0559 | [5 empty] | 2014-05-30 |  | 2014-11-26
C3260 | 359 | 2016-05-17 | Private Developer | West Roucan Farm | Anaerobic Digestion |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | West Roucan Farm, Low Road, Tinwald, Dumfries, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 302227 | 578926 | Dumfries and Galloway Council | 14/P/3/0383 | [5 empty] | 2014-07-21 | [6 empty] | 2014-09-23 |  |  |  | 2017-09-23 | 2015-04-15 | 2015-12-01
C3392 | 360 | 2018-03-02 | Biogen (formerly Tamar Energy) | Gedling Colliery AD | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land At Gedling Colliery Arnold Lane Gedling Nottinghamshire | Nottinghamshire | East Midlands | England | NG4 4HF | 461270 | 343928 | Gedling Borough Council | 2014/1025NCC | [5 empty] | 2014-08-22 | 2015-03-15 | [5 empty] | 2014-10-02
AA760 | 361 | 2014-09-16 | C.R.E.S Biogas | Twemlow Lane AD Plant (Waste AD) | Anaerobic Digestion |  |  | 1.15 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Former Fuel Storage Depot, Twemlow Lane, Twemlow, Crewe, Cheshire, CW4 8DS | Cheshire | North West | England |  | 378059 | 368999 | Cheshire East Council | 12/0705W | N/A |  |  |  |  | 2012-02-14 |  | 2001-07-22
B1341 | 362 | 2014-12-05 | Greener for Life Energy | Trenoweth Guidestone Biogas Plant (Farm AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land At Trenoweth Guidestone St Columb Cornwall | Cornwall | South West | England |  | 190542 | 64879 | Cornwall Council | PA14/03296 | [5 empty] | 2014-05-15 |  | 2014-11-24
AA695 | 363 | 2019-08-13 | Green Energy (South Wales) | Maesgwyn Anaerobic Digestion Facility (Waste AD) | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Former Coal Stocking Ground Maesgwyn Glynneath | West Glamorgan | Wales | Wales |  | 286587 | 208584 | Neath Port Talbot County Borough Council | P2012/0092 | [5 empty] | 2012-02-20 | [6 empty] | 2014-07-30 |  |  |  | 2019-07-30
B0214 | 365 | 2020-06-09 | Surrey County Council | Charlton Lane Eco Park (Waste AD) | Anaerobic Digestion |  |  | 1.7 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Charlton Lane Waste Managment Facility , Charlton Lane, Shepperton | Surrey | South East | England | TW17 8QA | 508556 | 168426 | Surrey County Council | 10/00947/SCC | [5 empty] | 2010-11-25 | [6 empty] | 2011-06-29 |  |  |  |  | 2015-07-01 | 2018-03-01
B1521 | 366 | 2014-12-03 | Eco Sustainable Solutions | Bourne Park AD (AD) | Anaerobic Digestion |  |  | 1.1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Piddlehinton, Dorchester, Dorset | Dorset | South West | England | DT2 7TU | 372306 | 97577 | Dorset County Council | PL\0698\08 | [5 empty] | 2008-05-21 | [6 empty] | 2010-06-08 |  |  |  | 2013-06-08 | 2012-01-01 | 2012-09-25
AA307 | 367 | 2016-09-27 | Organic Recycling | Decoy Farm (Farm AD) | Anaerobic Digestion |  |  | 1.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Spalding Road, Crowland, Peterborough | Lincolnshire | East Midlands | England | PE6 0LX | 525991 | 312650 | South Holland District Council | H02-1061-10 & H02-0492-10 | [5 empty] | 2010-12-22 | [6 empty] | 2011-02-21 |  |  |  |  | 2015-04-30 | 2016-07-01
AA567 | 368 | 2018-04-05 | AmeyCespa | Allerton Waste Recovery Park (Waste AD) | Anaerobic Digestion |  |  | 1.1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Allerton Waste Recovery Park, Allerton Quarry & Landfill, Knaresborough, North Yorkshire, HG5 | North Yorkshire | Yorkshire and Humber | England | HG5 | 440675 | 459799 | North Yorkshire County Council | NY/2011/0328/ENV | [5 empty] | 2011-10-12 | [6 empty] | 2012-10-01 |  |  |  |  | 2015-02-15 | 2018-03-04
AA611 | 369 | 2015-09-30 | British Sugar | Wissington Sugar Factory | Anaerobic Digestion |  |  | 18 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Wissington Sugar Access Road Stoke Ferry Norfolk | Norfolk | Eastern | England | PE33 9QG | 566070 | 297629 | Norfolk County Council | C/2/2011/2030 | [5 empty] | 2011-09-01 | [6 empty] | 2011-12-12 |  |  |  | 2014-12-12
AA691 | 370 | 2018-10-03 | Severn Trent (formerly Agrivert) | Coursers Farm AD Plant (Waste AD) | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Coursers Road, St Albans, Hertfordshire | Hertfordshire | Eastern | England | AL4 0PD | 520447 | 204547 | Hertfordshire County Council | 0/0262-12 | [5 empty] | 2012-01-20 | [6 empty] | 2012-08-15 |  |  |  | 2015-08-15 | 2015-08-25 | 2016-10-03
B0309 | 371 | 2017-05-03 | Ancala Bioenergy (formerly Biogen/Aluana Renewable Energy) | Millerhill AD (Waste AD) | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Former Millerhill Marshalling Yards Whitehill Mains Road Millerhill Dalkeith Midlothian | Lothian | Scotland | Scotland | EH11 | 332400 | 670800 | Midlothian Council | 13/00077/MSC | [5 empty] | 2013-01-25 | [6 empty] | 2013-05-31 |  |  |  |  | 2014-02-01 | 2016-12-01
B0639 | 373 | 2016-10-31 | PandaGreen | Willow Farm - New Earth Solutions (Waste AD) | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Willow Farm, Severn Road, Severnside, Nr Hallen, South Gloucestershire | Gloucestershire | South West | England | BS10 7SJ | 354564 | 181223 | South Gloucestershire Council | PT12/1015/MW | [5 empty] | 2012-03-22 | [6 empty] | 2012-06-22
B1099 | 375 | 2016-05-23 | Evergreen Biogas | Spout Road (Farm AD) | Anaerobic Digestion |  |  | 2.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | 120m north west of 22 Spout Road Strabane Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT82 8NA | 50598 | 560668 | Northern Ireland Planning Service | J/2011/0051/F | [5 empty] | 2011-02-09 | [6 empty] | 2012-01-19 |  |  |  | 2017-01-19
C1681 | 376 | 2016-05-25 | Greener for Life Energy | Hogsbrook Farm - Farm AD | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Hogsbrook Farm Woodbury Salterton Exeter EX5 1PY | Devon | South West | England |  | 302332 | 89045 | East Devon District Council | 13/1578/MFUL | [5 empty] | 2013-07-18 | [6 empty] | 2013-11-18 |  |  |  |  | 2014-03-01 | 2015-08-15
C2160 | 378 | 2015-09-28 | Clean Power Properties | Willowbrook | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Willowbrook East Industrial Estate, Shelton Road, Corby, Northamptonshire | Northamptonshire | East Midlands | England |  | 490943 | 290854 | Northamptonshire County Council | 13/00079/WASFUL | [5 empty] | 2013-09-16 | [6 empty] | 2014-02-07
C2170 | 379 | 2018-09-20 | Ylem Energy | Airfield Farm - AD | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Down Ampney Airfield, Down Ampney, Cirencester, Gloucestershire, GL7 5PL | Gloucestershire | South West | England | GL7 5PL | 411200 | 196800 | Cotswold District Council | 13/04090/FUL | [5 empty] | 2013-09-20 | [6 empty] | 2013-12-23
C2173 | 380 | 2018-10-30 | Evercreech Renewable Energy | Evercreech Junction - AD (food and farm waste) | Anaerobic Digestion |  |  | 4.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Unit 22, Evercreech Junction, Shepton Mallet | Somerset | South West | England | BA4 6NA | 363915 | 136582 | Somerset County Council | PL\2477\13 | [5 empty] | 2013-10-03 | [6 empty] | 2013-12-16
C2367 | 381 | 2016-05-17 | Private Developer | Wothersome Grange Farm House AD - crops | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wothersome Grange Farm House, Wothersome Grange, Thorner Lane, Bramham, Wetherby | West Yorkshire | Yorkshire and Humber | England | LS23 6LY | 439943 | 442482 | Leeds City Council | 13/04884/FU | [5 empty] | 2013-11-07 | [6 empty] | 2013-12-23 |  |  |  |  | 2014-09-01 | 2015-12-03
C2531 | 382 | 2020-05-27 | Kelda Water Services | Knostrop WWTW AD | Anaerobic Digestion |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Knostrop Sewage Treatment Works Knowsthorpe Lane Leeds LS9 0PJ | West Yorkshire | Yorkshire and Humber | England |  | 432562 | 431608 | Leeds City Council | 13/05378/FU | [5 empty] | 2013-12-11 | [6 empty] | 2014-04-22 |  |  |  |  | 2017-06-08 | 2019-07-11
C2553 | 383 | 2018-09-20 | Ylem Energy | Houghton Lodge Farm - AD - farm waste | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Houghton Lodge Farm, Houghton Lane, Houghton On The Hill, Leicestershire | Leicestershire | East Midlands | England | LE7 9GB | 466380 | 302338 | Harborough District Council | 13/01901/FUL | [5 empty] | 2014-01-02 | [6 empty] | 2014-03-18
IF1211 | 384 | 2017-01-16 | DJ AND SJ RECYCLING | Land South East Of Water Treatment Works Bridge End | Anaerobic Digestion |  |  | 1.487 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Hexham Northumberland | Northumberland | North East | England |  | 394860 | 564306 | Northumberland County Council | 12/03802/RENE | [5 empty] | 2012-12-31 | [6 empty] | 2013-04-10 |  |  |  |  | 2014-12-15 | 2015-12-15
B0596 | 385 | 2015-08-03 | B F BIO GAS | Teeside Green Energy Plant (Waste AD) | Anaerobic Digestion |  |  | 4.8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Forty Foot Road, Teeside | Cleveland | North East | England |  | 448771 | 520961 | Middlesbrough Council | M/FP/0216/11/P | [5 empty] | 2011-02-28 | [6 empty] | 2011-07-11 |  |  |  |  | 2013-04-25 | 2015-02-20
AA153 | 386 | 2018-10-03 | Severn Trent (formerly Agrivert) | Crowmarsh Battle Farm (Farm AD) | Anaerobic Digestion |  |  | 2.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Preston Crowmarsh, South Oxfordshire | Oxfordshire | South East | England |  | 462191 | 190619 | South Oxfordshire District Council | P10/W0877/CM | [5 empty] | 2010-06-15 | [6 empty] | 2011-03-30 | [5 empty] | 2013-05-17
EN00280 | 387 | 2018-09-20 | Scottish and Southern Energy (SSE) | Great Glen Scheme | Large Hydro |  |  | 36 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Dundreggan | Highland | Scotland | Scotland |  | 235700 | 815600 | Highland Council | [18 empty] | 1956-01-01 | 1957-01-01
N00010H | 388 | 2009-07-17 | Scottish and Southern Energy (SSE) | Glendoe Hydro Scheme | Large Hydro |  |  | 100 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Western Monadhliath Mountains, East of Fort Augustus, | Highland | Scotland | Scotland |  | 239200 | 809000 | Scottish Government (S36) | IN2003459 | [5 empty] | 2003-05-01 | [6 empty] | 2005-07-28 |  |  |  |  | 2006-05-01 | 2008-12-01
N00013H | 389 | 2005-05-12 | RWE npower | Stronelarig Hydro Scheme | Large Hydro |  |  | 10.7 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Stronelairg Whitebridge Inverness | Highland | Scotland | Scotland |  | 253500 | 806500 | Highland Council | IN2003700 | [6 empty] | 2005-05-12
N00026H | 390 | 2006-05-12 | Scottish and Southern Energy (SSE) | Fasnakyle Hydro Extension | Large Hydro |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fasnakyle Power Station Cannich Inverness-shire | Highland | Scotland | Scotland |  | 231850 | 829750 | Highland Council | IN2003917 | [5 empty] | 2003-09-04 | [6 empty] | 2004-04-01 |  |  |  |  | 2006-05-01 | 2006-08-01
N0021H | 391 | 2018-04-04 | Hydro Plan (on behalf of Alcan) | Kinlochleven Hydro Power Station | Large Hydro |  |  | 19.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kinlochleven | Highland | Scotland | Scotland |  | 218729 | 762021 | Highland Council | [19 empty] | 1909-01-01
EN00014 | 393 | 2006-04-04 | Scottish and Southern Energy (SSE) | Gaur | Large Hydro |  |  | 6.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Gaur | Tayside | Scotland | Scotland |  | 246415 | 756890 | Perth and Kinross Council | [19 empty] | 1953-01-01
EN00016 | 394 | 2006-04-04 | Scottish and Southern Energy (SSE) | Pitlochry | Large Hydro |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pitlochry | Tayside | Scotland | Scotland |  | 293515 | 757730 | Perth and Kinross Council | [19 empty] | 1950-01-01
EN00049 | 395 | 2006-04-03 | Scottish and Southern Energy (SSE) | Loch Gair | Large Hydro |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Gair | Strathclyde | Scotland | Scotland |  | 192865 | 691305 | Argyll and Bute Council | [19 empty] | 1961-01-01
EN00051 | 396 | 2006-04-03 | Scottish and Southern Energy (SSE) | Sron Mor | Large Hydro |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sron Mor | Highland | Scotland | Scotland |  | 264850 | 798415 | Highland Council | [19 empty] | 1957-01-01
EN00052 | 397 | 2010-03-03 | Scottish and Southern Energy (SSE) | Striven | Large Hydro |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Striven | Strathclyde | Scotland | Scotland |  | 205595 | 683990 | Argyll and Bute Council | [19 empty] | 1951-01-01
EN00053 | 398 | 2006-04-03 | Scottish and Southern Energy (SSE) | Aigas | Large Hydro |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Aigas | Highland | Scotland | Scotland |  | 247395 | 843655 | Highland Council | [19 empty] | 1962-01-01
EN00054 | 399 | 2006-04-03 | Scottish and Southern Energy (SSE) | Kilmorack | Large Hydro |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kilmorack | Highland | Scotland | Scotland |  | 249410 | 844225 | Highland Council | [19 empty] | 1962-01-01
EN00057 | 400 | 2006-04-03 | Scottish and Southern Energy (SSE) | Orrin | Large Hydro |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Highland | Highland | Scotland | Scotland |  | 246905 | 851695 | Highland Council | [19 empty] | 1959-01-01
EN00072 | 401 | 2006-04-03 | Scottish and Southern Energy (SSE) | Tor Achilty | Large Hydro |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Highland | Highland | Scotland | Scotland |  | 244625 | 854520 | Highland Council | [19 empty] | 1954-04-01
EN00074 | 402 | 2006-04-04 | Scottish and Southern Energy (SSE) | Ceannacroc | Large Hydro |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ceannocroc | Highland | Scotland | Scotland |  | 222745 | 810690 | Highland Council | [19 empty] | 1956-01-01
EN00075 | 403 | 2006-04-04 | Scottish and Southern Energy (SSE) | Foyers Falls | Large Hydro |  |  | 5.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Foyers Falls | Highland | Scotland | Scotland |  | 249845 | 820010 | Highland Council | [19 empty] | 1968-01-01
EN00076 | 404 | 2006-04-04 | Scottish and Southern Energy (SSE) | Invergarry | Large Hydro |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Invergarry | Highland | Scotland | Scotland |  | 231930 | 801320 | Highland Council | [19 empty] | 1956-01-01
EN00077 | 405 | 2006-04-04 | Scottish and Southern Energy (SSE) | Livishie | Large Hydro |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Livishie | Highland | Scotland | Scotland |  | 240245 | 817495 | Highland Council | [19 empty] | 1962-01-01
EN00078 | 406 | 2009-04-22 | Scottish and Southern Energy (SSE) | Cassley | Large Hydro |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Invercassley | Highland | Scotland | Scotland |  | 247325 | 901540 | Highland Council | [19 empty] | 1959-01-01
EN00081 | 407 | 2009-04-22 | Scottish and Southern Energy (SSE) | Cashlie | Large Hydro |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cashlie | Tayside | Scotland | Scotland |  | 248530 | 741735 | Perth and Kinross Council | [19 empty] | 2004-09-01
AA203 | 408 | 2016-04-04 | Scottish and Southern Energy (SSE) | Kildermorie Estate | Large Hydro |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Kildermorie Estate, near Alness, Ross-shire | Highland | Scotland | Scotland |  | 245987 | 880074 | Scottish Government (S36) | [6 empty] | 2009-12-15 | [6 empty] | 2010-09-10
B0049 | 410 | 2018-04-04 | Green Highland Renewables | Loch Eilde Mor Hydro (Kinlochleven extension) | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Eilde Mor dam , Kinlochleven | Highland | Scotland | Scotland |  | 221625 | 763589 | Scottish Government (S36) | [6 empty] | 2008-01-03 | [6 empty] | 2011-07-22 |  |  |  |  | 2016-02-25 | 2017-10-06
C3207 | 411 | 2016-04-04 | RWE Innogy UK | River Pattack Hydro Scheme | Large Hydro |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Powerhouse Building On The Shore Of Loch Laggan, Kinloch Laggan, Newtonmore | Highland | Scotland | Scotland |  | 252740 | 788520 | Highland Council | 14/02344/FUL | [5 empty] | 2014-06-20 | [6 empty] | 2015-07-28 |  |  |  | 2018-07-28
A0022 | 412 | 2019-04-29 | Scottish Enterprise/SSE | Hunterston | Battery |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Caledonia Road Lochshore Ind Est, Glengarnock, Beith, Strathclyde. KA14 3DD | Strathclyde | Scotland | Scotland | KA14 3DD | 232119 | 653198 | North Ayrshire Council | 08/00576/PPP | [5 empty] | 2008-07-15 | [6 empty] | 2011-03-23 |  |  |  | 2014-03-23
02029H3 | 414 | 2014-12-31 | H20 Power Limited | Beeston Weir Hydro Scheme | Small Hydro |  |  | 1.66 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beeston Weir Holgate Nottingham Nottinghamshire | Nottinghamshire | East Midlands | England |  | 453310 | 335270 | Nottingham City Council | [6 empty] | 1995-01-20 | [6 empty] | 1995-06-21 | [5 empty] | 2000-02-01
10003H3 | 415 | 2009-07-15 | Dwr Cymru Welsh Water | Llyn Brianne Dam | Small Hydro |  |  | 4.35 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Llyn Brianne Hydro Electric Power Station Land adjacent to existing Regulator House Llyn Brianne Dam Dyfed | Dyfed | Wales | Wales |  | 278920 | 248360 | Ceredigion County Council | [6 empty] | 1994-02-08 | [6 empty] | 1994-05-27 | [5 empty] | 1997-02-01
10004H3 | 416 | 2010-03-08 | Dwr Cymru Welsh Water | Elan Valley Hydro Scheme | Small Hydro |  |  | 2.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Elan Valley Reservoir Near Rhayader Powys | Powys | Wales | Wales |  | 290000 | 267500 | Powys County Council | [6 empty] | 1994-02-16 | [6 empty] | 1996-05-30 | [5 empty] | 1997-05-01
A0092 | 419 | 2010-04-30 |  | Turret water treatment works | Small Hydro |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | outside Crieff in Pertshire | Tayside | Scotland | Scotland |  | 286500 | 721600 | Perth and Kinross Council | [19 empty] | 1952-01-01
EN00272 | 420 | 2012-12-07 | Npower Renewables | Allt Hallater Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Allt Hallater, Glen Kinglass Loch. Etive Taynuilt Argyll | Strathclyde | Scotland | Scotland |  | 213500 | 739500 | Argyll and Bute Council | 04/00219/ELSE36 | [5 empty] | 2004-01-30 |  | 2005-02-28
EN00285 | 421 | 2009-07-03 | Green Power | Inverfarigaig | Small Hydro |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Inverfarigaig, near Foyers | Highland | Scotland | Scotland |  | 252100 | 823700 | Highland Council | [19 empty] | 1980-01-01
N00001H | 424 | 2006-05-10 | Scottish and Southern Energy (SSE) | Kingairloch | Small Hydro |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Aber Highlands | Highland | Scotland | Scotland |  | 183600 | 753300 | Highland Council | LO200298 | [5 empty] | 2002-03-19 | [6 empty] | 2003-03-26 | [5 empty] | 2005-05-01
N00008H | 425 | 2008-10-23 | RWE npower | Douglas Water Hydro | Small Hydro |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Near Inverbeg Argyll and Bute | Strathclyde | Scotland | Scotland |  | 204559 | 706950 | Argyll and Bute Council | 03/01360/GDCON | [5 empty] | 2003-07-17 | [6 empty] | 2005-11-17 |  |  |  |  | 2007-06-01 | 2008-05-01
N00023H | 426 | 2009-11-23 | RWE npower | Inverlael Hydro | Small Hydro |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Broom Near Ullapool | Highland | Scotland | Scotland |  | 218650 | 885650 | Highland Council | 05/00206/FULRC | [5 empty] | 2005-03-14 | [6 empty] | 2007-07-04 |  |  |  |  | 2008-09-01 | 2009-08-05
N00051H | 428 | 2010-10-05 | RWE npower | River E Hydro Scheme | Small Hydro |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | River E Loch Mhor Loch Ness | Highland | Scotland | Scotland |  | 252100 | 816300 | Highland Council | IN2003978 | [5 empty] | 2002-12-20 | [6 empty] | 2005-05-23 | [5 empty] | 2007-11-01
N0050H | 429 | 2011-06-06 | Innerhadden Hydro | Innerhadden Burn Hydro | Small Hydro |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 2 kilometres south east of Kinloch Rannoch | Tayside | Scotland | Scotland |  | 265950 | 750850 | Perth and Kinross Council | [6 empty] | 2005-12-06 | [6 empty] | 2008-04-01 | [5 empty] | 2011-02-01
S0009H2 | 430 | 2008-04-16 | Bolfracks Estate | Urlar Hydro Scheme | Small Hydro |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Aberfeldy | Tayside | Scotland | Scotland |  | 284800 | 748800 | Perth and Kinross Council | [7 empty] | 2008-04-16
S0010H2 | 431 | 2005-11-22 | Highland Light and Power | Shieldaig/Slattadale Hydro Scheme | Small Hydro |  |  | 3.55 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Achnasheen | Highland | Scotland | Scotland |  | 183700 | 869700 | Highland Council | RC/2003/401 | [5 empty] | 2003-05-05 |  | 2004-04-03
S0016H1 | 433 | 2004-08-06 | NORWEB Hydro Power | Inverbroom Hydro Project | Small Hydro |  |  | 3.17 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Inverbroom Estate | Highland | Scotland | Scotland |  | 219200 | 878900 | Highland Council | [8 empty] | 2004-08-06
S0020H1 | 434 | 2009-12-10 | Scottish Hydro-Electric plc | Cuileig Hydro Scheme | Small Hydro |  |  | 3.3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Abhainn Cuileig Braemore Junction Ross and Cromarty | Highland | Scotland | Scotland |  | 219300 | 878900 | Highland Council | [6 empty] | 1998-10-09 | [6 empty] | 2000-03-01 | [5 empty] | 2002-02-15
S0025H1 | 435 | 2006-05-08 | RWE npower | Garrogie Hydro Scheme | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fechlin River Near Whitebridge Invernesshire | Highland | Scotland | Scotland |  | 250100 | 813300 | Highland Council | IN2001964 | [5 empty] | 2001-11-20 | [6 empty] | 2003-06-01 | [5 empty] | 2005-03-01
C2077 | 436 | 2015-05-29 | RWE | Conwy Falls | Large Hydro |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Betws-y-Coed | Gwynedd | Wales | Wales |  | 279800 | 354500 | Snowdonia National Park Authority | NP4/26/323 | [5 empty] | 2015-04-23 |  | 2016-03-08
B0878 | 437 | 2014-02-24 | Inver Hydro LLP | Inver Hydro | Small Hydro |  |  | 1.97 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Inver Estate Isle Of Jura Argyll PA60 7XX | Strathclyde | Scotland | Scotland |  | 144165 | 671452 | Argyll and Bute Council | 11/00890/PP | [5 empty] | 2011-06-02 | [6 empty] | 2011-08-11 | [5 empty] | 2012-08-30
C0999 | 438 | 2017-12-19 | Gilkes Energy | Loch An Laoigh Hydro | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Loch An Laoigh Attadale Estate Strathcarron | Highland | Scotland | Scotland |  | 201607 | 839621 | Highland Council | 12/04688/FUL | [5 empty] | 2012-12-19 | [6 empty] | 2013-10-09 |  |  |  |  | 2016-04-15 | 2017-12-07
C1023 | 439 | 2017-10-17 | The West Highland Woodlands | Lower Suileag hydro | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land 150M East Of Fassfern House Fassfern Kinlocheil | Highland | Scotland | Scotland |  | 205628 | 778554 | Highland Council | 13/00031/FUL | [5 empty] | 2013-01-08 | [6 empty] | 2013-12-03
C1614 | 440 | 2019-05-30 | Hydroplan | Allt Beithe | Small Hydro |  |  | 1.3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land 2000M NE Of Old Stables Loch Merkland Achfary | Highland | Scotland | Scotland |  | 241636 | 923168 | Highland Council | 13/02386/FUL | [5 empty] | 2013-07-09 | [6 empty] | 2015-09-03 |  |  |  | 2018-09-03
C1615 | 441 | 2019-05-30 | Hydroplan | Allt a Chraois Hydroelectric Scheme | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land 1600M SE Of Gobernuisgach Lodge Gobernuisgach Altnaharra | Highland | Scotland | Scotland |  | 255229 | 911716 | Highland Council | 13/02382/FUL | [5 empty] | 2013-07-09 | [6 empty] | 2015-09-03 |  |  |  | 2018-09-03
C1710 | 442 | 2017-01-17 | DHG Hydro | Leacann Hydro | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land North Of Brenchoille Farm Furnace Inveraray Argyll And Bute PA32 8XN | Strathclyde | Scotland | Scotland |  | 202172 | 702341 | Argyll and Bute Council | 13/01481/PP | [5 empty] | 2013-07-29 | [6 empty] | 2013-12-06 |  |  |  |  | 2015-03-20 | 2016-08-15
IM0049 | 443 | 2019-05-30 | Hydroplan | Abhainn Srath Coir an Easaidh on the Reay Forest Estate, Sutherland. | Small Hydro |  |  | 1.25 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Abhainn Srath Hydro, Reay Forest Estate, Lairg, Sutherland, IV27 4NZ | Highland | Scotland | Scotland |  | 243457 | 941822 | Highland Council | 13/02384/FUL | [5 empty] | 2013-07-09 | [6 empty] | 2015-09-04 |  |  |  | 2018-09-04
C0996 | 444 | 2017-12-19 | Gilkes Energy | Uisge Dubh Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Uisge Dubh Attadale Estate Strathcarron IV54 8YR | Highland | Scotland | Scotland |  | 200062 | 836426 | Highland Council | 12/04687/FUL | [5 empty] | 2012-12-19 | [6 empty] | 2013-08-28 |  |  |  |  | 2016-04-15 | 2017-12-07
B1276 | 445 | 2014-03-31 | Gilkes Energy | Ederline Hydro | Small Hydro |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ederline, Loch Awe | Strathclyde | Scotland | Scotland |  | 192775 | 703372 | Argyll and Bute Council | 09/00526/ELSE36 | [5 empty] | 2009-04-20 | [6 empty] | 2009-06-02 |  |  |  |  | 2011-05-01 | 2014-01-31
C1443 | 446 | 2019-02-19 | Luss Estates | Glen Luss Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Glen Luss Hydro, Glen Luss, Luss | Argyll and Bute | Scotland | Scotland | G83 8TU | 236213 | 692906 | Loch Lomond and The Trossachs National Park Authority | 2013/0121/DET | [5 empty] | 2013-05-30 | [6 empty] | 2013-11-14 |  |  |  | 2016-11-14
B0233 | 447 | 2016-08-25 | Gilkes Energy | River Lochy Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | River Lochy Hydro Inverlochy Dalmally Argyll And Bute | Strathclyde | Scotland | Scotland |  | 219760 | 727460 | Argyll and Bute Council | 13/01953/PP | [5 empty] | 2013-10-03 | [6 empty] | 2013-12-19 |  |  |  |  | 2015-03-13 | 2016-08-16
C0998 | 448 | 2017-07-19 | Gilkes Energy | River Taodail Hydro | Small Hydro |  |  | 1.35 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At River Taodail Attadale Strathcarron | Highland | Scotland | Scotland |  | 194657 | 842146 | Highland Council | 12/04685/FUL | [5 empty] | 2012-12-19 | [6 empty] | 2013-07-15 |  |  |  |  | 2015-08-19 | 2017-01-15
B0588 | 449 | 2017-04-18 | RWE Npower Renewables | River Braan Hydro (Re-submission) | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Near the village of Trochry in Perthshire | Tayside | Scotland | Scotland |  | 299506 | 740918 | Perth and Kinross Council | 13/01698/FLL | [5 empty] | 2013-09-23 | [6 empty] | 2014-04-17 |  |  |  | 2017-04-17
B0231 | 450 | 2016-10-26 | Gilkes Energy/Broadland Energy | Donich Water Hydro | Small Hydro |  |  | 1.35 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Goil | Argyll and Bute | Scotland | Scotland |  | 221500 | 701500 | Loch Lomond and The Trossachs National Park Authority | 2013/0120/DET | [5 empty] | 2013-05-28 | [6 empty] | 2014-09-12 |  |  |  | 2017-09-12 | 2015-10-01 | 2016-09-08
C0551 | 451 | 2012-10-03 | Achomer Energy | Ardtalnaig Hydro Scheme | Small Hydro |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Ardtalnaig, Aberfeldy, Tayside, PH15 2HX | Tayside | Scotland | Scotland |  | 268858 | 739100 | Perth and Kinross Council | 11/02163/FLL | [5 empty] | 2012-01-23 | 2012-03-06
C0701 | 452 | 2015-08-24 | Ventient (formerly Infinis) | Glen Fyne 'Merk' Hydro | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Upper Glen Fyne Woodland Cladich Argyll And Bute | Strathclyde | Scotland | Scotland |  | 209952 | 709286 | Argyll and Bute Council | 10/02163/PP | [5 empty] | 2010-12-22 | [6 empty] | 2011-05-16 |  |  |  | 2016-05-16 | 2013-05-01 | 2015-08-24
C1217 | 453 | 2016-12-15 | Edradynate | Beinn Eagagach Hydro | Small Hydro |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beinn Eagagach Hydro Scheme Edradynate Aberfeldy | Tayside | Scotland | Scotland |  | 288377 | 751719 | Perth and Kinross Council | 13/00466/FLL | [5 empty] | 2013-03-15 | [6 empty] | 2013-12-24 |  |  |  |  | 2015-02-27 | 2016-01-29
C1887 | 454 | 2017-10-20 | Green Highland Renewables (on behalf of Highland Hydro Services) | Allt Garbh hydro | Small Hydro |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land 1540M SW Of Affric Lodge Cannich | Highland | Scotland | Scotland |  | 218018 | 822389 | Highland Council | 13/03022/FUL | [5 empty] | 2013-08-16 | [6 empty] | 2013-12-16 |  |  |  |  | 2016-04-07 | 2017-08-01
B0228 | 457 | 2012-05-11 | Green Highland Renewables | Allt Choire a Bhalachain Hydro | Small Hydro |  |  | 1.3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Glen Garry | Highland | Scotland | Scotland |  | 212500 | 799500 | [8 empty] | 2012-05-02
S0015H1 | 459 | 2005-03-30 | Highland Light and Power | Sheildaig Hydro Project | Small Hydro |  |  | 2.1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Gairloch, Highland | Highland | Scotland | Scotland |  | 181000 | 877855 | Highland Council | [6 empty] | 2003-05-05 |  | 2004-03-16
EN00100 | 460 | 2011-06-07 | Npower Renewables | Carnoch Hydro | Small Hydro |  |  | 1.35 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | East of Strontian Ardgour Lochaber | Highland | Scotland | Scotland |  | 185300 | 760500 | Highland Council | [6 empty] | 2005-10-06 | [6 empty] | 2007-10-01 | [5 empty] | 2009-07-01
EN00010 | 461 | 2006-04-03 | Scottish and Southern Energy (SSE) | Kilmelfort | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kilmelfort | Strathclyde | Scotland | Scotland |  | 184035 | 714385 | Argyll and Bute Council | [19 empty] | 1956-01-01
EN00011 | 462 | 2015-12-17 | Scottish and Southern Energy (SSE) | Dalchonzie | Small Hydro |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dalchonzie | Tayside | Scotland | Scotland |  | 274035 | 721990 | Perth and Kinross Council | [19 empty] | 1958-01-01
EN00012 | 463 | 2006-04-04 | Scottish and Southern Energy (SSE) | Lednock | Small Hydro |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lednock | Tayside | Scotland | Scotland |  | 276730 | 722040 | Perth and Kinross Council | [19 empty] | 1961-01-01
EN00013 | 464 | 2006-04-04 | Scottish and Southern Energy (SSE) | Lubreoch | Small Hydro |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lubreoch | Tayside | Scotland | Scotland |  | 245310 | 741720 | Perth and Kinross Council | [19 empty] | 1958-01-01
EN00015 | 465 | 2006-04-04 | Scottish and Southern Energy (SSE) | Loch Ericht | Small Hydro |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loch Ericht | Tayside | Scotland | Scotland |  | 255340 | 772785 | Perth and Kinross Council | [19 empty] | 1962-01-01
EN00050 | 466 | 2006-04-03 | Scottish and Southern Energy (SSE) | Lussa | Small Hydro |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lussa | Strathclyde | Scotland | Scotland |  | 164170 | 688680 | Argyll and Bute Council | [19 empty] | 1952-01-01
EN00055 | 467 | 2006-04-03 | Scottish and Southern Energy (SSE) | Mullardoch Tunnel | Small Hydro |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Highland | Highland | Scotland | Scotland |  | 222860 | 831415 | Highland Council | [19 empty] | 1955-01-01
EN00056 | 468 | 2006-04-27 | Scottish and Southern Energy (SSE) | Achanalt | Small Hydro |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Highland | Highland | Scotland | Scotland |  | 225895 | 861615 | Highland Council | [19 empty] | 1956-01-01
EN00073 | 469 | 2006-04-04 | Scottish and Southern Energy (SSE) | Mucomir | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Mucomir | Highland | Scotland | Scotland |  | 218350 | 783900 | Highland Council | [19 empty] | 1962-01-01
EN00079 | 470 | 2006-04-04 | Scottish and Southern Energy (SSE) | Lairg | Small Hydro |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lairg | Highland | Scotland | Scotland |  | 257505 | 906940 | Highland Council | [19 empty] | 1959-01-01
EN00080 | 471 | 2006-04-04 | Scottish and Southern Energy (SSE) | Cuaich | Small Hydro |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cuaich | Highland | Scotland | Scotland |  | 265640 | 787175 | Highland Council | [19 empty] | 1959-01-01
EN00305 | 472 | 2012-10-03 | Shawater | Innerwick Hydro | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glen Lyon, Perth and Kinross | Tayside | Scotland | Scotland |  | 258577 | 747751 | Perth and Kinross Council | 07/00001/HYDRO | [5 empty] | 2007-06-20 | [6 empty] | 2008-10-15 | [5 empty] | 2010-10-13
A0270 | 473 | 2013-04-29 | Osspower | Allt Fionn - resubmission | Small Hydro |  |  | 2.1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Nr Inverarnan, Crianlarich, Stirling | Stirling | Scotland | Scotland |  | 233200 | 720700 | Scottish Government (S36) | [6 empty] | 2009-07-21 | [6 empty] | 2010-04-24 |  |  |  |  | 2012-04-01 | 2012-07-27
A0356 | 474 | 2017-03-22 | Darroch Power Limited | Derrydarroch | Small Hydro |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glen Falloch Estate near Crianlarich, Stirlingshire | Highland | Scotland | Scotland |  | 212176 | 775418 | Scottish Government (S36) | [6 empty] | 2009-07-21 | [6 empty] | 2010-04-24 |  |  |  |  | 2015-02-11 | 2015-12-15
A0392 | 475 | 2016-08-24 | RWE Npower Renewables | Cia Aig Hydro | Small Hydro |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Achnacarry, Highland | Highland | Scotland | Scotland |  | 217196 | 788748 | Scottish Government (S36) | [6 empty] | 2009-09-04 | [6 empty] | 2010-06-26 |  |  |  |  | 2012-12-07 | 2016-08-24
AA844 | 476 | 2017-11-21 | Achomer Energy | Ardtalnaig Hydro Scheme (resubmission) | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ardtalnaig, Aberfeldy, Tayside, PH15 2HX | Tayside | Scotland | Scotland |  | 268858 | 739100 | Perth and Kinross Council | 12/01113/FLL | [5 empty] | 2012-07-12 | [6 empty] | 2012-12-03 |  |  |  |  | 2015-05-15 | 2017-07-15
B0495 | 477 | 2016-07-12 | Green Highland Renewables (on behalf of North Chesthill Estate) | Invervar Hydro - resubmission | Small Hydro |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Invervar, Glen Lyon Perth and Kinross | Tayside | Scotland | Scotland |  | 266469 | 748148 | Perth and Kinross Council | 12/00248/FLL | [5 empty] | 2012-02-14 | [6 empty] | 2012-04-24 |  |  |  |  | 2014-11-15 | 2015-11-15
C0093 | 478 | 2016-04-04 | Bruar Hydro / Gilkes | Bruar Hydro Scheme | Small Hydro |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pitagowan, Blair Atholl, Pitlochry, Tayside | Tayside | Scotland | Scotland | PH18 5TW | 282340 | 772772 | Perth and Kinross Council | 12/00009/FLL | [5 empty] | 2012-02-10 | [6 empty] | 2012-08-16 |  |  |  |  | 2014-03-01 | 2015-12-20
C0137 | 479 | 2016-12-20 | Garbhaig Hydro Power Co Ltd | Garbhaig Hydro Scheme | Small Hydro |  |  | 1.995 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | S/O Garbaig House, Slattadale, Anchnasheen, Highlands, IV22 2HW | Highland | Scotland | Scotland |  | 190263 | 871166 | Highland Council | 12/01202/FUL | [5 empty] | 2012-04-25 | [6 empty] | 2012-08-24 |  |  |  |  | 2015-03-16 | 2016-09-07
EN00101 | 480 | 2015-06-03 | Green Highland Renewables | Chonais Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Near Craig Achnashellach Ross and Cromarty | Highland | Scotland | Scotland |  | 204700 | 849300 | Highland Council | 07/00466/S36RC | [5 empty] | 2007-04-30 | [6 empty] | 2009-03-12 |  |  |  |  | 2013-11-30 | 2015-01-15
EN00614 | 482 | 2013-04-29 | Ardtornish Estate | Ardtornish Estate-Upgrade to existing | Small Hydro |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ardtornish Estate Morvern Peninsula River Ranoch Oban PA34 5DF | Highland | Scotland | Scotland |  | 173510 | 746790 | Scottish Government (S36) | EA/2008/2204 - 08/00317/S36LO | [5 empty] | 2008-09-10 | [6 empty] | 2009-05-18 |  |  |  |  | 2011-06-01 | 2012-12-20
N00011H | 483 | 2012-08-15 | Green Highland Renewables | Invervar Hydro | Small Hydro |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Invervar, Glen Lyon Perth and Kinross | Tayside | Scotland | Scotland |  | 266500 | 748500 | Perth and Kinross Council | 07/00004/HYDRO | [5 empty] | 2007-08-07 | [6 empty] | 2008-11-25
N00024H | 484 | 2014-03-26 | RWE npower | Maldie Burn | Small Hydro |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Maldie Burn Near Kylesku NW Sutherland | Highland | Scotland | Scotland |  | 225150 | 934050 | Highland Council | 09/00250/S36SU | [5 empty] | 2009-06-11 | [6 empty] | 2011-01-17 |  |  |  |  | 2012-05-16 | 2014-03-01
N00027H | 485 | 2013-04-05 | RWE npower | Black Rock | Small Hydro |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glenglass, nr Evanton | Highland | Scotland | Scotland |  | 259900 | 866800 | Highland Council | [6 empty] | 2006-12-20 | [6 empty] | 2008-12-04 |  |  |  |  | 2010-07-01 | 2012-06-01
N00050H | 486 | 2012-12-04 | RWE npower | River Braan Hydro | Small Hydro |  |  | 3.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Near the village of Trochry in Perthshire | Tayside | Scotland | Scotland |  | 299500 | 741500 | Perth and Kinross Council | 05/00001/HYDRO | [6 empty] | 2012-12-04
S0003H3 | 487 | 2016-11-24 | Gilkes Energy | Ben Glas | Small Hydro |  |  | 1.3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Nr Inverarnan, Crianlarich, Stirling | Stirling | Scotland | Scotland |  | 232100 | 718600 | Scottish Government (S36) | [6 empty] | 2009-07-21 | [6 empty] | 2010-04-24 |  |  |  |  | 2015-08-19 | 2016-09-15
B0227 | 488 | 2017-02-22 | Green Highland Renewables | Allt Ladaidh Hydro | Small Hydro |  |  | 1.3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glen Garry | Highland | Scotland | Scotland |  | 222875 | 800386 | Highland Council | 12/03914/FUL | [5 empty] | 2012-10-10 | [6 empty] | 2013-01-17 |  |  |  |  | 2015-02-15 | 2016-10-15
B0590 | 489 | 2019-12-11 | RWE Npower Renewables / Innogy | Allt na Moine | Small Hydro |  |  | 1.95 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South East Of Spindrift (Allt Na Moine) Callakille Applecross | Highland | Scotland | Scotland |  | 169268 | 854081 | Highland Council | 14/00150/FUL | [5 empty] | 2014-01-16 | [6 empty] | 2014-07-28
IM0064 | 490 | 2014-08-14 | Private Developer | Badachro hydro scheme | Small Hydro |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land Between Loch Braigh Horrisdale And River Badachro Gairloch | Highland | Scotland | Scotland |  | 179040 | 870370 | Highland Council | 14/00516/FUL | [5 empty] | 2014-02-17 | 2014-07-04
C3238 | 491 | 2017-02-21 | Badachro Hydro Limited | Badachro hydro scheme - resubmission | Small Hydro |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land Between Loch Braigh Horrisdale And River Badachro Gairloch | Highland | Scotland | Scotland |  | 179040 | 871370 | Highland Council | 14/02596/FUL | [5 empty] | 2014-07-07 | [6 empty] | 2014-09-30 |  |  |  | 2017-09-30 | 2014-06-30 | 2016-12-21
EN00302 | 492 | 2017-02-22 | Green Highland Renewables | Chaorach Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Allt Coire Chaorach, East of Crianlarich in Loch Lomond and the Trossachs National Park | Stirling | Scotland | Scotland |  | 246250 | 725250 | Scottish Government (S36) | [6 empty] | 2007-04-02 | [6 empty] | 2008-12-04 |  |  |  |  | 2015-05-15 | 2016-10-15
C1529 | 493 | 2018-04-04 | RWE Npower Renewables | Grudie | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | S/O Bridge Of Grudie, Loch Maree, Anchnasheen, Highlands, IV22 | Highland | Scotland | Scotland | IV22 2HL | 196459 | 867347 | Highland Council | 13/02171/FUL | [5 empty] | 2013-06-20 | [6 empty] | 2014-09-17 |  |  |  |  | 2016-02-01 | 2017-09-29
C2700 | 494 | 2017-01-17 | DHG Hydro | Langwell Estate hydro scheme | Small Hydro |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ruith Chnoc | Highland | Scotland | Scotland | IV26 2T | 218915 | 901914 | Highland Council | 14/00371/FUL | [5 empty] | 2014-01-29 | [6 empty] | 2014-08-22 |  |  |  |  | 2015-06-15 | 2016-12-15
C3024 | 495 | 2018-10-30 | Corrour Property Company | Ghuilbinn Hydro Scheme | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ghuilbinn Hydro Scheme Corrour Estate | Highland | Scotland | Scotland | PH22 1LB | 243130 | 780340 | Highland Council | 14/01646/FUL | [5 empty] | 2014-04-25 | [6 empty] | 2014-09-09 |  |  |  |  | 2015-09-15 | 2017-10-01
C3350 | 496 | 2017-05-16 | Nevis Range Development Company | Nevis Range | Small Hydro |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Allt Choille-Rais Burn 1900M East Of Top Gondola Station Nevis Range Torlundy Fort William | Highland | Scotland | Scotland |  | 220471 | 776708 | Highland Council | 14/03043/FUL | [5 empty] | 2014-08-13 | [6 empty] | 2014-12-16 |  |  |  |  | 2016-01-05 | 2017-03-16
C3368 | 497 | 2014-12-05 | Green Highland | Abhainn Rath | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Abhainn Rath, Loch Treig, Fort William, Highlands, PH33 | Highland | Scotland | Scotland |  | 228641 | 768161 | Highland Council | 14/03187/FUL | [5 empty] | 2014-08-28 | 2014-11-25
C3369 | 498 | 2017-10-20 | Green Highland Renewables | Abhainn Gleann Nam Fiadh | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Meall Mor 7000m Nw Of Corrour Station, Corrour, Highlands, PH30. | Highland | Scotland | Scotland |  | 230807 | 769237 | Highland Council | 14/03186/FUL | [5 empty] | 2014-08-28 | [6 empty] | 2014-12-22 |  |  |  | 2017-12-22 | 2016-04-07 | 2017-08-01
IM0069 | 500 | 2019-11-20 | Renewable Design & Development Limited | Munerigie HydroPower Scheme | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Land 1740M NE Of Munerigie Munerigie Invergarry | Highland | Scotland | Scotland | IV63 7YN | 226820 | 802600 | Highland Council | 14/01222/FUL | [5 empty] | 2014-04-01 | [6 empty] | 2014-06-30 |  |  |  | 2017-06-30
IM0065 | 502 | 2016-07-12 | Green Highland Renewables | Allt Cheanna Mhuir Hydro | Small Hydro |  |  | 1.25 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 5.36 KM West of Achnasaul, Achnacarry | Highland | Scotland | Scotland |  | 210472 | 791397 | Highland Council | 13/02874/FUL | [5 empty] | 2013-08-08 | [6 empty] | 2013-12-03 |  |  |  |  | 2014-09-07 | 2015-12-15
N00003H | 503 | 2007-05-09 | Innogy | Braevallich | Small Hydro |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Eredine, Braevallich, Loch Awe | Strathclyde | Scotland | Scotland |  | 196657 | 706909 | Argyll and Bute Council | 02/01407/GDCON | [5 empty] | 2002-08-07 | [6 empty] | 2003-03-26 | [5 empty] | 2005-01-01
EN00271 | 504 | 2012-01-25 | Keltneyburn Hydro Ltd | Keltneyburn Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | nr Carse Farm, Aberfeldy, Perthshire, PH15 2JQ | Tayside | Scotland | Scotland |  | 277190 | 748690 | Perth and Kinross Council | [6 empty] | 2004-11-22 | [6 empty] | 2008-09-24 | [5 empty] | 2010-05-01
01002L4 | 505 | 2003-12-09 | Ex Waste Ltd/Combined Landfill Projects Ltd (CLP) | Bellhouse Pit Landfill Scheme | Landfill Gas |  |  | 2.7 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bellhouse Pit , Church Lane , Stanway , Colchester | Essex | Eastern | England |  | 594200 | 223400 | Colchester Borough Council | [6 empty] | 1994-01-06 | [6 empty] | 1994-08-08 | [5 empty] | 1999-01-15
01004L4 | 506 | 2009-08-28 | Aveley Methane Ltd | Sandy Lane Landfill Scheme | Landfill Gas |  |  | 2.34 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sandy Lane Aveley Purflee Essex | Essex | Eastern | England |  | 555800 | 180700 | Thurrock Council | [6 empty] | 1994-03-04 | [6 empty] | 2003-12-09 | [5 empty] | 2006-08-01
01008L4 | 507 | 2011-10-30 | Pioneer Aggregates (UK) Ltd | Brazier Landfill Scheme | Landfill Gas |  |  | 3.88 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ware Quarry, Westmill Road, Ware, Hertfordshire | Hertfordshire | Eastern | England |  | 534100 | 214800 | East Hertfordshire District Council | [6 empty] | 1996-10-10 | [6 empty] | 1997-05-08 | [5 empty] | 1997-12-15
01012L4 | 508 | 2004-09-30 | Gengas Ltd | Lackford Landfill Scheme | Landfill Gas |  |  | 1.17 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bury Road Lackford Suffolk | Suffolk | Eastern | England |  | 580000 | 269300 | St Edmundsbury Borough Council | [6 empty] | 1999-08-24 | [6 empty] | 1999-11-02 | [5 empty] | 2000-04-12
01024L3 | 509 | 2003-12-09 | Renewable Power Generation Ltd | Attlebridge Landfill Site | Landfill Gas |  |  | 1.25 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Hales Waste Control Reepham Road Attlebridge Norfolk | Norfolk | Eastern | England |  | 614800 | 316100 | Broadland District Council | [6 empty] | 1995-03-08 | [6 empty] | 1996-01-22 | [5 empty] | 1997-09-01
01025L4 | 510 | 2013-10-08 | Waste Recycling Group | Aveley Landfill Scheme | Landfill Gas |  |  | 2.12 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sandy Lane Aveley Essex | Essex | Eastern | England |  | 555200 | 180700 | Thurrock Council | [6 empty] | 1998-01-13 | [6 empty] | 1998-06-04 | [5 empty] | 1999-07-20
01026L3 | 511 | 2003-12-09 | Renewable Power Generation Ltd | Elstow Landfill Site | Landfill Gas |  |  | 1.76 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Elstow Landfill Site Wilstead Road Elstow Bedfordshire | Bedfordshire | Eastern | England |  | 504800 | 246100 | Bedford Borough Council | [6 empty] | 1995-01-09 | [6 empty] | 1995-06-23 | [5 empty] | 1996-07-08
01026L4 | 512 | 2011-10-30 | Waste Recycling Group | Ongar Landfill Scheme 2 | Landfill Gas |  |  | 1.77 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | LECA Works, Mill Lane, High Ongar, Essex | Essex | Eastern | England |  | 556200 | 202300 | Epping Forest District Council | [6 empty] | 1997-05-06 | [6 empty] | 1997-07-28 | [5 empty] | 1998-05-01
01027L3 | 513 | 2003-12-09 | Renewable Power Generation Ltd | Sundon Landfill Site | Landfill Gas |  |  | 2.64 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sundon Landfill Site Common Lane Sundon Bedfordshire | Bedfordshire | Eastern | England |  | 503800 | 228300 | Central Bedfordshire Council | [6 empty] | 1994-12-29 | [6 empty] | 1995-06-23 | [5 empty] | 1996-09-01
01031L5 | 514 | 2013-10-08 | Waste Recycling Group | Aveley | Landfill Gas |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sandy Lane, Aveley, Essex | Essex | Eastern | England |  | 555100 | 180700 | Thurrock Council | [6 empty] | 1998-01-13 | [6 empty] | 1998-06-04 | [5 empty] | 1999-07-20
01039L5 | 515 | 2009-12-10 | Waste Recycling Group | Brogborough Phase III | Landfill Gas |  |  | 11 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Woburn Road, Brogborough, Bedfordshire | Bedfordshire | Eastern | England |  | 497000 | 240200 | Central Bedfordshire Council | [6 empty] | 1990-04-19 | [6 empty] | 1990-08-07 | [5 empty] | 2001-04-29
01040L5 | 516 | 2009-12-10 | Waste Recycling Group | Brogborough Phase IV | Landfill Gas |  |  | 11 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Brogborough Landfill, Woburn Road, Brogborough, Bedfordshire | Bedfordshire | Eastern | England |  | 497000 | 240600 | Central Bedfordshire Council | [6 empty] | 1999-01-15 | [6 empty] | 1999-04-01 | [5 empty] | 2000-02-04
01047L5 | 518 | 2010-04-28 | ENERGY DEVELOPMENTS (UK) LTD | Ockendon Area III | Landfill Gas |  |  | 8.48 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Grange Farm, Medebridge Road, Grays, South Ockenden, Essex | Essex | Eastern | England |  | 560900 | 183200 | Thurrock Council | [6 empty] | 1999-12-10 | [6 empty] | 2000-07-19 | [5 empty] | 2002-04-01
01048L4 | 519 | 2010-06-09 | Natural Power | Station Farm Landfill Scheme | Landfill Gas |  |  | 1.96 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Brampton Road Buckden Cambridgeshire | Cambridgeshire | Eastern | England |  | 521000 | 269300 | Huntingdonshire District Council | [6 empty] | 1998-03-12 | [6 empty] | 1998-06-01 | [5 empty] | 1999-09-07
01048L5 | 520 | 2011-02-01 | ENERGY DEVELOPMENTS (UK) LTD | Rainham Phase II | Landfill Gas |  |  | 16.95 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wennington Marshes, Rainham, Essex | Greater London | London | England |  | 552400 | 179100 | Havering London Borough Council | P1275.96 | [5 empty] | 1996-11-08 | [6 empty] | 1999-03-01 | [5 empty] | 2000-04-01
01050L5 | 521 | 2005-08-02 | ENERGY DEVELOPMENTS (UK) LTD | Water Hall Generation Plant | Landfill Gas |  |  | 1.21 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Water Hall Quarry, Lower Hatfield Road, Hertfordshire | Hertfordshire | Eastern | England |  | 529700 | 210000 | East Hertfordshire District Council | 3/99/1721/CM | [5 empty] | 1999-11-19 | [6 empty] | 2000-03-16
01069L4 | 522 | 2009-12-10 | Haul Waste Disposal Ltd | Masons Power Plant Landfill Scheme | Landfill Gas |  |  | 5.48 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Masons Landfill Great Blakenham Suffolk | Suffolk | Eastern | England |  | 611100 | 250100 | Mid Suffolk District Council | [6 empty] | 1997-03-20 | [6 empty] | 1997-06-19 | [5 empty] | 2008-02-26
01070L4 | 523 | 2009-04-22 | Haul Waste Disposal Ltd | Ockendon 'B' Landfill Scheme | Landfill Gas |  |  | 4.45 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Madebridge Road Grays Essex | Essex | Eastern | England |  | 560500 | 182000 | Thurrock Council | [6 empty] | 1997-05-15 | [6 empty] | 1997-06-26 | [5 empty] | 1998-12-09
01099L3 | 524 | 2011-10-30 | Waste Recycling Group | L'Field Stewartby Landfill Site | Landfill Gas |  |  | 10.66 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | L'Field Stewartby Landfill Site, Adjacent to Stewartby Village, Green Lane, Stewartby, Bedfordshire. | Bedfordshire | Eastern | England |  | 501500 | 243300 | Bedford Borough Council | [6 empty] | 1994-03-04 | [6 empty] | 1994-07-15 | [5 empty] | 1998-01-01
01100L3 | 525 | 2011-10-30 | Waste Recycling Group | Dogsthorpe South Landfill Site | Landfill Gas |  |  | 1.89 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dogsthorpe South Landfill Site near Peterborough Cambridgeshire | Cambridgeshire | Eastern | England |  | 520500 | 301900 | Peterborough City Council | [6 empty] | 1994-02-17 | [6 empty] | 1995-05-10 | [5 empty] | 1995-09-01
01107L3 | 526 | 2003-12-09 | Renewable Power Generation Ltd | Foxhall Landfill Site | Landfill Gas |  |  | 1.17 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Foxhall Road Landfill Site Brightwell Suffolk | Suffolk | Eastern | England |  | 623900 | 244000 | Suffolk Coastal District Council | [6 empty] | 1994-08-05 | [6 empty] | 1994-10-17 | [5 empty] | 1996-06-18
02001L5 | 527 | 2009-12-10 | LAFARGE REDLANDS AGGREGATES LTD | Cotesbach Landfill Gas Project | Landfill Gas |  |  | 2.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cotesbach Landfill Site Gibbet Lane Shawell Lutterworth Leicestershire LE17 6AA | Leicestershire | East Midlands | England |  | 453725 | 280820 | Harborough District Council | 1999/1202/03 | [5 empty] | 1999-11-02 | [6 empty] | 2000-03-09 | [5 empty] | 2000-12-22
02003L3 | 528 | 2004-12-20 | Biogeneration / Biffa | Portley Ford Landfill Site | Landfill Gas |  |  | 1.82 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Portley Ford Welford Cold Ashby Northants | Northamptonshire | East Midlands | England |  | 465900 | 277000 | Daventry District Council | [6 empty] | 1994-05-10 | [6 empty] | 1995-02-08 | [5 empty] | 1996-10-01
02005L5 | 529 | 2011-10-30 | Yorkshire Environmental Solutions / Waste Recycling Group | Glapwell | Landfill Gas |  |  | 1.15 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Palterton Lane, Glapwell, Derbyshire | Derbyshire | East Midlands | England |  | 446200 | 367200 | Bolsover District Council | CM5/0202/152 | [5 empty] | 1999-10-11 | [6 empty] | 2000-04-11 | [5 empty] | 2001-04-30
02008L5 | 530 | 2003-01-29 | Colsterworth Energy Ltd | Colsterworth Landfill Gas Project | Landfill Gas |  |  | 2.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Stainby Road, Colsterworth, Lincolnshire | Lincolnshire | East Midlands | England |  | 490500 | 324300 | South Kesteven District Council | [6 empty] | 1999-04-05 | [6 empty] | 2000-01-31 | [5 empty] | 2001-03-31
02019L4 | 531 | 2011-10-30 | Waste Recycling Group | Bradgate Quarry Landfill Gas Scheme | Landfill Gas |  |  | 2.47 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bradgate Quarry Markfield Leicestershire | Leicestershire | East Midlands | England |  | 451300 | 308600 | Highland Council | 1997/1097/4 | [5 empty] | 1997-12-15 | [6 empty] | 1998-02-22 | [5 empty] | 1998-08-01
02020L4 | 532 | 2014-12-19 | Waste Recycling Group | Burntstump Landfill Scheme | Landfill Gas |  |  | 1.8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ollerton Road Nottinghamshire | Nottinghamshire | East Midlands | England |  | 458500 | 350000 | Gedling Borough Council | [19 empty] | 1999-04-15
02021L4 | 533 | 2005-06-29 | Waste Recycling Group | Judkins Landfill Scheme | Landfill Gas |  |  | 2.73 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Judkins Landfill Site Tuttle Hill Nuneaton Warwickshire | Warwickshire | West Midlands | England |  | 435200 | 292800 | Nuneaton and Bedworth Borough Council | [19 empty] | 1999-04-01
02024L4 | 534 | 2010-06-09 | Warren Energy Ltd | Warren Quarry Landfill Gas Scheme | Landfill Gas |  |  | 1.9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Enderby Warren Quarry Harolds Lane Tenderby Leicestershire | Leicestershire | East Midlands | England |  | 453700 | 300300 | Blaby District Council | [6 empty] | 1997-07-31 | [6 empty] | 1997-11-25 | [5 empty] | 1998-11-14
02037L4 | 535 | 2006-05-10 | Hales Waste Control Ltd | Kilsby Landfill Scheme | Landfill Gas |  |  | 1.006 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Grove Farm Kilsby Northamptonshire | Northamptonshire | East Midlands | England |  | 456800 | 269500 | Daventry District Council | DA/97/1083c | [5 empty] | 1997-10-10 | [6 empty] | 1998-02-12 | [5 empty] | 1998-11-05
02042L5 | 536 | 2005-09-29 | Waste Recycling Group | Bletchley Phase II | Landfill Gas |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Newton Longville Landfill, Bletchley Road, Bletchley, Milton Keynes, Buckinghamshire | Buckinghamshire | South East | England |  | 484900 | 231900 | Aylesbury Vale District Council | [6 empty] | 1996-06-04 | [6 empty] | 1996-07-10 | [5 empty] | 2001-11-15
02044L5 | 537 | 2005-09-29 | Waste Recycling Group | Calvert Phase II | Landfill Gas |  |  | 11.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Brackley Lane, Calvert, Milton Keynes, Buckinghamshire | Buckinghamshire | South East | England |  | 469400 | 222900 | Aylesbury Vale District Council | 02/01933/ADP | [5 empty] | 2002-07-11 | [6 empty] | 2002-10-21 | [5 empty] | 2003-02-02
02045L5 | 538 | 2009-11-03 | Waste Recycling Group | Weldon Phase 1 and 2 | Landfill Gas |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kettering Road, Weldon, Northamptonshire | Northamptonshire | East Midlands | England |  | 492300 | 288500 | Corby Borough Council | [6 empty] | 1996-06-05 | [6 empty] | 1997-06-12 | [5 empty] | 2002-06-15
02046L5 | 539 | 2010-06-09 | NOVERA | Enderby Warren Phase II | Landfill Gas |  |  | 4.87 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Mill Hill, Enderby Warren, Leicestershire | Leicestershire | East Midlands | England |  | 453600 | 300200 | Blaby District Council | 1997/0785/1 | [5 empty] | 1997-07-31 | [6 empty] | 1997-11-25 | [5 empty] | 1999-06-01
02047L5 | 540 | 2005-06-29 | ENERGY DEVELOPMENTS (UK) LTD | Waverley Wood II | Landfill Gas |  |  | 2.42 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Waverley Wood Farm, Weston Lane, Coventry, West Midlands | Warwickshire | West Midlands | England |  | 436100 | 271400 | Warwick District Council | [6 empty] | 1999-06-29 | [6 empty] | 1999-10-14 | [5 empty] | 2004-05-01
02051L5 | 541 | 2011-02-01 | NOVERA | Glapwell Power | Landfill Gas |  |  | 1.95 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glapwell, Bolsover, Chesterfield, Derbyshire | Derbyshire | East Midlands | England |  | 446200 | 366800 | Bolsover District Council | [6 empty] | 1999-10-21 | [6 empty] | 2000-01-10 | [5 empty] | 2001-06-01
02066L3 | 542 | 2005-06-29 | Greenways | Judkins Landfill Site Phase 3 | Landfill Gas |  |  | 1.15 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Judkins Landfill Site Tuttle Hill Nuneaton Warwickshire | Warwickshire | West Midlands | England |  | 435300 | 292800 | Nuneaton and Bedworth Borough Council | [6 empty] | 1995-06-09 | [6 empty] | 1995-12-14 | [5 empty] | 1996-05-01
04002L5 | 543 | 2009-07-15 | Waste Recycling Group | Pen y Bont | Landfill Gas |  |  | 2.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Chirk, Wrexham, Clwyd | Clwyd | Wales | Wales |  | 329200 | 341600 | Wrexham County Borough Council | P20020261 | [5 empty] | 2002-03-12 | [6 empty] | 2002-07-08 | [5 empty] | 2003-01-02
04003L5 | 544 | 2009-07-15 | Waste Recycling Group | Ruabon | Landfill Gas |  |  | 2.06 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Gardden Lodge Landfill Site, Tatham Road, Ruabon, Wrexham, Clwyd | Clwyd | Wales | Wales |  | 330000 | 345000 | Wrexham County Borough Council | [6 empty] | 1999-11-29 |  | 2000-12-05 | [10 empty] | 2001-07-15
04007L3 | 545 | 2003-03-20 | Waste Recycling Group | Maw Green Landfill Site | Landfill Gas |  |  | 1.61 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Maw Green Landfill Site Coppenhall Crewe Cheshire | Cheshire | North West | England |  | 371800 | 357500 | Cheshire East Council | [6 empty] | 1994-09-06 | [6 empty] | 1994-12-09 | [5 empty] | 1996-12-01
04008L3 | 546 | 2003-03-20 | Waste Recycling Group | Gowy Landfill Site | Landfill Gas |  |  | 1.61 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Gowy Landfill Site Ince Lane Wimbolds Trafford near Chester Cheshire | Cheshire | North West | England |  | 344600 | 371500 | Cheshire West and Chester Council | [6 empty] | 1994-09-06 | [6 empty] | 1994-12-13 | [5 empty] | 1996-05-01
04016L4 | 547 | 2003-03-20 | NOVERA | Arpley Landfill Scheme 'A' | Landfill Gas |  |  | 7.87 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Off Liverpool Road Sankey Bridges Cheshire | Cheshire | North West | England |  | 357300 | 386300 | Warrington Borough Council | [6 empty] | 1994-08-01 | [6 empty] | 1995-02-24 | [5 empty] | 1999-12-10
04018L4 | 548 | 2003-06-30 | Biffa | Holiday Moss Landfill Gas Scheme | Landfill Gas |  |  | 2.9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Holiday Moss Landfill Site Reeds Brow Rainford St Helens Merseyside WA11 8PG | Merseyside | North West | England |  | 349000 | 402000 | St Helens Council | [6 empty] | 1994-03-11 | [6 empty] | 1994-07-07 | [5 empty] | 1998-05-08
04019L4 | 549 | 2003-03-20 | NOVERA | Arpley Landfill Scheme 'B' | Landfill Gas |  |  | 7.87 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Off Liverpool Road Sankey Bridges Cheshire | Cheshire | North West | England |  | 357300 | 386300 | Warrington Borough Council | [6 empty] | 1999-04-15 | [6 empty] | 1999-07-14 | [5 empty] | 1999-12-10
04020L4 | 550 | 2004-12-09 | Biffa | Bromborough Dock Landfill Scheme | Landfill Gas |  |  | 2.95 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dock Road South Bromborough Merseyside | Merseyside | North West | England |  | 334900 | 384800 | Wirral Council | [6 empty] | 1999-02-10 | [6 empty] | 1999-05-21 | [5 empty] | 1999-09-29
04023L4 | 551 | 2011-10-30 | Bidston Methane Ltd | Bidston Moss Landfill Scheme | Landfill Gas |  |  | 2.34 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bidston Birkenhead Merseyside | Merseyside | North West | England |  | 328600 | 390900 | Wirral Council | [6 empty] | 1997-11-03 | [6 empty] | 1997-12-15 | [5 empty] | 1998-01-19
04028L4 | 552 | 2009-07-15 | Waste Recycling Group | Llandulas Landfill Scheme | Landfill Gas |  |  | 2.88 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Llandulas, Abergele, Clwyd | Clwyd | Wales | Wales | LL22 8H | 291000 | 378500 | Conwy County Borough Council | [6 empty] | 1997-11-14 | [6 empty] | 1998-03-19 | [5 empty] | 1999-07-19
04056L5 | 553 | 2003-06-30 | Biffa | Holiday Moss Gas to Energy II | Landfill Gas |  |  | 1.406 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Holiday Moss Landfill, Reeds Brow, Rainford, Merseyside | Merseyside | North West | England |  | 349000 | 402000 | St Helens Council | [6 empty] | 1994-03-11 | [12 empty] | 2000-04-01
05002L3 | 554 | 2013-10-08 | Biogeneration / Biffa | Himley Wood Landfill Site | Landfill Gas |  |  | 4.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Himley Wood Landfill Site Himley Road Himley Staffordshire | Staffordshire | West Midlands | England |  | 389900 | 290900 | South Staffordshire Council | [6 empty] | 1992-11-26 | [6 empty] | 1995-03-24 | [5 empty] | 1996-08-01
05008L4 | 555 | 2005-09-27 | Severn Waste | Hill and Moor Landfill Scheme | Landfill Gas |  |  | 3.38 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Throckmorton Road Lower Moor Pershore Worcestershire | Hereford and Worcester | West Midlands | England |  | 398000 | 248300 | Wychavon District Council | [6 empty] | 1996-04-30 | [6 empty] | 1996-10-01 | [5 empty] | 1999-03-12
05012L4 | 556 | 2010-03-03 | Waste Recycling Group | Edwin Richards Landfill Scheme | Landfill Gas |  |  | 1.78 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Portway Road Rowley Regis Warley West Midlands | West Midlands | West Midlands | England |  | 396000 | 288000 | Sandwell Metropolitan Borough Council | [19 empty] | 2002-06-01
05016L5 | 557 | 2010-06-09 | ONYX LANDFILL LTD | Candles/Coalmoor Landfill | Landfill Gas |  |  | 2.85 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dog Lane, New Works, Telford | Shropshire | West Midlands | England |  | 366300 | 307700 | Telford and Wrekin Council | [6 empty] | 1999-02-25 | [6 empty] | 2001-09-01 | [5 empty] | 2005-10-01
05023L5 | 559 | 2010-04-30 | Energy Developments (UK) / SITA UK | Packington Generation Plant Phase 3 | Landfill Gas |  |  | 8.47 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Little Packington, Meriden, Coventry, West Midlands | Warwickshire | West Midlands | England |  | 421100 | 285800 | North Warwickshire Borough Council | NW6/02CM004 | [5 empty] | 2002-03-21 | [6 empty] | 2002-07-01 | [5 empty] | 2005-12-01
05024L5 | 560 | 2009-06-05 | ENERGY DEVELOPMENTS (UK) LTD/Cleanaway | Sandy Lane Generation Plant | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sandy Lane, Wildmoor, Bromsgrove, Worcestershire | Hereford and Worcester | West Midlands | England |  | 395200 | 276200 | Bromsgrove District Council | [6 empty] | 1999-12-21 | [6 empty] | 2000-07-25 | [5 empty] | 2006-08-01
05034L5 | 561 | 2005-06-29 | Thomas Graveson Ltd | Meece Landfill | Landfill Gas |  |  | 1.33 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Westgate, Swynnerton, Nr Stone, Staffordshire | Staffordshire | West Midlands | England |  | 385400 | 333900 | Stafford Borough Council | [6 empty] | 1996-04-01 | [6 empty] | 1997-03-24 | [5 empty] | 1999-02-24
05044L3 | 562 | 2010-06-09 | Biogas Technology Ltd/Natural Power | Granville Landfill Site | Landfill Gas |  |  | 1.39 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Granville Landfill Site , Red Hill , Telford | Shropshire | West Midlands | England |  | 372500 | 312000 | Telford and Wrekin Council | [6 empty] | 1994-04-30 | [6 empty] | 1994-07-01 | [5 empty] | 1999-10-01
06001L4 | 563 | 2011-10-30 | Durham County Waste Management Company | PG1-Coxhoe Waste Disposal Site | Landfill Gas |  |  | 3.8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Coxhoe Waste Disposal Site Coxhoe County Durham | Durham | North East | England |  | 432800 | 536700 | Durham County Council | [6 empty] | 1997-03-06 | [6 empty] | 1997-04-24 | [5 empty] | 1998-04-01
06001L5 | 564 | 2010-08-06 | CLP | PG2 Bolam Power Generation | Landfill Gas |  |  | 1.03 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bolam Quarry, Bolam Village, County Durham | Durham | North East | England |  | 419100 | 523100 | Durham County Council | [6 empty] | 1999-05-08 | [6 empty] | 1999-05-25 | [5 empty] | 2002-08-15
06003L4 | 565 | 2011-10-30 | SITA UK | Kibblesworth Landfill Site | Landfill Gas |  |  | 2.34 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Greenford Lane Lamesley Birtley Tyne and Wear | Tyne and Wear | North East | England |  | 425500 | 556500 | Gateshead Metropolitan Borough Council | [6 empty] | 1996-12-24 | [6 empty] | 1998-06-05 | [5 empty] | 1998-10-26
06003L5 | 566 | 2013-10-08 | DURHAM COUNTY WASTE MANAGEMENT LTD | PG4 St Bedes Power Generation | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Station Lane, Birtley, County Durham DH2 1AW | Durham | North East | England |  | 426600 | 555200 | Durham County Council | CMA/2/3 | [5 empty] | 1999-12-08 | [6 empty] | 2000-06-09 | [5 empty] | 2001-03-30
06012L3 | 567 | 2009-12-10 | Northumberland Waste Management / SITA UK | Seghill Village Waste Disposal Site phase 1 and 2 | Landfill Gas |  |  | 4.1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Seghill Village Waste Disposal Site Seghill Northumberland | Northumberland | North East | England |  | 429800 | 574300 | Northumberland County Council | [6 empty] | 1996-10-01 | [6 empty] | 1996-12-13 | [5 empty] | 1998-02-19
07002L5 | 568 | 2004-12-09 | Thomas Graveson Ltd | Distington Landfill | Landfill Gas |  |  | 1.77 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pitwood Road, Lillyhall Industrial Estate, Workington, Cumbria | Cumbria | North West | England |  | 302500 | 524300 | Copeland Borough Council | [6 empty] | 1994-05-16 | [6 empty] | 1994-07-28 | [5 empty] | 1998-12-01
07003L5 | 569 | 2003-03-21 | ALCO WASTE MANAGEMENT LTD | Shearman Field | Landfill Gas |  |  | 1.9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Joseph Noble Road, Lillyhall, Workington, Cumbria | Cumbria | North West | England |  | 302700 | 524900 | Allerdale Borough Council | [6 empty] | 1999-05-10 | [6 empty] | 1999-06-16 | [5 empty] | 2000-02-15
07005L3 | 570 | 2011-10-30 | Waste Recycling Group | Danes Moss Landfill Site | Landfill Gas |  |  | 1.63 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Danes Moss Landfill Site Congleton Road Gawsworth Macclesfield Cheshire | Cheshire | North West | England |  | 390400 | 371500 | Cheshire East Council | [6 empty] | 1992-10-16 | [6 empty] | 1995-01-25 | [5 empty] | 1996-07-01
07006L4 | 571 | 2009-12-10 | Terry Adams Ltd | Pilsworth Quarry Landfill Scheme | Landfill Gas |  |  | 4.12 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pilsworth Quarry,Pilsworth Road, Bury, Lancashire | Greater Manchester | North West | England |  | 383000 | 409700 | Bury Metropolitan Borough Council | [6 empty] | 1997-12-15 | [6 empty] | 1998-05-19 | [5 empty] | 1998-10-15
07011L4 | 572 | 2010-04-28 | Biffa | Risley '4' Landfill Scheme | Landfill Gas |  |  | 5.9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Silver Lane Risley Warrington Cheshire | Cheshire | North West | England |  | 366500 | 393500 | Warrington Borough Council | [6 empty] | 1996-11-08 | [6 empty] | 1997-03-17 | [5 empty] | 1999-05-01
07012L4 | 573 | 2011-10-30 | Bidston Methane | Billinge Hill Quarry Landfill Scheme | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Billinge Hill Quarry Landfill Rainford Road Billinge St Helens Merseyside | Merseyside | North West | England |  | 352500 | 401300 | St Helens Council | [6 empty] | 1996-06-04 | [6 empty] | 1996-08-12 | [5 empty] | 1998-04-03
07043L5 | 574 | 2005-11-30 | SITA UK | Whinney Hill II Energy | Landfill Gas |  |  | 1.78 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Enfield Road, Huncoat, Accrington, Lancashire | Lancashire | North West | England |  | 376000 | 430500 | Hyndburn Borough Council | [19 empty] | 1999-01-01
07079L5 | 576 | 2006-05-25 | CAIRD ENVIRONMENTAL LTD | Deerplay Landfill Site | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bacup Road, Burnley, Lancashire | Lancashire | North West | England |  | 385600 | 428300 | Burnley Borough Council | [6 empty] | 2004-12-17 | [6 empty] | 2005-03-01 | [5 empty] | 2006-05-24
07109L3 | 577 | 2009-12-10 | NORWEB Generation Limited | Butchersfield Landfill Site | Landfill Gas |  |  | 2.96 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Butchersfield Landfill Site Rixton Old Hall, Manchester Road Rixton, Warrington, Cheshire | Cheshire | North West | England |  | 367900 | 389100 | Warrington Borough Council | [6 empty] | 1995-04-28 | [6 empty] | 1995-09-05 | [5 empty] | 1995-10-16
08001L4 | 578 | 2004-11-29 | Brett Waste Management Ltd | Shelford Landfill Scheme | Landfill Gas |  |  | 1.94 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Shelford Landfill Site, Broad Oak Road Canterbury, Kent | Kent | South East | England |  | 616200 | 160000 | Canterbury City Council | [6 empty] | 1996-08-01 | [6 empty] | 1997-10-27 | [5 empty] | 2001-12-30
08020L4 | 579 | 2009-12-10 | Haul Waste Disposal Ltd | Beddingham 'B' Landfill Scheme | Landfill Gas |  |  | 7.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beddingham Landfill Site Old Rodwell Cement Works Beddingham East Sussex | East Sussex | South East | England |  | 544500 | 107500 | Lewes District Council | [6 empty] | 1997-03-24 | [6 empty] | 1997-06-23 | [5 empty] | 1998-05-18
08023L3 | 581 | 2005-06-30 | ARC Ltd (Greenways Landfill) | Stangate Landfill Site | Landfill Gas |  |  | 4.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land to the north of Mill Lane within Isles-Quarry West, Quarry Hill Road, Borough Green, Kent | Kent | South East | England |  | 560300 | 156300 | Tonbridge and Malling Borough Council | [6 empty] | 1994-03-03 | [6 empty] | 1995-10-02 | [5 empty] | 1997-02-01
08024L3 | 582 | 2008-06-16 | ARC Ltd (Greenways Landfill)/ Waste Recycling Group plc | Offham Landfill Site Phase II | Landfill Gas |  |  | 1.18 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land to Rear of White Ladies Teston Road, Offham, West Malling, Kent | Kent | South East | England |  | 564600 | 157400 | Tonbridge and Malling Borough Council | [6 empty] | 1994-03-04 | [6 empty] | 1995-08-29 | [5 empty] | 1996-12-01
08024L5 | 583 | 2010-03-03 | ENERGY DEVELOPMENTS (UK) LTD | Shelford Generation Plant II | Landfill Gas |  |  | 8.048 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Broad Oak Road, Canterbury, Kent | Kent | South East | England |  | 616195 | 160155 | Canterbury City Council | [19 empty] | 2001-12-01
08025L5 | 584 | 2005-10-19 | Biffa | Brookhurst Wood Gas to Energy | Landfill Gas |  |  | 5.088 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Langhurstwood Road, Warnham, West Sussex | West Sussex | South East | England | RH12 4QD | 517300 | 135000 | Horsham District Council | [6 empty] | 1999-05-04 | [6 empty] | 1999-07-30 | [5 empty] | 2000-11-23
08035L3 | 585 | 2009-04-27 | Haul Waste Limited | Horton Landfill Site | Landfill Gas |  |  | 1.976 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Horton Landfill Site Henfield Road Small Dole Henfield West Sussex | West Sussex | South East | England |  | 520500 | 112400 | Horsham District Council | [6 empty] | 1995-06-05 | [6 empty] | 1995-07-28 | [5 empty] | 1996-12-01
09008L3 | 586 | 2011-08-18 | Canford Renewable Energy Ltd | Whites Landfill Site (Canford) | Landfill Gas |  |  | 6.01 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Whites Landfill Site Arrowsmith Road Wimborne Dorset | Dorset | South West | England |  | 403000 | 96500 | Poole Borough Council | [6 empty] | 1993-01-28 | [6 empty] | 1993-05-13 | [5 empty] | 1996-05-01
09014L3 | 587 | 2005-06-30 | Haul Waste Limited | Ardley Fields Farm Landfill Site | Landfill Gas |  |  | 1.82 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ardley Fields Farm Oxford Oxfordshire | Oxfordshire | South East | England |  | 454500 | 227500 | Cherwell District Council | [6 empty] | 1995-08-16 | [6 empty] | 1996-01-31 | [5 empty] | 1996-12-01
09015L5 | 588 | 2004-07-28 | HILLS MINERALS & WASTE LTD | Compton Bassett Landfill | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Nr Calne, Wiltshire | Wiltshire | South West | England |  | 402000 | 171000 | Wiltshire Council | [6 empty] | 1999-04-16 | [6 empty] | 1999-07-30 | [5 empty] | 2002-05-01
09016L4 | 589 | 2005-06-30 | Waste Recycling Group | Sutton Courtenay Landfill Scheme | Landfill Gas |  |  | 5.61 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Appleford Sidings, Abingdon, Oxfordshire | Oxfordshire | South East | England |  | 450800 | 192800 | Vale of White Horse District Council | [6 empty] | 1997-12-18 | [6 empty] | 1998-05-18 | [5 empty] | 1999-03-05
09016L5 | 590 | 2009-11-05 | HILLS MINERALS & WASTE LTD | Chapel Farm Landfill | Landfill Gas |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Off A419, Nr Blunsdon, Swindon, Wiltshire | Wiltshire | South West | England |  | 413300 | 190800 | Swindon Borough Council | [6 empty] | 1999-04-27 | [6 empty] | 1999-07-12 | [5 empty] | 2001-01-15
09021L4 | 592 | 2004-07-27 | NOVERA | Dimmer Landfill Gas Scheme | Landfill Gas |  |  | 2.34 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dimmer Landfill Site near Castle Cary Somerse | Somerset | South West | England |  | 361300 | 130900 | South Somerset District Council | [6 empty] | 1998-06-29 | [6 empty] | 1998-09-03 | [5 empty] | 1999-04-12
09021L5 | 593 | 2001-12-11 | Gengas Ltd | Dimmer Landfill Site | Landfill Gas |  |  | 1.91 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dimmer, Nr Castle Cary, Somerset | Somerset | South West | England |  | 361300 | 130800 | South Somerset District Council | [6 empty] | 1998-07-01 | [6 empty] | 1998-09-03 | [5 empty] | 2000-12-15
09022L5 | 594 | 2013-10-08 | Biffa | Farnham Landfill | Landfill Gas |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Alton Road, Farnham, Surrey | Surrey | South East | England |  | 482000 | 144700 | Waverley Borough Council | WA990223 | [5 empty] | 1999-02-15 | [6 empty] | 2002-08-13 | [5 empty] | 2004-01-01
09028L5 | 595 | 2010-02-05 | Waste Recycling Group | Sutton Courtney | Landfill Gas |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Appleford Sidings, Abingdon, Oxfordshire | Oxfordshire | South East | England |  | 451700 | 193000 | Vale of White Horse District Council | [6 empty] | 2002-10-22 | [6 empty] | 2002-12-23 | [5 empty] | 2006-10-01
09037L5 | 596 | 2002-07-03 | LIDSEY LANDFILL LTD | Lidsey Landfill | Landfill Gas |  |  | 1.44 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Headhome Farm, Near Bognor Regis, West Sussex | West Sussex | South East | England |  | 493000 | 103400 | Arun District Council | AL/57/96 | [12 empty] | 1996-11-22 | [5 empty] | 2002-06-01
09073L4 | 597 | 2005-10-19 | Thames Waste Management | Norlands Lane Landfill Site | Landfill Gas |  |  | 2.7 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Norlands Lane , Thorpe , Egham , Surrey | Surrey | South East | England |  | 502500 | 169500 | Runnymede Borough Council | [6 empty] | 1997-03-11 | [6 empty] | 1997-06-10 | [5 empty] | 1997-12-01
09077L4 | 598 | 2004-10-29 | Haul Waste Disposal Ltd | Westbury Landfill Scheme | Landfill Gas |  |  | 1.1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Trowbridge Road Westbury Wiltshire | Wiltshire | South West | England |  | 388200 | 152600 | Wiltshire Council | [6 empty] | 1997-03-03 | [6 empty] | 1997-07-25 | [5 empty] | 1998-07-15
09143L3 | 599 | 2005-10-19 | Associated Energy Projects plc | Paulsgrove Landfill Site | Landfill Gas |  |  | 2.41 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Paulsgrove Landfill Site Land east of Port Solent and south of the M27 Portsmouth Hampshire | Hampshire | South East | England |  | 464000 | 104500 | Portsmouth City Council | [6 empty] | 1996-05-03 | [6 empty] | 1996-07-29 | [5 empty] | 1998-02-01
09157L3 | 600 | 2009-11-05 | Leigh Environmental | Wapsey's Wood II Landfill Site | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wapsey's Wood II Oxford Road Gerrards Cross Buckinghamshire | Buckinghamshire | South East | England |  | 497400 | 188900 | South Bucks District Council | [6 empty] | 1997-11-17 | [6 empty] | 1998-03-11 | [5 empty] | 1999-01-01
10015L4 | 601 | 2009-07-15 | NOVERA | Silent Valley Landfill Scheme | Landfill Gas |  |  | 2.65 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Silent Valley Landfill Site, Waunlwyd Ebbw Vale | Gwent | Wales | Wales |  | 318500 | 207000 | Blaenau Gwent County Borough Council | [6 empty] | 1994-03-08 | [6 empty] | 1994-04-14 | [5 empty] | 2006-03-11
10028L5 | 602 | 2004-10-04 | Neath Port Talbot Waste Management Co Ltd | Briton Ferry | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Giants Grave Road, Briton Ferry, Neath, West Glamorgan | West Glamorgan | Wales | Wales |  | 273400 | 195300 | Neath Port Talbot County Borough Council | 961021 | [5 empty] | 1996-04-18 | [6 empty] | 1996-06-05 | [5 empty] | 2004-09-01
10032L5 | 603 | 2009-06-30 |  | Withyhedge Generation Plant | Landfill Gas |  |  | 2.42 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bowling Farm, Rudbaxton, Haverfordwest, Pembroke, Dyfed | Dyfed | Wales | Wales |  | 196800 | 221800 | Pembrokeshire County Council | Possibly 99/718 | [5 empty] | 1999-12-06 | [6 empty] | 2000-03-07 |  |  |  |  | 2006-05-01 | 2007-09-01
10035L3 | 604 | 2003-12-09 | Renewable Power Generation Ltd | Tythegston Landfill Site | Landfill Gas |  |  | 1.17 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Tythegston Landfill Site Tythegston Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 285100 | 178800 | Bridgend County Borough Council | [6 empty] | 1997-07-01 | [6 empty] | 1997-09-04 | [5 empty] | 1998-10-01
10044L5 | 605 | 2009-07-15 | Natural Power | Briton / Neath | Landfill Gas |  |  | 2.22 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Neath Landfill, Giant Grave Road, West Glamorgan | West Glamorgan | Wales | Wales |  | 273300 | 195400 | Neath Port Talbot County Borough Council | [6 empty] | 2000-04-26 | [6 empty] | 2000-06-06 | [5 empty] | 2004-06-01
10050L4 | 606 | 2009-07-15 | South Wales Power Ltd | Lamby Way Landfill Site | Landfill Gas |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lamby Way Cardiff | South Glamorgan | Wales | Wales |  | 322200 | 178300 | Cardiff Council | [6 empty] | 1997-08-12 | [6 empty] | 1998-10-03 | [5 empty] | 1998-11-27
10053L4 | 607 | 2009-07-15 | NOVERA | Nant y Caws Landfill Site | Landfill Gas |  |  | 1.37 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Nant y Caws Landfill Site , Carmarthenshire | Dyfed | Wales | Wales |  | 247200 | 217700 | Carmarthenshire County Council | [6 empty] | 1999-05-27 | [6 empty] | 1999-09-15 | [5 empty] | 2001-12-01
11003L5 | 609 | 2004-07-27 | DEVON WASTE MANAGEMENT LTD | Deep Moor Gas to Energy | Landfill Gas |  |  | 1.95 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Deep Moor Landfill, High Bullen, Nr Torrington, Devon | Devon | South West | England |  | 252700 | 121300 | Torridge District Council | [6 empty] | 1998-02-04 | [6 empty] | 1998-06-12 | [5 empty] | 2000-01-13
11018L4 | 610 | 2006-05-03 | DEVON WASTE MANAGEMENT LTD | Chelson Meadow Gas to Energy Scheme | Landfill Gas |  |  | 1.8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Laira Bridge Road Plymouth Devon | Devon | South West | England |  | 249610 | 54475 | Plymouth City Council | [6 empty] | 1997-05-21 | [6 empty] | 1998-07-18 | [5 empty] | 1998-09-04
11023L4 | 611 | 2011-10-30 | East Midlands Electricity Generation | United Mines Landfill Scheme | Landfill Gas |  |  | 2.97 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | St Day Redruth Cornwall | Cornwall | South West | England |  | 173500 | 42500 | Cornwall Council | [6 empty] | 1994-03-03 | [6 empty] | 1994-11-29 | [5 empty] | 1998-11-19
11033L5 | 612 | 2005-03-10 | ENERGY DEVELOPMENTS (UK) LTD | Poole Generation Plant | Landfill Gas |  |  | 2.42 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Poole Landfill Site, Wellington, Somerset | Somerset | South West | England |  | 315200 | 121600 | Taunton Deane Borough Council | 46/1999/010 | [5 empty] | 1999-06-08 | [6 empty] | 1999-09-03 | [5 empty] | 2005-02-17
11043L5 | 613 | 2011-10-30 | Thomas Graveson Ltd | Walpole Landfill | Landfill Gas |  |  | 1.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pawlett, Bridgwater, Somerset | Somerset | South West | England |  | 331400 | 143200 | Sedgemoor District Council | [6 empty] | 1996-09-02 | [6 empty] | 1996-11-15 | [5 empty] | 1999-03-03
12002L5 | 614 | 2005-08-04 | Waste Recycling Group | Bootham Lane | Landfill Gas |  |  | 1.215 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dunscroft, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 465600 | 410400 | Doncaster Metropolitan Borough Council | [6 empty] | 2000-01-28 | [6 empty] | 2000-05-19 | [5 empty] | 2002-10-01
12009L4 | 616 | 2010-08-06 | Coal Products Ltd Energy | Parkwood Landfill Scheme | Landfill Gas |  |  | 1.17 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Parkwood Road (North) Neepsend Sheffield South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 434700 | 389800 | Sheffield City Council | [6 empty] | 1996-05-30 | [6 empty] | 1997-01-07 | [5 empty] | 2004-11-01
12010L4 | 618 | 2010-08-06 | Winerton Power Ltd | Immingham Landfill Scheme | Landfill Gas |  |  | 1.006 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Queens Road Immingham South Humberside | Humberside | Yorkshire and Humber | England |  | 520100 | 414500 | North East Lincolnshire Council | [6 empty] | 1994-03-02 | [6 empty] | 1994-06-02 | [5 empty] | 1999-03-01
12011L4 | 619 | 2014-12-03 | Winerton Power Ltd / FCC Environment | Humberfield Landfill Scheme | Landfill Gas |  |  | 2.34 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Humberfield Farm , Ferriby High Road , Hessle , North Humberside | Humberside | Yorkshire and Humber | England |  | 501000 | 426300 | East Riding of Yorkshire Council | 326-10172 | [6 empty] | 2005-08-04
12012L5 | 620 | 2010-08-06 | Waste Recycling Group | Immingham | Landfill Gas |  |  | 2.006 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Queens Road, Immingham, North Lincs, Doncaster, South Yorkshire | Humberside | Yorkshire and Humber | England |  | 520100 | 414500 | North East Lincolnshire Council | DC/705/00/1MM | [5 empty] | 2000-09-14 | [6 empty] | 2000-10-27 | [5 empty] | 2003-07-01
12015L5 | 621 | 2009-12-10 | DARRINGTON QUARRIES LTD | Skelbrooke Landfill Gas Project | Landfill Gas |  |  | 2.12 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Skelbrooke L/fill, Straight Lane, Nr Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 451000 | 411700 | Doncaster Metropolitan Borough Council | 99/50/0253/P/full | [5 empty] | 1999-01-29 | [6 empty] | 1999-07-19 | [5 empty] | 2001-01-17
12042L5 | 622 | 2009-11-03 | ONYX LANDFILL LTD | Soothills Landfill | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Quarry Lane, Woodkirk, Dewsbury, Yorkshire | West Yorkshire | Yorkshire and Humber | England |  | 426500 | 424700 | Kirklees Council | [6 empty] | 1999-03-10 | [6 empty] | 1999-11-05 | [5 empty] | 2004-01-01
12048L5 | 623 | 2009-04-22 | Biffa | Roxby Gas to Energy | Landfill Gas |  |  | 8.52 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Winterton Road, Roxby, Scunthorpe | Humberside | Yorkshire and Humber | England |  | 491000 | 417000 | North Lincolnshire Council | 7/14096 | [5 empty] | 1996-12-01 | [12 empty] | 2004-04-01
12071L3 | 625 | 2005-06-13 | Humberside Wastewise Ltd / Coal Products Limited | Winterton Landfill Site | Landfill Gas |  |  | 3.77 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Winterton Landfill Site Coleby Road West Halton Humberside | Humberside | Yorkshire and Humber | England |  | 491400 | 420100 | North Lincolnshire Council | [6 empty] | 1994-03-14 | [6 empty] | 1994-06-02 | [5 empty] | 1996-07-01
A0051 | 626 | 2009-06-09 |  | Pitsea Tipp | Landfill Gas |  |  | 14 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pitsea Hall Lane, Basildon, Essex | Essex | Eastern | England |  | 574100 | 185000 | Basildon Borough Council | [19 empty] | 2008-05-13
A0369 | 627 | 2010-06-09 |  | Queens Park Energy | Landfill Gas |  |  | 1.9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Burnley, Lancashire | Lancashire | North West | England |  | 385631 | 433704 | Burnley Borough Council | [19 empty] | 2000-11-01
B0660 | 628 | 2013-10-08 | Npower | Highfields South Landfill Gas | Landfill Gas |  |  | 1.03 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Highfields South, Lichfield Road, Walsall, Birmingham WS9 9AH | West Midlands | West Midlands | England |  | 404412 | 302851 | Walsall Council | 12/0926/FL | [5 empty] | 2012-07-20 | [6 empty] | 2012-09-13 | [5 empty] | 2012-09-27
EN00006 | 629 | 2014-12-03 | FCC Environment | Black Dog | Landfill Gas |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wester Hatton Landfill Site, Potterton, Aberdeen, AB23 8YY | Grampian | Scotland | Scotland |  | 396450 | 814422 | Aberdeenshire Council | APP/2005/0560 | [5 empty] | 2005-02-21 | [6 empty] | 2005-07-26 | [5 empty] | 2005-08-30
EN00023 | 630 | 2009-10-02 | Waste Recycling Group | Bootham Lane Phase 2 | Landfill Gas |  |  | 1.415 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bootham Lane Landfill Site, Bootham Lane, Dunscroft, Doncaster, South Yorkshire, DN7 4JT | South Yorkshire | Yorkshire and Humber | England |  | 465600 | 410400 | Doncaster Metropolitan Borough Council | 00/0350/P | [5 empty] | 2000-01-28 | [6 empty] | 2000-05-17 | [5 empty] | 2003-10-01
EN00269 | 631 | 2006-12-07 |  | Westmill Qaurry | Landfill Gas |  |  | 2.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Westmill Landfill Westmill Quarry Westmill Road Ware Herts | Hertfordshire | Eastern | England |  | 533985 | 215520 | East Hertfordshire District Council | 3/0416/-19 | [5 empty] | 1999-03-18 | [6 empty] | 1999-07-19 | [5 empty] | 2000-06-01
EN00369 | 632 | 2007-04-06 |  | St Day II | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | St Day Redruth Cornwall | Cornwall | South West | England |  | 174715 | 42285 | Cornwall Council | [6 empty] | 2003-01-01 | [6 empty] | 2003-06-01 | [5 empty] | 2003-06-01
EN00371 | 633 | 2007-04-06 |  | Connon Bridge Landfill | Landfill Gas |  |  | 1.006 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | East Taphouse, Liskeard, Cornwall | Cornwall | South West | England |  | 219100 | 62600 | Cornwall Council | [19 empty] | 2003-07-01
ENA0004 | 634 | 2006-05-23 |  | Rowley | Landfill Gas |  |  | 1.85 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Burnley | Lancashire | North West | England |  | 385506 | 433263 | Burnley Borough Council | [19 empty] | 1993-01-01
ENA0005 | 635 | 2006-05-24 |  | Withnell LFS | Landfill Gas |  |  | 2.25 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Chorley | Lancashire | North West | England |  | 363890 | 424010 | Chorley Borough Council | [19 empty] | 1996-01-01
ENA0006 | 636 | 2009-07-29 |  | Lune Power | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lancaster | Lancashire | North West | England |  | 345500 | 462500 | Lancaster City Council | [19 empty] | 2000-03-01
ENA0007 | 637 | 2009-07-06 |  | Rossendale Power | Landfill Gas |  |  | 1.63 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rossendale | Lancashire | North West | England |  | 380634 | 420905 | Rossendale Borough Council | [19 empty] | 2001-07-01
N00001L | 638 | 2009-07-06 | Shanks Group | Dogsthorpe South Landfill Site 2 | Landfill Gas |  |  | 1.41 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dogsthorpe South Landfill Site near Peterborough Cambridgeshire | Cambridgeshire | Eastern | England |  | 520550 | 301950 | Peterborough City Council | 03/00023/MMFUL | [5 empty] | 2003-01-09 | [6 empty] | 2004-05-24 | [5 empty] | 2005-08-01
N00002L | 639 | 2009-10-02 | Shanks Avondale | Avondale | Landfill Gas |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Shanks Landfill Site, Meikle, Drumgray Road, Greengairs, Airdrie, Lanarkshire | Strathclyde | Scotland | Scotland |  | 278500 | 669700 | North Lanarkshire Council | 01/01447/FUL | [5 empty] | 2001-11-05 | [6 empty] | 2002-01-29 | [5 empty] | 2006-01-01
N00004L | 640 | 2010-02-23 | ONYX | Springfield Farm | Landfill Gas |  |  | 1.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Springfield Farm, Gerrard Cross, Off Junction 12 of the M40 | Buckinghamshire | South East | England |  | 500044 | 188047 | South Bucks District Council | SBD/8204/06 | [5 empty] | 2006-03-16 | [6 empty] | 2006-05-23 | [5 empty] | 2006-09-01
N00005L | 641 | 2003-06-26 | Waste Recycling Group / NOVERA / Amber | Danes Moss Landfill Site (Extension) | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Danes Moss Landfill Site Congleton Road Gawsworth Macclesfield Cheshire | Cheshire | North West | England |  | 390400 | 371500 | Cheshire East Council | 5/002190 | [5 empty] | 2002-09-20 | [6 empty] | 2003-01-13 | [5 empty] | 2003-06-16
N00006L | 642 | 2009-12-10 | Viridor | Sands Farm Quarry Landfill Site | Landfill Gas |  |  | 3.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Calne Wiltshire | Wiltshire | South West | England |  | 401600 | 171100 | Wiltshire Council | N021935CM | [5 empty] | 2002-07-12 | [6 empty] | 2003-05-07 | [5 empty] | 2003-09-30
N00010L | 643 | 2011-03-03 | Viridor | Warmwell | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Warmwell Quarry , Dorset | Dorset | South West | England |  | 375500 | 85500 | West Dorset District Council | 1/E/2005/0155 | [6 empty] | 2011-03-03
N00012L | 644 | 2009-11-05 | Viridor | Squabb Wood | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Salisbury Road , Shootash , Romsey , Hants | Hampshire | South East | England | SO51 6GA | 433500 | 121500 | Test Valley Borough Council | TDS05746/3 | [5 empty] | 2002-02-11 | [6 empty] | 2002-06-14 | [5 empty] | 2006-01-01
N00024L | 646 | 2012-03-08 | Viridor | Wooton | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Northhampton | Northamptonshire | East Midlands | England |  | 476100 | 255500 | South Northamptonshire Council | SN/02/16C | [5 empty] | 2001-12-14 | [6 empty] | 2002-12-13 | [5 empty] | 2003-07-04
N00025L | 647 | 2007-09-03 | Biffa | Clifton Hall | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Manchester M27 8LN | Greater Manchester | North West | England |  | 379242 | 402721 | Salford City Council | 02/44153/FUL | [5 empty] | 2002-05-09 | [6 empty] | 2002-11-16 | [5 empty] | 2003-02-25
N00026L | 648 | 2010-08-06 | Natural Power | Chapman's Well | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Morrison Busty Industrial Estate, Anfield, Durham | Durham | North East | England |  | 417307 | 550811 | Durham County Council | CMA/1/8 | [5 empty] | 2002-05-30 | [6 empty] | 2002-08-21 | [5 empty] | 2003-03-01
N00027L | 649 | 2016-11-01 | Ylem Energy | Mark's Quarry | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Leamside Durham | Durham | North East | England |  | 431500 | 546500 | Durham County Council | CMA/4/10 | [5 empty] | 2002-07-25 | [6 empty] | 2002-11-20 | [5 empty] | 2003-12-01
N00029L | 650 | 2010-04-30 | Farley Engineering/ Kent Weald Properties/Cleanaway | Former Pluckley Landfill Site | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pluckley Kent | Kent | South East | England |  | 592690 | 145607 | Ashford Borough Council | [6 empty] | 2001-12-13 | [6 empty] | 2002-02-14 | [5 empty] | 2002-12-01
N00030L | 651 | 2003-02-06 | Natural Power | Horncliffe Quarry (Extension) | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Horncliffe Quarry Bury Rossendale Lancashire BB4 6EZ | Lancashire | North West | England |  | 380634 | 420905 | Rossendale Borough Council | [6 empty] | 2001-12-15 | [6 empty] | 2002-03-28 | [5 empty] | 2003-01-12
N00031L | 652 | 2009-07-28 | Yorwaste | Skibeden | Landfill Gas |  |  | 1.96 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Harrogate Road Skipton BD23 6AB | North Yorkshire | Yorkshire and Humber | England |  | 401344 | 452711 | Craven District Council | [6 empty] | 2001-12-01 | [6 empty] | 2002-05-07 | [5 empty] | 2009-05-17
N00032L | 653 | 2009-06-30 | Biffa | Ugley | Landfill Gas |  |  | 1.06 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ugley Near Stanstead Essex | Essex | Eastern | England |  | 552500 | 228500 | Uttlesford District Council | ESS0203UTT | [5 empty] | 2003-01-07 | [6 empty] | 2003-07-01 | [5 empty] | 2005-12-01
N00035L | 654 | 2005-09-27 | Biffa | Waresley Landfill Site | Landfill Gas |  |  | 1.646 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Waresley Hill Rear of Unit 100 Hartlebury trading Estate Worcs DY10 4JA | Hereford and Worcester | West Midlands | England |  | 385427 | 270719 | Wychavon District Council | 407551 | [5 empty] | 2003-01-29 | [6 empty] | 2003-04-22 | [5 empty] | 2005-02-02
N00036L | 655 | 2005-03-10 | Biffa | Whiteparish | Landfill Gas |  |  | 1.06 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | White Parish Landfill Site White Parish nr. Salisbury SP5 2QE | Wiltshire | South West | England |  | 421500 | 124500 | Wiltshire Council | S03.1754CM | [5 empty] | 2003-08-11 | [6 empty] | 2003-12-18 | [5 empty] | 2004-08-01
N00038L | 656 | 2009-07-20 | Biffa | Broockhurst Wood | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Horsham | West Sussex | South East | England |  | 515500 | 133500 | Horsham District Council | [19 empty] | 2000-12-01
N00039L | 657 | 2009-07-20 | Biffa | Bromborough Dock | Landfill Gas |  |  | 3.658 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Liverpool | Merseyside | North West | England | CH62 4SQ | 334819 | 383903 | Wirral Council | [19 empty] | 1999-09-01
N00042L | 658 | 2003-06-26 | Waste Recycling Group | Maw Green Landfill Site, Cheshire (Extension) | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Maw Green Landfill Site Coppenhall Crewe Cheshire | Cheshire | North West | England |  | 371800 | 357500 | Cheshire East Council | [6 empty] | 1994-09-06 | [6 empty] | 1994-12-09 | [5 empty] | 2003-06-09
N00043L | 659 | 2009-07-03 | Waste Recycling Group | Gowy Landfill Site, Cheshire (Extension) | Landfill Gas |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Gowy Landfill Site Ince Lane Wimbolds Trafford near Chester Cheshire CH2 4JP | Cheshire | North West | England |  | 344600 | 371500 | Cheshire West and Chester Council | 6/99/796 | [12 empty] | 1999-10-13 | [5 empty] | 2000-02-01
N00045L | 660 | 2002-08-23 | DURHAM COUNTY WASTE MANAGEMENT LTD | PG4 St Bedes Power Generation (Extension) | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Station Lane, Birtley, County Durham DH2 1AW | Durham | North East | England |  | 426500 | 555200 | Durham County Council | [6 empty] | 2001-10-26 | [6 empty] | 2002-02-21 | [5 empty] | 2002-07-18
N00047L | 661 | 2005-11-11 | Waste Notts Ltd | Sutton Landfill Site | Landfill Gas |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sutton Landfill site Huthwaite road Sutton in Ashfield | Nottinghamshire | East Midlands | England |  | 448151 | 358994 | Ashfield District Council | 4/99/0611 | [5 empty] | 1999-10-08 | [6 empty] | 2000-01-06 | [5 empty] | 2000-03-01
N00050L | 663 | 2013-10-08 | Natural Power | PG4 St Bedes Power Generation (Extension 2) | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Station Lane, Birtley, County Durham DH2 1AW | Durham | North East | England |  | 426700 | 555200 | Durham County Council | [6 empty] | 2003-01-08 | [6 empty] | 2003-06-06 | [5 empty] | 2003-10-02
N00051L | 664 | 2006-04-27 | Waste Recycling Group | Arlesey Landfill Site | Landfill Gas |  |  | 1.08 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Arlesey Landfill Site Arlesey Bedfordshire | Bedfordshire | Eastern | England |  | 518400 | 235100 | Central Bedfordshire Council | BC/CM/97/00013 | [5 empty] | 1994-02-15 | [6 empty] | 1994-04-11 | [5 empty] | 1998-07-18
N00053L | 665 | 2010-04-30 | NOVERA | Brynpica Landfill Site | Landfill Gas |  |  | 2.65 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Brynpica Landfill Site | Mid Glamorgan | Wales | Wales |  | 297500 | 196500 | Rhondda Cynon Taff County Borough Council | 03/0026 | [5 empty] | 2003-01-09 | [6 empty] | 2003-03-20 | [5 empty] | 2003-08-01
N00058L | 666 | 2005-08-05 | Integrated Waste Management | Humberfield Quarry Landfill Site | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Humberfield Farm , Ferriby High Road , North Ferriby | Humberside | Yorkshire and Humber | England |  | 501000 | 426300 | East Riding of Yorkshire Council | 03/00330/STPLS | [5 empty] | 2003-01-19 |  | 2005-08-05
N00059L | 667 | 2010-03-03 | ONYX LANDFILL LTD | Southleigh Landfill | Landfill Gas |  |  | 3.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Emsworth Common Road, Havant, Hampshire | Hampshire | South East | England |  | 473801 | 108109 | Havant Borough Council | [6 empty] | 1996-08-06 | [6 empty] | 1996-12-10 | [5 empty] | 2003-03-01
N00061L | 668 | 2005-02-14 | Viridor | Heathfield 'A' Landfill | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | John Acres Lane Fosterville Devon | Devon | South West | England |  | 290000 | 90000 | Teignbridge District Council | 05/2136/03 | [5 empty] | 2003-01-13 | [6 empty] | 2003-03-31 | [5 empty] | 2003-06-16
N00064L | 669 | 2004-09-28 | Waste Recycling Group | Ongar Landfill Scheme | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | LECA Works Mill Lane High Ongar Essex | Essex | Eastern | England |  | 556250 | 202350 | Epping Forest District Council | EFF/25/03/EPS | [5 empty] | 2003-07-04 | [12 empty] | 2004-07-01
N00067L | 670 | 2010-08-06 | CLP and Briagas | PG2 Bolam Power Generator (Extension) | Landfill Gas |  |  | 1.065 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bolam Quarry, Bolam Village, County Durham | Durham | North East | England |  | 419100 | 523100 | Durham County Council | [6 empty] | 2003-08-07 | [6 empty] | 2003-12-18 | [5 empty] | 2004-06-01
N00069L | 671 | 2010-03-03 | Garlaff Energy Ltd | Garlaff Landfill (Extension) | Landfill Gas |  |  | 3.03 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Garlaff Landfill Site | Strathclyde | Scotland | Scotland |  | 254300 | 617500 | East Ayrshire Council | 03-0723-FL | [5 empty] | 2003-08-13 | [6 empty] | 2003-12-18 | [5 empty] | 2003-12-29
N00071L | 672 | 2009-07-29 | Waste Recycling Group | Milton Landfill Site | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Milton Landfill Site | Cambridgeshire | Eastern | England |  | 547312 | 262455 | South Cambridgeshire District Council | [19 empty] | 1993-07-01
N00072L | 673 | 2011-10-30 | Biffa | Risley Sets 13 & 14 | Landfill Gas |  |  | 2.14 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Silver Lane Risley Warrington Cheshire | Cheshire | North West | England |  | 366500 | 393300 | Warrington Borough Council | [19 empty] | 2003-11-21
N00090L | 674 | 2009-07-28 | SITA UK | Path Head | Landfill Gas |  |  | 1.015 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Blaydon Tyne and Wear | Tyne and Wear | North East | England |  | 417508 | 563386 | Gateshead Metropolitan Borough Council | 1236/02 | [5 empty] | 2002-01-01 | [6 empty] | 2005-03-04 | [5 empty] | 2009-02-15
N00093L | 675 | 2009-06-30 | Waste Recycling Group | Oatslie Landfill Gas | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Near Roslin | Lothian | Scotland | Scotland |  | 327200 | 663100 | Midlothian Council | 04/00694/FUL | [5 empty] | 2004-09-01 | [6 empty] | 2005-01-10 |  |  |  |  | 2006-05-01 | 2006-12-01
N00113L | 676 | 2005-08-03 | CLP and Biogas | Snetterton Landfill Site | Landfill Gas |  |  | 1.065 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Snetterton Landfill Site Heath Road Snetterton Norfolk | Norfolk | Eastern | England |  | 601152 | 290001 | Breckland Council | 3/2004/3021 | [6 empty] | 2005-08-03
N00115L | 677 | 2011-03-08 | Biffa | Welford Landfill Site | Landfill Gas |  |  | 1.972 | No |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Welford Lanfill Site, intersection of A5119 and A14, Welford Road, Cold Ashby | Northamptonshire | East Midlands | England |  | 465920 | 278000 | Daventry District Council | DA/1994/0522 | [5 empty] | 1994-05-26
N00116L | 678 | 2005-07-21 | Vivid Waste Management | Weston Landfill Site | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Weston Landfill, South of Northampton, (M1 J16) | Northamptonshire | East Midlands | England |  | 467080 | 258920 | South Northamptonshire Council | SN/01/1584C | [18 empty] | 2003-12-31
N00118L | 679 | 2010-08-06 | RMC Aggregates | West Mill | Landfill Gas |  |  | 2.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Westmill Landfill Site, Westmill, Ware, Hertfordshire | Essex | Eastern | England | SG12 OES | 554384 | 222939 | Uttlesford District Council | 3/99/0416/CM | [5 empty] | 1999-04-22 | [6 empty] | 1999-07-19 | [5 empty] | 2005-03-01
N00141L | 680 | 2012-01-26 | Biffa | Skelton Grange Landfill | Landfill Gas |  |  | 5.206 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Skelton Grange Landfill , Newham Road , Newham Green , Leeds | West Yorkshire | Yorkshire and Humber | England | LS15 9AD | 436600 | 430600 | Leeds City Council | 32/472/04/MIN | [5 empty] | 2004-12-16 | [6 empty] | 2005-03-17 |  |  |  |  | 2006-05-01 | 2007-05-01
N00143L | 681 | 2010-04-30 | Biffa | Houghton-le-Spring Landfill Site | Landfill Gas |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Houghton-le-Spring Landfill Site , The Quarry , Quarry Road | Tyne and Wear | North East | England | DH4 4AU | 435320 | 550025 | Sunderland City Council | [6 empty] | 2004-01-01 | [12 empty] | 2006-12-01
N00149L | 682 | 2006-04-27 | William Tracey Ltd | Barkip Landfill Site | Landfill Gas |  |  | 1.15 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Barkip Landfill Site, Dalry | Strathclyde | Scotland | Scotland | KA24 4JJ | 229333 | 650530 | North Ayrshire Council | 03/00751/PP | [5 empty] | 2003-10-01 | [6 empty] | 2004-01-21 | [5 empty] | 2004-10-13
N00153L | 683 | 2010-06-01 | Fife Council | Lochhead | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | A823, Dunfermline, Fife | Fife | Scotland | Scotland | KY12 0RX | 308500 | 690500 | Fife Council | [19 empty] | 2006-09-01
N2011L2 | 684 | 2016-10-25 | Biffa | Cottonmount Quarry | Landfill Gas |  |  | 3.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cottonmount Quarry, 140 Mallusk Road, Mallusk, Newtownabbey, County Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT36 4QN | 141164 | 539297 | Northern Ireland Planning Service | U/1999/0264 | [5 empty] | 1999-06-25 | [6 empty] | 2001-01-02 | [5 empty] | 2009-02-10
S0011L3 | 686 | 2003-05-21 | ARC / Waste Recycling Group | Kaimes Landfill Site | Landfill Gas |  |  | 2.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Edinburgh | Lothian | Scotland | Scotland |  | 312800 | 666500 | Edinburgh City Council | [6 empty] | 1994-02-23 | [6 empty] | 1995-02-23 | [5 empty] | 2003-02-15
S0013L3 | 687 | 2005-11-30 | Waste Recycling Group | Greengairs Landfill Scheme Phase VI | Landfill Gas |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | North Lanarkshire | Strathclyde | Scotland | Scotland |  | 278500 | 669700 | North Lanarkshire Council | [6 empty] | 2000-12-12 | [6 empty] | 2002-03-15 | [5 empty] | 2002-12-01
S0014L3 | 688 | 2009-04-22 | Auchencarroch Energy Ltd / CLP | Auchencarroch Landfill | Landfill Gas |  |  | 2.113 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Auchencarroch landfill site, Auchencarroch Road, Jamestown, Alexandria, West Dunbartonshire | Strathclyde | Scotland | Scotland |  | 242100 | 681100 | West Dunbartonshire Council | WT00239 | [5 empty] | 2000-11-20 | [6 empty] | 2001-05-10 | [5 empty] | 2002-08-15
S0017L3 | 689 | 2006-04-27 | Graveson Energy Management | Greenoakhill | Landfill Gas |  |  | 3.94 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glasgow | Strathclyde | Scotland | Scotland |  | 266600 | 662700 | Glasgow City Council | [6 empty] | 1999-06-01 | [6 empty] | 1999-06-30 | [5 empty] | 2000-06-01
S0019L3 | 690 | 2010-03-03 | Barr Environmental / CLP | Garlaff Landfill | Landfill Gas |  |  | 1.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | East Ayrshire | Strathclyde | Scotland | Scotland |  | 254300 | 617500 | East Ayrshire Council | 02/0307FL | [5 empty] | 2002-03-18 | [6 empty] | 2002-06-13 | [5 empty] | 2003-12-29
S0020L3 | 691 | 2009-10-05 | Waste Recycling Group | Tarbothill Landfill Site | Landfill Gas |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bridge of Don, Aberdeen | Grampian | Scotland | Scotland |  | 395600 | 813500 | Aberdeen City Council | A2/1509 | [5 empty] | 2002-08-22 | [6 empty] | 2002-11-14 | [5 empty] | 2002-11-14
S0024L2 | 692 | 2011-10-30 | Waste Recycling Group | Greengairs Landfill Scheme Phase III | Landfill Gas |  |  | 1.96 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Airdrie | Strathclyde | Scotland | Scotland |  | 278500 | 669700 | North Lanarkshire Council | [6 empty] | 1997-06-24 | [6 empty] | 1997-09-12 | [5 empty] | 1999-08-13
S0025L2 | 693 | 2011-10-30 | Waste Recycling Group | Greengairs Landfill Scheme Phase IV | Landfill Gas |  |  | 1.96 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Airdrie | Strathclyde | Scotland | Scotland |  | 278500 | 669700 | North Lanarkshire Council | [6 empty] | 1997-06-24 | [6 empty] | 1997-09-12 | [5 empty] | 1999-08-13
S0028L1 | 694 | 2011-10-30 | Waste Recycling Group | Greengairs Landfill Scheme Phase I | Landfill Gas |  |  | 1.89 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Greengairs Landfill Site | Strathclyde | Scotland | Scotland |  | 278500 | 659700 | North Lanarkshire Council | [6 empty] | 1994-02-25 | [6 empty] | 1994-05-24 | [5 empty] | 1996-05-01
S0029L1 | 695 | 2011-10-30 | Waste Recycling Group | Greengairs Landfill Scheme Phase II | Landfill Gas |  |  | 1.89 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Greengairs Landfill Site | Strathclyde | Scotland | Scotland |  | 278500 | 669700 | North Lanarkshire Council | [6 empty] | 1994-02-25 | [6 empty] | 1994-05-24 | [5 empty] | 1996-10-01
ENA0008 | 696 | 2013-12-10 |  | West Quarry | Landfill Gas |  |  | 4.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | West Lancashire | Lancashire | North West | England |  | 352200 | 409700 | West Lancashire Borough Council | [19 empty] | 1992-01-01
N00131L | 697 | 2013-12-20 | Fife Council | Lower Melville Wood | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lower Melville Wood Landfill Site, Landfill Site Lower Melville Wood, Cupar | Fife | Scotland | Scotland | KY15 7UL | 330000 | 711700 | Fife Council | [19 empty] | 2007-02-28
N00139L | 698 | 2013-12-10 | Waste Recycling Group | Bennett Bank Landfill Site (lfg) | Landfill Gas |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Thwaite Flat, Barrow In Furness LA14 4QU | Cumbria | North West | England |  | 321500 | 474500 | Barrow in Furness Borough Council | 2594079 | [5 empty] | 2005-03-04 | [6 empty] | 2005-06-28 | [5 empty] | 2005-10-01
N00003L | 699 | 2015-01-09 | Veolia | Efford Landfill (Newmilton) | Landfill Gas |  |  | 2.8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Efford Landfill Site, Pennington, Lyminton | Hampshire | South East | England | SO41 8QZ | 423500 | 95400 | New Forest District Council | 03/78179 | [5 empty] | 2003-04-30 | [6 empty] | 2003-11-18 | [5 empty] | 2004-11-01
B0893 | 700 | 2017-09-18 | Cassidy & Ashton Group Ltd | Funtley Refuse Tip (Landfill Gas) | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Funtley Refuse Tip Titchfield Lane Wickham Fareham Hampshire PO15 6DY | Hampshire | South East | England |  | 454932 | 109261 | Winchester City Council | 13/01247/FUL | [5 empty] | 2013-06-05 | [6 empty] | 2013-08-28 |  |  |  | 2016-08-28
05004L5 | 701 | 2005-06-29 | SITA UK / Natural Power | Betton Abbots | Landfill Gas |  |  | 1.26 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cross Howes, Shrewsbury, Shropshire | Shropshire | West Midlands | England |  | 351400 | 308300 | Shropshire Council | MS20/0321/SY | [5 empty] | 2000-03-13 | [6 empty] | 2000-05-17 | [5 empty] | 2003-08-01
06002L4 | 702 | 2010-08-06 | SITA UK | Burnhills Landfill Scheme (L4) | Landfill Gas |  |  | 1.46 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Greenside Road, Blaydon, Tyne and Wear | Tyne and Wear | North East | England |  | 415600 | 562400 | Gateshead Metropolitan Borough Council | 176/98 | [5 empty] | 1998-02-27 | [6 empty] | 2001-12-12 | [5 empty] | 2005-06-01
06054L5 | 704 | 2005-03-23 | SITA UK / Natural Power | Brenkley Landfill | Landfill Gas |  |  | 1.91 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dinnington, Newcastle Upon Tyne, Tyne & Wear | Tyne and Wear | North East | England |  | 420900 | 575000 | Newcastle upon Tyne City Council | 2001/1186/01/DET | [5 empty] | 2001-06-05 | [6 empty] | 2002-05-16 | [5 empty] | 2003-12-01
06057L5 | 705 | 2010-02-05 | SITA UK | Burnhills Landfill (L5) | Landfill Gas |  |  | 3.832 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Longridge Road, Greenside, Tyne & Wear | Tyne and Wear | North East | England |  | 415600 | 562400 | Gateshead Metropolitan Borough Council | 176/98 | [5 empty] | 1998-02-27 | [6 empty] | 2001-12-12 | [5 empty] | 2006-05-01
07042L5 | 706 | 2006-07-13 | SITA UK / Natural Power | Clifton Marsh Energy | Landfill Gas |  |  | 3.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Newton With Clifton, Freckleton, Preston, Lancashire | Lancashire | North West | England |  | 347100 | 428700 | Fylde Borough Council | 05/02/0216 | [5 empty] | 2002-03-19 | [6 empty] | 2002-04-24 | [5 empty] | 2006-07-13
07044L5 | 707 | 2006-05-24 | SITA UK | Ulnes Walton Energy | Landfill Gas |  |  | 1.336 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ridley Lane, Croston, Preston, Lancashire | Lancashire | North West | England |  | 349400 | 420300 | Chorley Borough Council | 09/00/0050 | [5 empty] | 2000-01-20 | [6 empty] | 2000-05-10 | [5 empty] | 2003-03-03
07045L5 | 708 | 2009-12-10 | SITA UK | Jameson Road | Landfill Gas |  |  | 4.26 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Jameson Road Landfill Site, Jameson Road, Fleetwood, Lancs | Lancashire | North West | England |  | 333300 | 445700 | Wyre Borough Council | 03/00709/LCC | [5 empty] | 2003-06-16 | [6 empty] | 2003-08-06 | [5 empty] | 2006-07-13
07073L5 | 709 | 2004-12-10 | ONYX | Scouthead Power Plant | Landfill Gas |  |  | 2.86 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Highmoor Landfill, Whitegate Lane, Scouthead, Oldham, Lancashire | Greater Manchester | North West | England |  | 397500 | 406500 | Oldham Council | 40861 | [5 empty] | 2001-01-02 | [6 empty] | 2001-10-11 | [5 empty] | 2003-09-25
09009L5 | 710 | 2005-10-19 | SITA UK | Runfold Landfill | Landfill Gas |  |  | 1.21 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Guildford Road, Runfold, Farnham, Surrey | Surrey | South East | England |  | 486500 | 147300 | Waverley Borough Council | WA03/0481 | [5 empty] | 2003-03-04 | [6 empty] | 2003-07-15 | [5 empty] | 2005-10-01
02068L5 | 711 | 2010-06-09 | SITA UK | Narborough Landfill | Landfill Gas |  |  | 2.67 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Huncote Road, Narborough, Leicester, Leicestershire | Leicestershire | East Midlands | England |  | 452500 | 297500 | Blaby District Council | [6 empty] | 2000-09-11 | [6 empty] | 2001-11-17 | [5 empty] | 2005-03-11
02070L5 | 712 | 2005-02-28 | SITA UK | Lount/Smoile | Landfill Gas |  |  | 1.07 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Nottingham Road, Lount, Ashby De La Zouch, Leicestershire | Leicestershire | East Midlands | England |  | 438200 | 318700 | North West Leicestershire District Council | 2000/0219/7 | [5 empty] | 2000-03-09 | [6 empty] | 2000-06-21 | [5 empty] | 2003-07-21
02071L5 | 713 | 2005-09-22 | Nene Valley Waste Ltd | Sidegate Lane | Landfill Gas |  |  | 2.42 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sidegate Lane, Wellingborough, Northamptonshire | Northamptonshire | East Midlands | England |  | 491700 | 270300 | Wellingborough Borough Council | [19 empty] | 1996-01-01
N00017L | 714 | 2010-06-09 | Natural Power / SITA UK | Godmanchester | Landfill Gas |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Godmanchester Landfill Cow Lane Huntingdon Cambridgeshire | Cambridgeshire | Eastern | England |  | 525700 | 271000 | Huntingdonshire District Council | [6 empty] | 2001-11-30 | [6 empty] | 2002-03-18 | [5 empty] | 2003-06-27
S0016L3 | 715 | 2010-03-03 | SITA UK / Natural Power | Binn Landfill | Landfill Gas |  |  | 1.92 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glenfarg, Perthshire | Tayside | Scotland | Scotland |  | 317600 | 713900 | Perth and Kinross Council | 01/00395/FUL | [5 empty] | 2001-03-23 | [6 empty] | 2001-06-19 | [5 empty] | 2004-04-01
S0022L2 | 716 | 2009-04-22 | Natural Power | Auchinlea Landfill Site | Landfill Gas |  |  | 2.272 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bellside | Strathclyde | Scotland | Scotland |  | 281000 | 659000 | North Lanarkshire Council | [19 empty] | 2002-11-01
02062L5 | 717 | 2005-09-27 | Biffa | Ufton | Landfill Gas |  |  | 1.006 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ufton, Nr Southam, Leamington Spa | Warwickshire | West Midlands | England |  | 438100 | 261200 | Stratford on Avon District Council | [6 empty] | 1999-04-14 | [6 empty] | 1999-09-06 | [5 empty] | 1999-11-26
02063L5 | 718 | 2005-09-27 | Biffa | Wilnecote Landfill Site | Landfill Gas |  |  | 1.006 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rush Lane, Dosthill, Tamworth, Staffordshire | Staffordshire | West Midlands | England |  | 421500 | 300500 | Tamworth Borough Council | [6 empty] | 1999-05-19 | [6 empty] | 2000-02-18 | [5 empty] | 2000-06-08
08041L5 | 719 | 2005-09-29 | Biffa | Pebsham | Landfill Gas |  |  | 3.018 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Freshfields, Bexhill Road, St Leonards On Sea, East Sussex | East Sussex | South East | England |  | 577500 | 109000 | Hastings Borough Council | [6 empty] | 1999-12-09 | [6 empty] | 2000-05-17 | [5 empty] | 2000-10-05
08042L5 | 720 | 2009-12-10 | Biffa | Redhill 2 | Landfill Gas |  |  | 3.01 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cormongers Lane, Nutfield, Nr Redhill, Surrey | Surrey | South East | England |  | 529500 | 150100 | Tandridge District Council | [6 empty] | 1999-07-22 | [6 empty] | 1999-11-01 | [5 empty] | 2001-12-10
08043L5 | 721 | 2005-03-30 | Biffa | Shakespeare Farm Landfill Site | Landfill Gas |  |  | 1.006 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | St Mary Hoo, Rochester, Kent | Kent | South East | England |  | 581500 | 177100 | Medway Council | [6 empty] | 1999-05-10 | [6 empty] | 1999-11-01 | [5 empty] | 2000-08-02
05072L3 | 722 | 2011-10-30 | Biogas Technology Ltd and Avon CC | Harn Hill Quarry Landfill Site | Landfill Gas |  |  | 2.61 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Harn Hill Quarry Aust Road Olveston Bristol Avon | Avon | South West | England |  | 359000 | 188000 | South Gloucestershire Council | [6 empty] | 1995-07-06 | [6 empty] | 1995-09-25 | [5 empty] | 1996-10-01
N00018L | 723 | 2010-08-06 | Combined Landfill Projects (CLP) / SITA UK | Beacon Hill | Landfill Gas |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beacon Hill Dorset | Dorset | South West | England |  | 398000 | 95000 | East Dorset District Council | [6 empty] | 2001-12-28 | [6 empty] | 2002-07-05 | [5 empty] | 2004-12-01
08002L3 | 724 | 2005-10-19 | Biogeneration / Biffa | Patteson Court Landfill Site | Landfill Gas |  |  | 1.82 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Patteson Court Landfill Site Cormongers Lane Surrey | Surrey | South East | England |  | 529300 | 151000 | Reigate and Banstead Borough Council | [6 empty] | 1994-01-12 | [6 empty] | 1994-03-07 | [5 empty] | 1996-07-01
01003L4 | 725 | 2005-01-13 | Cleanaway / EDL | Rainham Landfill Scheme, Phase I | Landfill Gas |  |  | 3.88 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ferry Lane Rainham Havering | Greater London | London | England |  | 552400 | 179100 | Havering London Borough Council | [6 empty] | 1996-11-08 | [6 empty] | 1998-02-06 | [5 empty] | 2000-02-28
N00094L | 726 | 2010-03-09 | CLP Envirogas | South Cathkin Landfill Site | Landfill Gas |  |  | 7.39 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cathkin Landfill site. near to Rogerton, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 262500 | 657500 | South Lanarkshire Council | EK/04/0285 | [5 empty] | 2004-05-17 | [6 empty] | 2005-03-09 | [5 empty] | 2006-01-01
11007L5 | 727 | 2002-05-08 | Combined Landfill Projects (CLP Envirogas) | Connon Bridge Landfill Gas Project | Landfill Gas |  |  | 5.23 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | East Taphouse, Liskeard, Cornwall | Cornwall | South West | England |  | 219000 | 62500 | Cornwall Council | [6 empty] | 2000-06-01 | [6 empty] | 2001-07-31 | [5 empty] | 2002-03-15
01006L3 | 728 | 2005-03-30 | Combined Landfill Projects (CLP) | Mayton Wood Landfill Site | Landfill Gas |  |  | 1.51 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Mayton Wood Landfill Site Little Hautbois Coltishall Norfolk | Norfolk | Eastern | England |  | 624600 | 320800 | Broadland District Council | [6 empty] | 1993-12-10 | [6 empty] | 1994-04-14 | [5 empty] | 1996-03-01
01007L3 | 729 | 2001-05-05 | Combined Landfill Projects (CLP) | Blackborough End Landfill Site | Landfill Gas |  |  | 1.519 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Blackborough End Landfill Site Mill Drove Blackborough End Kings Lynn Norfolk | Norfolk | Eastern | England |  | 567200 | 314600 | King's Lynn and West Norfolk Borough Council | [6 empty] | 1993-12-10 | [6 empty] | 1995-12-22 | [5 empty] | 1996-06-01
07001L4 | 730 | 2006-05-24 | Combined Landfill Projects (CLP) | Whinney Hill Waste Disposal Site | Landfill Gas |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Whinney Hill Waste Disposal Site, Hyndburn Whinney Hill Road Clayton-le-Moors Lancashire | Lancashire | North West | England |  | 375600 | 430300 | Hyndburn Borough Council | [6 empty] | 1997-12-02 | [6 empty] | 1998-03-04 | [5 empty] | 1999-01-08
07009L5 | 731 | 2006-05-24 | Combined Landfill Projects (CLP) | Queen's Park Road Energy | Landfill Gas |  |  | 1.77 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rowley Landfill, Queen Park Road, Burnley, Lancashire | Lancashire | North West | England |  | 385095 | 433435 | Burnley Borough Council | 1991/0191 | [5 empty] | 1992-03-26 | [6 empty] | 1992-08-20 | [5 empty] | 2000-09-01
11008L5 | 732 | 2009-12-10 | Combined Landfill Projects (CLP) | Chelson Meadow 2 | Landfill Gas |  |  | 1.38 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Laira Bridge Road, Plymouth, Devon | Devon | South West | England |  | 249610 | 54475 | Plymouth City Council | [6 empty] | 1997-05-21 | [6 empty] | 1998-07-18 | [5 empty] | 1999-08-02
N00055L | 733 | 2003-12-09 | Combined Landfill Projects (CLP) | Costessey Landfill Gas Project 2 | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Longwater Industrial Estate Dereham Road Norwich Norfolk | Norfolk | Eastern | England |  | 616150 | 310750 | South Norfolk Council | C/7/2002/7008 | [5 empty] | 2002-05-21 | [6 empty] | 2002-09-27 | [5 empty] | 2003-05-14
S0017L2 | 734 | 2011-10-30 | Combined Landfill Projects (CLP) | Summerston Landfill | Landfill Gas |  |  | 2.78 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Glasgow | Strathclyde | Scotland | Scotland |  | 258000 | 671700 | Glasgow City Council | [6 empty] | 1998-03-30 | [6 empty] | 1998-12-01 | [5 empty] | 1999-07-28
01003L5 | 735 | 2009-04-22 | Cory Environmental | Barling Hall Farm | Landfill Gas |  |  | 2.443 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Little Wakening Road, Great Wakering, Essex | Essex | Eastern | England |  | 593600 | 190500 | Rochford District Council | [6 empty] | 1999-08-25 | [6 empty] | 2000-02-04 | [5 empty] | 2004-06-01
01004L5 | 736 | 2006-04-27 | Cory Environmental | Bellhouse South | Landfill Gas |  |  | 3.88 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Warren Lane, Stanway, Colchester, Essex | Essex | Eastern | England |  | 594900 | 222200 | Colchester Borough Council | [6 empty] | 2000-06-22 | [6 empty] | 2000-09-22 | [5 empty] | 2004-05-01
01005L5 | 737 | 2004-09-29 | Cory Environmental | Mucking Gas 3 Landfill Scheme | Landfill Gas |  |  | 3.88 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Crown Cottage, Mucking Wharf Road, Stanford le Hope, Essex | Essex | Eastern | England |  | 568400 | 180000 | Thurrock Council | [6 empty] | 1999-03-09 | [6 empty] | 1999-07-22 | [5 empty] | 2000-07-18
02015L3 | 738 | 2011-10-30 | East Midlands Electricity Generation | Sidegate Lane Landfill Site | Landfill Gas |  |  | 1.33 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sidegate Lane Landfill Site , Finedon , near Wellingborough , Northants | Northamptonshire | East Midlands | England |  | 491500 | 270300 | Wellingborough Borough Council | [6 empty] | 1995-04-26 | [6 empty] | 1995-06-09 | [5 empty] | 1996-08-01
01001L4 | 739 | 2008-09-08 | ENERGY DEVELOPMENTS (UK) LTD | Mucking Gas 2 Landfill Scheme | Landfill Gas |  |  | 3.77 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Mucking Wharf Road Mucking Stanford Essex | Essex | Eastern | England |  | 568400 | 180000 | Thurrock Council | [6 empty] | 1999-03-12 | [6 empty] | 1999-07-22 | [5 empty] | 2000-07-19
11014L4 | 740 | 2011-10-30 | Haul Waste Limited | Heathfield 'C' Landfill Scheme | Landfill Gas |  |  | 2.22 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | John Acres Lane Fosterville Devon | Devon | South West | England |  | 286100 | 76200 | Teignbridge District Council | [6 empty] | 1997-03-20 | [6 empty] | 1997-07-14 | [5 empty] | 1998-08-04
02046L4 | 741 | 2004-09-30 | Natural Power | Lincoln Landfill Scheme | Landfill Gas |  |  | 1.95 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Whisby Rd North Hykeham Lincoln Lincolnshire | Lincolnshire | East Midlands | England |  | 493000 | 367600 | North Kesteven District Council | [6 empty] | 1994-09-14 | [6 empty] | 1994-12-08 | [5 empty] | 2000-06-06
02053L5 | 742 | 2009-07-20 | Natural Power | Bretby Power | Landfill Gas |  |  | 1.55 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Newhall, Swadlincote, Derbyshire | Derbyshire | East Midlands | England |  | 428100 | 321100 | South Derbyshire District Council | [19 empty] | 2001-09-01
12053L5 | 743 | 2006-05-09 | Natural Power | Bootham Lane Landfill | Landfill Gas |  |  | 2.666 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bootham Lane Landfill, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 465700 | 410800 | Doncaster Metropolitan Borough Council | 00/51/0350/P/full | [5 empty] | 2000-01-28 | [6 empty] | 2000-05-19 | [5 empty] | 2002-12-01
12103L4 | 744 | 2004-07-29 | Natural Power | Peckfield Quarry Landfill Scheme | Landfill Gas |  |  | 3.92 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Peckfield Quarry Pit Lane Micklefield Leeds | West Yorkshire | Yorkshire and Humber | England |  | 443500 | 432000 | Leeds City Council | [6 empty] | 1998-06-30 | [6 empty] | 1998-09-22 | [5 empty] | 2000-01-25
N00022L | 745 | 2004-12-10 | Natural Power | Horncliffe Quarry | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Horncliffe Quarry Bury Rossendale, Lancashire BB4 6EZ | Lancashire | North West | England |  | 380634 | 420905 | Rossendale Borough Council | [6 empty] | 2000-06-20 | [6 empty] | 2000-09-24 | [5 empty] | 2001-04-01
S0008L3 | 746 | 2003-12-16 | Natural Power | Dunlop Landfill Gas Scheme | Landfill Gas |  |  | 2.41 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | East Ayrshire | Strathclyde | Scotland | Scotland |  | 244600 | 651500 | East Ayrshire Council | [6 empty] | 2000-01-17 | [6 empty] | 2000-09-27 | [5 empty] | 2003-04-15
S0009L3 | 747 | 2001-10-29 | Natural Power | Bonnyrigg | Landfill Gas |  |  | 2.18 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Melville Landfill Site, Lasswade, Midlothian | Lothian | Scotland | Scotland |  | 329700 | 666500 | Midlothian Council | [6 empty] | 2000-02-10 | [6 empty] | 2000-03-29 | [5 empty] | 2001-07-15
07060L5 | 748 | 2006-05-24 | Natural Power / SITA UK | Salt Ayre | Landfill Gas |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Salt Ayre Landfill, Ovangle Road, Lancaster, Lancashire | Lancashire | North West | England |  | 345500 | 462500 | Lancaster City Council | [6 empty] | 1999-06-14 | [6 empty] | 1999-10-29 | [5 empty] | 2000-03-22
02080L3 | 749 | 2009-04-22 | Redland Aggregates Ltd / Combined Landfill Projects (CLP) | Mountsorrel Landfill Site | Landfill Gas |  |  | 1.582 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Mountsorrel Quarry Loughborough Road Mountsorrel Leicestershire | Leicestershire | East Midlands | England |  | 457100 | 315000 | Charnwood Borough Council | 1994/1486/2 | [5 empty] | 1994-06-07 | [6 empty] | 1994-10-24 | [5 empty] | 1996-05-01
N00147L | 750 | 2005-10-19 | Renewable Power Generation Ltd | Fairoak Landfill | Landfill Gas |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fairoak Landfill East Horten Farm Mortimer Lane Hampshire | Hampshire | South East | England |  | 450495 | 118446 | Eastleigh Borough Council | S/05/53911 | [5 empty] | 2005-04-19 | [6 empty] | 2005-09-13 | [5 empty] | 2006-04-24
01060L5 | 751 | 2005-08-02 | Renewable Power Systems | Water Hall Generation Project | Landfill Gas |  |  | 1.96 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Lower Hatfield Road, Hertfordshire | Hertfordshire | Eastern | England |  | 529700 | 210000 | East Hertfordshire District Council | 3/0324-99 | [6 empty] | 2005-08-02
02052L4 | 752 | 2005-11-15 | Renewable Power Systems | Boston Landfill Scheme | Landfill Gas |  |  | 1.27 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Slippery Gowt Farm Boston Lincolnshire | Lincolnshire | East Midlands | England |  | 534800 | 341300 | Boston Borough Council | [6 empty] | 1997-11-27 | [6 empty] | 1998-03-16 | [5 empty] | 1999-03-15
09012L4 | 753 | 2005-10-19 | Renewable Power Systems | Trumps Farm Landfill Scheme | Landfill Gas |  |  | 2.93 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kitsmead Lane Longcross Chertsey Surrey | Surrey | South East | England |  | 499400 | 166100 | Runnymede Borough Council | [6 empty] | 1996-10-18 | [6 empty] | 1996-12-09 | [5 empty] | 1998-04-14
09056L5 | 754 | 2005-09-29 | Renewable Power Systems | High Heavens Landfill | Landfill Gas |  |  | 1.92 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Clay Lane, Booker, High Wycombe, Buckinghamshire | Buckinghamshire | South East | England |  | 483300 | 189800 | Wycombe District Council | [6 empty] | 1999-03-02 | [6 empty] | 1999-06-04 | [5 empty] | 2000-04-12
10052L4 | 756 | 2009-07-15 | Renewable Power Systems | Docksway Landfill Scheme | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Newport | Gwent | Wales | Wales |  | 330500 | 185300 | Newport City Council | 99/0337 | [5 empty] | 1999-03-23 | [6 empty] | 1999-05-19 | [5 empty] | 2000-03-30
02064L5 | 757 | 2009-10-07 | SITA UK | Cranford | Landfill Gas |  |  | 1.1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cranford Landfill Site, Thrapston Lane, Cranford St. John Nr Kettering, Northamptonshire | Northamptonshire | East Midlands | England |  | 493100 | 276200 | Kettering Borough Council | KET/2006/0301 | [5 empty] | 2006-03-29 | [6 empty] | 2006-04-19 | [5 empty] | 2006-12-01
02020L5 | 758 | 2009-12-10 | Summerleaze | Ling Hall 1 | Landfill Gas |  |  | 3.04 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Coalpit Lane Lawford Heath Nr Rugby Warwickshire | Warwickshire | West Midlands | England | CV23 9LH | 444900 | 272800 | Rugby Borough Council | [6 empty] | 1998-02-13 | [6 empty] | 1998-05-28 | [5 empty] | 2000-08-25
09025L5 | 759 | 2009-11-05 | Summerleaze | Wapsey's Wood III | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Oxford Road, Gerrards Cross, Buckinghamshire | Buckinghamshire | South East | England |  | 497400 | 188800 | South Bucks District Council | [19 empty] | 2004-03-01
S0012L3 | 760 | 2005-11-30 | Waste Recycling Group | Greengairs Landfill Scheme Phase V | Landfill Gas |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | North Lanarkshire | Strathclyde | Scotland | Scotland |  | 278500 | 669700 | North Lanarkshire Council | C/00/01446/FUL | [5 empty] | 2000-12-12 | [6 empty] | 2002-03-15 | [5 empty] | 2002-12-01
06021L5 | 761 | 2003-12-15 | Yorwaste | Seamer Carr | Landfill Gas |  |  | 1.33 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dunslow Road, Eastfield, Seamer, Scarborough, North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 503300 | 482400 | Scarborough Borough Council | [6 empty] | 1999-05-11 | [6 empty] | 1999-09-23 | [5 empty] | 2000-03-15
06029L3 | 762 | 2005-06-29 | Yorwaste /Biogas | Harewood Whin Landfill Site | Landfill Gas |  |  | 2.37 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Harewood Whin Tinkers Lane Rufforth North Yokshire | North Yorkshire | Yorkshire and Humber | England |  | 454400 | 451600 | York City Council | [6 empty] | 1994-08-10 | [6 empty] | 1994-12-02 | [5 empty] | 1997-12-11
N00028L | 763 | 2014-06-09 | Natural Power | Lochhead Landfill Scheme | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Restenneth Landfill Site, Montrose Road, Forfar, Angus, DD8 Near Forfar DD8 2RL | Tayside | Scotland | Scotland |  | 348536 | 750898 | Angus Council | 02/00519/FUL | [5 empty] | 2002-05-28 | [6 empty] | 2002-07-31 | [5 empty] | 2004-08-01
02010L5 | 764 | 2014-04-03 | Waste Recycling Group | Whisby Landfill Gas Project | Landfill Gas |  |  | 1.3 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Thorpe Road/Eagle Road, Whisby, Lincolnshire | Lincolnshire | East Midlands | England |  | 491000 | 366500 | North Kesteven District Council | [6 empty] | 2000-08-17 | [6 empty] | 2000-10-24
02052L5 | 765 | 2014-04-03 | Waste Recycling Group | Staveley Power | Landfill Gas |  |  | 2.12 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Hall Lane, Staveley, Chesterfield, Derbyshire S43 3TP | Derbyshire | East Midlands | England |  | 442700 | 375400 | Chesterfield Borough Council | CW2/0103/121 (site ref: 2.600.7) | [5 empty] | 2003-01-20 | [6 empty] | 2003-04-28 | [5 empty] | 2005-04-01
04082L4 | 766 | 2014-04-03 | Waste Recycling Group | Dark Lane (Astbury) Landfill Scheme | Landfill Gas |  |  | 1.95 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Astbury Quarry Rackery Lane Llay Wrexham | Clwyd | Wales | Wales |  | 333500 | 356500 | Wrexham County Borough Council | P/2005/0409 | [5 empty] | 2005-04-15 | [6 empty] | 2005-07-04
08004L5 | 767 | 2014-02-17 | SITA UK | Albury Landfill | Landfill Gas |  |  | 1.54 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Shere Road, Albury, Guildford, Surrey | Surrey | South East | England |  | 505500 | 148300 | Guildford Borough Council | [19 empty] | 2012-12-19
10037L5 | 768 | 2018-07-19 | Infinis/Novera Energy (TREHIR DEVELOPMENT COMPANY LTD) | Trehir Generation Project | Landfill Gas |  |  | 1.26 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Caerphilly, Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 315500 | 189700 | Caerphilly County Borough Council | 10/0213/FULL | [5 empty] | 2010-03-24 | [6 empty] | 2010-05-19 |  |  |  | 2015-05-19
10046L5 | 769 | 2005-01-10 | Biffa | Trecatti | Landfill Gas |  |  | 7.042 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fochriw Road, Nr Merthyr Tydfil, Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 311626 | 205713 | Caerphilly County Borough Council | [6 empty] | 1997-05-20 | [6 empty] | 1997-07-24 | [5 empty] | 2002-07-30
12011L5 | 770 | 2014-04-02 | FCC Environment | Gallymoor Landfill | Landfill Gas |  |  | 2.86 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Market Weighton Road, Holme-On-Spalding, Yorkshire | Humberside | Yorkshire and Humber | England |  | 483900 | 439600 | East Riding of Yorkshire Council | 94/20522/PLF | [5 empty] | 1994-11-02 | [6 empty] | 1995-01-20 | [5 empty] | 2004-04-01
12036L4 | 771 | 2014-02-25 | West Yorkshire Waste Disposal Authority / EDL | Lower Spen Landfill Scheme | Landfill Gas |  |  | 2.91 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | ParkRoad Ravensthorpe Dewsbury West Yorkshire | West Yorkshire | Yorkshire and Humber | England |  | 422500 | 421000 | Kirklees Council | [6 empty] | 1997-07-09 | [6 empty] | 1998-07-17
12051L5 | 772 | 2013-07-18 | Waste Recycling Group | Meadow Hall Power | Landfill Gas |  |  | 1.11 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rotherham, South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 439500 | 392300 | Rotherham Metropolitan Borough Council | RB19940251 | [5 empty] | 1994-03-07 | [6 empty] | 1994-08-11 |  |  |  |  | 2006-05-01 | 2007-07-01
B0416 | 773 | 2014-02-24 | B9 Organic Energy and Craigahulliar Energy | Craigahulliar Landfill Gas | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Craigahulliar Landfill | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 106712 | 598842 | Northern Ireland Planning Service | C/2010/0474 | [5 empty] | 2010-09-02 | [6 empty] | 2011-09-19 | [5 empty] | 2012-12-12
EN00021 | 774 | 2015-11-05 | Waste Recycling Group | Arlesey Landfill Gas (Extension) | Landfill Gas |  |  | 2.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Mill lane Arlesey Landfill Arlesey Bedfordshire | Bedfordshire | Eastern | England |  | 518832 | 235251 | Central Bedfordshire Council | BC/CM/2005/21 | [5 empty] | 2005-06-02 | [6 empty] | 2006-01-21 | [5 empty] | 2006-12-01
EN00270 | 775 | 2015-11-05 | Veolia | Wapsey's Wood | Landfill Gas |  |  | 7.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wapsys Wood Landfill Site, Oxford Road, Gerrards Cross, Bucks | Buckinghamshire | South East | England | SL9 8TE | 497342 | 188862 | South Bucks District Council | 03/08218/CM | [5 empty] | 2004-01-02 | [6 empty] | 2004-01-30 | [5 empty] | 2004-10-01
EN00593 | 776 | 2015-07-23 | Biffa | Newhurst Quarry | Landfill Gas |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Shepshed , Leicestershire | Leicestershire | East Midlands | England | LE12 9BU | 448680 | 317986 | Leicestershire County Council | 2007/1987/02 | [5 empty] | 2007-06-25 | [6 empty] | 2009-02-13
N00033L | 777 | 2013-09-05 | Biffa | Standen Heath | Landfill Gas |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Isle of Wight | Isle of Wight | South East | England |  | 445337 | 88184 | Isle of Wight Council | P/03058/06 | [5 empty] | 2003-06-02 | [6 empty] | 2007-01-30 | [5 empty] | 2010-03-28
N00037L | 778 | 2013-10-08 | Biffa | Risley | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Warrington | Cheshire | North West | England |  | 366720 | 393546 | Warrington Borough Council | 02/44000/ART10 | [5 empty] | 2002-04-12 | [6 empty] | 2003-06-01 | [5 empty] | 2003-11-01
N00040L | 779 | 2015-07-23 | Biffa | Hitchin | Landfill Gas |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Holwell Sandpit North Herts SG5 3RT | Hertfordshire | Eastern | England |  | 517000 | 232300 | North Hertfordshire District Council | 04/00779/1CM | [5 empty] | 2004-06-01 | [6 empty] | 2004-11-15 |  |  |  |  | 2006-07-01 | 2006-11-15
N00048L | 780 | 2013-02-07 | Waste Recycling Group | Newhurst Quarry | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Newhurst Quarry Off Ashby Road East Shepshed | Leicestershire | East Midlands | England |  | 448656 | 317887 | Charnwood Borough Council | P/99/0128/2 | [5 empty] | 1999-01-01 | 2002-02-04
N00060L | 782 | 2013-10-08 | Biffa | Pebsham (Extension) | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Freshfields, Bexhill Road, St Leonards On Sea, East Sussex, TN38 8AY | East Sussex | South East | England |  | 577500 | 109000 | East Sussex County Council | RR/413/CM | [5 empty] | 2004-08-11 | [6 empty] | 2004-10-14 | [5 empty] | 2004-11-01
N00062L | 783 | 2014-12-02 | Natural Power | Arden Quarry Landfill | Landfill Gas |  |  | 3.09 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Arden Quarry Landfill , Oven Hill Road , Birch Vale , Derbyshire | Derbyshire | East Midlands | England |  | 402220 | 386100 | High Peak Borough Council | CON/2002/0026 | [5 empty] | 2002-01-23 | [6 empty] | 2002-12-18 |  |  |  |  | 2012-10-08 | 2013-01-22
N00068L | 784 | 2012-04-23 | Hanson Brick Ltd | Capel Landfill | Landfill Gas |  |  | 1.03 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Capel Landfill Site Capel land adjacent to withdrawn MSW application site | Surrey | South East | England |  | 517283 | 139031 | Mole Valley District Council | M003/0878 | [5 empty] | 2003-06-02 | [6 empty] | 2004-07-13 | [5 empty] | 2006-02-01
N00070L | 785 | 2013-10-08 | Combined Landfill Projects (CLP Envirogas) | Folly Lane | Landfill Gas |  |  | 1.024 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beetley Landfill Site, Folly Lane, Beetley, Dereham | Norfolk | Eastern | England |  | 597460 | 317895 | Breckland Council | 3CM/2004/0007/F | [5 empty] | 2004-03-19 | [6 empty] | 2005-01-11 | [5 empty] | 2005-10-01
N00145L | 786 | 2013-10-08 | Auchencarroch Energy Ltd/CLP | Auchencarroch Landfill Extension | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Auchencarroch Landfill Site Jamestown Alexandria West Dunbartonshire | Strathclyde | Scotland | Scotland |  | 242150 | 681150 | West Dunbartonshire Council | DC05-224 | [5 empty] | 2005-09-01 | [6 empty] | 2005-10-31 | [5 empty] | 2005-11-01
N00146L | 787 | 2014-12-03 | FCC Environment | Rigby Landfill | Landfill Gas |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rigby Houghton House Quarry Landfill Site Adlington Chorley | Lancashire | North West | England |  | 359222 | 412764 | Chorley Borough Council | 09/05/0661 | [5 empty] | 2005-06-24 | [6 empty] | 2005-10-07 | [5 empty] | 2009-12-07
N00150L | 788 | 2013-10-08 | Stoneyhill Waste Management Ltd | Stoneyhill Landfill Site | Landfill Gas |  |  | 4.272 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Longhaven, Peterhead | Grampian | Scotland | Scotland |  | 407756.7 | 840971.9 | Aberdeenshire Council | APP/2004/1901 | [5 empty] | 2004-06-04 | [6 empty] | 2005-03-03 | [5 empty] | 2005-04-01
S0018L3 | 789 | 2013-05-23 | Combined Landfill Projects (CLP) | Kilgarth | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Kilgarth landfill site , North Lanarkshire | Strathclyde | Scotland | Scotland |  | 271900 | 667300 | North Lanarkshire Council | 01/00487/FUL | [5 empty] | 2001-04-24 | [6 empty] | 2001-12-03 |  |  |  |  | 2006-05-01 | 2007-01-01
N00073L | 790 | 2014-07-07 | Thames Waste Management | Norlands Lane Landfill Site (Extension) | Landfill Gas |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Norlands Lane , Thorpe , Egham , Surrey | Surrey | South East | England |  | 503448 | 169106 | Runnymede Borough Council | RU03/1204 | [5 empty] | 2003-10-14 | [6 empty] | 2003-12-29 | [5 empty] | 2004-02-01
01039L4 | 791 | 2014-09-25 | Redland Aggregates Ltd (Lafarge Redland) | Roxwell Landfill Scheme | Landfill Gas |  |  | 1.26 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Boyton Hall Roxwell Chelmsford Essex | Essex | Eastern | England |  | 566100 | 209900 | Chelmsford City Council | [6 empty] | 1994-10-12 | [6 empty] | 1995-04-19 | [5 empty] | 1999-07-13
07063L5 | 792 | 2014-12-03 | FCC Environment | Kirkless Power | Landfill Gas |  |  | 2.08 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kirkless Landfill, Kirkless, Higher Ince, Wigan. | Greater Manchester | North West | England |  | 361000 | 405800 | Wigan Council | [6 empty] | 2000-02-23 | [6 empty] | 2000-06-13 | [5 empty] | 2004-12-01
EN00009 | 793 | 2014-09-25 | Viridor | Dunbar Power Plant | Landfill Gas |  |  | 14 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Oxwell Mains, Dunbar, East Lothian | Lothian | Scotland | Scotland |  | 371365 | 675845 | East Lothian Council | [6 empty] | 2003-03-01 | [6 empty] | 2003-10-10 | [5 empty] | 2004-12-01
N00015L | 794 | 2014-09-25 | Viridor | Dunbar | Landfill Gas |  |  | 2.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | East Lothian | Lothian | Scotland | Scotland |  | 371600 | 675600 | East Lothian Council | 01/00989/FUL | [5 empty] | 2001-09-19 | [6 empty] | 2002-02-28 | [5 empty] | 2004-12-01
N00092L | 795 | 2014-09-25 | Biridor Limited | Whitehead Landfill | Landfill Gas |  |  | 5.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Off Lower Green Lane, Astley Green, Wigan. | Greater Manchester | North West | England |  | 370300 | 399550 | Wigan Council | A/02/55506 | [5 empty] | 2002-02-13 | [6 empty] | 2002-05-01 | [5 empty] | 2002-09-01
N00130L | 796 | 2020-06-04 | NPL Estates (formerly Viridor) | Whitehead Landfill 2 | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Whitehead Landfill and Land Reclamation Site, Off Lower Green Lane, Astley Green, Wigan. | Greater Manchester | North West | England |  | 370223 | 399507 | Wigan Council | A/05/64854 | [5 empty] | 2005-08-12 | [6 empty] | 2006-02-01
09020L5 | 797 | 2010-03-03 | Biffa | Colnbrook Landfill | Landfill Gas |  |  | 1.91 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sutton Lane, Colnbrook, Berkshire | Buckinghamshire | South East | England |  | 502300 | 177700 | Slough Borough Council | [6 empty] | 1999-04-16 | [6 empty] | 2000-03-08 | [5 empty] | 2005-09-01
N00135L | 798 | 2016-05-10 | Waste Recycling Group | Dorket Head | Landfill Gas |  |  | 2.826 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dorket Head Landfill Site, Woodborough Lane, Arnold, NG5 8PU | Nottinghamshire | East Midlands | England |  | 459500 | 347500 | Gedling Borough Council | 2003/2727 | [5 empty] | 2003-12-05 | [6 empty] | 2004-06-21 |  |  |  |  | 2004-08-01 | 2005-02-01
N00132L | 799 | 2016-05-10 | Waste Recycling Group | Drummond Moor Landfill | Landfill Gas |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | South of Rosewell Midlothian | Lothian | Scotland | Scotland |  | 332700 | 665980 | Midlothian Council | 040081FUL | [5 empty] | 2004-10-18 | [6 empty] | 2004-12-22 |  |  |  |  | 2004-12-23 | 2005-04-01
N00046L | 800 | 2010-08-06 | Hampshire Waste Services/ ONYX / Power Plant Services | Netley Landfill Site, Hampshire (Extension) | Landfill Gas |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Netley Landfill Site, Grange Road, Netley, Hampshire | Hampshire | South East | England |  | 446700 | 110200 | Eastleigh Borough Council | [6 empty] | 1995-06-16 | [6 empty] | 1996-01-26 | [5 empty] | 1997-06-18
01030L4 | 801 | 2005-11-18 | Veolia | Pitsea Landfill Scheme | Landfill Gas |  |  | 11.64 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pitsea Landfill Site Pitsea Hall Lane Basildon Essex | Essex | Eastern | England |  | 574200 | 185000 | Basildon Borough Council | [6 empty] | 1997-12-16 | [6 empty] | 1998-08-11 | [5 empty] | 2004-01-10
N00152L | 802 | 2009-07-15 | Waste Recycling Group | PwllfaWatkin Landfill Gas Site | Landfill Gas |  |  | 3.24 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pwllfawatkin Landfill Site Rhy Dy Fro Pontardawe Swansea West Glamorgan SA8 4RX | West Glamorgan | Wales | Wales |  | 271645 | 205725 | Neath Port Talbot County Borough Council | P/05/213 | [5 empty] | 2005-01-26 | [6 empty] | 2005-08-11 | [5 empty] | 2005-11-01
N00041L | 803 | 2006-05-26 | Yorwaste | Scorton | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Scorton, Catterick, Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 425500 | 500500 | Richmondshire District Council | C1/12/196A/CM | [5 empty] | 2001-08-30 | [6 empty] | 2001-10-25 | [5 empty] | 2003-11-01
05032M3 | 813 | 2010-04-30 | MES Environmental (CNIM Group) | Dudley EfW | EfW Incineration |  |  | 7.4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dudley Incinerator Lister Road Dudley West Midlands | West Midlands | West Midlands | England |  | 394300 | 289100 | Dudley Metropolitan Borough Council | [6 empty] | 1994-09-16 | [6 empty] | 1996-02-01 | [5 empty] | 1998-02-01
05033M3 | 814 | 2010-04-30 | MES Environmental (CNIM Group) | Wolverhampton EfW | EfW Incineration |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wolverhampton Waste Incinerator Corporation Yard Crown Street Wolverhampton | West Midlands | West Midlands | England |  | 391628 | 299909 | Wolverhampton City Council | C/1281/94 | [5 empty] | 1994-12-19 | [6 empty] | 1995-04-11 | [5 empty] | 1998-06-01
05034M3 | 815 | 2010-04-30 | MES Environmental (CNIM Group) | Stoke-on-Trent EfW | EfW Incineration |  |  | 14.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Stoke-on-Trent Waste Incinerator Plant, Campbell Road, Sideway, Stoke on Trent Staffordshire | Staffordshire | West Midlands | England |  | 387800 | 343500 | Stoke on Trent City Council | [6 empty] | 1994-12-06 | [6 empty] | 1995-04-11 | [5 empty] | 1998-01-10
05036M3 | 816 | 2010-04-30 | Veolia | Tyseley ERF | EfW Incineration |  |  | 30 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | James Road, Tyseley, Birmingham | West Midlands | West Midlands | England |  | 410300 | 284200 | Birmingham City Council | [6 empty] | 1993-11-12 | [6 empty] | 1994-02-24 | [5 empty] | 1996-09-01
06002M3 | 817 | 2006-05-09 | Cleveland Waste Management Ltd | Haverton Hill Incinerator | EfW Incineration |  |  | 20.06 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Process Plant Park Billingham Cleveland | County Durham | North East | England |  | 447900 | 522400 | Stockton on Tees Borough Council | [6 empty] | 1993-08-09 | [6 empty] | 1993-11-05 | [5 empty] | 1998-05-12
06062M5 | 822 | 2010-01-25 | N.E.M. LTD | Teeside 3 EFW Plant | EfW Incineration |  |  | 9.9 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Haverton Hill Road, Billingham, Teeside, Cleveland | County Durham | North East | England |  | 448000 | 522500 | Stockton on Tees Borough Council | 00/0026/P | [5 empty] | 2000-01-20 | [6 empty] | 2000-08-15
08015M3 | 826 | 2005-10-19 | European Development Corporation Ltd | Copyhold Works Incinerator | EfW Incineration |  |  | 43 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Copyhold Works Nutfield Road Redhill Surrey | Surrey | South East | England |  | 528750 | 150500 | Reigate and Banstead Borough Council | RE94/1094 | ATT/3600/A/95/250539 |  |  |  |  | 1994-06-01 |  | 1996-07-15
08021M5 | 827 | 2005-09-22 | SITA UK | Ridham Dock | EfW Incineration |  |  | 24.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Iwade, Sittingbourne, Kent | Kent | South East | England |  | 592200 | 168100 | Swale Borough Council | sw99777 | [5 empty] | 1999-05-14 |  | 2000-12-20
08023M5 | 828 | 2005-08-12 | ENERGY DEVELOPMENTS (UK) LTD | Shelford WTE Plant | EfW Incineration |  |  | 16.147 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Broad Oak Road, Canterbury, Kent | Kent | South East | England |  | 616000 | 160100 | Canterbury City Council | CA/02/01349 | [5 empty] | 2002-10-14 | 2003-12-05
08031M3 | 830 | 2005-08-12 | Pyrogen (Kent) Ltd | Betteshanger Colliery | EfW Incineration |  |  | 9 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | BetteshangerColliery Northbourne Betteshanger near Deal Kent | Kent | South East | England |  | 633600 | 152900 | Dover District Council | [7 empty] | 2005-08-12
09045C4 | 831 | 2012-07-06 | Scottish and Southern Energy (SSE) | Fibrepower, Slough | EfW Incineration |  |  | 50 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Slough Trading Estate, Greenock Road , Slough | Berkshire | South East | England |  | 495300 | 181500 | DECC (S36) | [6 empty] | 1994-09-23 | [6 empty] | 1999-03-29 | [5 empty] | 2002-05-01
09144M3 | 834 | 2010-04-30 | Veolia | Chineham ERF | EfW Incineration |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Chineham , Basingstoke , Hampshire | Hampshire | South East | England |  | 467200 | 155200 | Basingstoke and Deane Borough Council | [6 empty] | 1998-10-01 | [6 empty] | 1999-11-17 | [5 empty] | 2002-11-01
09145M3 | 835 | 2015-01-08 | Veolia | Marchwood ERF | EfW Incineration |  |  | 16 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bury Road , Marchwood , Hampshire | Hampshire | South East | England |  | 438400 | 111100 | New Forest District Council | [6 empty] | 2000-07-01 | [6 empty] | 2000-12-01 | [5 empty] | 2004-12-01
10071M3 | 838 | 2011-10-31 | Covanta | Brig y Cwm | EfW Incineration |  |  | 77 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Merthyr Tydfil Trelewis Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 310300 | 199500 | The Planning Inspectorate - National Infrastructure | EN010004 | [5 empty] | 2011-01-26 | 2011-10-24
12100C4 | 843 | 2015-01-08 | SITA UK | Vine Street EfW | EfW Incineration |  |  | 9.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Vine Street , Huddersfield , West Yorkshire | West Yorkshire | Yorkshire and Humber | England |  | 414800 | 417800 | Kirklees Council | [19 empty] | 2000-01-01
A0124 | 846 | 2011-06-07 | Surrey Waste Management | Trumps Farm | EfW Incineration |  |  | 14 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Long Cross, Chertsey, Surrey. KT16 0EF | Surrey | South East | England |  | 499675 | 165561 | Runnymede Borough Council | RU.08/0556 | [5 empty] | 2008-06-09 | 2010-01-06
A0146 | 847 | 2012-01-04 | SITA UK | Granville | EfW Incineration |  |  | 3.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Grange Lane, Redhill, Telford | Shropshire | West Midlands | England | TF2 9PB | 372138 | 311433 | Telford and Wrekin Council | W2008/1083 | [5 empty] | 2008-09-23 |  | 2009-12-30
A0159 | 848 | 2014-11-25 | Viridor | Trident Park | EfW Incineration |  |  | 30 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Trident Park, Rumney, Cardiff, South Glamorgan | South Glamorgan | Wales | Wales | CF3 | 323014 | 180704 | Cardiff Council | 08/02616/E | APP/Z6815/A/09/2113747/WF |  |  |  |  | 2008-11-27 |  | 2009-07-09 | 2009-11-24 | 2010-01-01
A0474 | 849 | 2013-10-08 | Swindon Borough Council | Cheney Manor EfW | EfW Incineration |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Cheney Manor Ind Est, Swindon, Wilts | Wiltshire | South West | England |  | 413275 | 186463 | Swindon Borough Council | S/SP/10/1715 | [5 empty] | 2011-01-18 | 2011-08-09
A0535 | 850 | 2011-08-20 | Newlincs Developments | Newlincs EfW | EfW Incineration |  |  | 3.18 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land off South Marsh Road (North of Synthomer Ltd) Stallingborough North East Lincolnshire | Humberside | Yorkshire and Humber | England |  | 521604 | 413270 | North East Lincolnshire Council | DC/468/00/IMM | [5 empty] | 2000-05-24 | [6 empty] | 2001-01-05 | [5 empty] | 2004-04-01
AA106 | 851 | 2012-01-04 | Sky Properties | Green Lane Eco Park | Advanced Conversion Technologies |  |  | 9 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | 1.6 km nort west of Eccles town centre, Greater manchester | Greater Manchester | North West | England |  | 376384 | 399099 | Salford City Council | 10/59092/FULEIA | [5 empty] | 2010-07-16 |  | 2011-06-02
AA539 | 853 | 2011-11-02 | Biffa | Kingswood EFW | EfW Incineration |  |  | 34 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Kingswood Lakeside Business Park, Cannock, Staffordshire | Staffordshire | West Midlands | England |  | 400026 | 308415 | East Staffordshire Borough Council | CH.10/10/775 W | [5 empty] | 2010-09-13 |  | 2011-10-13
AA690 | 854 | 2015-03-02 | Veolia | Fieldes Lock EFW | EfW Incineration |  |  | 50 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Hoddesdon, Hertfordshire | Hertfordshire | Eastern | England |  | 538858 | 209129 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2012-09-07 | 2013-04-22
AA758 | 855 | 2013-06-06 | Veolia | Llanwern Steelworks Energy Recovery Facility | EfW Incineration |  |  | 19 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Queensway, Llanwern, Newport, Gwent | Gwent | Wales | Wales |  | 338108 | 185767 | Newport City Council | 11/1303 | N/A |  |  |  |  | 2012-03-22 |  | 2012-07-25 |  | 2013-03-20
AA951 | 856 | 2012-10-04 | Irish Recycling Services | Ballyutoag Road | EfW Incineration |  |  | 12.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Belfast, Northern Ireland | Co. Down | Northern Ireland | Northern Ireland |  | 141254 | 534827 | Northern Ireland Planning Service | T/2009/0283/F | [5 empty] | 2009-06-17 |  | 2012-10-02
B0480 | 857 | 2012-08-24 | Trackwork | Trackwork Limited (EfW) | EfW Incineration |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | PO Box 139, Sandall Lane, Kirk Sandall Industrial Estate, Doncaster | South Yorkshire | Yorkshire and Humber | England | DN3 1WZ | 461772 | 409433 | Doncaster Metropolitan Borough Council | 04/6912/P | [5 empty] | 2004-10-12 | [6 empty] | 2005-01-06 | [5 empty] | 2011-02-28
B0864 | 858 | 2013-08-27 | Grundon | Shore Road | Advanced Conversion Technologies |  |  | 16 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Shore Road, Perth | Tayside | Scotland | Scotland |  | 311964 | 722430 | Scottish Government (S36) | 11/00788/AMM | 12/00012/REF |  |  |  |  | 2011-05-13 |  | 2012-02-14 |  |  | 2013-08-20
EN00088 | 859 | 2017-04-04 | Cory Environmental | Riverside Resource Recovery Facility (RRRF) | EfW Incineration |  |  | 72 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Riverside Resource Recovery, PO Box 51, Bexleyheath, Kent | Greater London | London | England | DA16 1ZN | 547200 | 176500 | DECC (S36) | [6 empty] | 1999-09-29 | [6 empty] | 2006-06-15 |  |  |  |  | 2010-09-01 | 2011-09-01
EN00090 | 860 | 2011-02-08 | Peterborough Renewable Energy | Fengate Industrial Estate | Advanced Conversion Technologies |  |  | 174 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Fengate Industrial Estate, Peterborough | Cambridgeshire | Eastern | England |  | 520709 | 298561 | DECC (S36) | [7 empty] | 2011-02-08
EN00442 | 861 | 2018-12-04 | BCB | Marston Moor Industrial Estate | EfW Incineration |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | BCB Environmental Management Marston Moor Industrial Estate Tockwith | North Yorkshire | Yorkshire and Humber | England |  | 445500 | 451500 | North Yorkshire County Council | NY/2009/0176/FUL | [5 empty] | 2009-04-23 |  | 2009-12-15
N00001M | 863 | 2006-04-27 | SITA UK | Former Astra Fireworks Site | EfW Incineration |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Former Astra Fireworks Site Richborough, Nr Sandwich, Kent | Kent | South East | England |  | 632476 | 158720 | Dover District Council | [6 empty] | 2001-04-01 |  | 2001-07-16
N00005M | 864 | 2004-07-29 | County Environmental Services (CES) | Roche Energy from Waste Scheme | EfW Incineration |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Opposite Victoria Industrial Park Roche Cornwall | Cornwall | South West | England |  | 198677 | 60276 | Cornwall Council | R203(1) | [5 empty] | 2002-05-28 |  | 2003-12-15
N00020M | 865 | 2012-05-21 | Grundon Waste / Viridor | Lakeside EfW | EfW Incineration |  |  | 30 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lakeside Road , Colnbrook , Slough | Buckinghamshire | South East | England |  | 502500 | 177500 | Slough Borough Council | P/09858/005 | [5 empty] | 1999-08-06 | [6 empty] | 2000-03-26 | [5 empty] | 2010-09-01
N00032M | 866 | 2007-09-03 | Surrey Waste Management / SITA UK | Capel Landfill Site | EfW Incineration |  |  | 1.3 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Capel Landfill site , Horsham Road , Capel | Surrey | South East | England |  | 517283 | 139031 | Mole Valley District Council | MO 00/0913 | [5 empty] | 2000-05-31 | 2001-12-16
N00051M | 867 | 2005-07-26 | HLC Projects Ltd / Compact Power | Oak Road | EfW Incineration |  |  | 3.7 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Oak Road Wrexham Industrial Estate Wrexham | Clwyd | Wales | Wales |  | 335000 | 350000 | Wrexham County Borough Council | P/2003/0547 | [6 empty] | 2005-07-26
N00053M | 868 | 2014-12-02 | HLC Projects Ltd / Compact Power | Bryn Lane Recycling | EfW Incineration |  |  | 5.2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Bryn Lane Wrexham | Clwyd | Wales | Wales |  | 338991 | 349994 | Wrexham County Borough Council | P/2005/0334 | [5 empty] | 2005-03-24 | 2005-10-25
N00060M | 869 | 2015-01-09 | Torino Limited | Red Scar Industrial Estate | Advanced Conversion Technologies |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Unit G10, Redscar Business Park, Longridge Road, Preston | Lancashire | North West | England | PR2 5LX | 358242 | 433287 | Lancashire County Council | 06/04/0197 | [5 empty] | 2004-02-19 | [6 empty] | 2004-05-12 |  |  |  | 2007-05-12
N00070M | 870 | 2011-07-13 | Ethos Energy | Avonmouth Pyrolysis Plant | Advanced Conversion Technologies |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Avonmouth Waste Transfer Kingsweston Lane Bristol BS11 0YS | Avon | South West | England |  | 353358 | 179393 | Bristol City Council | 04/02319/F | [5 empty] | 2004-08-31 | [6 empty] | 2004-11-19
N2052I2 | 871 | 2012-03-20 | TIRU/SAUR (UK) | Duncrue Road Energy from Waste Plant | EfW Incineration |  |  | 6.65 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | 31-39 Duncrue Road Belfast | Co. Down | Northern Ireland | Northern Ireland |  | 146660 | 527559 | Northern Ireland Planning Service | Z/1997/2681 | [5 empty] | 1997-08-22 |  | 2008-05-15
S0020L2 | 874 | 2001-09-24 | Dundee Energy Recycling | Baldovie | EfW Incineration |  |  | 8.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dundee | Tayside | Scotland | Scotland |  | 344500 | 733100 | Dundee City Council | [6 empty] | 1994-09-09 | [6 empty] | 1996-03-18 | [5 empty] | 2000-03-31
S0021L2 | 875 | 2013-10-08 | Global Environment ltd | Westfield MIW | EfW Incineration |  |  | 14.7 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Ballingrey Fife | Fife | Scotland | Scotland |  | 319400 | 698100 | Fife Council | 00/01118CNEA | [6 empty] | 2013-10-08
C2068 | 876 | 2016-03-23 | JCB Broadcrown | Wednesbury | Advanced Conversion Technologies |  |  | 3.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Portway Road, Wednesbury | West Midlands | West Midlands | England | WS10 7DZ | 398080 | 294961 | Sandwell Metropolitan Borough Council | DC/13/56344 | [5 empty] | 2013-09-12 | [6 empty] | 2013-12-02
A0471 | 877 | 2014-11-25 | Raynesway Resource Park UK Ltd | Derby Commercial Park EfW | EfW Incineration |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Phase 2, Raynesway East Development, Raynesway, Spondon, Derby | Derbyshire | East Midlands | England |  | 438608 | 334114 | Derby City Council | 06/09/00627 | APP/C1055/A/10/2137912/NWF |  |  |  |  | 2009-06-12 |  | 2010-04-13 | 2010-09-30 | 2010-11-01
AA568 | 878 | 2012-10-18 | Burts Wharf Resource Park Ltd And Standard Life Investment | Burts Wharf Resource Park | Advanced Conversion Technologies |  |  | 12.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Former Nufarm Uk Ltd, Crabtree Manorway North, Belvedere, Kent | Greater London | London | England |  | 550106 | 180346 | Bexley London Borough Council | 11/01715/FULMEA | [5 empty] | 2011-10-28 |  | 2012-06-27
AA659 | 879 | 2012-06-28 | COGEN (CEW) LIMITED | Lock Street Energy from Waste Plant | Advanced Conversion Technologies |  |  | 10.6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Ravenhead Glass Warehouse, Lock Street, St Helens, Merseyside, WA9 1HS. | Merseyside | North West | England |  | 351841 | 396197 | St Helens Council | P/2012/0020 | [5 empty] | 2012-01-06 |  | 2012-05-02
N00008M | 880 | 2005-03-11 | SITA UK | Altens Incinerator | EfW Incineration |  |  | 12 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Near Cove South Aberdeen | Grampian | Scotland | Scotland |  | 395500 | 801500 | Aberdeen City Council | A11844 | [5 empty] | 2001-10-25 |  | 2004-05-05
12033C4 | 883 | 2010-02-03 | City Energy | Parkwood Landfill | EfW Incineration |  |  | 12.25 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Warren Street Sheffield South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 436900 | 388200 | Sheffield City Council | 97/01585/REM | [5 empty] | 1997-10-22 | [6 empty] | 1997-12-11
IF1026 | 884 | 2013-02-14 | Clean Power Properties & Network Rail Infrastructure Ltd | Wheldon Road | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Castleford Wakefield WF10 2PP | West Yorkshire | Yorkshire and Humber | England |  | 444005 | 426240 | Wakefield Council | 12/01966/FUL | [5 empty] | 2012-10-05 | 2013-01-16
01013M5 | 885 | 2020-02-04 | Veolia | Cleanaway Project 3 | EfW Incineration |  |  | 27.8 | No |  |  |  | n/a | n/a | n/a | n/a | No Application Required | Awaiting Construction | Pitsea Hall Lane, Pitsea, Basildon, Essex | Essex | Eastern | England | SS16 4UH | 574100 | 185000 | Basildon Borough Council
A0003 | 886 | 2010-04-30 | Kent Enviropower (FCC Environment) | Allington EFW | EfW Incineration |  |  | 51 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Allington Quarry, Laverstoke Road, 20/20 Business Park, Allington, Maidstone, Kent | Kent | South East | England | ME16 0LE | 573764 | 157097 | Maidstone Borough Council | 98/1212 | [5 empty] | 1998-08-14 | [6 empty] | 2000-07-13 | [5 empty] | 2008-12-01
N00006M | 887 | 2004-11-29 | Mercia Waste Management / British Sugar Plc | British Sugar Site | EfW Incineration |  |  | 14 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | North Worcestershire IWMF, British Sugar Site, Stourport Road, Kidderminster | Hereford and Worcester | West Midlands | England |  | 383733 | 271107 | Wychavon District Council | WF990/001 | APP/E1855/A/01/1070998 |  |  |  |  | 2000-11-10 |  | 2002-07-10
N00007M | 888 | 2005-10-19 | Thames Waste Management | Slyfield Industrial Estate | EfW Incineration |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Slyfield Industrial Estate | Surrey | South East | England |  | 499500 | 152500 | Guildford Borough Council | GU 00/1421 | [5 empty] | 2000-07-14 |  | 2001-12-07
EN00176 | 889 | 2011-02-01 | Waste Recycling Group | Saltend Energy from Waste Facility | EfW Incineration |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Saltend, Hull | Humberside | Yorkshire and Humber | England |  | 515566 | 428683 | Kingston upon Hull City Council | 29745 - 06/05284/STPLFE | [5 empty] | 2006-06-30 | [6 empty] | 2007-01-01
N00039M | 890 | 2005-06-29 | Waste Recycling Group | Foster Street, Hull | EfW Incineration |  |  | 13 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Foster Street Hull | Durham | North East | England |  | 430568 | 510130 | Darlington Borough Council | 26438 | [5 empty] | 2000-12-04 |  | 2001-12-20
B1337 | 891 | 2018-07-19 | Innovative Environmental Solutions UK Ltd | Alexandra Dock | Advanced Conversion Technologies |  |  | 30 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Alexandra Branch Dock 1 Regent Road Bootle | Merseyside | North West | England |  | 333346 | 395020 | Sefton Council | S/2009/0640 | [5 empty] | 2009-08-12 | [6 empty] | 2010-02-11 |  |  |  | 2013-02-11
C1211 | 892 | 2016-11-30 | Air Products | Tees Valley Renewable Energy Facility - TV2 | Advanced Conversion Technologies |  |  | 49 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Reclamation Pond Development Area Huntsman Drive Seal Sands TS2 1TT | County Durham | North East | England |  | 451855 | 522830 | Stockton on Tees Borough Council | 13/0780/EIS | [5 empty] | 2013-04-15 | [6 empty] | 2013-07-15
01028C4 | 893 | 2012-08-29 | SITA UK | Edmonton 'B' CHP Plant | EfW Incineration |  |  | 18 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Advent Way Edmonton London | Greater London | London | England |  | 535800 | 192700 | Enfield London Borough Council | EL/98/0001 | [5 empty] | 1998-11-23 |  | 2002-05-23
02003C5 | 894 | 2012-08-29 | GLOBAL ENVIRONMENTAL LTD | Eastcroft Third Line CHP | EfW Incineration |  |  | 6.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Cattle Market Road, Nottingham, Nottinghamshire | Nottinghamshire | East Midlands | England |  | 458200 | 339100 | Nottingham City Council | 05/01520/PMFUL3 | [5 empty] | 2005-07-28 |  | 2006-09-28
02051C4 | 895 | 2012-08-29 | Coventry & Solihull WDC | Coventry | EfW Incineration |  |  | 4.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | The Lodge Bar Road Coventry West Midlands | West Midlands | West Midlands | England |  | 434700 | 277700 | Coventry City Council | [6 empty] | 1998-06-15 | [6 empty] | 1998-11-16 | [5 empty] | 2001-09-28
07077M3 | 897 | 2014-01-07 | Associated Energy Projects plc | Ardwick Railway Goods Yard Incinerator (Newhaven EFW Plant) | EfW Incineration |  |  | 33.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ardwick Railway Goods Yard Ardwick Manchester | Greater Manchester | North West | England |  | 386300 | 397500 | Manchester City Council | [19 empty] | 2011-08-01
07081C4 | 898 | 2012-08-29 | Viridor (GMWDA) | Bolton TRF | EfW Incineration |  |  | 10.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bolton Waste Incinerator, Raikes Lane , Bolton | Greater Manchester | North West | England | BL4 0JR | 373100 | 407900 | Bolton Metropolitan Borough Council | [6 empty] | 1996-12-16 | [6 empty] | 1997-05-30 | [5 empty] | 2001-06-01
08032M4 | 899 | 2012-07-26 | Veolia | North Quay ERF | EfW Incineration |  |  | 18.31 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | North Quay Road , Newhaven , East Sussex | East Sussex | South East | England |  | 547700 | 101700 | Lewes District Council | LW462/CM(EIA) | [5 empty] | 2005-12-02 | [6 empty] | 2007-02-21 |  |  |  |  | 2009-08-01 | 2012-02-01
11023C5 | 901 | 2013-10-08 | Atlantic Energy / Sidknowles Energy | Dolcoath Energy | EfW Incineration |  |  | 7.75 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | South Crofty, Dudnance Lane, Pool, Redruth, Cornwall | Cornwall | South West | England |  | 166400 | 40600 | Cornwall Council | PA03/000951/F | [5 empty] | 2003-01-22 | [6 empty] | 2000-11-15
12032M5 | 902 | 2013-01-28 | British Sugar | Brigg Energy Resource Centre | EfW Incineration |  |  | 19.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Scawby Brook, Brigg, South Humberside | Humberside | Yorkshire and Humber | England |  | 498900 | 406100 | North Lincolnshire Council | PA/2004/0918 | [5 empty] | 2004-05-26 | 2004-08-16
12049M3 | 903 | 2014-03-14 | Veolia | Sheffield ERF | EfW Incineration |  |  | 19.3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Sheffield Incinerator Bernard Road Sheffield Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 436800 | 387900 | Sheffield City Council | [6 empty] | 1996-01-16 | [6 empty] | 1996-03-07 | [5 empty] | 1999-03-31
A0015 | 904 | 2012-08-02 | Covanta | Midpoint 18 Business Park | EfW Incineration |  |  | 35.5 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Pochin Way, Middlewich, Cheshire | Cheshire | North West | England | CW10 0TE | 371517 | 366014 | Cheshire East Council | 09/0738W | [5 empty] | 2009-03-17 |  | 2011-04-29 |  |  | 2012-07-23
A0147 | 905 | 2016-01-20 | Viridor | Peterborough EfW | EfW Incineration |  |  | 7.25 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fourth Drove, Fengate, Peterborough, Cambs. PE1 5UR | Cambridgeshire | Eastern | England |  | 521658 | 299003 | Peterborough City Council | 09/00078/MMFUL | [5 empty] | 2009-02-15 | [6 empty] | 2010-05-06 |  |  |  |  | 2013-06-24 | 2016-01-19
A0329 | 906 | 2020-02-27 | Tata Chemicals Europe (formerly Brunner Mond & E.on) | Lostock | EfW Incineration |  |  | 60 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Northwich, Cheshire | Cheshire | North West | England | CW9 7WL | 366164 | 373928 | DECC (S36) | S36 | [5 empty] | 2010-02-25 | [6 empty] | 2012-10-02
A0481 | 907 | 2012-11-19 | Viridor | New England Resource Recovery EfW | EfW Incineration |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Disused New England Quarry, Lee Mill, near Ivybridge to the east of Plymouth | Devon | South West | England |  | 259440 | 54699 | Devon County Council | DCC/2975/2010 | [5 empty] | 2010-01-19 |  | 2012-10-24
A0495 | 908 | 2019-12-09 | AssestGen Partner / Hoddesdon Energy | Ratty's Lane Sustainable Energy Facility (ACT) | Advanced Conversion Technologies |  |  | 9.6 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Ratty’s Lane, Hoddesdon | Hertfordshire | Eastern | England | EN11 0RG | 538126 | 209495 | Hertfordshire County Council | 7/0510-10 | [5 empty] | 2010-06-28 | [6 empty] | 2012-03-26 |  |  |  | 2015-03-26 | 2016-07-25
AA096 | 909 | 2018-07-04 | Scotgen (South Lanarkshire) | Carlisle Road RRF | Advanced Conversion Technologies |  |  | 7 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Carlisle Road Stonehouse Larkhall South Lanarkshire | Strathclyde | Scotland | Scotland | ML9 3PR | 277519 | 646369 | South Lanarkshire Council | HM/10/0345 | [5 empty] | 2010-07-02 | [6 empty] | 2011-02-25 |  |  |  | 2014-02-25
AA122 | 910 | 2015-06-24 | Veolia | Battlefield EfW | EfW Incineration |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Vanguard Way, Shrewsbury, Shropshire | Shropshire | West Midlands | England | SY1 3TG | 351002 | 316351 | Shropshire Council | SC/MS2009/0125/SY | 11/01876/REF |  |  |  |  | 2009-01-21 |  | 2010-09-22 |  |  |  | 2012-01-10 | 2012-01-10 |  |  |  |  | 2013-03-31 | 2015-05-01
AA135 | 911 | 2014-05-19 | Veolia | Four Ashes EfW | EfW Incineration |  |  | 23 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | The Dell, Enterprise Drive, Four Ashes, Wolverhampton | Staffordshire | West Midlands | England |  | 392139 | 308482 | Staffordshire County Council | SS.10/16/636 | [5 empty] | 2010-08-19 | [6 empty] | 2011-02-18 |  |  |  |  | 2011-06-01 | 2014-05-14
AA177 | 912 | 2014-03-12 | Viridor | Salford Refuse Treatment Plant (AD) | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cobden Street, Salford | Greater Manchester | North West | England | M6 6NA | 381036 | 399888 | Salford City Council | 07/55275/FUL | [5 empty] | 2007-08-15 | [6 empty] | 2008-03-06 |  |  |  |  | 2010-11-01 | 2013-11-30
AA233 | 913 | 2014-01-21 | Warwick Energy | Alfreton WtE | Advanced Conversion Technologies |  |  | 5.2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Pye Bridge Industrial Estate, Somercotes, Alfreton, Derbyshire | Derbyshire | East Midlands | England |  | 443625 | 352932 | Derbyshire County Council | CW6/0210/203 | [5 empty] | 2010-02-23 | 2013-11-29
AA404 | 914 | 2018-07-04 | SUEZ | Cornwall ERC | EfW Incineration |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Rostowrack Farm Wheal Remfry, Goonvean And Parkandillick St Dennis | Cornwall | South West | England | PL26 8DY | 194637 | 56502 | Cornwall Council | C2/08/00761 | APP/D0840/A/09/2113075 |  |  |  |  | 2008-05-14 |  | 2012-07-10 |  |  |  | 2011-05-19 | 2011-05-19 |  |  |  |  | 2012-08-06 | 2017-04-04
AA439 | 915 | 2016-12-20 | Avonmouth Biopower | Avonmouth | Advanced Conversion Technologies |  |  | 6.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | New Earth Solutions Former Britannia Zinc Site Kings Weston Lane Lawrence Weston Bristol BS11 8HT | Avon | South West | England |  | 352153 | 179196 | Bristol City Council | 10/02837/F | [5 empty] | 2010-06-30 | [6 empty] | 2010-10-18 | [5 empty] | 2013-06-17
AA464 | 916 | 2012-11-20 | New Earth Energy | Canford | Advanced Conversion Technologies |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Magna Road, Poole | Dorset | South West | England | BH21 3AP | 404168 | 97469 | Poole Borough Council | APP/09/00810/C and APP/11/01669/C | [5 empty] | 2009-07-20 | [6 empty] | 2009-09-11 | [5 empty] | 2011-07-01
AA465 | 917 | 2013-08-12 | New Earth Energy | Dorset Green Technology Park | Advanced Conversion Technologies |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land at Dorset Green Technology Park, Winfrith, Dorchester, Dorset | Dorset | South West | England |  | 381981 | 87135 | Dorset County Council | 6/2010/0172 | [5 empty] | 2010-03-17 | [6 empty] | 2011-03-09
AA497 | 918 | 2016-12-19 | SITA UK | Severnside Energy Recovery Centre | EfW Incineration |  |  | 32 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Severnside Works, Severn Road, Hallen, Bristol, South Gloucestershire | Avon | South West | England | BS10 7SP | 354653 | 182612 | South Gloucestershire Council | PT09/5982/FMW | 10/00058/REFUS |  |  |  |  | 2009-12-03 |  | 2010-07-28 |  |  |  | 2011-09-15 | 2011-09-15 |  |  |  |  | 2014-01-06 | 2016-12-14
AA651 | 919 | 2018-03-15 | Energy Works / The Spencer Group | Energy Works (Hull) | Advanced Conversion Technologies |  |  | 25 | Yes |  |  | 25 | n/a | n/a | n/a | n/a | Operational | Operational | Cleveland Street (former Adm Cocoa Plant), Dalton Street, Kingston Upon Hull | Humberside | Yorkshire and Humber | England |  | 510170 | 430424 | Kingston upon Hull City Council | 11/00615/CM | [5 empty] | 2011-06-27 | [6 empty] | 2011-10-20 |  |  |  |  | 2016-01-05 | 2018-03-01
AA726 | 920 | 2013-12-02 | Goodman International | Avonmouth Resource Park | Advanced Conversion Technologies |  |  | 12.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Plot M2 Kings Weston Lane Avonmouth Bristol | Avon | South West | England |  | 352372 | 180028 | Bristol City Council | 09/00608/F | N/A |  |  |  |  | 2009-02-27 | [6 empty] | 2009-05-28
AA735 | 921 | 2013-01-21 | Biossence / Atco | East London Sustainable Energy Facility (Thames Gateway Power facility) | Advanced Conversion Technologies |  |  | 13 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Adj Fairview Industrial Park within Ford Motor Company, Frog Island, Rainham, Essex, RM13 | Greater London | London | England |  | 550656 | 181287 | Havering London Borough Council | U0004.06 | N/A |  |  |  |  | 2006-05-08 | [6 empty] | 2008-07-02
AA741 | 922 | 2018-06-04 | Viridor | Trident Park | EfW Incineration |  |  | 30 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land at Trident Park, Glass Avenue, Cardiff | South Glamorgan | Wales | Wales | CF24 5EN | 320179 | 175481 | Cardiff Council | 10/00149/E | [5 empty] | 2010-02-01 | [6 empty] | 2010-06-29 |  |  |  |  | 2012-07-30 | 2015-03-10
AA841 | 923 | 2012-11-19 | ORGANIC WASTE MANAGEMENT (ST HELENS) | Ravenhead Glassworks Bioenergy Plant | EfW Incineration |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | THE OLD RAVENHEAD GLASSWORKS, RAVENHEAD ROAD, ST HELENS, MERSEYSIDE, WA10 3XP | Merseyside | North West | England |  | 350714 | 394493 | St Helens Council | P/2012/0535 | [5 empty] | 2012-07-11 |  | 2012-09-18
AA891 | 924 | 2014-05-09 | Lincolnshire County Council | Lincoln EFW | EfW Incineration |  |  | 16.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | North Hykeham Landfill Site, Whisby Road, Lincoln, Lincolnshire, LN6 3QZ. | Lincolnshire | East Midlands | England |  | 493142 | 367809 | Lincolnshire County Council | N43\1186\08 | [5 empty] | 2008-11-28 | [6 empty] | 2009-03-16 |  |  |  |  | 2011-05-30 | 2014-03-14
AA944 | 925 | 2014-04-30 | SITA UK | North East Energy Recovery Centre (adjacent to Teesside EfW) | EfW Incineration |  |  | 21 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Haverton Hill Road, Billingham | County Durham | North East | England | TS23 1PY | 448016 | 522664 | Stockton on Tees Borough Council | 08/2469/EIS | [5 empty] | 2008-07-31 | [6 empty] | 2008-10-30 |  |  |  |  | 2011-05-10 | 2014-04-30
B0149 | 926 | 2020-06-05 | SITA UK/Binn Group | Binn Eco Park | Advanced Conversion Technologies |  |  | 4.64 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Glenfarg, Perthshire | Tayside | Scotland | Scotland | PH2 9PX | 317233 | 713295 | Perth and Kinross Council | 10/01767/FLM | [5 empty] | 2010-10-05 | [6 empty] | 2011-10-20
B0294 | 927 | 2015-02-18 | Cory Environmental | Willows power and recycling centre (EfW) | EfW Incineration |  |  | 24.2 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land at The Willows Business Park, High (Saddlebow) Road, Saddlebow Industrial Area, King's Lynn | Norfolk | Eastern | England | PE34 3RD | 561105 | 317203 | Norfolk County Council | C/2/2011/2020 |  | APP/X2600/V/12/2183389 |  |  |  | 2011-06-10 | [7 empty] | 2012-08-30
B0458 | 928 | 2020-04-29 | Viridor | Glasgow Renewable Energy and Recycling Centre (ACT) | Advanced Conversion Technologies |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Polmadie Disposal Complex, 425 Polmadie Road, Glasgow | Strathclyde | Scotland | Scotland | G42 0PJ | 259509 | 662366 | Glasgow City Council | 12/01631/DC | [5 empty] | 2012-08-14 | [6 empty] | 2013-01-29 |  |  |  |  | 2013-11-18 | 2019-08-01
B0733 | 929 | 2014-03-20 | Shanks / Bricckiln / Sisk | Maydown | Advanced Conversion Technologies |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Enviroparc, Electra Road, Derry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 6UL | 98900 | 534400 | Northern Ireland Planning Service | A/2009/0211/F | [5 empty] | 2009-03-27 | [6 empty] | 2011-09-16
B0751 | 930 | 2018-07-04 | SUEZ / Sembcorp UK | Wilton 11 EfW | EfW Incineration |  |  | 49 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wilton International, Wilton, Middlesbrough, Cleveland | Cleveland | North East | England |  | 458500 | 519500 | Redcar and Cleveland Borough Council | R/2010/0621/CL | [5 empty] | 2010-08-11 | [6 empty] | 2010-10-06 |  |  |  |  | 2014-10-21 | 2017-04-04
C1512 | 931 | 2014-05-14 | WASTE TO ENERGY (NW) | Lock Street Energy from Waste Plant (resubmission) | EfW Incineration |  |  | 10.6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Ravenhead Glass Warehouse, Lock Street, St Helens, Merseyside, WA9 1HS. | Merseyside | North West | England |  | 351833 | 396174 | St Helens Council | P/2013/0475 | [5 empty] | 2013-06-21 |  | 2014-03-31
EN00545 | 932 | 2019-03-21 | INEOS Chlor / Viridor-Laing | Runcorn EfW | EfW Incineration |  |  | 100 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Picow Farm, Weston Point, in Runcorn, Cheshire | Cheshire | North West | England |  | 349985 | 381240 | DECC (S36) | [6 empty] | 2007-01-19 | [6 empty] | 2008-09-16 |  |  |  |  | 2009-06-08 | 2013-06-08
EN00561 | 933 | 2012-02-27 | Bedminster BioEnergy Solution | Bedminster BioEnergy Facility | EfW Incineration |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Lostock Works, Griffiths Road, Northwich in Cheshire | Cheshire | North West | England | CW9 7LS | 367555 | 374155 | Cheshire West and Chester Council | [6 empty] | 2007-12-14 | [6 empty] | 2008-04-21
IF1007 | 934 | 2013-08-30 | Clean Power Properties | Brierley Hill Energy Recovery Centre | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Brierley Hill Freight and Steel Terminal, Moor Street, Brierley Hill, West Midlands, DY5 3SN | West Midlands | West Midlands | England | DY5 3SN | 391166 | 286880 | Dudley Metropolitan Borough Council | P12/1287 | [5 empty] | 2012-10-08 |  | 2013-08-28
IF1046 | 935 | 2016-08-11 | Veolia | Cross Green ERF | EfW Incineration |  |  | 11.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Former Wholesale Market Site Newmarket Approach, Cross Green Industrial Estate, Leeds, LS9 0QB | West Yorkshire | Yorkshire and Humber | England |  | 432800 | 432549 | Leeds City Council | 12/02668/FU | [5 empty] | 2012-06-27 | [6 empty] | 2013-02-08 |  |  |  |  | 2013-10-04 | 2016-04-20
N00002M | 936 | 2011-12-06 | SITA UK | Copyhold Works Incinerator Resubmission | EfW Incineration |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Copyhold Works Nutfield Road Redhill Surrey | Surrey | South East | England |  | 528800 | 150400 | Reigate and Banstead Borough Council | RE00/0910 | [5 empty] | 2000-02-01 |  | 2001-12-06
N00003M | 937 | 2013-01-29 | EQ-Gen | Breg | Advanced Conversion Technologies |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Weldon Road Northamptonshire | Northamptonshire | East Midlands | England |  | 490060 | 288853 | Corby Borough Council | 01/00283/COC | [5 empty] | 2001-07-30 | [6 empty] | 2001-11-20
N00052M | 938 | 2015-01-06 | Glenfarm | Glenavy Incinerator | EfW Incineration |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | 29 Ballyvannon Rd, Glenavy | Co. Antrim | Northern Ireland | Northern Ireland |  | 123848 | 531430 | Northern Ireland Planning Service | S/1998/0162 | [5 empty] | 1998-03-04 | [6 empty] | 2001-06-07 |  |  |  | 2006-06-07
AA158 | 939 | 2014-11-04 | Viridor | Exeter EfW | EfW Incineration |  |  | 13 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Grace Road South, Marsh Barton Trading Estate, Exeter | Devon | South West | England | EX2 8QE | 292605 | 90422 | Exeter City Council | 07/0927/25 | [5 empty] | 2007-04-26 | [6 empty] | 2007-06-27 |  |  |  |  | 2012-04-01 | 2014-10-16
AA501 | 940 | 2019-12-09 | Reform Energy | Fleetwood Energy Centre | EfW Incineration |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Wyre Waste Recycling, Jameson Road, Fleetwood | Lancashire | North West | England |  | 333039 | 445726 | Wyre Borough Council | 11/00671/LCC | [5 empty] | 2011-09-15 | [6 empty] | 2011-11-17
AA565 | 941 | 2015-11-05 | MVV Environment | North Yard EfW | EfW Incineration |  |  | 22.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land at North Year, H. M. Naval Base Devenport, Close to Weston Mill Creek and Viaduct, Plymouth | Devon | South West | England | PL2 2DQ | 244810 | 57524 | Plymouth City Council | 11/00750/FUL | [5 empty] | 2011-05-10 | [6 empty] | 2012-02-03 |  |  |  |  | 2012-03-01 | 2015-04-27
AA874 | 942 | 2020-04-29 | Viridor | Beddington EfW | EfW Incineration |  |  | 26 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beddington Farmlands Waste Management Facility, Beddington Lane, Beddington | Greater London | London | England | CR0 4TD | 529039 | 166236 | Sutton London Borough Council | D2012/66220 | [5 empty] | 2012-07-25 | [6 empty] | 2013-05-15 |  |  |  |  | 2015-12-01 | 2019-11-01
B0003 | 943 | 2019-12-04 | Premier Aggregates | Finmere Quarry | Advanced Conversion Technologies |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Finmere Quarry, Banbury Road, Finmere, Buckingham, Buckinghamshire | Oxfordshire | South East | England | MK18 4AJ | 462416 | 233212 | Cherwell District Council | 11/00015/CM | [5 empty] | 2011-01-06 | [6 empty] | 2011-01-28
B0310 | 944 | 2015-10-06 | Zero Waste Project | Millerhill EfW | EfW Incineration |  |  | 7.5 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Former Millerhill Marshalling Yards, Whitehill Mains Road, Millerhill, Dalkeith, Midlothian | Lothian | Scotland | Scotland |  | 332400 | 670800 | Midlothian Council | 11/00174/PPP | [5 empty] | 2011-03-11 | [6 empty] | 2012-01-19
IF1045 | 946 | 2020-01-24 | E.ON / Wheelabrator Technologies | K3 CHP Facility (Kemsley EfW) | EfW Incineration |  |  | 45 | Yes |  |  | 45 | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land to the East of Kemsley Paper Mill, Kemsley, Sittingbourne, Kent | Kent | South East | England | ME10 2TD | 592144 | 166704 | Kent County Council | SW/10/444 | [5 empty] | 2010-03-23 | [6 empty] | 2010-07-13 |  |  |  |  | 2016-09-30
C3133 | 947 | 2016-01-06 | Devon Waste Management | Deep Moor Waste Management Facility - Energy Recovery Facility | EfW Incineration |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Devon Waste Management Ltd, Deepmoor Landfill Site, High Bullen, Torrington | Devon | South West | England | EX38 7JA | 253005 | 120813 | Devon County Council | DCC/3664/2014 | [5 empty] | 2014-05-19 | 2015-12-21
AA104 | 948 | 2017-03-08 | Air Products | Tees Valley Renewable Energy Facility - TV1 | Advanced Conversion Technologies |  |  | 49 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Reclamation Pond, Huntsman Drive Seal Sands | County Durham | North East | England |  | 444971 | 518650 | Stockton on Tees Borough Council | 11/0359/EIS | [5 empty] | 2011-02-15 | [6 empty] | 2011-08-09 |  |  |  |  | 2012-08-07
AA246 | 949 | 2017-02-20 | Tata Steel (formerly Corus UK) | Shotton Works CHP | EfW Incineration |  |  | 12 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Corus, Shotton Works, Weighbridge Road, Deeside Industrial Park, Deeside, CH5 2NH | Clwyd | Wales | Wales |  | 329786 | 370622 | Flintshire County Council | 046316 | [5 empty] | 2009-05-18 | [6 empty] | 2010-01-20 |  |  |  | 2015-01-20
AA409 | 950 | 2017-02-23 | IES (Chinook Energy) | Oldbury | Advanced Conversion Technologies |  |  | 40 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | NCP Vehicle Compound, Union Road, Oldbury, West Midlands | West Midlands | West Midlands | England | B69 3EL | 398141 | 290999 | Sandwell Metropolitan Borough Council | DC/10/52897 | [5 empty] | 2011-01-11 | [6 empty] | 2011-12-01 |  |  |  |  | 2012-06-30 | 2014-01-15
AA696 | 951 | 2019-12-20 | Clean Power Properties & Network Rail Infrastructure Ltd | Willesden | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Willesden Junction Freight Terminal Site, Channel Gate Road, Willesden, London, NW10 6UQ | Greater London | London | England |  | 521379 | 182799 | Ealing London Borough Council | PP/2012/3267 | [5 empty] | 2012-08-03 |  | 2019-12-10
AA855 | 952 | 2014-07-23 | Clean Power Properties & Network Rail Infrastructure | Washwood | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Washwood Heath Energy Recovery Centre | West Midlands | West Midlands | England |  | 410878 | 289562 | Birmingham City Council | 2012/05409/PA | [5 empty] | 2012-08-08 | [6 empty] | 2012-11-23 |  |  |  | 2015-11-22
B0663 | 953 | 2019-12-19 | E.ON / EQT (Becon) | Hightown Quarry EfW | EfW Incineration |  |  | 14 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Hightown Quarry, 40 Boghill Road, Ballyutoag, Templepatrick, Antrim BT36 4QS | Co. Antrim | Northern Ireland | Northern Ireland |  | 141893 | 537064 | Northern Ireland Planning Service | T/2014/0114/F | [5 empty] | 2014-03-27
H0086 | 954 | 2019-07-31 | Lisburn Energy Recovery Ltd | Lisburn | Advanced Conversion Technologies |  |  | 7 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Lissue Industrial Estate, Moira Road, Lisburn | Co. Down | Northern Ireland | Northern Ireland | BT28 2RF | 128144 | 522925 | Northern Ireland Planning Service | S/2010/0041/F | [5 empty] | 2010-01-19 | [6 empty] | 2013-07-11 |  |  |  | 2018-07-11
IF1020 | 955 | 2014-07-23 | Singleton Birch / Energos | Melton Ross | Advanced Conversion Technologies |  |  | 5.75 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Brigg Road, Melton Ross, Croxton | Humberside | Yorkshire and Humber | England | DN38 6AE | 509093 | 411749 | North Lincolnshire Council | WD/2008/0044 | [5 empty] | 2008-01-08 | [6 empty] | 2008-11-05
B1030 | 956 | 2020-04-29 | Syngas Products/ Canford Renewable Energy Ltd | Canford | Advanced Conversion Technologies |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Magna Road, Poole BH21 3AP | Dorset | South West | England |  | 403439 | 96722 | Poole Borough Council | APP/12/01559/F | [5 empty] | 2012-11-21 | [6 empty] | 2013-07-01 |  |  |  |  | 2015-01-01
B1063 | 957 | 2020-06-04 | Bombardier | Belfast Harbour Estate | EfW Incineration |  |  | 14.85 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | 7 Airport Road, Belfast | Co. Down | Northern Ireland | Northern Ireland | BT3 9DY | 149599 | 531901 | Northern Ireland Planning Service | Z/2012/1387/F | [5 empty] | 2012-12-19 | [6 empty] | 2014-01-23 |  |  |  | 2019-01-23 | 2016-01-25
C2238 | 958 | 2015-09-02 | Teal Energy Ltd | Manor Way Business Park | Advanced Conversion Technologies |  |  | 23 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Manor Way Business Park, Swanscombe, Kent | Kent | South East | England |  | 560787 | 174975 | Kent County Council | KCC/DA/0201/2013 |  | APP/W2275/V/14/2228465 |  |  |  | 2013-07-25 | 2015-07-27
C2310 | 959 | 2020-06-17 | Clean Power Properties | Eastleigh | EfW Incineration |  |  | 12 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Chickenhall Lane, Eastleigh Central, Eastleigh | Hampshire | South East | England | SO50 6RQ | 446272 | 118254 | Hampshire County Council | S/13/73507 | [5 empty] | 2013-10-25 | [6 empty] | 2014-03-31 |  |  |  | 2017-03-31
AA566 | 960 | 2018-04-05 | AmeyCespa | Allerton Waste Recovery Park (EfW) | EfW Incineration |  |  | 27 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | nr. Knaresborough, North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 440675 | 459799 | North Yorkshire County Council | NY/2011/0328/ENV | [5 empty] | 2011-10-12 | [6 empty] | 2012-10-01 |  |  |  |  | 2015-02-15 | 2018-03-04
A0035 | 962 | 2014-12-31 | Viridor | Ardley EfW | EfW Incineration |  |  | 24 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Middleton Stoney Road, Ardley, Bicester, Oxon | Oxfordshire | South East | England | OX25 3TH | 453074 | 220584 | Oxfordshire County Council | MW.0078/10 | [5 empty] | 2010-03-31 |  | 2011-08-18 |  |  |  | 2011-08-18 | 2011-08-18 |  |  |  |  | 2011-12-01 | 2014-10-24
B1464 | 963 | 2019-12-09 | Balfour Beatty Capital | Avonmouth BioEnergy Facility | Advanced Conversion Technologies |  |  | 11 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Land Eastern Side Of Chittening Trading Estate, Greensplott Road, Avonmouth, Bristol | Avon | South West | England |  | 353395 | 181643 | Bristol City Council | 14/03210/F | APP/Z0116/A/14/2228846 |  |  |  |  | 2014-07-01 |  | 2014-11-07 |  |  |  | 2015-04-29 | 2015-04-29
C1557 | 964 | 2019-11-21 | Waste2Tricity (Peel Energy / Bilsthorpe Waste) | Bilsthorpe Energy Centre | Advanced Conversion Technologies |  |  | 9.6 | No |  |  |  | n/a | n/a | n/a | n/a | Secretary of State - Granted | Awaiting Construction | Bilsthorpe Business Park, Eakring Road, Bilsthorpe, Nottingham, Nottinghamshire | Nottinghamshire | East Midlands | England | NG22 8ST | 466142 | 359180 | Nottinghamshire County Council | ES/2950 |  | APP/L3055/V/14/3001886 | Call-In |  |  | 2013-11-29 | [6 empty] | 2016-06-01 | 2014-12-19 |  | 2016-06-01
AA157 | 965 | 2020-06-04 | Energos (formerly Biogen Power) | Bradford Energy Recovery Facility | EfW Incineration |  |  | 12.85 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Former Solaglas Site, Ripley Road, Bradford, West Yorkshire, BD4 7TP | West Yorkshire | Yorkshire and Humber | England |  | 416566 | 431792 | Bradford Metropolitan District Council | 13/01257/FUL | [5 empty] | 2013-04-01 | [6 empty] | 2013-06-26 |  |  |  | 2016-06-26
B0568 | 966 | 2015-01-09 | E R I Neath Port Talbot | Crymlyn Burrows EfW Incinerator | EfW Incineration |  |  | 2.5 | No |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | The Former Freightliner Depot, Jersey Marine, Crymlyn Burrows, Swansea | West Glamorgan | Wales | Wales | SA1 8PZ | 269849 | 193362 | Neath Port Talbot County Borough Council | P1998/1234 | [5 empty] | 1998-10-21 | [6 empty] | 1999-04-23 |  |  |  |  | 2000-09-30 | 2002-01-01
B1339 | 967 | 2019-10-01 | Grundon | New Circular Technology Park | Advanced Conversion Technologies |  |  | 14 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | New Circular Technology Park (Former Ford Blockworks), Ford Airfield Industrial Estate, Ford, Arundel, West Sussex, BN18 0HY | West Sussex | South East | England |  | 499368 | 103388 | West Sussex County Council | WSCC/096/13/F | [5 empty] | 2013-11-21 | [6 empty] | 2014-05-27 |  |  |  | 2017-05-27
AA589 | 968 | 2016-02-25 | FCC Environment | Greatmoor EfW | EfW Incineration |  |  | 22 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Greatmoor Farm At Southern End Of WRG's Ownership Of Land At Calvert, Bicester Road, Woodham, Buckinghamshire | Buckinghamshire | South East | England |  | 468957 | 224446 | Buckinghamshire County Council | 11/20000/AWD | [5 empty] | 2011-02-18 | [6 empty] | 2012-07-26 |  |  |  |  | 2013-09-30 | 2016-02-23
A0470 | 969 | 2017-02-20 | Covanta | Green Hills | EfW Incineration |  |  | 21 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Drumshangie, North Lanarkshire | Strathclyde | Scotland | Scotland |  | 277564 | 667080 | North Lanarkshire Council | 08/01023/FUL | [5 empty] | 2008-07-08 | [6 empty] | 2009-05-07 |  |  |  | 2014-05-07
EN00091 | 970 | 2018-04-25 | Peel Environmental | Ince Resource and Recovery Park | EfW Incineration |  |  | 35 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Chester, Cheshire. CH1 3AN | Cheshire | North West | England |  | 345500 | 376500 | DECC (S36) | 09/01120/COU | [5 empty] | 2006-01-30 | [6 empty] | 2009-08-11
B1508 | 971 | 2019-12-17 | Combined Power And Heat (Highlands) | Invergordon EfW | EfW Incineration |  |  | 4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land At Cromarty Firth Industrial Estate Invergordon Highland | Highland | Scotland | Scotland | IV18 0LT | 271222 | 870387 | Highland Council | 08/00455/FULRC | PPA-270-2017-2 |  |  | 41884 |  | 2008-06-05 |  | 2009-08-24 | 2009-11-20 |  | 2019-10-15
A0069 | 972 | 2020-03-20 | Energos | Knowsley ERF | Advanced Conversion Technologies |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Penrhyn Road/Villiers Road, Knowsley Business Park, Prescot, Merseyside. L34 9HY | Merseyside | North West | England |  | 343032 | 396683 | Knowsley Metropolitan Borough Council | 08/00474/FUL | [5 empty] | 2008-07-10 | [6 empty] | 2009-05-19
AA644 | 973 | 2020-04-23 | Thermeco (Seneca) | Melton Energy from Waste Plant | Advanced Conversion Technologies |  |  | 24 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South West Of Melton Waste Park Gibson Lane South Melton East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 496737 | 425344 | East Riding of Yorkshire Council | 11/05606/STPLF | [5 empty] | 2011-12-22 | [6 empty] | 2012-03-20
C0150 | 974 | 2015-10-29 | Clean Power Properties & Network Rail Infrastructure Ltd | Micheldever | Advanced Conversion Technologies |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Micheldever Rail Sidings, Overton Road, Micheldever Station, Winchester | Hampshire | South East | England | SO21 3AN | 451868 | 143268 | Hampshire County Council | 12/02013/HCS | APP/Q1770/W/14/3001572 |  |  |  |  | 2012-12-13 |  | 2014-06-10 | 2015-01-26 | 2015-10-29
B0576 | 975 | 2019-08-09 | AmeyCespa | Milton Keynes Waste Recovery Park | Advanced Conversion Technologies |  |  | 7 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Dickens Road, Old Wolverton, Milton Keynes | Buckinghamshire | South East | England | MK12 5QQ | 481336 | 241639 | Milton Keynes Council | 13/00861/FULEIS | [5 empty] | 2013-04-26 | [6 empty] | 2013-07-12 |  |  |  |  | 2014-06-03 | 2018-03-01
A0193 | 976 | 2015-01-13 | Multifuel Energy (SSE & Wheelabrator) | Newhurst Quarry - Revised | EfW Incineration |  |  | 33 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Ashby Road East, Shepshed. Leicestershire | Leicestershire | East Midlands | England |  | 448680 | 317986 | Leicestershire County Council | 2011/1119/02 | APP/M2460/A/11/2150748 |  |  |  |  | 2011-04-26 |  | 2011-10-13 |  |  |  | 2012-06-28 | 2012-06-28
A0491 | 977 | 2020-06-19 | Banks Renewables | Pond Green Energy Park | Advanced Conversion Technologies |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Whitburn Road, Bathgate, West Lothian | Lothian | Scotland | Scotland |  | 296452 | 667203 | West Lothian Council | 0086/FUL/09 | [5 empty] | 2009-02-24 | [6 empty] | 2011-03-08
01002M5 | 978 | 2019-01-29 | Gent Fairhead Environmental Services | Wren Power and Pulp (Rivenhall Airfield) | EfW Incineration |  |  | 49.75 | Yes |  |  | 49.75 | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Woodhouse Farm, Near Braintree, Essex | Essex | Eastern | England |  | 582400 | 220500 | Essex County Council | ESS/37/08/BTE | [5 empty] | 2008-09-08 | [6 empty] | 2010-03-02 |  |  |  | 2015-03-02
A0336 | 979 | 2020-02-04 | Veolia/Covanta | Rookery South | EfW Incineration |  |  | 65 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Rookery South, a former brick clay pit, near Stewartby, Bedfordshire | Bedfordshire | Eastern | England |  | 501063 | 242971 | The Planning Inspectorate - National Infrastructure | EN010011 | [5 empty] | 2010-08-05 | [6 empty] | 2011-10-13 |  |  |  |  | 2018-01-15
AA469 | 980 | 2020-05-27 | BH Energy Gap | The WandE, Doncaster | Advanced Conversion Technologies |  |  | 20 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Sandall Stones Road, Kirk Sandall, Kirk Sandall Industrial Estate, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | DN3 1Q | 460712 | 407099 | Doncaster Metropolitan Borough Council | 09/00246/TIPA | [5 empty] | 2009-02-05 | [6 empty] | 2009-07-21
IF1132 | 981 | 2020-04-23 | Seneca Global Energy | Seal Sands | Advanced Conversion Technologies |  |  | 24 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Billingham, Cleveland, TS23 3NF | County Durham | North East | England |  | 453150 | 524496 | Stockton on Tees Borough Council | 12/2766/EIS | [5 empty] | 2012-11-20 | [6 empty] | 2013-04-29
A0070 | 982 | 2018-03-29 | Energos | Shewalton (Irvine Plant) | Advanced Conversion Technologies |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Irvine, Strathclyde | Strathclyde | Scotland | Scotland | KA11 5DF | 234665 | 639169 | North Ayrshire Council | 07/00072/PP | [5 empty] | 2007-01-17 | [6 empty] | 2009-01-16 |  |  |  | 2012-01-16
A0378 | 983 | 2018-04-27 | Shanks/ Resource Recovery Solutions (Derbyshire) Ltd | Sinfin Lane | Advanced Conversion Technologies |  |  | 7.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Disused land adjacent 1 - 5 Railway Cottages, Sinfin Lane, Sinfin, Derby | Derbyshire | East Midlands | England |  | 435118 | 332969 | Derby City Council | 05/09/00571 | APP/C1055/A/10/2124772/NWF |  |  |  |  | 2009-05-27 |  | 2010-01-05 |  |  |  | 2010-11-16 | 2010-11-16 |  |  |  |  | 2016-01-01 | 2018-02-16
AA906 | 984 | 2020-06-09 | Peel Environmental | Southmoor Energy Centre | EfW Incineration |  |  | 26 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Kellingley Colliery, Weeland Road, Beal, Goole, North Humberside | Humberside | Yorkshire and Humber | England |  | 452496 | 423758 | North Yorkshire County Council | NY/2013/0128/ENV | [5 empty] | 2013-05-09 | [6 empty] | 2014-09-02
AA227 | 985 | 2014-08-11 | Biogen Power | Twinwoods Energy Recovery Facility - Resubmission | Biomass (dedicated) |  |  | 11.2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Twinwoods Business Park, Thurleigh Road, Milton Ernest, Bedfordshire | Bedfordshire | Eastern | England |  | 503475 | 256155 | Bedford Borough Council | 10/02851/FULWME | [5 empty] | 2010-11-17 |  | 2011-03-29
B1438 | 986 | 2016-06-30 | Growing Beds / Bioflame | Twinwoods Heat & Power CHP | EfW Incineration |  |  | 3.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Twinwoods Business Park, Thurleigh Road, Milton Ernest, Bedford, Bedfordshire | Bedfordshire | Eastern | England | MK41 6AE | 503240 | 256004 | Bedford Borough Council | 08/02465/COM | [5 empty] | 2008-09-01 | [6 empty] | 2008-11-13 |  |  |  |  | 2014-08-11 | 2016-06-15
B0887 | 987 | 2020-05-27 | BH EnergyGap (Walsall) | BHEG Walsall | Advanced Conversion Technologies |  |  | 44 | No |  |  | 26 | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Fryers Road, Leamore Lane Industrial Estate, Walsall WS3 2XJ | West Midlands | West Midlands | England |  | 399450 | 301442 | Walsall Council | 13/0725/WA | [5 empty] | 2013-05-31 | [6 empty] | 2013-09-20
C2639 | 988 | 2014-09-03 | Clean Power Properties & Network Rail Infrastructure Ltd |  | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Castleford Wakefield WF10 2PP | West Yorkshire | Yorkshire and Humber | England |  | 443976 | 426218 | Wakefield Council | 13/03470/FUL | [5 empty] | 2014-01-09 |  | 2014-07-17
AA873 | 989 | 2020-06-17 | Green EfW Investments | Cornwall Bio Park (Redruth) | EfW Incineration |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Hallenbeagle Sawmills Lane Scorrier Cornwall TR16 5BE | Cornwall | South West | England |  | 172760 | 44681 | Cornwall Council | PA12/06846 | [5 empty] | 2012-07-20 | [6 empty] | 2012-11-06
AA935 | 990 | 2018-04-03 | Biffa | Bickershaw Lane EfW | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Junction Works Bickershaw Lane Bickershaw Wigan WN2 5TB | Greater Manchester | North West | England |  | 361391 | 402160 | Wigan Council | A/10/73764 | [5 empty] | 2009-12-18 | [6 empty] | 2011-08-12 |  |  |  | 2014-08-12
C3083 | 991 | 2014-12-05 | Peel Environmental | Houghton Main Renewable Energy - Timber RRC | EfW Incineration |  |  | 23 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land off Houghton Main Colliery Roundabout, Park Spring Road, Houghton Main, Barnsley | South Yorkshire | Yorkshire and Humber | England |  | 441799 | 406582 | Barnsley Council | 2014/0559 | [5 empty] | 2014-05-30 |  | 2014-11-26
EN00568 | 992 | 2020-06-04 | Viridor | Dunbar EfW (previously Oxwellmains EfW) | EfW Incineration |  |  | 25.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Oxwellmains, Dunbar, East Lothian | Lothian | Scotland | Scotland |  | 371051 | 675563 | East Lothian Council | 08/00467/FUL | 10/00003/P01 |  |  |  |  | 2008-05-13 |  | 2009-11-06 |  |  |  | 2010-12-14 | 2010-12-14 |  |  |  |  | 2015-07-24 | 2019-03-01
S0021M3 | 993 | 2015-01-09 | SCOTGEN / Batneec (Dumfries) (Compact Power) | Dargavel | Advanced Conversion Technologies |  |  | 7.2 | No |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Dumfriesshire | Dumfries and Galloway | Scotland | Scotland |  | 301400 | 577400 | Dumfries and Galloway Council | 00/P/3056 | [5 empty] | 2000-11-21 | [6 empty] | 2001-05-23 | [5 empty] | 2012-03-25
S0022M3 | 994 | 2014-09-25 | Energy From Waste | Energy from Waste Glasgow Ltd | Advanced Conversion Technologies |  |  | 15 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Barnkirk Farm, Barnkirk Road , Newton Stewart | Dumfries and Galloway | Scotland | Scotland |  | 239900 | 564900 | Dumfries and Galloway Council | [7 empty] | 2014-09-25
AA610 | 995 | 2015-09-14 | Veolia | New Barnfield ERF | EfW Incineration |  |  | 30 | No |  |  |  | n/a | n/a | n/a | n/a | Secretary of State - Refusal | Application Refused | New Barnfield, Travellers Lane, Hatfield, Hertfordshire | Hertfordshire | Eastern | England |  | 522631 | 206193 | Hertfordshire County Council | 6/2570-11 |  | APP/M1900/V/13/2192045 |  | 41865 |  | 2011-12-05 | [7 empty] | 2013-01-28 | 2015-07-17
C2704 | 996 | 2016-03-04 | Clean Power Properties | New Lodge Farm - ACT | Advanced Conversion Technologies |  |  | 12 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused |  | Dyfed | Wales | Wales | SA14 6PW | 257192 | 209823 | Carmarthenshire County Council | S/29559 | [5 empty] | 2014-02-05 |  | 2016-02-05
AA131 | 997 | 2014-12-02 | SITA UK | Great Blakenham EfW | EfW Incineration |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lodge Lane, Great Blakenham, Suffolk | Suffolk | Eastern | England |  | 612295 | 249597 | Suffolk County Council | MS/210/11 | [5 empty] | 2011-01-10 | [6 empty] | 2011-08-08 |  |  |  | 2014-08-08 | 2012-01-30 | 2014-12-02
AA729 | 998 | 2020-01-15 | Urbaser Balfour Beatty | Javelin Park EfW | EfW Incineration |  |  | 14.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Javelin Park, Bath Road, Haresfield, Stonehouse, Gloucestershire | Gloucestershire | South West | England |  | 380048 | 210468 | Gloucestershire County Council | 12/0008/STMAJW | APP/T1600/A/13/2200210 |  | Recovery |  |  | 2012-03-05 |  | 2013-03-22 | 2013-08-13 |  |  | 2015-01-06 | 2015-01-06 |  |  | 2015-01-06 | 2018-01-06 | 2016-07-17 | 2019-10-24
B0213 | 999 | 2020-06-09 | SITA UK | Charlton Lane Eco Park (ACT) | Advanced Conversion Technologies |  |  | 3.6 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Charlton Lane Waste Managment Facility , Charlton Lane, Shepperton | Surrey | South East | England | TW17 8QA | 508556 | 168426 | Surrey County Council | 10/00947/SCC | [5 empty] | 2010-11-25 | [6 empty] | 2011-06-29 |  |  |  |  | 2015-05-01
B1291 | 1000 | 2020-05-20 | Multifuel Energy (Wheelabrator)/ BIFFA | Newhurst Quarry - Revision 2 | EfW Incineration |  |  | 33 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Ashby Road East, Shepshed. Leicestershire | Leicestershire | East Midlands | England |  | 448680 | 317986 | Leicestershire County Council | 2014/1440/02 | [5 empty] | 2014-07-11 | [6 empty] | 2014-10-10 |  |  |  | 2015-06-28
B1315 | 1001 | 2020-04-02 | Wheelabrator | Parc Adfer EfW | EfW Incineration |  |  | 16 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Shotton Works, Deeside Industrial Park, Deeside | Clwyd | Wales | Wales | CH5 2NH | 331063 | 371586 | Flintshire County Council | 052626 | [5 empty] | 2014-09-22 | [6 empty] | 2015-06-09 |  |  |  | 2020-06-09 | 2017-04-15 | 2020-01-02
IF1003 | 1002 | 2019-07-23 | Cogen | Hooton Park | Advanced Conversion Technologies |  |  | 28 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | North Road, Eastham, Wirral | Merseyside | North West | England | CH65 1AJ | 337706 | 379601 | Wirral Council | APP/08/06316 | [5 empty] | 2008-07-15 | [6 empty] | 2009-07-29 |  |  |  |  | 2018-11-15
B1525 | 1003 | 2019-12-09 | Avon Power | Severn Road Resource Recovery Centre (Avonmouth RRC) | Advanced Conversion Technologies |  |  | 12 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Part Of Former Sevalco Site, Chittening Road, Bristol, South Gloucestershire | Avon | South West | England | BS11 0YU | 353497 | 181570 | Bristol City Council | 14/03974/F | [5 empty] | 2014-08-20 | [6 empty] | 2015-01-13 |  |  |  | 2018-01-13
A0059 | 1004 | 2015-04-07 | London Thames Gateway Development Corporation | Thames Gateway Power facility | Advanced Conversion Technologies |  |  | 16 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | London Sustainable Industries Park, Chequers Lane, Dagenham | Greater London | London | England | RM9 6PF | 549072 | 182452 | Barking and Dagenham London Borough Council | 10/00287/FUL | [5 empty] | 2010-03-25 | [6 empty] | 2011-03-31 |  |  |  | 2014-03-31
AA039 | 1005 | 2017-04-04 | Mercia Waste Management | EnviRecover | EfW Incineration |  |  | 15.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Oak Drive, Hartlebury Trading Estate, Worcester, DY10 4JB | Hereford and Worcester | West Midlands | England |  | 385577 | 269836 | Worcestershire County Council | 10/000032/CM | [5 empty] | 2010-05-04 | [6 empty] | 2012-07-20 |  |  |  |  | 2014-08-05 | 2017-03-16
AA120 | 1006 | 2017-03-24 | Biffa | Skelton Grange ERF | EfW Incineration |  |  | 26 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Former Skelton Grange Power Station Site, Pontefract Lane, Newsam Green, Leeds, West Yorkshire, LS15 9AD | West Yorkshire | Yorkshire and Humber | England |  | 433196 | 431231 | Leeds City Council | 11/03705/FU | [5 empty] | 2011-09-27 | [6 empty] | 2013-02-08
AA386 | 1007 | 2020-04-27 | Golder Associates (UK) Ltd/ Shore Energy | Coatbridge Material Recovery and Renewable Energy Facility | Advanced Conversion Technologies |  |  | 25 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land At Former Shanks & McEwan Site 251, Glasgow And Edinburgh Road, Coatbridge, North Lanarkshire | Strathclyde | Scotland | Scotland | ML5 4UG | 274352 | 662620 | North Lanarkshire Council | 09/00675/FUL | 10/00007/REFSL |  |  |  |  | 2009-06-22 |  | 2009-07-31 |  |  |  | 2011-05-27 | 2011-05-27 |  |  |  | 2014-05-27 | 2014-03-15
AA414 | 1008 | 2020-06-04 | Viridor | Avonmouth Resource Recovery Centre (formerly Severn Road) | EfW Incineration |  |  | 34 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Former Sevalco Site (North), Severn Road, Avonmouth, Bristol | Avon | South West | England | BS11 0YU | 353850 | 181366 | Bristol City Council | 09/04470/F | APP/Z0116/A/10/2132394 |  |  |  |  | 2009-11-05 |  | 2011-06-21 |  |  |  | 2011-04-06 | 2011-04-06 |  |  |  |  | 2017-04-15
AA664 | 1009 | 2020-06-09 | Fortum (formerly Peel Environmental) | South Clyde Energy Centre | EfW Incineration |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land to the south of King George V Dock, Glasgow | Strathclyde | Scotland | Scotland |  | 252615 | 665698 | Glasgow City Council | 12/01293/DC | [5 empty] | 2012-06-25 | [6 empty] | 2012-12-14
B1051 | 1010 | 2016-07-01 | Birmingham Bio-Power | Birmingham Bio-Power Plant | Advanced Conversion Technologies |  |  | 10.3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Webster & Horsfall off Speedwell Road, Hay Mills, Birmingham | West Midlands | West Midlands | England | B25 8DW | 410850 | 284950 | Birmingham City Council | 2012/05481/PA | [5 empty] | 2012-08-13 | [6 empty] | 2012-10-26 |  |  |  |  | 2014-01-01 | 2016-06-15
C2159 | 1011 | 2016-08-17 | Clean Power Properties | Willowbrook | Advanced Conversion Technologies |  |  | 16.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Willowbrook East Industrial Estate, Shelton Road, Corby, Northamptonshire | Northamptonshire | East Midlands | England |  | 490943 | 290854 | Northamptonshire County Council | 13/00079/WASFUL |  |  | Call-in |  |  | 2013-09-16 | [7 empty] | 2016-02-29
IF1112 | 1012 | 2018-03-08 | Origin Renewable Energy | Magnetic Park Energy Centre | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Desborough, Northamptonshire | Northamptonshire | East Midlands | England |  | 479813 | 284245 | Northamptonshire County Council | 12/00043/WASFUL | [5 empty] | 2012-05-25 | [6 empty] | 2012-11-20
AA792 | 1013 | 2015-07-06 | Biossence / Atco | East London Sustainable Energy Facility (Thames Gateway Power facility) | Advanced Conversion Technologies |  |  | 25 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Adj Fairview Industrial Park within Ford Motor Company, Frog Island, Rainham, Essex | Greater London | London | England | RM13 | 550656 | 181287 | Havering London Borough Council | P0558.12 | [5 empty] | 2012-05-10 | [6 empty] | 2012-08-30
B0739 | 1014 | 2016-12-20 | Avonmouth Biopower | Avonmouth Low Carbon Energy Facility - Phase 2 | Advanced Conversion Technologies |  |  | 6.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | New Earth Solutions Former Britannia Zinc Site Kings Weston Lane Lawrence Weston Bristol BS11 8HT | Avon | South West | England |  | 352153 | 179196 | Bristol City Council | 10/02837/F | [5 empty] | 2010-06-30 | [6 empty] | 2010-10-18 | [5 empty] | 2013-12-30
N00040M | 1015 | 2015-07-06 | Tradebe | Fawley Waste to Energy Plant | EfW Incineration |  |  | 8.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Charleston Road, Hardley Hythe, Southampton | Hampshire | South East | England |  | 443772 | 105625 | New Forest District Council | 70529 | [5 empty] | 2000-10-31 | [6 empty] | 2001-02-01 | [5 empty] | 2001-06-01
09147M3 | 1017 | 2010-04-30 | Veolia | Portsmouth ERF | EfW Incineration |  |  | 14 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Portsmouth Incinerator, Quartremaine Road, Copnor, Portsmouth, Hampshire | Hampshire | South East | England |  | 466716 | 102919 | Portsmouth City Council | A*29026/AF | APP/21775/A/00/1037287 |  |  |  |  | 1998-08-14 |  | 2001-10-15 | [10 empty] | 2005-03-01
A0429 | 1018 | 2011-07-21 | Ecotricity | Fen Farm Solar Park | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fen Farm, Fen Lane, Conisholme, South Lincolnshire | Lincolnshire | East Midlands | England |  | 537585 | 393825 | East Lindsey District Council | N/036/01536/10 | [5 empty] | 2010-08-13 | [6 empty] | 2010-11-12 | [5 empty] | 2011-07-11
A0503 | 1019 | 2011-09-01 | Low carbon Solar Partners | Manor Farm | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Manor Farm, Burngullow Lane, High Street, St Austell, Cornwall | Cornwall | South West | England | PL26 7TQ | 198260 | 52426 | Cornwall Council | PA11/00670 | [5 empty] | 2011-02-02 | [6 empty] | 2011-04-14 | [5 empty] | 2011-07-25
A0504 | 1020 | 2011-09-01 | Low carbon Solar Partners | Nanterrow Farm | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Churchtown Farm, Gwithian, Land South Of Nanterrow Cottage, Nanterrow Lane, Connor Downs, Cornwall | Cornwall | South West | England |  | 159822 | 40754 | Cornwall Council | PA11/00751 | [5 empty] | 2011-02-07 | [6 empty] | 2011-04-14 | [5 empty] | 2011-07-25
A0506 | 1021 | 2011-07-08 | Low carbon Solar Partners | Howton Farm | Solar Photovoltaics |  |  | 4.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Howton Farm Pillaton Saltash Cornwall | Cornwall | South West | England | PL12 6QY | 238063 | 62770 | Cornwall Council | PA11/00311 | [5 empty] | 2011-01-14 | [6 empty] | 2011-04-18 | [5 empty] | 2011-07-22
A0507 | 1022 | 2011-09-01 | Low carbon Solar Partners | East Langford Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | East Langford Farm Kilkhampton Bude Cornwall | Cornwall | South West | England | EX22 7LB | 229318 | 110657 | Cornwall Council | PA11/01139 | [5 empty] | 2011-02-12 | [6 empty] | 2011-04-18 | [5 empty] | 2011-07-25
A0509 | 1023 | 2012-04-30 | The Green Company | Trevemper solar farm | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Trevemper Crantock Cornwall | Cornwall | South West | England |  | 181946 | 59506 | Cornwall Council | PA11/00374 | [5 empty] | 2011-01-20 | [6 empty] | 2011-05-02 | [5 empty] | 2011-09-20
A0512 | 1024 | 2012-11-22 | Chester Energy (Eastcott) | Chester Energy (East Woolley Farm) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of East Woolley Farm, Morwenstow, Bude, Cornwall | Cornwall | South West | England | EX23 9PP | 225352 | 116729 | Cornwall Council | PA10/08695 | [5 empty] | 2010-12-17 | [6 empty] | 2011-04-18 | [5 empty] | 2012-06-01
A0514 | 1025 | 2012-02-27 | PV Sunpower Ltd | West Ditchen Farm Solar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land South Of Hornacott Chapel Boyton Launceston Cornwall | Cornwall | South West | England |  | 232118 | 93833 | Cornwall Council | PA11/01581 | [6 empty] | 2012-02-27
A0520 | 1028 | 2011-09-01 | Low carbon Solar Partners | Chynoweth Farm | Solar Photovoltaics |  |  | 2.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chynoweth Farm St Allen Truro Cornwall | Cornwall | South West | England | TR4 9DG | 180663 | 49493 | Cornwall Council | PA11/01510 | [5 empty] | 2011-02-22 | [6 empty] | 2011-03-31 | [5 empty] | 2011-07-25
A0521 | 1029 | 2012-04-24 | Private Developer | Carlton Farm Solar farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Carlton Farm, Old Yarmouth Road, North Walsham, Norfolk, NR28 9NA. | Norfolk | Eastern | England |  | 629186 | 328437 | North Norfolk District Council | PF/11/0418 | [5 empty] | 2011-04-07 | [6 empty] | 2011-05-24 | [5 empty] | 2011-10-31
AA147 | 1032 | 2011-07-25 | 35 Degrees | Wheal Jane | Solar Photovoltaics |  |  | 1.42 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Baldhu, Truro, Cornwall | Cornwall | South West | England | TR3 6ED | 177412 | 42176 | Cornwall Council | PA10/03993 | [5 empty] | 2010-06-21 | [6 empty] | 2010-09-17 | [5 empty] | 2011-07-06
AA232 | 1034 | 2017-02-02 | Innogy (previously - Belectric (previously Alectron Investments Ltd)) | Cantelupe Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to West of Cantelupe Road, Cantelupe Farm, Haslingfield, Cambridgeshire | Cambridgeshire | Eastern | England |  | 541469 | 254668 | South Cambridgeshire District Council | S/0154/11 | [5 empty] | 2011-01-28 | [6 empty] | 2011-04-27 |  |  |  |  | 2012-06-01 | 2013-02-28
AA239 | 1035 | 2011-11-30 | Private Developer | Benbole Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | St Kew Highway, Bodmin | Cornwall | South West | England | PL30 3EF | 202931 | 74850 | Cornwall Council | PA10/04656 | [5 empty] | 2010-08-04 | [6 empty] | 2010-12-20 | [5 empty] | 2011-07-28
AA240 | 1036 | 2011-08-24 | Private Developer | Trentworthy Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Youlstone, Holsworthy, Devon | Devon | South West | England | EX22 7SB | 228667 | 115194 | Torridge District Council | 1/1132/2010/FULM | [5 empty] | 2011-01-04 | 2011-04-20
AA253 | 1037 | 2011-05-24 | Eclipse Planning Services | Bourn Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | north of Bourn in Cambridgeshire, to the east of the Broadway and to the south of Bourn Airfield | Cambridgeshire | Eastern | England |  | 533382 | 258572 | South Cambridgeshire District Council | S/2205/10 | [5 empty] | 2010-12-13 |  | 2011-03-08
AA254 | 1038 | 2012-01-24 | Town Planning Services | Turves Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | land at Burnthouse Farm, Turves, Cambridgeshire | Cambridgeshire | Eastern | England |  | 534011 | 294340 | Fenland District Council | F/YR11/0020/F | 11/00014/REF |  |  |  |  | 2010-12-20 |  | 2011-03-21
AA255 | 1039 | 2011-08-24 | Terrence O'Rourke Ltd | Langage Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent to Lower Langage Farm, Plympton, Plymouth | Devon | South West | England | PL7 5AW | 257294 | 56289 | South Hams District Council | 49/0277/11/F | [5 empty] | 2011-01-21 | [6 empty] | 2011-03-31 | [5 empty] | 2011-07-15
AA258 | 1040 | 2011-08-07 | Lark Energy | Grange Solar Farm | Solar Photovoltaics |  |  | 4.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off Cotham Road, Hawton, Nottingham, Nottinghamshire | Nottinghamshire | East Midlands | England | NG13 | 479603 | 348537 | Newark and Sherwood District Council | 11/00333/FULM | [5 empty] | 2011-02-25 | [6 empty] | 2011-05-25 | [5 empty] | 2011-07-13
AA263 | 1041 | 2012-04-26 | GKA Limited | Ebbsfleet Farm Solar Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ebbsfleet Lane, Ramsgate, CT12 5DL | Kent | South East | England |  | 633253 | 162715 | Thanet District Council | F/TH/11/0029 | [5 empty] | 2011-01-31 | [6 empty] | 2011-03-18 | [5 empty] | 2011-09-05
AA295 | 1042 | 2012-11-28 | Rockspring Hanover Property Unit Trust | Westcott Venture Park Phase 2 & 3 | Solar Photovoltaics |  |  | 1.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | High Street, Westcott, Buckinghamshire | Buckinghamshire | South East | England |  | 472035 | 216827 | Aylesbury Vale District Council | 11/00245/APP | [5 empty] | 2011-02-09 | [6 empty] | 2011-06-09 |  |  |  |  | 2012-04-01 | 2012-09-01
AA300 | 1043 | 2011-08-24 | Alectron Investments | Baileys Meadow Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Hardingham, Norwich, Norfolk | Norfolk | Eastern | England |  | 606037 | 304353 | South Norfolk Council | 2011/0202 | [5 empty] | 2011-02-08 |  | 2011-08-18
AA311 | 1044 | 2011-08-24 | ZW North Tawton | North Tawton Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land To Rear Of Taw Valley Creamery, North Tawton, Devon | Devon | South West | England |  | 264942 | 100942 | West Devon Borough Council | 01270/2011 | [5 empty] | 2011-02-11 |  | 2011-05-24
AA314 | 1045 | 2012-02-24 | ZW Bushfurlong Ltd / WRS Energy | Langport Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Near Bushfurlong Lane, Somerset | Somerset | South West | England |  | 336966 | 121406 | South Somerset District Council | 11/00662/FUL | [6 empty] | 2012-02-24
AA322 | 1046 | 2012-10-25 | BNRG Renewables | Summerway Drove | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | E/o M5, Westonzoyland Road, Bridgwater, Somerset | Somerset | South West | England |  | 332514 | 136379 | Sedgemoor District Council | 09/11/00009 | [5 empty] | 2011-02-24 | [6 empty] | 2011-05-24 |  |  |  |  | 2011-08-01 | 2011-09-01
AA323 | 1047 | 2012-10-25 | BNRG Renewables | Puriton Solar Farm | Solar Photovoltaics |  |  | 4.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bridgwater, Somerset | Somerset | South West | England |  | 332462 | 142273 | Sedgemoor District Council | 42/10/00030 | [5 empty] | 2011-02-23 | [6 empty] | 2011-05-24 |  |  |  |  | 2011-08-01 | 2011-10-01
AA324 | 1048 | 2016-04-29 | Bluefield Solar Income Fund | Toyota Solar Farm | Solar Photovoltaics |  |  | 4.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Burnaston, Derby, Derbyshire, DE1 9TA | Derbyshire | East Midlands | England |  | 428727 | 331153 | South Derbyshire District Council | 9/2011/0180 | [5 empty] | 2011-03-11 | [6 empty] | 2011-04-11 | [5 empty] | 2011-07-25
AA329 | 1049 | 2011-08-24 | Moor Solar | Long Sutton Butterfly And Wildlife Park | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Little London, Spalding, Lincolnshire | Lincolnshire | East Midlands | England | PE12 9LE | 544055 | 323522 | South Holland District Council | H11-0817-10 | [5 empty] | 2010-09-29 | [6 empty] | 2011-02-21 | [5 empty] | 2011-07-14
AA330 | 1050 | 2011-08-24 | Moor Solar | Long Sutton Butterfly And Wildlife Park (extension) | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Little London, Spalding, Lincolnshire | Lincolnshire | East Midlands | England | PE12 9LE | 544125 | 323559 | South Holland District Council | H11-0206-11 | [5 empty] | 2011-03-18 | [6 empty] | 2011-04-28 | [5 empty] | 2011-07-14
AA337 | 1051 | 2011-08-05 | ZW Nether Stowey Ltd | Inwood Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Nether Stowey, Bridgwater, Somerset | Somerset | South West | England |  | 319828 | 139682 | Sedgemoor District Council | 36/11/00005 | [5 empty] | 2011-03-31 |  | 2011-06-20
AA363 | 1052 | 2011-08-24 | WRS Energy Ltd | Kingsland Barton Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Near South Molton, Devon | Devon | South West | England |  | 270051 | 126002 | North Devon District Council | 51860 | [5 empty] | 2011-03-25 |  | 2011-06-24
AA373 | 1053 | 2018-09-04 | Greencoat Capital | Springhill Solar Park (Northwick) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chipping Campden, Gloucestershire | Gloucestershire | South West | England |  | 413653 | 235615 | Cotswold District Council | 11/01247/FUL | [5 empty] | 2011-04-18 | [6 empty] | 2011-07-21 | [5 empty] | 2013-02-01
AA401 | 1054 | 2017-12-19 | Private Developer | Westmill Farm - PV | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Highworth Road, Watchfield, Swindon | Oxfordshire | South East | England | SN6 8TH | 424744 | 191164 | Vale of White Horse District Council | 11/00077/FUL | [5 empty] | 2011-01-04 | [6 empty] | 2011-03-28 |  |  |  |  | 2011-06-01 | 2011-07-19
AA412 | 1055 | 2011-08-24 | Private Developer | Rhosygilwen Solar Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rhoshill, Cardigan | Dyfed | Wales | Wales | SA43 2TW | 220298 | 240670 | Pembrokeshire County Council | 10/0750/PA | [5 empty] | 2010-11-23 | [6 empty] | 2011-01-06 | [5 empty] | 2011-07-09
AA528 | 1056 | 2012-05-29 | m03 Power | Llancayo Solar Farm | Solar Photovoltaics |  |  | 3.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Llancayo Farm, Llancayo, Usk, Gwent | Gwent | Wales | Wales | NP15 1HY | 336790 | 203067 | Monmouthshire County Council | DC/2011/00196 | [5 empty] | 2011-04-16 | [6 empty] | 2011-06-03 | [5 empty] | 2011-07-01
AA630 | 1057 | 2012-03-26 | Lomond Holdings Ltd | Enstone Solar Park | Solar Photovoltaics |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Enstone Airfield, Enstone | Oxfordshire | South East | England |  | 438787 | 225447 | West Oxfordshire District Council | 11/1924/P/FP | [5 empty] | 2011-12-15 |  | 2012-02-08
AA697 | 1058 | 2013-06-13 | Moser Baer | Shacks Barn Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Shacks Barn Farm, Silverstone | Northamptonshire | East Midlands | England |  | 468260 | 245328 | South Northamptonshire Council | S/2012/0258/MAF | [5 empty] | 2012-03-01 | [6 empty] | 2012-08-03 | [5 empty] | 2013-03-28
AA831 | 1059 | 2013-04-29 | Solar Securities Group Ltd | Carines Farm Solar Array | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cubert, Newquay, Cornwall | Cornwall | South West | England | TR8 5ET | 178921 | 58340 | Cornwall Council | PA12/06913 | [5 empty] | 2012-07-18 | [6 empty] | 2012-12-11 |  |  |  |  | 2013-02-01 | 2013-03-30
AA832 | 1060 | 2013-04-11 | Trigon Solar Farm Ltd | Trigon Solar Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Trigon (Trigon House), Wareham | Dorset | South West | England | BH20 7PD | 387816 | 90139 | Purbeck District Council | 6/2012/0415 | [5 empty] | 2012-07-05 | [6 empty] | 2012-11-28 | [5 empty] | 2013-03-08
AA865 | 1061 | 2012-01-17 | MTS Trewidland Solar Ltd | Lowertown Farm | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Trewidland Liskeard | Cornwall | South West | England | PL14 4ST | 225840 | 59763 | Cornwall Council | PA12/07247 | [5 empty] | 2012-08-14 |  | 2013-01-14
AA890 | 1062 | 2013-04-12 | Abbey Properties Cambs | Chittering Solar Farm Extension | Solar Photovoltaics |  |  | 6.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at, Radical Farm, Chittering Drove, Chittering, Cambridgeshire | Cambridgeshire | Eastern | England |  | 551264 | 270881 | South Cambridgeshire District Council | S/1542/12/FL | [5 empty] | 2012-07-24 | [6 empty] | 2012-10-15 |  |  |  |  | 2013-01-28 | 2013-03-21
AA892 | 1063 | 2012-10-11 | AEE Renewables | Nether Mill Farm | Solar Photovoltaics |  |  | 3.08 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Halberton | Devon | South West | England | EX15 2QQ | 301983 | 112019 | Mid Devon District Council | 12/01071/MFUL | [5 empty] | 2012-08-21 | 2012-10-02
AA894 | 1064 | 2015-09-29 | Kronos Solar | Tredinnick Fields | Solar Photovoltaics |  |  | 5.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Tredinnick Fields, Luxulyan, Bodmin, Cornwall | Cornwall | South West | England | PL30 5DT | 204104 | 59947 | Cornwall Council | PA12/04998 | [5 empty] | 2012-06-01 | [6 empty] | 2012-08-31 | [5 empty] | 2013-03-15
AA895 | 1065 | 2013-06-14 | Solar Securities Group Ltd | Summercourt Solar Farm (Glebe Farm) | Solar Photovoltaics |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Glebe Farm, Narrow Lane, Penhale, Summercourt | Cornwall | South West | England | TR8 5ED | 189770 | 56798 | Cornwall Council | PA12/05890 | [5 empty] | 2012-06-26 | [6 empty] | 2012-10-31 |  |  |  |  | 2013-02-01 | 2013-03-30
AA902 | 1066 | 2013-06-14 | AEE Renewables | Yonder Netherton | Solar Photovoltaics |  |  | 3.2 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | South Of Millpool Rilla Mill Liskeard Cornwall | Cornwall | South West | England | PL14 5BD | 228471 | 72954 | Cornwall Council | PA11/01438 | [5 empty] | 2011-05-05 | [6 empty] | 2011-08-01
AA903 | 1067 | 2013-08-16 | Smarter Energy Solutions Ltd | Higher Trevartha Farm | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pengover Liskeard | Cornwall | South West | England | PL14 3NJ | 227721 | 64135 | Cornwall Council | PA12/01530 | [5 empty] | 2012-08-01 | [6 empty] | 2012-08-01 | [5 empty] | 2013-03-31
AA910 | 1068 | 2013-04-04 | Elgin Energy EsCo | Land At Lanthrone | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Tideford Cross Lane Tideford Cornwall | Cornwall | South West | England | PL12 5JY | 234230 | 60596 | Cornwall Council | PA12/05854 | [5 empty] | 2012-06-21 |  | 2013-01-29
AA971 | 1069 | 2013-02-07 | Wessex Solar Energy | Gratton Copse | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Loyton Farm, Morebath | Devon | South West | England |  | 296879 | 124901 | Mid Devon District Council | 12/01195/MFUL | [5 empty] | 2012-08-28 | 2013-01-18
AA975 | 1070 | 2013-10-08 | AEE Renewables | Beechgrove Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hawkchurch, Axminster | Devon | South West | England | EX13 5TX | 335062 | 99382 | East Devon District Council | 11/0321/MFUL | [5 empty] | 2011-03-22 | [6 empty] | 2011-05-13 | [5 empty] | 2011-07-01
AA977 | 1071 | 2013-02-07 | Fulford Solar Park Ltd | Goldcross Hill (resubmission) | Solar Photovoltaics |  |  | 6.9 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land South Of Goldcross Hill, Tedburn St Mary, Devon, | Devon | South West | England |  | 279292 | 92523 | Teignbridge District Council | 12/02784/MAJ | [5 empty] | 2012-09-11 |  | 2012-12-03
AA983 | 1073 | 2013-02-21 | Sunsave 10 (FAREHAM) / Vogt Solar | Newlands Farm Solar | Solar Photovoltaics |  |  | 49 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | between Fareham and Stubbington, Portsmouth | Hampshire | South East | England |  | 456642 | 103814 | Fareham Borough Council | P/12/0905/FP | [5 empty] | 2012-10-29 | 2013-02-13
AA989 | 1074 | 2013-06-12 | Elgin Energy EsCo | Trequite Farm | Solar Photovoltaics |  |  | 11.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Menheniot, Liskeard | Cornwall | South West | England | PL14 3RQ | 232294 | 60920 | Cornwall Council | PA13/02242 | [5 empty] | 2013-03-22 | 2013-05-23
B0012 | 1076 | 2012-07-13 | Solar Power Generation Limited | PARK WOOD SOLAR FARM | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Park Wood, Butleigh, Glastonbury | Somerset | South West | England | BA6 | 352990 | 134204 | Mendip District Council | 2011/0781 | [5 empty] | 2011-05-04 | [6 empty] | 2011-07-28 | [5 empty] | 2011-09-29
B0022 | 1077 | 2012-01-06 | ZW Bushfurlong Ltd | BUSHFURLONG SOLAR FARM | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Bushfurlong Farm, Bushfurlong Road, Isle Brewers, Taunton | Somerset | South West | England | TA3 6QS | 337461 | 121498 | South Somerset District Council | 1100662FUL | [5 empty] | 2011-02-18 | 2011-12-09
B0048 | 1078 | 2013-03-06 | Lightsource Renewable Energy | Promens Solar | Solar Photovoltaics |  |  | 1.65 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Promens Plastic Plant, Ellough, Beccles | Suffolk | Eastern | England | NR34 7TB | 644496 | 288255 | Waveney District Council | [19 empty] | 2011-07-21
B0060 | 1079 | 2013-03-06 | Sunstroom Energy | Malmesbury Solar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Upper Marsh Farm, Brokenborough, Malmesbury | Wiltshire | South West | England | SN16 9SR | 392558 | 191729 | Wiltshire Council | 11/01081/FUL | [5 empty] | 2011-03-25 | [6 empty] | 2011-05-26 | [5 empty] | 2011-07-25
B0085 | 1080 | 2015-09-25 | Bosch Solar Energy | Trefullock Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Trefullock, Trefullock Moor, Summercourt | Cornwall | South West | England |  | 189840 | 56035 | Cornwall Council | PA10/06679 | [5 empty] | 2010-10-20 | [6 empty] | 2011-01-07 |  |  |  |  | 2011-07-01 | 2011-07-07
B0106 | 1081 | 2011-08-30 | Solar South West | Lower Coombe Farm Solar | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lower Coombe Farm, Roundham, Crewkerne, Somerset | Somerset | South West | England | TA18 8RL | 341635 | 109855 | South Somerset District Council | 10/04729/FUL | [5 empty] | 2010-11-19 | [6 empty] | 2011-01-25 | [5 empty] | 2011-06-24
B0110 | 1082 | 2015-09-29 | Kronos Solar/Vogt Solar | Durrants Farm Solar | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | land at Durrants Farm, Colemans Lane, Porchfield, Newport | Isle of Wight | South East | England | PO30 4PE | 444831 | 90217 | Isle of Wight Council | P/01901/10 | [5 empty] | 2010-12-14 | [6 empty] | 2011-02-28 | [5 empty] | 2011-07-01
B0512 | 1083 | 2012-09-21 | Eco Sustainable Solutions | Parley Renewable Energy Park (PV) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Chapel Lane, Parley, Christchurch, Dorset | Dorset | South West | England | BH23 6BG | 410259 | 99260 | Christchurch Borough Council | 8/10/0604 | [5 empty] | 2010-12-23 |  | 2011-03-16
B0629 | 1084 | 2013-03-12 | Dunsfold Park Ltd | Dunsfold Park Solar Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The East Side Of High Loxley Road, Stovolds Hill, Cranleigh | Surrey | South East | England | GU8 4BS | 501944.1 | 136562 | Waverley Borough Council | WA/2010/1904 | [5 empty] | 2010-11-03 | [6 empty] | 2011-03-30 | [5 empty] | 2011-07-26
B0884 | 1085 | 2013-10-01 | Alan Bartlett & Sons Ltd | Alan Bartlett & Sons Solar | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Great Acre Fen, Chatteris | Cambridgeshire | Eastern | England | PE16 6EG | 538587 | 285638 | Fenland District Council | [19 empty] | 2013-03-31
C0029 | 1086 | 2013-04-12 | Hive Energy | Tavells Lane Solar Farm | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tavells Lane, Marchwood, Southampton | Hampshire | South East | England | SO40 4WH | 438181 | 110655 | New Forest District Council | 12/98402 | [5 empty] | 2012-03-12 | [6 empty] | 2012-05-08 |  |  |  |  | 2013-02-04 | 2013-03-20
C0216 | 1088 | 2013-04-12 | Private Developer | LITTLE TREVEASE SOLAR PARK | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Little Trevease Farm, Constantine, Falmouth | Cornwall | South West | England | TR11 5QU | 171916 | 31778 | Cornwall Council | PA12/04124 | [5 empty] | 2012-06-14 | [6 empty] | 2012-10-26 |  |  |  |  | 2013-01-03 | 2013-03-20
C0218 | 1089 | 2013-10-07 | PS Renewables | Cobbs Cross Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | S/O Durleigh Hill, Bridgwater, Somerset | Somerset | South West | England | TA5 2AG | 327500 | 135300 | Sedgemoor District Council | 23/12/00005 | [5 empty] | 2012-05-28 | [6 empty] | 2012-09-20 | [5 empty] | 2013-03-30
C0230 | 1090 | 2013-06-04 | PS Renewables | NOTTINGTON LANE SOLAR FARM | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | North Farm, Nottington Lane, Buckland Ripers, Weymouth | Dorset | South West | England | DT3 4BU | 364300 | 82750 | West Dorset District Council | 1/D/12/000858 | [5 empty] | 2012-05-31 | [6 empty] | 2012-09-20 |  |  |  |  | 2013-01-18 | 2013-03-30
C0353 | 1091 | 2016-05-10 | Orta Solar | RUDGE FARM SOLAR FARM | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rudge Manor Farm, Rudge, Marlborough | Wiltshire | South West | England | SN8 2HN | 427444 | 169114 | Wiltshire Council | E/2012/0946/FUL | [5 empty] | 2012-07-26 | [6 empty] | 2012-12-21 |  |  |  |  | 2012-12-22 | 2013-03-28
C0636 | 1092 | 2013-02-26 | Shaw Coltishall Solar Park Limited | SCOTTOW ROAD SOLAR FARM | Solar Photovoltaics |  |  | 12.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Scottow Road, Scottow, Norwich, Norfolk | Norfolk | Eastern | England | NR10 | 626063 | 324056 | North Norfolk District Council | PF/12/1094 | [5 empty] | 2012-11-12 | 2012-12-21
C0638 | 1093 | 2013-01-18 | Trafford Estate Solar Park Ltd | BELAUGH ROAD SOLAR FARM | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Belaugh Road, Hoveton, Norwich, Norfolk | Norfolk | Eastern | England | NR12 8UU | 629936 | 319079 | North Norfolk District Council | PF/12/1142 | [5 empty] | 2012-11-12 | 2012-12-21
C0641 | 1094 | 2016-02-05 | Sunsave 4 Ltd/ Vogt Solar | CRINACOTT SOLAR FARM (Pyworthy) | Solar Photovoltaics |  |  | 6.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Crinacott Farm, Pyworthy, Holsworthy, Devon | Devon | South West | England | EX22 6LJ | 230835 | 101736 | Torridge District Council | 1/0883/2012/FULM | [5 empty] | 2012-10-18 | [6 empty] | 2013-01-17 | [5 empty] | 2013-03-31
C0643 | 1095 | 2013-06-06 | BNRG Renewables | Chawton Farm Solar Farm | Solar Photovoltaics |  |  | 3.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chawton Farm, Chawton Lane, Cowes, Isle of Wight | Isle of Wight | South East | England | PO31 8PR | 449357 | 93055 | Isle of Wight Council | P/01483/12 | [5 empty] | 2012-10-05 | [6 empty] | 2012-12-17 | [5 empty] | 2013-03-22
C0644 | 1096 | 2013-06-06 | BNRG Renewables | VENTNOR ROAD SOLAR PARK | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | S/O Apse New Barn Farm, Ventnor Road, Shanklin, Isle of Wight | Isle of Wight | South East | England | PO37 7PP | 456363 | 82780 | Isle of Wight Council | P/01484/12 | [5 empty] | 2012-10-09 | [6 empty] | 2012-12-21 | [5 empty] | 2013-03-23
C0649 | 1097 | 2013-06-21 | Prosolia UK Ltd | ROOKERY FARM SOLAR FARM | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | W/O Rookery Farm, Kimbolton Road, Stow Longa, Huntingdon, Cambridgeshire | Cambridgeshire | Eastern | England | PE28 0TR | 510308 | 270151 | Huntingdonshire District Council | 1201638FUL | [5 empty] | 2012-11-02 | [6 empty] | 2013-02-01 | [5 empty] | 2013-06-03
C0917 | 1098 | 2013-07-19 | Little White Alice Ltd | Little White Alice Solar Park | Solar Photovoltaics |  |  | 1.29 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Little White Alice Calvadnack Carnmenellis Redruth Cornwall | Cornwall | South West | England | TR16 6PL | 169784 | 35058 | Cornwall Council | PA12/09881 | [5 empty] | 2012-12-04 | [6 empty] | 2013-01-07 | [5 empty] | 2013-04-30
C1066 | 1103 | 2013-04-15 |  | Park Wall Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the east of M5 motorway, and south of A372, Westonzoyland Road, Bridgwater Without, Bridgwater | Somerset | South West | England |  | 332133 | 136030 | Sedgemoor District Council | 09/11/00010 | [5 empty] | 2011-03-01 | [6 empty] | 2011-05-24 |  |  |  |  | 2012-08-01 | 2013-03-21
C1113 | 1108 | 2016-03-04 | Solar Park Developments (Blackrock) | Hall Farm Solar park | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Hall Farm Bungay Road Tasburgh Norfolk | Norfolk | Eastern | England |  | 624721 | 294006 | South Norfolk Council | 2014/0562 | [5 empty] | 2014-03-21 | [6 empty] | 2014-10-24 |  |  |  | 2017-10-24 |  | 2016-02-15
C1145 | 1111 | 2013-07-24 | Kinetic Energy Ltd | Bodrawl Farm Solar Park | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Bodrawl Farm East Taphouse Liskeard Cornwall | Cornwall | South West | England | PL14 4QT | 219807 | 62102 | Cornwall Council | PA13/03107 | [5 empty] | 2013-04-24 | 2013-06-07
C1279 | 1121 | 2013-09-23 | MS POWER PROJECTS LIMITED | RITHERDENS FARM solar park | Solar Photovoltaics |  |  | 9.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | LAND NORTH-WEST OF RITHERDENS FARM, BRADFORD ON TONE | Somerset | South West | England |  | 318973 | 124444 | Taunton Deane Borough Council | 07/13/0016 | [5 empty] | 2013-05-09 |  | 2013-08-22
C1333 | 1128 | 2016-07-01 | Solar Century/ Bluefield Solar | Oulton Airfield Solar Farm (Phase 1) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Oulton Airfield, The Street, Oulton, Norwich | Norfolk | Eastern | England | NR11 6AF | 614742 | 326962 | Broadland District Council | 20150952 | [5 empty] | 2015-06-15 | [6 empty] | 2015-09-24 |  |  |  | 2018-09-24 | 2016-05-01 | 2016-02-18
C1342 | 1130 | 2013-09-04 | Esconrg Ltd | Sheephouse Farm solar park | Solar Photovoltaics |  |  | 9.03 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land OS 3969 Brewham Road Bruton Somerset | Somerset | South West | England |  | 369575 | 135537 | South Somerset District Council | 13/01668/FUL | [5 empty] | 2013-05-21 |  | 2013-08-16
IF1010 | 1156 | 2013-01-25 | SPGL (Solar Power Generation Limited) | Westover Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The South Of Longbarrow Westover Farm, Barrow Hill, Goodworth, Clatford, Andover | Hampshire | South East | England | SP11 7SE | 434623 | 140438 | Test Valley Borough Council | 12/02159/FULLN | [5 empty] | 2012-10-04 | 2012-12-11
IF1030 | 1157 | 2013-04-12 | Chalcroft Solar Park | Chalcroft Solar Park | Solar Photovoltaics |  |  | 6.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Chalcroft Farm, Burnetts Lane, West End, Southampton | Hampshire | South East | England | SO30 2HU | 448713 | 116890 | Eastleigh Borough Council | F/12/71539 | [5 empty] | 2012-09-28 | [6 empty] | 2012-12-13 | [5 empty] | 2013-03-24
IF1053 | 1158 | 2013-04-12 | Wessex Solar Energy | Bradford Solar Park | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Bradford Manor Farm Pyworthy Devon | Devon | South West | England |  | 227973 | 100750 | Torridge District Council | 1/0035/2011/FULM | [5 empty] | 2011-06-10 | [6 empty] | 2011-12-14 |  |  |  |  | 2012-12-10 | 2013-03-21
IF1060 | 1159 | 2013-02-26 | Saxthorpe Solar Farm Limited | Church Farm Solar | Solar Photovoltaics |  |  | 5.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Saxthorpe, Norfolk | Norfolk | Eastern | England | NR11 7BP | 612704 | 330757 | North Norfolk District Council | PF/12/1113 | [5 empty] | 2012-11-12 | 2012-12-21
IF1061 | 1160 | 2013-05-07 | A H Warren Trust | Lower Coombe Farm (Bean Field) | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Roundham. Crewkerne, Somerset | Somerset | South West | England | TA18 8RR | 341153 | 109631 | South Somerset District Council | 12/02268/FUL | [5 empty] | 2012-06-22 | [6 empty] | 2012-08-01 | [5 empty] | 2012-08-31
IF1063 | 1161 | 2013-06-04 | Private Developer | Ffos Las Racecourse | Solar Photovoltaics |  |  | 5.5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Trimsaran, Kidwelly, Carmarthenshire | Dyfed | Wales | Wales | SA17 4DE | 245478 | 205296 | Carmarthenshire County Council | S/24039 | [5 empty] | 2010-11-22 | [6 empty] | 2011-04-22 | [5 empty] | 2012-06-30
IF1067 | 1162 | 2013-02-26 | Trafford Estate Solar Park Ltd | Land off Belaugh Road | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Belaugh Road, Hoveton | Norfolk | Eastern | England | NR12 8UU | 629442 | 318878 | Broadland District Council | 20121424 | [5 empty] | 2012-10-23 | 2012-12-21
IF1068 | 1163 | 2013-10-02 | Esconrg | Woodforde Farm | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Weston Green Road, Weston Longville | Norfolk | Eastern | England | NR9 5LG | 608889 | 315630 | Broadland District Council | 20121337 | [5 empty] | 2012-09-17 | [6 empty] | 2012-11-06 | [5 empty] | 2013-03-31
IF1074 | 1164 | 2013-02-20 | Granite Consultants Limited | Land east of Kingsley Sports Club | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Sickles Lane, Kingsley, Alton | Hampshire | South East | England |  | 479300 | 138900 | East Hampshire District Council | 52947/001 | [5 empty] | 2012-11-08 | 2013-02-07
IF1083 | 1165 | 2013-03-08 | BOA Property / AEE Renewables UK | Kingston Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Holt Road, Bradford-on-Avon, Wiltshire | Wiltshire | South West | England | BA15 1AH | 383092 | 160863 | Wiltshire Council | W/11/01064/FUL | [5 empty] | 2011-03-31 | [6 empty] | 2011-05-17 |  |  |  |  | 2011-07-01 | 2011-10-01
IF1088 | 1166 | 2018-03-02 | Abic | Spriggs Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Spriggs Farm Little Sampford | Essex | Eastern | England |  | 562818 | 232492 | Uttlesford District Council | UTT/12/5601/FUL | [5 empty] | 2012-11-08 | [6 empty] | 2013-01-17 | [5 empty] | 2013-06-30
IF1090 | 1167 | 2012-11-27 | Private Developer | Somborne Park Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Stockbridge, Chichester Hampshire | Hampshire | South East | England | SO20 6EN | 436739 | 134466 | Test Valley Borough Council | 12/01573/FULLN | [5 empty] | 2012-08-01 |  | 2012-11-22
IF1100 | 1168 | 2013-03-05 | Inazin Power Ltd | Goldcross Hill | Solar Photovoltaics |  |  | 8.6 | n/a |  |  |  | n/a | n/a | n/a |  | Appeal Refused | Application Refused | Land South Of Goldcross Hill, Tedburn St Mary, Devon, | Devon | South West | England |  | 279447 | 93446 | Teignbridge District Council | 12/00781/MAJ | 12/00043/REF |  |  |  |  | 2012-03-09 |  | 2012-07-13 |  |  | 2012-12-12
IF1135 | 1169 | 2013-05-21 | Vale Green Energy | Rotherdale Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Long Lane, Tilesford, Pershore, Worcestershire | Hereford and Worcester | West Midlands | England | WR10 2LA | 396913 | 250467 | Wychavon District Council | 12/02528 | [5 empty] | 2012-11-13 | [6 empty] | 2013-01-04 |  |  |  |  | 2014-11-01 | 2015-01-01
IF1156 | 1170 | 2013-02-19 | Solar Power Generation Limited | North Creake Airfield | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Egmere, Walsingham, Norfolk | Norfolk | Eastern | England |  | 590428 | 338001 | North Norfolk District Council | PF/12/1318 | [5 empty] | 2012-12-06 | 2013-02-07
IF1196 | 1171 | 2013-04-12 | Abbey Renewables | Turves Solar Farm (Resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of 15 Burnthouse Sidings, Turves, Whittlesey, Cambridgeshire | Cambridgeshire | Eastern | England |  | 533992 | 294321 | Fenland District Council | F/YR11/0362/F | [5 empty] | 2011-05-13 | [6 empty] | 2012-04-12 |  |  |  |  | 2012-11-02 | 2013-03-19
IF1219 | 1172 | 2013-02-22 | Solar Power Generation Ltd | Little Park Farm | Solar Photovoltaics |  |  | 8.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Park Lane, Pitney, Langport, Somerset | Somerset | South West | England | TA10 9AU | 346238 | 130128 | South Somerset District Council | 12/04673/FUL | [5 empty] | 2012-12-05 | 2013-02-08
IF1221 | 1173 | 2013-07-22 | Padero Solaer | Rexton Cross | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Broadwoodwidger Devon | Devon | South West | England | PL16 0JJ | 241363 | 88612 | Torridge District Council | 1/1054/2012/FULM | [5 empty] | 2012-12-18 | [6 empty] | 2013-02-06 |  |  |  |  | 2013-03-01 | 2013-05-01
IF1224 | 1174 | 2015-11-05 | Lightsource Renewable Energy | Wadley Hill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Wadley Hill Farm, , Beckley, Elsfield, Oxford | Oxfordshire | South East | England | OX3 9SR | 455659 | 210037 | South Oxfordshire District Council | P15/S2202/FUL | [5 empty] | 2015-07-01 |  | 2015-10-30
IF1255 | 1175 | 2013-07-24 | Private Developer | Home Farm (PV) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Street Lane Denby Ripley Derbyshire | Derbyshire | East Midlands | England | DE5 8NE | 438511 | 348466 | Amber Valley Borough Council | AVA/2012/1026 | [5 empty] | 2012-11-05 |  | 2013-07-04
IF1258 | 1176 | 2013-03-11 | Orta Solar | Hatchlands Farm | Solar Photovoltaics |  |  | 5.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Haberton, Totnes | Devon | South West | England |  | 273302 | 59712 | South Hams District Council | 23/1754/12/F | [5 empty] | 2012-08-01 | [6 empty] | 2012-10-23 |  |  |  |  | 2012-12-03 | 2013-03-25
IF1263 | 1177 | 2013-04-05 | Wessex Solar Energy | Bidwell Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at Southdown Farm, Dartington, Totnes | Devon | South West | England | TQ9 6DU | 276964 | 61303 | South Hams District Council | 14/2182/12/F | [6 empty] | 2013-04-05
IF1319 | 1182 | 2013-06-13 | Hive Energy | Land at Hill Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Baylham, Suffolk | Suffolk | Eastern | England |  | 610846 | 251030 | Mid Suffolk District Council | 3319/12 | [5 empty] | 2013-02-19 | 2013-05-23
IF1366 | 1184 | 2015-09-29 | PS Renewables | Land At Potash Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nash Road Beachampton Buckinghamshire | Buckinghamshire | South East | England | MK19 6EA | 478049 | 235969 | Aylesbury Vale District Council | 11/00179/APP | [5 empty] | 2011-02-07 | [6 empty] | 2011-04-20 | [5 empty] | 2013-03-30
C1602 | 1193 | 2013-11-19 | Camborne Energy Investments (10) Ltd | The Flats | Solar Photovoltaics |  |  | 6.75 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Parcel 0074, Flatts Lane, Farmborough, Bath, | Somerset | South West | England |  | 364193 | 159583 | Bath and North East Somerset Council | 13/02527/FUL | [5 empty] | 2013-07-03 | 2013-10-02
C1301 | 1194 | 2013-11-19 | Bond Holdings Ltd | Dunstan Lodge solar farm | Solar Photovoltaics |  |  | 8.53 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Dunstan Lodge St Mellion Cornwall | Cornwall | South West | England |  | 237614 | 66307 | Cornwall Council | PA13/03583 | [5 empty] | 2013-05-20 |  | 2013-08-29
C2143 | 1198 | 2015-12-22 | Lightsource Renewable Energy | Land at Upper Clayhill Farm | Solar Photovoltaics |  |  | 4.9 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Upper Clayhill Farm, Uckfield Road, Ringmer, Lewes | East Sussex | South East | England | BN8 5RR | 544578 | 114951 | Lewes District Council | LW/14/0771 | [5 empty] | 2014-10-14 | [6 empty] | 2014-12-18 |  |  |  | 2017-12-18 | 2015-08-20 | 2015-12-16
C2182 | 1203 | 2015-12-01 | Aquila Capital | Towerbrook Farm (Banwell Solar Farm) | Solar Photovoltaics |  |  | 7.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to north of Towerhead Road, Banwell | Avon | South West | England | BS29 6PQ | 340553 | 159505 | North Somerset Council | 14/P/1842/F | [5 empty] | 2014-08-26 | [6 empty] | 2014-11-28 |  |  |  | 2017-11-28 | 2014-12-01 | 2015-03-27
C2225 | 1206 | 2016-05-30 | Green Switch Solutions | Wanes Blades Road Solar Farm | Solar Photovoltaics |  |  | 16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Secretary of State - Refusal | Application Refused | Land To The East Of Wanes Blades Road, Lathom | Lancashire | North West | England |  | 347650 | 411650 | West Lancashire Borough Council | 2014/0791/FUL | APP/P2365/W/15/3011997 |  |  |  |  | 2014-07-24 |  | 2014-11-17 | 2015-05-13 |  | 2016-01-21 |  |  | 2015-08-05 | 2016-01-21
C0132 | 1207 | 2013-12-10 | Blackdown Solar Power | Culmhead Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Former Culmhead Airfield, Culmhead, Churchstanton, Taunton, Somerset | Somerset | South West | England | TA3 | 320746 | 114572 | Taunton Deane Borough Council | 10/12/0009 | [5 empty] | 2012-04-17 | 2012-06-19
C1102 | 1208 | 2013-12-10 |  | Twin Elm Solar Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Twin Elm Farm off Stock Lane Congresbury | Avon | South West | England | BS49 5JL | 344680 | 162402 | North Somerset Council | 12/P/0490/F | [5 empty] | 2012-03-19 | [6 empty] | 2012-06-11 | [5 empty] | 2012-07-25
C1373 | 1209 | 2013-12-23 | AEE Renewables | Little Sharpshaw Farm solar park | Solar Photovoltaics |  |  | 5.27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Little Sharpshaw Farm, Marston Bigot, Frome | Somerset | South West | England | BA11 5DD | 375616 | 145449 | Mendip District Council | 2013/1149 | [5 empty] | 2013-06-11 |  | 2013-11-23
C1425 | 1210 | 2013-12-24 | Rethink Energy Limited | Hall Farm and Field Barn Farm | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at Hall Farm and Field Barn Farm | Norfolk | Eastern | England |  | 594816 | 285818 | Breckland Council | 3PL/2013/0546/F | [5 empty] | 2013-06-11 | 2013-09-25
C1787 | 1211 | 2014-01-08 | Lightsource Renewable Energy | Bowhay Farm (resubmission) | Solar Photovoltaics |  |  | 5.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Bowhay Farm, Shillingford Abbott, Exeter | Devon | South West | England | EX2 9QQ | 290076 | 88682 | Teignbridge District Council | 13/02301/MAJ | [5 empty] | 2013-08-15 |  | 2013-11-14
C1790 | 1212 | 2013-12-23 | Lightsource Renewable Energy | Westerfield Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Westerfield Farm, Carterton, Oxfordshire | Oxfordshire | South East | England | OX18 | 427124 | 209714 | West Oxfordshire District Council | 13/1129/P/FP | [5 empty] | 2013-08-09 |  | 2013-10-22
C1859 | 1213 | 2013-12-16 | Sun Glow Power | Brickyard Barn | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land at Brickyard Barn, Mallory Road, Bishops Tachbrook, Leamington Spa | Warwickshire | West Midlands | England | CV33 9QD | 430420 | 261470 | Warwick District Council | W/13/1134 | [5 empty] | 2013-08-15 | 2013-11-05
IF1009 | 1218 | 2013-12-10 | Wessex Solar Energy | Garleys Wood Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | The Oaks, Downside Road, Backwell, Bristol, Avon | Avon | South West | England | BS48 3DQ | 350212 | 166236 | North Somerset Council | 12/P/1654/F | [5 empty] | 2012-09-19 |  | 2012-12-10
C2031 | 1220 | 2017-07-28 | Private Developer | Bunkers Hill | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a |  | Appeal Refused | Application Refused | Land At Bunkers Hill Pilgrims Way St Erth Hayle Cornwall | Cornwall | South West | England | TR27 6ER | 158389 | 34014 | Cornwall Council | PA13/08286 | APP/D0840/W/15/3140774 |  |  |  |  | 2013-09-11 |  | 2013-12-20 | 2016-02-08 |  | 2017-07-06
IF1160 | 1221 | 2017-07-24 | Solar IQ | Cwm Nant Gwyn | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | Cegn Ydfa Coytrahen, Bridgend | Mid Glamorgan | Wales | Wales | CF32 0EG | 287395 | 187266 | Bridgend County Borough Council | P/12/887/FUL | [5 empty] | 2012-12-19 | [6 empty] | 2013-02-13
B1036 | 1223 | 2014-02-06 | Solar Century/ Bluefield Solar | Hardingham Solar Farm | Solar Photovoltaics |  |  | 14.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hardingham | Norfolk | Eastern | England | NR9 4EG | 605625 | 305027 | Breckland Council | 3PL/2012/1021/F | [5 empty] | 2012-10-01 | [6 empty] | 2012-12-21 | [5 empty] | 2014-01-05
C2105 | 1224 | 2014-01-24 | Private Developer | Helland Meads | Solar Photovoltaics |  |  | 1.175 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Pondpool Lane, Helland, North Curry, Taunton | Somerset | South West | England | TA3 6DU | 332821 | 124658 | Taunton Deane Borough Council | 24/13/0044 | [5 empty] | 2013-09-18 | 2013-11-15
C2281 | 1226 | 2014-02-09 | Lightsource Renewable Energy | Hollamoor Farm (PV) | Solar Photovoltaics |  |  | 1.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND AT HOLLAMOOR FARM TAWSTOCK BARNSTAPLE DEVON | Devon | South West | England | EX31 3NY | 254698 | 129964 | North Devon District Council | 54884 | [5 empty] | 2012-11-19 | [6 empty] | 2013-02-18 | [5 empty] | 2013-08-01
B0697 | 1229 | 2014-02-06 |  | Langlands Solar Farm | Solar Photovoltaics |  |  | 2.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational |  | Devon | South West | England |  | 304391 | 111754 | Mid Devon District Council | 12/00628/MFUL | [5 empty] | 2012-05-14 | [6 empty] | 2012-08-07 | [5 empty] | 2013-03-20
AA701 | 1230 | 2015-09-29 | Vogt Solar | Langunnett Solar Farm | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Langunnett Farm, St Veep, Lostwithiel | Cornwall | South West | England | PL22 0NQ | 215569 | 57824 | Cornwall Council | PA12/02354 | [5 empty] | 2012-03-20 | [6 empty] | 2012-07-30 |  |  |  |  | 2013-01-14 | 2013-03-28
C1911 | 1231 | 2014-02-07 | RB & T Barton Ltd | Manor Farm (Wiltshire) | Solar Photovoltaics |  |  | 9.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land East of Manor Farm Wadswick Box Corsham Wiltshire | Wiltshire | South West | England | SN13 8JB | 384809 | 167875 | Wiltshire Council | 13/04055/FUL | [5 empty] | 2013-09-20 |  | 2013-12-18
C0565 | 1232 | 2014-01-23 | Vogt Solar | Manston Solar Farm | Solar Photovoltaics |  |  | 9.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Great West Autos, Manston Court Road, Ramsgate, Kent | Kent | South East | England | CT12 5AT | 634574 | 166813 | Thanet District Council | F/TH/12/0722 | [5 empty] | 2012-09-17 | [6 empty] | 2012-11-27 | [5 empty] | 2013-03-28
C0165 | 1233 | 2015-04-14 | Constantine Land Ltd | Marsh House Solar Park | Solar Photovoltaics |  |  | 5.508 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ne/O Gully Copse, Cheeks Farm Lane, Bentley, Alton, Hampshire | Hampshire | South East | England | GU34 | 480530 | 145789 | East Hampshire District Council | 53234/001 | A/13/2189797/NWF |  |  |  |  | 2012-03-06 |  | 2012-08-28 |  |  |  | 2013-12-23 | 2013-12-23 |  |  |  |  | 2014-06-06 | 2015-03-21
C1699 | 1236 | 2014-01-24 | Orta Moorhouse Solar Ltd | Moorhouse Lane | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land Adjoining Moorhouse Caravans Moorhouse Lane Hallen Bristol | Avon | South West | England | BS10 7RU | 354465 | 179761 | Bristol City Council | 13/03371/F | [5 empty] | 2013-07-25 | 2013-08-19
C1334 | 1237 | 2014-02-07 | Morrisons | Morrisons roof mounted solar | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Morrisons Supermarket Warehouse and Distribution Buildings, Barge Way, Kemsley, Sittingbourne, Kent | Kent | South East | England | ME10 2FD | 591187 | 167209 | Swale Borough Council | SW/13/0630 | [5 empty] | 2013-05-28 | [6 empty] | 2013-07-29 | [5 empty] | 2013-11-15
C1600 | 1239 | 2014-02-07 | Private Developer | Pierces Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land North Of Goring Lane Grazeley Reading Berkshire | Berkshire | South East | England |  | 468119 | 167296 | West Berkshire Council | 13/01675/COMIND | [5 empty] | 2013-07-16 | 2014-01-11
C1123 | 1240 | 2015-02-25 | Western Power Distribution | Rickfield Farm solar park | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Rickfield Farm North Of River Swere South Newington Road Bloxham | Oxfordshire | South East | England |  | 440354 | 234057 | Cherwell District Council | 13/01197/F | [5 empty] | 2013-08-05 | [6 empty] | 2013-11-01 |  |  |  |  | 2014-08-01 | 2014-11-01
C1504 | 1241 | 2015-08-27 | Private Developer | The Ferns | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | The Ferns, Back Lane, Hazelbury Bryan, Sturminster Newton, Dorset, DT10 2DT | Dorset | South West | England |  | 375361 | 109719 | North Dorset District Council | 2/2013/0442/PLNG | [5 empty] | 2013-05-14 | [6 empty] | 2013-07-09
C1939 | 1242 | 2014-01-24 | Cassidy & Ashton Group | Tithe Barn Lane | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land Bounded By Black Brook, Chapel Lane And Tithe Barn Lane Heapey | Lancashire | North West | England |  | 360436 | 419966 | Chorley Borough Council | 13/00811/FULMAJ | [5 empty] | 2013-08-29 |  | 2014-01-14
C2429 | 1243 | 2017-05-31 | Green Energy UK Direct | Tump Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tump Farm, Sedbury Lane, Sedbury, Chepstow, Gwent | Gloucestershire | South West | England | NP16 7HN | 354911 | 194235 | Forest of Dean District Council | P0578/15/FUL | [5 empty] | 2015-05-07 | [6 empty] | 2015-08-14 |  |  |  | 2018-08-14 | 2017-01-08 | 2017-03-08
AA991 | 1244 | 2015-09-29 | Vogt Solar | West Farm (Solar) | Solar Photovoltaics |  |  | 7.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cosheston, Pembroke Dock | Dyfed | Wales | Wales | SA72 4UN | 199608 | 203981 | Pembrokeshire County Council | 12/0050/PA | [5 empty] | 2012-05-01 | [6 empty] | 2012-11-28 | [5 empty] | 2013-03-28
C1899 | 1245 | 2014-01-24 | Hive Energy | West Kingdown | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land Between Fawkham Road And Crowhurst Lane West Kingsdown KENT (Intersecting By M20) | Kent | South East | England |  | 558329 | 163779 | Sevenoaks District Council | 13/02487/FUL | [5 empty] | 2013-08-15 | 2013-11-08
C2185 | 1246 | 2017-08-16 | Lightsource Renewable Energy | Yealmpton | Solar Photovoltaics |  |  | 2.56 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | SX 600 521, Yealmpton | Devon | South West | England | PL8 2ET | 260020 | 52193 | South Hams District Council | 62/2326/13/F | [5 empty] | 2013-10-10 | 2013-12-02
AA340 | 1247 | 2014-02-20 | Anesco (previously AEE Renewables) | Owls Lodge Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Longparish, Andover | Hampshire | South East | England |  | 443869 | 142971 | Test Valley Borough Council | 11/00430/FULLN | [5 empty] | 2011-02-20 | [6 empty] | 2011-10-07 | [5 empty] | 2013-02-28
B1212 | 1250 | 2018-09-25 | Solar Tech | Penhalurick Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land At Penhalurick Barton, Lancarrow Four Lanes, Redruth, Cornwall | Cornwall | South West | England | TR16 6TG | 170821 | 38090 | Cornwall Council | PA15/02336 | APP/D0840/W/16/3146349 |  |  |  |  | 2015-04-08 |  | 2015-11-25 | 2016-03-23 |  |  | 2016-11-21 | 2016-11-21
C0130 | 1252 | 2016-05-10 | Anesco | Beckley Solar Farm | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Beckley, Hinton, Christchurch, Dorset | Hampshire | South East | England | BH23 | 422677 | 95851 | New Forest District Council | 12/98608 | [5 empty] | 2012-04-19 | [6 empty] | 2012-06-15 |  |  |  |  | 2012-06-16 | 2012-07-27
C2028 | 1258 | 2014-02-13 | Pegasus Group | Oaklands Farm | Solar Photovoltaics |  |  | 11.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land north of Oaklands Farm, Pluckley Road, Hothfield, Kent | Kent | South East | England |  | 595597 | 143652 | Ashford Borough Council | 13/01022/AS | [5 empty] | 2013-09-12 |  | 2013-12-23
C2166 | 1259 | 2014-02-21 | Thriplow Farms | Manor Farm | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land to the East of Church Street, Thriplow | Cambridgeshire | Eastern | England |  | 545106 | 246980 | South Cambridgeshire District Council | S/2080/13/FL | [5 empty] | 2013-09-20 | 2014-01-07
C2624 | 1269 | 2016-04-18 | Anesco/Parklands Solar | Oakham Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Oakham Farm Land At Parklands Almondsbury Bristol South Gloucestershire | Avon | South West | England | BS32 4BS | 359904 | 183151 | South Gloucestershire Council | PT15/2164/F | [5 empty] | 2015-05-22 | [11 empty] | 2016-02-18 | 2016-02-22
IF1355 | 1272 | 2014-02-20 | Anesco | Limberlost Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Landfill Site Crookham Common Thatcham Berkshire | Berkshire | South East | England | RG19 8DH | 453510 | 164953 | West Berkshire Council | 12/02253/COMIND | [5 empty] | 2012-09-14 | [6 empty] | 2012-12-14 | [5 empty] | 2013-03-22
IF1078 | 1273 | 2014-02-20 | Anesco | Office Field | Solar Photovoltaics |  |  | 7.2 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Hinton, Bransgore, Hants | Hampshire | South East | England |  | 421000 | 95300 | New Forest District Council | 12/99313 | [5 empty] | 2012-10-15 | [6 empty] | 2012-12-11 | [5 empty] | 2013-03-28
IF1220 | 1274 | 2014-02-20 | Anesco | Sandys Moor Road | Solar Photovoltaics |  |  | 2.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the south of Sandys Moor Road, Wiveliscombe, Somerset | Somerset | South West | England | TA4 2LY | 308509 | 127381 | Taunton Deane Borough Council | 49/12/0075 | [5 empty] | 2012-11-22 | [6 empty] | 2013-02-01 | [5 empty] | 2013-08-31
IF1274 | 1275 | 2014-02-20 | Anesco | Skylark Meadow Solar park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Caxton Road, Bourn, Cambridgeshire | Cambridgeshire | Eastern | England | CB23 2SU | 531754 | 257635 | South Cambridgeshire District Council | S/1611/12/FL | [5 empty] | 2012-08-14 | [6 empty] | 2012-11-13 | [5 empty] | 2013-03-19
C2775 | 1277 | 2014-12-05 | J Charlton & Sons Ltd | Ainderby Steeple | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land South East Of Pumping Station, Ainderby, Steeple, North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 433420 | 492119 | Hambleton District Council | 14/00411/FUL | [5 empty] | 2014-02-24 |  | 2014-11-24
C1666 | 1278 | 2015-12-21 | Aldi | Aldi Distribution Centre - Darlington | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Aldi Regional Distribution Centre, Faverdale North, Darlington | Durham | North East | England | DL3 0UW | 427658 | 517108 | Darlington Borough Council | 13/00553/FUL | [5 empty] | 2013-07-11 | [6 empty] | 2013-09-17 | [5 empty] | 2014-03-26
C1933 | 1282 | 2014-10-29 | Lightsource Renewable Energy | Bishops Sutton | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Whitehill Lane, Alresford, Hampshire | Hampshire | South East | England |  | 459558 | 131825 | Winchester City Council | 13/01805/FUL | [5 empty] | 2013-09-02 | [6 empty] | 2013-11-15 |  |  |  |  | 2014-01-02 | 2014-03-27
C2451 | 1283 | 2014-12-17 | Maria Bailey Planning | Blackawton Solar Farm | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Proposed Solar Farm site at SX828 522, Blackawton | Devon | South West | England |  | 283302 | 52862 | South Hams District Council | 06/2883/13/F | [5 empty] | 2013-12-03 | [6 empty] | 2014-03-04 |  |  |  |  | 2014-06-01 | 2014-09-30
C2466 | 1284 | 2014-12-17 | Free Green Energy | BMW UK Manufacturing Ltd | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Bmw Uk Manufacturing Ltd, Garsington Road, Oxford, Oxfordshire, OX4 6NJ | Oxfordshire | South East | England | OX4 6NJ | 455711 | 204098 | Oxford City Council | 13/03312/PDC | [18 empty] | 2014-11-05
C2677 | 1285 | 2016-05-26 | EBS Energy LLP | Land to the East of Burton Lane | Solar Photovoltaics |  |  | 2.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Ridgewold Farm, Burton Lane, Wymeswold, Loughborough | Leicestershire | East Midlands | England |  | 459993 | 323231 | Charnwood Borough Council | P/14/1723/2 | [5 empty] | 2014-10-17 | [6 empty] | 2015-09-21 |  |  |  | 2018-09-21 | 2016-03-15 | 2016-03-15
C2706 | 1286 | 2015-09-28 | Clean Power Properties | New Lodge Farm - Solar | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused |  | Dyfed | Wales | Wales |  | 257192 | 209823 | Carmarthenshire County Council | S/29559 | [5 empty] | 2014-02-05 |  | 2016-02-05
C2721 | 1287 | 2014-03-17 | Solar Power South | Eashing Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Eashing Farm, Eashing Lane, Godalming, GU7 2QA | Surrey | South East | England |  | 495184 | 143848 | Guildford Borough Council | 13/P/01737 | [5 empty] | 2013-10-16 |  | 2014-01-15
C2668 | 1292 | 2017-05-26 | Lightsource Renewable Energy | Land west of Hawkspur Green (Hill Hall Solar) | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land west of Hill Hall, Hawkspur Green, Little Sampford Road, Little Bardfield | Essex | Eastern | England | CM7 4SH | 565225 | 232165 | Uttlesford District Council | UTT/15/0676/FUL | APP/C1570/W/15/3132904 |  |  |  |  | 2015-03-05 |  | 2015-06-12 | 2015-10-27 |  |  | 2016-04-14 | 2016-04-14 |  |  |  |  | 2016-10-03 | 2016-12-09
B1220 | 1294 | 2017-06-01 | Kingspan Insulation/ Eneco | Kingspan Insulation Solar Installation | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Enterprise Way, Sherburn In Elmet, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | LS25 6NE | 451090 | 433403 | Selby District Council | 2013/1173/FUL | [5 empty] | 2013-12-11 | [6 empty] | 2014-03-12 |  |  |  |  | 2014-03-13 | 2014-03-31
C2488 | 1296 | 2016-04-26 | Lightsource Renewable Energy | Land to the South of 15 Lough Road | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the South of 15 Lough Road, Upper Ballinderry | Co. Antrim | Northern Ireland | Northern Ireland | BT28 2PQ | 129148 | 526209 | Northern Ireland Planning Service | S/2013/0625/F | [5 empty] | 2013-11-19 | [6 empty] | 2014-07-18 |  |  |  | 2017-07-18 | 2016-02-01 | 2016-04-07
C1648 | 1298 | 2014-11-28 | Lark Energy | Langley Hall Farm | Solar Photovoltaics |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field part of Langley Hall Farm between Chalgrove and Newington | Oxfordshire | South East | England |  | 462500 | 196438 | South Oxfordshire District Council | P13/S1885/FUL | [5 empty] | 2013-07-11 | [6 empty] | 2013-09-27 |  |  |  |  | 2014-01-21 | 2014-03-31
C1816 | 1299 | 2014-11-28 | Lark Energy | Pond Farm | Solar Photovoltaics |  |  | 3.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Pond Farm, Bodham | Norfolk | Eastern | England |  | 613181 | 338444 | North Norfolk District Council | PF/13/0960 | [5 empty] | 2013-08-19 | [6 empty] | 2013-11-15 |  |  |  |  | 2014-02-01 | 2014-07-03
C0653 | 1303 | 2014-11-27 | AEE Renewables | Nether Mill Farm (resubmission) | Solar Photovoltaics |  |  | 3.08 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Halberton | Devon | South West | England | EX15 2QQ | 301983 | 112019 | Mid Devon District Council | 12/01518/MFUL | [5 empty] | 2012-10-31 |  | 2013-02-19 |  |  |  | 2014-02-19 | 2014-02-19 | [5 empty] | 2014-09-01
C1631 | 1304 | 2014-04-03 | Anesco | NEWNTON DAIRY FARM | Solar Photovoltaics |  |  | 7.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | NEWTON DAIRY FARM, BROKENBOROUGH, MALMESBURY, WILTSHIRE | Wiltshire | South West | England |  | 392277 | 191968 | Wiltshire Council | 13/01561/FUL | [5 empty] | 2013-06-12 | [6 empty] | 2013-09-10 | [5 empty] | 2014-03-19
C2600 | 1306 | 2018-07-04 | NextEnergy Capital | Pierces Farm - resubmission | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Goring Lane, Grazeley, Reading, Berkshire | Berkshire | South East | England |  | 468119 | 167296 | West Berkshire Council | 13/03187/COMIND | [5 empty] | 2013-12-23 | [6 empty] | 2014-03-19 |  |  |  |  | 2014-10-16 | 2015-03-15
C0428 | 1308 | 2014-04-04 | Lightsource Renewable Energy | Rew Farm Solar Farm | Solar Photovoltaics |  |  | 6.12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rew Farm Sweetshouse Bodmin Cornwall | Cornwall | South West | England | PL30 5AW | 209034 | 61130 | Cornwall Council | PA12/08097 | 13/00024/REF |  |  |  |  | 2012-08-28 |  | 2012-11-27 |  |  |  | 2013-06-10 | 2013-06-10 | [5 empty] | 2014-03-27
C2106 | 1310 | 2020-02-26 | Spencer Farm Produce (Juwi Renewable Energies) | The Hollies Solar Park - Skegness - extension | Solar Photovoltaics |  |  | 1.35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | The Hollies, High Lane, Croft, Skegness, Lincolnshire | Lincolnshire | East Midlands | England | PE24 4SH | 550002 | 363104 | East Lindsey District Council | S/039/01716/13 | [5 empty] | 2013-09-19 | [6 empty] | 2013-12-04
C2372 | 1311 | 2014-03-17 | Bee Green Solar | Vantage Point Solar Park | Solar Photovoltaics |  |  | 3.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land To The North East Of Vantage Point Business Village Mitcheldean Gloucestershire | Gloucestershire | South West | England |  | 366936 | 219263 | Forest of Dean District Council | P1639/13/FUL | [5 empty] | 2013-11-06 |  | 2014-02-13
C2150 | 1312 | 2016-05-20 | EBS Energy LLP | Venn Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land and Buildings at NGR 303362 113321 (Venn Farm) Sampford Peverell Devon | Devon | South West | England |  | 303362 | 113321 | Mid Devon District Council | 13/01416/MFUL | [5 empty] | 2013-10-14 | [6 empty] | 2014-02-07
C2771 | 1313 | 2015-12-22 | Kinetica Solar | West End Farm - Treswell | Solar Photovoltaics |  |  | 16.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land East Of Ashley Lane Treswell Nottinghamshire | Nottinghamshire | East Midlands | England |  | 477540 | 378957 | Bassetlaw District Council | 14/00989/FUL | [5 empty] | 2014-09-09 | [6 empty] | 2015-02-27 |  |  |  | 2018-02-27
C1667 | 1314 | 2014-11-04 | Viridor | Westbury (Closed) Landfill Site | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND SOUTH OF 40 Park Lane Heywood Wiltshire | Wiltshire | South West | England |  | 388879 | 152665 | Wiltshire Council | 13/01962/WCM | [5 empty] | 2013-07-17 | [6 empty] | 2013-10-21 |  |  |  |  | 2014-05-01 | 2014-08-05
C2427 | 1315 | 2015-05-28 | Lightsource Renewable Energy | Wiggin Hill Solar Farm - Phase 2 | Solar Photovoltaics |  |  | 4.06 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Wiggin Hill Old Ramsey Road St Ives | Cambridgeshire | Eastern | England | PE27 3 | 530960 | 274838 | Huntingdonshire District Council | 1301787FUL | [5 empty] | 2013-11-25 | [6 empty] | 2014-02-14 |  |  |  |  | 2014-11-14 | 2015-03-14
IF1318 | 1319 | 2014-04-22 | Sovereign Energy Partners LLP | Big Deere Lodge | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Field Church Street Belchamp St Paul Essex | Essex | Eastern | England |  | 579190 | 242294 | Braintree District Council | 13/00832/FUL | [5 empty] | 2013-08-06 |  | 2014-04-17
C2526 | 1320 | 2016-01-06 | Grain Harvesters Ltd | Grain Harvesters Ltd | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Grain Harvesters Ltd, Staple Road, Wingham, Canterbury, CT3 1LS | Kent | South East | England | CT3 1LS | 625509 | 156911 | Dover District Council | 13/01006 | [5 empty] | 2013-12-05 | [6 empty] | 2014-03-06 |  |  |  |  | 2014-09-21 | 2014-12-01
C2430 | 1321 | 2014-04-25 | Orta East Hendred Solar Ltd | Reading Road | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land North of Reading Road, East Hendred | Oxfordshire | South East | England |  | 446107 | 190207 | Vale of White Horse District Council | P13/V2544/FUL | [5 empty] | 2013-11-27 |  | 2014-02-26
C1934 | 1322 | 2014-11-14 | Lightsource Renewable Energy / Push Energy | Hyde Farm | Solar Photovoltaics |  |  | 10.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hydes Solar Farm Little Bardfield Braintree Essex | Essex | Eastern | England |  | 564364 | 231548 | Uttlesford District Council | UTT/13/2207/FUL | [5 empty] | 2013-08-27 | [6 empty] | 2013-11-22 | [5 empty] | 2014-11-13
C2163 | 1323 | 2016-06-30 | Sun & Soil | Rogers Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Rogers Farm, Rogers Lane, Newton, SUDBURY | Suffolk | Eastern | England | CO10 5LA | 593113 | 241405 | Babergh District Council | B/13/01107 | APP/D3505/W/14/2218072 |  |  | 42338 |  | 2013-09-20 |  | 2014-02-27 | 2014-05-09 |  | 2016-06-08
C2779 | 1324 | 2015-05-14 | Lightsource Renewable Energy | St Francis Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | St Francis Farm, Potmans Lane, Catsfield/Bexhill | East Sussex | South East | England |  | 572709 | 111249 | Rother District Council | RR/2014/558/P | [5 empty] | 2014-02-28 | [6 empty] | 2014-08-26 |  |  |  | 2017-08-26 | 2014-11-17 | 2015-03-19
C2821 | 1325 | 2017-05-31 | Solafields U/Bishop's Waltham Renewables Ltd | Bishop’s Waltham Solar Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Winchester Road, Bishops Waltham | Hampshire | South East | England | SO32 2LL | 455734 | 116390 | Winchester City Council | 15/00786/FUL | [5 empty] | 2015-04-17 | [6 empty] | 2015-08-07 |  |  |  | 2018-08-07 | 2016-10-31 | 2017-02-17
B1296 | 1327 | 2019-11-26 | Juwi Renewable Energies | Blaenporth Solar Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Blaenporth, Cardigan | Dyfed | Wales | Wales |  | 226464 | 248292 | Ceredigion County Council | A140370 | [5 empty] | 2014-05-22 | [6 empty] | 2014-09-03 |  |  |  | 2017-09-03
C1208 | 1328 | 2017-01-03 | Equitix | Nova Scotia Farm solar park | Solar Photovoltaics |  |  | 13.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nova Scotia Farm, West Caister, Great Yarmouth, Norfolk | Norfolk | Eastern | England | NR30 5SH | 650384 | 313545 | Great Yarmouth Borough Council | 06/13/0180/F | [5 empty] | 2013-04-16 | [6 empty] | 2013-07-10 |  |  |  |  | 2013-11-30 | 2014-03-31
C1523 | 1329 | 2014-04-30 | TGC Renewables | Hall Farm, East Beckham | Solar Photovoltaics |  |  | 10.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hall Farm, Land At Hall Farm, East Beckham, Holt, Norfolk, BR11 8GA | Norfolk | Eastern | England |  | 614370 | 339859 | North Norfolk District Council | PF/13/0772 | [5 empty] | 2013-06-27 | [6 empty] | 2013-09-23 | [5 empty] | 2014-03-31
C1421 | 1330 | 2014-04-30 | Wessex Solar Energy | Cefn Betingau Farm | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Cefn Betingau Farm, Morriston, Swansea | West Glamorgan | Wales | Wales | SA6 6NX | 266050 | 212400 | City and County Council of Swansea | 2013/0865 | [5 empty] | 2013-06-10 | [6 empty] | 2013-08-28 | [5 empty] | 2014-03-31
C1597 | 1331 | 2014-04-30 | Hill Farm Solar Park Limited | Hill Farm Solar Park (VoWH) | Solar Photovoltaics |  |  | 14.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land west of Hill Farm Steventon | Oxfordshire | South East | England |  | 445237 | 191060 | Vale of White Horse District Council | P13/V1478/FUL | [5 empty] | 2013-07-12 | [6 empty] | 2013-10-01 |  |  |  |  | 2013-12-01 | 2014-03-31
C1898 | 1332 | 2014-04-30 | Sunsave 25 (Wix Lodge Farm) Limited/ Vogt Solar | Wix Lodge | Solar Photovoltaics |  |  | 18.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Wix Lodge Colchester Road Wix Manningtree Essex CO11 2RP | Essex | Eastern | England |  | 614962 | 228422 | Tendring District Council | 13/00896/FUL | [5 empty] | 2013-08-19 | [6 empty] | 2013-11-15 | [5 empty] | 2014-03-31
C1969 | 1333 | 2014-04-30 | Solar Century/ Bluefield Solar | Saxley Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Saxley Farm Saxley Farm Lane Red Rice Andover Hampshire SP11 7PG | Hampshire | South East | England |  | 432525 | 140299 | Test Valley Borough Council | 13/02122/FULLN | [5 empty] | 2013-09-27 | [6 empty] | 2013-12-18 | [5 empty] | 2014-03-31
C2019 | 1334 | 2018-07-03 | Good Energy Generation | Mapperton Farm | Solar Photovoltaics |  |  | 24 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Mapperton Farm, Mapperton, Almer | Dorset | South West | England |  | 389660 | 99160 | East Dorset District Council | 3/13/0681/FUL |  |  |  | 42207 |  | 2013-07-25 | 2018-06-11
C2407 | 1335 | 2017-02-01 | Foresight | Snarlton Farm (Melksham solar farm) | Solar Photovoltaics |  |  | 49.6 | n/a | 1.3 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Snarlton Farm Snarlton Lane Melksham Wilts | Wiltshire | South West | England | SN12 7QP | 393855 | 163823 | Wiltshire Council | 13/06140/FUL | APP/Y3940/A/14/2221012 |  |  |  |  | 2013-11-19 |  | 2014-04-16 | 2014-07-03 |  |  | 2015-06-18 | 2015-06-18 |  |  |  | 2018-06-18 | 2015-11-23 | 2016-03-31
AA188 | 1337 | 2011-04-20 | Alectron Investments Ltd | Cornbury Park Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Cornbury Park, Charlbury | Oxfordshire | South East | England |  | 433594 | 219035 | West Oxfordshire District Council | 11/0184/P/FP | [6 empty] | 2011-04-20
B1306 | 1338 | 2014-04-30 | Lackford Estate Solar Park Ltd | Lackford Estate Solar Park | Solar Photovoltaics |  |  | 20.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bury St Edmunds, Suffolk IP28 | Suffolk | Eastern | England |  | 578180 | 268835 | St Edmundsbury Borough Council | DC/13/0017/FUL | [5 empty] | 2013-08-13 | [6 empty] | 2013-11-02 | [5 empty] | 2014-03-31
AA237 | 1339 | 2018-09-04 | Greencoat Capital | Colpmans Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Islip, Kettering, Northamptonshire, NN14 3LT | Northamptonshire | East Midlands | England |  | 497983 | 279596 | East Northamptonshire Council | 11/00079/FUL | [5 empty] | 2011-01-19 | [6 empty] | 2011-05-27 | [5 empty] | 2012-04-17
AA351 | 1340 | 2013-03-14 | KL Technologies | Porvair International Ltd | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Estuary Road, Kings Lynn, Norfolk | Norfolk | Eastern | England | PE30 2HS | 561175 | 321828 | King's Lynn and West Norfolk Borough Council | 10/01859/FM | [5 empty] | 2011-01-17 | [6 empty] | 2011-03-09 | [5 empty] | 2012-10-04
AA374 | 1341 | 2013-04-12 | The Green Company | Willsland Solar farm | Solar Photovoltaics |  |  | 3.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Highampton, Beaworthy, Devon | Devon | South West | England |  | 250049 | 104054 | West Devon Borough Council | 01537/2011 | No appeal number |  |  |  |  | 2011-05-18 |  | 2011-09-13 |  |  |  | 2012-03-07 | 2012-03-07 |  |  |  |  | 2013-01-10 | 2013-03-21
AA410 | 1342 | 2012-10-15 | Private Developer | Frying Down Copse Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | north of Bushywarren Lane, Ellisfield, Basingstoke | Hampshire | South East | England |  | 465093 | 146525 | Basingstoke and Deane Borough Council | BDB/73851 | [5 empty] | 2011-02-02 | [6 empty] | 2011-05-13 | [5 empty] | 2012-04-16
AA667 | 1343 | 2013-04-11 | Low Carbon Solar | Wilmingham Lane Solar Farm | Solar Photovoltaics |  |  | 7.01 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Btw Tapnell Furze And Wilmingham Plantation, Wilmingham Lane, Freshwater, Isle of Wight, PO40 9UQ | Isle of Wight | South East | England |  | 436444 | 87630 | Isle of Wight Council | P/00053/12 | [5 empty] | 2012-01-27 | [6 empty] | 2012-04-12 |  |  |  |  | 2012-11-16 | 2013-03-14
AA739 | 1344 | 2018-07-26 | NextEnery Solar Fund (NESF) | Chilton Cantelo Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The Cypress House Road, Chilton Cantelo, Yeovil, Somerset, BA22 8BQ | Somerset | South West | England |  | 357797 | 121851 | South Somerset District Council | 12/01055/FUL | N/A |  |  |  |  | 2012-03-20 | [6 empty] | 2012-07-11 | [5 empty] | 2013-02-28
AA753 | 1345 | 2017-08-16 | Lightsource Renewable Energy | Hunscott Solar Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Hunscott Farm Ashwater Beaworthy Devon | Devon | South West | England | EX21 5DJ | 239247 | 99586 | Torridge District Council | 1/0240/2012/FULM | N/A |  |  |  |  | 2012-03-30 | 2012-06-29
AA860 | 1346 | 2013-06-21 | Wessex Solar Energy | Beaford Brook Solar Park | Solar Photovoltaics |  |  | 5.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Upcott Barton Beaford Devon | Devon | South West | England |  | 256805 | 115563 | Torridge District Council | 1/0571/2012/FULM | [5 empty] | 2012-07-23 | [6 empty] | 2012-12-07 | [5 empty] | 2013-06-03
AA863 | 1347 | 2012-12-11 | AEE Renewables | Reydon Farm | Solar Photovoltaics |  |  | 4.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land At Quay Lane, Reydon, Suffolk, IP18 6SE | Suffolk | Eastern | England |  | 648627 | 277692 | Waveney District Council | DC/12/0761/FUL | [5 empty] | 2012-08-01 | 2012-10-02
AA943 | 1348 | 2015-09-02 | WS Systems Ltd | Hayford Farm | Solar Photovoltaics |  |  | 8.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Westbury, Shrewsbury, Shropshire | Shropshire | West Midlands | England | SY5 9PF | 336254 | 310618 | Shropshire Council | 12/03725/FUL | [5 empty] | 2012-09-10 | [6 empty] | 2012-12-20 |  |  |  |  | 2014-07-01 | 2014-09-10
AA979 | 1349 | 2013-06-14 | AEE Renewables | Halse Farm | Solar Photovoltaics |  |  | 8.24 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bishop's Lydeard, TA4 3LZ | Somerset | South West | England |  | 315101 | 128738 | Taunton Deane Borough Council | 06/12/0034 | [5 empty] | 2012-06-15 | [6 empty] | 2012-09-06 | [5 empty] | 2013-03-28
B1249 | 1350 | 2015-06-05 | Bombardier Aerospace | Bombardier Factory | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Airport Road West | Co. Down | Northern Ireland | Northern Ireland | BT3 9ED | 145881 | 537550 | Northern Ireland Planning Service | Z/2013/1267/F | [5 empty] | 2013-11-01 | [6 empty] | 2014-02-07 |  |  |  | 2019-02-07 | 2015-03-15 | 2015-05-27
C0109 | 1351 | 2012-06-21 | Private Developer | OKEFORD FITZPAINE - SOLAR FARM | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Okeford Fitzpaine, Blandford Forum, Dorset, DT11 | Dorset | South West | England |  | 377833 | 111009 | North Dorset District Council | 2/2012/0254/PLNG | [5 empty] | 2012-03-20 | 2012-05-29
C0190 | 1352 | 2013-04-12 | Ms Power Projects Ltd | STRETE FARM SOLAR FARM | Solar Photovoltaics |  |  | 4.78 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Strete Farm, Whimple, Exeter, Devon | Devon | South West | England | EX5 2PL | 304235 | 94913 | East Devon District Council | 12/1082/MFUL | [5 empty] | 2012-05-09 | [6 empty] | 2012-08-08 |  |  |  |  | 2013-01-16 | 2013-03-08
C0217 | 1353 | 2013-04-12 | Private Developer | Tregassow Farm - Solar Modules | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tregassow Farm, St Erme, Truro, Cornwall | Cornwall | South West | England | TR4 9BL | 185395 | 49565 | Cornwall Council | PA12/04244 | [5 empty] | 2012-05-24 | [6 empty] | 2012-11-16 |  |  |  |  | 2013-01-13 | 2013-03-28
C0567 | 1354 | 2013-01-25 | Lark Energy | Thornham Solar Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Lyng Farm, Ringstead Road, Thornham, Hunstanton, Norfolk | Norfolk | Eastern | England | PE36 6NN | 573903 | 340478 | King's Lynn and West Norfolk Borough Council | 12/01505/FM | [5 empty] | 2012-09-17 |  | 2012-12-10
C0975 | 1355 | 2013-07-14 | Private Developer | Higher Hatherleigh Solar Farm extension | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Higher Hatherleigh Farm Grove Lane North Cheriton Templecombe Somerset | Somerset | South West | England |  | 371305 | 127243 | South Somerset District Council | 12/03914/FUL | [5 empty] | 2012-10-05 | [6 empty] | 2013-02-21 | [5 empty] | 2013-03-28
C1060 | 1356 | 2013-03-26 | Lightsource Renewable Energy | Pont Andrew Solar Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND AT FORMER CYNHEIDRE SHAFTS 3 & 4, CYNHEIDRE, LLANELLI | Dyfed | Wales | Wales |  | 252617 | 210675 | Carmarthenshire County Council | S/24069 | [5 empty] | 2010-11-29 | [6 empty] | 2011-04-22 | [5 empty] | 2012-07-31
C1135 | 1357 | 2013-12-10 | AEE Renewables | Glebe Farm Solar Park (resubmission) | Solar Photovoltaics |  |  | 4.16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Glebe Farm, Tolland, Taunton, Somerset | Somerset | South West | England | TA4 3PR | 310153 | 132127 | Taunton Deane Borough Council | 41/13/0001 | [5 empty] | 2013-04-08 |  | 2013-06-07
C1158 | 1358 | 2016-02-16 | Green Cat Renewables | Cairnhill Farm solar park | Solar Photovoltaics |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cairnhill, Turriff, Grampian | Grampian | Scotland | Scotland | AB53 5TN | 377824 | 852312 | Aberdeenshire Council | APP/2013/0997 | [5 empty] | 2013-04-02 | [6 empty] | 2013-05-31 |  |  |  |  | 2015-04-15 | 2015-09-15
C1288 | 1359 | 2014-04-02 | Sunsave 16 Ltd/ Vogt Solar | Manston Solar Farm extension (Westwood) | Solar Photovoltaics |  |  | 9.18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND TO SOUTH SIDE OF PRESTON ROAD RAMSGATE | Kent | South East | England |  | 635063 | 166833 | Thanet District Council | F/TH/13/0315 | [5 empty] | 2013-05-10 | [6 empty] | 2013-07-24 | [5 empty] | 2014-03-28
C1450 | 1361 | 2017-08-16 | Lightsource Renewable Energy | Gaston Lane | Solar Photovoltaics |  |  | 5.8 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land South of, Gaston Lane, Farringdon, Alton | Hampshire | South East | England |  | 471623 | 135539 | East Hampshire District Council | 54507/001 | [5 empty] | 2013-06-11 | 2013-08-14
C1492 | 1362 | 2014-04-02 | Sunsave 10 (FAREHAM) / Vogt Solar | Newlands Farm Solar - resubmission | Solar Photovoltaics |  |  | 20.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND AT NEWLANDS FARM SOUTH OF TANNERS LANE/ WEST OF NEWGATE LANE FAREHAM | Hampshire | South East | England | PO14 1AU | 456710 | 103840 | Fareham Borough Council | P/13/0528/FP | [5 empty] | 2013-06-28 | [6 empty] | 2013-09-27 | [5 empty] | 2014-03-29
C1743 | 1367 | 2014-11-28 | Lark Energy | Fen Road | Solar Photovoltaics |  |  | 1.44 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off Fen Road, Boston, Lincolnshire | Lincolnshire | East Midlands | England | PE21 7JD | 529606 | 342676 | Boston Borough Council | B/13/0345 | [5 empty] | 2013-09-11 | [6 empty] | 2013-12-10 |  |  |  |  | 2014-02-01 | 2014-07-22
C1815 | 1371 | 2020-05-27 | RG and RJ Allen Ltd | Hill Top Farm | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Hill Top Farm, Main Street, Barrow, OAKHAM, Rutland | Leicestershire | East Midlands | England | LE15 7PE | 488970 | 315114 | Rutland County Council | 2013/0688/MAJ | [5 empty] | 2013-08-16 | [6 empty] | 2013-11-11 |  |  |  | 2016-11-11
C1943 | 1373 | 2014-01-24 | Lightsource Renewable Energy | Halwell Airfield | Solar Photovoltaics |  |  | 5.7 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land at SX786 529, South of Halwell Airfield, Halwell | Devon | South West | England |  | 278608 | 52889 | South Hams District Council | 22/2050/13/F | [5 empty] | 2013-09-03 |  | 2013-11-22
C1963 | 1374 | 2016-01-21 | Private Developer | Long Meadow Farm | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Long Meadow Farm, Horton Road, Ivinghoe, Leighton Buzzard, Bedfordshire, LU7 | Buckinghamshire | South East | England | LU7 | 493244 | 217149 | Aylesbury Vale District Council | 13/02392/APP | [5 empty] | 2013-09-04 | [6 empty] | 2014-01-10 | [5 empty] | 2015-12-01
C1998 | 1375 | 2014-01-24 | Lightsource Renewable Energy | South of Beckingham Road | Solar Photovoltaics |  |  | 10.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land South Of Beckingham Road, Great Totham, Essex | Essex | Eastern | England |  | 587408 | 211978 | Maldon District Council | 13/00818/FUL | [5 empty] | 2013-09-05 |  | 2013-11-21
C2033 | 1376 | 2015-01-07 | Gamma Solar Limited | Ingham solar farm | Solar Photovoltaics |  |  | 26 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land North West Of Ingham, Thetford Road, Ingham, Suffolk | Suffolk | Eastern | England |  | 585075 | 271612 | St Edmundsbury Borough Council | SE/13/0905/FUL | APP/E3525/A/14/2218805 |  |  |  |  | 2013-07-24 |  | 2014-02-07 | 2014-06-02 |  | 2015-01-07
C2124 | 1379 | 2014-01-09 | IKEA Properties Investments Ltd | Ikea Distribution Centre - Doncaster | Solar Photovoltaics |  |  | 1.98 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Application Withdrawn | Application Withdrawn | Ikea Distribution Centre Yorkshire Way Armthorpe Doncaster DN3 3FB | South Yorkshire | Yorkshire and Humber | England |  | 464343 | 404848 | Doncaster Metropolitan Borough Council | 13/02025/FUL | [5 empty] | 2013-10-02 | 2013-11-25
C2148 | 1380 | 2015-03-31 | Clinton Devon Estates | Liverton Farm | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Liverton Farm Salterton Road Exmouth | Devon | South West | England | EX8 5BW | 303131 | 82478 | East Devon District Council | 13/2202/MFUL | [5 empty] | 2013-10-15 | [6 empty] | 2014-01-10 |  |  |  |  | 2014-11-01 | 2015-03-19
C2235 | 1381 | 2014-02-19 | Lark Energy | Land Adjacent to A422 | Solar Photovoltaics |  |  | 3.4 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land Adjacent To Brackley Road, Turweston, Buckinghamshire | Buckinghamshire | South East | England |  | 459570 | 236472 | Aylesbury Vale District Council | 13/02921/APP | [5 empty] | 2013-10-21 | 2014-01-16
C2237 | 1382 | 2014-04-02 | Sunsave 20 (Knowlton) Ltd/ Vogt Solar | Home Farm (Knowlton - solar) | Solar Photovoltaics |  |  | 11.54 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Home Farmhouse, Knowlton, Goodnestone, Canterbury, CT3 1PT | Kent | South East | England |  | 628013 | 153474 | Dover District Council | 13/00405 | [5 empty] | 2013-05-25 | [6 empty] | 2013-10-07 | [5 empty] | 2014-03-30
IF1084 | 1384 | 2013-03-07 | AEE Renewables | Lake Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Draycot Cerne, Sutton Benger, Wiltshire | Wiltshire | South West | England | SN15 4SQ | 393800 | 177700 | Wiltshire Council | 11/00003/FUL | [5 empty] | 2011-01-14 | [6 empty] | 2011-04-11 | [5 empty] | 2011-07-01
IF1226 | 1385 | 2013-04-15 | Orta Solar | Parkhouse Corner (Orta Solar) | Solar Photovoltaics |  |  | 6.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Snoddington Farm, Salisbury Road, Shipton Bellinger, Tidworth | Hampshire | South East | England | SP9 | 422792 | 144085 | Test Valley Borough Council | 12/01725/FULLN | [5 empty] | 2012-08-09 | [6 empty] | 2012-11-14 |  |  |  |  | 2012-12-03 | 2013-02-23
IF1357 | 1386 | 2013-03-12 | Solar Power South | Sandhill Solar Park | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | SANDHILL PARK, BISHOPS LYDEARD | Somerset | South West | England |  | 316188 | 129704 | Taunton Deane Borough Council | 06/10/0044 | [5 empty] | 2010-11-09 | [6 empty] | 2011-01-20 | [5 empty] | 2011-07-13
AA421 | 1387 | 2011-07-20 | Abbey Renewables | Mingay Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Mingay Farm, Twentypence Road, Wilburton, Cambridgeshire | Cambridgeshire | Eastern | England |  | 547655 | 274082 | East Cambridgeshire District Council | 10/00958/FUM | [5 empty] | 2010-10-22 | [6 empty] | 2011-02-09 | [5 empty] | 2011-07-14
AA835 | 1388 | 2013-06-14 | AEE Renewables | Jordanston Solar Farm | Solar Photovoltaics |  |  | 4.96 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | St Florence, Tenby, Dyfed | Dyfed | Wales | Wales | SA70 8NQ | 206785 | 201103 | Pembrokeshire County Council | 12/0252/PA | [5 empty] | 2012-06-28 | [6 empty] | 2012-09-26 | [5 empty] | 2013-03-28
C0347 | 1389 | 2013-12-10 | AEE Renewables | Glebe Farm Solar Farm | Solar Photovoltaics |  |  | 4.55 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Glebe Farm, Tolland, Taunton, Somerset | Somerset | South West | England | TA4 3PR | 310153 | 132127 | Taunton Deane Borough Council | 41/12/0005 | [5 empty] | 2012-07-17 | 2012-11-09
C1698 | 1390 | 2015-12-21 | Aldi | Aldi Distribution Centre - Neston | Solar Photovoltaics |  |  | 1.18 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Aldi Distribution Centre, Chester High Road, Neston | Cheshire | North West | England | CH64 3TS | 331289 | 377434 | Cheshire West and Chester Council | 13/03012/FUL | [5 empty] | 2013-07-09 | [6 empty] | 2013-09-13 | [5 empty] | 2014-03-24
C0236 | 1394 | 2014-03-24 | British Solar Renewables | Rodbourne Rail Farm - Solar Park | Solar Photovoltaics |  |  | 7.64 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rodbourne Rail Farm, Grange Lane, Corston, Malmesbury, Wiltshire | Wiltshire | South West | England | SN16 0ES | 393204 | 184703 | Wiltshire Council | 12/01122/FUL | [5 empty] | 2012-05-25 | [6 empty] | 2012-11-13 | [5 empty] | 2013-08-02
C0978 | 1395 | 2013-07-26 | British Solar Renewables | Southfield Farm Solar Park | Solar Photovoltaics |  |  | 11.47 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Southfield Farm Smithy Lane Yeovilton Yeovil Somerset | Somerset | South West | England |  | 357535 | 123569 | South Somerset District Council | 13/01192/FUL | [5 empty] | 2013-04-16 |  | 2013-07-11
C1332 | 1396 | 2013-09-04 | Energi | South Hill Farm solar park | Solar Photovoltaics |  |  | 7.84 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at South Hill Farm Bridgwater Road Bleadon BS24 0AL | Avon | South West | England |  | 333202 | 157052 | North Somerset Council | 13/P/0854/F2 | [5 empty] | 2013-05-14 |  | 2013-08-21
IF1365 | 1404 | 2015-08-11 | Lark Energy | Barnby Moor | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | N/O Station Road, Barnby Moor, Retford, Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 8QZ | 466961 | 384866 | Bassetlaw District Council | 13/01311/FUL | [5 empty] | 2013-11-15 | [6 empty] | 2014-02-03 |  |  |  |  | 2015-02-01 | 2015-03-30
AA869 | 1416 | 2018-07-26 | NextEnery Solar Fund (NESF) | Knockworthy Farm | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Huntshaw Torrington Devon | Devon | South West | England | EX38 7HJ | 251121 | 122799 | Torridge District Council | 1/0643/2012/FULM | [5 empty] | 2012-08-02 | [6 empty] | 2012-11-01 | [5 empty] | 2013-08-31
C2357 | 1417 | 2014-03-17 | Hive Energy | Green Farm (Wix Manningtree) | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Green Farm Oakley Road Wix Manningtree Essex CO11 2SE | Essex | Eastern | England |  | 616994 | 228407 | Tendring District Council | 13/01210/FUL | [5 empty] | 2013-11-08 |  | 2014-02-07
C0138 | 1418 | 2018-07-26 | NextEnery Solar Fund (NESF) | Raglington Farm, Botley Road, Shedfield, Southampton, Hampshire | Solar Photovoltaics |  |  | 5.77 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Raglington Farm, Botley Road, Shedfield, Southampton | Hampshire | South East | England | SO32 2HL | 454062 | 113445 | Winchester City Council | 12/00913/FUL | [5 empty] | 2012-04-10 | [6 empty] | 2012-07-10 | [5 empty] | 2013-08-31
IF1043 | 1419 | 2017-08-16 | Lightsource Renewable Energy | Bowhay Farm | Solar Photovoltaics |  |  | 10.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Shillingford Abbot, Exeter, Devon | Devon | South West | England | EX2 9QQ | 289494 | 88559 | Teignbridge District Council | 12/03220/MAJ | [5 empty] | 2012-10-26 | 2013-01-15
IF1049 | 1420 | 2013-02-26 | Lightsource Renewable Energy | Barleclose Farm | Solar Photovoltaics |  |  | 1.02 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Two Ash Hill, Chard, Somerset | Somerset | South West | England | TA20 2NW | 333157 | 106525 | South Somerset District Council | 12/03797/FUL | [5 empty] | 2012-10-01 |  | 2013-01-10
IF1077 | 1421 | 2013-03-25 | Lightsource Renewable Energy | Stables Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Warlands Lane Shalfleet Newport Isle Of Wight PO30 4NH | Isle of Wight | South East | England |  | 440920 | 88770 | Isle of Wight Council | P/00353/12 | [5 empty] | 2012-03-13 | [6 empty] | 2012-06-12 |  |  |  |  | 2012-07-09 | 2012-08-07
IF1251 | 1423 | 2013-03-15 | Lightsource Renewable Energy | Luson Farm | Solar Photovoltaics |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ermington, Ivybridge | Devon | South West | England | PL21 9JZ | 262016 | 53112 | South Hams District Council | 21/2606/12/F | [5 empty] | 2012-11-09 | [6 empty] | 2013-01-08 |  |  |  |  | 2013-01-30 | 2013-02-26
C2370 | 1426 | 2014-02-19 | Hive Energy | Winham Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Winham Farm, Westcott, Cullompton, Devon | Devon | South West | England | EX15 1SA | 301973 | 103977 | Mid Devon District Council | 13/01408/MFUL | [5 empty] | 2013-11-14 | 2014-01-20
C1705 | 1427 | 2014-02-14 | INRG Solar | Poltimore solar farm | Solar Photovoltaics |  |  | 5.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land To The East Of The M5 And West Of Jarvishayes Poltimore | Devon | South West | England |  | 297438 | 96563 | East Devon District Council | 13/1650/MFUL | [5 empty] | 2013-07-25 |  | 2013-12-19
C1752 | 1428 | 2016-03-22 | INRG Solar | Kellygreen Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Kellygreen Farm, St Kew, Bodmin | Cornwall | South West | England | PL30 3DT | 205482 | 77292 | Cornwall Council | PA13/07973 | APP/D0840/A/14/2212325 |  |  |  |  | 2013-09-02 |  | 2013-11-22 | 2014-01-30 |  |  | 2014-06-23 | 2014-06-23 |  |  |  |  | 2016-02-05 | 2016-03-30
C2426 | 1429 | 2015-05-28 | juwi Renewable Energies | Grove Farm (solar) | Solar Photovoltaics |  |  | 3.476 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Grove Farm, Lydeard, St. Lawrence | Somerset | South West | England |  | 311670 | 131572 | Taunton Deane Borough Council | 41/13/0004 | [5 empty] | 2013-12-03 | [6 empty] | 2014-02-27 |  |  |  |  | 2015-01-05 | 2015-03-24
C1432 | 1431 | 2015-09-30 | KS SPV29 Ltd | Pithayes | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land To West & North West Pithayes Farm Whimple | Devon | South West | England |  | 303922 | 96954 | East Devon District Council | 13/1202/MFUL | [5 empty] | 2013-06-11 |  | 2013-11-09
AA321 | 1432 | 2011-08-19 | Lark Energy | Melton Mowbray Solar Farm | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | off Leicester Road, Melton Mowbray | Leicestershire | East Midlands | England |  | 472881 | 317868 | Melton Borough Council | 11/00156/FUL | [5 empty] | 2011-02-25 | 2011-07-21
AA375 | 1433 | 2011-08-30 | Lark Energy | Marston Solar Farm | Solar Photovoltaics |  |  | 4.89 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | off Toll Bar Road, Marston | Lincolnshire | East Midlands | England |  | 488029 | 342114 | South Kesteven District Council | S11/0548 | [5 empty] | 2011-03-29 | [6 empty] | 2011-05-19 | [5 empty] | 2011-07-18
C1237 | 1434 | 2014-01-24 | Lark Energy | Deeping Gate Tree Nurseries solar park | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land adj. Deeping Gate Tree Nurseries, Northfield Road, Market Deeping | Lincolnshire | East Midlands | England |  | 514339 | 311962 | South Kesteven District Council | S13/2242 | [5 empty] | 2013-08-23 |  | 2013-12-11
B1238 | 1435 | 2014-02-17 | Lightsource Renewable Energy | Tredown Solar Farm | Solar Photovoltaics |  |  | 1.22 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to S/E of Kelly Cross SX398815 (part of Tredown Farm) Meadwell, Kelly, Devon | Devon | South West | England |  | 239431 | 81407 | West Devon Borough Council | 02517/2012 | [5 empty] | 2012-03-28 | [6 empty] | 2013-03-28 | [5 empty] | 2013-08-27
AA727 | 1436 | 2017-08-16 | Lightsource Renewable Energy | Tinny Hall Solar Farm | Solar Photovoltaics |  |  | 1.45 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Tinny Hall Farm Lewannick Launceston | Cornwall | South West | England | PL15 7QE | 226709 | 80753 | Cornwall Council | PA12/02869 | N/A |  |  |  |  | 2012-03-23 | 2012-04-24
AA899 | 1437 | 2017-08-16 | Lightsource Renewable Energy | Trehane Farm | Solar Photovoltaics |  |  | 1.42 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Davidstow Camelford Cornwall | Cornwall | South West | England | PL32 9XP | 214522 | 87798 | Cornwall Council | PA12/03098 | [5 empty] | 2012-03-30 | 2012-12-03
AA913 | 1438 | 2017-08-16 | Lightsource Renewable Energy | Trelay Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Pelynt Looe Cornwall | Cornwall | South West | England | PL13 2JX | 220957 | 54217 | Cornwall Council | PA12/02878 | [5 empty] | 2012-03-26 | 2012-12-03
AA930 | 1439 | 2013-04-12 | Lightsource Renewable Energy | Slaughtergate Farm | Solar Photovoltaics |  |  | 1.81 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Wavering Lane West, Gillingham, Dorset, SP8 4NR | Dorset | South West | England |  | 378233 | 127441 | North Dorset District Council | 2/2012/1042/PLNG | [5 empty] | 2012-08-31 | [6 empty] | 2012-11-06 |  |  |  |  | 2013-01-15 | 2013-03-20
AA950 | 1440 | 2017-08-16 | Lightsource Renewable Energy | Yew Tree Cottage | Solar Photovoltaics |  |  | 2.75 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Penryn Cornwall | Cornwall | South West | England | TR10 9BX | 174260 | 32687 | Cornwall Council | PA12/09032 | [5 empty] | 2012-10-03 | 2012-10-12
AA969 | 1441 | 2013-04-12 | Lightsource Renewable Energy | Kia Ora Farm | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Knowle Lane, Cullompton, Devon | Devon | South West | England | EX15 1PZ | 300975 | 107058 | Mid Devon District Council | 12/01350/MFUL | [5 empty] | 2012-09-19 | [6 empty] | 2012-11-30 |  |  |  |  | 2013-01-30 | 2013-03-21
AA970 | 1442 | 2013-04-12 | Lightsource Renewable Energy | Ellicombe Farm | Solar Photovoltaics |  |  | 1.43 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Morchard Road, Crediton, Devon | Devon | South West | England | EX17 5LS | 274429 | 105004 | Mid Devon District Council | 12/01306/MFUL | [5 empty] | 2012-09-13 | [6 empty] | 2012-12-13 |  |  |  |  | 2013-03-04 | 2013-03-18
AA974 | 1443 | 2013-04-12 | Lightsource Renewable Energy | Southcombe Farm | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Shebbear, Devon | Devon | South West | England | EX21 5RG | 244284 | 111956 | Torridge District Council | 1/0724/2012/FULM | [5 empty] | 2012-08-29 | [6 empty] | 2012-11-28 |  |  |  |  | 2013-01-07 | 2013-03-20
AA988 | 1444 | 2013-05-14 | Lightsource Renewable Energy | Pitts Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Chilcote Lane, Chilcote | Somerset | South West | England | BA5 3DX | 359176 | 146235 | Mendip District Council | 2012/0645 | [5 empty] | 2012-04-16 | [6 empty] | 2013-01-07
AA990 | 1445 | 2013-03-25 | Lightsource Renewable Energy | West Bradley Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Templeton, Tiverton, Devon | Devon | South West | England | EX16 8BJ | 289684 | 114161 | Mid Devon District Council | 12/00415/MFUL | [5 empty] | 2012-03-16 | [6 empty] | 2012-05-18 |  |  |  |  | 2012-06-14 | 2012-08-03
AA992 | 1446 | 2013-04-12 | Lightsource Renewable Energy | Whiddon Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ashwater Beaworthy, Devon | Devon | South West | England | EX21 5EP | 239451 | 97227 | Torridge District Council | 1/0239/2012/FULM | [5 empty] | 2012-03-28 | [6 empty] | 2012-06-27 |  |  |  |  | 2012-12-17 | 2013-03-25
IF1031 | 1449 | 2013-04-26 | Lightsource Renewable Energy | Lovedean Farm | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Day Lane, Horndean, Waterlooville, Hampshire, PO8 0SH | Hampshire | South East | England |  | 468005 | 112956 | East Hampshire District Council | 54495/001 | [5 empty] | 2012-10-02 | [6 empty] | 2012-12-24 | [5 empty] | 2013-03-28
IF1032 | 1450 | 2013-04-12 | Lightsource Renewable Energy | Higher Knapp Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Higher Knapp Farm, Knapp, Taunton, Somerset, TA3 6AY | Somerset | South West | England |  | 330222 | 124913 | Taunton Deane Borough Council | 24/12/0039 | [5 empty] | 2012-10-08 | [6 empty] | 2013-01-11 |  |  |  |  | 2013-02-11 | 2013-03-21
C1929 | 1452 | 2017-08-16 | Lightsource Renewable Energy | Barn Farm (Bradfield) | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at Barn Farm Wix Road Bradfield Manningtree Essex CO11 2SP | Essex | Eastern | England |  | 615682 | 231393 | Tendring District Council | 13/00958/FUL | [5 empty] | 2013-08-30 | 2013-11-29
IF1168 | 1453 | 2013-06-14 | Low Carbon Solar | Park Farm | Solar Photovoltaics |  |  | 4.01 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Iwerne Minster, Blandford Forum | Dorset | South West | England | DT11 8TP | 385726 | 113717 | North Dorset District Council | 2/2011/0304/PLNG | [5 empty] | 2011-03-22 | [6 empty] | 2011-05-04 |  |  |  |  | 2011-08-01 | 2013-03-02
C1965 | 1454 | 2015-05-28 | Lumicity | Dunkeswell Airfield | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent Flightway Business Park Dunkeswell Airfield | Devon | South West | England | EX14 4LJ | 313746 | 107938 | East Devon District Council | 13/1954/MFUL | [5 empty] | 2013-08-30 | [6 empty] | 2014-03-11 |  |  |  |  | 2015-01-01 | 2015-03-11
C1144 | 1455 | 2013-07-15 | Lumicity | Tintinhull Forts Solar Park | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land Adjacent A303 Tintinhull Forts Tintinhull Forts Tintinhull Yeovil Somerset BA22 8PA | Somerset | South West | England |  | 349284 | 122400 | South Somerset District Council | 13/01409/FUL | [5 empty] | 2013-04-11 | 2013-06-25
C1719 | 1456 | 2013-11-19 | Lumicity | Tintinhull Forts Solar Park - resubmission | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Adjacent A303 Tintinhull Forts Tintinhull Forts Tintinhull Yeovil Somerset BA22 8PA | Somerset | South West | England |  | 349284 | 122400 | South Somerset District Council | 13/02925/FUL | [5 empty] | 2013-07-18 |  | 2013-10-01
C1786 | 1457 | 2013-12-23 | Lumicity | East Hill Strips | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land At East Hill Strips Ridgeway Sidbury | Devon | South West | England |  | 311687 | 93382 | East Devon District Council | 13/1817/MFUL | [5 empty] | 2013-08-12 |  | 2013-12-12
C2380 | 1460 | 2014-04-01 | Push Energy | Holland Road | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land adjacent to Electricity Substation Holland Road Little Clacton Essex CO16 9QG | Essex | Eastern | England |  | 619809 | 217902 | Tendring District Council | 13/01292/FUL | [5 empty] | 2013-11-13 |  | 2014-02-12
C1668 | 1461 | 2013-11-19 | Push Energy | Sladburys Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Sladburys Farm Sladburys Lane Clacton On Sea Essex CO15 4SS | Essex | Eastern | England |  | 619809 | 217902 | Tendring District Council | 13/00775/FUL | [5 empty] | 2013-08-09 | 2013-09-23
C2324 | 1462 | 2014-02-24 | Push Energy | Butlers Farm | Solar Photovoltaics |  |  | 9.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Butlers Farm Butlers Lane Saffron Walden Essex CB10 2ND | Essex | Eastern | England |  | 556052 | 240692 | Uttlesford District Council | UTT/13/2889/FUL | [5 empty] | 2013-11-01 |  | 2014-01-30
C2403 | 1463 | 2015-03-17 | NextEnergy Solar Fund | Langenhoe Solar Farm | Solar Photovoltaics |  |  | 21.25 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Langenhoe Hall, Langenhoe, Colchester | Essex | Eastern | England |  | 602531 | 216912 | Colchester Borough Council | 132330 | [5 empty] | 2013-11-22 | [6 empty] | 2014-08-29 |  |  |  |  | 2014-09-08 | 2015-03-04
C1735 | 1464 | 2017-04-18 | Push Energy/ NextEnergy Solar Fund (NESF) | Kentishes Solar Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Kentishes Farm, Kentish Farm Road, Stisted, Braintree | Essex | Eastern | England | CM77 8BX | 579119 | 226235 | Braintree District Council | 14/00922/FUL | APP/Z1510/W/15/3130930 |  |  |  |  | 2014-11-05 |  | 2015-02-04 | 2015-09-23 |  |  | 2016-04-08 | 2016-04-08 |  |  |  |  | 2017-01-04 | 2016-12-13
AA752 | 1467 | 2013-04-08 | TGC Renewables | Marley Thatch Solar Farm | Solar Photovoltaics |  |  | 6.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Marley Thatch Farm, South Brent | Devon | South West | England | TQ10 9LW | 271573 | 59890 | South Hams District Council | 39_45/0706/12/F | N/A |  |  |  |  | 2012-03-29 | [6 empty] | 2012-06-28 |  |  |  |  | 2013-01-28 | 2013-03-31
AA984 | 1468 | 2013-04-12 | TGC Renewables | Newlands Farm (East Devon) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Crewkerne Road Axminster | Devon | South West | England | EX13 5SF | 333040 | 97434 | East Devon District Council | 12/1575/MFUL | [5 empty] | 2012-07-26 | [6 empty] | 2012-11-22 |  |  |  |  | 2013-01-18 | 2013-03-20
C0212 | 1469 | 2012-09-14 | TGC Renewables | Tengore Lane SOLAR DEVELOPMENT | Solar Photovoltaics |  |  | 5.82 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | N/O Tengore Lane, Long Sutton, Langport, Somerset, TA10 9JL | Somerset | South West | England |  | 344750 | 127350 | South Somerset District Council | 12/01902/FUL | [5 empty] | 2012-05-21 |  | 2012-08-20
IF1215 | 1470 | 2013-04-04 | TGC Renewables | Wilmington Farm | Solar Photovoltaics |  |  | 7.55 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Chelwood Road, Marksbury, Bath | Somerset | South West | England |  | 365134 | 161664 | Bath and North East Somerset Council | 12/04345/FUL | [5 empty] | 2012-10-17 |  | 2013-02-14
AA438 | 1472 | 2011-08-09 | Vogt Solar | Croydon Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at Valley Farm, South Of Lower Road, Croydon, Cambridgeshire | Cambridgeshire | Eastern | England |  | 532019 | 248464 | South Cambridgeshire District Council | S/0319/11 | [5 empty] | 2011-02-23 | 2011-06-21
C1282 | 1473 | 2014-06-02 | Aldi | Goldthorpe | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Land adjacent to Goldthorpe Industrial Estate, Commercial Road, Goldthorpe, Rotherham | South Yorkshire | Yorkshire and Humber | England |  | 445406 | 403864 | Barnsley Council | 2013/0515 | [5 empty] | 2013-05-14 | [6 empty] | 2013-07-02 | [5 empty] | 2014-05-21
C2492 | 1474 | 2015-05-14 | Lightsource Renewable Energy | Barley Wood Farm Lane (Gaston Lane - resubmission) | Solar Photovoltaics |  |  | 5.43 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South of, Gaston Lane, Farringdon, Alton | Hampshire | South East | England | GU34 3EE | 471623 | 135539 | East Hampshire District Council | 54507/002 | [5 empty] | 2013-12-09 | [6 empty] | 2014-03-31 |  |  |  |  | 2015-01-01 | 2015-03-20
C1297 | 1476 | 2014-05-20 | Battens Farm Solar Park Ltd | Battens Farm Solar Park | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Battens Farm, Allington, Chippenham, Wiltshire | Wiltshire | South West | England | SN14 6LT | 388642 | 175907 | Wiltshire Council | 13/01311/FUL | [5 empty] | 2013-05-10 | [6 empty] | 2013-08-08 | [5 empty] | 2014-03-15
C2859 | 1478 | 2015-09-02 | INRG Solar | Combermere Abbey | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the North East of Combermere Abbey, Combermbere Park Drive, Dodcott Cum Wilkesley, Whitchurch | Cheshire | North West | England | SY13 4AJ | 360082 | 344837 | Cheshire East Council | 14/2247N | [5 empty] | 2014-05-22 | [6 empty] | 2014-12-01 |  |  |  | 2017-12-01 | 2015-01-01 | 2015-03-29
C1900 | 1480 | 2014-01-09 | UK Sustainable Energy | Foxburrow Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Foxburrow Farm Waldringfield Road Brightwell Suffolk | Suffolk | Eastern | England |  | 625330 | 243797 | Waveney District Council | DC/13/2252/FUL | [5 empty] | 2013-08-22 | [6 empty] | 2013-11-27 |  |  |  |  | 2014-07-01 | 2014-10-31
C1589 | 1484 | 2018-07-30 | Sunsave 49 SPV (prev. Cherry Solar) | Great Houndbeare Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The Southwest & West Of Great Houndbeare Farm Aylesbeare Exeter | Devon | South West | England | EX5 2DB | 304736 | 93429 | East Devon District Council | 13/1390/MFUL | [5 empty] | 2013-07-05 | [6 empty] | 2013-11-18 |  |  |  |  | 2017-01-31 | 2017-03-31
C1983 | 1485 | 2015-04-20 | NextEnergy Solar Fund | Condover (Green Farm) | Solar Photovoltaics |  |  | 10.2 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land east of Cound Brook, Gree, Green Farm, Condover, Shrewsbury, Shropshire, SY5 7DA | Shropshire | West Midlands | England | SY5 7DA | 350731 | 306821 | Shropshire Council | 13/03519/FUL | [5 empty] | 2013-09-03 | [6 empty] | 2014-01-09 |  |  |  |  | 2014-11-01 | 2015-03-24
C2850 | 1487 | 2016-03-03 | Green Switch Solutions | Howgrove Farm | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Parcel 2900, Greenhouse Lane, Nempnett Thrubwell, Bristol | Somerset | South West | England | BS40 7UY | 352112 | 161937 | Bath and North East Somerset Council | 14/03990/FUL | APP/F0114/W/15/3103260 |  |  |  |  | 2014-09-22 |  | 2015-06-11 | 2015-08-12 |  | 2016-02-11
C2552 | 1488 | 2016-02-05 | Huddlestone Farm Solar Park | Huddlestone Farm | Solar Photovoltaics |  |  | 16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Huddlestone Farm, Horsham Road, Steyning | West Sussex | South East | England |  | 518076 | 113586 | Horsham District Council | DC/13/2420 | APP/Z3825/W/14/2218035 |  |  |  |  | 2014-01-07 |  | 2014-04-16 | 2014-05-15 |  | 2016-01-26
C2051 | 1489 | 2014-11-27 | Bee Green Solar | Hurst Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hurst Farm, Cross Hands, Lydney, Gloucestershire | Gloucestershire | South West | England | GL15 4LH | 365050 | 203446 | Forest of Dean District Council | P1358/13/FUL | [5 empty] | 2013-09-09 | [6 empty] | 2013-11-15 |  |  |  |  | 2014-01-06 | 2014-05-19
C2733 | 1490 | 2016-07-27 | IKEA Properties Investments Ltd | Ikea Distribution Centre - resubmission | Solar Photovoltaics |  |  | 1.746 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Ikea Distribution Centre Yorkshire Way Armthorpe Doncaster DN3 3FB | South Yorkshire | Yorkshire and Humber | England |  | 464288 | 405319 | Doncaster Metropolitan Borough Council | 14/00366/FUL | [5 empty] | 2014-02-17 | [6 empty] | 2014-04-08 |  |  |  |  | 2014-11-10 | 2015-12-23
C2777 | 1491 | 2014-12-08 | Jaguar Land Rover | Jaguar Land Rover | Solar Photovoltaics |  |  | 5.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Jaguar Land Rover, Unit B, Innovation Drive, Pendeford, Wolverhampton | Staffordshire | West Midlands | England | WV9 5GA | 390582 | 303976 | South Staffordshire Council | 14/00395/FUL | [5 empty] | 2014-05-15 | [6 empty] | 2014-08-15 |  |  |  | 2017-08-15 |  | 2014-03-31
C1845 | 1494 | 2014-05-28 | Hazel Capital LLP | Leverton Ings | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Leverton Ings, Leverton, Boston, Lincolnshire | Lincolnshire | East Midlands | England |  | 538495 | 348945 | Boston Borough Council | B/13/0306 | [5 empty] | 2013-08-14 | [6 empty] | 2013-10-15 |  |  |  |  | 2014-01-03 | 2014-03-28
C1422 | 1497 | 2014-10-29 | Lightsource Renewable Energy | Little Morton Solar Farm | Solar Photovoltaics |  |  | 14.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Coal Board Area N 7 35 South Of Mansfield Road Morton Nottinghamshire | Nottinghamshire | East Midlands | England |  | 467187 | 379023 | Bassetlaw District Council | 13/01113/FUL | [5 empty] | 2013-09-23 | [6 empty] | 2014-01-09 | [5 empty] | 2014-03-31
C1931 | 1498 | 2014-05-20 | Lightsource Renewable Energy | Lodge Farm - Orston | Solar Photovoltaics |  |  | 12.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lodge Farm Longhedge Lane Orston Nottinghamshire | Nottinghamshire | East Midlands | England |  | 478519 | 341598 | Rushcliffe Borough Council | 13/01609/FUL | [5 empty] | 2013-08-16 | [6 empty] | 2013-11-15 | [5 empty] | 2014-03-28
C2575 | 1500 | 2015-03-25 | Lowther Farms | Lowther Farms | Solar Photovoltaics |  |  | 1.782 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off West Haddon Road, Guilsborough, Northamptonshire | Northamptonshire | East Midlands | England |  | 466544 | 273985 | Daventry District Council | DA/2014/0016 | [5 empty] | 2014-01-07 | [6 empty] | 2014-04-15 |  |  |  |  | 2014-06-13 | 2014-07-28
B1258 | 1501 | 2015-09-29 | Mackies Of Scotland Ltd | Mackies Dairy PV | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the North East of Mackies of Scotland Dairy, Hill of Easterton, Rothienorman, Inverurie | Grampian | Scotland | Scotland | AB51 8US | 376700 | 832011 | Aberdeenshire Council | APP/2014/0251 | [5 empty] | 2014-02-11 | [6 empty] | 2014-05-12 |  |  |  |  | 2015-07-28 | 2015-09-28
C1702 | 1502 | 2015-03-05 | Octopus Imvetments | Mingay Farm - extension | Solar Photovoltaics |  |  | 19.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Solar Farm, S/O Mingay Farm, Twentypence Road, Wilburton, Ely | Cambridgeshire | Eastern | England | CB6 | 547073 | 272967 | East Cambridgeshire District Council | 13/00499/ESF | [5 empty] | 2013-07-11 | [6 empty] | 2013-10-30 | [5 empty] | 2014-03-31
C2963 | 1503 | 2015-05-18 | PS Renewables | Redcourt Farm | Solar Photovoltaics |  |  | 3.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Redcourt Farm, Llysonnen Road, Carmarthen, Dyfed | Dyfed | Wales | Wales | SA33 5DR | 237904 | 219365 | Carmarthenshire County Council | W/30060 | [5 empty] | 2014-05-01 | [6 empty] | 2014-10-07 |  |  |  | 2019-10-07 | 2015-01-15 | 2015-03-30
C2625 | 1505 | 2014-06-02 | Sustainable Charlbury | Southill Solar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land south of B4022 between Charlbury and Fawler | Oxfordshire | South East | England |  | 436294 | 217901 | West Oxfordshire District Council | 14/0217/P/FP | [5 empty] | 2014-02-14 |  | 2014-05-07
C2979 | 1506 | 2018-09-27 | Gamma Solar Limited | Sowerby Lodge Farm | Solar Photovoltaics |  |  | 4.99 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Sowerby Lodge Farm, Bank Lane, Barrow-in-Furness | Cumbria | North West | England | LA14 4QY | 319090 | 472162 | Barrow in Furness Borough Council | B03/2014/0643 | [5 empty] | 2014-10-07 | [6 empty] | 2015-02-13 |  |  |  | 2018-02-13 | 2018-05-30 | 2018-06-30
C2096 | 1507 | 2014-06-02 | Solar Century | Stone Hill | Solar Photovoltaics |  |  | 2.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND AT STONE HILL, CHIDDINGLY ROAD, HORAM | East Sussex | South East | England | TN21 0JN | 556616 | 115760 | Wealden District Council | WD/2013/2164/MAJ | [5 empty] | 2013-10-28 | [6 empty] | 2014-01-24 | [5 empty] | 2014-03-31
C2607 | 1509 | 2017-02-02 | Green Hedge (BayWa r.e.) | Taunton Racecourse | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Taunton Racecourse, Orchard Portman, Taunton, Somerset | Somerset | South West | England | TA3 | 323785 | 122205 | Taunton Deane Borough Council | 30/13/0053 | [5 empty] | 2014-01-09 | [6 empty] | 2014-04-07 |  |  |  |  | 2014-06-01 | 2015-03-15
C2623 | 1510 | 2014-12-16 | Anesco | The Stables | Solar Photovoltaics |  |  | 1.797 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | The Stables, Pine Close, Stoke Golding, Nuneaton, Leicestershire | Leicestershire | East Midlands | England | CV13 6EB | 440294 | 297805 | Hinckley and Bosworth Borough Council | 12/00873/FUL | APP/K2420/A/13/2198127 |  |  |  |  | 2012-10-29 |  | 2013-04-02 | 2013-06-03 |  |  | 2014-04-14 | 2014-04-14 | [5 empty] | 2014-08-22
C2851 | 1512 | 2016-11-01 | Solar Power Parks | Tyn y Pant | Solar Photovoltaics |  |  | 1.62 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Tyn Y Pant Farm, Caehopkin, Abercrave, Swansea | Powys | Wales | Wales | SA9 1UE | 282906 | 212243 | Powys County Council | P/2015/1013 | [5 empty] | 2015-12-03 |  | 2016-10-18
B1314 | 1513 | 2016-03-14 | Bee Green Solar | Vantage Point | Solar Photovoltaics |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Building 1, Vantage Point Business Village Mitcheldean Glos | Gloucestershire | South West | England | GL17 0DD | 366679 | 218887 | Forest of Dean District Council | P0825/11/FUL | [5 empty] | 2011-05-03 | [6 empty] | 2011-06-15 |  |  |  |  | 2011-07-15 | 2011-09-29
C2849 | 1515 | 2016-07-28 | Canadian solar | Wilsom Farm | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cakers Lane, East Worldham, Alton, Hampshire | Hampshire | South East | England | GU34 3AB | 473543 | 138648 | East Hampshire District Council | 55465/001 | [5 empty] | 2015-01-20 | [6 empty] | 2015-11-02 |  |  |  | 2018-11-02 | 2015-12-21 | 2016-03-31
C1632 | 1516 | 2015-05-14 | Lightsource Renewable Energy | Woodlands Farm Solar Park | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Woodlands Farm, Calcott Hill, Sturry | Kent | South East | England | CT3 4NB | 617755 | 163087 | Canterbury City Council | CA//14/00169 | [5 empty] | 2014-02-18 | [6 empty] | 2014-05-07 |  |  |  |  | 2014-11-24 | 2015-03-30
C2899 | 1517 | 2015-10-05 | Green Switch Developments | Bollands Hill | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a |  | Appeal Refused | Application Refused | Land to the east of Bollands Hill and North of The Kennet and Avon Canal, Seend | Wiltshire | South West | England |  | 393461 | 161735 | Wiltshire Council | 14/03736/FUL | APP/Y3940/W/15/3005078 |  |  |  |  | 2014-04-04 |  | 2014-09-09 | 2015-04-27 |  | 2015-09-04
C2858 | 1518 | 2015-10-05 | KWTN Solar | Bowerhouse Farm | Solar Photovoltaics |  |  | 8.28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Bowerhouse East of Riverside Banwell | Avon | South West | England | BS29 6EL | 340122 | 161010 | North Somerset Council | 14/P/1666/F | [5 empty] | 2014-07-31 | [6 empty] | 2014-10-30 |  |  |  | 2017-10-30 | 2015-01-01 | 2015-03-29
C2343 | 1519 | 2014-11-27 | Sun Glow Power | Brickyard Barn (resubmission) | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Brickyard Barn, Mallory Road, Bishops Tachbrook, Leamington Spa | Warwickshire | West Midlands | England | CV33 9QD | 430420 | 261470 | Warwick District Council | W/13/1608 | [5 empty] | 2013-11-15 | [6 empty] | 2013-12-20 |  |  |  |  | 2014-10-01 | 2014-11-27
C2920 | 1520 | 2016-01-05 | Wrexham County Borough Council | Bronwylfa Reservoir | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | E/o Bronwylfa Reservoir, Aberoer Road, Aberoer, Wrexham, Clwyd, LL14 4LG | Clwyd | Wales | Wales |  | 329049 | 348801 | Wrexham County Borough Council | P/2014/0263 | [5 empty] | 2014-04-11 | [6 empty] | 2014-07-18 |  |  |  | 2019-07-18 | 2015-01-01 | 2015-06-15
C2922 | 1521 | 2015-12-18 | Sybac Solar International GmbH | Land At Court Farm | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Court Farm, Treoes, Bridgend, Mid Glamorgan | Vale of Glamorgan | Wales | Wales | CF35 5DD | 294767 | 178755 | Vale of Glamorgan Council | 2015/00026/FUL | [5 empty] | 2015-01-21 | [6 empty] | 2015-06-05 |  |  |  | 2020-06-05 | 2015-11-15 | 2016-03-16
B0736 | 1522 | 2014-05-20 | Lightsource Renewable Energy | Crapnell Farm Solar Farm | Solar Photovoltaics |  |  | 5.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Crapnell, Wells | Somerset | South West | England | BA5 3HQ | 359691 | 145698 | Mendip District Council | 2013/1243 | [5 empty] | 2013-07-03 | [6 empty] | 2013-09-13 | [5 empty] | 2014-03-28
C2861 | 1523 | 2016-04-28 | Lightsource Renewable Energy | Crookedstone Road | Solar Photovoltaics |  |  | 4.83 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West of no 24 Crookedstone Road Aldergrove | Co. Antrim | Northern Ireland | Northern Ireland |  | 129401 | 538723 | Northern Ireland Planning Service | T/2014/0098/F | [5 empty] | 2014-03-24 | [6 empty] | 2014-09-08 |  |  |  | 2019-09-08 | 2016-02-18 | 2016-05-31
B1330 | 1525 | 2017-02-01 | Freewatt Renewable Energy | Danes Farm - extension | Solar Photovoltaics |  |  | 10.47 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stow Park Road, Stow, Lincoln | Lincolnshire | East Midlands | England | LN1 2AJ | 486859 | 381401 | West Lindsey District Council | 131968 | [5 empty] | 2014-10-23 | [6 empty] | 2014-12-04 |  |  |  |  | 2015-11-11 | 2016-03-11
IF1360 | 1527 | 2015-03-17 | Next Energy Solar Fund Ltd | Ellough Airfield (Resubmission) | Solar Photovoltaics |  |  | 13.23 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Ellough Airfield, Benacre Road, Ellough, Beccles, Suffolk | Suffolk | Eastern | England | NR34 7UH | 645184 | 287900 | Waveney District Council | DC/13/0239/FUL | [5 empty] | 2013-03-04 | [6 empty] | 2013-04-18 |  |  |  |  | 2014-01-01 | 2014-03-31
C1244 | 1528 | 2015-03-05 | Octopus Investments | Ermine Street Farm solar park | Solar Photovoltaics |  |  | 32.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Ermine Street Farm Ermine Street Ancaster Heath Grantham Lincolnshire | Lincolnshire | East Midlands | England | NG32 3RN | 499291 | 347452 | North Kesteven District Council | 13/0929/FUL | [5 empty] | 2013-08-20 | [6 empty] | 2013-12-06 | [5 empty] | 2014-07-29
C1988 | 1529 | 2014-12-01 | Belltown Power | Eynsham Solar Farm | Solar Photovoltaics |  |  | 13.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Salutation Farm Barnard Gate | Oxfordshire | South East | England |  | 439658 | 210754 | West Oxfordshire District Council | 13/1277/P/FP | [5 empty] | 2013-09-12 | [6 empty] | 2013-12-04 | [5 empty] | 2014-03-31
C2784 | 1530 | 2014-06-02 | Green Energy UK Direct | Farthinghoe Solar Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land to the east of Cockley Road Farthinghoe | Northamptonshire | East Midlands | England |  | 454388 | 239937 | South Northamptonshire Council | S/2014/0282/MAF | [5 empty] | 2014-02-25 | 2014-05-07
C2452 | 1531 | 2016-04-01 | Conergy | Ford Farm (Ashurst) | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Sopers Copse Honeybridge Lane Ashurst West Sussex | West Sussex | South East | England |  | 517966 | 117273 | Horsham District Council | DC/13/2310 | APP/Z3825/W/14/2222037 |  |  |  |  | 2013-12-09 |  | 2014-05-02 | 2014-07-30 |  |  | 2015-09-09 | 2015-09-09 |  |  |  |  | 2015-11-15 | 2016-02-29
C2503 | 1536 | 2017-01-23 | Gamma Solar Limited | Priors Byne Farm | Solar Photovoltaics |  |  | 7.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Priors Byne Farm Bines Road Partridge Green Horsham West Sussex | West Sussex | South East | England | RH13 8EQ | 516559 | 117631 | Horsham District Council | DC/13/2381 | APP/Z3825/A/14/2219843 |  |  |  |  | 2013-12-18 |  | 2014-04-16 | 2014-06-15 |  |  | 2015-04-15 | 2015-04-15 |  |  |  | 2018-04-15 | 2015-08-01 | 2016-01-20
B1326 | 1537 | 2017-04-04 | Greencoat Capital | Scottow Moor - RAF Coltishall Solar Farm (Phase 1) | Solar Photovoltaics |  |  | 32 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Former RAF Coltishall, Coltishall Airfield, Filby Road, Norwich, Norfolk | Norfolk | Eastern | England |  | 626626 | 322780 | North Norfolk District Council | PF/14/1334 | [5 empty] | 2014-10-09 | [6 empty] | 2014-12-23 |  |  |  |  | 2015-01-15 | 2015-03-31
AA833 | 1538 | 2014-03-24 | Anesco | Owls Lodge Farm Extension | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nuns Walk Longparish Hampshire | Hampshire | South East | England |  | 444310 | 143340 | Test Valley Borough Council | 12/01186/FULLN | [5 empty] | 2012-07-09 | [6 empty] | 2012-09-05 | [5 empty] | 2013-12-31
A0450 | 1539 | 2017-05-26 | Lightsource Renewable Energy | Hexworthy Solar Park | Solar Photovoltaics |  |  | 5.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Hexworthy Barton, Lawhitton, Launceston, Cornwall | Cornwall | South West | England |  | 235727 | 80988 | Cornwall Council | PA13/03036 | [5 empty] | 2013-04-10 | [6 empty] | 2013-07-08
A0451 | 1540 | 2020-03-31 | Moser Baer | Hawksland Solar | Solar Photovoltaics |  |  | 3.1 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Whitecross, Wadebridge, Cornwall | Cornwall | South West | England |  | 195027 | 70983 | Cornwall Council | PA10/08667 | [5 empty] | 2010-12-29 | [6 empty] | 2011-05-24 |  |  |  |  | 2013-01-25 | 2013-03-28
A0452 | 1541 | 2017-02-02 | Innogy (previously BELECTRIC Solar) | Middle Treworder Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of Wadebridge, Cornwall | Cornwall | South West | England |  | 198444 | 70952 | Cornwall Council | PA11/00777 | [5 empty] | 2011-02-04 | [6 empty] | 2011-05-06 | [5 empty] | 2013-03-30
A0496 | 1542 | 2014-11-28 | Lark Energy | Black Bush Farm | Solar Photovoltaics |  |  | 2.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Reach Drove, at Black Bush Farm, Whittlesey, Cambridgeshire | Cambridgeshire | Eastern | England |  | 525681 | 296267 | Fenland District Council | F/YR11/0256/F | [5 empty] | 2011-03-04 | [6 empty] | 2012-03-16 |  |  |  |  | 2014-05-01 | 2014-07-01
A0508 | 1543 | 2014-05-23 | Wardell Armstrong International Ltd | Goonhilly Downs - PV | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Bonython Estate Cury Cross Lanes Helston Cornwall | Cornwall | South West | England | TR12 7BA | 169711 | 21226 | Cornwall Council | PA11/00559 | [5 empty] | 2011-01-27 | [6 empty] | 2011-05-24 |  |  |  |  | 2013-11-01 | 2014-03-19
A0510 | 1544 | 2017-07-03 | John Laing Environmental Assets | Higher Tregarne Solar Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.6 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Higher Tregarne Mawnan Smith Falmouth Cornwall | Cornwall | South West | England | TR11 5JW | 175993 | 29329 | Cornwall Council | PA11/00674 | [5 empty] | 2011-01-17 | [6 empty] | 2011-04-18 | [5 empty] | 2013-04-07
A0511 | 1545 | 2013-06-12 | China Sunergy | Causilgey Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Causilgey Barton Tregavethan Truro Cornwall | Cornwall | South West | England | TR4 9EP | 177775 | 47586 | Cornwall Council | PA10/07837 | [5 empty] | 2010-11-29 | [6 empty] | 2011-04-21 | [5 empty] | 2013-03-31
A0513 | 1546 | 2013-04-25 | The Green Company | Ninnis Farm Solar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ninnis Farm Sticker St Austell Cornwall | Cornwall | South West | England | PL26 7EJ | 198252 | 50490 | Cornwall Council | PA11/01432 | [5 empty] | 2011-02-25 | [6 empty] | 2011-06-03 | [5 empty] | 2013-03-30
A0515 | 1547 | 2013-02-12 | Low carbon Solar Partners | Trelow Farm | Solar Photovoltaics |  |  | 1.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Crealy Adventure Park St Issey Wadebridge Cornwall | Cornwall | South West | England |  | 192281 | 69666 | Cornwall Council | PA11/01577 | [5 empty] | 2011-03-02 | [6 empty] | 2011-07-05 | [5 empty] | 2012-03-01
A0519 | 1548 | 2013-07-03 | Lightsource Renewable Energy | Hewas Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Hewas Farm Ladock Truro Cornwall | Cornwall | South West | England | TR2 4EP | 191590 | 53161 | Cornwall Council | PA10/08675 | [5 empty] | 2011-03-02 | [6 empty] | 2011-03-31 | [5 empty] | 2013-05-07
A0534 | 1549 | 2013-02-22 | The Green Company | Great Knowle Farm Solar | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Great Knowle Farm, Derriton Road, Pyworthy, Holsworthy, Devon | Devon | South West | England | EX22 6JY | 232612 | 103213 | Torridge District Council | 1/0218/2011/FULM | [5 empty] | 2011-04-04 | [6 empty] | 2011-06-23 |  |  |  |  | 2012-04-10 | 2012-07-27
AA207 | 1550 | 2013-03-25 | P V Farms 01 | Airfield Farm PV | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chalk Lane, Norwich, Norfolk | Norfolk | Eastern | England | NR16 2JZ | 600459 | 290384 | Breckland Council | 3PL/2010/1211/F | [5 empty] | 2010-11-22 | [6 empty] | 2011-01-27 | [5 empty] | 2012-03-29
AA209 | 1551 | 2012-08-08 | Wardell Armstrong International Ltd | Lower Bodiniel Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bodiniel Road Bodmin Cornwall | Cornwall | South West | England | PL31 2PF | 205819 | 68052 | Cornwall Council | PA11/01747 | [5 empty] | 2011-03-10 | [6 empty] | 2011-06-07 | [5 empty] | 2012-03-15
AA230 | 1552 | 2014-02-20 | Anesco | Shelswell Park Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fringford, Oxfordshire | Oxfordshire | South East | England |  | 460822 | 230982 | Cherwell District Council | 11/00177/F | [5 empty] | 2011-02-07 | [6 empty] | 2011-05-20 | [5 empty] | 2013-03-22
AA231 | 1553 | 2012-10-23 | Abbey Renewables | Chittering Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Radical Farm, Chittering Drove, Chittering, Cambridgeshire | Cambridgeshire | Eastern | England |  | 551488 | 271214 | South Cambridgeshire District Council | S/2198/10 | [5 empty] | 2010-12-15 | [6 empty] | 2011-03-15 | [5 empty] | 2012-06-28
AA238 | 1554 | 2018-09-03 | Cornwall Council Property Services | Kernow Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Trebarber, St. Mawgan Nr Newquay | Cornwall | South West | England |  | 186644 | 63197 | Cornwall Council | PA11/00498 | [5 empty] | 2011-01-27 | [6 empty] | 2011-04-18 |  |  |  |  | 2012-09-06 | 2012-11-30
AA262 | 1555 | 2013-04-08 | Lark Energy | Limes Farm Solar Farm | Solar Photovoltaics |  |  | 4.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Limes Farm, Bourne | Lincolnshire | East Midlands | England |  | 513524 | 320915 | South Kesteven District Council | S11/0431 | [5 empty] | 2011-02-25 | [6 empty] | 2011-04-27 | [5 empty] | 2013-03-28
AA271 | 1556 | 2012-07-26 | Private Developer | Kencot Hill Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land to the North of Kencot Road, Kencot | Oxfordshire | South East | England |  | 424785 | 207101 | West Oxfordshire District Council | 11/0412/P/FP | [5 empty] | 2011-03-17 | [6 empty] | 2011-06-27
AA272 | 1557 | 2013-04-12 | Wessex Solar Energy | Bratton Fleming Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent to four cross way, Bratton Fleming | Devon | South West | England |  | 265395 | 137979 | North Devon District Council | 51698 | [5 empty] | 2011-02-01 | [6 empty] | 2012-04-17 |  |  |  |  | 2012-12-03 | 2013-03-21
AA283 | 1558 | 2014-01-23 | Vogt Solar | Lee Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Main Road, Wellow, Yarmouth, Isle Of Wight | Isle of Wight | South East | England |  | 439007 | 88241 | Isle of Wight Council | P/00168/11 | [5 empty] | 2011-02-07 | [6 empty] | 2011-04-14 | [5 empty] | 2012-07-31
AA290 | 1560 | 2015-09-29 | Laurence Associates | Woodlands Barton Solar Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Victorie, Roche, St Austell, Cornwall | Cornwall | South West | England |  | 200842 | 61987 | Cornwall Council | PA10/07307 | [5 empty] | 2010-11-11 | [6 empty] | 2011-02-04 |  |  |  |  | 2012-10-01 | 2013-03-13
AA291 | 1561 | 2015-11-24 | Primrose Solar | Winsdon Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Winsdon Farm, North Petherwin, Launceston, Cornwall | Cornwall | South West | England | PL15 8NW | 227112 | 91567 | Cornwall Council | PA10/06811 | [5 empty] | 2010-10-26 | [6 empty] | 2011-01-28 |  |  |  | 2014-01-28 | 2013-02-21 | 2014-01-28
AA293 | 1562 | 2014-02-20 | The Manor of Cadland Estate | The Manor of Cadland Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Whitefield Farm, Langley | Hampshire | South East | England |  | 445171 | 100816 | New Forest National Park Authority | 11/96086 | [5 empty] | 2011-01-21 | [6 empty] | 2011-05-17 |  |  |  |  | 2012-05-22 | 2012-07-23
AA297 | 1563 | 2013-02-12 | Low Carbon Solar | Trenouth Farm | Solar Photovoltaics |  |  | 3.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | St Ervan, Wadebridge, Cornwall | Cornwall | South West | England | PL27 7SG | 190018 | 70255 | Cornwall Council | PA11/00760 | [5 empty] | 2011-01-25 | [6 empty] | 2011-05-05 | [5 empty] | 2012-06-01
AA298 | 1564 | 2014-05-22 | Inazin (Low Carbon Solar) | Callington Solar Farm | Solar Photovoltaics |  |  | 6.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Haye Lane, Callington, Cornwall | Cornwall | South West | England |  | 235160 | 70069 | Cornwall Council | PA11/00774 | [5 empty] | 2011-02-07 | [6 empty] | 2011-09-26 | [5 empty] | 2014-01-17
AA303 | 1565 | 2017-04-21 | Low Carbon Solar UK (dissolved) | Fiddlers Green Solar Farm | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | St. Newlyn East, Newquay, Cornwall | Cornwall | South West | England |  | 182301 | 54328 | Cornwall Council | PA11/00380 | [5 empty] | 2011-01-21 | [6 empty] | 2011-04-08 |  |  |  | 2014-04-08
AA313 | 1566 | 2014-05-22 | Inazin Solar (previoulsy owned by Low Carbon Solar) | St Columb Major Solar Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Trekenning Farm, Trekenningm, Newquay, Cornwall | Cornwall | South West | England | TR8 4JA | 192127 | 62214 | Cornwall Council | PA11/00560 | [5 empty] | 2011-01-27 | [6 empty] | 2011-04-28 | [5 empty] | 2014-03-14
AA315 | 1567 | 2013-06-04 | NextEnery Solar Fund (NESF) | Crossways Pit Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Redbridge Road, Crossways, Dorchester, Dorset | Dorset | South West | England | DT2 8DX | 377194 | 88984 | West Dorset District Council | 1/D/11/000168 | [5 empty] | 2011-02-24 | [6 empty] | 2011-08-23 | [5 empty] | 2013-03-28
AA320 | 1568 | 2014-12-22 | Western Solar | Rhondda Valley Solar Farm | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Adjacent to the Rhondda Golf Club, Trealaw | Mid Glamorgan | Wales | Wales |  | 300002 | 193239 | Rhondda Cynon Taff County Borough Council | 11/0098/10 | [5 empty] | 2011-03-03 | 2014-12-11
AA325 | 1569 | 2013-06-14 | AEE Renewables | Ayshford Court Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Westleigh, Tiverton, Devon | Devon | South West | England |  | 305519 | 115583 | Mid Devon District Council | 10/01930/MFUL | [5 empty] | 2010-12-24 | [6 empty] | 2011-06-03 | [5 empty] | 2013-03-28
AA326 | 1570 | 2013-11-18 | The Clark Trustees | Andover Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Andover Business Park, Monxton Road, Andover, Hampshire | Hampshire | South East | England |  | 432479 | 145878 | Test Valley Borough Council | 11/00529/FULLN | [5 empty] | 2011-03-01 | [6 empty] | 2011-09-29 | [5 empty] | 2013-03-22
AA327 | 1571 | 2012-12-06 | Vogt Solar | Oving Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Woodhorn Farm, Church Lane, nr.Oving, West Sussex | West Sussex | South East | England |  | 491253 | 104998 | Chichester District Council | 11/00738/FUL | [5 empty] | 2011-02-21 | [6 empty] | 2011-05-03 |  |  |  |  | 2012-05-04 | 2012-08-14
AA333 | 1572 | 2015-09-29 | Vogt Solar | Grange Farm (Cornwall) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Boyton, Launceston, Cornwall | Cornwall | South West | England |  | 229006 | 92956 | Cornwall Council | PA11/01592 | [5 empty] | 2011-03-04 | [6 empty] | 2011-05-24 | [5 empty] | 2013-02-28
AA338 | 1573 | 2013-04-15 | Low Carbon Solar | Shipton Bellinger - Park House Corner Solar Farm | Solar Photovoltaics |  |  | 5.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Salisbury Road, Shipton Bellinger, Hampshire | Hampshire | South East | England |  | 423437 | 143998 | Test Valley Borough Council | 11/00554/FULLN | [5 empty] | 2011-03-04 | [6 empty] | 2011-05-17 |  |  |  |  | 2012-12-03 | 2013-02-21
AA360 | 1574 | 2018-07-26 | NextEnery Solar Fund (NESF) | Wyld Meadow Solar Farm | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Wyld Meadow Farm, Pound Lane, Monkton Wyld, Bridport | Dorset | South West | England | DT6 6DD | 334144 | 98155 | West Dorset District Council | 1/D/11/000453 | [5 empty] | 2011-04-13 | [6 empty] | 2011-07-13 | [5 empty] | 2012-04-01
AA365 | 1575 | 2014-04-03 | Anesco | Shooters Bottom Solar Park | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Townsend Lane, Chewton, Mendip | Somerset | South West | England | BA3 4LU | 359176 | 151234 | Mendip District Council | 2011/0529 | [5 empty] | 2011-03-23 | [6 empty] | 2011-07-28 | [5 empty] | 2014-02-05
AA366 | 1576 | 2013-06-10 | Cricket St Thomas Estate | Goldenhaye Field Solar Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cricket St Thomas, Chard, Somerset | Somerset | South West | England |  | 336362 | 108657 | South Somerset District Council | 11/01534/FUL | [5 empty] | 2011-04-18 | [6 empty] | 2011-08-09 | [5 empty] | 2013-04-15
AA367 | 1577 | 2016-09-23 | Heritage Energy | Clearwell Farm - solar | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pentre-poeth Road, Cardiff | Gwent | Wales | Wales |  | 324580 | 185321 | Newport City Council | 11/0339 | [5 empty] | 2011-04-07 | [6 empty] | 2011-05-20 |  |  |  |  | 2014-09-01 | 2015-12-15
AA377 | 1578 | 2014-06-02 | Freewatt Renewable Energy | Danes Farm | Solar Photovoltaics |  |  | 3.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stow Park Road, Stow, Lincoln | Lincolnshire | East Midlands | England | LN1 2AJ | 486859 | 381401 | West Lindsey District Council | 126864 | [5 empty] | 2011-01-28 | [6 empty] | 2011-04-26 | [5 empty] | 2011-07-31
AA378 | 1579 | 2015-12-17 | Evans Group | Marchington Solar Park | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Former Barracks, Land off Stubby Lane, Marchington, Staffordshire | Staffordshire | West Midlands | England | ST14 8LX | 413565 | 329410 | East Staffordshire Borough Council | P/2010/01499/JI | [5 empty] | 2011-01-06 | [6 empty] | 2013-08-02
AA380 | 1580 | 2013-06-14 | Private Developer | Langstone Court Road Solar Farm | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Langstone Court Road, Langstone, Newport, Gwent | Gwent | Wales | Wales |  | 336926 | 189507 | Newport City Council | 11/0311 | [5 empty] | 2011-03-25 | [6 empty] | 2011-11-09 | [5 empty] | 2013-01-11
AA415 | 1581 | 2012-12-06 | John Laing Environmental Assets | Five Oaks Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Haven Road Five Oaks West Sussex | West Sussex | South East | England |  | 509003 | 130058 | Horsham District Council | DC/11/0090 | [5 empty] | 2011-02-15 | [6 empty] | 2011-07-22 | [5 empty] | 2011-12-01
AA416 | 1582 | 2015-04-13 | Private Developer | Culworth House Solar Farm | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | East of Banbury Lane, Culworth Grounds Farm, Thorpe Manderville | Northamptonshire | East Midlands | England |  | 454564 | 245985 | South Northamptonshire Council | S/2011/0314/MAF | APP/Z2830/A/11/2155999 |  | Recovery |  |  | 2011-03-11 |  | 2011-06-10 | 2011-07-28 |  |  | 2013-03-04 | 2013-03-04 |  |  | 2013-03-04 | 2016-03-04 | 2014-09-01 | 2015-01-15
AA435 | 1583 | 2013-04-11 | Low Carbon Solar | Warleigh Barton Solar Farm | Solar Photovoltaics |  |  | 4.95 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Station Road, Tamerton Foliot | Devon | South West | England |  | 246569 | 61623 | South Hams District Council | 04/0770/11/F | [5 empty] | 2011-06-01 | [6 empty] | 2012-11-02 | [5 empty] | 2013-03-20
AA470 | 1584 | 2015-09-29 | Kronos Solar | Trenoweth Solar Farm | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Luxulyan Bodmin Cornwall | Cornwall | South West | England | PL30 5DP | 204725 | 58885 | Cornwall Council | PA10/07114 | [5 empty] | 2010-11-17 | [6 empty] | 2011-02-15 | [5 empty] | 2013-03-28
AA692 | 1585 | 2013-04-15 | Foresight Solar Fund | Wymeswold Airfield | Solar Photovoltaics |  |  | 34 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Former Wymeswold Airfield, Wymeswold, Loughborough | Leicestershire | East Midlands | England | LE12 5SN | 459993 | 323231 | Charnwood Borough Council | P/12/1781/2 | [5 empty] | 2012-09-04 | [6 empty] | 2012-11-09 |  |  |  |  | 2013-02-01 | 2013-03-28
AA702 | 1586 | 2013-07-14 | Hive Energy | Higher Hatherleigh Solar Farm | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Grove Lane, North Cheriton, Templecombe, Somerset, BA9 8AE | Somerset | South West | England |  | 370149 | 127237 | South Somerset District Council | 12/00884/FUL | [5 empty] | 2012-03-09 | [6 empty] | 2012-08-10 | [5 empty] | 2013-03-28
AA705 | 1587 | 2012-11-22 | Lightsource Renewable Energy | Barton Solar Farm | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Burlescombe, Tiverton, Devon | Devon | South West | England | EX16 7JW | 307778 | 117118 | Mid Devon District Council | 12/00412/MFUL | [5 empty] | 2012-03-16 | [6 empty] | 2012-05-25 |  |  |  |  | 2012-05-29 | 2012-07-27
AA728 | 1588 | 2015-05-14 | Lightsource Renewable Energy | Clann Solar Farm | Solar Photovoltaics |  |  | 1.41 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Clann Farm, Clan Lane, Lanivet, Bodmin, Cornwall | Cornwall | South West | England | PL30 5HD | 202869 | 63790 | Cornwall Council | PA12/02871 | APP/D0840/W/15/3002662 |  |  |  |  | 2012-03-23 |  |  | 2015-02-10 |  |  |  | 2012-10-05 |  |  |  |  | 2014-07-25 | 2014-11-04
AA751 | 1589 | 2014-01-06 |  | Dolmans Hill (Redbridge Farm) Solar Arrays | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lytchett Matravers, BH16 6HP. | Dorset | South West | England |  | 392823 | 94543 | Purbeck District Council | 6/2012/0228 | N/A |  |  |  |  | 2012-04-02 | [6 empty] | 2012-11-08 |  |  |  |  | 2013-09-15 | 2014-01-03
AA854 | 1590 | 2018-03-02 | NESF (formerly Lumicity) | North Norfolk Business Centre Solar Park | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Manor Farm, Crossdale Street, Northrepps, Cromer, NR27 9LD | Norfolk | Eastern | England |  | 622513 | 338865 | North Norfolk District Council | PF/12/0816 | [5 empty] | 2012-07-30 | [6 empty] | 2012-11-16 |  |  |  |  | 2013-08-30 | 2014-02-28
AA859 | 1591 | 2014-03-24 | Hazel Capital LLP | Horsacott Farm Solar Park | Solar Photovoltaics |  |  | 6.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LYDACOTT BARNSTAPLE DEVON | Devon | South West | England | EX31 2PD | 252330 | 131541 | North Devon District Council | 54349 | [5 empty] | 2012-07-30 | [6 empty] | 2012-11-30 | [5 empty] | 2013-03-29
AA864 | 1592 | 2014-04-30 | Lark Energy | Broxted Solar Farm (Stradishall Airfield) | Solar Photovoltaics |  |  | 31.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lancaster Way, Hundon | Suffolk | Eastern | England |  | 572387 | 251110 | St Edmundsbury Borough Council | SE/12/1114/FUL | [5 empty] | 2012-09-10 | [6 empty] | 2012-12-10 |  |  |  |  | 2013-09-12 | 2014-03-31
AA870 | 1593 | 2014-04-30 | Moser Baer | Pentylands Farm | Solar Photovoltaics |  |  | 19 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pentylands Lane, Highworth, Swindon, Wiltshire | Wiltshire | South West | England | SN6 7RB | 418743 | 194942 | Swindon Borough Council | S/12/1094 | [5 empty] | 2012-08-08 | [6 empty] | 2012-11-15 |  |  |  |  | 2013-09-30 | 2014-03-31
AA877 | 1594 | 2014-03-27 | MTS Trefinnick Solar Ltd | Trefinnick Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Trefinnick Road Bray Shop Callington | Cornwall | South West | England | PL17 8QD | 233642 | 74030 | Cornwall Council | PA12/07093 | [5 empty] | 2012-07-25 | [6 empty] | 2012-12-21 | [5 empty] | 2013-10-01
AA893 | 1595 | 2015-03-30 | TRIG | Four Burrows Solar farm | Solar Photovoltaics |  |  | 7.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Little Lambriggan Penhallow Truro Cornwall | Cornwall | South West | England | TR4 9NG | 176400 | 49603 | Cornwall Council | PA10/07942 | [5 empty] | 2010-12-02 | [6 empty] | 2011-03-03 |  |  |  |  | 2014-07-01 | 2015-01-12
AA901 | 1596 | 2014-04-03 | Lightsource Renewable Energy | Trew Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Tresmeer Launceston Cornwall | Cornwall | South West | England | PL15 8TB | 221747 | 87585 | Cornwall Council | PA12/02876 | [5 empty] | 2012-03-23 | [6 empty] | 2012-10-05
AA908 | 1597 | 2019-02-19 | Ms Power Projects Ltd | Clawddcam-Mathry Solar Farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Haverfordwest | Dyfed | Wales | Wales | SA62 5HY | 187717 | 228957 | Pembrokeshire County Council | 12/0162/PA | [5 empty] | 2012-05-31 | [6 empty] | 2013-12-16 |  |  |  | 2018-12-16
AA909 | 1598 | 2014-05-22 | Rudbaxton Solar Park Limited | Rudbaxton Solar Park | Solar Photovoltaics |  |  | 10.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Withyhedge Landfill Site, RUDBAXTON, Haverfordwest, SA62 4DB | Dyfed | Wales | Wales |  | 196753 | 220959 | Pembrokeshire County Council | 11/1056/PA | [5 empty] | 2012-02-02 | [6 empty] | 2012-07-27 | [5 empty] | 2014-03-08
AA920 | 1599 | 2014-01-20 | AEE Renewables | Hurlingpot Farm | Solar Photovoltaics |  |  | 5.28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Doulting | Somerset | South West | England | BA4 4PT | 364039 | 143602 | Mendip District Council | 2012/1562 | [5 empty] | 2012-08-13 |  | 2013-01-11 |  |  | 2013-12-19
AA926 | 1601 | 2014-05-22 | Hope Solar Park Ltd | Hope Solar Farm | Solar Photovoltaics |  |  | 7.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Seven Adjoining Fields Situated Off Gwithian Road Approximately 500M North Of The A30 | Cornwall | South West | England |  | 159932 | 39974 | Cornwall Council | PA12/00827 | [5 empty] | 2012-02-01 | [6 empty] | 2012-08-30 | [5 empty] | 2014-01-23
AA942 | 1602 | 2014-06-02 | Hive Energy | Hacheston Solar farm | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | N/O Easton Lane, Hacheston, Woodbridge, Suffolk, IP13 | Suffolk | Eastern | England |  | 629977 | 259437 | Suffolk Coastal District Council | C/12/1899 | C/12/1899 |  |  |  |  | 2012-09-04 |  | 2013-02-08 |  |  | 2014-05-22
AA945 | 1603 | 2014-04-03 | Anesco | Culmhead Solar Farm (Resubmission) | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Culmhead Airfield, Culmhead, Churchstanton, Taunton, Somerset | Somerset | South West | England |  | 320819 | 114679 | Taunton Deane Borough Council | 10/12/0024 | [5 empty] | 2012-09-11 | [6 empty] | 2012-10-19 | [5 empty] | 2014-01-26
AA949 | 1604 | 2013-07-09 | TGC Renewables | Wheal Alfred Road Solar Farm | Solar Photovoltaics |  |  | 3.47 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off Wheal Alfred Road Hayle Cornwall | Cornwall | South West | England |  | 158256 | 36251 | Cornwall Council | PA12/08856 | [5 empty] | 2012-09-27 | [6 empty] | 2013-02-12 | [5 empty] | 2013-04-30
AA964 | 1605 | 2013-06-10 | Lightsource Renewable Energy | Blatchworthy Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | TIVERTON, DEVON | Devon | South West | England | EX16 9QH | 250572 | 140713 | Mid Devon District Council | 12/01381/MFUL | [5 empty] | 2012-09-25 | [6 empty] | 2013-03-22 | [5 empty] | 2013-04-29
AA987 | 1606 | 2013-08-16 | Private Developer | Parsonage Barn (extension) | Solar Photovoltaics |  |  | 7.6 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Stocklinch Road, Whitelackington, Ilminster, Somerset | Somerset | South West | England |  | 336700 | 115500 | South Somerset District Council | 12/02823/FUL | [5 empty] | 2012-07-27 | [6 empty] | 2012-10-18 |  |  |  |  | 2013-05-28 | 2013-06-28
B0001 | 1607 | 2013-03-14 | AGR | BIOSSENCE SOLAR PARK | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | S C A Island Site, Bull Lane, Eccles, Aylesford, Kent ME20 7HT | Kent | South East | England |  | 573020 | 160827 | Tonbridge and Malling Borough Council | 11/00985/FL | [5 empty] | 2011-04-14 | [6 empty] | 2011-06-08 | [5 empty] | 2011-07-31
B0016 | 1608 | 2015-03-25 | Oakridge Farm Limited | Oakridge Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Oakridge Farm, Ashfield Road, Ditton Priors, Bridgnorth, Shropshire, WV16 6TW | Shropshire | West Midlands | England |  | 359296 | 288893 | Shropshire Council | 11/01193/FUL | [5 empty] | 2011-03-31 | [6 empty] | 2011-06-02
B0020 | 1609 | 2013-10-08 | Hendra Holiday Park | HENDRA HOLIDAY PARK SOLAR FARM | Solar Photovoltaics |  |  | 1.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Trevilley Farm, Lane, Newquay, Cornwall | Cornwall | South West | England | TR8 4PX | 182941 | 59990 | Cornwall Council | PA11/03163 | [5 empty] | 2011-04-14 | [6 empty] | 2011-07-14 | [5 empty] | 2011-08-07
B0021 | 1610 | 2012-10-23 | The Green Company | EASTACOMBE SOLAR FARM | Solar Photovoltaics |  |  | 3.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Eastacombe Farm, Clawton, Holsworthy, Devon | Devon | South West | England | EX22 6RP | 235435 | 99648 | Torridge District Council | 1/0208/2011/FULM | [5 empty] | 2011-04-11 | [6 empty] | 2011-06-30 |  |  |  |  | 2012-05-01 | 2012-07-01
B0023 | 1611 | 2020-01-22 | Ecotricity | Lodge Farm Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Lodge Farm, Doulting, Shepton Mallet, Somerset | Somerset | South West | England | BA4 4ND | 364775 | 145212 | Mendip District Council | 2011/0765 | [5 empty] | 2011-05-09 | [6 empty] | 2011-12-06 |  |  |  |  | 2015-10-06
B0318 | 1612 | 2012-10-25 | Wrexham Council | Wrexham Social Housing PV | Solar Photovoltaics |  |  | 5.4 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Wrexham | Clwyd | Wales | Wales |  | 333726 | 349750 | Wrexham County Borough Council | [18 empty] | 2012-03-01 | 2012-08-01
B0322 | 1613 | 2014-01-03 | Renewable Resources | Sainsbury's Stores (169 individual Stores) | Solar Photovoltaics |  |  | 16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | [27 empty] | 2012-08-03
B0652 | 1614 | 2017-08-23 | Good Energy Generation | Creathorne Farm - Solar Farm | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Creathorne Farm, Poundstock, Bude | Cornwall | South West | England | EX23 0NE | 220734 | 102650 | Cornwall Council | PA13/00489 | [5 empty] | 2013-01-13 | [6 empty] | 2013-09-03 |  |  |  |  | 2014-07-15 | 2014-08-01
B0666 | 1615 | 2014-01-20 | Lightsource Renewable Energy | Little Braxted Solar Park | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Land South Of Little Braxted Hall, Witham Road Little Braxted, Essex | Essex | Eastern | England |  | 583587 | 214798 | Maldon District Council | 13/00036/FUL | [5 empty] | 2013-01-14 |  | 2013-06-14 |  | 2013-08-08
B0885 | 1616 | 2016-07-13 | First Wessex Housing Association | First Wessex Housing Properties (multiple) | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Aldershot, Eastleigh & Portsmouth | Hampshire | South East | England | [22 empty] | 2014-04-01 | 2015-12-15
C0027 | 1617 | 2013-10-08 | Lightsource Renewable Energy | Higher Pirzwell Solar Farm | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Higher Pirzwell, Kentisbeare, Cullompton, Devon | Devon | South West | England | EX15 2AH | 307546 | 109156 | Mid Devon District Council | 12/00373/MFUL | [5 empty] | 2012-03-14 | [6 empty] | 2012-05-21 |  |  |  |  | 2012-06-25 | 2012-07-26
C0028 | 1618 | 2013-10-08 | Lightsource Renewable Energy | Broadgate Solar Farm | Solar Photovoltaics |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Broadgate, Morchard, Bishop, Crediton Devon | Devon | South West | England | EX17 6RU | 277641 | 107308 | Mid Devon District Council | 12/00376/MFUL | [5 empty] | 2012-03-15 | [6 empty] | 2012-05-24 |  |  |  |  | 2012-06-12 | 2012-07-27
C0112 | 1619 | 2013-03-25 | Lightsource BP | CRAYSMARSH SOLAR FARM | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | N/O Craysmarsh Farm, Bowerhill, Melksham, Wiltshire | Wiltshire | South West | England | SN12 6RG | 393506 | 162624 | Wiltshire Council | W/12/00467/FUL | [5 empty] | 2012-03-20 | [6 empty] | 2012-06-20 |  |  |  |  | 2012-10-25 | 2012-11-26
C0122 | 1620 | 2014-04-03 | Anesco | SOLAR PARK - WHITCHURCH FARM | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Whitchurch Farm, Chilcompton, Bath, Avon | Somerset | South West | England | BA3 4DW | 363439 | 153553 | Mendip District Council | 2012/0554 | [5 empty] | 2012-04-13 | [6 empty] | 2012-11-06 | [5 empty] | 2014-01-17
C0135 | 1621 | 2014-01-06 | Lightsource Renewable Energy | Solar Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Adjacent Beech Farm, Warmwell Mill Access Road, Warmwell, Dorchester, Dorset, DT2 8LZ | Dorset | South West | England |  | 374868 | 86689 | West Dorset District Council | 1/D/12/000430 | [5 empty] | 2012-04-18 | [6 empty] | 2012-09-14
C0263 | 1622 | 2013-11-12 | Private Developer | THE HOLLIES SOLAR PARK - SKEGNESS | Solar Photovoltaics |  |  | 8.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The Hollies, High Lane, Croft, Skegness, Lincolnshire, PE24 4SH | Lincolnshire | East Midlands | England |  | 549558 | 363539 | East Lindsey District Council | S/039/00984/12 | [5 empty] | 2012-06-28 | [6 empty] | 2012-10-19 |  |  |  |  | 2012-12-01 | 2013-06-07
C0264 | 1623 | 2014-01-29 | Arqiva Ltd | AMBLESTON SOLAR PANELS | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Television Transmitter Centre, Ambleston, Haverfordwest, Dyfed, SA61 | Dyfed | Wales | Wales |  | 202885 | 226177 | Pembrokeshire County Council | 11/0104/PA | [5 empty] | 2011-06-16 | [6 empty] | 2011-08-11 |  |  |  |  | 2011-10-24 | 2012-01-25
C0346 | 1625 | 2013-07-04 | Lumicity | Hacche Barton Solar Farm | Solar Photovoltaics |  |  | 9.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Hacche Barton, South Molton, Devon | Devon | South West | England | EX36 3EH | 271309 | 127777 | North Devon District Council | 54387 | [6 empty] | 2013-07-04
C0352 | 1626 | 2014-03-27 | Ford Farm PV Scheme LLP | Ford Farm Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ford Farm, St Ive, Liskeard, Cornwall | Cornwall | South West | England | PL14 3LX | 231356 | 67125 | Cornwall Council | PA12/06666 | [5 empty] | 2012-07-16 | [6 empty] | 2012-10-05 | [5 empty] | 2013-05-02
C0435 | 1628 | 2018-03-21 | Caledon Partners (Smarter Energy Solutions Ltd) | Hendra Barns Solar Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land Adj Hendra Barns Mitchell Cornwall | Cornwall | South West | England | TR8 5AZ | 185976 | 53140 | Cornwall Council | PA13/02466 | [5 empty] | 2013-03-21 | [6 empty] | 2013-07-08 |  |  |  | 2016-07-08
C0447 | 1630 | 2017-01-03 | Equitix | Canworthy Water | Solar Photovoltaics |  |  | 41 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land west of South Wheatley, Wheatley Road, Nr Canworthy Water, Launceston | Cornwall | South West | England | PL15 8LY | 224225 | 92272 | Cornwall Council | PA12/07626 | [5 empty] | 2012-08-22 | [6 empty] | 2013-01-21 |  |  |  |  | 2014-02-28 | 2014-12-10
C0570 | 1631 | 2013-11-18 | Private Developer | Foxcombe Farm Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Foxcombe Farm, Hollacombe, Holsworthy, Devon | Devon | South West | England | EX22 6NW | 238472 | 102820 | Torridge District Council | 1/0817/2012/FULM | [5 empty] | 2012-09-18 | [6 empty] | 2013-02-11 | [5 empty] | 2013-06-10
C0647 | 1634 | 2015-09-29 | Milford Haven Port Authority | Liddeston Ridge Solar Park (Milford Haven) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The S/E/O Court Road, Liddeston, Milford Haven, Dyfed | Dyfed | Wales | Wales | SA73 3QD | 189837 | 206570 | Pembrokeshire County Council | 12/0614/PA | [5 empty] | 2012-10-02 | [6 empty] | 2013-01-24 |  |  |  |  | 2013-11-13 | 2014-03-31
C0877 | 1639 | 2017-12-04 | Greencoat Capital | Bodwen Solar Park | Solar Photovoltaics |  |  | 5.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of A391 Near Bodwen Bugle Cornwall | Cornwall | South West | England |  | 202672 | 60536 | Cornwall Council | PA13/03710 | [5 empty] | 2013-05-22 |  | 2014-02-25 |  |  |  | 2015-03-24 | 2015-03-24 |  |  |  |  | 2016-10-15 | 2017-02-15
C0910 | 1641 | 2015-03-31 | Private Developer | Treswarrow Solar Park | Solar Photovoltaics |  |  | 6.45 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Treswarrow, Trelights, Port Isaac, Cornwall | Cornwall | South West | England | PL29 3TN | 198285 | 78122 | Cornwall Council | PA13/04287 | APP/D0840/A/14/2213107 |  |  |  |  | 2013-05-16 |  | 2013-10-25 | 2014-02-11 |  |  | 2014-10-20 | 2014-10-20 |  |  |  |  | 2015-01-02 | 2015-03-18
C0921 | 1642 | 2016-06-21 | Elgin Energy EsCo | Carnemough Farm Solar Park | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Carnemough Farm Grampound Road Truro Cornwall | Cornwall | South West | England | TR2 4EL | 191629 | 52065 | Cornwall Council | PA13/06755 | [5 empty] | 2013-08-13 |  | 2013-11-22 |  |  |  | 2015-02-27 | 2015-02-27 |  |  |  |  | 2015-11-15 | 2016-03-31
C0977 | 1646 | 2017-05-03 | NESF (formerly British Solar Renewables) | Aller Court Farm Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Os 4716 And Os 4300, Church Path, Aller, Langport, Somerset | Somerset | South West | England | TA10 0QR | 339461 | 129049 | South Somerset District Council | 14/04300/FUL | APP/R3325/W/15/3135346 |  |  |  |  | 2014-09-22 |  | 2015-07-23 | 2015-11-10 |  |  | 2016-06-08 | 2016-06-08 |  |  |  |  | 2017-02-01 | 2017-04-01
C0981 | 1647 | 2013-06-12 | AEE Renewables | Caves Farm Solar Park | Solar Photovoltaics |  |  | 4.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land OS 3100 At Caves Farm Pitney Langport Somerset | Somerset | South West | England |  | 345196 | 128763 | South Somerset District Council | 13/00441/FUL | [5 empty] | 2013-02-07 |  | 2013-05-02
C0984 | 1648 | 2014-04-30 | Sunsave 12 (Derriton Fields) Limited./ Vogt solar | Derriton Fields Solar Farm | Solar Photovoltaics |  |  | 11.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Derriton Fields Farm Holsworthy Devon | Devon | South West | England | EX22 6JX | 233249 | 103010 | Torridge District Council | 1/0978/2012/FULM | [5 empty] | 2012-11-06 | [6 empty] | 2013-02-05 |  |  |  |  | 2014-01-13 | 2014-03-31
C0987 | 1649 | 2014-04-02 | Lightsource Renewable Energy | Cleave Farm Solar Park | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent Alverdiscott Substation Near Gammaton Moor Alverdiscott Devon | Devon | South West | England |  | 249891 | 124902 | Torridge District Council | 1/0997/2012/FULM | [5 empty] | 2012-11-19 | [6 empty] | 2013-02-18 | [5 empty] | 2013-10-25
C1008 | 1655 | 2014-12-17 | Renewable Energy Systems (RES) | Four Burrows Farm (Extension 2) | Solar Photovoltaics |  |  | 6.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Four Burrows Farm Four Burrows Blackwater Cornwall | Cornwall | South West | England | TR4 8JB | 176498 | 48238 | Cornwall Council | PA13/01195 | [5 empty] | 2013-02-20 | [6 empty] | 2013-07-09 |  |  |  |  | 2014-02-23 | 2014-11-03
C1011 | 1656 | 2014-11-27 | Bath & West Community Energy Ltd | Chelworth Industrial Estate Solar Park | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Chelworth Industrial Estate, Braydon Lane, Nr Cricklade, Wiltshire | Wiltshire | South West | England |  | 407876 | 192091 | Wiltshire Council | 12/03968/FUL | [5 empty] | 2012-12-05 | [6 empty] | 2013-04-22 |  |  |  |  | 2014-02-03 | 2014-02-24
C1061 | 1658 | 2014-05-20 | Lightsource Renewable Energy | Drapers Farm Solar Park | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | E/O Milch Hill Lane, Great Leighs, Chelmsford, Essex, CM3 1QF | Essex | Eastern | England |  | 572146 | 220468 | Uttlesford District Council | UTT/13/0561/FUL | [5 empty] | 2013-03-15 | [6 empty] | 2013-06-07 |  |  |  |  | 2013-09-26 | 2014-03-30
C1128 | 1659 | 2014-04-02 |  | Week Farm Solar Park | Solar Photovoltaics |  |  | 3.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Week Farm Torrington Devon | Devon | South West | England | EX38 7HU | 251218 | 119059 | Torridge District Council | 1/0280/2013/FUL | [5 empty] | 2013-04-15 | [6 empty] | 2013-07-30 | [5 empty] | 2014-03-28
C1147 | 1661 | 2015-12-22 | Lightsource Renewable Energy | Langton Farm Solar park | Solar Photovoltaics |  |  | 4.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land west of Langton Farm, Dwrbach, Fishguard, Pembrokeshire | Dyfed | Wales | Wales |  | 194473 | 233813 | Pembrokeshire County Council | 12/1160/PA | [5 empty] | 2013-03-18 | [6 empty] | 2013-11-19 |  |  |  |  | 2015-10-28 | 2015-12-03
C1150 | 1663 | 2014-04-02 | AEE Renewables | Says Court Farm solar park | Solar Photovoltaics |  |  | 19.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Says Court Farm Badminton Road Coalpit Heath Bristol South Gloucestershire BS36 2NY | Avon | South West | England |  | 368922 | 181730 | South Gloucestershire Council | PT13/1082/F | [5 empty] | 2013-04-09 | [6 empty] | 2013-10-01 | [5 empty] | 2014-03-31
C1192 | 1667 | 2014-05-07 | Lark Energy | Ketton solar farm | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | North Field, Off Pit Lane, Ketton, Stamford, Lincolnshire`` | Leicestershire | East Midlands | England | PE9 3SZ | 497610 | 306126 | Rutland County Council | 2013/0286/FUL | [5 empty] | 2013-04-23 | [6 empty] | 2013-06-23 |  |  |  |  | 2013-10-11 | 2014-03-31
C1224 | 1668 | 2013-10-08 | Lightsource Renewable Energy | Treguff Farm Solar Park | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Treguff Farm, St Mary Church, Cowbridge | South Glamorgan | Wales | Wales |  | 302489 | 171132 | Vale of Glamorgan Council | 2013/00247/FUL | [5 empty] | 2013-03-22 |  | 2013-07-08
C1247 | 1669 | 2014-04-03 | Manor of Cadland | The Manor of Cadland Estate - extension | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | NEWHOUSE FIELD, WHITEFIELD FARM, LANGLEY, HAMPSHIRE, SO45 1YH | Hampshire | South East | England |  | 445200 | 101300 | New Forest National Park Authority | 13/98465 | [5 empty] | 2013-04-30 | [6 empty] | 2013-07-18 | [5 empty] | 2014-02-07
C1277 | 1671 | 2016-10-04 | United Photovoltaics | Rowles Farm solar park | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Rowles Farm Bletchingdon Oxfordshire | Oxfordshire | South East | England | OX5 | 453433 | 216448 | Cherwell District Council | 13/01027/F | 13/00066/REFAPP |  |  |  |  | 2013-07-09 |  | 2013-10-07 |  |  |  | 2014-04-17 | 2014-04-17 |  |  |  |  | 2014-12-01 | 2015-03-14
C1280 | 1672 | 2015-08-03 | Lightsource Renewable Energy | Ryston Estate Solar Park | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent A10, Ryston, Norfolk | Norfolk | Eastern | England | PE38 0AE | 562344 | 302319 | King's Lynn and West Norfolk Borough Council | 13/00692/FM | [5 empty] | 2013-05-14 | [6 empty] | 2013-08-13 |  |  |  |  | 2014-08-06 | 2015-05-07
C1298 | 1673 | 2014-05-20 | Lightsource Renewable Energy | Reaches Farm Solar Park | Solar Photovoltaics |  |  | 6.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Reaches Farm Thetford Road Northwold Norfolk | Norfolk | Eastern | England |  | 573913 | 298817 | King's Lynn and West Norfolk Borough Council | 13/00735/FM | [5 empty] | 2013-05-20 | [6 empty] | 2013-08-01 | [5 empty] | 2014-03-21
C1306 | 1676 | 2018-03-21 | Countryside Renewables | Pastures Farm solar park (Gonerby Lane) | Solar Photovoltaics |  |  | 4.95 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Pasture Farm, Gonerby Lane, Allington, Grantham | Lincolnshire | East Midlands | England | NG32 2DU | 487557 | 339761 | South Kesteven District Council | S15/0194 | [5 empty] | 2015-02-26 | [6 empty] | 2015-06-10 |  |  |  | 2018-06-10
C1352 | 1680 | 2014-03-07 | Brilliant Harvest Installations | Deptford Farm solar park | Solar Photovoltaics |  |  | 7.77 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land north of Deptford Farm Wylye Warminster Wiltshire | Wiltshire | South West | England |  | 401847 | 140200 | Wiltshire Council | 13/00699/FUL | [5 empty] | 2013-05-24 |  | 2013-12-10
C1417 | 1681 | 2014-12-01 | Belltown Power | Watchfield Lawn | Solar Photovoltaics |  |  | 10.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at, Watchfield Lawn, Watchfield, Highbridge, TA9 4LD | Somerset | South West | England |  | 334135 | 147772 | Sedgemoor District Council | 12/13/00009 | [5 empty] | 2013-05-24 | [6 empty] | 2013-08-01 |  |  |  |  | 2013-11-07 | 2014-03-12
C1513 | 1682 | 2014-03-31 | Corton Farm Solar Park Ltd | Corton Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Corton Farm, Friar Waddon Lane, Friar Waddon, Weymouth, Dorset, DT3 4EP | Dorset | South West | England |  | 363615 | 85472 | West Dorset District Council | 1/D/13/000772 | [5 empty] | 2013-06-04 |  | 2013-11-26
C1515 | 1683 | 2015-09-30 | KS SPV33 Ltd | Beaurepaire Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Beaurepaire Farm New Road Bramley Tadley Hampshire RG26 5ED | Hampshire | South East | England |  | 462948 | 157606 | Basingstoke and Deane Borough Council | 13/00751/FUL | [5 empty] | 2013-06-10 |  | 2014-01-24
C1526 | 1684 | 2014-11-25 | INRG Solar | New Tyning Farm | Solar Photovoltaics |  |  | 5.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | New Tyning Farm, Waterside Lane, Kilmersdon, Bath, Avon | Somerset | South West | England | BA3 5TE | 369416 | 152710 | Mendip District Council | 2013/1356 | APP/Q3305/A/14/2214650 |  |  |  |  | 2013-06-29 |  | 2014-01-16 | 2014-03-17 |  | 2014-10-01
C1635 | 1685 | 2014-04-25 |  | Highfield Farm | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Highfield Farm, Long Street, Foston, Grantham, NG322LD | Lincolnshire | East Midlands | England |  | 494122 | 345265 | South Kesteven District Council | S13/2132 | [5 empty] | 2013-08-28 | 2014-03-12
C1652 | 1694 | 2019-03-21 | Anesco | Manor Farm | Solar Photovoltaics |  |  | 15.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Manor Farm, Wainfleet Road, Irby-in-the-Marsh, Skegness | Lincolnshire | East Midlands | England | PE24 5AY | 546683 | 363395 | East Lindsey District Council | S/051/00772/17 | [5 empty] | 2017-05-02 | [6 empty] | 2017-11-30
C1748 | 1699 | 2014-05-20 | Smarter Energy Solutions | Witches Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Prothither Farm, Hoarwithy, Herefordshire | Hereford and Worcester | West Midlands | England | HR2 6QJ | 353748 | 230751 | Herefordshire Council | S103018/F | [5 empty] | 2010-11-29 | [6 empty] | 2011-02-08 | [5 empty] | 2013-02-19
IF1004 | 1712 | 2016-07-27 | Neame Sutton Ltd | Maydwell Avenue | Solar Photovoltaics |  |  | 2.1 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Expired | Planning Permission Expired | Slinfold, West Sussex, | West Sussex | South East | England |  | 511107 | 130810 | Horsham District Council | DC/12/1838 | [5 empty] | 2012-10-02 | [6 empty] | 2013-05-31 |  |  |  | 2016-05-31
IF1006 | 1713 | 2014-10-29 | Lightsource Renewable Energy | Burntstalk Solar Park | Solar Photovoltaics |  |  | 11.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Low Road, Narford, Kings Lynn, Norfolk | Norfolk | Eastern | England |  | 577721 | 311630 | Breckland Council | 3PL/2012/1036/F | [5 empty] | 2012-10-08 | [6 empty] | 2012-12-21 | [5 empty] | 2013-03-30
IF1014 | 1714 | 2014-10-29 | Lightsource Renewable Energy | Claypit Moor Solar Farm (Lexham) | Solar Photovoltaics |  |  | 7.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tittleshall, Kings Lynn, Norfolk, PE32 | Norfolk | Eastern | England |  | 587463 | 319985 | Breckland Council | 3PL/2012/1020/F | [5 empty] | 2012-09-25 | [6 empty] | 2012-12-21 | [5 empty] | 2013-03-29
IF1025 | 1715 | 2014-03-27 | Private Developer | Holton Airfield | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bernard Matthews Ltd Upper Holton HALESWORTH IP19 8NJ | Suffolk | Eastern | England |  | 640162 | 279467 | Waveney District Council | DC/12/1187/FUL | [5 empty] | 2012-10-15 | [6 empty] | 2012-12-19 | [5 empty] | 2013-12-19
IF1037 | 1716 | 2014-02-28 | IKAROS SOLAR LIMITED | Goose Willow Farm | Solar Photovoltaics |  |  | 11.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hanney Road, Abingdon, Oxfordshire | Oxfordshire | South East | England | OX13 6AP | 444604 | 193209 | Vale of White Horse District Council | P12/V2112/FUL | [5 empty] | 2012-10-18 | [6 empty] | 2012-12-11 |  |  |  |  | 2013-07-31 | 2013-12-23
IF1052 | 1717 | 2016-05-10 | Lightsource Renewable Energy | Chediston Hall Solar Park | Solar Photovoltaics |  |  | 12.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent To Bonners Farm, Mill Road, Wissett, Suffolk | Suffolk | Eastern | England |  | 636663 | 278367 | Waveney District Council | DC/12/1119/FUL | [5 empty] | 2012-10-08 | [6 empty] | 2013-01-03 |  |  |  |  | 2013-01-04 | 2013-05-24
IF1055 | 1718 | 2015-05-28 | Elgin Energy EsCo | Burthy Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Summercourt Newquay Cornwall | Cornwall | South West | England | TR8 5BN | 190555 | 55377 | Cornwall Council | PA13/05983 | APP/D0840/W/14/2212340 |  |  |  |  | 2013-07-12 |  | 2013-10-30 | 2014-01-27 |  |  | 2014-09-30 | 2014-09-30 |  |  |  | 2017-09-30 | 2014-12-01 | 2015-03-20
IF1057 | 1719 | 2015-09-29 | Munich RE | Caeremlyn Solar Farm | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Caermelyn Solar Farm, Land nr Llanlliwe Farm, Hellan Amgoed, Whitland | Dyfed | Wales | Wales | SA34 0SS | 218627 | 217644 | Carmarthenshire County Council | W/26672 | [5 empty] | 2012-05-31 | [6 empty] | 2013-01-14 |  |  |  |  | 2014-02-12 | 2014-03-31
IF1065 | 1720 | 2014-06-03 | TGC Renewables | Hazard Farm | Solar Photovoltaics |  |  | 6.37 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Harberton, Totnes | Devon | South West | England | TQ9 7LN | 274991 | 59302 | South Hams District Council | 23/2485/12/F | [5 empty] | 2012-10-29 | [6 empty] | 2013-05-13 | [5 empty] | 2014-03-31
IF1069 | 1721 | 2013-11-29 | R S Assemblies Limited | Home Farm (Merton - solar) | Solar Photovoltaics |  |  | 18.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Merton Oxfordshire OX25 2ND | Oxfordshire | South East | England |  | 459052 | 218811 | Cherwell District Council | 12/01414/F | [5 empty] | 2012-10-26 | [6 empty] | 2013-02-15 | [5 empty] | 2013-11-12
IF1076 | 1722 | 2016-07-27 | Low Carbon Solar (Liquidated) | Newnham Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Newnham Lane Ryde Isle Of Wight PO334ED | Isle of Wight | South East | England |  | 456522 | 91466 | Isle of Wight Council | P/00338/11 | [5 empty] | 2011-03-21 | [6 empty] | 2011-05-20 |  |  |  | 2016-05-20
IF1079 | 1723 | 2015-08-27 | Lightsource Renewable Energy | Rudge Hill Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rivers Corner, Dorset | Dorset | South West | England |  | 378118 | 112656 | North Dorset District Council | 2/2012/0253/PLNG | [5 empty] | 2012-03-20 |  | 2012-06-08 |  |  |  | 2013-02-20 | 2013-02-20 |  |  |  |  | 2013-09-03 | 2013-10-25
IF1092 | 1724 | 2014-02-18 | AEE Renewables | Sevor Farm | Solar Photovoltaics |  |  | 9.26 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nightingale Lane South Marston Swindon | Wiltshire | South West | England | SN3 4SL | 419764 | 188194 | Swindon Borough Council | S/13/0165 | [5 empty] | 2013-02-11 | [6 empty] | 2013-05-28 |  |  |  |  | 2013-09-30 | 2013-11-30
IF1094 | 1725 | 2017-02-02 | Steadfast Marsh Solar - Innogy (previously BELECTRIC Solar) | Marsh Farm | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Long Newnton Airfield, Brokenborough, Malmesbury, Wiltshire | Wiltshire | South West | England | SN16 9SR | 392426 | 191961 | Wiltshire Council | 12/02104/FUL | [5 empty] | 2012-07-27 | [6 empty] | 2013-01-15 | [5 empty] | 2014-01-22
IF1099 | 1726 | 2014-02-26 | Inazin Power Ltd | Four Burrows Solar farm (Extension 1) | Solar Photovoltaics |  |  | 1.45 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of Little Lambriggan Farm (South West Of Higher Callestick Farm) Callestick Cornwall | Cornwall | South West | England |  | 176618 | 49601 | Cornwall Council | PA12/02338 | [5 empty] | 2012-03-28 | [6 empty] | 2013-03-01 | [5 empty] | 2014-02-23
IF1131 | 1727 | 2014-03-26 | Sunsave 9 (Old Rides) Ltd/ Vogt solar | Old Rides solar Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Old Rides Farm, Leysdown Road, Eastchurch, Sheerness, Kent, ME12 4BD | Kent | South East | England |  | 599732 | 169890 | Swale Borough Council | SW/12/1448 | [5 empty] | 2012-11-28 | [6 empty] | 2013-02-14 |  |  |  |  | 2013-08-01 | 2014-01-15
IF1133 | 1728 | 2013-12-10 | 35 Degrees | Parabel North Beer Solar Farm | Solar Photovoltaics |  |  | 6.835 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | W/O North Beer Farm, North Beer Lane, Boyton, Launceston, Cornwall | Cornwall | South West | England | PL15 8NP | 230442 | 91828 | Cornwall Council | PA12/10520 | [5 empty] | 2012-11-07 | [6 empty] | 2013-02-11 | [5 empty] | 2013-03-31
IF1134 | 1729 | 2014-03-26 | Private Developer | Crockers Hele | Solar Photovoltaics |  |  | 1.25 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Meeth, Okehampton, Devon | Devon | South West | England | EX20 3QN | 252587 | 106849 | West Devon Borough Council | 03273/2012 | [5 empty] | 2012-11-26 | [6 empty] | 2013-02-13 | [5 empty] | 2013-09-15
IF1137 | 1730 | 2013-04-15 | Bentley Motor Cars Ltd | Bentley Motors Ltd 1 | Solar Photovoltaics |  |  | 5.1 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Pyms Lane, Crewe, Cheshire, CW1 3PL | Cheshire | North West | England |  | 368446 | 356533 | Cheshire East Council | 11/1042N | [5 empty] | 2011-03-14 | [6 empty] | 2011-06-08 |  |  |  |  | 2012-12-15 | 2013-03-21
IF1153 | 1731 | 2013-07-19 | Northwick Power Ltd | Northwick Estate (Extension) | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent To Northwick 5MW Solar Panel Array, Northwick Estate, Upton Wold, Moreton-in-Marsh, Glouestershire, GL56 9TR | Gloucestershire | South West | England |  | 413600 | 235700 | Cotswold District Council | 12/05072/FUL | [5 empty] | 2012-11-13 | [6 empty] | 2013-03-05 | [5 empty] | 2013-05-31
IF1183 | 1732 | 2015-02-25 | Blenheim Farm | North Of Field Barn | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hook Norton Road, Sibford Ferris, Banbury, Oxfordshire, OX15 5QR | Oxfordshire | South East | England |  | 436126 | 236972 | Cherwell District Council | 12/01737/F | [5 empty] | 2012-12-18 | [6 empty] | 2013-04-02 |  |  |  |  | 2014-06-01 | 2014-08-01
IF1216 | 1733 | 2014-02-07 | Mickram | Mickram Limited | Solar Photovoltaics |  |  | 1.41 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | Bank Road King's Lynn Norfolk PE30 2HD | Norfolk | Eastern | England |  | 561191 | 321253 | King's Lynn and West Norfolk Borough Council | 12/01681/FM | [5 empty] | 2012-10-22 | [6 empty] | 2013-02-05
IF1217 | 1734 | 2014-01-28 | Solar Power Generation Ltd | Great Curham Farm | Solar Photovoltaics |  |  | 6.34 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Ash Thomas, Tiverton | Devon | South West | England | EX16 4NP | 300756 | 111313 | Mid Devon District Council | 12/01664/MFUL | 13/00024/WR |  |  |  |  | 2012-11-30 |  | 2013-06-05 |  | 2013-11-15
IF1223 | 1735 | 2017-07-31 | Rockfire Capital | Wroughton Airfield Solar Park | Solar Photovoltaics |  |  | 50 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Science Museum, Orbital Road, Wroughton, Swindon | Wiltshire | South West | England |  | 413114 | 179071 | Swindon Borough Council | S/13/0809 |  | APP/U3935/V/14/2216792 | Call-in |  |  | 2013-07-15 | [7 empty] | 2014-04-02 |  | 2015-03-19 |  | 2016-02-11 | 2016-03-31
IF1225 | 1736 | 2015-03-17 | Munich RE | Forest Heath Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fordham Road, Newmarket, Suffolk | Suffolk | Eastern | England |  | 563237 | 267275 | Forest Heath District Council | F/2012/0655/FUL | [5 empty] | 2012-11-07 | [6 empty] | 2013-01-02 | [5 empty] | 2014-02-04
IF1227 | 1737 | 2014-04-03 | Anesco | Abbey Farm | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Double Bank Lane, Sawtry, Huntingdon, Cambridgeshire, PE28 5YJ | Cambridgeshire | Eastern | England |  | 520021 | 281612 | Huntingdonshire District Council | 1202026FUL | [5 empty] | 2013-01-15 | [6 empty] | 2013-09-05 | [5 empty] | 2014-03-19
IF1240 | 1738 | 2015-09-30 | Kronos Solar | Land At Woodlands Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | North Tamerton Holsworthy | Cornwall | South West | England | EX22 6SQ | 230310 | 99817 | Cornwall Council | PA12/12014 | [5 empty] | 2013-01-25 |  | 2014-01-02
IF1253 | 1739 | 2013-07-24 | Private Developer | Park Hall Stud Farm | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Park Hall Road Denby Ripley Derbyshire DE5 8PX | Derbyshire | East Midlands | England |  | 438011 | 347647 | Amber Valley Borough Council | AVA/2012/0946 | [5 empty] | 2012-11-02 |  | 2013-07-04
IF1254 | 1740 | 2013-07-24 | Private Developer | Iron Works Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Street Lane Ripley Derbyshire DE5 8HT | Derbyshire | East Midlands | England |  | 438250 | 349295 | Amber Valley Borough Council | AVA/2012/1010 | [5 empty] | 2012-11-05 |  | 2013-07-04
IF1256 | 1741 | 2013-07-24 | Private Developer | Knob Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Morley Park Road Belper Derbyshire DE56 0HQ | Derbyshire | East Midlands | England |  | 437351 | 348648 | Amber Valley Borough Council | AVA/2012/0989 | [5 empty] | 2012-11-05 |  | 2013-07-04
IF1264 | 1742 | 2013-09-23 | Lumicity | Buckhayes Farm | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Chevithorne,, Tiverton, Devon | Devon | South West | England |  | 297241 | 120444 | Mid Devon District Council | 13/00185/MFUL | [5 empty] | 2013-02-04 |  | 2013-08-21
IF1266 | 1743 | 2014-03-26 | Mells Park Trust | Land at Soho Farm | Solar Photovoltaics |  |  | 1.53 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Soho Leigh upon Mendip, Radstock | Somerset | South West | England | BA3 5RD | 369602 | 148085 | Mendip District Council | 2012/2982 | [5 empty] | 2013-01-15 | [6 empty] | 2013-05-15 |  |  |  |  | 2013-11-15 | 2014-03-24
IF1268 | 1744 | 2016-05-16 | Cyrasol Ecotec | Land South West Of Apollo Business Park | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Drift Lane Wroxton Oxfordshire | Oxfordshire | South East | England |  | 440058 | 242501 | Cherwell District Council | 13/00015/F | [5 empty] | 2013-01-18 | [6 empty] | 2013-04-03 |  |  |  |  | 2014-02-15 | 2014-04-15
IF1276 | 1745 | 2013-07-24 | Wiltshire Wildlife Trust and Bath and West Community Energy Ltd | LAND AT SANDPOOL FARM | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Oaksey Road, Poole Keynes, Cirencester, Gloucestershire, GL7 6EA | Gloucestershire | South West | England |  | 401236 | 194295 | Cotswold District Council | 13/00276/FUL | [5 empty] | 2013-01-22 | 2013-06-26
IF1308 | 1746 | 2016-09-22 | 3C Energy/Conergy | Manor Farm (Monmouthshire) | Solar Photovoltaics |  |  | 10.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Llanvapley, Monmouthshire | Gwent | Wales | Wales |  | 336338 | 215519 | Monmouthshire County Council | DC/2013/00006 | APP/E6840/A/14/2212987 |  |  |  |  | 2013-01-07 |  | 2013-09-13 | 2014-04-04 |  |  | 2014-10-24 | 2014-10-24 |  |  |  |  | 2016-04-18 | 2016-06-23
IF1312 | 1747 | 2014-02-06 | Community Power Ltd | Land at Mill Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Quab Lane, Wedmore | Somerset | South West | England | BS28 4AR | 342716 | 148091 | Sedgemoor District Council | 50/13/00003 | [5 empty] | 2013-01-30 | [6 empty] | 2013-04-09 |  |  |  |  | 2013-10-21 | 2013-11-04
IF1354 | 1748 | 2014-06-02 | Anesco | Land at East Farm | Solar Photovoltaics |  |  | 6.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Codford Dairy, East Farm, Church Lane, Codford | Wiltshire | South West | England |  | 398727 | 142115 | Wiltshire Council | W/12/02216/FUL | [5 empty] | 2013-01-03 | [6 empty] | 2013-03-19 |  |  |  |  | 2013-10-09 | 2013-11-09
IF1363 | 1750 | 2014-03-24 | TGC Renewables | New Rendy Farm | Solar Photovoltaics |  |  | 4.779 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Oake, Taunton, Somerset, TA4 1BB | Somerset | South West | England |  | 315819 | 123804 | Taunton Deane Borough Council | 27/13/0003 | [5 empty] | 2013-03-05 | [6 empty] | 2013-05-29 | [5 empty] | 2013-12-15
IF1411 | 1751 | 2017-02-02 | Green Hedge (BayWa r.e.) | Reydon Farm (resubmission) | Solar Photovoltaics |  |  | 3.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Quay Lane, Reydon, Southwold, Suffolk, IP18 6SF | Suffolk | Eastern | England |  | 648509 | 277624 | Waveney District Council | DC/13/0269/FUL | [5 empty] | 2013-03-11 | [6 empty] | 2013-06-06 |  |  |  |  | 2014-01-20 | 2015-03-15
IF1418 | 1752 | 2016-03-04 | TGC Renewables | Copley Farm | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Doddington Lane, Claypole, Newark, Nottingham | Lincolnshire | East Midlands | England | NG23 5AT | 484930 | 347958 | South Kesteven District Council | S13/3273 | APP/E2530/A/14/2218270 |  |  |  |  | 2014-01-13 |  | 2014-04-24 | 2014-05-16 |  |  | 2015-01-06 | 2015-01-06 |  |  |  | 2018-01-06 | 2015-06-28 | 2016-01-13
AA883 | 1753 | 2016-04-26 | Lark Energy | Ellough Airfield (Ellough 2 extension) | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Former Ellough Airfield, Suffolk | Suffolk | Eastern | England | NR34 7UH | 645184 | 288436 | Waveney District Council | DC/12/1113/FUL | APP/006/2013 |  |  | 41769 |  | 2012-09-25 |  | 2013-02-12 |  |  |  | 2013-10-16 | 2013-10-16 | 2013-10-17 |  | 2015-03-12 |  | 2015-05-01 | 2016-03-31
AA922 | 1754 | 2015-09-30 | British Solar Renewables | Nanteague Farm | Solar Photovoltaics |  |  | 7.65 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nanteague Farm, Marazanvose, Truro, Cornwall | Cornwall | South West | England | TR4 9DH | 179708 | 49721 | Cornwall Council | PA14/06773 | [5 empty] | 2012-09-07 | [6 empty] | 2013-04-09 |  |  |  |  | 2014-10-22 | 2015-02-05
AA978 | 1755 | 2014-06-10 | Lark Energy | Grange Farm (Burton Pedwardine) | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Asgarby Road, Burton Pedwardine, Lincoln | Lincolnshire | East Midlands | England |  | 510532 | 342920 | North Kesteven District Council | 12/1242/FUL | [5 empty] | 2012-11-27 | [6 empty] | 2013-02-04 |  |  |  |  | 2013-06-10 | 2014-04-30
B0894 | 1756 | 2016-01-06 | Telford and Wrekin Borough Council | Wheat Leasows Solar Park | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at, Wheat Leasows, Telford | Shropshire | West Midlands | England | TF6 6DS | 367250 | 313787 | Telford and Wrekin Council | TWC/2014/0134 | [5 empty] | 2014-02-13 | [6 empty] | 2014-05-08 |  |  |  |  | 2014-09-01 | 2014-12-01
C0487 | 1757 | 2017-08-31 | NextEnergy Solar Fund (NESF) | Honington Solar Farm | Solar Photovoltaics |  |  | 13.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Euston Estate, Honnington, Suffolk | Suffolk | Eastern | England |  | 590071 | 274942 | St Edmundsbury Borough Council | SE/12/1069/FUL | [5 empty] | 2012-08-22 | [6 empty] | 2012-12-10 | [5 empty] | 2014-03-31
C0645 | 1758 | 2014-07-03 | Lightsource Renewable Energy (BNRG Renewables) | Hill Farm Solar Park | Solar Photovoltaics |  |  | 10.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hill Farm, Carpenters Road, Brading, Ryde, Isle of Wight, PO33 1YN | Isle of Wight | South East | England |  | 461387 | 89012 | Isle of Wight Council | P/01485/12 | [5 empty] | 2012-10-05 | [6 empty] | 2013-01-29 | [5 empty] | 2014-05-30
C0868 | 1759 | 2014-06-20 | St Anthony 101 PV Park Ltd | Anthony Estate Solar Farm | Solar Photovoltaics |  |  | 9.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land North Of Freathy Farm Freathy Cornwall | Cornwall | South West | England |  | 240028 | 52879 | Cornwall Council | PA13/11705 | [5 empty] | 2013-12-23 |  | 2014-06-06
C1289 | 1760 | 2017-09-19 | Caledon Partners | Trendeal Solar Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land Adj To Homer Downs Ladock Cornwall | Cornwall | South West | England |  | 189927 | 53184 | Cornwall Council | PA13/06612 | [5 empty] | 2013-08-09 | [6 empty] | 2013-10-29
C1376 | 1761 | 2015-01-07 | Foresight | Homeland Solar Farm | Solar Photovoltaics |  |  | 13.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Homeland Farm, Ringwood Road, Three Legged Cross, Wimborne, Dorset | Dorset | South West | England | BH21 6QZ | 409618 | 105289 | East Dorset District Council | 3/13/0470/FUL | [5 empty] | 2013-05-28 | [6 empty] | 2013-10-08 |  |  |  |  | 2013-12-01 | 2014-03-01
C1426 | 1762 | 2015-05-07 | The Solar Building Company Ltd | East Fairlee | Solar Photovoltaics |  |  | 7.25 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | part of East Fairlee Farm Fairlee Road Newport Isle Of Wight PO30 | Isle of Wight | South East | England | PO30 2LB | 460993 | 90461 | Isle of Wight Council | P/00737/13 | [5 empty] | 2013-06-14 | [6 empty] | 2013-10-17 |  |  |  |  | 2014-05-13 | 2015-02-12
C1428 | 1763 | 2015-07-15 | MS Power Projects Ltd | Fairwind Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fairwind Farm Lower Dunton Road Laindon Essex | Essex | Eastern | England |  | 565725 | 187731 | Thurrock Council | 13/00543/FUL | [5 empty] | 2013-06-10 | [6 empty] | 2013-11-25 |  |  |  |  | 2014-06-23 | 2014-09-30
C1451 | 1764 | 2015-06-16 | juwi Renewable Energies | Redlands Farm | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | N/O Butleigh Drove,, Butleigh Drove, Pedwell, Bridgwater, Somerset | Somerset | South West | England | TA7 | 342751 | 135160 | Mendip District Council | 2013/1189 | [5 empty] | 2013-06-20 | [6 empty] | 2013-11-11 |  |  |  |  | 2014-09-01 | 2015-02-18
C1595 | 1765 | 2014-11-27 | Sunsave | Fenton Home Farm | Solar Photovoltaics |  |  | 31.28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fenton Home Farm, Crundale, Haverfordwest | Dyfed | Wales | Wales | SA62 4PY | 198922 | 217459 | Pembrokeshire County Council | 13/0278/PA | [5 empty] | 2013-07-02 | [6 empty] | 2013-12-05 |  |  |  | 2018-12-05 | 2014-06-04 | 2014-09-12
C1814 | 1766 | 2015-03-05 | Octopus Investment | Abbots Ripton Solar Farm | Solar Photovoltaics |  |  | 24.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Railway Line And South Of Brooklands Farm, Rectory Lane, Abbots, Ripton | Cambridgeshire | Eastern | England |  | 522746 | 277158 | Huntingdonshire District Council | 1301218FUL | [5 empty] | 2013-08-05 | [6 empty] | 2013-10-28 | [5 empty] | 2014-03-27
C2164 | 1767 | 2014-12-17 | Solar Century | South Lees Farm | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent South Lees Farm, Lower Road, Minster On Sea, Sheerness, Kent | Kent | South East | England | ME12 3SW | 595301 | 170696 | Swale Borough Council | SW/13/1202 | [5 empty] | 2013-10-04 | [6 empty] | 2014-01-22 |  |  |  |  | 2014-02-14 | 2014-06-22
C2214 | 1768 | 2015-03-17 | Bluefield Solar Income Fund | Southwick Estate | Solar Photovoltaics |  |  | 48 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Proposed Solar Park Southwick Estate, Belney Lane, Southwick, Hampshire | Hampshire | South East | England | PO17 6ET | 464724 | 109837 | Winchester City Council | 13/02304/FUL | [5 empty] | 2013-10-16 | [6 empty] | 2013-12-13 |  |  |  |  | 2014-12-10 | 2015-03-10
C2286 | 1769 | 2015-05-13 | Lightsource Renewable Energy | Waterloo solar park | Solar Photovoltaics |  |  | 14.55 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West of Fernbury Farm, Tempsford Road, Everton | Bedfordshire | Eastern | England | SG19 2JW | 519401 | 251547 | Central Bedfordshire Council | CB/13/03549/FULL | [5 empty] | 2013-10-25 | [6 empty] | 2014-04-30 |  |  |  |  | 2015-01-05 | 2015-03-19
C2338 | 1770 | 2014-06-20 | Solar Power South | Deppers Bridge | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land At Deppers Bridge Southam | Warwickshire | West Midlands | England |  | 439797 | 259354 | Stratford on Avon District Council | 13/02689/FUL | [5 empty] | 2013-10-18 |  | 2014-04-09
C2449 | 1771 | 2014-06-16 | ROC Energy Ltd | Egmanton Solar Farm | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Between Weston Road And The A1 Egmanton Nottinghamshire | Nottinghamshire | East Midlands | England |  | 475706 | 367774 | Newark and Sherwood District Council | 13/01422/FULM | [5 empty] | 2013-12-02 |  | 2014-05-15
C2589 | 1772 | 2015-03-17 | Lark Energy | Ketton solar farm - phase 2 | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | North Field, Off Pit Lane, Ketton, Stamford, Lincolnshire | Leicestershire | East Midlands | England | PE9 3SZ | 497610 | 306126 | Rutland County Council | 2014/0025/FUL | [5 empty] | 2014-01-09 | [6 empty] | 2014-04-25 |  |  |  |  | 2014-08-01 | 2015-01-10
C2638 | 1773 | 2015-12-02 | Mynthurst Farms | Mynthurst Farm | Solar Photovoltaics |  |  | 13.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Mynthurst Farm, Mynthurst, Leigh, Surrey | Surrey | South East | England | RH2 8QD | 522290 | 145009 | Mole Valley District Council | MO/2014/0061 | APP/C3620/W/14/3000674 |  |  |  |  | 2014-01-13 |  | 2014-06-09 | 2014-12-10 |  | 2015-11-24
C2688 | 1774 | 2015-11-03 | Anesco | Oak Cottage | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South of Oak Cottage, Wiston, Haverfordwest, Pembrokeshire, SA62 4PR | Dyfed | Wales | Wales | SA62 4PR | 202911 | 217724 | Pembrokeshire County Council | 13/0916/PA | [5 empty] | 2014-01-28 | [6 empty] | 2014-06-13 |  |  |  |  | 2015-07-01 | 2015-08-21
IF1013 | 1775 | 2014-07-03 | BNRG Renewables | Sycamore Farm | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Millbank Lane Old Romney Kent TN29 9SY | Kent | South East | England |  | 601943 | 125385 | Shepway District Council | Y12/0918/SH | [5 empty] | 2012-10-08 | [6 empty] | 2013-01-17 |  |  |  |  | 2014-02-11 | 2014-05-30
IF1072 | 1776 | 2015-09-30 | KS SPV21 Ltd | North Wayton Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Landulph Saltash Cornwall | Cornwall | South West | England | PL12 6QQ | 242671 | 62588 | Cornwall Council | PA12/09275 | [5 empty] | 2012-10-09 | [6 empty] | 2013-04-09 | [5 empty] | 2014-03-31
IF1359 | 1777 | 2016-08-18 | Lightsource BP | South Creake Solar Farm | Solar Photovoltaics |  |  | 26 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Leicester Square Farm Leicester Road South Creake Norfolk | Norfolk | Eastern | England | NR21 9NX | 586656 | 332974 | King's Lynn and West Norfolk Borough Council | 13/00336/FM | [5 empty] | 2013-03-05 | [6 empty] | 2013-06-04 |  |  |  |  | 2015-11-16 | 2016-03-11
IF1369 | 1778 | 2014-07-03 | Hive Energy | Valley Farm | Solar Photovoltaics |  |  | 16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Cox Hall Road, Tattingstone | Suffolk | Eastern | England |  | 614665 | 237965 | Babergh District Council | B/12/01279 | [5 empty] | 2013-02-18 |  | 2013-06-12 |  |  | 2014-06-02
C1193 | 1781 | 2017-05-02 | Rockfire Capital | Pen Y Cae solar farm | Solar Photovoltaics |  |  | 6.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pen Y Cae, Saron, Ammanford, Dyfed | Dyfed | Wales | Wales | SA18 3BJ | 260143 | 211806 | Carmarthenshire County Council | E/28086 | [5 empty] | 2013-04-18 | [6 empty] | 2013-09-19 |  |  |  |  | 2014-11-03 | 2015-03-26
C2749 | 1782 | 2014-06-25 | Lumicity | East Hill Strips - resubmission | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land At East Hill Strips Ridgeway Sidbury | Devon | South West | England |  | 311687 | 93382 | East Devon District Council | 14/0430/MFUL | [5 empty] | 2014-02-21 |  | 2014-05-30
C2754 | 1783 | 2016-06-21 | Elgin Energy EsCo | Rose And Crown Farm | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rose And Crown Farm Walpole Bank Walpole St Andrew Wisbech Norfolk PE14 7JB | Norfolk | Eastern | England |  | 548479 | 314975 | King's Lynn and West Norfolk Borough Council | 14/00283/FM | APP/V2635/W/14/3001281 |  |  |  |  | 2014-02-25 |  | 2014-06-12 | 2015-02-16 |  |  | 2015-09-11 | 2015-09-11 |  |  |  | 2018-09-11 | 2015-11-26 | 2016-03-18
C2803 | 1784 | 2017-07-04 | NESF (formerly A C Crocker Properties Ltd) | Wickfield Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Wickfield Farm Royal Wootton Bassett Swindon | Wiltshire | South West | England | SN4 8QR | 409055 | 182523 | Wiltshire Council | 14/02508/FUL | [5 empty] | 2014-03-06 | [6 empty] | 2014-06-05 |  |  |  |  | 2017-01-02 | 2017-03-21
C2805 | 1785 | 2015-06-15 | Green Switch Solutions | Rookery Farm | Solar Photovoltaics |  |  | 3.76 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land between Bilsham and Flansham North of A259 Flansham | West Sussex | South East | England | PO22 8NN | 497086 | 101635 | Arun District Council | Y/14/14/ | [5 empty] | 2014-03-07 | [6 empty] | 2014-05-29 |  |  |  |  | 2015-03-01 | 2015-03-30
C2811 | 1786 | 2014-06-26 | Good Energy Generation | Creathorne Farm - Solar Farm - extension | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Creathorne Farm Poundstock Bude Cornwall | Cornwall | South West | England | EX23 0NE | 221230 | 102488 | Cornwall Council | PA14/01919 | [5 empty] | 2014-03-05 | 2014-06-04
C2816 | 1787 | 2016-07-01 | Private Developer | Seaview Farm | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Seaview Farm, Pyle Road, Porthcawl | Mid Glamorgan | Wales | Wales | CF36 5TB | 282372 | 178754 | Bridgend County Borough Council | P/14/148/FUL | [5 empty] | 2014-03-05 | [6 empty] | 2014-06-11 |  |  |  | 2017-06-11 | 2016-05-01 | 2016-03-30
C2823 | 1788 | 2014-12-17 | Chelveston Renewable Energy | Chelveston Airfield - extension | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chelveston Airfield Kimbolton Road Chelveston Northamptonshire | Bedfordshire | Eastern | England |  | 501045 | 268135 | Bedford Borough Council | 14/00469/MAF | [5 empty] | 2014-03-10 | [6 empty] | 2014-06-02 |  |  |  |  | 2014-06-30 | 2014-09-30
C2868 | 1789 | 2017-05-03 | Lightsource Renewable Energy | Knockcairn Road | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | 20 Knockcairn Road, Crumlin | Co. Antrim | Northern Ireland | Northern Ireland | BT29 4UE | 131013 | 531722 | Northern Ireland Planning Service | T/2014/0066/F | [5 empty] | 2014-02-26 | [6 empty] | 2014-06-26 |  |  |  | 2019-06-26 | 2016-11-21 | 2017-03-15
C3043 | 1800 | 2016-05-04 | Green Switch Solutions | Britannia Crest | Solar Photovoltaics |  |  | 2.63 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land Adj To Britanniacrest, 26 Reigate Road, Hookwood, Horley | Surrey | South East | England | RH6 0HJ | 525944 | 144597 | Reigate and Banstead Borough Council | 15/01424/F | APP/L3625/W/16/3142233 |  |  |  |  | 2015-06-24 |  | 2015-11-27 | 2016-01-20 |  | 2016-04-14
C3048 | 1802 | 2015-08-28 | Associated British Ports (ABP) | Port of Barry | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Atlantic Way, Port of Barry, Barry | South Glamorgan | Wales | Wales |  | 312810 | 167042 | Vale of Glamorgan Council | 2014/01089/FUL | [5 empty] | 2014-09-18 | [6 empty] | 2014-12-19 |  |  |  | 2019-12-19
C3073 | 1804 | 2018-07-05 | NESF (formerly Green Energy Networks) | Huddlesford Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Huddlesford House, Huddlesford Lane, Huddlesford, Lichfield | Staffordshire | West Midlands | England | WS13 8PY | 415272 | 309606 | Lichfield District Council | 14/00513/FULM | [5 empty] | 2014-06-04 | [6 empty] | 2014-10-20 |  |  |  | 2017-10-20 | 2016-01-04 | 2016-04-15
C3074 | 1805 | 2017-05-04 | RenPlan Consulting | Potbridge Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Potbridge Farm, Potbridge, Odiham Hook | Hampshire | South East | England | RG29 1JN | 474827 | 153523 | Hart District Council | 14/01069/MAJOR | APP/N1730/W/15/3132803 |  |  |  |  | 2014-05-22 |  | 2015-02-24 |  |  | 2016-03-22
C3078 | 1806 | 2018-07-05 | NESF (formerly Green Energy Networks) | Park Lane | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of The Cottage, Park Lane, Huddlesford, Lichfield, Staffordshire | Staffordshire | West Midlands | England | WS13 8QB | 415990 | 309615 | Lichfield District Council | 14/00518/FULM | [5 empty] | 2014-06-04 | [6 empty] | 2014-11-24 |  |  |  | 2017-11-24 | 2015-11-16 | 2016-04-04
C3106 | 1807 | 2015-10-29 | Green Switch Developments | High Trees Farm | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | High Trees Farm, Proposed Solar Farm, North West Of Tasley Bridgnorth, Shropshire | Shropshire | West Midlands | England | WV16 4RE | 369563 | 294380 | Shropshire Council | 14/02386/FUL | APP/L3245/W/15/3032646 |  |  |  |  | 2014-05-30 |  | 2015-01-27 | 2015-07-09 |  | 2015-10-15
C3112 | 1808 | 2015-10-05 | Pencefnarda Solar | Pencefnarda Uchaf Farm | Solar Photovoltaics |  |  | 3.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Pencefnarda Uchaf Farm, Pencefnarda Road, Gorseinon, Swansea, West Glamorgan | West Glamorgan | Wales | Wales | SA4 4FY | 258281 | 200175 | City and County Council of Swansea | 2014/0761 | APP/B6855/A/15/3005095 |  |  |  |  | 2014-06-03 |  | 2015-02-09 | 2015-05-22 |  | 2015-09-29
C3121 | 1811 | 2017-10-31 | BE Renewables | Gypsom Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North West of Sileby Road, Barrow, Leicestershire | Leicestershire | East Midlands | England | LE12 8GB | 459770 | 316156 | Charnwood Borough Council | P/14/2359/2 | [5 empty] | 2015-01-05 | [6 empty] | 2015-09-22 |  |  |  | 2018-09-22 | 2017-01-31 | 2017-03-31
C3134 | 1812 | 2014-07-07 | Devon Waste Management | Deep Moor Waste Management Facility - Solar Park | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Devon Waste Management Ltd, Deepmoor Landfill Site, High Bullen, Torrington | Devon | South West | England | EX38 7JA | 253005 | 120813 | Devon County Council | DCC/3664/2014 | [5 empty] | 2014-05-19 | 2015-12-21
AA273 | 1813 | 2015-03-17 | Munich RE | Polmaugan Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Polmaugan Farm Trebyan Lostwithiel Cornwall | Cornwall | South West | England | PL22 0LS | 210935 | 62242 | Cornwall Council | PA10/05105 | [5 empty] | 2010-08-18 | [6 empty] | 2010-11-17 | [5 empty] | 2014-07-03
AA284 | 1814 | 2016-07-28 | The Royal Bath and West of England Society | The Royal Bath & West Showground Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Shepton Mallet | Somerset | South West | England | BA4 6QN | 363500 | 139046 | Mendip District Council | 2011/0440 | [5 empty] | 2011-03-09 | [6 empty] | 2011-04-20
AA381 | 1815 | 2017-12-20 | NextEnergy Solar Fund | Land at Gilley's Mill Dam | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | New Road, Roche, Cornwall | Cornwall | South West | England |  | 197848 | 58800 | Cornwall Council | PA11/03436 | [5 empty] | 2011-05-18 | [6 empty] | 2011-08-05 |  |  |  |  | 2015-12-21 | 2016-03-21
AA666 | 1816 | 2015-09-29 | Laurence Associates | East Lenham Solar Farm | Solar Photovoltaics |  |  | 6.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | East Lenham Farm, East Lenham Road, Lenham, Maidstone, Kent, | Kent | South East | England | ME17 2DP | 589450 | 151072 | Maidstone Borough Council | 12/0013 | [5 empty] | 2012-01-20 | [6 empty] | 2012-11-01 |  |  |  |  | 2014-02-01 | 2014-03-30
AA840 | 1817 | 2018-09-04 | Foresight | Steventon Solar Park | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to West of Steventon Field, Steventon, Abingdon, Oxon | Oxfordshire | South East | England |  | 444299 | 192928 | Vale of White Horse District Council | P12/V1571/FUL | [5 empty] | 2012-07-18 | [6 empty] | 2012-10-17 |  |  |  |  | 2014-03-15 | 2014-06-19
B0868 | 1818 | 2015-01-13 | Lightsource Renewable Energy | Westwood Farm Solar Park | Solar Photovoltaics |  |  | 5.1 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ollerton Road, Tuxford, Newark, Nottinghamshire | Nottinghamshire | East Midlands | England | NG22 0PF | 471765 | 370062 | Bassetlaw District Council | 13/01182/FUL | [5 empty] | 2013-10-18 | [6 empty] | 2013-12-24 |  |  |  |  | 2014-09-27 | 2015-01-12
C1368 | 1820 | 2014-07-23 |  | Meadow Farm solar park | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | NW of Main Road Brookville Norfolk | Norfolk | Eastern | England |  | 572611 | 296975 | King's Lynn and West Norfolk Borough Council | 13/00796/FM | [5 empty] | 2013-05-31 | [6 empty] | 2013-07-30 |  |  |  |  | 2013-11-30 | 2014-03-31
C1479 | 1821 | 2017-09-18 | Cassidy & Ashton Group Ltd | Funtley Refuse Tip | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Funtley Refuse Tip, Titchfield Lane, Wickham, Fareham, Hampshire, PO15 6DY | Hampshire | South East | England | PO15 6DY | 454932 | 109261 | Winchester City Council | 13/01247/FUL | [5 empty] | 2013-06-05 | [6 empty] | 2013-08-28 |  |  |  | 2016-08-28
C1497 | 1822 | 2019-11-21 | Elveden Farms Ltd | Icklingham Solar Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land west of Avenue Farm Lakenheath Road (B1112) Icklingham | Suffolk | Eastern | England |  | 575573 | 274729 | Forest Heath District Council | F/2013/0258/ESF | [5 empty] | 2013-05-16 | [6 empty] | 2013-08-07 |  |  |  | 2017-08-07
C1596 | 1823 | 2014-10-29 | Lightsource Renewable Energy | Sutton Mawr Farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Sutton Mawr Farm, Barry, South Glamorgan | South Glamorgan | Wales | Wales | CF62 3AA | 307823 | 169675 | Vale of Glamorgan Council | 2013/00617/FUL | [5 empty] | 2013-07-02 | [6 empty] | 2014-01-17 | [5 empty] | 2014-03-04
C1598 | 1824 | 2017-08-23 | Good Energy Generation | Carloggas Farm Solar Park | Solar Photovoltaics |  |  | 8.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Carloggas Farm St. Stephen St. Austell | Cornwall | South West | England | PL26 7RA | 195504 | 54111 | Cornwall Council | PA13/06288 | [5 empty] | 2013-07-18 | [6 empty] | 2013-10-29 |  |  |  |  | 2014-10-01 | 2015-03-17
C1603 | 1825 | 2014-07-15 | Lightsource Renewable Energy | Jackletts Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | S/O Jackletts Farm, Slough Road, Danbury, Chelmsford, Essex, CM3 4LX | Essex | Eastern | England |  | 580030 | 202417 | Chelmsford City Council | 13/00926/FUL | 13/00047/REFUSE |  |  |  |  | 2013-07-09 |  | 2013-10-08
C1651 | 1826 | 2016-07-01 | juwi Renewable Energies | Lincoln Farm | Solar Photovoltaics |  |  | 11.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lincoln Farm, Wainfleet Road, Irby In The Marsh, Skegness | Lincolnshire | East Midlands | England | PE24 5AT | 547402 | 362881 | East Lindsey District Council | S/020/02242/13 | [5 empty] | 2014-03-07 | [6 empty] | 2014-10-20 |  |  |  | 2017-10-20 | 2016-05-01 | 2016-03-25
C1693 | 1827 | 2015-06-16 | Next Energy Solar Fund | Llwyn Du Solar Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Llwyn Ddu, Blaenporth, Cardigan | Dyfed | Wales | Wales |  | 227279 | 248567 | Ceredigion County Council | A130555 | [5 empty] | 2013-07-08 | [6 empty] | 2014-01-20 |  |  |  |  | 2014-09-01 | 2015-02-26
AA963 | 1828 | 2015-02-03 | Lumicity | West Hill Farm (solar) | Solar Photovoltaics |  |  | 7.335 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | ILFRACOMBE DEVON | Devon | South West | England | EX34 8NF | 250572 | 140713 | North Devon District Council | 54388 | [5 empty] | 2012-08-06 | [6 empty] | 2012-11-30 | [5 empty] | 2014-07-29
C2378 | 1829 | 2017-08-16 | Lightsource Renewable Energy | Tye Green Farm | Solar Photovoltaics |  |  | 14.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Tye Green Farm Elsenham Elsenham Bishops Stortford Hertfordshire | Essex | Eastern | England |  | 554783 | 224944 | Uttlesford District Council | UTT/14/1916/FUL | [5 empty] | 2014-07-04 | 2014-09-25
C2405 | 1830 | 2014-11-23 | Push Energy | Mill Farm | Solar Photovoltaics |  |  | 9.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Mill Farm, Mentley Lane, Great Munden, Ware, Hertfordshire | Hertfordshire | Eastern | England | SG11 1JR | 534472 | 225009 | East Hertfordshire District Council | 3/14/1058/FP | [5 empty] | 2014-06-16 |  | 2014-11-12
C2467 | 1831 | 2014-07-29 | COOMBE BISSETT PV PARK LIMITED | Bake Farm | Solar Photovoltaics |  |  | 16.07 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land to the west of Bake Farm Buildings Salisbury Road Coombe Bissett Salisbury | Wiltshire | South West | England | SP5 4JT | 411771 | 127679 | Wiltshire Council | 13/06336/FUL | [5 empty] | 2013-12-05 | 2014-06-18
C2604 | 1832 | 2015-03-17 | Bluefield Solar | Elms Farm | Solar Photovoltaics |  |  | 29 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Elms Farm Grove | Oxfordshire | South East | England |  | 441630 | 189754 | Vale of White Horse District Council | P14/V1135/FUL | [5 empty] | 2014-05-28 | [6 empty] | 2014-08-28 |  |  |  | 2017-08-28 | 2014-12-01 | 2015-03-16
C2605 | 1833 | 2015-09-30 | Kronos Solar | Chadwicks Farms | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land near Chadwick's Farm, Garford, Abingdon | Oxfordshire | South East | England | OX13 5PH | 441459 | 194821 | Vale of White Horse District Council | P14/V0552/FUL | APP/V3120/W/14/2223429 |  |  |  |  | 2014-03-26 |  | 2014-06-25 | 2014-08-18 |  | 2014-12-17
C2612 | 1834 | 2015-03-03 | Good Energy Generation | Rock Farm / Goldborough Farm (Rookwood) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Goldborough Farm Goldborough Broad Town Swindon | Wiltshire | South West | England | SN4 7QX | 408374 | 180086 | Wiltshire Council | 13/07071/FUL | [5 empty] | 2013-12-20 | [6 empty] | 2014-07-07 |  |  |  |  | 2015-01-01 | 2015-03-02
C2693 | 1835 | 2015-04-01 | Inazin Energy Limited / Low Carbon | Great Wilbraham Solar Farm | Solar Photovoltaics |  |  | 38.1 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mill Road, Great Wilbraham, Cambridge | Cambridgeshire | Eastern | England | CB21 5JW | 555282 | 256460 | South Cambridgeshire District Council | S/2763/13/FL | [5 empty] | 2014-01-14 | [6 empty] | 2014-07-28 |  |  |  |  | 2014-09-19 | 2015-03-31
C2723 | 1836 | 2015-05-14 | Lightsource Renewable Energy | Somerton Door Farm | Solar Photovoltaics |  |  | 8.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Somerton Door Farm, Somerton Door Drove, Somerton, Somerset | Somerset | South West | England | TA11 6JA | 347036 | 130048 | South Somerset District Council | 14/00876/FUL | [5 empty] | 2014-03-05 | [6 empty] | 2014-06-02 |  |  |  |  | 2014-08-18 | 2015-03-01
C3160 | 1838 | 2017-07-19 | HB & CH Barker Ltd | Barugh Farm | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Barugh Farm, Hutton Conyers, Ripon | North Yorkshire | Yorkshire and Humber | England | HG4 5NA | 433028 | 475596 | Harrogate Borough Council | 14/04525/FULMAJ | [5 empty] | 2014-11-01 | [6 empty] | 2015-01-26 |  |  |  | 2018-01-26 | 2015-12-01 | 2016-01-15
C3161 | 1839 | 2015-01-21 | European Energy Photovoltaics | Woodhouse Farm | Solar Photovoltaics |  |  | 11 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Wood House Farm, Ferryboat Lane, North Hylton, Sunderland | Tyne and Wear | North East | England | SR5 3HP | 434613 | 556860 | Sunderland City Council | 14/02132/FUL | [5 empty] | 2014-10-10 |  | 2015-01-15
C3162 | 1840 | 2016-07-01 | INRG | Lains Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Lains Farm, Lains Paddock, Quarley, Andover, Hampshire | Hampshire | South East | England | SP11 8PU | 427233 | 144461 | Test Valley Borough Council | 14/03017/FULLN | [5 empty] | 2014-12-05 | [6 empty] | 2015-07-17 |  |  |  | 2018-07-17 | 2016-05-01 | 2016-03-24
C3164 | 1842 | 2016-07-14 | Conergy | Great Seabrook Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Great Seabrook Farm, Seabrook Farm Lane, Cheddington | Buckinghamshire | South East | England | LU7 9AA | 493192 | 217705 | Aylesbury Vale District Council | 14/01572/APP | [5 empty] | 2014-06-10 | [6 empty] | 2014-11-13 |  |  |  | 2017-11-13 | 2015-05-15 | 2015-09-28
C3167 | 1843 | 2016-03-15 | Anesco | Cotgrave solar farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Blackberry Farm Main Road Cotgrave Nottinghamshire | Nottinghamshire | East Midlands | England |  | 463974 | 336042 | Rushcliffe Borough Council | 14/01221/FUL | [5 empty] | 2014-06-23 | [6 empty] | 2015-01-28 |  |  |  | 2018-01-28 | 2015-05-15 | 2015-07-15
C3169 | 1844 | 2016-02-05 | Hive Energy | Gerard Hall Solar Farm | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land North West And South West Of Gerard Hall Prescot Road Aughton Ormskirk Lancashire L39 6TA | Lancashire | North West | England |  | 339859 | 403536 | West Lancashire Borough Council | 2014/0601/FUL | APP/P2365/W/15/3002667 |  |  |  |  | 2014-06-11 |  | 2014-10-17 | 2015-02-18 |  | 2016-01-18
C3170 | 1845 | 2016-10-25 | Bowler Energy | Colleen Farm | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Colleen Farm, Blackawton, Totnes, | Devon | South West | England | TQ9 7DW | 279736 | 52872 | South Hams District Council | 22/1610/14/F | [5 empty] | 2014-06-25 | [6 empty] | 2015-03-26 |  |  |  | 2018-03-26
C3172 | 1846 | 2015-08-24 | NextEnergy | Parkview solar park | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at SX765, 687, east of Parkfield Farm, Ashburton | Devon | South West | England |  | 276015 | 68671 | South Hams District Council | 50/1623/14/F | [5 empty] | 2014-06-26 | [6 empty] | 2014-10-28 |  |  |  | 2017-10-28 | 2015-02-01 | 2015-03-31
C3174 | 1848 | 2016-03-16 | British Solar Renewables | Overton | Solar Photovoltaics |  |  | 3.95 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjoining Lordsfield Plantation, The Lynch, Overton, Hampshire | Hampshire | South East | England |  | 450772 | 150312 | Basingstoke and Deane Borough Council | 14/01777/FUL | [5 empty] | 2014-06-17 | [6 empty] | 2014-12-18 |  |  |  | 2017-12-18 | 2015-10-01 | 2015-12-15
C3175 | 1849 | 2014-11-07 | Pylle Solar | Lower Easton Farm | Solar Photovoltaics |  |  | 13.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Off Easton Lane, Pylle, Somerset | Somerset | South West | England | BA4 6SY | 362355 | 138696 | Mendip District Council | 2014/1174/FUL | [5 empty] | 2014-06-20 |  | 2014-10-16
C3177 | 1850 | 2016-03-22 | INRG Solar | Lower Basset Down Farm | Solar Photovoltaics |  |  | 10.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Lower Basset Down Farm Hay Lane Bassett Down Swindon | Wiltshire | South West | England | SN4 9QP | 414571 | 180637 | Swindon Borough Council | S/14/0899 | [5 empty] | 2014-06-20 | [6 empty] | 2014-12-03 |  |  |  | 2017-12-03 | 2015-11-20 | 2016-03-18
C3181 | 1853 | 2014-11-06 | JBM Solutions Limited | Stonebrig Lane | Solar Photovoltaics |  |  | 18.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Stonebrig Lane Hardwick Road Little Harrowden Wellingborough Northamptonshire | Northamptonshire | East Midlands | England |  | 485502 | 270555 | Wellingborough Borough Council | WP/14/00359/FUL | [5 empty] | 2014-06-04 |  | 2014-10-29
C3199 | 1862 | 2017-05-26 | Lightsource Renewable Energy | Morfa Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Morfa Farm, Morfa Lane, Llantwit Major, South Glamorgan | Vale of Glamorgan | Wales | Wales | CF61 2YT | 295957 | 170244 | Vale of Glamorgan Council | 2015/00782/FUL | [5 empty] | 2015-07-15 | [6 empty] | 2015-11-20 |  |  |  | 2020-11-20 | 2016-10-18 | 2016-12-19
C3200 | 1863 | 2018-09-17 | Lark Energy | Lockington Solar Park | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At M1 Junction 24, Lockington And Hemington, Leicestershire | Leicestershire | East Midlands | England |  | 447160 | 330389 | North West Leicestershire District Council | 14/00488/FULM | [5 empty] | 2014-06-17 | [6 empty] | 2015-01-14 |  |  |  | 2018-01-14
IF1050 | 1864 | 2016-04-14 | British Solar Renewables | Barton Close Farm | Solar Photovoltaics |  |  | 5.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Georgeham, Braunton, Devon | Devon | South West | England | EX33 1HX | 248058 | 141648 | North Devon District Council | 54722 | A/13/2199207/NWF |  |  |  |  | 2012-10-04 |  | 2013-03-18 |  |  |  | 2014-04-15 | 2014-04-15 |  |  |  |  | 2015-06-10 | 2016-02-15
IF1155 | 1865 | 2015-05-28 | Lightsource Renewable Energy | Wiggin Hill Solar Farm - Phase 1 | Solar Photovoltaics |  |  | 6.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Wiggin Hill Old Ramsey Road St Ives | Cambridgeshire | Eastern | England | PE27 3L | 531033 | 274808 | Huntingdonshire District Council | 1201911FUL | [5 empty] | 2012-11-20 | [6 empty] | 2013-02-19 |  |  |  |  | 2014-11-14 | 2015-03-14
IF1161 | 1866 | 2017-07-18 | Higher Hill Farm Partnership | Rampisham Down Transmitting Station | Solar Photovoltaics |  |  | 24 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Rampisham, Dorchester, Dorset | Dorset | South West | England | DT2 0HS | 354819 | 101221 | West Dorset District Council | 1/D/12/001664 |  | APP/F1230/V/15/3129159 | Call-In |  |  | 2012-12-03 | 2017-02-20
IF1166 | 1867 | 2015-07-01 | Peterborough City Council | Morris Fen (PV) | Solar Photovoltaics |  |  | 27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The East And West Of Black Drove, Thorney, Peterborough | Cambridgeshire | Eastern | England |  | 528600 | 306400 | Peterborough City Council | 12/01905/R3FUL | [5 empty] | 2012-12-18 | 2015-06-09
IF1167 | 1868 | 2015-07-01 | Peterborough City Council | Farms of Newborough | Solar Photovoltaics |  |  | 49 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The East Of Peterborough Road Crowland Peterborough | Cambridgeshire | Eastern | England |  | 523900 | 306500 | Peterborough City Council | 12/01906/R3FUL | [5 empty] | 2012-12-18 | 2015-06-09
IF1169 | 1869 | 2014-07-28 | Peterborough City Council | America Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The South Of America Farm Oxney Road Peterborough | Cambridgeshire | Eastern | England |  | 523600 | 300300 | Peterborough City Council | 12/01904/R3FUL | [5 empty] | 2012-12-18 | 2015-12-11
IF1210 | 1870 | 2015-04-15 | Lark Energy | Thornham Solar Farm (Resubmission) | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Lyng Farm Burnham Road Thornham Hunstanton Norfolk | Norfolk | Eastern | England | PE36 5LH | 573903 | 340478 | King's Lynn and West Norfolk Borough Council | 13/00049/FM | [5 empty] | 2013-01-14 | [6 empty] | 2013-04-15
IF1218 | 1871 | 2014-08-05 | juwi Renewable Energies | Keens Farm | Solar Photovoltaics |  |  | 5.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Morebath, Tiverton, Devon | Devon | South West | England | EX16 9AF | 296710 | 124577 | Mid Devon District Council | 12/01522/MFUL | 13/00015/WR |  |  |  |  | 2012-11-07 |  | 2013-02-06 |  |  | 2014-07-08
IF1267 | 1872 | 2015-06-04 | Primrose Solar | Wilton Farm (pv) | Solar Photovoltaics |  |  | 9.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Wilton farm, Trerulefoot, Saltash, Cornwall | Cornwall | South West | England | PL12 5BX | 231050 | 58450 | Cornwall Council | PA12/11941 | [5 empty] | 2013-01-09 |  | 2013-05-02 |  |  |  | 2014-01-30 | 2014-01-30 |  |  |  |  | 2015-01-01 | 2015-06-01
IF1299 | 1873 | 2015-09-30 | Kronos Solar | Eveley Farm | Solar Photovoltaics |  |  | 49 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Stevens Drove, Houghton, Stockbridge, Hampshire | Hampshire | South East | England | SO20 6SA | 432987 | 134363 | Test Valley Borough Council | 13/02735/FULLS | APP/C1760/A/14/2228317 |  |  |  |  | 2013-12-11 |  | 2014-08-15 | 2014-11-26 | 2015-07-01
IF1320 | 1874 | 2015-02-03 | British Solar Renewables | Canada Farm | Solar Photovoltaics |  |  | 8.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Winterborne Stickland, Blandford Forum, Dorset, DT11 9AD | Dorset | South West | England |  | 384027 | 104272 | North Dorset District Council | 2/2013/0770/PLNG | [5 empty] | 2013-07-08 | [6 empty] | 2014-03-10 |  |  |  |  | 2014-07-23 | 2014-12-02
IF1323 | 1875 | 2014-11-26 | TGC Renewables | Hoback Farm | Solar Photovoltaics |  |  | 13.08 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | 81 Cambridge Road, Wimpole, Royston, Cambridgeshire | Cambridgeshire | Eastern | England | SG8 5QB | 535036 | 248586 | South Cambridgeshire District Council | S/0155/13/FL | [5 empty] | 2013-02-14 | [6 empty] | 2013-07-15 |  |  |  |  | 2014-08-01 | 2014-11-01
IF1325 | 1876 | 2017-02-02 | Innogy (previously BELECTRIC Solar) | The Rainbows Solar Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The North Of The Byre, Badsey Lane, Willersey, Gloucestershire | Gloucestershire | South West | England |  | 409627 | 241319 | Cotswold District Council | 13/00578/FUL | [5 empty] | 2013-02-12 |  | 2013-03-25 |  |  |  | 2013-06-13 | 2013-06-13 | [5 empty] | 2014-03-31
B1067 | 1877 | 2019-08-14 | Private Developer | Tylerfedwen Farm Solar Park | Solar Photovoltaics |  |  | 13.28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Tylerfedwen Farm, Cwmafan, Port Talbot, West Glamorgan, SA12 9YA | West Glamorgan | Wales | Wales | SA12 9YA | 276557 | 193490 | Neath Port Talbot County Borough Council | P2013/1087 | [5 empty] | 2013-12-19 | [6 empty] | 2014-07-22 |  |  |  | 2019-07-22
B1178 | 1878 | 2018-07-04 | NextEnergy Capital | Salcey Solar Farm | Solar Photovoltaics |  |  | 4.95 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bulls Head Farm, Eakley Lanes, Stoke Goldington, Newport Pagnell, Buckinghamshire | Buckinghamshire | South East | England | MK16 8LP | 485184 | 250544 | Milton Keynes Council | 13/02504/FUL | [5 empty] | 2013-12-02 | [6 empty] | 2014-03-07 |  |  |  |  | 2014-06-01 | 2014-09-25
B1373 | 1882 | 2020-06-16 | Strathcaro And Careston Estates | Ballochy Solar Farm | Solar Photovoltaics |  |  | 19 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Field 400M SE Of East Ballochy East Ballochy Montrose | Tayside | Scotland | Scotland |  | 366850 | 762000 | Angus Council | 14/00549/FULL | [5 empty] | 2014-07-04 | [6 empty] | 2014-12-11 |  |  |  | 2017-12-11
B1387 | 1883 | 2019-06-12 | Rockspring Hanover Property Unit Trust | Westcott Venture Park Solar Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Westcott Venture Park Site Office Building 214 Westcott Buckinghamshire | Buckinghamshire | South East | England | HP18 0XB | 471748 | 216610 | Aylesbury Vale District Council | 14/01909/APP | [5 empty] | 2014-07-03 | [6 empty] | 2017-05-11 |  |  |  | 2020-05-11
B1396 | 1884 | 2017-08-16 | Mosscliff Environmental | Hillsmoor Solar Farm | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hillsmoor, Holsworthy Road, Hatherleigh, Okehampton, Devon | Devon | South West | England | EX20 3LE | 253079 | 103374 | West Devon Borough Council | 00765/2014 | [5 empty] | 2014-06-27 | [6 empty] | 2014-10-31 |  |  |  | 2017-10-31 | 2017-05-15 | 2017-07-27
B1402 | 1885 | 2016-11-28 | Trina Solar | Desford Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent Charnwood Poultry Farm Desford Road Desford Leicester Leicestershire | Leicestershire | East Midlands | England | LE9 2BF | 450270 | 304950 | Hinckley and Bosworth Borough Council | 14/00654/FUL | [5 empty] | 2014-07-07 | [6 empty] | 2014-12-10 |  |  |  | 2017-12-10 | 2015-11-15 | 2016-03-23
B1413 | 1886 | 2015-06-19 | Wessex Solar Energy | Iwood Lane Solar Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fields off Stock Lane and Iwood Lane, near Congresbury | Avon | South West | England | BS40 5AA | 345000 | 162550 | North Somerset Council | 13/P/2382/F | [5 empty] | 2013-12-12 | [6 empty] | 2014-05-14 | [5 empty] | 2014-12-19
B1422 | 1887 | 2014-12-05 | Iota Solar (OPDE) | Catsfield Solar Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Catsfield Road - Land to the East of, Catsfield | East Sussex | South East | England | TN33 9BB | 571750 | 112773 | Rother District Council | RR/2014/1664/P | [5 empty] | 2014-07-24 |  | 2014-11-25
B1427 | 1889 | 2016-03-04 | Anesco | Playters Solar Farm | Solar Photovoltaics |  |  | 8.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Playters New Farm, Church Road, Ellough, Beccles | Suffolk | Eastern | England | NR34 7TN | 643920 | 288420 | Waveney District Council | DC/14/1169/FUL | [5 empty] | 2014-04-02 | [6 empty] | 2014-07-22 |  |  |  |  | 2015-05-15 | 2016-02-26
B1431 | 1890 | 2014-08-05 | Sun Spirit | Bypass Nurseries Solar Farm | Solar Photovoltaics |  |  | 3.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bypass Nursery, The Bungalow, Evesham WR11 8UB | Hereford and Worcester | West Midlands | England |  | 405573 | 244904 | Wychavon District Council | 12/02700 | [5 empty] | 2012-12-10 | [6 empty] | 2013-04-02 | [5 empty] | 2014-07-28
B1433 | 1892 | 2016-07-28 | Warrington Council | Warrington Home Solar Scheme | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Warrington | Cheshire | North West | England |  | 360000 | 388000 | Warrington Borough Council | [18 empty] | 2014-08-01 | 2016-01-01
B1434 | 1893 | 2016-08-16 | Babergh District Council | Babergh Home Solar Scheme | Solar Photovoltaics |  |  | 2.75 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Babergh | Suffolk | Eastern | England |  | 602000 | 243000 | Babergh District Council | [18 empty] | 2014-07-04 | 2016-06-01
B1435 | 1894 | 2016-09-19 | Mid Suffolk District Council | Mid Suffolk Home Solar Scheme | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Mid Suffolk | Suffolk | Eastern | England |  | 608000 | 255000 | Mid Suffolk District Council | [18 empty] | 2014-07-01 | 2016-01-30
C0261 | 1895 | 2017-01-03 | Equitix | Garn Solar Farm | Solar Photovoltaics |  |  | 7.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The Garn Farm, St. Hilary, Cowbridge, South Glamorgan | South Glamorgan | Wales | Wales | CF71 7DP | 303612 | 173658 | Vale of Glamorgan Council | 2012/01224/FUL | [5 empty] | 2012-11-16 | [6 empty] | 2013-02-08 | [5 empty] | 2014-05-12
C0897 | 1896 | 2015-12-16 | Trethosa Solar Ltd | Trethosa Farm Solar Park | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Trethosa Farm Trethosa St Stephen St Austell Cornwall | Cornwall | South West | England | PL26 7QH | 193895 | 54659 | Cornwall Council | PA13/11191 | [5 empty] | 2014-01-28 | [6 empty] | 2014-06-06 |  |  |  |  | 2015-07-29 | 2015-10-09
C1002 | 1897 | 2015-04-16 | Lumicity | Garvinack Farm Solar Park | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Garvinack Farm, Truro, Cornwall | Cornwall | South West | England | TR4 9EP | 177804 | 47967 | Cornwall Council | PA13/10523 | [5 empty] | 2013-12-16 | [6 empty] | 2014-05-23 |  |  |  |  | 2015-01-01 | 2015-03-31
C1103 | 1898 | 2016-08-31 | Juwi Renewable Energies | Caswell Farm Solar Park | Solar Photovoltaics |  |  | 6.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Caswell Farm, Common Lane, Ryme Intrinseca, Sherborne, Dorset | Dorset | South West | England | DT9 6JP | 358160 | 109979 | West Dorset District Council | 1/D/13/000242 | [5 empty] | 2013-03-08 | [6 empty] | 2013-12-13 |  |  |  |  | 2016-01-23 | 2016-03-23
C1119 | 1899 | 2015-03-19 | Private Developer | Epwell Grounds Farm solar park | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Epwell Grounds Farm, Shutford Road, Epwell, Banbury | Oxfordshire | South East | England | OX15 6HF | 436715 | 241041 | Cherwell District Council | 13/01600/F | [5 empty] | 2013-10-21 | [6 empty] | 2014-01-13 |  |  |  |  | 2014-10-13 | 2014-12-10
C1740 | 1900 | 2016-02-03 | Canadian Solar | Pant-Y-Moch Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pantymoch Farm Penycae Port Talbot | West Glamorgan | Wales | Wales | SA14 2UT | 277876 | 190467 | Neath Port Talbot County Borough Council | P2014/0567 | [5 empty] | 2014-06-27 | [6 empty] | 2014-10-31 |  |  |  | 2019-10-31 | 2015-11-01 | 2016-01-06
C1764 | 1901 | 2018-10-29 | C A Strawson Ltd | Featherstone House Farm | Solar Photovoltaics |  |  | 3.22 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Field Reference 2958 Off Mickledale Lane Bilsthorpe Nottinghamshire | Nottinghamshire | East Midlands | England |  | 464223 | 359525 | Newark and Sherwood District Council | 13/00893/FULM |  | APP/B3030/V/15/3129889 | Call-In |  |  | 2013-08-02 | [6 empty] | 2016-04-19 |  |  |  | 2019-04-19
C1772 | 1902 | 2017-08-23 | Good Energy Generation | Woolbridge Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tout Hill, Woolbridge | Dorset | South West | England | BH20 6HH | 384311 | 87689 | Purbeck District Council | 6/2013/0446 | [5 empty] | 2013-08-05 | [6 empty] | 2013-12-10 |  |  |  |  | 2014-04-15 | 2014-06-18
C1774 | 1903 | 2018-09-04 | Foresight | Tengore Lane - resubmission | Solar Photovoltaics |  |  | 3.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of, Tengore Lane, Long Sutton, Langport, Somerset | Somerset | South West | England | TA10 9JL | 344570 | 127344 | South Somerset District Council | 13/03053/FUL | [5 empty] | 2013-08-01 |  | 2013-10-25 |  |  |  | 2014-06-24 | 2014-06-24 |  |  |  |  | 2014-11-01 | 2015-02-12
C1841 | 1904 | 2014-07-23 | INRG Solar | Manor Farm (Dorset) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Manor Farm E377815 N128359, Gillingham, Dorset | Dorset | South West | England |  | 377815 | 128359 | North Dorset District Council | 2/2013/0791/PLNG | [5 empty] | 2013-08-05 | [6 empty] | 2013-11-08 |  |  |  |  | 2013-11-30 | 2014-06-09
C1964 | 1905 | 2015-05-28 | Hadlow Solar Park | Hadlow Place solar farm | Solar Photovoltaics |  |  | 14.31 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | OS Plots 0072 6400 4568 Off Sherenden Road Tudeley Tonbridge Kent | Kent | South East | England |  | 563692 | 145682 | Tunbridge Wells Borough Council | 14/00870/FULL | [5 empty] | 2014-03-28 | [6 empty] | 2014-11-27 |  |  |  | 2017-11-27 | 2014-12-01 | 2015-03-27
C1999 | 1906 | 2015-04-28 | Push Energy | Bassingbourn Solar Farm | Solar Photovoltaics |  |  | 14.4 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent Highfield Farm, Bassingbourn, Cambridge | Cambridgeshire | Eastern | England |  | 534281 | 243106 | South Cambridgeshire District Council | S/0098/14/FL | [5 empty] | 2014-01-17 | [6 empty] | 2014-08-29 |  |  |  | 2017-08-29 | 2014-10-01 | 2015-03-31
C2002 | 1907 | 2014-08-04 | West Solent Solar Cooperative | Lower Pennington Farm | Solar Photovoltaics |  |  | 2.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | (Field Off Iley Lane) Lower Pennington Farm, Lower Pennington Lane, Pennington, Lymington, Hampshire | Hampshire | South East | England | SO41 8AL | 431648 | 93476 | New Forest District Council | 13/11100 | [5 empty] | 2013-09-06 | [6 empty] | 2013-12-02 | [5 empty] | 2014-06-27
C2003 | 1908 | 2016-07-23 | Ikaros Solar Limited | Goose Willow Farm - extension | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hanney Road, Abingdon, Oxfordshire | Oxfordshire | South East | England | OX13 6AP | 445170 | 192892 | Vale of White Horse District Council | P13/V1975/FUL | [5 empty] | 2013-09-09 | [6 empty] | 2013-12-23 |  |  |  |  | 2014-01-01 | 2014-03-01
C2107 | 1909 | 2015-05-14 | Lightsource Renewable Energy | Avenue Farm | Solar Photovoltaics |  |  | 7.31 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Avenue Farm Back Road Yelverton Norfolk | Norfolk | Eastern | England |  | 629728 | 302939 | South Norfolk Council | 2014/0411 | [5 empty] | 2014-03-04 | [6 empty] | 2014-10-31 |  |  |  | 2017-10-31 | 2014-12-03 | 2015-03-20
C2132 | 1910 | 2018-07-05 | NESF (formerly Lark Energy) | Sywell Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off, Sywell Road, Mears Ashby, Northampton, Northamptonshire | Northamptonshire | East Midlands | England |  | 483454 | 267948 | Wellingborough Borough Council | WP/14/00368/FUL | [5 empty] | 2014-06-05 | [6 empty] | 2014-10-29 |  |  |  | 2017-10-29 | 2015-12-18 | 2017-03-23
C2141 | 1911 | 2015-12-18 | Fred Walter & Sons Ltd | Bellmoor Grassland | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | Land At Bellmoor Grassland Sutton Cum Lound Retford Notts | Nottinghamshire | East Midlands | England | DN22 8SB | 468701 | 384064 | Bassetlaw District Council | 13/01126/FUL | [5 empty] | 2013-10-08 | [6 empty] | 2013-12-21
C2147 | 1912 | 2015-03-19 | Push Energy | Gosfield Airfield | Solar Photovoltaics |  |  | 12.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Gosfield Airfield, Land At Southey Green Sible, Hedingham, Essex | Essex | Eastern | England | CO9 3 | 577359 | 231733 | Braintree District Council | 13/01463/FUL | [5 empty] | 2013-12-23 | [6 empty] | 2014-04-17 |  |  |  |  | 2014-10-01 | 2015-02-01
C2227 | 1913 | 2017-02-02 | Vortex (formerly Sun Edison) | Exning | Solar Photovoltaics |  |  | 29.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off Heath Road, Burwell | Cambridgeshire | Eastern | England |  | 560421 | 263930 | East Cambridgeshire District Council | 13/00878/ESF | [5 empty] | 2013-10-22 | [6 empty] | 2014-07-04 |  |  |  |  | 2014-11-01 | 2015-03-27
C2232 | 1914 | 2015-05-29 | Solar Power South | Grange Farm (Avon) | Solar Photovoltaics |  |  | 21 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Grange Farm, Old Gloucester Road, Winterbourne, Bristol, South Gloucestershire | Avon | South West | England | BS36 1RR | 363842 | 182442 | South Gloucestershire Council | PT13/3662/F | [5 empty] | 2013-10-17 | [6 empty] | 2014-01-06 |  |  |  |  | 2014-09-01 | 2014-12-11
C2234 | 1915 | 2016-07-01 | J.M. Stratton & Co. | Land at East Farm - extension | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | East Farm, Codford, Warminster | Wiltshire | South West | England | BA12 0PJ | 399330 | 141762 | Wiltshire Council | 13/05001/FUL | [5 empty] | 2013-10-09 | [6 empty] | 2014-01-07 |  |  |  |  | 2016-05-01 | 2016-03-01
C2298 | 1916 | 2014-08-05 | Private Developer | Green Lane (Westgate) | Solar Photovoltaics |  |  | 2.04 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land north of, Green Lane, Westgate, Belton | Humberside | Yorkshire and Humber | England |  | 477308 | 408030 | North Lincolnshire Council | PA/2013/1402 | [5 empty] | 2013-11-06 |  | 2014-07-02
C2312 | 1917 | 2019-07-23 | Clean Power Properties | Eastleigh Energy Recovery Centre & Photovoltaic Solar Array - solar | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | Chickenhall Lane, Eastleigh Central, Eastleigh | Hampshire | South East | England | SO50 6RQ | 446272 | 118254 | Hampshire County Council | S/13/73507 | [5 empty] | 2013-10-25 | [6 empty] | 2014-03-31 |  |  |  | 2017-03-31
C2356 | 1918 | 2015-07-16 | Wessex Solar Energy | Laughton Level | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Kitty Hawk Farm, Darp Lane, Ripe, Lewes, East Sussex | East Sussex | South East | England | BN8 6BB | 549288 | 109798 | Wealden District Council | WD/2013/2264/MEA | [5 empty] | 2013-11-06 | [6 empty] | 2014-03-13 |  |  |  |  | 2014-12-01 | 2015-03-26
C2359 | 1919 | 2015-04-27 | Push Energy/ NextEnergy Solar Fund (NESF) | Croydon / Church Farm (Royston) | Solar Photovoltaics |  |  | 16.45 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Church Farm, Church Lane, Croydon, Royston, Hertfordshire | Cambridgeshire | Eastern | England | SG8 0DL | 531544 | 249533 | South Cambridgeshire District Council | S/2293/13/FL | [5 empty] | 2013-10-31 | [6 empty] | 2014-08-01 |  |  |  |  | 2015-01-20 | 2015-03-20
C2746 | 1920 | 2015-05-28 | Foresight Solar | Hadley Farm (Orta Membury Solar Farm) | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The West Of Membury Services Westbound Membury Hungerford Berkshire | Berkshire | South East | England | RG17 7TR | 430374 | 175829 | West Berkshire Council | 14/00385/COMIND | [5 empty] | 2014-02-21 | [6 empty] | 2014-05-27 |  |  |  |  | 2014-12-01 | 2015-03-26
C2796 | 1921 | 2016-02-05 | Holmwood Solar | Holmwood Solar Farm | Solar Photovoltaics |  |  | 19 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land South of Holmwood Farm, Brook Hall Road, Fingringhoe, Colchester | Essex | Eastern | England | CO5 7DG | 603950 | 219950 | Colchester Borough Council | 142446 | APP/A1530/W/15/3013657 |  |  |  |  | 2014-03-20 |  | 2015-02-06 | 2015-06-12 |  | 2016-01-13
C2797 | 1922 | 2014-07-29 | Hive Energy | Wilbees Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Wilbees Farm, The Street, Polegate | East Sussex | South East | England | BN26 | 554329 | 107032 | Wealden District Council | WD/2014/0436/MEA | [5 empty] | 2014-03-13 |  | 2014-06-02
C2802 | 1923 | 2017-03-16 | RB & T Barton Ltd | Manor Farm (Wiltshire) - resubmission | Solar Photovoltaics |  |  | 6.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of Manor Farm, Wadswick Box, Corsham, Wiltshire | Wiltshire | South West | England | SN13 8JB | 384872 | 167858 | Wiltshire Council | 14/03084/FUL | [5 empty] | 2014-03-17 | [6 empty] | 2014-12-23 |  |  |  | 2017-12-23 | 2015-03-01 | 2015-08-01
C2804 | 1924 | 2016-08-24 | Martifer Solar (Voltalia) | Tonge Corner Farm | Solar Photovoltaics |  |  | 22 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North and West of Tonge Corner Farm, Tonge Corner Road, Tonge, Sittingbourne, Kent | Kent | South East | England | ME9 9BB | 593719 | 165447 | Swale Borough Council | SW/14/0224 | [5 empty] | 2014-03-11 | [6 empty] | 2015-08-28 |  |  |  | 2018-08-28 | 2016-01-20 | 2016-03-30
C2820 | 1925 | 2015-05-19 | Lightsource Renewable Energy | Oaklands Farm - resubmission | Solar Photovoltaics |  |  | 6.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north of Oaklands Farm, Pluckley Road, Hothfield, Kent | Kent | South East | England |  | 596397 | 144740 | Ashford Borough Council | 14/00326/AS | [5 empty] | 2014-03-24 | [6 empty] | 2014-06-20 |  |  |  |  | 2014-11-04 | 2015-03-30
C2834 | 1927 | 2017-12-01 | Renesola UK | North East of Ainderby Steeple | Solar Photovoltaics |  |  | 5.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North East Of Ainderby Steeple North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 433420 | 492119 | Hambleton District Council | 14/00471/FUL | [5 empty] | 2014-03-05 | [6 empty] | 2014-12-24 |  |  |  | 2017-12-24 | 2017-01-24 | 2017-03-24
C2844 | 1928 | 2014-07-28 | Private Developer | Highfield Farm - resubmission | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Highfield Farm, Willoughby Road, West Willoughby, Grantham, Lincolnshire, NG32 3SJ | Lincolnshire | East Midlands | England |  | 494122 | 345265 | South Kesteven District Council | S14/0731 | [5 empty] | 2014-03-12 |  | 2014-06-19
C2847 | 1929 | 2016-10-25 | Bowler Energy | Oakwood Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Oakwood Farm Ledburn Mentmore Buckinghamshire | Buckinghamshire | South East | England | LU7 0QD | 491216 | 220825 | Aylesbury Vale District Council | 14/00615/APP | [5 empty] | 2014-03-05 | [6 empty] | 2014-12-05 |  |  |  | 2017-12-05
C2860 | 1930 | 2016-06-21 | Elgin Energy EsCo | Errol Estate | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land 500 Metres South East Of Cottown House Cottown | Tayside | Scotland | Scotland | PH2 7RA | 321208 | 720222 | Perth and Kinross Council | 14/00353/FLL | [5 empty] | 2014-03-17 | [6 empty] | 2014-06-12 |  |  |  |  | 2015-12-07 | 2016-03-19
C2877 | 1931 | 2015-08-19 | INRG Solar | Grange Farm | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ashlea Farm Solent Grange Nursing Home And Grange Farm, Staplers Road, Wootton Bridge, Ryde | Isle of Wight | South East | England | PO33 4RW | 452340 | 90642 | Isle of Wight Council | P/00343/14 | [5 empty] | 2014-03-20 | [6 empty] | 2014-06-19 |  |  |  |  | 2015-01-01 | 2015-03-13
C2937 | 1932 | 2014-07-31 | Orta East Hendred Solar Ltd | Reading Road - resubmission | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land North of Reading Road East Hendred | Oxfordshire | South East | England |  | 446107 | 190207 | Vale of White Horse District Council | P14/V0839/FUL | [5 empty] | 2014-04-15 | 2014-06-26
C2996 | 1933 | 2014-07-21 | Hive Energy | Durley Farm | Solar Photovoltaics |  |  | 6.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | LAND AT DURLEY FARM, POUND LANE, COLBURY, SO40 7EJ | Hampshire | South East | England |  | 435855 | 111211 | New Forest National Park Authority | 14/00361 | [5 empty] | 2014-05-06 | 2014-07-04
C3156 | 1935 | 2017-08-16 | Lightsource Renewable Energy | Chiltern Green Road | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn |  | Bedfordshire | Eastern | England |  | 512827 | 219270 | Central Bedfordshire Council | CB/15/01285/FULL | [5 empty] | 2015-04-01 | 2015-06-30
C3208 | 1936 | 2020-06-05 | Walters Group | Mynydd Bwllfa solar farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | E/O Mynydd Bwllfa Wind Farm, Aberdare, Mid Glamorgan, CF44 | Mid Glamorgan | Wales | Wales |  | 296708 | 203386 | Rhondda Cynon Taff County Borough Council | 14/0466/10 | [5 empty] | 2014-04-11 | [6 empty] | 2019-04-30
C3209 | 1937 | 2014-11-06 | Faldo Solar Farm Ltd | Faldo Farm | Solar Photovoltaics |  |  | 10.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Faldo Farm, Faldo Road, Barton-le-Clay, Bedford | Bedfordshire | Eastern | England | MK45 4RF | 507459 | 231884 | Central Bedfordshire Council | CB/14/02447/FULL | [5 empty] | 2014-07-02 |  | 2014-09-25
C3210 | 1938 | 2017-06-22 | Sirius Solar Building | Wraysbury Landfill | Solar Photovoltaics |  |  | 4.77 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Wraysbury Landfill, Adj Staines Road, Wraysbury, Staines, Middlesex, TW19 5BS | Berkshire | South East | England |  | 501325 | 173097 | Royal Borough of Windsor and Maidenhead | 14/02044/FULL | [5 empty] | 2014-07-02 | [6 empty] | 2014-10-29 |  |  |  | 2017-10-29 | 2017-02-06 | 2017-03-21
C3212 | 1939 | 2019-05-16 | Abbey Renewables (North Fen Solar Energy) | Chittering Solar Farm - extension 2 | Solar Photovoltaics |  |  | 9.58 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land east and south of Radical Farm, Chittering Drove, Chittering, Cambridgeshire, CB25 9PH | Cambridgeshire | Eastern | England |  | 551679 | 270919 | South Cambridgeshire District Council | S/1331/14/FL | [5 empty] | 2014-06-09 | [6 empty] | 2015-06-16 |  |  |  | 2018-06-16
IF1080 | 1940 | 2014-11-27 | Push Energy | Wisbridge Farm | Solar Photovoltaics |  |  | 9.34 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | High Street, Reed, Royston | Hertfordshire | Eastern | England | SG8 8AH | 536451 | 236258 | North Hertfordshire District Council | 12/02365/1 | [5 empty] | 2012-10-23 | [6 empty] | 2013-03-27 |  |  |  |  | 2014-07-01 | 2014-10-01
IF1095 | 1941 | 2018-07-18 | Novus Solar Developments | Blaen Bowi | Solar Photovoltaics |  |  | 5.7 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Expired | Planning Permission Expired | Capel Iwan, Newcastle, Emlyn, Carmarthenshire | Dyfed | Wales | Wales |  | 232248 | 235208 | Carmarthenshire County Council | W/26003 | [5 empty] | 2012-01-18 | [6 empty] | 2012-02-24 |  |  |  | 2017-02-24
AA306 | 1942 | 2015-06-10 | Raybridge Corporation | Caddington Solar Farm (Phase 1) | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Millfield Farm, Caddington, Bedfordshire | Bedfordshire | Eastern | England | LU1 4EH | 505923 | 219056 | Central Bedfordshire Council | CB/11/00455/FULL | [5 empty] | 2011-02-09 | [6 empty] | 2011-05-24 |  |  |  |  | 2014-07-11 | 2014-12-11
C1514 | 1943 | 2015-06-16 | juwi Renewable Energies | Capeland Farm | Solar Photovoltaics |  |  | 8.27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Capelands Farm, Bratton Fleming, Barnstaple, Devon | Devon | South West | England | EX32 7JN | 266581 | 138617 | North Devon District Council | 55798 | [5 empty] | 2013-06-19 | [6 empty] | 2014-02-28 |  |  |  |  | 2014-09-01 | 2015-02-27
C3257 | 1944 | 2015-04-15 | Sunsave 17 / Vogt Solar | Castle Combe Circuit | Solar Photovoltaics |  |  | 12 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Castle Combe, Circuit Castle, Combe, Chippenham | Wiltshire | South West | England | SN14 7EY | 385003 | 177211 | Wiltshire Council | 14/06821/FUL | [5 empty] | 2014-07-16 | [6 empty] | 2014-11-10 |  |  |  | 2017-11-10 | 2015-01-05 | 2015-03-31
IF1091 | 1945 | 2014-09-02 | Hive Energy | Castle Eaton Farm | Solar Photovoltaics |  |  | 17.79 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mill Lane, Castle Eaton, Swindon | Wiltshire | South West | England | SN6 6JX | 414576 | 194495 | Swindon Borough Council | S/12/1766 | [5 empty] | 2012-12-11 | [6 empty] | 2013-03-25 | [5 empty] | 2014-03-30
C2935 | 1946 | 2017-03-01 | BlackRock | Chancery Farm (Ardleigh) | Solar Photovoltaics |  |  | 11.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chancery Farm, Park Road, Ardleigh, Colchester | Essex | Eastern | England | CO7 7SS | 606014 | 227776 | Tendring District Council | 14/00408/FUL | [5 empty] | 2014-04-15 | [6 empty] | 2015-12-22 |  |  |  | 2018-12-22 | 2015-12-23 | 2016-03-29
C3269 | 1947 | 2016-11-23 | SBC Renewables | Clapham solar farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of And Including The Baulk Clapham | Bedfordshire | Eastern | England | MK41 6HD | 503736 | 254248 | Bedford Borough Council | 14/01789/MAF | [5 empty] | 2014-07-18 | [6 empty] | 2014-11-24 |  |  |  | 2017-11-24 | 2015-12-01 | 2016-03-01
C2293 | 1948 | 2015-12-02 | BNRG Renewables | Chapmans Hill | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land at, Chapmans Hill, Aylesham, Canterbury, CT15 4LE | Kent | South East | England |  | 624478 | 152058 | Dover District Council | 14/00419 | [5 empty] | 2014-05-08 | 2015-11-13
IF1059 | 1949 | 2014-06-28 | Chelveston Renewable Energy Limited | Chelveston Airfield | Solar Photovoltaics |  |  | 16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Chelveston Base Crescent And East Of Upper Higham Lane Northants | Bedfordshire | Eastern | England | NN9 6AU | 500650 | 268200 | Bedford Borough Council | 12/02408/MAF | [5 empty] | 2012-12-19 | [6 empty] | 2013-04-25 |  |  |  |  | 2014-02-15 | 2014-02-28
C1353 | 1950 | 2015-05-19 | ESCO NRG | Chisbon Solar Farm (Frowick Lane) | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Frowick Lane St Osyth Essex CO16 8HJ | Essex | Eastern | England | CO16 8HJ | 612862 | 218208 | Tendring District Council | 13/00360/FUL | [5 empty] | 2013-05-08 | [6 empty] | 2013-07-26 |  |  |  |  | 2014-11-15 | 2015-03-05
B1486 | 1951 | 2014-08-26 | Elgin Energy EsCo | Clawdd Ddu PV | Solar Photovoltaics |  |  | 13.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Potardulas Road, Tycroes, Swansea | Dyfed | Wales | Wales | SA18 3RE | 259473 | 209981 | Carmarthenshire County Council | S/27987 | [5 empty] | 2013-03-27 | [6 empty] | 2013-10-07 | [5 empty] | 2014-03-26
B1465 | 1952 | 2016-03-23 | FIM Solar Distribution | Congresbury Solar Farm | Solar Photovoltaics |  |  | 7.06 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Carditch Drove, Honeyhall Lane, Congresbury, Bristol, North Somerset, BS49 5JX | Somerset | South West | England |  | 342667 | 161552 | North Somerset Council | 14/P/1319/F | [5 empty] | 2014-06-19 | [6 empty] | 2014-11-20 |  |  |  | 2017-11-20 | 2015-09-19 | 2015-12-19
B1040 | 1953 | 2018-09-04 | Foresight | Abergelli Glas Solar Farm | Solar Photovoltaics |  |  | 7.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Abergelli Farm Felindre Swansea | Powys | Wales | Wales | SA5 7NN | 265507 | 202009 | City and County Council of Swansea | 2013/0135 | [5 empty] | 2013-02-18 | [6 empty] | 2013-05-28 |  |  |  |  | 2014-11-01 | 2015-03-15
C3278 | 1954 | 2015-10-05 | St Anthony 101 PV Park Ltd | Anthony Estate Solar Farm - resubmission | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Freathy Farm Freathy Cornwall | Cornwall | South West | England |  | 240035 | 52453 | Cornwall Council | PA14/06879 | [5 empty] | 2014-07-29 | [6 empty] | 2014-12-17 |  |  |  | 2017-12-17 | 2015-05-01 | 2015-07-01
B1445 | 1955 | 2015-05-29 | Solar century / Magnetar Solar | Aston House Solar Farm | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Aston House Farm, Aston Lane, Sudbury, Derbyshire | Derbyshire | East Midlands | England | DE6 5HG | 417391 | 331610 | Derbyshire Dales District Council | 14/00450/FUL | [5 empty] | 2014-07-07 | [6 empty] | 2014-11-17 |  |  |  | 2017-11-17 | 2014-12-01 | 2015-03-27
C3258 | 1956 | 2014-11-06 | COOMBE BISSETT PV PARK LIMITED | Bake Farm - resubmission | Solar Photovoltaics |  |  | 14.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land to the west of Bake Farm Buildings Salisbury Road Coombe Bissett Salisbury | Wiltshire | South West | England | SP5 4JT | 411771 | 127679 | Wiltshire Council | 14/06864/FUL | [5 empty] | 2014-07-11 |  | 2014-10-22
C1861 | 1957 | 2016-08-02 | Quercus Renewable Holding 2 | Bakers Farm (solar) | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bakers Farm Selsey Road Sidlesham Chichester West Sussex | West Sussex | South East | England | PO20 7NE | 485215 | 96787 | Chichester District Council | 14/00870/FULEIA | [5 empty] | 2014-03-19 | [6 empty] | 2014-10-06 |  |  |  | 2017-10-06 | 2015-01-30 | 2015-03-20
B1453 | 1958 | 2016-03-23 | Due South Energy & SunE Project6 Ltd | Balls Wood Solar Farm | Solar Photovoltaics |  |  | 8.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Balls Wood, Plymouth, Devon | Devon | South West | England |  | 255174 | 51965 | South Hams District Council | 07/1814/14/F | [5 empty] | 2014-07-15 | [6 empty] | 2014-10-14 |  |  |  | 2017-10-14 | 2015-09-15 | 2015-12-15
C3246 | 1959 | 2015-08-27 | Lightsource Renewable Energy | Barn Farm - resubmission | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Barn Farm Wix Road Bradfield Manningtree Essex CO11 2SP | Essex | Eastern | England |  | 615682 | 231393 | Tendring District Council | 14/00918/FUL | [5 empty] | 2014-07-10 | [6 empty] | 2014-10-20 |  |  |  | 2017-10-20 | 2015-05-08 | 2015-08-14
C2997 | 1960 | 2016-04-04 | Barrow Green Solar Park | Barrow Green Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Barrow Green Farm, Haxted Road, Lingfield | Surrey | South East | England | RH7 6DE | 540136 | 144342 | Tandridge District Council | 2014/1014 | APP/M3645/W/15/3133066 |  |  |  |  | 2014-07-18 |  | 2014-10-24 | 2015-09-17 |  | 2016-03-30
AA867 | 1961 | 2017-08-31 | NextEnergy Solar Fund (NESF) | Bay Farm | Solar Photovoltaics |  |  | 8.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Barton Mills, Bury St Edmunds, Suffolk, IP28 6BS. | Suffolk | Eastern | England | IP28 6BS | 570430 | 271632 | Forest Heath District Council | F/2012/0464/FUL | [5 empty] | 2012-08-06 | [6 empty] | 2012-11-30 |  |  |  |  | 2013-06-01 | 2014-03-01
C2770 | 1962 | 2014-09-01 | Lightsource Renewable Energy | Beckingham Road (resubmission) | Solar Photovoltaics |  |  | 10.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land South Of Beckingham Road, Great Totham, Essex | Essex | Eastern | England |  | 586903 | 212277 | Maldon District Council | 14/00283/FUL | [5 empty] | 2014-05-12 |  | 2014-07-28
C1813 | 1963 | 2015-04-01 | Susenco/Low Carbon | Berwick solar farm | Solar Photovoltaics |  |  | 8.2 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Berwick, Polegate, West Sussex | East Sussex | South East | England |  | 553171 | 108530 | Wealden District Council | WD/2013/1664/MEA | [5 empty] | 2013-08-12 | [6 empty] | 2013-10-21 |  |  |  |  | 2014-10-20 | 2015-03-31
C1248 | 1964 | 2015-07-16 | Wessex Solar Energy | Bidwell Solar Farm - resubmission | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Solar energy facility at South Downs, Dartington, Totnes | Devon | South West | England | TQ9 6DU | 277150 | 61350 | South Hams District Council | 14/1040/13/F | [5 empty] | 2013-05-01 | [6 empty] | 2013-07-01 |  |  |  |  | 2013-12-10 | 2015-04-01
B1463 | 1965 | 2014-11-23 | Elgin Energy EsCo | Bilsborrow Solar Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Off Moss Lane, Bilsborrow | Lancashire | North West | England | PR3 0RU | 349814 | 438915 | Wyre Borough Council | 14/00558/LMAJ | [5 empty] | 2014-07-04 |  | 2014-11-17
C2337 | 1966 | 2015-03-17 | NextEnergy Solar Fund | Bilsham Farm | Solar Photovoltaics |  |  | 14.5 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Southwest of Drove Lane Farm Yapton | West Sussex | South East | England |  | 496214 | 102475 | Arun District Council | Y/87/13/ | [5 empty] | 2013-11-04 | [6 empty] | 2014-02-13 |  |  |  |  | 2014-08-04 | 2014-11-10
B1448 | 1967 | 2015-10-05 | AEE Renewables | Birch Holt Solar Farm | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Birch Holt Farm, Woodcote Lane, Burton, Lincoln | Lincolnshire | East Midlands | England | LN1 2RD | 495593 | 374886 | West Lindsey District Council | 131507 | APP/N2535/W/15/3006201 |  |  |  |  | 2014-07-04 |  | 2014-11-17 | 2015-03-24 |  | 2015-09-10
C3276 | 1968 | 2017-04-26 | Conergy | Blackwell Grange Solar Farm | Solar Photovoltaics |  |  | 4.98 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To North Of Ilmington Road Blackwell | Warwickshire | West Midlands | England |  | 422892 | 243330 | Stratford on Avon District Council | 14/01732/FUL | APP/J3720/W/15/3132381 |  |  |  |  | 2014-07-21 |  | 2015-03-23 | 2015-09-01 |  |  | 2016-03-01 | 2016-03-01 |  |  |  |  | 2016-12-15 | 2017-03-15
IF1165 | 1969 | 2018-07-26 | NextEnery Solar Fund (NESF) | Blenches Mill | Solar Photovoltaics |  |  | 6.1 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Adj Sewage Treatment Works, Slag Lane, Westbury, Wiltshire | Wiltshire | South West | England | BA13 4HZ | 386848 | 152850 | Wiltshire Council | W/12/02081/FUL | [5 empty] | 2012-11-22 | [6 empty] | 2013-11-28 | [5 empty] | 2014-03-31
C2961 | 1970 | 2016-04-01 | Solar Securities (Group) | Bobbing solar farm | Solar Photovoltaics |  |  | 11.33 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cold Harbour Lane, Bobbing, Sittingbourne, Kent | Kent | South East | England | ME9 8NN | 587308 | 165542 | Swale Borough Council | SW/14/0525 | APP/V2255/W/15/3017938 |  |  |  |  | 2014-05-06 |  | 2014-10-20 | 2015-06-22 |  |  | 2015-12-07 | 2015-12-07 |  |  |  | 2018-12-07 | 2016-01-31 | 2016-03-31
IF1028 | 1971 | 2016-05-10 | Solar Securities Group | Bodmin 2 Solar Farm | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Middle Bodiniel Farm, Bodiniel Road, Bodmin, Cornwall | Cornwall | South West | England | PL31 2PF | 206175 | 68428 | Cornwall Council | PA12/09057 | [5 empty] | 2012-09-26 | [6 empty] | 2013-04-12 |  |  |  |  | 2015-02-01 | 2015-03-01
C1773 | 1973 | 2015-04-01 | Inazin Energy/Low Carbon | Bottom Plain | Solar Photovoltaics |  |  | 10 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Bottom Plain, Bere Road, Trigon, Wareham | Dorset | South West | England |  | 388420 | 90356 | Purbeck District Council | 6/2013/0443 | [5 empty] | 2013-08-02 | [6 empty] | 2013-11-01 |  |  |  |  | 2014-10-06 | 2014-12-04
C1531 | 1974 | 2016-07-18 | Public Power Solutions | Braydon Manor Farm | Solar Photovoltaics |  |  | 8.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Braydon Manor Farm, Braydon | Wiltshire | South West | England | SN5 0AG | 404515 | 187745 | Wiltshire Council | 13/01723/FUL | [5 empty] | 2013-06-12 | [6 empty] | 2013-10-29 |  |  |  |  | 2015-09-24 | 2016-01-15
C3273 | 1975 | 2018-03-02 | Core Pisces / Gower Power Co-op CIC | Brynwhilach solar park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Brynwhilach Felindre Road Llangyfelach Swansea | West Glamorgan | Wales | Wales | SA5 7PE | 264728 | 200461 | City and County Council of Swansea | 2014/1022 | [5 empty] | 2014-07-16 | [6 empty] | 2014-11-04 |  |  |  |  | 2017-01-16 | 2017-03-16
C2528 | 1976 | 2015-02-03 | Anesco | Bulls Head Farm North | Solar Photovoltaics |  |  | 4.74 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bulls Head Farm, Eakley Lanes, Stoke Goldington, Newport Pagnell, Buckinghamshire | Northamptonshire | East Midlands | England | MK16 8LP | 481460 | 251327 | South Northamptonshire Council | S/2013/1642/MAF | [5 empty] | 2013-12-12 | [6 empty] | 2014-04-01 |  |  |  |  | 2014-07-01 | 2014-10-02
C2495 | 1977 | 2015-10-26 | Kinetica Solar | Burnt Ash Farm | Solar Photovoltaics |  |  | 13.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Burnt Ash Farm Spinnels Lane Wix Manningtree Essex | Essex | Eastern | England | CO11 2UJ | 616492 | 229433 | Tendring District Council | 13/01340/FUL | 14/00055/REFUSE |  |  |  |  | 2013-12-17 |  | 2014-08-01 | 2014-09-29 |  | 2015-09-08
AA361 | 1978 | 2018-07-26 | NextEnery Solar Fund (NESF) | Burrowton Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Broadclyst, Exeter, | Devon | South West | England |  | 299889 | 96705 | East Devon District Council | 11/0604/MFUL | [5 empty] | 2011-04-12 | [6 empty] | 2011-10-13 |  |  |  |  | 2016-11-18 | 2016-09-18
C3245 | 1979 | 2020-05-27 | First Renewable Developments | Burton Wold Solar Farm - Site A | Solar Photovoltaics |  |  | 19.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Wold Road (land south of), Burton Latimer | Northamptonshire | East Midlands | England |  | 492596 | 274532 | Kettering Borough Council | KET/2014/0540 | [5 empty] | 2014-08-01 | [6 empty] | 2014-10-27 |  |  |  | 2019-10-27
C3224 | 1980 | 2018-03-23 | Solar Planning | Defford Aerodrome | Solar Photovoltaics |  |  | 49.86 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Defford Aerodrome, Rebecca Road, Besford, Worcester, Worcestershire | Hereford and Worcester | West Midlands | England | WR8 9ES | 389437 | 243352 | Wychavon District Council | 14/01244 | [5 empty] | 2014-06-27 | [6 empty] | 2015-01-08 |  |  |  | 2018-01-08
C2112 | 1981 | 2016-01-05 | Thanet Solar Ltd/ Vogt Solar | Ebbsfleet Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the South of the River Stour, Ramsgate Road, Sandwich, CT13 9NL | Kent | South East | England | CT13 9NL | 632795 | 162120 | Dover District Council | 13/00794 | [5 empty] | 2013-09-26 | [6 empty] | 2014-01-24 |  |  |  |  | 2014-02-18 | 2014-03-15
C1243 | 1982 | 2016-01-11 | Suncredit UK/ Vogt Solar | Court Colman solar park | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND AT COURT COLMAN PENYFAI BRIDGEND | Mid Glamorgan | Wales | Wales |  | 287791 | 181659 | Bridgend County Borough Council | P/14/337/FUL | [5 empty] | 2014-05-13 | [6 empty] | 2014-12-24 |  |  |  | 2019-12-24 | 2015-07-01 | 2015-11-15
C2946 | 1983 | 2017-02-02 | Equitix | Cowdown Lane | Solar Photovoltaics |  |  | 40 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Cowdown Lane, Goodworth Clatford, Andover | Hampshire | South East | England | SP11 6LE | 437820 | 144233 | Test Valley Borough Council | 14/00949/FULLN | APP/C1760/W/15/3016531 |  |  |  |  | 2014-05-01 |  | 2014-10-15 | 2015-06-22 |  |  | 2015-12-24 | 2015-12-24 |  |  |  | 2018-12-24 | 2016-01-01 | 2016-03-23
IF1358 | 1984 | 2014-08-26 | MS Power Projects | Crannaford Solar Farm | Solar Photovoltaics |  |  | 12.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North East Of Crannaford House Broadclyst | Devon | South West | England |  | 301013 | 96534 | East Devon District Council | 13/0430/MFUL | [5 empty] | 2013-02-28 | [6 empty] | 2013-09-05 |  |  |  |  | 2014-01-20 | 2014-03-31
C3012 | 1985 | 2015-09-30 | Kronos Solar | Cwmcaesingrug Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cwmcaesingrug Farm Mynyddislwyn Mountain Road Mynyddislwyn Blackwood NP12 2BG | Mid Glamorgan | Wales | Wales | NP12 2BG | 319137 | 193566 | Caerphilly County Borough Council | 14/0276/FULL | [5 empty] | 2014-05-06 | [6 empty] | 2014-08-08 |  |  |  |  | 2015-01-01 | 2015-03-02
C3282 | 1986 | 2016-06-30 | Sawston Solar Farm | Land North of Dales Manor Business Park | Solar Photovoltaics |  |  | 28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | N/O Dales Manor Business Park, West Way, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB2 | 549406 | 250809 | South Cambridgeshire District Council | S/1615/14/FL | APP/W0530/W/15/3012014 |  |  |  |  | 2014-07-28 |  | 2014-10-07 | 2015-10-06 |  | 2016-06-15
C0226 | 1987 | 2014-09-03 | Ms Power Projects Ltd | Decoy Farm House Solar Modules | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Decoy Farm House,, Decoy Lane, Oving, Chichester, West Sussex | West Sussex | South East | England | PO20 3TR | 492213 | 104099 | Chichester District Council | 12/01819/FUL | [5 empty] | 2012-05-17 | [6 empty] | 2012-10-17 |  |  |  |  | 2013-11-11 | 2014-03-31
C2487 | 1988 | 2016-03-31 | BE Renewables/Little Eau Solar | Fendyke Solar Farm | Solar Photovoltaics |  |  | 18.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Fendyke Farm, Fen Dyke, Sutton St James, Spalding, Lincs | Lincolnshire | East Midlands | England | PE12 0LQ | 536677 | 316760 | South Holland District Council | H20-0017-14 | [5 empty] | 2014-01-13 |  | 2014-07-11
C3244 | 1989 | 2015-12-18 | GE Capital Real Estate | GE Crossflow | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | GE Crossflow Poplar Way East Cabot Park Avonmouth Bristol | Avon | South West | England | BS11 0YH | 353827 | 179649 | Bristol City Council | 14/03292/F | [5 empty] | 2014-07-15 | [6 empty] | 2014-10-06 |  |  |  | 2017-10-06
B1349 | 1990 | 2015-12-22 | Lightsource Renewable Energy | Hadley Solar Farm | Solar Photovoltaics |  |  | 6.56 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hadley Farm Wrexham Road Whitchurch Shropshire | Shropshire | West Midlands | England | SY13 3AB | 351460 | 340636 | Shropshire Council | 14/02914/FUL | [5 empty] | 2014-07-07 | [6 empty] | 2014-10-06 |  |  |  | 2017-10-06 | 2015-09-21 | 2015-12-16
B1270 | 1991 | 2016-07-18 | Push Energy/ NextEnergy Solar Fund (NESF) | Hall Farm Solar Farm (Newbold Verdon) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hall Farm, Main Street, Newbold Verdon, LEICESTER, LE9 9NL | Leicestershire | East Midlands | England |  | 444216 | 303818 | Hinckley and Bosworth Borough Council | 14/00660/FUL | [5 empty] | 2014-07-17 | [6 empty] | 2015-06-03 |  |  |  | 2018-06-03 | 2015-09-07 | 2015-12-08
C3277 | 1992 | 2016-12-16 | Solar Power South | Hammond Court Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hammond Court Farm Trench Lane Winterbourne Bristol South Gloucestershire BS36 1RY | Avon | South West | England |  | 363238 | 182360 | South Gloucestershire Council | PT14/2575/F | [5 empty] | 2014-07-25 | [6 empty] | 2015-02-12 |  |  |  | 2018-02-12 | 2015-02-12 | 2015-03-31
C2905 | 1993 | 2014-09-03 | Haymaker Energy | Handley Park | Solar Photovoltaics |  |  | 19 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Handley Park Farm, Handley Park, Towcester | Northamptonshire | East Midlands | England |  | 467064 | 246060 | South Northamptonshire Council | S/2014/0492/MAF | [5 empty] | 2014-04-09 |  | 2014-07-03
B1488 | 1994 | 2014-08-26 | Private Developer | Hatch Penn Farm PV | Solar Photovoltaics |  |  | 1.03 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hatchpen Farm, Reed, Royston | Hertfordshire | Eastern | England | SG8 8AZ | 536397 | 237730 | North Hertfordshire District Council | 13/02128/1 | [5 empty] | 2013-11-24 | [6 empty] | 2013-12-03 | [5 empty] | 2014-03-08
C2945 | 1995 | 2015-09-02 | Green Power | Hayford Farm - extension | Solar Photovoltaics |  |  | 8.152 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hayford Farm Westbury Shrewsbury | Shropshire | West Midlands | England | SY5 9PF | 336421 | 310318 | Shropshire Council | 14/01760/FUL | [5 empty] | 2014-04-28 | [6 empty] | 2014-08-26 |  |  |  |  | 2015-02-01 | 2015-03-26
C1633 | 1996 | 2016-03-03 | Haymaker Energy | Heath Lane Solar Park | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at, Heath Lane, Honington | Lincolnshire | East Midlands | England |  | 495586 | 343012 | South Kesteven District Council | S14/1084 | APP/E2530/W/15/3028011 |  |  |  |  | 2014-04-11 |  | 2014-12-03 | 2015-05-18 |  | 2016-02-11
B1450 | 1997 | 2014-11-06 | Henley Solar Farm | Henley Solar Farm | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land North of Henley Common, Henley Lane, Acton Scott, Church Stretton, Shropshire | Shropshire | West Midlands | England |  | 345678 | 288418 | Shropshire Council | 14/02807/FUL | [5 empty] | 2014-07-07 |  | 2014-10-27
C1009 | 1998 | 2014-09-02 | Hive Energy | High Penn Solar Park | Solar Photovoltaics |  |  | 9.64 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | High Penn Farm, Calne, Wiltshire | Wiltshire | South West | England | SN11 8TE | 401072 | 172471 | Wiltshire Council | 12/04169/FUL | [5 empty] | 2013-02-25 | [6 empty] | 2013-10-08 | [5 empty] | 2014-03-30
IF1250a | 1999 | 2014-09-02 | Hive Energy | Highfields Farm (Braintree) | Solar Photovoltaics |  |  | 2.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Highfields Lane, Messing Colchester CO5 9BJ | Essex | Eastern | England |  | 587510 | 217512 | Braintree District Council | 12/01472/FUL | [5 empty] | 2012-12-21 | [6 empty] | 2013-09-03 | [5 empty] | 2014-03-28
IF1250 | 2000 | 2014-09-02 | Hive Energy | Highfields Farm (Colchester) | Solar Photovoltaics |  |  | 12.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Highfields Lane, Messing, Colchester | Essex | Eastern | England | CO5 9BJ | 587510 | 217512 | Colchester Borough Council | 121949 (12/1949/FUL) | [5 empty] | 2012-12-21 | [6 empty] | 2013-09-25 | [5 empty] | 2014-03-28
IF1066 | 2001 | 2014-08-26 | Lightsource Renewable Energy | Hill End Farm | Solar Photovoltaics |  |  | 2.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hill End Farm, Aldermaston Road, Salters Heath, Tadley, Hampshire, RG26 | Hampshire | South East | England |  | 462034 | 157344 | Basingstoke and Deane Borough Council | 13/01007/FUL | [5 empty] | 2013-07-12 | [6 empty] | 2013-12-20 | [5 empty] | 2014-03-29
C2576 | 2002 | 2014-09-01 | Hive Energy | Hill Farm (Baylham) | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at Hill Farm, Upper Street, Baylham (in the Parish of Great Blakenham) | Suffolk | Eastern | England |  | 610859 | 251069 | Mid Suffolk District Council | 2801/13 | [5 empty] | 2014-01-20 | 2014-06-06
C3286 | 2004 | 2016-05-27 | Lightsource Renewable Energy | Holwell Hill | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Toid, Burts Hill To Nunney Catch Roundabout, Trudoxhill, Frome, Somerset | Somerset | South West | England |  | 373269 | 144417 | Mendip District Council | 2014/1562/FUL | APP/Q3305/W/15/3007564 |  |  |  |  | 2014-08-01 |  | 2015-01-30 | 2015-04-01 |  |  | 2015-08-28 | 2015-08-28 |  |  |  | 2018-08-28 | 2016-02-15 | 2016-05-15
IF1081 | 2005 | 2014-08-26 | British Solar Renewables (formerly know as Solar Power Generation) | Hook Valley Solar Park | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lawrence Hill, Wincanton, Somerset, BA9 8AD | Somerset | South West | England |  | 369613 | 127790 | South Somerset District Council | 12/04445/FUL | 12/04445/FUL |  |  |  |  | 2012-11-21 |  | 2013-02-20 |  |  |  | 2013-09-26 | 2013-09-26 | [5 empty] | 2014-03-31
C2936 | 2006 | 2016-04-14 | Eco Energy World | Partridge Farm | Solar Photovoltaics |  |  | 10.59 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land south of National Grid Converter Station, Church Lane, Aldington, Kent | Kent | South East | England |  | 608480 | 137870 | Ashford Borough Council | 14/00398/AS | APP/E2205/W/15/3003125 |  |  |  |  | 2014-04-28 |  | 2014-07-22 | 2015-02-18 |  |  | 2015-10-06 | 2015-10-06 |  |  |  |  | 2015-12-07 | 2016-03-24
C3221 | 2007 | 2016-10-04 | United Photovoltaics | Aspatria | Solar Photovoltaics |  |  | 19 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pasture Farm, Westnewon Road, Aspatria, Wigton, Cumbria | Cumbria | North West | England | CA7 3JU | 314932 | 543374 | Allerdale Borough Council | 2/2014/0468 | [5 empty] | 2014-07-02 | [6 empty] | 2014-11-18 |  |  |  | 2017-11-18 | 2014-12-01 | 2015-03-30
C0425 | 2008 | 2014-08-26 | British Solar Renewables (formerly Solar Power Generation) | Penare Farm Solar Farm | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Penare Farm St Allen Truro Cornwall | Cornwall | South West | England | TR4 9DG | 181089 | 49385 | Cornwall Council | PA12/12106 | [5 empty] | 2012-12-27 | [6 empty] | 2013-04-26 | [5 empty] | 2014-03-18
C3284 | 2009 | 2015-05-28 | First Solar Project Ltd | Pencoose Farm | Solar Photovoltaics |  |  | 8.51 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | W F Gluyas & Son, Pencoose Farm, Stithians, Truro, Cornwall | Cornwall | South West | England | TR3 7DN | 173927 | 37998 | Cornwall Council | PA14/07019 | [5 empty] | 2014-07-25 | [6 empty] | 2014-10-24 |  |  |  | 2017-10-24 | 2015-01-01 | 2015-03-27
AA912 | 2010 | 2014-08-26 | Elgin Energy EsCo | Pensipple Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | St. Keyne Liskeard | Cornwall | South West | England | PL14 4SP | 225875 | 59256 | Cornwall Council | PA12/04228 | [5 empty] | 2012-05-17 | [6 empty] | 2013-03-06 | [5 empty] | 2014-03-31
C3281 | 2011 | 2015-11-13 | BayWa/ SunGift | Pingewood Road South | Solar Photovoltaics |  |  | 15.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Pingewood Road, South Burghfield, Reading, Berkshire | Berkshire | South East | England |  | 468636 | 169185 | West Berkshire Council | 14/01800/COMIND | [5 empty] | 2014-07-24 | [6 empty] | 2014-10-09 |  |  |  | 2017-10-09 | 2014-12-01 | 2015-03-30
IF1029 | 2012 | 2015-05-28 | Coleford Energy | Pingry Farm - Phase 1 | Solar Photovoltaics |  |  | 3.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Pingry Farm, Pingry Lane, Milkwall, Coleford | Gloucestershire | South West | England | GL16 8QD | 357121 | 209434 | Forest of Dean District Council | P1418/12/FUL | [5 empty] | 2013-03-06 | [6 empty] | 2013-04-11 |  |  |  |  | 2014-01-01 | 2014-03-24
C0637 | 2013 | 2018-03-02 | Hive Energy | Pitworthy Farm Solar Park | Solar Photovoltaics |  |  | 15.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pitworthy Farm Pancrasweek Holsworthy Devon | Devon | South West | England | EX22 7JT | 229109 | 105236 | Torridge District Council | 1/0833/2012/FULM | [5 empty] | 2012-10-18 | [6 empty] | 2013-07-04 |  |  |  |  | 2013-12-31 | 2014-03-31
C1992 | 2014 | 2015-05-21 | Sun & Soil | Primrose Hill Farm | Solar Photovoltaics |  |  | 3.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Primrose Hill Farm, Bardney Road, Wragby, Market Rasen, Lincolnshire, LN8 5JE | Lincolnshire | East Midlands | England | LN8 5JE | 513835 | 376615 | East Lindsey District Council | S/216/00470/14 | [5 empty] | 2014-03-25 | [6 empty] | 2014-08-09 |  |  |  |  | 2015-01-15 | 2015-03-25
C1924 | 2015 | 2014-08-26 | Wessex Solar Energy | Pyde Drove | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at, Pyde Drove (2), The Causeway, Woolavington, Bridgwater | Somerset | South West | England |  | 335530 | 142499 | Sedgemoor District Council | 54/13/00010 | [5 empty] | 2013-08-09 | [6 empty] | 2013-10-31 | [5 empty] | 2014-03-27
IF1364 | 2016 | 2017-01-03 | Equitix | Race farm | Solar Photovoltaics |  |  | 6.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Race Farm, Huntick Road, Lytchett Mmatravers, Poole, Dorset | Dorset | South West | England | BH16 6EH | 395765 | 94289 | Purbeck District Council | 6/2013/0132 | [5 empty] | 2013-03-06 | [6 empty] | 2013-06-28 | [5 empty] | 2014-03-21
C3217 | 2017 | 2015-08-13 | Sirius Solar Building | Radcliffe Solar Farm | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South East Of Holme House Stragglethorpe Road Holme Pierrepont Nottinghamshire | Nottinghamshire | East Midlands | England |  | 463336 | 337992 | Rushcliffe Borough Council | 14/01228/FUL | [5 empty] | 2014-06-23 | [6 empty] | 2014-11-14 |  |  |  | 2017-11-14 | 2015-04-13 | 2015-06-13
C2228 | 2018 | 2017-09-27 | Lunar Energy Power | RAF Faldingworth | Solar Photovoltaics |  |  | 50 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Former RAF Faldingworth Spridlington Road Faldingworth Market Rasen | Lincolnshire | East Midlands | England |  | 503422 | 385353 | West Lindsey District Council | 130514 | [5 empty] | 2013-09-23 | [6 empty] | 2014-03-31 |  |  |  | 2017-03-31
IF1038 | 2019 | 2015-02-03 | Dodds Limited | Redhall Industrial Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South And East Of Redhall Industrial Estate Patrington Road Ottringham East Riding Of Yorkshire HU12 0AD | Humberside | Yorkshire and Humber | England | HU12 0AD | 527936 | 423997 | East Riding of Yorkshire Council | 12/04362/STPLF | [5 empty] | 2012-10-22 | [6 empty] | 2013-01-21 | [5 empty] | 2014-08-08
C3233 | 2020 | 2016-10-03 | Green Energy UK Direct | Ring O Bells Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ring O Bells Farm Pucklechurch Road Hinton Chippenham South Gloucestershire SN14 8HJ | Avon | South West | England |  | 372598 | 176745 | South Gloucestershire Council | PK14/2339/F | [5 empty] | 2014-06-26 | [6 empty] | 2015-08-07 |  |  |  | 2018-08-07 | 2015-11-25 | 2016-08-18
C2572 | 2021 | 2015-12-17 | Fengate Capital | Roanhead Farm | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north of Roanhead Farm Hawthwaite Lane Barrow-in-Furness LA14 4QL | Cumbria | North West | England |  | 321134 | 476090 | Barrow in Furness Borough Council | B03/2014/0473 | [5 empty] | 2014-07-07 | [6 empty] | 2014-09-25 |  |  |  | 2017-09-25 | 2015-01-01 | 2015-03-21
C2934 | 2022 | 2017-03-20 | Vale Green Energy | Rotherdale Farm - extension | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Long Lane, Tilesford, Pershore, Worcestershire | Hereford and Worcester | West Midlands | England | WR10 2LA | 397764 | 250587 | Wychavon District Council | W/14/00830/PN | [5 empty] | 2014-04-29 | [6 empty] | 2014-06-23 |  |  |  |  | 2014-09-01 | 2015-03-01
C2493 | 2023 | 2015-04-15 | Hive Energy | Roundponds Farm Solar Park | Solar Photovoltaics |  |  | 13.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South East Of Leechpool Farm Norrington Lane Broughton Gifford Wiltshire | Wiltshire | South West | England |  | 388770 | 164574 | Wiltshire Council | 13/06707/FUL | [5 empty] | 2014-01-09 | [6 empty] | 2014-05-23 |  |  |  |  | 2014-12-15 | 2015-03-31
C1527 | 2024 | 2014-09-02 | Hopton PV Ltd | Hopton Road Industrial Estate | Solar Photovoltaics |  |  | 1.3 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | N/O Hopton Industrial Estate, Hopton Road, Devizes, Wiltshire | Wiltshire | South West | England | SN10 2EU | 402353 | 163586 | Wiltshire Council | 13/00984/FUL | [5 empty] | 2013-07-03 | [6 empty] | 2013-08-30 | [5 empty] | 2014-08-01
C3275 | 2025 | 2015-08-04 | TGC Renewables | Horsham Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Appeal Refused | Application Refused | Land adjacent to the A24 bypass, to the south west of Beare Green, Mole Valle, Surrey | Surrey | South East | England |  | 517330 | 142513 | Mole Valley District Council | MO/2014/1092 | APP/C3620/W/14/3002006 |  |  |  |  | 2014-07-16 |  | 2014-10-15 | 2015-01-22 |  | 2015-07-10
C2893 | 2026 | 2018-09-04 | Foresight | Field House Solar / Hursley Road | Solar Photovoltaics |  |  | 6.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field House Farm, Hursley, Winchester | Hampshire | South East | England | SO21 2LE | 442789 | 123431 | Winchester City Council | 14/00813/FUL | [5 empty] | 2014-04-03 | [6 empty] | 2014-07-04 |  |  |  |  | 2015-01-01 | 2015-03-24
AA839 | 2027 | 2015-04-27 | Foresight Solar Fund Limited | Kencot Hill Solar Farm (revised application) | Solar Photovoltaics |  |  | 37 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to north and east of Kencot Hill Farm House, Kencot, Lechlade, Gloucestershire, GL7 3QY | Oxfordshire | South East | England | GL7 3QY | 424971 | 206886 | West Oxfordshire District Council | 12/0584/P/FP | [5 empty] | 2012-04-16 | [6 empty] | 2012-06-20 | [5 empty] | 2014-10-30
C0580 | 2028 | 2014-08-26 | Private Developer | KERNICK MICA DAM - SOLAR FARM | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Kernick Mica Dam, Trethosa Downs, Trethosa, St Stephen, St Austell, Cornwall | Cornwall | South West | England | PL26 | 193490 | 54417 | Cornwall Council | PA12/07557 | [5 empty] | 2012-08-08 | [6 empty] | 2013-01-31 | [5 empty] | 2014-03-29
C3274 | 2029 | 2014-11-06 | Solar Planning | Land near Manston | Solar Photovoltaics |  |  | 8.1 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Manston Road, E/O Worlds Wonder, Manston, Ramsgate, Kent, CT12 5BQ | Kent | South East | England |  | 634527 | 165873 | Thanet District Council | F/TH/14/0645 | [5 empty] | 2014-07-30 |  | 2014-10-13
C1902 | 2030 | 2017-02-02 | First Solar/Innogy (previously BELECTRIC Solar)/Foresight Solar Fund | Landmead Farm (East Hanney) | Solar Photovoltaics |  |  | 46 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Landmead Farm, East Hanney, Abingdon | Oxfordshire | South East | England | OX13 5PA | 443442 | 194093 | Vale of White Horse District Council | P13/V1664/FUL | [5 empty] | 2013-07-22 | [6 empty] | 2013-10-29 |  |  |  |  | 2014-11-07 | 2014-12-19
B1328 | 2031 | 2015-05-27 | Solar Planning | Little Chalfield Solar Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land West Of Ganbrook Farm Little Chalfield Wiltshire | Wiltshire | South West | England |  | 384892 | 164588 | Wiltshire Council | 14/05253/FUL | APP/Y3940/A/14/2228679 |  |  |  |  | 2014-05-29 |  | 2014-09-29 | 2014-12-09 |  | 2015-05-18
C2947 | 2032 | 2015-04-16 | Novus Solar Developments | Lower Newton Farm | Solar Photovoltaics |  |  | 11.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lower Newton Farm, Draycott Road, Tean, Stoke-On-Trent, Staffordshire | Staffordshire | West Midlands | England | ST10 4JN | 398731 | 338883 | Staffordshire Moorlands District Council | SMD/2014/0197 | [5 empty] | 2014-04-25 | [6 empty] | 2014-08-26 |  |  |  |  | 2014-11-01 | 2015-03-31
IF1324 | 2033 | 2015-12-15 | PS Renewables | Lower Slade Farm | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Kingsbridge | Devon | South West | England | TQ7 2HE | 274224 | 45194 | South Hams District Council | 08_28/0430/13/F | [5 empty] | 2013-02-21 |  | 2013-09-03 |  |  |  | 2014-08-11 | 2014-08-11 |  |  |  |  | 2015-06-28 | 2015-11-26
C3243 | 2034 | 2015-07-24 | William Notcutt Estates | Lower Ufford Lane | Solar Photovoltaics |  |  | 1.068 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent A12 Lower Ufford Lane Pettistree Suffolk | Suffolk | Eastern | England |  | 630425 | 254042 | Waveney District Council | DC/14/2236/FUL | [5 empty] | 2014-07-11 | [6 empty] | 2014-10-07 |  |  |  | 2017-10-07 | 2015-03-15 | 2015-06-15
C2108 | 2035 | 2015-04-15 | Meag | Lynt Farm | Solar Photovoltaics |  |  | 27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Lynt Farm, Lynt Farm Lane, Inglesham, Swindon | Wiltshire | South West | England | SN6 7QZ | 420821 | 196008 | Swindon Borough Council | S/14/1048 | [5 empty] | 2014-06-20 | [6 empty] | 2015-01-09 |  |  |  | 2018-01-09 | 2015-01-15 | 2015-03-31
B1449 | 2036 | 2016-08-31 | Trina Solar | Marchington Solar Farm | Solar Photovoltaics |  |  | 4.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Moisty Lane Marchington Staffordshire | Staffordshire | West Midlands | England |  | 411401 | 331186 | East Staffordshire Borough Council | P/2014/00825 | [5 empty] | 2014-07-10 | [6 empty] | 2014-10-15 |  |  |  | 2017-10-15 | 2015-11-15 | 2016-03-23
C3216 | 2037 | 2015-10-05 | RGE Energy UK | Middle Street | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Middle Street, Burton, Lincoln | Lincolnshire | East Midlands | England | LN1 | 496940 | 375551 | West Lindsey District Council | 131496 | APP/N2535/W/15/3004150 |  |  |  |  | 2014-06-30 |  | 2014-11-17 | 2015-02-12 |  | 2015-09-10
C3249 | 2038 | 2015-03-09 | SBC Renewables | Moneystone Quarry | Solar Photovoltaics |  |  | 8.5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | W B B Minerals, Moneystone Quarry, Cheadle Road, Oakamoor, Stoke on Trent, Staffordshire, ST10 2DZ | Staffordshire | West Midlands | England |  | 404555 | 345692 | Staffordshire Moorlands District Council | SMD/2014/0432 | [5 empty] | 2014-06-28 |  | 2015-03-05
C1335 | 2039 | 2015-08-13 | John Laing Environmental Assets Group | Monksham Solar Farm | Solar Photovoltaics |  |  | 10.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Monksham Farm, Marston Bigot, Frome | Somerset | South West | England | BA11 5BR | 376630 | 142871 | Mendip District Council | 2013/1118 | [5 empty] | 2013-05-16 | [6 empty] | 2013-09-17 | [5 empty] | 2014-03-30
C2453 | 2040 | 2015-05-18 | Orta Solar Ltd | Moorhouse Lane - resubmission | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjoining Moorhouse Caravans Moorhouse Lane Hallen Bristol | Avon | South West | England | BS10 7RU | 354465 | 179761 | Bristol City Council | 13/05491/F | [5 empty] | 2013-12-03 | [6 empty] | 2014-05-15 |  |  |  |  | 2014-11-01 | 2015-05-11
C3272 | 2041 | 2016-05-19 | Sun & Soil | Morton Wood Farm | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Morton Wood Farm, Morton Wood Lane, Abbots Morton, Evesham, WR7 4LU | Hereford and Worcester | West Midlands | England |  | 403051 | 253675 | Wychavon District Council | W/14/01549/PN | [5 empty] | 2014-07-30 | [6 empty] | 2014-12-15 |  |  |  | 2017-12-15 | 2015-12-15 | 2016-03-15
C2888 | 2042 | 2014-09-03 | Haymaker Energy | Mountmill Farm | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Mountmill Farm Stratford Road Wicken | Northamptonshire | East Midlands | England |  | 475895 | 238630 | South Northamptonshire Council | S/2014/0470/MAF | [5 empty] | 2014-04-04 |  | 2014-06-11
C2709 | 2043 | 2015-01-27 | Haymaker Energy | Natewood Farm | Solar Photovoltaics |  |  | 8.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Natewood Farm, Polegate Road, Hailsham, East Sussex | East Sussex | South East | England | BN27 3PH | 557492 | 107430 | Wealden District Council | WD/2014/0153/MAJ | [5 empty] | 2014-02-06 | [6 empty] | 2014-04-17 |  |  |  |  | 2014-10-27 | 2015-01-27
C3285 | 2044 | 2018-09-01 | REG Solarpower/Veolia | Netley Landfill Solar | Solar Photovoltaics |  |  | 12 | n/a |  |  | 12 | n/a | n/a | n/a | Ground | Operational | Operational | Netley Landfill Site Portsmouth Road Netley Southampton | Hampshire | South East | England | SO19 9NA | 447013 | 110328 | Eastleigh Borough Council | F/14/75012 | [5 empty] | 2014-08-05 | [6 empty] | 2014-10-30 |  |  |  | 2017-10-30 | 2017-01-01 | 2017-03-31
C2686 | 2045 | 2015-04-01 | INRG Solar | New Stone House | Solar Photovoltaics |  |  | 12.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of New Stone House, Main Street, Wendlebury | Oxfordshire | South East | England | OX25 2PT | 456393 | 219144 | Cherwell District Council | 14/00565/F | [5 empty] | 2014-04-10 | [6 empty] | 2014-07-17 |  |  |  |  | 2014-12-01 | 2015-03-16
IF1295 | 2046 | 2014-08-26 | British Solar Renewables (formerly known as Solar Power Generation) | North Creake Airfield (Resubmission) | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Egmere, Walsingham | Norfolk | Eastern | England |  | 590428 | 338001 | North Norfolk District Council | PF/13/0168 | [5 empty] | 2013-02-11 | [6 empty] | 2013-03-21 | [5 empty] | 2014-03-27
IF1443 | 2047 | 2015-03-06 | Primrose Solar | North of Newton Farm | Solar Photovoltaics |  |  | 2.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lytchett Minster, Poole, Dorset | Dorset | South West | England |  | 393388 | 93923 | Purbeck District Council | 6/2013/0133 | [5 empty] | 2013-03-06 | [6 empty] | 2013-06-28 | [5 empty] | 2014-03-19
AA376 | 2048 | 2015-03-09 | AEE Renewables | Roves Farm (Solar) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Roves Lane, Sevenhampton, Swindon | Wiltshire | South West | England | SN6 7QG | 420682 | 189012 | Swindon Borough Council | S/11/0248 | [5 empty] | 2011-03-28 | [6 empty] | 2011-05-16 |  |  |  | 2014-05-16
B1456 | 2049 | 2015-03-09 | Bluefield Solar | Roves Farm (Solar) - resubmission | Solar Photovoltaics |  |  | 12.65 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Roves Lane, Sevenhampton, Swindon | Wiltshire | South West | England | SN6 7QG | 420992 | 188816 | Swindon Borough Council | S/14/0992 | [5 empty] | 2014-07-08 | [6 empty] | 2014-10-28 |  |  |  | 2017-10-28 | 2014-12-01 | 2015-02-24
C1330 | 2050 | 2015-12-16 | Island Green Power | Salhouse Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Stonehouse Road,Salhouse | Norfolk | Eastern | England | NR13 6EZ | 629878 | 315535 | Broadland District Council | 20131408 | [5 empty] | 2013-10-08 | [6 empty] | 2014-02-05 |  |  |  |  | 2015-07-29 | 2015-10-20
IF1117 | 2051 | 2014-08-26 | Ms Power Projects Ltd | Norton Hall | Solar Photovoltaics |  |  | 2.8 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Mickleton, Chipping Campden, Gloucestershire, GL55 6PX | Gloucestershire | South West | England |  | 414685 | 244775 | Cotswold District Council | 12/05095/FUL | [5 empty] | 2012-11-14 |  | 2013-03-13 |  |  |  | 2013-10-10 | 2013-10-10 | [5 empty] | 2014-03-31
C3222 | 2052 | 2017-01-03 | Eneco UK | Oaklands Plantation | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bere Road (Oaklands Plantation) Coldharbour Wareham | Dorset | South West | England | BH20 7PA | 389957 | 89555 | Purbeck District Council | 6/2014/0338 | [5 empty] | 2014-06-30 | [6 empty] | 2014-11-07 |  |  |  |  | 2015-08-01 | 2016-01-29
B1504 | 2053 | 2020-02-05 | REG Solarpower/Veolia | Ockendon Landfill Solar Farm | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | South Ockendon Quarry And Landfill Site Medebridge Road South Ockendon Essex | Essex | Eastern | England |  | 560977 | 183363 | Thurrock Council | 14/00836/FUL | [5 empty] | 2014-07-29 | [6 empty] | 2016-01-22 |  |  |  | 2019-01-22
B1447 | 2054 | 2015-05-14 | Solstice Renewables | Packington Solar Farm | Solar Photovoltaics |  |  | 13.88 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Babelake Street Packington Ashby De La Zouch Leicestershire LE65 1TG | Leicestershire | East Midlands | England |  | 435738 | 312311 | North West Leicestershire District Council | 14/00535/FULM | [5 empty] | 2014-06-27 | [6 empty] | 2014-10-20 |  |  |  | 2017-10-20 | 2014-11-15 | 2015-03-16
C0640 | 2055 | 2018-07-26 | NextEnery Solar Fund (NESF) | SAUNDERCROFT SOLAR FARM | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Adj Saundercroft, Whimple, Exeter, Devon | Devon | South West | England | EX5 2PF | 301466 | 97090 | East Devon District Council | 12/2247/MFUL | [5 empty] | 2012-10-23 | [6 empty] | 2013-01-02 | [5 empty] | 2014-03-29
C2386 | 2056 | 2015-04-14 | Bee Green Solar | Sedbury Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | E/O Sedbury Park, Sedbury, Chepstow, Gwent, NP16 | Gloucestershire | South West | England | NP16 7EY | 354762 | 193562 | Forest of Dean District Council | P1628/13/FUL | [5 empty] | 2013-11-11 | [6 empty] | 2014-04-23 |  |  |  |  | 2014-11-01 | 2015-03-27
B1446 | 2057 | 2015-05-14 | Lightsource Renewable Energy | Six Hills Solar Farm | Solar Photovoltaics |  |  | 18.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field OS 00077 And 6867 Six Hills Road Ragdale | Leicestershire | East Midlands | England |  | 465779 | 320785 | Melton Borough Council | 14/00529/FUL | [5 empty] | 2014-06-27 | [6 empty] | 2014-10-16 |  |  |  | 2017-10-16 | 2014-12-16 | 2015-03-24
IF1442 | 2058 | 2017-01-03 | Equitix | South Newton Farm | Solar Photovoltaics |  |  | 11.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Newton Farm, Lytchett Minster, Poole, Dorset | Dorset | South West | England | BH16 6HS | 393212 | 92885 | Purbeck District Council | 6/2013/0134 | [5 empty] | 2013-03-06 | [6 empty] | 2013-06-28 | [5 empty] | 2014-03-19
C3279 | 2059 | 2015-12-21 | Ethical Power | Southdown Quarry | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | The Quarry At Southdown Quay Millbrook Torpoint Cornwall | Cornwall | South West | England | PL10 1HG | 243454 | 53023 | Cornwall Council | PA14/06734 | [5 empty] | 2014-07-16 | [6 empty] | 2014-10-09 |  |  |  | 2017-10-09 |  | 2015-12-21
C2582 | 2060 | 2016-07-28 | British Solar Renewables | Southfield Farm Solar Park (resubmission) | Solar Photovoltaics |  |  | 11.47 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Southfield Farm, Smithy Lane, Yeovilton, Yeovil, Somerset | Somerset | South West | England |  | 357405 | 124030 | South Somerset District Council | 14/00215/FUL | [5 empty] | 2014-01-20 | [6 empty] | 2015-07-09 |  |  |  | 2018-07-09 | 2015-09-15 | 2016-03-31
C1796 | 2061 | 2014-08-26 | MTS Spittleborough Solar Ltd | Spittleborough Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Swindon Road Lydiard Tregoze Royal Wootton Bassett Wiltshire | Wiltshire | South West | England | SN4 8ET | 408318 | 183058 | Wiltshire Council | 13/02191/FUL | [5 empty] | 2013-07-15 | [6 empty] | 2013-12-09 |  |  |  |  | 2014-01-31 | 2014-03-25
C2998 | 2062 | 2016-08-02 | Quercus Renewable Holding 2 | Stanton solar park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Trenchard Road Stanton Fitzwarren Swindon | Wiltshire | South West | England | SN6 7RY | 417307 | 191077 | Swindon Borough Council | S/14/0757 | [5 empty] | 2014-05-07 | [6 empty] | 2014-08-19 |  |  |  |  | 2015-01-28 | 2015-03-15
AA292 | 2063 | 2014-08-26 | Private Developer | Stantway Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rodley Court Farm, Westbury On Severn Gloucestershire GL14 1QG | Gloucestershire | South West | England |  | 372541 | 213700 | Forest of Dean District Council | P0031/11/FUL | [5 empty] | 2011-01-12 | [6 empty] | 2011-04-13 | [5 empty] | 2014-03-29
IF1116 | 2064 | 2014-08-26 | British Solar Renewables (formerly known as Solar Power Generation) | Stonebarrow Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Opposite Woodcote National Substation Hawkchurch Devon | Devon | South West | England | EX13 5RX | 334899 | 98840 | East Devon District Council | 12/2410/MFUL | [5 empty] | 2012-11-09 | [6 empty] | 2013-04-19 | [5 empty] | 2014-01-30
AA925 | 2065 | 2015-02-05 | Magnetar Solar | Stowbridge Farm | Solar Photovoltaics |  |  | 24 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Green End, Stretham, Cambridgeshire | Cambridgeshire | Eastern | England | CB6 3LF | 551252 | 272416 | East Cambridgeshire District Council | 12/00732/ESF | [5 empty] | 2012-09-24 | [6 empty] | 2012-12-10 | [5 empty] | 2014-03-28
IF1024 | 2066 | 2014-08-26 | Stratton Hall Solar Park Limited | Stratton Hall Solar Park | Solar Photovoltaics |  |  | 11.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Walk Farm, Croft Lane, Stratton Hall, Ipswich, Suffolk | Suffolk | Eastern | England | IP10 0LR | 625674 | 239588 | Suffolk Coastal District Council | C/12/2059 | [5 empty] | 2012-10-04 | [6 empty] | 2013-03-22 |  |  |  |  | 2013-04-19 | 2014-03-07
C0979 | 2067 | 2015-05-18 | PS Renewables | Sutton Montis Road Solar Park / Sutton Bridge Solar Farm | Solar Photovoltaics |  |  | 5.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land OS 4200, Sutton Montis Road, Queen Camel, Yeovil | Somerset | South West | England |  | 360480 | 123924 | South Somerset District Council | 13/01697/FUL | [5 empty] | 2013-04-29 | [6 empty] | 2014-01-28 |  |  |  |  | 2014-09-01 | 2015-02-10
C3270 | 2068 | 2017-02-27 | Big 60 Million | Thame solar farm | Solar Photovoltaics |  |  | 4.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the east of Windmill Road, Towersey | Oxfordshire | South East | England | OX9 3QH | 473633 | 205988 | South Oxfordshire District Council | P14/S2242/FUL | APP/Q3115/W/15/3032498 |  |  |  |  | 2014-07-17 |  | 2015-02-13 | 2015-06-05 |  |  | 2015-10-29 | 2015-10-29 |  |  |  |  | 2016-09-16 | 2016-12-16
C2514 | 2069 | 2016-05-04 | Lumicity | The Engine Shed Field | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Old Engine Shed Field, Sutton Court Farm, (Land between Pineham & East Langdon) | Kent | South East | England |  | 633459 | 149347 | Dover District Council | 13/01106 | APP/X2220/W/15/3138584 |  |  |  |  | 2013-12-24 |  | 2015-09-18 | 2015-12-09 |  | 2016-04-29
C2876 | 2070 | 2014-08-14 | Camborne Energy Investments (10) Ltd | The Flatts - resubmission | Solar Photovoltaics |  |  | 6.75 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Parcel 0074, Flatts Lane, Farmborough, Bath, | Somerset | South West | England |  | 364135 | 159542 | Bath and North East Somerset Council | 14/01510/FUL | [5 empty] | 2014-03-24 |  | 2014-06-09
C3028 | 2071 | 2016-10-04 | United Photovoltaics | The Flit | Solar Photovoltaics |  |  | 10.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Parcel 9827, South East Of Yarnton And North Of Woodstock Road, Yarnton, Oxfordshire | Oxfordshire | South East | England | OX5 1 | 448774 | 212010 | Cherwell District Council | 14/00786/F | [5 empty] | 2014-05-20 | [6 empty] | 2014-08-07 |  |  |  |  | 2014-12-01 | 2015-03-30
C2224 | 2072 | 2015-05-29 | Lumicity | The Old Airfield | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The Old Airfield, Airfield Lane, Weston Longville, Norwich | Norfolk | Eastern | England | NR9 5JF | 609858 | 314993 | Broadland District Council | 20131702 | [5 empty] | 2013-12-03 | [6 empty] | 2014-03-04 |  |  |  |  | 2015-01-01 | 2015-03-31
C1701 | 2073 | 2014-11-06 | Lightsource Renewable Energy | Thorne Farm | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | N/O Thorne Farm, Thorne Hill, Minster, Ramsgate, Kent, CT12 5DS | Kent | South East | England | CT12 5DS | 633263 | 165267 | Thanet District Council | F/TH/13/0596 | [5 empty] | 2013-07-31 | [6 empty] | 2014-01-15 | [5 empty] | 2014-11-05
C1599 | 2074 | 2015-02-03 | Good Energy Generation | Tiers Cross Solar Farm | Solar Photovoltaics |  |  | 23.985 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rose Cottage Farm; Woodson Farm; Tierson Farm, Tiers Cross, Milford Haven, Dyfed | Dyfed | Wales | Wales | SA73 3TN | 190200 | 209976 | Pembrokeshire County Council | 13/0214/PA | [5 empty] | 2013-05-24 | [6 empty] | 2013-10-14 |  |  |  |  | 2013-12-19 | 2014-10-25
C1858 | 2075 | 2016-02-24 | Ovenden Plant Hire Limited | Tilmanstone Colliery | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Tilmanstone Colliery Tip, Pike Road, Eythorne, Dover | Kent | South East | England | CT15 4DJ | 628941 | 150723 | Dover District Council | 13/00654 | [5 empty] | 2013-08-15 | [6 empty] | 2014-03-12 |  |  |  |  | 2015-12-10 | 2016-01-25
IF1185 | 2076 | 2016-08-24 | Forest Heath District Council | Toggam Farm | Solar Photovoltaics |  |  | 12.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Newfen Gravel Drove, Lakenheath, Brandon, Suffolk, IP27 9LN | Suffolk | Eastern | England | IP27 9LN | 570115 | 284654 | Forest Heath District Council | F/2012/0741/FUL | [5 empty] | 2012-12-13 | [6 empty] | 2013-05-10 |  |  |  |  | 2016-02-06 | 2016-03-24
C3283 | 2077 | 2015-12-01 | NextEnergy Solar Fund (NESF) | Tower Hill Farm | Solar Photovoltaics |  |  | 8.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Cuttsheath Road And New Road, Tytherington, Wotton Under Edge, South Gloucestershire | Avon | South West | England | GL12 8QA | 367372 | 188828 | South Gloucestershire Council | PT14/2810/F | [5 empty] | 2014-07-16 | [6 empty] | 2014-10-15 |  |  |  | 2017-10-15 | 2015-01-01 | 2015-03-30
C2322 | 2078 | 2014-11-04 | Toyota Motor Manufacturing | Toyota Motor Manufacturing Uk - Deeside | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Toyota Motor Manufacturing Uk, Tenth Avenue, Deeside Industrial Park, Deeside, Clwyd | Clwyd | Wales | Wales | CH5 2TW | 331682 | 370582 | Flintshire County Council | 051425 | [5 empty] | 2013-10-30 | [6 empty] | 2013-12-19 |  |  |  |  | 2014-05-26 | 2014-08-26
C3240 | 2079 | 2016-05-10 | Lightsource Renewable Energy | Trench Farm | Solar Photovoltaics |  |  | 7.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Trench Farm, Red Hall Lane, Penley, Wrexham LL13 0NA | Clwyd | Wales | Wales |  | 338419 | 339068 | Wrexham County Borough Council | P/2014/0484 | [5 empty] | 2014-07-03 | [6 empty] | 2014-11-05 |  |  |  | 2019-11-05 | 2014-11-06 | 2015-03-30
IF1326 | 2080 | 2016-07-01 | Hive Energy | Troughton Farm | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stoke Road, Stoke Orchard, Cheltenham | Gloucestershire | South West | England | GL52 7R | 391748 | 228979 | Tewkesbury Borough Council | 12/01220/FUL | [5 empty] | 2013-02-11 | [6 empty] | 2014-07-22 |  |  |  |  | 2015-11-01 | 2016-03-23
C1522 | 2081 | 2015-03-19 | INRG Solar | Turweston Solar Farm | Solar Photovoltaics |  |  | 16.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Turweston Aerodrome, Whitfield Road, Biddlesden, Buckinghamshire | Buckinghamshire | South East | England | NN13 5YD | 461474 | 237534 | Aylesbury Vale District Council | 13/01561/APP | [5 empty] | 2013-06-14 | [6 empty] | 2013-09-10 |  |  |  |  | 2013-11-15 | 2014-12-19
C1307 | 2082 | 2015-09-30 | Kronos Solar | Upper Farm solar park | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Upper Farm Bradley Alresford Hampshire SO24 9SA | Hampshire | South East | England | SO24 9SA | 463037 | 141814 | Basingstoke and Deane Borough Council | 13/00653/FUL | 14/00023/REF |  |  |  |  | 2013-06-13 |  | 2014-01-15 |  |  |  | 2014-08-12 | 2014-08-12 |  |  |  |  | 2014-11-15 | 2015-03-30
C1788 | 2083 | 2018-09-04 | Foresight | Upper Huntingford Farm | Solar Photovoltaics |  |  | 7.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Upper Huntingford Farm Charfield, Wotton-Under-Edge, Gloucestershire, GL12 8EY | Gloucestershire | South West | England | GL12 8EY | 371971 | 193941 | Stroud District Council | S.14/0929/FUL | [5 empty] | 2014-04-15 | [6 empty] | 2014-07-14 |  |  |  |  | 2015-06-28 | 2016-01-16
C3016 | 2084 | 2015-04-02 | Lark Energy | Walnut Yard (Phase 1) | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The West Of Gelscoe House Farm Outbuildings Gelscoe Lane Diseworth | Leicestershire | East Midlands | England |  | 442964 | 322649 | North West Leicestershire District Council | 14/00408/FULM | [5 empty] | 2014-05-06 | [6 empty] | 2014-10-07 |  |  |  | 2017-10-07 | 2015-01-01 | 2015-03-31
C2898 | 2085 | 2018-03-02 | Foresight/ Vogt solar | Water Eaton Farm / Port Farm | Solar Photovoltaics |  |  | 34.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Water Eaton Farm, Latton | Wiltshire | South West | England | SN6 6JT | 412705 | 193851 | Wiltshire Council | 14/04326/FUL | [5 empty] | 2014-04-25 | [6 empty] | 2014-08-21 |  |  |  |  | 2014-10-01 | 2015-03-25
C1807 | 2086 | 2015-03-19 | Orta Solar | Wedgehill Farm | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Wedgehill Farm, Woodlands, Wimborne, Dorset | Dorset | South West | England | BH21 8LX | 407075 | 106873 | East Dorset District Council | 3/13/0669/FUL | [5 empty] | 2013-07-22 | [6 empty] | 2014-01-17 |  |  |  |  | 2014-10-01 | 2015-01-30
C2538 | 2087 | 2016-02-05 | Elveden Farms Ltd | West Farm (Barnham) | Solar Photovoltaics |  |  | 29 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land West Of West Farm Dukes Ride Barnham Suffolk | Suffolk | Eastern | England |  | 584276 | 277118 | St Edmundsbury Borough Council | DC/13/0801/FUL | APP/E3525/W/14/3001409 |  |  |  |  | 2013-12-03 |  | 2014-12-04 | 2015-02-02 |  | 2016-01-06
C2230 | 2088 | 2015-04-09 | Bluefield Solar | West Raynham | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Airfield, West Raynham, Fakenham, Norfolk | Norfolk | Eastern | England | NR21 | 585177 | 324968 | North Norfolk District Council | PF/13/1166 | [5 empty] | 2013-10-31 | [6 empty] | 2013-12-20 |  |  |  |  | 2014-09-23 | 2015-03-31
C2326 | 2089 | 2015-05-14 | Lightsource Renewable Energy | Westerfield Farm - resubmission | Solar Photovoltaics |  |  | 12.47 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Westerfield Farm, Carterton | Oxfordshire | South East | England |  | 427125 | 209714 | West Oxfordshire District Council | 13/1534/P/FP | APP/D3125/A/14/2214281 |  |  |  |  | 2013-10-29 |  | 2014-01-23 | 2014-02-27 |  |  | 2014-12-01 | 2014-12-01 |  |  |  | 2017-12-01 | 2015-02-04 | 2015-03-25
B1248 | 2090 | 2014-08-26 | Private Developer | Westover Farm - resubmission | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The South Of Longbarrow Westover Farm Barrow Hill Goodworth Clatford Andover Hampshire SP11 7SE | Hampshire | South East | England |  | 434623 | 140438 | Test Valley Borough Council | 12/02707/FULLN | [5 empty] | 2012-12-12 | [6 empty] | 2013-03-13 |  |  |  |  | 2013-09-30 | 2014-03-30
C1745 | 2091 | 2018-07-26 | NextEnery Solar Fund (NESF) | Whitley Farm (1 of 2) | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | On Land at, Whitley Wood Farm, Whitley Lane, Ashcott, Bridgwater | Somerset | South West | England |  | 344449 | 137081 | Sedgemoor District Council | 01/13/00015 | [5 empty] | 2013-07-17 | [6 empty] | 2013-10-15 | [5 empty] | 2014-03-31
C1746 | 2092 | 2018-07-26 | NextEnery Solar Fund (NESF) | Whitley Farm (2 of 2) | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | On Land at, Whitley Wood Farm, Whitley Lane, Ashcott, Bridgwater | Somerset | South West | England |  | 345206 | 136870 | Mendip District Council | 2013/1515 | [5 empty] | 2013-07-15 | [6 empty] | 2013-10-04 | [5 empty] | 2014-03-31
C3287 | 2093 | 2017-06-16 | Cenin Renewables | Whitton Mawr | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land east of Five Mile Lane | South Glamorgan | Wales | Wales | CF62 3AB | 308077 | 172202 | Vale of Glamorgan Council | 2014/00798/FUL | [5 empty] | 2014-07-18 | [6 empty] | 2014-11-21 |  |  |  | 2017-11-21 | 2016-11-15 | 2017-05-15
C1975 | 2094 | 2016-04-04 | EBS Energy LLP | Whitton solar farm | Solar Photovoltaics |  |  | 8.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Whitton Solar Farm Caynham Shropshire | Shropshire | West Midlands | England |  | 356500 | 273400 | Shropshire Council | 14/02873/FUL | APP/L3245/W/15/3014413 |  |  |  |  | 2014-06-30 |  | 2014-10-27 | 2015-10-08 |  | 2016-03-22
C2904 | 2095 | 2016-02-16 | Hive Energy | Winham Farm - resubmission | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at NGR 301672 103703 (Land West of Winham Farm) Westcott Devon | Devon | South West | England |  | 301672 | 103703 | Mid Devon District Council | 14/00536/MFUL | [5 empty] | 2014-04-07 | [6 empty] | 2014-07-04 |  |  |  |  | 2015-11-01 | 2015-12-01
IF1164 | 2096 | 2014-08-26 | Caerau Solar IQ | Woden Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cwrt Yr Ala Road, Michaelston-Le-Pit, Dinas Powys, South Glamorgan, CF5 | South Glamorgan | Wales | Wales |  | 313742 | 175059 | Vale of Glamorgan Council | 2012/01285/FUL | [5 empty] | 2012-12-06 | [6 empty] | 2013-03-18 | [5 empty] | 2014-03-26
A0505 | 2098 | 2014-10-02 | Inazin (previously Low carbon Solar Partners) | West Kingsmill Farm Solar Park | Solar Photovoltaics |  |  | 1.55 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | West Kingsmill Farm Kingsmill Park Road From Leigh Lane To Kingsmill Lake And Farm Hatt Saltash Cornwall | Cornwall | South West | England | PL12 6NB | 240828 | 62572 | Cornwall Council | PA11/01235 | [5 empty] | 2011-02-17 | [6 empty] | 2011-05-30 | [5 empty] | 2014-03-31
AA526 | 2100 | 2018-02-23 | Hallhill Developments | Dunbar Energy Park | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Spott Road Dunbar East Lothian | Lothian | Scotland | Scotland | EH42 1QL | 368814 | 677402 | East Lothian Council | 11/00868/PM | [5 empty] | 2011-10-04 | [6 empty] | 2012-03-07 |  |  |  | 2017-03-07
AA861 | 2101 | 2016-07-28 | Steadfast Molland Solar Ltd | Bommertown Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bommertown Farm, Bottreaux Mill, South Molton | Devon | South West | England | EX36 3PS | 281934 | 125747 | North Devon District Council | 54402 | APP/X1118/A/14/2211328 |  |  |  |  | 2012-07-30 |  | 2013-10-23 |  |  |  | 2014-08-05 | 2014-08-05 |  |  |  |  | 2016-02-06 | 2015-12-16
AA900 | 2102 | 2016-03-04 | PV Sunpower Ltd | West Ditchen Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Hornacott Chapel Boyton Launceston Cornwall | Cornwall | South West | England |  | 230312 | 94341 | Cornwall Council | PA12/02141 | [5 empty] | 2012-03-02 | [6 empty] | 2014-10-03 | [5 empty] | 2016-02-26
AA982 | 2103 | 2014-10-01 | Solar Power South | Lower Marsh Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Kingston St Mary, Somerset | Somerset | South West | England |  | 321852 | 130297 | Taunton Deane Borough Council | 20/11/0026 | [5 empty] | 2011-11-18 | [6 empty] | 2012-02-07 | [5 empty] | 2014-03-24
B0615 | 2104 | 2014-10-01 | Anesco | Bodorgan Solar Farm | Solar Photovoltaics |  |  | 12.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tai Moelion farm near Aberffraw, Anglesey | Isle of Anglesey | Wales | Wales |  | 238717 | 367342 | Isle of Anglesey County Council | 10C114A | [5 empty] | 2012-11-15 | [6 empty] | 2013-02-09 |  |  |  |  | 2013-09-15 | 2014-06-20
B0849 | 2105 | 2014-11-05 | Eco Sustainable Solutions | Chapel Lane Parley Solar Farm Phase 2 | Solar Photovoltaics |  |  | 36 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chapel Lane, Parley, Christchurch, Dorset | Dorset | South West | England | BH23 6BG | 410222 | 99598 | Christchurch Borough Council | 8/13/0332 | [5 empty] | 2013-07-16 | [6 empty] | 2013-09-26 |  |  |  |  | 2014-03-01 | 2014-08-29
B1208 | 2106 | 2019-12-04 | Private Developer | Buckwell Farm Solar Park | Solar Photovoltaics |  |  | 8.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Buckwell Farm, Pen Y Cae Mawr Usk Monmouthshire | Gwent | Wales | Wales | NP15 1LX | 342153 | 196498 | Monmouthshire County Council | DC/2013/00925 | [5 empty] | 2013-10-31 | [6 empty] | 2014-08-06 |  |  |  | 2019-08-06
B1278 | 2107 | 2015-12-15 | Conergy | Arkwright Solar Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To West Of Duckmanton and North Of Tom Lane Chesterfield Derbyshire | Derbyshire | East Midlands | England |  | 443707 | 372522 | Chesterfield Borough Council | CHE/14/00644/FUL | [5 empty] | 2014-09-15 | [6 empty] | 2015-02-24 |  |  |  | 2018-04-14 | 2015-06-01 | 2015-12-18
B1348 | 2108 | 2020-05-21 | Lightsource Renewable Energy | Charity Farm (Burlton Solar Farm) | Solar Photovoltaics |  |  | 14.4 | n/a |  |  | 14.67 | n/a | n/a | n/a | Ground | Operational | Operational | Land east of B4397, Charity Farm, Burlton, Shropshire | Shropshire | West Midlands | England | SY4 5SX | 345545 | 325520 | Shropshire Council | 14/02537/FUL | [5 empty] | 2014-06-12 | [6 empty] | 2014-09-29 |  |  |  | 2017-09-29 | 2016-05-28 | 2016-08-02
B1350 | 2109 | 2015-05-28 | Foresight | Verwood Solar Farm | Solar Photovoltaics |  |  | 20.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Manor Farm St Michaels Road Verwood Dorset | Dorset | South West | England | BH31 6JA | 408332 | 107310 | East Dorset District Council | 3/14/0457/FUL | [5 empty] | 2014-04-15 | [6 empty] | 2014-07-31 |  |  |  |  | 2014-11-01 | 2015-02-25
B1367 | 2110 | 2015-09-30 | Kronos Solar | Parciau Farm Solar Park | Solar Photovoltaics |  |  | 13.86 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Parciau Farm, Griffiths Crossing, Caernarfon, Gwynedd | Gwynedd | Wales | Wales | LL55 1TS | 250255 | 365482 | Gwynedd Council | C14/0498/20/LL | [5 empty] | 2014-06-06 | [6 empty] | 2014-09-22 |  |  |  |  | 2014-11-15 | 2015-03-23
B1385 | 2111 | 2017-02-01 | Trina Solar | Smith Hall Farm Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Smith Hall Farm Smith Hall Lane Hulland Ward Derbyshire DE6 3ES | Derbyshire | East Midlands | England | DE6 3ES | 426765 | 346192 | Derbyshire Dales District Council | 14/00415/FUL | [5 empty] | 2014-06-27 | [6 empty] | 2014-09-24 |  |  |  |  | 2015-11-15 | 2016-03-29
B1391 | 2112 | 2015-05-14 | Lightsource Renewable Energy | Bystock Solar Farm | Solar Photovoltaics |  |  | 4.07 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The West Of St Johns Road Bystock Farm Exmouth | Devon | South West | England | EX8 5 | 302353 | 83979 | East Devon District Council | 14/1560/MFUL | [5 empty] | 2014-07-03 | [6 empty] | 2014-09-30 |  |  |  |  | 2015-01-29 | 2015-03-31
B1424 | 2113 | 2017-04-26 | Green Energy UK Direct | Strevenage Road Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land opposite Wymondley Grid S, Sperberry Hill, St. Ippolyts, Hitchin | Hertfordshire | Eastern | England | SG4 7 | 520223 | 226459 | North Hertfordshire District Council | 15/01532/1 | APP/X1925/W/16/3156843 |  |  |  |  | 2015-06-18 |  | 2016-02-24 | 2016-10-14 |  | 2017-04-07
B1430 | 2114 | 2016-03-04 | Solstice Renewables Ltd | Bedborough Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bedborough Farm, Land At Uddens Drive Wimborne Dorset | Dorset | South West | England | BH21 7BQ | 405429 | 101978 | East Dorset District Council | 3/14/0790/FUL | [5 empty] | 2014-08-14 | [6 empty] | 2014-11-03 |  |  |  | 2017-11-03 | 2015-07-15 | 2016-02-26
B1444 | 2117 | 2017-02-27 | Cranham Golf Course | Cranham Golf Course Solar Park | Solar Photovoltaics |  |  | 2.642 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cranham Golf Course St. Marys Lane Upminster | Greater London | London | England |  | 558338 | 186896 | Havering London Borough Council | P0907.14 | APP/B5480/A/14/2227508 |  |  |  |  | 2014-06-27 |  | 2014-10-02 | 2014-11-25 |  |  | 2015-08-13 | 2015-08-13 |  |  |  |  | 2016-09-21 | 2016-12-21
B1455 | 2118 | 2015-04-29 | Dillington Farms Ltd | Hurcott Copse Solar Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hurcott Copse, Boxstone Hill, Hurcott, Ilminster, Somerset | Somerset | South West | England | TA19 0JS | 339249 | 115679 | South Somerset District Council | 14/02977/FUL | [5 empty] | 2014-07-10 | [6 empty] | 2014-09-19 |  |  |  |  | 2014-12-15 | 2015-03-20
C0639 | 2119 | 2015-08-27 | Private Developer | HALVASSO - SOLAR FARM | Solar Photovoltaics |  |  | 2.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Formerly Boundis Farm, Halvasso, Penryn, Cornwall | Cornwall | South West | England | TR10 9BY | 174289 | 32552 | Cornwall Council | PA12/09502 | [5 empty] | 2012-10-10 | [6 empty] | 2018-01-11
C0646 | 2120 | 2014-10-01 | Anesco | Grange Farm Solar Farm | Solar Photovoltaics |  |  | 4.94 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | N/O Grange Farm, Nynehead, Wellington, Somerset | Somerset | South West | England | TA21 0BU | 314364 | 123660 | Taunton Deane Borough Council | 23/12/0032 | [5 empty] | 2012-10-15 | [6 empty] | 2013-01-14 | [5 empty] | 2013-08-28
C0903 | 2121 | 2018-09-04 | Foresight | Trehawke Barton (Doddycross) Solar Farm | Solar Photovoltaics |  |  | 10.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Trehawke Barton Blunts Liskeard Cornwall | Cornwall | South West | England | PL14 3RH | 231165 | 62264 | Cornwall Council | PA12/11024 | [5 empty] | 2012-11-23 | [6 empty] | 2013-06-21 | [5 empty] | 2014-03-31
C0919 | 2122 | 2015-08-27 | Lightsource Renewable Energy | Villaton Farm Solar Park | Solar Photovoltaics |  |  | 12.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Villaton Farm And Killarney Boyton, Launceston, Cornwall | Cornwall | South West | England | PL15 8NT | 228980 | 94614 | Cornwall Council | PA14/08272 | [5 empty] | 2014-09-11 |  | 2014-12-19
C0926 | 2123 | 2015-08-27 | Lightsource Renewable Energy | Hornacott Solar Park | Solar Photovoltaics |  |  | 29 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land South Of Hornacott Chapel Boyton Launceston Cornwall | Cornwall | South West | England |  | 230646 | 94753 | Cornwall Council | PA14/08270 | [5 empty] | 2014-09-11 |  | 2014-12-19
C1116 | 2124 | 2016-02-05 | Antigua Solar | Butteriss Solar Park | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land Adjoining Butteriss Farm, Edgcumbe, Penryn, Cornwall | Cornwall | South West | England | TR10 9EF | 171606 | 32741 | Cornwall Council | PA13/11664 | APP/D0840/A/14/2229290 |  |  |  |  | 2014-01-23 |  | 2014-06-30 | 2014-12-15 |  | 2016-01-28
C1173 | 2125 | 2016-04-25 | Gruene Energien | Newton Ferrers solar park | Solar Photovoltaics |  |  | 19.54 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land In Newton Ferrers Callington Cornwall | Cornwall | South West | England | PL17 7HS | 235734 | 66376 | Cornwall Council | PA14/04185 | [5 empty] | 2014-05-07 | [6 empty] | 2014-08-01 |  |  |  |  | 2016-01-01 | 2016-03-29
C1175 | 2126 | 2016-07-28 | Second Solar Project | Nancrossa Farm solar park | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nancrossa Farm Rame Cross Penryn Cornwall | Cornwall | South West | England | TR10 9EA | 172731 | 33747 | Cornwall Council | PA14/04493 | APP/D0840/W/15/3002512 |  |  |  |  | 2014-05-14 |  | 2014-09-30 | 2015-03-04 |  |  | 2015-09-08 | 2015-09-08 |  |  |  | 2018-09-08 | 2016-01-05 | 2016-03-31
C1198 | 2127 | 2014-10-01 |  | Pitts Farm (revised application) | Solar Photovoltaics |  |  | 2.64 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chilcote Lane, Chilcote | Somerset | South West | England | BA5 3DX | 359176 | 146235 | Mendip District Council | 2013/0526 | [5 empty] | 2013-04-10 | [6 empty] | 2013-06-07 | [5 empty] | 2014-03-28
C1299 | 2128 | 2015-05-29 | Green Switch Solutions | Walmoor Farm solar park | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To South West Of Greenfields Grove Road Retford Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 | 472106 | 378955 | Bassetlaw District Council | 14/00034/FUL | [5 empty] | 2014-01-21 | [6 empty] | 2014-04-22 |  |  |  |  | 2015-02-20 | 2015-03-27
C1337 | 2129 | 2014-10-01 | Elgin Energy EsCo | Trequite Farm solar park (resubmission) | Solar Photovoltaics |  |  | 9.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Trequite Farm, Menheniot, Liskeard | Cornwall | South West | England | PL14 3RQ | 232069 | 61167 | Cornwall Council | PA13/04650 | [5 empty] | 2013-05-24 | [6 empty] | 2013-08-22 | [5 empty] | 2014-03-31
C1733 | 2132 | 2017-02-27 | Lightsource Renewable Energy | Bentley Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | BENTLEY ESTATE, UCKFIELD, EAST SUSSEX, TN22 5QP | East Sussex | South East | England |  | 548420 | 117019 | Wealden District Council | WD/2014/1245/MAJ | [5 empty] | 2014-06-20 |  | 2014-08-28 | 2015-03-23 |  |  | 2015-07-23 | 2015-07-23 |  |  |  |  | 2015-09-23 | 2015-12-17
C1789 | 2133 | 2014-10-01 | Lightsource Renewable Energy | New Row Farm | Solar Photovoltaics |  |  | 3.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | New Row Farm, Yelling Mill Lane, Downside, Shepton Mallet | Somerset | South West | England | BA4 4JT | 363204 | 145130 | Mendip District Council | 2013/1510 | [5 empty] | 2013-08-05 | [6 empty] | 2013-11-11 | [5 empty] | 2014-03-31
C1901 | 2134 | 2016-02-05 | juwi Renewable Energies | Norwood Park Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Norwood Park Farm, Wick Lane, Glastonbury | Somerset | South West | England | BA6 8JS | 352554 | 138982 | Mendip District Council | 2013/1749 | APP/Q3305/W/15/3011465 |  |  |  |  | 2013-08-27 |  | 2014-10-03 | 2015-05-20 |  | 2016-01-06
C1997 | 2135 | 2015-06-19 | Wessex Solar Energy | MALMAYNES HALL FARM | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | LAND OFF MALMAYNES HALL FARM, MALMAYNES HALL ROAD, STOKE, ROCHESTER, KENT | Kent | South East | England |  | 581725 | 176147 | Medway Council | MC/14/2082 | [5 empty] | 2014-07-31 | [6 empty] | 2014-11-06 |  |  |  | 2017-11-06 | 2014-11-15 | 2015-03-31
C2021 | 2136 | 2014-10-02 | Solar Planning Limited | Crucis Park | Solar Photovoltaics |  |  | 12.46 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Crucis Park, Barnsley Road, Ampney Crucis, Cirencester, Gloucestershire, GL7 5DX | Gloucestershire | South West | England |  | 406095 | 202822 | Cotswold District Council | 13/03656/FUL | [5 empty] | 2013-08-22 | [6 empty] | 2013-12-20 |  |  |  |  | 2014-03-01 | 2014-07-31
C2158 | 2137 | 2015-05-14 | Lightsource Renewable Energy | Treguff Farm - resubmission | Solar Photovoltaics |  |  | 4.36 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Treguff Farm, St. Mary Church, Cowbridge | South Glamorgan | Wales | Wales | CF71 7LT | 302265 | 171141 | Vale of Glamorgan Council | 2013/00912/FUL | [5 empty] | 2013-09-24 |  | 2014-01-17 |  |  |  | 2014-08-12 | 2014-08-12 |  |  |  |  | 2014-10-28 | 2015-02-11
C2162 | 2138 | 2015-09-30 | Kronos Solar | Kenardington Place Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Kenardington Place Farm, Appledore Road, Kenardington, Ashford, Kent, TN26 2LZ | Kent | South East | England | TN26 2LZ | 597181 | 132855 | Ashford Borough Council | 13/01074/AS | [5 empty] | 2013-10-07 |  | 2014-01-23 |  |  |  | 2014-09-15 | 2014-09-15 |  |  |  |  | 2015-01-01 | 2015-03-31
C2169 | 2139 | 2015-05-14 | Lightsource Renewable Energy | Henbury Quarry | Solar Photovoltaics |  |  | 3.92 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adj To Henbury Quarry Henbury Plantation Old Market Road Corfe Mullen Wimborne Dorset BH21 3QZ | Dorset | South West | England | BH21 3QZ | 396735 | 97102 | East Dorset District Council | 3/13/0948/FUL | [5 empty] | 2013-09-20 | [6 empty] | 2014-05-28 |  |  |  |  | 2014-12-01 | 2015-03-31
C2279 | 2140 | 2015-04-13 | Solar Park Developments | Grange Farm (Kirkby on Bain) | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | and at Grange Farm, Kirkby Lane, Kirkby-on-Bain, Woodhall Spa, Lincolnshire, LN10 6YY | Lincolnshire | East Midlands | England | LN10 6YY | 523131 | 362337 | East Lindsey District Council | S/094/01115/14 | [5 empty] | 2014-07-01 | [6 empty] | 2014-09-30 |  |  |  |  | 2015-02-01 | 2015-03-30
C2314 | 2141 | 2014-10-07 | Solartech Ltd | Tas Valley | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land North Of Tas Valley View Station Road Flordon Norfolk | Norfolk | Eastern | England |  | 619515 | 297081 | South Norfolk Council | 2014/0511 | [5 empty] | 2014-03-17 | 2014-08-26
C2394 | 2142 | 2014-10-06 | Private Developer | Court Farm | Solar Photovoltaics |  |  | 8.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Forming Part Of Court Farm, Magor Road, Newport, South Wales | Gwent | Wales | Wales |  | 339241 | 189511 | Newport City Council | 13/1203 | [5 empty] | 2013-11-15 |  | 2014-10-01
C2404 | 2143 | 2015-08-14 | NextEnergy Solar Fund | Boxted Airfield | Solar Photovoltaics |  |  | 18.8 | n/a |  | 1.4 |  | n/a | n/a | n/a | Ground | Operational | Operational | Langham, Colchester | Essex | Eastern | England | CO4 5NW | 601454 | 231228 | Colchester Borough Council | 145101 | [5 empty] | 2014-06-16 | [6 empty] | 2014-09-15 |  |  |  |  | 2014-11-26 | 2015-03-19
C2420 | 2144 | 2015-04-01 | Low Carbon | Rectory Farm/Emberton | Solar Photovoltaics |  |  | 9 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The East of Rectory Farm Newton Road Emberton | Buckinghamshire | South East | England | MK46 5DN | 489570 | 249520 | Milton Keynes Council | 14/00407/FUL | [5 empty] | 2014-02-26 | [6 empty] | 2014-09-12 |  |  |  |  | 2014-12-01 | 2015-03-31
C2424 | 2145 | 2017-03-24 | Martifer Solar (Voltalia) | St Francis Court Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Francis Court Farm (west Of The M5 Adjacent To Cutton Alders Wood, South Of Cutton Farm ) Poltimore | Devon | South West | England | EX4 0BQ | 296731 | 97379 | East Devon District Council | 13/2568/MFUL | [5 empty] | 2013-11-29 | [6 empty] | 2014-05-07 |  |  |  |  | 2015-10-15 | 2017-02-01
C2513 | 2147 | 2014-09-19 | Locogen | Limolands Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Limolands Farm, Vaggs Lane, Hordle, Lymington | Hampshire | South East | England | SO41 0FP | 426921 | 96715 | New Forest National Park Authority | 14/00470 | [5 empty] | 2014-06-11 | 2014-08-15
C2523 | 2148 | 2017-09-18 | Eastleigh Borough Council | Lower Russells Field | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Expired | Planning Permission Expired | Lower Russell's Field Itchen Valley Country Park Allington Lane West End | Hampshire | South East | England | SO50 7D | 445963 | 115802 | Eastleigh Borough Council | F/13/73809 | [5 empty] | 2013-12-19 | [6 empty] | 2014-05-04 |  |  |  | 2017-05-04
C2586 | 2149 | 2017-08-16 | Lightsource Renewable Energy | Manor Farm (Thruxton) | Solar Photovoltaics |  |  | 12.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land North Of Snoddington Road Manor Farm Thruxton Andover Hampshire | Hampshire | South East | England |  | 425756 | 145565 | Test Valley Borough Council | 14/01830/FULLN | [5 empty] | 2014-08-05 | 2014-10-06
C2627 | 2150 | 2018-11-26 | Green Switch Solutions - SOLD | Berry Court Farm | Solar Photovoltaics |  |  | 4.23 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Berry Court Farm, New Road, Little London, Tadley | Hampshire | South East | England | RG26 5EU | 461955 | 159138 | Basingstoke and Deane Borough Council | 14/02338/FUL | [5 empty] | 2014-08-27 | [6 empty] | 2015-04-23 |  |  |  | 2018-04-23 | 2016-10-01 | 2016-12-01
C2670 | 2151 | 2015-06-19 | Solar century / Magnetar Solar | Walkers Wood Solar Park | Solar Photovoltaics |  |  | 27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Green Lane Off Straight Mile Ranby Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 8 | 466740 | 379967 | Bassetlaw District Council | 14/00681/FUL | [5 empty] | 2014-05-27 | [6 empty] | 2014-09-18 |  |  |  |  | 2014-10-01 | 2015-03-10
C2685 | 2152 | 2015-04-15 | Vento Ludens | Odell Glebe Solar Farm | Solar Photovoltaics |  |  | 16.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At The Old Airfield Site Podington Airfield Airfield Road (Odell Glebe Solar Farm) Podington | Bedfordshire | Eastern | England | NN29 7XA | 495930 | 260200 | Bedford Borough Council | 14/01333/MAF | [5 empty] | 2014-06-26 | [6 empty] | 2014-09-22 |  |  |  |  | 2014-12-22 | 2015-03-31
C2713 | 2153 | 2016-02-04 | Bath & West Community Energy Ltd | Hunstrete (Wilmington Farm) | Solar Photovoltaics |  |  | 2.34 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Parcel 0153, Chelwood Road, Marksbury, Bath | Somerset | South West | England | BA2 9AD | 365003 | 161514 | Bath and North East Somerset Council | 14/00424/FUL | [5 empty] | 2014-02-10 | [6 empty] | 2014-06-24 |  |  |  |  | 2014-10-01 | 2014-12-30
C2724 | 2154 | 2017-10-18 | Sigma Solar Limited / OPDE | Lower Severalls Farm | Solar Photovoltaics |  |  | 10.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent Lower Severalls Farm, Lower Severalls Farm Road ,Crewkerne, Somerset | Somerset | South West | England | TA18 7NX | 345439 | 111331 | South Somerset District Council | 14/03128/FUL | [5 empty] | 2014-07-15 | [6 empty] | 2014-09-19 |  |  |  |  | 2015-10-05 | 2017-10-18
C2725 | 2155 | 2014-10-06 | AVIC-PCI | Whitebreads Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land south of A1066 Thetford Road | Norfolk | Eastern | England |  | 602536 | 281162 | Breckland Council | 3PL/2014/0143/F | [5 empty] | 2014-02-12 |  | 2014-07-14
C2747 | 2156 | 2014-10-06 | Guston A Solar Farm Ltd & Guston C Solar Farm Ltd | Guston Court Farm | Solar Photovoltaics |  |  | 27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Guston Court Farm, East Langdon Road, Guston, Dover, CT15 5EX | Kent | South East | England |  | 633530 | 144887 | Dover District Council | 14/00153 | [5 empty] | 2014-02-19 |  | 2014-09-26
C2781 | 2157 | 2016-08-02 | Quercus Renewable Holding 2 | Burton Farm | Solar Photovoltaics |  |  | 4.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Burton Farm Bishopton Stratford-upon-Avon | Warwickshire | West Midlands | England | CV37 0RW | 418054 | 257281 | Stratford on Avon District Council | 14/00536/FUL | [5 empty] | 2014-02-18 | [6 empty] | 2014-07-10 |  |  |  |  | 2015-01-28 | 2015-03-15
C2799 | 2158 | 2015-04-14 | Elgin Energy EsCo | Sundorne Grove | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Development Land At Sundorne Battlefield Shrewsbury Shropshire | Shropshire | West Midlands | England | SY1 4LL | 352294 | 315486 | Shropshire Council | 14/00759/FUL | [5 empty] | 2014-03-18 | [6 empty] | 2014-08-28 |  |  |  |  | 2015-01-01 | 2015-03-31
C2837 | 2159 | 2017-08-23 | Good Energy Generation | Lower End Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lower End Farm Long Street Marston Devizes | Wiltshire | South West | England | SN10 5SL | 397396 | 156384 | Wiltshire Council | 14/02273/FUL | [5 empty] | 2014-03-12 | [6 empty] | 2014-08-26 |  |  |  |  | 2015-05-30 | 2015-06-30
C2848 | 2160 | 2016-05-20 | Skegness Solar Park | Skegness Solar Park | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Coronation Fmar, Burgh Road West, Skegness, Lincs | Lincolnshire | East Midlands | England |  | 553659 | 364456 | East Lindsey District Council | S/023/01092/14 | [5 empty] | 2014-09-10 | [6 empty] | 2014-12-10 |  |  |  | 2017-12-10 | 2015-09-30 | 2015-12-01
C2857 | 2162 | 2018-07-05 | NESF (formerly Lark Energy) | Land north of Temple Normanton | Solar Photovoltaics |  |  | 4.85 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The East Of The A617 And North Of The Sewage Disposal Works Postmans Lane Temple Normanton | Derbyshire | East Midlands | England |  | 442015 | 367962 | North East Derbyshire District Council | 14/00806/FL | [5 empty] | 2014-08-14 | [6 empty] | 2014-12-17 |  |  |  | 2017-12-17 | 2015-12-15 | 2016-03-31
C2929 | 2164 | 2015-07-27 | Private Developer | Helland Meads - resubmission | Solar Photovoltaics |  |  | 1.242 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pondpool Lane, Helland, North Curry, Taunton | Somerset | South West | England | TA3 6DU | 332821 | 124658 | Taunton Deane Borough Council | 24/14/0020 | [5 empty] | 2014-04-09 | [6 empty] | 2014-06-30 |  |  |  |  | 2014-09-29 | 2014-11-01
C2933 | 2165 | 2018-09-04 | Foresight | Crow Trees Farm | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Crow Trees Farm, Pinxton Lane, Fulwood, Sutton In Ashfield | Nottinghamshire | East Midlands | England | NG17 1JF | 447020 | 356903 | Ashfield District Council | V/2014/0188 | [5 empty] | 2014-04-24 | [6 empty] | 2014-06-25 |  |  |  |  | 2015-11-15 | 2016-03-23
C2962 | 2166 | 2016-05-24 | Mellington Farm | Priest Weston | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Priest Weston, Montgomery, Powys | Shropshire | West Midlands | England | SY15 6DE | 328904 | 297350 | Shropshire Council | 14/01815/FUL | [5 empty] | 2014-04-22 | [6 empty] | 2014-07-18 |  |  |  |  | 2014-12-10 | 2015-03-10
C2980 | 2167 | 2014-09-30 | REG Solarpower | Mendennick Farm | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Mendennick Farm Millbrook Torpoint | Cornwall | South West | England | PL11 3AU | 240703 | 52965 | Cornwall Council | PA14/04646 | [5 empty] | 2014-06-09 |  | 2014-09-26
C2991 | 2169 | 2015-04-20 | Vogt Solar | Horam | Solar Photovoltaics |  |  | 8.1 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land AND WEST OF HORAM MANOR, HORAM | East Sussex | South East | England | TN21 0YD | 557342 | 117038 | Wealden District Council | WD/2014/1642 | [5 empty] | 2014-08-07 | [6 empty] | 2014-09-19 |  |  |  | 2017-09-19 | 2015-01-01 | 2015-03-31
C3000 | 2170 | 2016-05-30 | Green Switch Solutions | Clay Tye Farm | Solar Photovoltaics |  |  | 15.93 | n/a |  |  |  | n/a | n/a | n/a | Ground | Secretary of State - Refusal | Application Refused | Land Associated to Clay Tye Farm Clay Tye Road & South of St Marys Lane Upminster | Greater London | London | England |  | 559850 | 186750 | Havering London Borough Council | P1249.14 | APP/B5480/W/15/3007618 |  |  |  |  | 2014-09-08 |  | 2015-01-06 | 2015-06-02 |  | 2016-02-02 |  |  | 2015-09-30 | 2016-02-02
C3006 | 2171 | 2015-01-29 | Lightsource Renewable Energy | Turves/Burtnhouse Solar Farm extension | Solar Photovoltaics |  |  | 4.67 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North West Of 15 Burnthouse Sidings Turves Cambridgeshire | Cambridgeshire | Eastern | England | PE7 2HS | 533992 | 294234 | Fenland District Council | F/YR14/0354/F | [5 empty] | 2014-04-25 | [6 empty] | 2014-07-24 |  |  |  |  | 2014-11-15 | 2015-01-21
C3017 | 2172 | 2014-09-25 | juwi Renewable Energies | Home Farm (Swaffham) | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Home Farm, Swaffham, Norfolk, PE37 | Norfolk | Eastern | England |  | 583795 | 307864 | Breckland Council | 3PL/2014/0272/F | [5 empty] | 2014-05-15 | 2014-07-18
C3018 | 2173 | 2015-06-19 | Renewable Energy Systems Ltd (RES) | Coombe Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Coombe Farm, Exe View Road, Lympstone, Exmouth, Devon | Devon | South West | England | EX8 5AZ | 301601 | 85206 | East Devon District Council | 14/1233/MFUL | [5 empty] | 2014-05-15 | [6 empty] | 2014-09-26 |  |  |  |  | 2015-01-01 | 2015-03-30
C3037 | 2174 | 2016-11-18 | British Solar Renewables | Higher Hill Farm (extension) | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Higher Hill Farm, Butleigh Hill, Butleigh, Glastonbury, Somerset | Somerset | South West | England | BA6 8TW | 351373 | 131348 | Mendip District Council | 2014/0646/FUL | [5 empty] | 2014-05-14 | [6 empty] | 2014-09-18 |  |  |  |  | 2015-09-15 | 2016-05-01
C3062 | 2175 | 2016-03-22 | INRG (Solar Park) 14 | Mount Farm | Solar Photovoltaics |  |  | 22 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off Longdon Hill, Wickhamford | Hereford and Worcester | West Midlands | England |  | 406250 | 241513 | Wychavon District Council | 14/01029 | APP/H1840/W/14/3001928 |  |  |  |  | 2014-05-13 |  | 2014-09-15 | 2015-02-02 |  |  | 2015-07-06 | 2015-07-06 |  |  |  | 2018-07-06 | 2016-01-15 | 2016-03-23
C3070 | 2176 | 2016-01-19 | KS SPV53 Ltd | Hafod-Y-Dafal Farm | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hafod-Y-Dafal Farm, Aberbeeg, Blaina, Gwent | Gwent | Wales | Wales | NP13 2ER | 320100 | 203640 | Blaenau Gwent County Borough Council | C/2014/0126 |  |  |  | 42012 |  | 2014-05-16 | [6 empty] | 2014-11-07 |  |  |  | 2019-11-07 | 2015-11-15 | 2015-12-22
C3079 | 2178 | 2015-04-15 | Lark Energy | Barr Farm | Solar Photovoltaics |  |  | 1.81 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Barr Farm, Stafford Road, Standeford, South Staffordshire | Staffordshire | West Midlands | England | WV10 7BN | 391529 | 307941 | South Staffordshire Council | 14-00406-FUL | [5 empty] | 2014-06-04 | [6 empty] | 2014-08-19 |  |  |  |  | 2014-11-01 | 2015-04-01
C3081 | 2179 | 2016-03-14 | British Aerospace Defence Limited | BAE Samlesbury Aerodrome | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | BAE Samlesbury Aerodrome Whalley Road Samlesbury Blackburn Lancashire BB2 7LB | Lancashire | North West | England |  | 361989 | 430666 | South Ribble Borough Council | 07/2014/0430/FUL | [5 empty] | 2014-06-23 | [6 empty] | 2014-09-18 |  |  |  |  | 2015-04-15 | 2015-05-01
C3096 | 2180 | 2017-07-03 | John Laing Environmental Assets Group | Shoals Hook Farm | Solar Photovoltaics |  |  | 12.14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land east of Shoals Hook Farm, Shoals Hook Lane, Haverfordwest, SA61 2XN | Dyfed | Wales | Wales | SA61 2XN | 197321 | 216854 | Pembrokeshire County Council | 14/0056/PA | [5 empty] | 2014-05-06 | [6 empty] | 2014-10-03 |  |  |  |  | 2015-01-01 | 2015-03-31
C3119 | 2181 | 2015-08-27 | Lightsource Renewable Energy | Manor Farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north of Leighton Road, Eggington, Leighton Buzzard | Bedfordshire | Eastern | England | LU7 9PB | 495555 | 226052 | Central Bedfordshire Council | CB/14/03113/FULL | [5 empty] | 2014-08-18 | [6 empty] | 2015-01-23 |  |  |  | 2018-01-23 | 2015-03-01 | 2015-03-30
C3123 | 2182 | 2015-08-19 |  | Littlewood Farm | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Nw of Littlewood Farm Tathall End Hanslope | Buckinghamshire | South East | England | MK19 7NF | 481892 | 248274 | Milton Keynes Council | 14/01227/FUL | [5 empty] | 2014-06-04 | [6 empty] | 2014-10-03 |  |  |  |  | 2014-11-15 | 2015-03-26
C3135 | 2183 | 2015-08-04 | Solstice Renewables | Orchard solar park | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land Surrounding Walnut Cottages, Oil Mill Lane, Clyst St Mary | Devon | South West | England |  | 299134 | 90217 | East Devon District Council | 14/1379/MFUL | APP/U1105/W/15/3007994 |  |  |  |  | 2014-06-06 |  | 2014-09-15 | 2015-04-10 |  | 2015-07-24
C3145 | 2184 | 2016-12-22 | Trina Solar | Cherry Tree Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cherry Tree Farm Chesterfield Road Duckmanton Chesterfield S44 5JG | Derbyshire | East Midlands | England | S44 5JG | 443978 | 371339 | North East Derbyshire District Council | 14/00563/FL | [5 empty] | 2014-05-29 | [6 empty] | 2014-09-11 |  |  |  |  | 2015-11-15 | 2016-03-30
C3150 | 2185 | 2016-03-14 | G & D Castle Ltd | Lodge Farm | Solar Photovoltaics |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South East Of Lodge Farm Bridge Road Broughton | Cambridgeshire | Eastern | England | PE28 3AZ | 527311 | 276335 | Huntingdonshire District Council | 1400783FUL | [5 empty] | 2014-06-03 | [6 empty] | 2014-09-05 |  |  |  |  | 2015-06-15 | 2015-09-25
C3165 | 2186 | 2017-06-30 | Solar Planning | Bumpers Farm Phase 1 | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Bumpers Farm, Ilmer Lane, Ilmer, Buckinghamshire | Buckinghamshire | South East | England | HP17 8 | 476290 | 206089 | Aylesbury Vale District Council | 14/01926/APP | APP/K0425/W/14/3001711 |  |  |  |  | 2014-07-11 |  | 2014-09-05 | 2015-02-04 |  |  | 2015-10-26 | 2015-10-26 |  |  |  |  | 2017-01-25 | 2017-03-25
C3166 | 2187 | 2015-07-23 | Push Energy/ NextEnergy Solar Fund (NESF) | Birch Airfield | Solar Photovoltaics |  |  | 5.62 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | ch Airfield, Blind Lane, Colchester | Essex | Eastern | England | CO5 9XE | 592218 | 219053 | Colchester Borough Council | 145133 | [5 empty] | 2014-06-23 | [6 empty] | 2014-09-16 |  |  |  |  | 2015-05-06 | 2015-06-29
C3168 | 2188 | 2016-10-04 | United Photovoltaics | Gaultney Solar Park | Solar Photovoltaics |  |  | 20.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Gaultney Farm, Pipewell Road, Desborough | Northamptonshire | East Midlands | England | NN14 2SW | 481773 | 284102 | Kettering Borough Council | KET/2014/0391 | [5 empty] | 2014-06-17 | [6 empty] | 2014-09-05 |  |  |  |  | 2014-12-01 | 2015-03-31
C3171 | 2189 | 2014-09-19 | Wessex Solar Energy | West Holcombe | Solar Photovoltaics |  |  | 5.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at NGR 299298 125070 (East Of Bowdens Lane) Shillingford Devon | Devon | South West | England |  | 298519 | 125428 | Mid Devon District Council | 14/00903/MFUL | [5 empty] | 2014-06-16 | 2014-08-20
C3176 | 2190 | 2016-02-29 | SBC Renewables | Puriton Landfill Solar Farm | Solar Photovoltaics |  |  | 11.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at, Walpole and Puriton Landfill Sites off Puriton Road and, Batch Road, Puriton, Bridgwater | Somerset | South West | England | TA7 8BY | 331704 | 142629 | Sedgemoor District Council | 42/14/00012 | [5 empty] | 2014-06-25 | [6 empty] | 2014-09-23 |  |  |  |  | 2015-10-01 | 2015-12-01
C3178 | 2191 | 2015-05-07 | Gower Power Community Cooperative | Webbsfield | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Webbsfield, Near Brookvale, Ilston, Swansea, West Glamorgan | West Glamorgan | Wales | Wales | SA2 7LD | 255683 | 190908 | City and County Council of Swansea | 2014/0876 | APP/B6855/A/14/2226732 |  |  |  |  | 2014-06-18 |  | 2014-09-02 | 2014-11-19 |  | 2015-04-21
C3183 | 2192 | 2015-05-28 | Solar century / Magnetar Solar | Hunciecroft Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North West Of Hunciecroft Farm Holbeck Lane Holbeck Nottinghamshire | Nottinghamshire | East Midlands | England |  | 454277 | 373986 | Bassetlaw District Council | 14/01015/FUL | [5 empty] | 2014-08-15 | [6 empty] | 2014-11-20 |  |  |  | 2017-11-20 | 2015-01-01 | 2015-03-06
C3194 | 2193 | 2018-07-19 | Neo Environmental | East Culkae Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | East Culkae Farm, Sorbie | Dumfries and Galloway | Scotland | Scotland | DG8 8EP | 242998 | 546343 | Dumfries and Galloway Council | 14/P/1/0576 | [5 empty] | 2014-09-18 | [6 empty] | 2014-12-04 |  |  |  | 2017-12-04
C3202 | 2194 | 2014-09-23 | Caldecote Solar Park Ltd | Caldecote Manor Farm | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land South West Of Caldecote Manor Farm St Neots Road Abbotsley | Cambridgeshire | Eastern | England |  | 522603 | 258420 | Huntingdonshire District Council | 1400873FUL | [5 empty] | 2014-06-12 | 2014-08-21
C3211 | 2195 | 2014-09-19 | Archiception | Knapps Hook Farm | Solar Photovoltaics |  |  | 8.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Knapps Hook Farm, Doddershall, Quainton, Aylesbury, Buckinghamshire, HP18 0QL | Buckinghamshire | South East | England |  | 470762 | 220156 | Aylesbury Vale District Council | 14/01750/APP | [5 empty] | 2014-06-27 | 2014-08-08
C3219 | 2196 | 2015-10-05 | Push Energy | Rolleston Park Farm | Solar Photovoltaics |  |  | 18.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rolleston Park Farm, Lodge Hill, Tutbury | Staffordshire | West Midlands | England | DE13 9HQ | 421291 | 326955 | East Staffordshire Borough Council | P/2014/00830 | [5 empty] | 2014-07-09 | [6 empty] | 2014-09-10 |  |  |  |  | 2014-12-01 | 2015-03-31
C3220 | 2197 | 2015-10-06 | Lightsource Renewable Energy | Sheriffhales Solar Farm | Solar Photovoltaics |  |  | 30.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Sheriffhales, Shifnal, Shropshire | Shropshire | West Midlands | England | TF11 | 374778 | 312267 | Shropshire Council | 14/03444/FUL | APP/L3245/W/15/3005553 |  |  |  |  | 2014-08-01 |  | 2014-12-10 | 2015-05-12 | 2015-09-15
C3225 | 2198 | 2015-04-16 | Smiths Gore | Hawkers Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land at Hawkers Farm, Yeo Moor Drove, Theale, Wedmore | Somerset | South West | England | BS28 4SN | 346740 | 147660 | Sedgemoor District Council | 50/14/00069 | [5 empty] | 2014-06-26 | [6 empty] | 2014-10-01
C3242 | 2199 | 2020-04-27 | Hazel Capital LLP | Scopwick (Blankney Farm) | Solar Photovoltaics |  |  | 48 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land North East Of Scopwick And West Of Railway Line (Blankney Estate) Lincolnshire | Lincolnshire | East Midlands | England | LN4 3PQ | 509414 | 358487 | North Kesteven District Council | 14/0937/FUL | [5 empty] | 2014-07-11 | [6 empty] | 2014-09-25 |  |  |  | 2019-07-15
C3271 | 2200 | 2018-05-02 | Foresight | Prestop Park Farm | Solar Photovoltaics |  |  | 16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Prestop Park Farm, Burton Road, Ashby De La Zouch | Leicestershire | East Midlands | England | LE65 2TE | 433908 | 317806 | North West Leicestershire District Council | 14/00635/FULM | [5 empty] | 2014-07-11 | [6 empty] | 2014-09-30 |  |  |  |  | 2014-11-26 | 2015-03-21
C3280 | 2201 | 2018-05-02 | Foresight | Yardwall Manor | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Yardwall Manor Farm Mark Highbridge TA9 4QE | Somerset | South West | England | TA9 4LH | 336434 | 147337 | Sedgemoor District Council | 33/14/00024 | [5 empty] | 2014-07-09 | [6 empty] | 2014-09-29 |  |  |  |  | 2015-04-30 | 2015-06-08
C3288 | 2202 | 2015-03-04 | Canadian Solar | Royston Solar Farm (Phase 1) (a) | Solar Photovoltaics |  |  | 5 | n/a |  |  | 13.78 | n/a | n/a | n/a | Ground | Operational | Operational | Land between Railway and Sewage Disposal Works, Royston Road, Melbourn, Cambridgeshire | Cambridgeshire | Eastern | England |  | 535667 | 242584 | South Cambridgeshire District Council | S/1427/14/FL | [5 empty] | 2014-07-01 | [6 empty] | 2014-10-29 |  |  |  | 2017-10-29 | 2015-12-01 | 2016-01-29
C3296 | 2203 | 2018-02-02 | Defence Infrastructure Organisation | MOD Lyneham | Solar Photovoltaics |  |  | 69.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mod Lyneham, Lyneham, Chippenham, Wiltshire | Wiltshire | South West | England | SN15 4XX | 402315 | 178635 | Wiltshire Council | 14/06989/FUL | [5 empty] | 2014-07-23 | [6 empty] | 2014-11-13 |  |  |  | 2017-11-13 | 2015-01-01 | 2015-03-31
C3305 | 2204 | 2016-10-03 | Deepdale Farm Solar Ltd | Deepdale Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Deepdale Farm, Leasingham Moor, Sleaford, Lincolnshire, NG34 8SH | Lincolnshire | East Midlands | England |  | 507464 | 349010 | North Kesteven District Council | 14/0952/FUL | [5 empty] | 2014-07-16 | [6 empty] | 2014-11-10 |  |  |  | 2017-11-10 | 2016-03-30 | 2016-06-30
C3306 | 2205 | 2016-05-31 | Capital Stage | Manor Farm (Horton) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Manor Farm Ravenstone Lane Horton | Northamptonshire | East Midlands | England |  | 483499 | 253697 | South Northamptonshire Council | S/2014/1289/MAF | [5 empty] | 2014-07-25 | [6 empty] | 2014-11-21 |  |  |  | 2017-11-21 | 2016-02-03 | 2016-04-15
C3311 | 2206 | 2015-04-16 | MTS Hill Farm Solar Ltd | Penrhiwarwydd Farm | Solar Photovoltaics |  |  | 8.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Penrhiwarwydd Farm Mynyddislwyn Mountain Road Mynyddislwyn Newport NP11 7BB | Mid Glamorgan | Wales | Wales |  | 319934 | 193293 | Caerphilly County Borough Council | 14/0512/FULL | [5 empty] | 2014-07-29 | [6 empty] | 2014-11-07 |  |  |  | 2019-11-07 | 2015-01-01 | 2015-03-26
C3312 | 2207 | 2017-01-16 | Sovereign Energy Partners/Creswell Solar | Creswell | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Abandoned | Abandoned | The Ns/O Sewage Treatment Plant, Frithwood Lane, Elmton, Worksop, Nottinghamshire, S80 4LT | Derbyshire | East Midlands | England |  | 452973 | 373493 | Bolsover District Council | 14/00349/FUL | [5 empty] | 2014-08-07 | [6 empty] | 2014-11-12 |  |  |  | 2017-11-12
C3313 | 2208 | 2015-04-14 | Estover Energy | Nowhere Farm | Solar Photovoltaics |  |  | 8.121 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nowhere Farm, Fishmere End Road, Sutterton, Boston, Lincolnshire, PE20 2HX | Lincolnshire | East Midlands | England | PE20 2HX | 527442 | 338175 | Boston Borough Council | B/14/0267 | [5 empty] | 2014-07-02 | [6 empty] | 2014-09-17 |  |  |  |  | 2015-01-07 | 2015-03-20
C3314 | 2209 | 2017-10-25 | Estover Energy | Ewerby Thorpe Farm | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Ewerby Thorpe Farm, Ewerby Thorpe, Sleaford, Lincolnshire, NG34 9PR | Lincolnshire | East Midlands | England |  | 513170 | 347680 | North Kesteven District Council | 14/1003/FUL | [5 empty] | 2014-08-07 | [6 empty] | 2014-10-03 |  |  |  | 2017-10-03
C3315 | 2210 | 2017-12-15 | Kappa Solar/ OPDE | Langar Lane | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | OS Fields 6230 And 7657 Langar Lane, Colston, Bassett | Nottinghamshire | East Midlands | England |  | 470671 | 334431 | Rushcliffe Borough Council | 14/01594/FUL | [5 empty] | 2014-08-06 | [6 empty] | 2014-12-05 |  |  |  | 2017-12-05 | 2015-10-05 | 2016-06-15
C3316 | 2211 | 2015-08-27 | Lightsource Renewable Energy | Pitchford | Solar Photovoltaics |  |  | 10.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stockbatch, Pitchford, Shrewsbury, Shropshire | Shropshire | West Midlands | England | SY5 | 351826 | 302964 | Shropshire Council | 14/03464/FUL | [5 empty] | 2014-08-01 | [6 empty] | 2014-11-21 |  |  |  | 2017-11-21 | 2014-12-19 | 2015-03-29
C3317 | 2212 | 2015-05-14 | Lightsource Renewable Energy | Condover Airfield | Solar Photovoltaics |  |  | 12.28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Disused Airfield Condover Shrewsbury Shropshire | Shropshire | West Midlands | England |  | 350687 | 304131 | Shropshire Council | 14/03446/FUL | [5 empty] | 2014-08-01 | [6 empty] | 2014-11-21 |  |  |  | 2017-11-21 | 2014-11-15 | 2015-03-31
C3318 | 2213 | 2015-11-03 | Anesco | Askern Colliery solar farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Former Colliery, Campsall Road, Askern, Doncaster | South Yorkshire | Yorkshire and Humber | England | DN6 0BT | 455645 | 414136 | Doncaster Metropolitan Borough Council | 14/01829/FULM | [5 empty] | 2014-08-01 | [6 empty] | 2014-12-08 |  |  |  | 2017-12-08 | 2015-03-12 | 2015-08-14
C3319 | 2214 | 2014-09-19 | Green Energy UK Direct | Stones Hill | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land at NGR 302663 109953 (Stoneshill Farm) Willand Road Cullompton Devon | Devon | South West | England |  | 302683 | 109929 | Mid Devon District Council | 14/01248/MFUL | [5 empty] | 2014-08-08 | 2014-10-20
C3320 | 2215 | 2017-05-22 | Walters Group | Maesgwyn solar farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of Maesgwyn Wind Farm Glynneath Neath | West Glamorgan | Wales | Wales |  | 288221 | 208706 | Neath Port Talbot County Borough Council | P2014/0762 | [5 empty] | 2014-08-05 | [6 empty] | 2015-05-28 |  |  |  | 2020-05-28 | 2016-12-01 | 2017-02-15
C3321 | 2216 | 2015-12-22 | Lightsource Renewable Energy | Church Farm | Solar Photovoltaics |  |  | 6.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To South Of Church Farm Church Road Slapton Buckinghamshire LU7 9BX | Buckinghamshire | South East | England |  | 494241 | 220134 | Aylesbury Vale District Council | 14/02302/APP | [5 empty] | 2014-08-01 | [6 empty] | 2014-10-31 |  |  |  |  | 2015-09-23 | 2015-12-16
C3322 | 2217 | 2015-04-15 | Hive Energy | Folly Farm | Solar Photovoltaics |  |  | 13.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Folly Farm, Potash Lane, Long Marston, Tring, Hertfordshire | Hertfordshire | Eastern | England | HP23 4QY | 486942 | 216405 | Dacorum Borough Council | 4/02099/14/MFA | [5 empty] | 2014-08-13 | [6 empty] | 2014-11-11 |  |  |  | 2017-11-11 | 2014-12-15 | 2015-03-31
C3323 | 2218 | 2015-05-28 | FC Palmer and Sons | Stowbridge Farm - Extension (Phase 2) | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stowbridge Farm, Green End, Stretham, Cambridgeshire | Cambridgeshire | Eastern | England | CB6 3LF | 551742 | 272943 | East Cambridgeshire District Council | 14/00839/ESF | [5 empty] | 2014-07-30 | [6 empty] | 2014-11-11 |  |  |  | 2019-11-11 | 2014-12-01 | 2015-03-20
C3324 | 2219 | 2015-05-14 | Lightsource Renewable Energy | Black Peak Farm | Solar Photovoltaics |  |  | 31.79 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Black Peak Farm, Fowlmere Road, Melbourn, Royston, Hertfordshire | Cambridgeshire | Eastern | England | SG8 7PJ | 540507 | 244190 | South Cambridgeshire District Council | S/1902/14/FL | [5 empty] | 2014-08-07 | [6 empty] | 2014-12-15 |  |  |  | 2017-12-15 | 2014-12-30 | 2015-03-25
C3325 | 2220 | 2018-09-26 | Green Switch Solutions - Liquidated | White Gorse Farm | Solar Photovoltaics |  |  | 11.61 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | White Gorse Farm, Gorse Drove, Scredington, Sleaford, Lincolnshire, NG34 0AJ | Lincolnshire | East Midlands | England |  | 509987 | 339519 | North Kesteven District Council | 14/0954/FUL | [5 empty] | 2014-08-01 | [6 empty] | 2014-11-25 |  |  |  | 2017-11-25
C3326 | 2221 | 2017-07-05 | NESF (formerly Lark Energy) | Jubilee Farm, Barnby Moor | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Jubilee Farm, Retford Road, Barnby Moor, Nottinghamshire | Nottinghamshire | East Midlands | England | S81 8EU | 464444 | 385885 | Bassetlaw District Council | 14/01036/FUL | [5 empty] | 2014-07-31 | [6 empty] | 2015-01-13 |  |  |  | 2018-01-13 | 2017-01-15 | 2017-03-15
C3327 | 2222 | 2019-11-19 | Archiception | Hall Farm (Hannington) | Solar Photovoltaics |  |  | 10.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Walgrave Road, Hannington, Northampton | Northamptonshire | East Midlands | England | NN6 9SX | 480650 | 271848 | Daventry District Council | DA/2014/0694 | [5 empty] | 2014-08-07 | [6 empty] | 2015-07-09 |  |  |  | 2018-07-09
C3328 | 2223 | 2015-02-17 | Cookley Solar Park Ltd | Hill Farm | Solar Photovoltaics |  |  | 15.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Hill Farm Cookley Halesworth | Suffolk | Eastern | England | IP19 0LU | 635826 | 275350 | Waveney District Council | DC/14/2150/FUL | [5 empty] | 2014-08-11 | [6 empty] | 2014-11-11 |  |  |  | 2017-11-11
C3329 | 2224 | 2015-07-01 | Hive Energy | Orrell Hill | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Bounded By Moss Lane And North End Lane Hightown | Merseyside | North West | England |  | 331018 | 403806 | Sefton Council | DC/2014/01439 | [5 empty] | 2014-08-12 |  | 2015-06-11
C3330 | 2225 | 2015-04-02 | Solstice Renewables | Newnham Estate | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | SX559 587, Hemerdon, Plympton | Devon | South West | England |  | 255883 | 58478 | South Hams District Council | 49/2133/14/F | [5 empty] | 2014-08-15 | [5 empty] | 2014-11-27 | 2014-11-27 |  |  |  | 2017-11-27 | 2014-12-01 | 2015-03-31
C3331 | 2226 | 2016-03-14 | Sunsave 19 (Wambrook)/ Vogt Solar | Wambrook Farm | Solar Photovoltaics |  |  | 4.08 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Part Of Wambrook Farm, Weston Road, Wambrook, Chard, Somerset | Somerset | South West | England | TA20 3DF | 330614 | 108791 | South Somerset District Council | 14/03678/FUL | [5 empty] | 2014-08-13 | [6 empty] | 2014-11-28 |  |  |  | 2017-11-28 | 2015-07-15 | 2015-08-15
C3332 | 2227 | 2016-04-25 | Harper Solar Ltd | Gawcott Fields Farm | Solar Photovoltaics |  |  | 9.18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Gawcott Fields Farm Gawcott Road Buckingham Buckinghamshire MK18 1TN | Buckinghamshire | South East | England |  | 468420 | 232700 | Aylesbury Vale District Council | 14/02293/APP | [5 empty] | 2014-07-29 | [6 empty] | 2014-10-28 |  |  |  |  | 2015-11-02 | 2015-12-15
C3333 | 2228 | 2015-05-19 | OPDE | Mount Mill Farm - resubmission | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mount Mill Farm, Stratford Road, Wicken | Northamptonshire | East Midlands | England |  | 475935 | 238464 | South Northamptonshire Council | S/2014/1374/MAF | [5 empty] | 2014-08-08 | [6 empty] | 2014-09-25 |  |  |  | 2017-09-25 | 2015-01-01 | 2015-03-30
C3335 | 2229 | 2015-10-29 | Northfield UK Solar | Barn Farm (Stanford On Soar) | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land North And West Of Barn Farm, Leake Lane, Stanford On Soar | Nottinghamshire | East Midlands | England | LE12 5QL | 453955 | 322996 | Rushcliffe Borough Council | 14/01589/FUL | APP/P3040/W/15/3005788 |  |  |  |  | 2014-07-16 |  | 2014-10-10 | 2015-05-07 |  | 2015-10-26
C3336 | 2230 | 2014-11-23 | Green Energy UK Direct | Farthinghoe Solar Farm - resubmission | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land to the east of Cockley Road Farthinghoe | Northamptonshire | East Midlands | England |  | 454219 | 240400 | South Northamptonshire Council | S/2014/1495/MAF | [5 empty] | 2014-08-14 |  | 2014-11-12
C3337 | 2231 | 2016-06-30 | Haymaker Energy | Handley Park - resubmission | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Handley Park Farm, Handley Park, Towcester | Northamptonshire | East Midlands | England |  | 467163 | 245965 | South Northamptonshire Council | S/2014/1522/MAF | APP/Z2830/W/14/3001220 |  |  |  |  | 2014-08-21 |  | 2014-10-23 | 2015-01-08 |  |  | 2015-09-09 | 2015-09-09 |  |  |  | 2018-09-09 | 2016-05-01 | 2016-03-24
C3338 | 2232 | 2016-08-31 | CRE8 Energy (UK) | Tollgate Farm | Solar Photovoltaics |  |  | 4.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tollgate Farm, Banbury Road, Bishops Tachbrook, Leamington Spa | Warwickshire | West Midlands | England | CV33 9QJ | 431223 | 259709 | Warwick District Council | W/14/1266 | [5 empty] | 2014-08-20 | [6 empty] | 2015-01-12 |  |  |  |  | 2016-01-16 | 2016-03-16
C3339 | 2233 | 2015-05-28 | British Solar Renewables | North Farm (Spetisbury) | Solar Photovoltaics |  |  | 11.63 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At E388136 N102088, West Of North Farm, West End, Spetisbury, Dorset | Dorset | South West | England |  | 388136 | 102088 | North Dorset District Council | 2/2014/0825/FUL | [5 empty] | 2014-08-13 | [6 empty] | 2014-11-12 |  |  |  | 2017-11-12 | 2014-12-01 | 2015-03-30
C3340 | 2234 | 2015-11-30 | Eco Sustainable Solutions | Chapel Lane Parley Solar Farm Phase 3 | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chapel Lane, Parley, Christchurch, Dorset | Dorset | South West | England | BH23 6BG | 409653 | 100413 | Christchurch Borough Council | 8/14/0412 | [5 empty] | 2014-08-28 | [6 empty] | 2015-01-30 |  |  |  | 2018-01-30 |  | 2015-09-01
C3341 | 2235 | 2020-06-09 | Marcol Afan Energy | Foel Fawr | Solar Photovoltaics |  |  | 5.1 | n/a |  |  |  | n/a | n/a | n/a |  | Appeal Granted | Awaiting Construction | LAND NORTH BRYNHEULOG CAERAU PARK MAESTEG BRIDGEND | Mid Glamorgan | Wales | Wales | CF34 0YH | 285648 | 195107 | Bridgend County Borough Council | P/14/543/FUL | APP/F6915/A/15/3133430 |  |  |  |  | 2014-08-15 |  | 2015-06-12 | 2015-11-24 |  |  | 2016-04-22 | 2016-04-22 |  |  |  | 2021-04-22
C3342 | 2236 | 2017-03-23 | Hadstone Energy/Island Green Power | Ballinderry Road Solar Phase 1 (Lisburn) | Solar Photovoltaics |  |  | 13.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands located 110m WNW of 29 Ballinderry Road, Lisburn | Co. Antrim | Northern Ireland | Northern Ireland | BT28 2SL | 134798 | 521384 | Northern Ireland Planning Service | S/2014/0492/F | [5 empty] | 2014-07-22 | [6 empty] | 2014-11-11 |  |  |  | 2019-11-11 | 2016-06-01 | 2017-02-20
C3343 | 2237 | 2016-10-31 | Green Switch Solutions | GDL Wymeswold Solar Farm/land off the A6006 | Solar Photovoltaics |  |  | 6.09 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land south of Wide Lane Wymeswold Leicestershire | Leicestershire | East Midlands | England |  | 461609 | 323941 | Charnwood Borough Council | P/14/1484/2 | [5 empty] | 2014-08-07 | [6 empty] | 2015-02-11 |  |  |  | 2018-02-11 | 2015-12-16 | 2016-02-16
C3344 | 2238 | 2015-04-20 | Cambridge Solar Power/ Vogt Solar | Hillhouse Farm | Solar Photovoltaics |  |  | 28.5 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hillhouse Farm Bristol Road, Cambridge, Gloucester, Gloucestershire | Gloucestershire | South West | England | GL2 7AN | 375073 | 204169 | Stroud District Council | S.14/1800/FUL | [5 empty] | 2014-08-05 | [6 empty] | 2014-12-08 |  |  |  | 2017-12-08 | 2015-01-01 | 2015-03-31
C3346 | 2239 | 2015-12-21 | CEE | Gib Lane (Aston Clinton solar park) | Solar Photovoltaics |  |  | 24.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To East Of Gib Lane, Bierton, Buckinghamshire | Buckinghamshire | South East | England |  | 487386 | 213197 | Aylesbury Vale District Council | 14/02315/APP | [5 empty] | 2014-08-11 | [6 empty] | 2014-11-12 |  |  |  | 2017-11-12 | 2014-12-01 | 2015-03-30
C3347 | 2240 | 2016-07-01 | MS Power Projects | Outwood Farm (Phase 1) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Outwood Farm Road Billericay, Essex | Essex | Eastern | England |  | 569468 | 194288 | Basildon Borough Council | 14/00948/FULL | [5 empty] | 2014-08-07 | [6 empty] | 2014-12-11 |  |  |  | 2017-12-11 | 2015-11-01 | 2016-03-30
C3348 | 2241 | 2015-12-17 | Fengate Capital | Raventhorpe Farm | Solar Photovoltaics |  |  | 38 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Raventhorpe Farm, Raventhorpe Farm Road, Broughton and Holme, DN16 3RH | Humberside | Yorkshire and Humber | England |  | 494072 | 408026 | North Lincolnshire Council | PA/2014/0892 | [5 empty] | 2014-08-14 | [6 empty] | 2014-11-05 |  |  |  | 2017-11-05 | 2015-01-01 | 2015-03-21
C3349 | 2242 | 2017-07-28 | Brilliant Harvest Installations | Manor Farm (Castle Cary) | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjoining Manor Farm The ark Castl Cary Somerset | Somerset | South West | England |  | 364360 | 131378 | South Somerset District Council | 14/03587/FUL | [5 empty] | 2014-08-11 | [6 empty] | 2015-01-07 |  |  |  | 2018-01-07 | 2017-01-06 | 2017-03-06
C3351 | 2243 | 2015-12-22 | Lightsource Renewable Energy | Maes Bach Farm | Solar Photovoltaics |  |  | 4.86 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Maes Bach, Willowford Road, Tonte, Pontypridd, Mid Glamorgan | Mid Glamorgan | Wales | Wales | CF38 1SL | 310571 | 185789 | Rhondda Cynon Taff County Borough Council | 14/1014/10 | [5 empty] | 2014-07-31 | [6 empty] | 2014-12-30 |  |  |  | 2019-12-30 | 2015-09-16 | 2015-11-19
C3352 | 2244 | 2018-09-04 | Foresight | Sheepbridge Court Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Sheepbridge Court Farm Basingstoke Road Swallowfield Reading | Berkshire | South East | England |  | 472389 | 166123 | Wokingham Borough Council | F/2014/1495 | [5 empty] | 2014-08-05 | [6 empty] | 2014-12-12 |  |  |  | 2017-12-12 | 2015-10-20 | 2015-12-20
C3353 | 2245 | 2018-08-30 | Solstice Renewables | Swangleys Farm | Solar Photovoltaics |  |  | 8.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land At Swangleys Farm, Swangleys Lane, Knebworth | Hertfordshire | Eastern | England |  | 525597 | 219859 | North Hertfordshire District Council | 14/02153/1 |  | APP/X1925/V/15/3005096 | Call-In Application |  |  | 2014-08-19 | 2015-09-16
C3355 | 2246 | 2016-01-26 | TGC Renewables | Copley Farm - resubmission | Solar Photovoltaics |  |  | 10.08 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Doddington Lane, Claypole, Newark | Lincolnshire | East Midlands | England | NG23 5AT | 484930 | 347958 | South Kesteven District Council | S14/2290 | [5 empty] | 2014-08-08 | [6 empty] | 2014-12-03 |  |  |  | 2017-12-03
C3356 | 2247 | 2016-03-18 | Valfortec | Elton solar farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of The Railway Line & East Of Station Road Elton Nottinghamshire | Nottinghamshire | East Midlands | England |  | 477523 | 339594 | Rushcliffe Borough Council | 14/01739/FUL | [5 empty] | 2014-08-14 | [6 empty] | 2015-02-13 |  |  |  | 2018-02-13 | 2015-06-01 | 2015-08-01
C3357 | 2248 | 2017-08-23 | Good Energy Generation | Cross Roads Plantation | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cross Roads Plantation Ringwood Road Alderholt Fordingbridge Hants | Dorset | South West | England | SP6 3DF | 411316 | 111949 | East Dorset District Council | 3/14/0774/FUL | [5 empty] | 2014-08-19 | [6 empty] | 2014-11-04 |  |  |  | 2017-11-04 | 2015-05-30 | 2015-06-30
C3359 | 2249 | 2015-05-14 | Lightsource Renewable Energy | Munceys Farm | Solar Photovoltaics |  |  | 31.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Munceys Farm, London Way, Melbourn, Royston, Cambridgeshire | Cambridgeshire | Eastern | England | SG8 6DJ | 537951 | 242629 | South Cambridgeshire District Council | S/1898/14/FL | [5 empty] | 2014-08-07 | [6 empty] | 2014-11-24 |  |  |  | 2017-11-24 | 2014-12-30 | 2015-03-25
C3360 | 2250 | 2015-02-09 | Green Energy UK Direct | Nailcote Farm | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Nailcote Farm, Nailcote Lane, Berkswell, Coventry | West Midlands | West Midlands | England | CV7 7DE | 426442 | 277257 | Solihull Metropolitan Borough Council | 2014/1212 | [5 empty] | 2014-07-09 |  | 2014-11-03
C3361 | 2251 | 2018-08-30 | Green Switch Solutions | Wharrels Hill | Solar Photovoltaics |  |  | 14.63 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | E/O Wharrels Hill Wind Farm, Adjacent A591, Bothel, Cockermouth, Cumbria | Cumbria | North West | England |  | 318022 | 538154 | Allerdale Borough Council | 2/2014/0636 | APP/G0908/W/15/3132595 |  |  |  |  | 2014-08-22 |  | 2015-07-09 | 2015-11-17 | 2016-03-01
C3362 | 2252 | 2016-02-01 | Sunsave 7 Luscott Barton Ltd/ vogt Solar | Luscott Barton | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Luscott Barton, Ashford, Barnstaple, Devon | Devon | South West | England | EX31 4DE | 251657 | 136715 | North Devon District Council | 58007 | [5 empty] | 2014-08-20 | [6 empty] | 2015-09-03 |  |  |  | 2018-09-03 | 2015-10-15 | 2015-11-15
C3363 | 2253 | 2016-07-25 | Haymaker Energy | Kinmel 1 CIC | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land immediately north of A547, Rhuddlan Road, Towyn, Conwy | Gwynedd | Wales | Wales |  | 298420 | 377733 | Conwy County Borough Council | 0/40999 | [5 empty] | 2014-08-27 | [6 empty] | 2015-03-11 |  |  |  | 2020-03-11 | 2016-03-21 | 2016-06-27
C3364 | 2254 | 2018-06-21 | R C Upchurch & Partners | Chalgrave Manor | Solar Photovoltaics |  |  | 24.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land adjacent Chalgrave Manor, Luton Road, Toddington | Bedfordshire | Eastern | England |  | 501637 | 227287 | Central Bedfordshire Council | CB/14/01480/FULL | [5 empty] | 2014-08-27 | [6 empty] | 2015-01-27 |  |  |  | 2018-01-27
C3365 | 2255 | 2016-10-03 | Cubico Sustainable Investments | Owls Hatch Road | Solar Photovoltaics |  |  | 48 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land south of Owl's Hatch Road, Herne | Kent | South East | England |  | 615860 | 165945 | Canterbury City Council | CA//14/01792 | [5 empty] | 2014-08-22 | [6 empty] | 2015-01-30 |  |  |  | 2018-01-30 | 2015-02-01 | 2015-03-29
C3367 | 2256 | 2014-11-23 | Private Developer | Stokeford Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Stokeford Farm, East Stoke, Wareham, Dorset, BH20 6AN | Dorset | South West | England |  | 387124 | 87619 | Purbeck District Council | 6/2014/0446 | [5 empty] | 2014-08-27 | 2014-11-17
C3370 | 2257 | 2014-12-05 | A Rosen Invest APS | Tilsworth | Solar Photovoltaics |  |  | 20.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land North of Stanbridge Road Tilsworth, Leighton Buzzard | Bedfordshire | Eastern | England | LU7 9PU | 497332 | 224831 | Central Bedfordshire Council | CB/14/03129/FULL | [5 empty] | 2014-09-01 | 2014-12-02
C3371 | 2258 | 2016-11-17 | Hive Energy | Wilbees Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Wilbees Farm, The Street, Polegate, East Sussex, BN26 | East Sussex | South East | England |  | 554339 | 106829 | Wealden District Council | WD/2014/1838/MEA | [5 empty] | 2014-09-05 | [6 empty] | 2014-11-14 |  |  |  | 2017-11-14 | 2016-07-01 | 2016-10-21
C3372 | 2259 | 2017-12-15 | S.A.T. Sun & Alternative Technology | Winterbrook | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Land West of Reading Road Cholsey | Oxfordshire | South East | England | OX10 9HA | 460277 | 187911 | South Oxfordshire District Council | P14/S2846/FUL | [5 empty] | 2014-09-03 | [6 empty] | 2015-01-13 |  |  |  | 2018-01-13 | 2015-08-01 | 2015-10-15
C3373 | 2260 | 2015-08-03 | Solar century / Magnetar Solar | Welbeck Solar / Hazel Gap | Solar Photovoltaics |  |  | 16 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The South Of Forge Lodge, Carburton Road, Norton | Nottinghamshire | East Midlands | England | S80 3BP | 459630 | 371882 | Bassetlaw District Council | 14/01030/FUL | [5 empty] | 2014-08-14 | [6 empty] | 2015-01-09 |  |  |  | 2018-01-09 | 2015-01-10 | 2015-03-19
C3374 | 2261 | 2016-03-23 | CEE | Homestead Farm (Alderton) | Solar Photovoltaics |  |  | 17.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Homestead Farm located east of the A5 and south of Alderton, (Paulerspury & Grafton Regis & Alderton Parish) | Northamptonshire | East Midlands | England |  | 473852 | 245470 | South Northamptonshire Council | S/2014/1680/MAF | [5 empty] | 2014-09-11 | [6 empty] | 2014-12-11 |  |  |  | 2017-12-11 | 2015-01-01 | 2015-03-30
C3375 | 2262 | 2016-05-04 | BERTY 003 | Park Farm (Claverdon) | Solar Photovoltaics |  |  | 7.52 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Park Farm, Church Road, Claverdon, Warwick | Warwickshire | West Midlands | England | CV35 8PB | 420921 | 264349 | Stratford on Avon District Council | 14/02034/FUL | APP/J3720/W/15/3029788 |  |  |  |  | 2014-09-15 |  | 2015-03-12 | 2015-08-21 |  | 2016-04-20
C3376 | 2263 | 2017-07-28 | BE Renewables (on behalf of Arna Wood) | Arna Wood Solar | Solar Photovoltaics |  |  | 6.17 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Arna Wood Farm, East Arna Wood Lane, Lancaster, Lancashire | Lancashire | North West | England | LA2 0AE | 346189 | 458787 | Lancaster City Council | 14/00907/FUL | [5 empty] | 2014-08-18 | [6 empty] | 2015-07-01 |  |  |  | 2018-07-01 | 2017-01-31 | 2017-03-31
C3377 | 2264 | 2016-05-23 | Envantage Renewables | Knottingley A | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Middle Lane, England Lane, Knottingley, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF11 0BZ | 450120 | 423193 | Wakefield Council | 14/01734/FUL | [5 empty] | 2014-08-26 | [6 empty] | 2015-01-23 |  |  |  | 2018-01-23 | 2015-08-31 | 2016-03-29
C3378 | 2265 | 2017-10-04 | Anesco | Clayhill Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | North Clayhill Farm, Greenfield Road, Westoning, Bedford, Bedfordshire | Bedfordshire | Eastern | England | MK45 5JD | 504351 | 233195 | Central Bedfordshire Council | CB/14/03419/FULL | [5 empty] | 2014-09-01 | [6 empty] | 2015-01-29 |  |  |  | 2018-01-29 | 2016-04-24 | 2016-06-24
C3379 | 2266 | 2015-07-31 | Foresight Solar Fund | Paddock Wood | Solar Photovoltaics |  |  | 9.2 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Knells Farm, Pearson's Green Road, Paddock Wood, Tonbridge, Kent | Kent | South East | England | TN12 6NP | 568713 | 144255 | Tunbridge Wells Borough Council | 14/502851/FULL | [5 empty] | 2014-09-05 | [6 empty] | 2014-12-19 |  |  |  | 2017-12-19 | 2015-02-01 | 2015-03-31
C3380 | 2267 | 2017-11-24 | Friths Solar Limited | Friths Farm | Solar Photovoltaics |  |  | 28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land at Friths Farm, Fen Road, Frampton West, Boston, Lincolnshire, PE201SA | Lincolnshire | East Midlands | England |  | 529836 | 342114 | Boston Borough Council | B/14/0287 | [5 empty] | 2014-08-04 | [6 empty] | 2014-10-09 |  |  |  | 2017-10-09
C3382 | 2268 | 2017-08-14 | Countryside Renewables | Wick Farm (Burnham on Crouch) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | E/O Burnham Wick Farm, Wick Road, Burnham on Crouch, Essex, CM0 8FA | Essex | Eastern | England |  | 596876 | 195875 | Maldon District Council | 14/00775/FUL | [5 empty] | 2014-09-09 | [6 empty] | 2015-01-26 |  |  |  | 2018-01-26 | 2015-09-11 | 2015-12-17
C3383 | 2269 | 2014-10-02 | Thriplow Farms | Manor Farm - resubmission | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land to the East of Church Street, Thriplow | Cambridgeshire | Eastern | England |  | 544282 | 246623 | South Cambridgeshire District Council | S/1687/14/FL | [5 empty] | 2014-08-13 |  | 2015-01-14
C3384 | 2270 | 2017-09-28 | Big 60 Million | Coalville solar farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land Between School Lane Normanton Le Heath And Ashby Road Ravenstone Leicestershire | Leicestershire | East Midlands | England |  | 438841 | 313519 | North West Leicestershire District Council | 14/00786/FULM | [5 empty] | 2014-09-02 | [6 empty] | 2014-11-19 |  |  |  | 2017-11-19
C3385 | 2271 | 2015-05-29 | Lightsource Renewable Energy | Netherfield Lane | Solar Photovoltaics |  |  | 19.67 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field Reference Number 7390 Netherfield Lane Perlethorpe Cum Budby Nottinghamshire | Nottinghamshire | East Midlands | England |  | 460746 | 370838 | Newark and Sherwood District Council | 14/01546/FULM | [5 empty] | 2014-09-12 | [6 empty] | 2014-12-10 |  |  |  | 2017-12-10 | 2015-01-01 | 2015-03-23
C3386 | 2272 | 2017-10-04 | GDL Upper Meadowley | Upper Meadowley Farm | Solar Photovoltaics |  |  | 10.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Upper Meadowley Farm, Upton Cresset, Bridgnorth, Shropshire | Shropshire | West Midlands | England | WV16 6UQ | 366792 | 292516 | Shropshire Council | 14/03933/FUL | [5 empty] | 2014-08-28 | [6 empty] | 2015-11-12 |  |  |  | 2018-11-12 | 2017-01-31 | 2017-03-31
C3387 | 2273 | 2015-10-05 | juwi Renewable Energies | Stumpy Cross | Solar Photovoltaics |  |  | 4.45 | n/a |  |  |  | n/a | n/a | n/a |  | Appeal Refused | Application Refused | Dunsmore Farm, Babylon Lane, Exeter, Devon | Devon | South West | England | EX5 | 295073 | 101829 | Mid Devon District Council | 14/01501/MFUL | APP/Y1138/W/15/3004976 |  |  |  |  | 2014-09-05 |  | 2014-12-05 | 2015-03-16 |  | 2015-08-28
C3388 | 2274 | 2016-01-04 | Hadstone Energy/ Communities for Renewables | Wick Farm Solar Park | Solar Photovoltaics |  |  | 14.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | S/O Wick Farm, Brean Road, Lympsham, Weston Super Mare, North Somerset | Somerset | South West | England | BS24 0HD | 331664 | 154677 | Sedgemoor District Council | 05/14/00019 | [5 empty] | 2014-08-20 | [6 empty] | 2014-10-28 |  |  |  | 2017-10-28 | 2016-04-01 | 2016-07-01
C3389 | 2275 | 2017-02-28 | Lightsource Renewable Energy | Three Houses Lane | Solar Photovoltaics |  |  | 11.28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Secretary of State - Refusal | Application Refused | Land adjacent to, Three Houses Lane, Codicote | Hertfordshire | Eastern | England |  | 520911 | 220037 | North Hertfordshire District Council | 14/02360/1 |  | APP/X1925/V/15/3131943 | Call-In |  |  | 2014-09-10 | [7 empty] | 2015-07-27 | 2016-10-31
C3390 | 2276 | 2018-05-21 | BE Renewables/Little Eau Solar | Fendyke Solar Farm (resubmission) | Solar Photovoltaics |  |  | 17.55 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Fendyke Farm, Fen Dyke, Sutton St James, Spalding, Lincs | Lincolnshire | East Midlands | England | PE12 0LQ | 536677 | 316760 | South Holland District Council | H20-0764-14 | [5 empty] | 2014-09-15 | [6 empty] | 2014-12-08 |  |  |  | 2017-12-08
C3391 | 2277 | 2016-02-17 | European Energy Photovoltaics | High Leas | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north of High Leas Farm, Willoughby Lane, South Reston, Louth, Lincolnshire | Lincolnshire | East Midlands | England | LN11 8PJ | 539629 | 382380 | East Lindsey District Council | N/161/01563/14 | [5 empty] | 2014-09-10 | [6 empty] | 2014-12-10 |  |  |  | 2017-12-10 | 2015-10-15 | 2015-12-18
C3393 | 2278 | 2015-07-31 | Foresight Solar Fund | Atherstone | Solar Photovoltaics |  |  | 14.65 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of Grendon House Farm Warton Lane Grendon | Warwickshire | West Midlands | England |  | 429958 | 301789 | North Warwickshire Borough Council | PAP/2014/0483 | [5 empty] | 2014-09-12 | [6 empty] | 2014-11-14 |  |  |  | 2017-11-14 | 2015-01-01 | 2015-03-31
C3394 | 2279 | 2015-07-31 | Foresight Solar Fund | The Elms | Solar Photovoltaics |  |  | 10.388 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The Elms Plough Lane Bishops Itchington Southam | Warwickshire | West Midlands | England | CV47 2QG | 437983 | 257474 | Stratford on Avon District Council | 14/02341/FUL | [5 empty] | 2014-09-03 | [6 empty] | 2014-11-27 |  |  |  | 2017-11-27 | 2015-02-01 | 2015-03-31
IF1071 | 2280 | 2014-10-02 | Aardvark Environment Matters | Hunters Race Solar Park | Solar Photovoltaics |  |  | 9.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lavant Quarry, Hunters Race, Lavant, Chichester, West Sussex | West Sussex | South East | England | PO19 5UD | 485062 | 107653 | Chichester District Council | 13/00382/FUL | [5 empty] | 2013-02-12 | [6 empty] | 2013-05-13 |  |  |  |  | 2014-03-12 | 2014-07-23
IF1093 | 2281 | 2014-10-01 | AG Renewables Ltd | Parham Airfield (Great Glenham) | Solar Photovoltaics |  |  | 17.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | North of Runway Farm, Great Glemham, Suffolk | Suffolk | Eastern | England |  | 633149 | 260842 | Suffolk Coastal District Council | C/12/2067 | [5 empty] | 2012-09-27 | [6 empty] | 2013-04-05 |  |  |  |  | 2013-05-01 | 2013-12-04
IF1114 | 2282 | 2014-09-22 | Solar Power Generation Limited | Chapel Lane Parley Solar Farm Phase 1 | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Parley (Adjacent to Ecos Sustainable Solutions Waste & Recycling Facility) | Dorset | South West | England |  | 409877 | 99146 | Christchurch Borough Council | 8/12/0512 | [5 empty] | 2012-11-28 | [6 empty] | 2013-03-28 |  |  |  |  | 2014-01-10 | 2014-03-31
IF1147 | 2283 | 2018-09-04 | Foresight | Welbeck Colliery | Solar Photovoltaics |  |  | 11.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Elkesley Road, Meden Vale, Mansfield, Nottinghamshire | Nottinghamshire | East Midlands | England | NG20 9PS | 457669 | 369999 | Mansfield District Council | 2012/0557/NT | [5 empty] | 2012-11-21 | [6 empty] | 2013-02-11 |  |  |  |  | 2014-03-15 | 2014-07-25
IF1148 | 2284 | 2014-10-01 | Private Developer | Priory Farm | Solar Photovoltaics |  |  | 3.12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mutfordwood Lane, Carlton Colville, Lowestoft, Suffolk, NR33 8HD | Suffolk | Eastern | England |  | 649805 | 289745 | Waveney District Council | DC/12/1362/FUL | [5 empty] | 2012-11-27 | [6 empty] | 2013-02-25 | [5 empty] | 2014-03-29
IF1259 | 2285 | 2017-02-02 | Terraform Power (SunEdison) | Norrington Common Solar Farm | Solar Photovoltaics |  |  | 9.997 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Broughton Gifford, Wiltshire | Wiltshire | South West | England |  | 388259 | 164933 | Wiltshire Council | W/12/02072/FUL | [5 empty] | 2012-11-22 | [6 empty] | 2013-04-25 |  |  |  |  | 2014-03-01 | 2014-07-04
IF1343 | 2286 | 2015-08-19 | INRG Solar | Hendre Fawr Farm | Solar Photovoltaics |  |  | 11.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Hendrefawr Farm, Mount Road, Rhigos, Neath, West Glamorgan | West Glamorgan | Wales | Wales | CF44 9RJ | 290227 | 205890 | Neath Port Talbot County Borough Council | P2013/0635 | [5 empty] | 2013-09-18 | [6 empty] | 2014-07-06 |  |  |  |  | 2014-11-15 | 2015-03-06
IF1417 | 2287 | 2014-10-03 | Oakapple Renewable Energy Ltd | Haigh Hall Solar Farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Batley Road, Tingley, Wakefield | West Yorkshire | Yorkshire and Humber | England |  | 428383 | 424026 | Leeds City Council | 13/00874/FU | [5 empty] | 2013-03-15 | [6 empty] | 2013-08-02
IF1428 | 2288 | 2016-05-10 | Lightsource Renewable Energy | Northmoor | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Whitstone Holsworthy Cornwall | Cornwall | South West | England | EX22 6TD | 227223 | 97462 | Cornwall Council | PA14/08271 | [5 empty] | 2014-09-11 | [6 empty] | 2014-11-21 |  |  |  | 2017-11-21 | 2014-11-22 | 2015-03-31
C1136 | 2289 | 2014-09-16 | Lightsource Renewable Energy | Chalhanger Farm Solar Park | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Chalhanger Farm Buckland Filleigh Beaworthy Devon | Devon | South West | England | EX21 5JB | 245551 | 108489 | Torridge District Council | 1/0332/2013/FULM | [5 empty] | 2013-04-09 |  | 2013-07-15 |  |  | 2014-07-01
C1240 | 2290 | 2014-11-25 | Solar Securities Group Ltd | West Venn solar farm | Solar Photovoltaics |  |  | 10.225 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land At West Venn Farm Ashwater Beaworthy Devon | Devon | South West | England | EX21 5DF | 237810 | 97603 | Torridge District Council | 1/0368/2013/FULM | APP/W1145/A/14/2212551 |  |  |  |  | 2013-04-25 |  | 2013-11-26 | 2014-01-29 |  | 2014-11-18
C1250 | 2291 | 2014-09-16 | Vogt Solar | Marshborough Farm solar park | Solar Photovoltaics |  |  | 12.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Marshborough Farm off Ash Road, Sandwich | Kent | South East | England | CT13 0PJ | 630622 | 157583 | Dover District Council | 13/00332 | APP/X2220/A/13/2203582# |  |  |  |  | 2013-05-04 |  | 2013-08-13 |  |  | 2014-07-21
C1655 | 2292 | 2014-09-16 | TGC Renewables | Aller Farm | Solar Photovoltaics |  |  | 8.27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Aller Farm, East of Woodford and North of Monnksilver, Williton | Somerset | South West | England | TA4 4HH | 307214 | 139932 | West Somerset District Council | 3/28/13/005 | APP/H3320/A/13/2207951 |  |  |  |  | 2013-07-04 |  | 2013-09-30 | 2014-11-05 |  | 2014-10-08
C1669 | 2293 | 2014-11-25 | The Landmark Practice | Littles Manor Farm | Solar Photovoltaics |  |  | 9.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Littles Manor Farm, Ashford Road, Sheldwich, Faversham, Kent | Kent | South East | England | ME13 0LL | 600954 | 158459 | Swale Borough Council | SW/13/0832 | APP/V2255/A/14/2212592 |  |  |  |  | 2013-07-19 |  | 2013-11-22 | 2014-02-05 |  | 2014-05-07
C1700 | 2294 | 2015-08-04 | Sunsave 8 (Pluckley) Limited | Land South of Dowle Street | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a |  | Appeal Refused | Application Refused | Land north of railway and south of, Dowle Street Road, Pluckley, Kent | Kent | South East | England |  | 593459 | 143378 | Ashford Borough Council | 13/00789/AS | APP/E2205/A/14/2215733 |  |  |  |  | 2013-07-30 |  | 2014-02-26 | 2014-04-01 |  | 2015-06-23
B1247 | 2295 | 2018-04-04 | Green Cat Renewables | Tealing Airfield PV | Solar Photovoltaics |  |  | 31 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Former Airfield, Tealing, Dundee, Angus | Tayside | Scotland | Scotland | DD4 | 340350 | 736850 | Angus Council | 14/00428/FULM | [5 empty] | 2014-05-29 | [6 empty] | 2014-12-11 |  |  |  | 2017-12-11
C3101 | 2296 | 2016-04-19 | BNRG Renewables | Manor Farm - Shripney | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Manor Farm Shripney Lane Shripney | West Sussex | South East | England | PO22 9UR | 492911 | 102524 | Arun District Council | BE/63/14/PL | [5 empty] | 2014-06-05 | [6 empty] | 2014-08-12 |  |  |  |  | 2015-12-15 | 2016-03-07
C1980 | 2297 | 2014-09-16 | Temporis Capital | Chainbridge Road | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land 1 Chainbridge Road Lound Nottinghamshire | Nottinghamshire | East Midlands | England |  | 471909 | 386124 | Bassetlaw District Council | 14/00087/FUL | [5 empty] | 2014-01-29 | 2014-08-14
C3061 | 2298 | 2016-07-20 | Mongoose Energy Coop | Chelwood Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Parcel 1326, Church Farm, Main Road, Chelwood, Bristol | Somerset | South West | England | BS39 4NR | 364184 | 161166 | Bath and North East Somerset Council | 14/01895/FUL | [5 empty] | 2014-05-19 | [6 empty] | 2014-09-12 |  |  |  |  | 2015-10-01 | 2015-12-10
C3033 | 2299 | 2016-01-04 | Prosolia UK | Manor Farm - Pertenhall | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Manor Farm Green End Pertenhall Bedfordshire | Bedfordshire | Eastern | England |  | 507682 | 264475 | Bedford Borough Council | 14/00986/MAF | [5 empty] | 2014-05-20 | [6 empty] | 2014-11-19 |  |  |  | 2017-11-19 | 2015-09-01 | 2015-10-17
C3076 | 2300 | 2017-01-16 | Solar Century/ Bluefield Solar | Hardingham Solar Farm - extension | Solar Photovoltaics |  |  | 5.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the East of Hardingham | Norfolk | Eastern | England | NR9 4EG | 605307 | 304915 | Breckland Council | 3PL/2014/0545/F | [5 empty] | 2014-05-23 | [6 empty] | 2014-10-28 |  |  |  | 2017-10-28 | 2014-12-03 | 2015-02-19
C3147 | 2301 | 2015-03-09 | Rethink Energy | Hall Farm and Field Barn Farm - resubmission | Solar Photovoltaics |  |  | 34 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Hall Farm and Field Barn Farm | Norfolk | Eastern | England | NR16 2SB | 594816 | 285818 | Breckland Council | 3PL/2014/0589/F | [5 empty] | 2014-06-09 |  | 2015-02-18
C1097 | 2302 | 2014-09-16 | Green Energy UK Direct Ltd | Nackington Farm Solar Park- Site C | Solar Photovoltaics |  |  | 12.03 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Nackington Farm, Nackington Road, Lower Hardres | Kent | South East | England | CT4 7AF | 615546 | 154407 | Canterbury City Council | CA//14/00085 | [5 empty] | 2014-01-31 | 2014-09-01
C1097A | 2303 | 2014-09-16 | Green Energy UK Direct Ltd | Nackington Farm Solar Park- Site A | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Nackington Farm, Nackington Road, Lower Hardres | Kent | South East | England | CT4 7AF | 615930 | 154399 | Canterbury City Council | CA//14/00087 | [5 empty] | 2014-01-31 | 2014-09-01
C1097B | 2304 | 2014-09-16 | Green Energy UK Direct Ltd | Nackington Farm Solar Park- Site B | Solar Photovoltaics |  |  | 16.61 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Nackington Farm, Nackington Road, Lower Hardres | Kent | South East | England | CT4 7AF | 615546 | 154407 | Canterbury City Council | CA//14/00086 | [5 empty] | 2014-01-31 | 2014-09-01
C3045 | 2305 | 2015-01-08 | Green Switch Developments | Bryn Cyrnau Isaf | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | LAND SOUTH OF, BRYN CYRNAU ISAF, CWMFFRWD, CARMARTHEN, SA31 2LS | Dyfed | Wales | Wales |  | 242800 | 217100 | Carmarthenshire County Council | W/30204 | [5 empty] | 2014-05-23 |  | 2014-12-19
C2923 | 2306 | 2015-08-04 | Epsilon Solar | Melton Road (PV) | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land South of Melton Road, Burton On The Wolds, Leicestershire | Leicestershire | East Midlands | England | LE12 5TQ | 460796 | 321384 | Charnwood Borough Council | P/14/1140/2 | APP/X2410/A/14/2227418 |  |  |  |  | 2014-06-11 |  | 2014-09-01 | 2014-11-13 |  | 2015-07-03
C1121 | 2307 | 2015-04-01 | Green Energy UK Direct Ltd | Brooks Farm Solar Park | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Brooks Farm Murcott Road Lower Arncott | Oxfordshire | South East | England | OX25 1NX | 459891 | 217614 | Cherwell District Council | 14/00950/F | [5 empty] | 2014-06-13 | [6 empty] | 2014-09-05 |  |  |  |  | 2015-01-01 | 2015-03-28
C3027 | 2308 | 2015-04-16 | New Forest Energy Ltd | Christchurch Energy | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at East Close Farm Waterditch, Christchurch | Dorset | South West | England | BH23 7 | 417714 | 95129 | Christchurch Borough Council | 8/14/0226 | [5 empty] | 2014-05-21 | [6 empty] | 2014-08-29 |  |  |  |  | 2015-01-05 | 2015-03-27
C1840 | 2309 | 2018-09-04 | Foresight | Yarburgh Grove Farm | Solar Photovoltaics |  |  | 8.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land rear of Yarburgh Grove Farm, Westfield Road, Yarburgh | Lincolnshire | East Midlands | England |  | 534300 | 391971 | East Lindsey District Council | N/218/00928/14 | [5 empty] | 2014-05-21 | [6 empty] | 2014-10-20 |  |  |  | 2017-10-20 | 2015-10-01 | 2015-11-12
C3136 | 2310 | 2014-09-16 | AEE Renewables | Nibley Mill Farm | Solar Photovoltaics |  |  | 15.94 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Lydney Gloucestershire GL15 4LN | Gloucestershire | South West | England |  | 365269 | 204909 | Forest of Dean District Council | P0871/14/FUL | [5 empty] | 2014-05-28 |  | 2014-09-10
C3146 | 2311 | 2015-08-28 | Abbey Renewables | Theddingworth solar farm | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land At Beeches Farm Mowsley Road Theddingworth Leicestershire | Leicestershire | East Midlands | England |  | 465520 | 286041 | Harborough District Council | 14/00833/FUL | [5 empty] | 2014-06-13 | 2014-11-27
C1278 | 2312 | 2016-07-01 | PS Renewables | Taplins Farm solar park | Solar Photovoltaics |  |  | 5.93 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of Taplins Farm Lane Winchfield Hook Hampshire | Hampshire | South East | England |  | 477955 | 154961 | Hart District Council | 14/00998/MAJOR | [5 empty] | 2014-05-30 | [6 empty] | 2014-10-20 |  |  |  | 2017-10-20 | 2016-05-01 | 2016-06-15
C3100 | 2313 | 2014-11-23 | Costain Engineering & Construction | Sipson Road | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Adj To Sipson Road, In Holloway Lane, Harmondsworth, West Drayton, Middlesex | Greater London | London | England | UB7 0AE | 506712 | 178385 | Hillingdon London Borough Council | 46223/APP/2014/1867 | [5 empty] | 2014-06-02 |  | 2014-10-30
C3137 | 2314 | 2016-03-15 | Anesco | Homestead Farm | Solar Photovoltaics |  |  | 10.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | land at Homestead Farm, Caulbourne Lane AND land at Lower Dodpits Farm, Warlands Lane, Ningwood, Newport | Isle of Wight | South East | England | PO30 | 439433 | 88404 | Isle of Wight Council | P/00607/14 | [5 empty] | 2014-05-20 | [6 empty] | 2014-10-21 |  |  |  | 2017-10-21 | 2015-09-15 | 2015-12-15
C2165 | 2315 | 2017-04-26 | Sunsave 22 (Pagehurst Farm) Limited | Great Pagehurst Farm | Solar Photovoltaics |  |  | 13.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Great Pagehurst Farm, Pagehurst Road, Staplehurst, Tonbridge, Kent | Kent | South East | England | TN12 0JD | 576155 | 144510 | Maidstone Borough Council | 13/1456 | APP/U2235/W/16/3146969 |  |  |  |  | 2013-09-19 |  | 2016-02-11 | 2016-04-22 |  | 2017-04-10
C3063 | 2316 | 2014-09-16 | Sunsave 24 (West Woodlands) Limited | Court Farm (Frome) | Solar Photovoltaics |  |  | 6.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Farm West Woodlands, Frome | Somerset | South West | England | BA11 5EN | 377846 | 144006 | Mendip District Council | 2014/0852/FUL | APP/Q3305/W/14/2226815 |  |  |  |  | 2014-05-08 |  | 2014-08-06 | 2014-10-16 |  | 2015-08-24
C3149 | 2317 | 2015-10-05 | Good Energy Generation | Worminster Down | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Worminster Down Cross Farm North Wootton | Somerset | South West | England | BA4 4HB | 356062 | 142974 | Mendip District Council | 2014/0962/FUL | APP/Q3305/W/15/3003992 |  |  |  |  | 2014-06-10 |  | 2014-08-19 | 2015-03-18 |  | 2015-08-28
C3108 | 2318 | 2014-09-16 | British Solar Renewables | Great Curham Farm (resubmission) | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at NGR 300991 111214 (Great Curham Farm) Brithem Bottom Devon | Devon | South West | England |  | 300756 | 111313 | Mid Devon District Council | 14/00889/MFUL | [5 empty] | 2014-06-02 |  | 2014-08-29
C3041 | 2319 | 2016-04-22 | Green Energy UK Direct Ltd/ Vogt Solar | The Kickles | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | The Kickles Lakes Lane Newport Pagnell | Buckinghamshire | South East | England | MK16 8EF | 486215 | 244957 | Milton Keynes Council | 14/01068/FUL | [5 empty] | 2014-05-22 | [6 empty] | 2014-11-07 |  |  |  | 2017-11-07 | 2015-11-25 | 2016-03-22
C3020 | 2320 | 2015-05-14 | Lightsource Renewable Energy | Eakring Solar Farm | Solar Photovoltaics |  |  | 11.88 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To North Of Eaking Road Eakring Nottinghamshire | Nottinghamshire | East Midlands | England |  | 466033 | 362403 | Newark and Sherwood District Council | 14/00839/FULM | [5 empty] | 2014-05-09 | [6 empty] | 2014-10-08 |  |  |  | 2017-10-08 | 2014-12-01 | 2015-03-20
C3126 | 2321 | 2016-10-04 | United Photovoltaics | Egmanton Solar Farm - resubmission | Solar Photovoltaics |  |  | 14.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Between Weston Road, And The A1, Egmanton, Nottinghamshire | Nottinghamshire | East Midlands | England | NG22 0HB | 474907 | 368832 | Newark and Sherwood District Council | 14/00975/FULM | [5 empty] | 2014-06-05 | [6 empty] | 2014-07-23 |  |  |  |  | 2014-12-01 | 2015-03-30
C3110 | 2322 | 2014-11-23 | Phoenix Capital R-Energy Ltd | Coal Pit Lane | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Application Withdrawn | Application Withdrawn | Land Between M4 And Channel View, Castleton, Cardiff | Gwent | Wales | Wales |  | 324689 | 183126 | Newport City Council | 14/0531 | [5 empty] | 2014-06-06 | 2014-10-13
C1281 | 2323 | 2015-04-01 | Inazin Energy Limited/Low Carbon | Branston solar park | Solar Photovoltaics |  |  | 18.9 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adj Mere Road Branston Lincoln | Lincolnshire | East Midlands | England |  | 502105 | 366002 | North Kesteven District Council | 14/0672/FUL | [5 empty] | 2014-06-02 | [6 empty] | 2014-10-15 |  |  |  | 2017-10-15 | 2014-11-09 | 2015-03-31
C3042 | 2324 | 2017-05-03 | Lightsource Renewable Energy | Moira Road | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Adjacent land north and west of no 63 Moira Road Crumlin Co. Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT29 4JL | 129536 | 531688 | Northern Ireland Planning Service | T/2014/0201/F | [5 empty] | 2014-05-27 | [6 empty] | 2014-12-03 |  |  |  | 2019-12-03 | 2017-01-20 | 2017-03-15
C3095 | 2325 | 2017-07-03 | John Laing Environmental Assets Group | Golden Hill | Solar Photovoltaics |  |  | 6.2 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of Mylett's Hill, Golden Hill, Pembroke, Pembrokeshire | Dyfed | Wales | Wales | SA71 4 | 199087 | 202465 | Pembrokeshire County Council | 14/0129/PA | [5 empty] | 2014-05-07 | [6 empty] | 2014-09-10 |  |  |  |  | 2014-12-01 | 2015-03-31
C3109 | 2326 | 2015-06-19 | Wessex Solar Energy | Chapel Hill | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land east of Chapel Hill, Orielton, Pembroke, Dyfed | Dyfed | Wales | Wales | SA71 5HY | 196092 | 197842 | Pembrokeshire County Council | 14/0148/PA | [5 empty] | 2014-05-14 | [6 empty] | 2014-07-29 |  |  |  |  | 2015-01-01 | 2015-03-27
C2323 | 2327 | 2017-05-26 | Lightsource Renewable Energy | Pen Rhiw Caradog | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | FARMHOUSE, PENRHIW CRADOC FARM, LLANWONNO ROAD, MOUNTAIN ASH, CF45 3UX | Mid Glamorgan | Wales | Wales |  | 304594 | 197985 | Rhondda Cynon Taff County Borough Council | 13/0901/10 | [5 empty] | 2013-09-03 | [6 empty] | 2016-07-11 |  |  |  | 2019-07-11 | 2016-11-07 | 2017-02-24
C3054 | 2328 | 2014-09-18 | Green Energy UK Direct | Skinners Farm | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Skinners Farm, Skinners Lane, Edenbridge | Kent | South East | England | TN8 6LW | 546008 | 146601 | Sevenoaks District Council | 14/01270/FUL | [5 empty] | 2014-05-20 | 2014-08-19
B1293 | 2329 | 2017-02-02 | Allianz | Vine Farm Solar Park | Solar Photovoltaics |  |  | 45 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Vine House, Vine Farm, High Street, Shingay Cum Wendy, Royston | Cambridgeshire | Eastern | England | SG8 0HJ | 532326 | 247631 | South Cambridgeshire District Council | S/1067/14/FL |  |  | Call-in |  |  | 2014-05-09 | [7 empty] | 2014-08-06 |  | 2014-09-02 | 2017-09-02 | 2015-08-01 | 2016-03-15
C3055 | 2330 | 2016-01-04 | AEE Renewables | Green Farm | Solar Photovoltaics |  |  | 9.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Green Farm, Folly Road, Iron Acton, South Gloucestershire | Avon | South West | England | BS37 9TU | 366325 | 184511 | South Gloucestershire Council | PK14/1755/F | APP/P0119/W/15/3004513 |  |  |  |  | 2014-05-12 |  | 2014-10-31 | 2015-02-20 |  | 2015-12-21
B1254 | 2331 | 2018-05-02 | Foresight | Coombeshead Solar Farm | Solar Photovoltaics |  |  | 7.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Coombeshead Farm Diptford | Devon | South West | England |  | 274517 | 55506 | South Hams District Council | 17/0265/14/F | [5 empty] | 2014-01-31 | [6 empty] | 2014-08-29 |  |  |  |  | 2014-09-01 | 2015-03-15
C3075 | 2332 | 2016-07-18 | Push Energy/ NextEnergy Solar Fund (NESF) | Decoy Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Decoy Farm, Spalding Road, Crowland, Peterborough | Lincolnshire | East Midlands | England | PE6 0LX | 526272 | 312782 | South Holland District Council | H02-0454-14 | [5 empty] | 2014-05-29 | [6 empty] | 2014-08-13 |  |  |  |  | 2015-06-08 | 2015-11-13
C3031 | 2333 | 2015-05-06 | Chalgrove Solar | Easington Farm (Chalgrove) | Solar Photovoltaics |  |  | 21.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Part of Easington Farm near Monument Business Park Chalgrove | Oxfordshire | South East | England | OX44 7RW | 465126 | 197272 | South Oxfordshire District Council | P14/S1734/FUL | [5 empty] | 2014-06-03 | [6 empty] | 2014-08-14 |  |  |  |  | 2015-01-19 | 2015-03-17
C3111 | 2334 | 2015-06-19 | Solar Park Developments | Gelliwern Isaf Farm | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to South of Gelliwern Isaf Felindre Swansea | West Glamorgan | Wales | Wales | SA5 7PJ | 262382 | 202019 | City and County Council of Swansea | 2014/0739 | [5 empty] | 2014-05-21 | [6 empty] | 2014-11-12 |  |  |  | 2019-11-12 | 2015-01-01 | 2015-03-31
C3148 | 2335 | 2018-05-02 | Foresight | Sawmills Solar Farm | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Sawmills, Ashcombe Estate, Ashcombe, Devon | Devon | South West | England | EX7 0QD | 291535 | 78055 | Teignbridge District Council | 14/01576/MAJ | [5 empty] | 2014-05-30 | [6 empty] | 2014-11-07 |  |  |  | 2016-11-07 | 2015-02-04 | 2015-03-16
C3053 | 2336 | 2015-05-14 | Lightsource Renewable Energy | Walland Farm | Solar Photovoltaics |  |  | 5.02 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Associated With Walland Farm Bucks Cross Woolsery Devon | Devon | South West | England | EX39 5DP | 235344 | 122223 | Torridge District Council | 1/0518/2014/FULM | [5 empty] | 2014-05-22 | [6 empty] | 2014-08-21 |  |  |  |  | 2014-11-11 | 2015-02-04
C1750 | 2337 | 2014-09-18 | West Coast Energy | Capel Grange | Solar Photovoltaics |  |  | 10.36 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | OS Plot 8200 Badsell Road Five Oak Green Tonbridge Kent | Kent | South East | England |  | 565033 | 144747 | Tunbridge Wells Borough Council | 14/00271/FULL | [5 empty] | 2014-02-03 |  | 2014-09-15
C2659 | 2338 | 2016-06-21 | Elgin Energy EsCo | Weycock Road | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off Weycock Cross, Waycock Road, Barry, South Glamorgan | South Glamorgan | Wales | Wales | CF62 3AA | 309173 | 169565 | Vale of Glamorgan Council | 2014/00081/FUL | [5 empty] | 2014-01-22 | [6 empty] | 2014-08-01 |  |  |  |  | 2015-11-26 | 2016-03-02
C3086 | 2339 | 2015-01-08 | British Solar Renewables | Southern Counties Shooting Ground | Solar Photovoltaics |  |  | 8.75 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Southern Counties Shooting Ground, Southern Counties Leisure, Long Ash Lane, Wardon Hill, Dorchester | Dorset | South West | England | DT2 9PW | 360954 | 102552 | West Dorset District Council | WD/D/14/001307 | [5 empty] | 2014-05-21 |  | 2014-12-17
C3155 | 2340 | 2015-08-04 | Wessex Solar Energy | Yellowham solar park | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Higher Kingston Farm, Higher Kingston Farm Lane, Stinsford, Dorchester, Dorset | Dorset | South West | England | DT2 8QE | 371584 | 92877 | West Dorset District Council | WD/D/14/001496 | APP/F1230/W/14/3001896 |  |  |  |  | 2014-06-12 |  | 2014-11-07 | 2015-01-30 |  | 2015-06-30
C3124 | 2341 | 2014-09-18 | Lightsource Renewable Energy | Wootton Balk | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Refused | Application Refused | Land adjacent to Banbury Road Wootton Balk Tackley | Oxfordshire | South East | England |  | 446470 | 220271 | West Oxfordshire District Council | 14/0819/P/FP | [5 empty] | 2014-06-04 |  | 2014-08-08
C3039 | 2342 | 2015-05-28 | Anesco | Higher Bye Farm | Solar Photovoltaics |  |  | 6.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Higher Bye Farm, Higher Bye Farm | Somerset | South West | England | TA23 0JT | 305042 | 142360 | West Somerset District Council | 3/26/14/013 | [5 empty] | 2014-05-23 | [6 empty] | 2014-09-26 |  |  |  | 2017-09-26 | 2015-01-01 | 2015-03-19
B1327 | 2343 | 2015-07-14 | Next Energy Solar Fund Ltd | Cockhill Solar Farm | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Cockhill Farm Cockhill Trowbridge Wiltshire | Wiltshire | South West | England | BA14 9BQ | 384487 | 159180 | Wiltshire Council | 14/05596/FUL | [5 empty] | 2014-06-10 | [6 empty] | 2014-08-28 |  |  |  |  | 2014-11-15 | 2015-03-26
C2258 | 2344 | 2015-07-16 | Hive Energy | Bentham Farm | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bentham Farm, Bentham Lane,Bentham, Purton, Swindon, Wiltshire | Wiltshire | South West | England | SN5 4JB | 407114 | 189633 | Wiltshire Council | 13/04872/FUL | [5 empty] | 2013-10-08 | [6 empty] | 2014-12-15 |  |  |  | 2017-12-15 | 2015-03-15 | 2015-07-15
C3049 | 2345 | 2015-04-15 | Lark Energy | Boscombe Airfield | Solar Photovoltaics |  |  | 12.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | land adjacent to Boscombe Downs Airbase just off Tidworth Road, Idmiston | Wiltshire | South West | England |  | 418428 | 139160 | Wiltshire Council | 14/05740/FUL | [5 empty] | 2014-06-12 | [6 empty] | 2014-11-24 |  |  |  | 2017-11-24 | 2015-01-01 | 2015-03-31
C2626 | 2346 | 2014-11-06 | Hive Energy | Forty Green Farm | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Forty Green Farm Forty Green Bledlow Buckinghamshire | Buckinghamshire | South East | England | HP27 9PN | 476729 | 203583 | Wycombe District Council | 14/05105/FUL | [5 empty] | 2014-01-24 |  | 2014-10-29
B1028 | 2347 | 2018-02-02 | Foresight Solar Fund | Shotwick Solar Farm | Solar Photovoltaics |  |  | 45.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Weighbridge Road, Sealand, Deeside, Clwyd, CH5 2NN | Flintshire | Wales | Wales | CH5 2NN | 331844 | 372029 | Flintshire County Council | 051772 | [5 empty] | 2014-02-21 | [6 empty] | 2015-06-01 |  |  |  | 2017-06-01 | 2015-11-15 | 2016-03-31
C0214 | 2348 | 2014-09-19 | Solar Securities Group | Winnards Perch Solar Farm | Solar Photovoltaics |  |  | 3.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Southmoor Farm, Winnards Perch, St Columb, Cornwall | Cornwall | South West | England | TR9 6DG | 192864 | 66586 | Cornwall Council | PA12/05258 | [5 empty] | 2012-06-13 | [6 empty] | 2012-10-26 |  |  |  |  | 2013-06-15 | 2013-07-31
C1932 | 2349 | 2018-08-30 | Good Energy Generation | Lanyon Farm | Solar Photovoltaics |  |  | 12.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Lanyon Farm Gwinear Lane Gwinear Hayle Cornwall | Cornwall | South West | England | TR27 5LA | 160383 | 37814 | Cornwall Council | PA13/07812 | APP/D0840/A/14/2213745 |  |  |  |  | 2013-09-04 |  | 2013-11-25 | 2014-08-19 | 2016-06-07
C1959 | 2350 | 2018-05-18 | Novus Solar Developments | Blaen Bowi Solar park | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Blaen Bowi, Capel Iwan, Newcastle Emlyn, Dyfed | Dyfed | Wales | Wales | SA38 9NG | 232248 | 235208 | Carmarthenshire County Council | W/28837 | [5 empty] | 2013-09-09 | [6 empty] | 2014-05-14 |  |  |  | 2017-05-14
C2233 | 2351 | 2015-04-15 | Hive Energy | Lodge Farm (Poulshot) | Solar Photovoltaics |  |  | 14.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lodge Farm Poulshot Road Poulshot Devizes Wiltshire | Wiltshire | South West | England | SN10 1RQ | 396417 | 190978 | Wiltshire Council | 13/05244/FUL | [5 empty] | 2013-10-23 | [6 empty] | 2014-02-27 |  |  |  |  | 2014-09-15 | 2015-03-31
B0741 | 2352 | 2015-04-15 | Vento Ludens | Glebe Farm Solar Energy Park | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The North East Glebe Farm Forty Foot Lane Souldrop Bedfordshire | Bedfordshire | Eastern | England |  | 496400 | 262540 | Bedford Borough Council | 13/00218/MAF | [5 empty] | 2013-02-05 | [6 empty] | 2013-06-03 |  |  |  |  | 2014-11-24 | 2015-03-31
B0993 | 2353 | 2015-04-16 | New Forest Energy Ltd | Bryn yr Odyn Solar Farm | Solar Photovoltaics |  |  | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bryn yr Odyn | Isle of Anglesey | Wales | Wales |  | 239600 | 373400 | Isle of Anglesey County Council | 10C118A/RE | [5 empty] | 2013-09-08 | [6 empty] | 2013-11-06 |  |  |  |  | 2014-11-06 | 2015-02-28
B1316 | 2354 | 2015-05-29 | Wessex Solar Energy | Rhyd-y-Pandy Solar Farm | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cefn Betingau Farm, Rhydypandy Road, Morriston, Swansea | West Glamorgan | Wales | Wales | SA6 6NX | 266057 | 201531 | City and County Council of Swansea | 2013/1639 | [5 empty] | 2013-11-15 | [6 empty] | 2014-02-20 |  |  |  |  | 2014-11-01 | 2015-03-06
C1204 | 2355 | 2015-08-11 | Anesco | Saron Road solar park | Solar Photovoltaics |  |  | 6.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | E/O Saron Road, N/O Dyffryn Road, Saron, Ammanford, Dyfed | Dyfed | Wales | Wales | SA18 3TW | 260904 | 212664 | Carmarthenshire County Council | E/28054 | [5 empty] | 2013-04-12 | [6 empty] | 2013-09-19 |  |  |  |  | 2014-11-24 | 2015-02-15
C1300 | 2356 | 2015-06-19 | Pfalz Solar | Tiln Farm solar park | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of Tiln Farm Tiln Lane Retford Nottinghamshire | Nottinghamshire | East Midlands | England |  | 471371 | 383853 | Bassetlaw District Council | 13/00997/FUL | [5 empty] | 2013-09-27 | [6 empty] | 2013-12-20 |  |  |  |  | 2015-01-01 | 2015-03-31
C1555 | 2357 | 2015-04-15 | Lark Energy | Langford Solar Farm | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Edworth Road, Biggleswade, Bedfordshire | Bedfordshire | Eastern | England | SG18 9PJ | 519906 | 239446 | Central Bedfordshire Council | CB/13/02288/FULL | [5 empty] | 2013-06-28 | [6 empty] | 2013-09-24 |  |  |  |  | 2014-06-01 | 2015-03-31
C1797 | 2358 | 2017-11-02 | South West Solar Parks | Stokes Marsh Farm | Solar Photovoltaics |  |  | 16.62 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stokes Marsh Farm Coulston Westbury Wilts | Wiltshire | South West | England | BA13 4NZ | 394200 | 156500 | Wiltshire Council | 13/02309/FUL | [5 empty] | 2013-08-01 | [6 empty] | 2013-12-18 |  |  |  |  | 2014-12-01 | 2015-03-12
C1897 | 2359 | 2016-05-10 | INRG Solar | West Hall Solar Farm | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at West Hall Farm, Aberthaw, St. Athan | South Glamorgan | Wales | Wales |  | 302351 | 167146 | Vale of Glamorgan Council | 2013/00724/FUL | [5 empty] | 2013-08-01 | [6 empty] | 2014-01-17 |  |  |  |  | 2014-01-18 | 2014-03-31
C1903 | 2360 | 2015-05-28 | FC Palmer & Sons Ltd | Stowbridge Farm - Extension (Phase 1) | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stowbridge Farm, Green End, Stretham, Cambridgeshire | Cambridgeshire | Eastern | England | CB6 3LF | 551763 | 272656 | South Cambridgeshire District Council | S/1516/13/FL | [5 empty] | 2013-08-20 | [6 empty] | 2014-03-06 |  |  |  |  | 2014-12-01 | 2015-03-20
C1942 | 2361 | 2015-05-28 | Sovereign Energy Partners LLP | Bourne Park (Solar) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hanford Plc, Bourne Park, Piddlehinton, Dorchester | Dorset | South West | England | DT2 7TU | 372299 | 97660 | West Dorset District Council | 1/D/13/001116 | [5 empty] | 2013-08-09 | [6 empty] | 2013-10-30 |  |  |  |  | 2015-01-01 | 2015-03-19
C2030 | 2362 | 2015-04-14 | United Photovoltaics | Hall Farm | Solar Photovoltaics |  |  | 5.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hall Farm, Radstone, Brackley | Northamptonshire | East Midlands | England |  | 458154 | 239733 | South Northamptonshire Council | S/2013/1228/MAF | [5 empty] | 2013-09-23 | [6 empty] | 2013-12-03 |  |  |  | 2016-12-03 | 2014-12-01 | 2015-03-30
C2032 | 2363 | 2015-03-19 | Brynteg Solar | Brynteg Farm | Solar Photovoltaics |  |  | 16.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land forming part of Brynteg farm adjacent to the B4309, five roads, Llanelli | Dyfed | Wales | Wales | SA15 4ND | 249621 | 203809 | Carmarthenshire County Council | S/28898 | [5 empty] | 2013-09-19 | [6 empty] | 2014-03-11 |  |  |  |  | 2014-09-01 | 2014-12-22
C2040 | 2364 | 2016-05-10 | Lark Energy | Stonepit Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stonepit Farm Hanslope Road Hartwell | Northamptonshire | East Midlands | England |  | 479012 | 249026 | South Northamptonshire Council | S/2013/1201/MAF | [5 empty] | 2013-09-16 | [6 empty] | 2013-12-24 |  |  |  |  | 2014-05-28 | 2014-07-28
C2156 | 2365 | 2016-02-05 | Sunsave 23 Limited/ Vogt solar | Yerbeston Gate Farm | Solar Photovoltaics |  |  | 6.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north, west and south of Yerbeston Gate, Yerbeston, Kilgetty, SA68 0NS | Dyfed | Wales | Wales | SA68 0NS | 207186 | 209092 | Pembrokeshire County Council | 13/0501/PA | [5 empty] | 2013-09-02 | [6 empty] | 2013-12-02 |  |  |  |  | 2015-09-25 | 2015-11-25
C2229 | 2366 | 2015-06-15 | Green Switch Solutions | Grange Farm (Lincolnshire) | Solar Photovoltaics |  |  | 12.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Grange Farm, Fishergate, Sutton St James, Spalding, Lincs | Lincolnshire | East Midlands | England | PE12 0EZ | 538539 | 318458 | South Holland District Council | H20-0937-13 | [5 empty] | 2013-11-01 | [6 empty] | 2014-03-19 |  |  |  |  | 2014-10-01 | 2015-03-30
C2275 | 2367 | 2015-04-20 | Bluefield Solar Income Fund | Molehill Farm | Solar Photovoltaics |  |  | 18 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Molehill Farm, Chestfield, Whitestable, Kent | Kent | South East | England | CT6 7PA | 614920 | 166471 | Canterbury City Council | CA//13/02004 | [5 empty] | 2013-10-30 | [6 empty] | 2014-02-05 |  |  |  |  | 2015-01-01 | 2015-03-31
C2340 | 2368 | 2015-04-20 | Bluefield Solar Income Fund | Pashley Farm | Solar Photovoltaics |  |  | 11.5 | n/a | 1.4 |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pashley Farm, Ninfield Road, Bexhill on Sea, East Sussex | East Sussex | South East | England | TN39 5JS | 570890 | 110991 | Wealden District Council | WD/2013/2223/MAJ | [5 empty] | 2013-11-04 | [6 empty] | 2014-01-10 |  |  |  |  | 2014-08-01 | 2015-03-31
C2376 | 2369 | 2018-07-05 | NESF (formerly Lark Energy) | Fiskerton Airfield (Phase 1) | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Reepham Road, Fiskerton, Lincoln | Lincolnshire | East Midlands | England | LN3 4EZ | 504955 | 373023 | West Lindsey District Council | 130671 | [5 empty] | 2013-11-07 | [6 empty] | 2014-01-30 |  |  |  |  | 2014-08-01 | 2015-03-31
C2455 | 2370 | 2015-03-31 | Conergy UK | Hendai Farm | Solar Photovoltaics |  |  | 13.35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Hendai Farm Heol Adam Gelligaer Hengoed CF82 8FU | Mid Glamorgan | Wales | Wales | CF82 8FU | 311830 | 198070 | Caerphilly County Borough Council | 13/0846/FULL | [5 empty] | 2013-12-10 | [6 empty] | 2014-04-10 |  |  |  |  | 2014-10-01 | 2015-03-01
C2489 | 2371 | 2017-09-21 | BNRG Northern Power | Tullynaskeagh Solar Farm | Solar Photovoltaics |  |  | 5.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land immediately north of No. 22 Tullynaskeagh Road, Downpatrick | Co. Down | Northern Ireland | Northern Ireland | BT30 7EU | 164660 | 496054 | Northern Ireland Planning Service | R/2013/0361/F | [5 empty] | 2013-08-15 | [6 empty] | 2014-01-17 |  |  |  | 2019-01-17
C2497 | 2372 | 2017-02-02 | Vortex (formerly Sun Edison) | Bury Lane Fruit Farm | Solar Photovoltaics |  |  | 24 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bury Lane Fruit Farm, Melbourn Bypass, Meldreth, Royston, Cambridgeshire | Cambridgeshire | Eastern | England | SG8 6DF | 537290 | 244247 | South Cambridgeshire District Council | S/2616/13/FL | [5 empty] | 2013-12-18 | [6 empty] | 2014-05-12 |  |  |  |  | 2014-09-01 | 2014-12-19
C2698 | 2373 | 2018-09-04 | Foresight | Marsh Farm Hilperton | Solar Photovoltaics |  |  | 9.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Marsh Farm Marsh Road Hilperton Marsh Wiltshire | Wiltshire | South West | England | BA14 7PJ | 387169 | 160365 | Wiltshire Council | 14/00592/FUL | [5 empty] | 2014-01-29 | [6 empty] | 2014-04-30 |  |  |  |  | 2014-12-01 | 2015-03-14
C2710 | 2374 | 2017-07-19 | Granite Solar | Land east of Kingsley Sports Club - resubmission | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a |  | Planning Permission Expired | Planning Permission Expired | Sickles Lane, Kingsley, Alton | Hampshire | South East | England |  | 479288 | 138479 | East Hampshire District Council | 52947/002 | [5 empty] | 2014-01-29 | [6 empty] | 2014-04-30 |  |  |  | 2017-04-30
C2846 | 2375 | 2015-02-25 |  | Ashlawn Farm | Solar Photovoltaics |  |  | 6.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ashlawn Farm, Pill Road, Rooksbridge, Axbridge, Somerset, BS26 2TS | Somerset | South West | England | BS26 2TS | 337007 | 151114 | Sedgemoor District Council | 24/14/00007 | [5 empty] | 2014-03-21 | [6 empty] | 2014-05-14 |  |  |  |  | 2014-10-01 | 2015-03-31
IF1129 | 2376 | 2018-09-04 | Foresight | Cuckoo Grove Farm | Solar Photovoltaics |  |  | 6.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the North of Cuckoo Grove Farm, Cuckoo Lane, Haverfordwest, SA61 2UY | Dyfed | Wales | Wales | SA61 2UY | 192777 | 216646 | Pembrokeshire County Council | 12/0744/PA | [5 empty] | 2012-11-09 | [6 empty] | 2013-04-25 |  |  |  |  | 2015-01-01 | 2015-03-26
IF1146 | 2377 | 2018-09-04 | Foresight | Gedling Solar Farm | Solar Photovoltaics |  |  | 5.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Gedling Colliery, Arnold Lane, Gedling, Nottinghamshire | Nottinghamshire | East Midlands | England | NG4 4GZ | 461655 | 344045 | Gedling Borough Council | 2012/1335 | [5 empty] | 2012-11-21 | [6 empty] | 2013-10-23 |  |  |  |  | 2014-08-01 | 2015-03-15
IF1157 | 2378 | 2015-02-03 | Anesco | Bilsthorpe Quarry Solar Park | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bilsthorpe Business Park Eakring Road Bilsthorpe Nottinghamshire | Nottinghamshire | East Midlands | England | NG22 8 | 465301 | 360985 | Newark and Sherwood District Council | 12/01594/FULM | [5 empty] | 2012-12-05 | [6 empty] | 2013-08-12 | [5 empty] | 2014-11-18
IF1361 | 2379 | 2015-03-05 | Bluefield Solar Income Fund | Littlebourne | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Elbridge farm, Stturry, Cantenbury, Kent | Kent | South East | England | CT3 1TL | 619386 | 157434 | Canterbury City Council | CA//13/01750 | [5 empty] | 2013-10-02 | [6 empty] | 2014-01-08 |  |  |  |  | 2014-07-01 | 2014-11-13
IF1405 | 2380 | 2014-11-28 | Lark Energy | Wellingborough Solar Farm | Solar Photovoltaics |  |  | 8.53 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Great Doddington, Wellingborough, Northamptonshire | Northamptonshire | East Midlands | England | NN29 7TU | 489205 | 265630 | Wellingborough Borough Council | WP/2013/0372 | [5 empty] | 2013-07-22 | [6 empty] | 2013-10-09 |  |  |  |  | 2013-12-01 | 2014-03-31
AA225 | 2381 | 2014-09-16 | St. Modwen Developments | Baglan Bay Solar Farm - Phase 1 | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Baglan Energy Park, Port Talbot | West Glamorgan | Wales | Wales |  | 273414 | 191650 | Neath Port Talbot County Borough Council | P2011/0054 | [5 empty] | 2011-02-01 | [6 empty] | 2013-01-30 | [5 empty] | 2014-03-30
C0911 | 2382 | 2014-11-05 | Green Energy UK Direct Ltd | Gover Farm Solar Park | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Gover Farm Gover Hill Mount Hawke St Agnes Cornwall | Cornwall | South West | England |  | 172387 | 48080 | Cornwall Council | PA13/03890 | [5 empty] | 2013-06-05 | [6 empty] | 2013-08-30 |  |  |  |  | 2014-02-03 | 2014-10-24
C1005 | 2383 | 2015-09-29 | Kronos Solar | Kerriers Solar Park | Solar Photovoltaics |  |  | 9.58 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Kerriers Withiel Bodmin Cornwall | Cornwall | South West | England |  | 200121 | 64070 | Cornwall Council | PA12/10939 | [5 empty] | 2013-01-15 | [6 empty] | 2013-03-15 |  |  |  |  | 2014-02-01 | 2014-09-19
C1010 | 2384 | 2016-05-10 | Wessex Solar Energy | Hullavington Solar Park | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Hullavington, Wiltshire | Wiltshire | South West | England |  | 388650 | 182700 | Wiltshire Council | 13/01495/FUL | [5 empty] | 2013-05-22 | [6 empty] | 2013-11-13 |  |  |  |  | 2014-10-20 | 2015-02-03
B0096 | 2385 | 2012-01-11 | Thames Water Utilities | Crossness Sewage Works PV | Solar Photovoltaics |  |  | 1.503 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Belvedere Road, London | Greater London | London | England | SE2 9AR | 548450 | 180950 | Bexley London Borough Council | [19 empty] | 2011-07-27
AA342 | 2386 | 2012-10-25 | Solar Power Generation | Higher Hill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Butleigh, Glastonbury, Somerset | Somerset | South West | England |  | 351817 | 131004 | Mendip District Council | 2011/0688 | [5 empty] | 2011-03-29 | [6 empty] | 2011-06-24 | [5 empty] | 2011-09-26
AA336 | 2387 | 2013-03-14 | Private Developer | Manor Farm (Keinton Mandeville) | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Keinton Mandeville, Somerset | Somerset | South West | England |  | 355189 | 130227 | Mendip District Council | 2011/0687 | [5 empty] | 2011-03-29 | [6 empty] | 2011-05-23 | [5 empty] | 2011-07-15
B0097 | 2388 | 2013-10-08 | Thames Water Utilities | Walton WTW PV | Solar Photovoltaics |  |  | 1.786 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | Walton Water Treatment Works, Hurst Road, Walton On Thames, Surrey | Surrey | South East | England |  | 511550 | 168450 | Elmbridge Borough Council | [19 empty] | 2011-07-30
B1287 | 2389 | 2014-04-02 | Wolseley UK | Wolseley National Distribution Centre | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Wolseley Centre, Harrison Way, Leamington Spa | Warwickshire | West Midlands | England | CV31 3HH | 431775 | 264043 | Warwick District Council | [19 empty] | 2014-03-18
B0888 | 2390 | 2013-10-01 | Anglian Water Services Ltd | Colchester STW | Sewage Sludge Digestion |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Colchester Sewage Treatment Works Haven Road, Colchester, CO2 8HT | Essex | Eastern | England |  | 601995 | 223773 | Essex County Council | 121032 | [5 empty] | 2012-06-01 | [6 empty] | 2012-10-09 | [5 empty] | 2013-09-11
A0156 | 2391 | 2012-08-29 | Dwr Cymru Welsh Water | Cardiff Waste Water Treatment | Sewage Sludge Digestion |  |  | 5.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Tide Fields Road, Splott, Cardiff, South Glamorgan. CF24 2 | South Glamorgan | Wales | Wales |  | 320496 | 176903 | Cardiff Council | 08/01949/E | [5 empty] | 2008-08-11 | [6 empty] | 2008-12-10 |  |  |  |  | 2009-09-01 | 2010-10-02
B1334 | 2392 | 2020-02-20 | Thames Water Utilities | Longreach STW - extension | Sewage Sludge Digestion |  |  | 1.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Long Reach Sewage Treatment Works, Marsh Street, Dartford, Kent | Kent | South East | England | DA1 5PP | 555150 | 176522 | Kent County Council | DA/12/1170 | [5 empty] | 2012-09-24 | [6 empty] | 2012-10-15 |  |  |  |  | 2013-07-01 | 2014-07-01
AA686 | 2393 | 2020-05-19 | Thames Water Utilities | Riverside Sewage Treatment Works Digestion Plant | Sewage Sludge Digestion |  |  | 4 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Riverside Sewage Treatment Works, Ferry Lane, North Off Lamson Road, Rainham | Greater London | London | England | RM13 8QS | 551737 | 181984 | Havering London Borough Council | U0005.08 | [5 empty] | 2008-06-02 | [6 empty] | 2009-10-30 |  |  |  |  | 2012-08-27 | 2014-01-30
B0130 | 2394 | 2014-03-04 | Northumbrian Water | Howdon STW | Sewage Sludge Digestion |  |  | 6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land South of Northumberland Dock Road East Howdon North Tyneside Tyne & Wear | Tyne and Wear | North East | England |  | 436432 | 568239 | North Tyneside Council | 10/01823/FUL | [5 empty] | 2010-07-21 | [6 empty] | 2010-10-14 | [5 empty] | 2012-09-01
B0397 | 2397 | 2018-04-25 | Atlantic Resource | AR-1000 (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | EMEC | Offshore | Offshore | Scotland |  | 314195 | 1009356 | Scottish Government (S36) | [6 empty] | 2010-07-01 | [6 empty] | 2011-01-01 |  |  |  |  | 2011-06-15 | 2011-07-15
B0407 | 2399 | 2018-04-24 | Rolls Royce TGL | TGL (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | EMEC | Offshore | Offshore | Scotland |  | 314195 | 1009356 | Scottish Government (S36)
B0408 | 2400 | 2012-06-20 | Voith Hydro | Voith (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | EMEC | Offshore | Offshore | Scotland |  | 314195 | 1009356 | Scottish Government (S36) | [6 empty] | 2010-07-01 | [6 empty] | 2012-07-01 |  |  |  |  | 2013-05-15 | 2013-07-15
B0410 | 2401 | 2018-04-24 | Kawasaki | Kawasaki (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | EMEC | Offshore | Offshore | Scotland |  | 314195 | 1009356 | Scottish Government (S36) | [6 empty] | 2010-01-01 | [6 empty] | 2010-07-01 |  |  |  |  | 2011-06-15 | 2013-07-15
B0677 | 2402 | 2018-11-08 | Scotrenewables | SR-2000 (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fall of Warness, Eday, Orkney | Orkney Islands | Offshore | Scotland |  | 354000 | 1028400 | Scottish Government (S36) | 15/031/S36CON | [15 empty] | 2015-03-09 |  | 2016-10-07 | 2017-04-14
EN00524 | 2403 | 2019-10-01 | Marine Current Turbines (MCT) | SeaGen Tidal Farm | Tidal Barrage and Tidal Stream |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Strangford Narrows, Northern Ireland | Offshore | Offshore | Northern Ireland |  | 170120 | 500920 | Northern Ireland Planning Service | [6 empty] | 2003-11-01 | [6 empty] | 2005-12-21 |  |  |  |  | 2008-03-01 | 2009-07-08
A0182 | 2405 | 2013-11-27 | Pulse Tidal | Kylerhea | Tidal Barrage and Tidal Stream |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Isle of Skye, | Offshore | Offshore | Scotland |  | 179386 | 820428 | Marine Scotland | [7 empty] | 2013-11-27
B0389 | 2407 | 2020-01-29 | Pulse Tidal | Lynmouth Tidal Demo | Tidal Barrage and Tidal Stream |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Lynmouth, Devon | Offshore | Offshore | England |  | 271966 | 150179 | Crown Estate | [6 empty] | 2011-10-01 | [6 empty] | 2012-04-27
EN00450 | 2411 | 2019-11-20 | Tocardo (EMEC) | The Fall of Warness Tidal Scheme, (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Fall of Warness, Eday, Orkney | Orkney Islands | Offshore | Scotland |  | 354000 | 1028400 | Scottish Government (S36) | [6 empty] | 2016-06-01 | [6 empty] | 2016-08-15
A0041 | 2414 | 2019-11-19 | Godshill Park Developments | Wootton Bridge | Tidal Barrage and Tidal Stream |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | High Street, Wotton Bridge, Ryde, Isle of Wight. PO33 4LJ | Offshore | Offshore | England |  | 454641 | 92078 | DECC (S36) | TCP/29446 | [5 empty] | 2009-01-19 | [6 empty] | 2009-05-08
A0192 | 2415 | 2020-04-30 | The Islay Energy Trust/ Atlantis | Sound of Islay | Tidal Barrage and Tidal Stream |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Islay, Western Isles | Offshore | Offshore | Scotland |  | 143843 | 667672 | Scottish Government (S36) | [6 empty] | 2010-07-25 | [6 empty] | 2011-03-17
A0294 | 2416 | 2018-11-08 | DCNS OpenHydro/SSE Renewables | Brims Tidal Array (Cantick Head) | Tidal Barrage and Tidal Stream |  |  | 200 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Pentland Firth, Off South Walls, Hoy, Orkney Islands | Orkney Islands | Offshore | Scotland | KW17 | 328689 | 986676 | Marine Scotland | [6 empty] | 2016-05-20
AA967 | 2419 | 2017-03-02 | DP Marine Energy (DP Marine Energy & DEME Blue Energy) | Fair Head | Tidal Barrage and Tidal Stream |  |  | 100 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | off of Fair Head, Northern Ireland | Offshore | Offshore | Northern Ireland |  | 139527 | 600089 | Northern Ireland Planning Service | [6 empty] | 2017-02-07
B0404 | 2420 | 2018-04-24 | Hamerfest Strom/SPR | Hammerfest (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | EMEC | Offshore | Offshore | Scotland |  | 314195 | 1009356 | Scottish Government (S36) | [19 empty] | 2012-02-01
B0594 | 2421 | 2020-06-15 | Solent Ocean Energy Centre/Isle of Wight Council/ Perpetuus Tidal Energy Centre | St. Catherine's Race | Tidal Barrage and Tidal Stream |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | n/a | Secretary of State - Granted | Awaiting Construction | St Catherine's Point, Isle of Wight | Isle of Wight | Offshore | England | PO38 1UF | 449740 | 72980 | Crown Estate | P/01485/14 | [5 empty] | 2014-12-12 | [6 empty] | 2016-04-20 |  |  | 2016-04-20 | 2021-04-20
A0284 | 2422 | 2019-12-06 | Tidal Lagoon Power | Swansea Bay Tidal Lagoon | Tidal Barrage and Tidal Stream |  |  | 320 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Swansea, Wales | Offshore | Offshore | Wales |  | 265285 | 191774 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2014-03-06 | [6 empty] | 2015-06-09 |  |  |  | 2020-06-09
AA507 | 2423 | 2020-06-05 | Nautricity | Mull of Kintyre | Tidal Barrage and Tidal Stream |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | waters off the Mull of Kintyre | Offshore | Offshore | Scotland |  | 157228 | 603340 | Scottish Government (S36) | [13 empty] | 2014-07-23
B0499 | 2429 | 2019-03-22 | DP Marine Energy | West Islay Tidal Array | Tidal Barrage and Tidal Stream |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Islay | Offshore | Offshore | Scotland |  | 116500 | 652500 | Marine Scotland | [6 empty] | 2013-10-10 | [6 empty] | 2017-06-21
IF1445 | 2435 | 2015-08-11 | Sea Generation (Kyle Rhea) Ltd | Kyle Rhea Tidal Stream Array | Tidal Barrage and Tidal Stream |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Kylerhea Breakish | Offshore | Offshore | Scotland |  | 179183 | 821973 | Marine Scotland | [6 empty] | 2013-02-11 | 2015-07-01
B0899 | 2436 | 2018-11-06 | Atlantis Resources | Inner Sound Phase 1A (MeyGen) | Tidal Barrage and Tidal Stream |  |  | 6 | n/a |  |  |  | n/a | n/a |  | n/a | Operational | Operational | Pentland Firth and Orkney waters strategic area, between Caithness on the Scottish mainland and the island of Stroma | Orkney Islands | Offshore | Scotland |  | 335503 | 984335 | Scottish Government (S36) | [6 empty] | 2012-07-19 | [6 empty] | 2013-09-16 |  |  |  |  | 2015-01-21 | 2017-02-20
EN00526 | 2437 | 2014-09-19 | Marine Current Turbines (MCT) / NPower | SeaGen Wales Tidal Farm | Tidal Barrage and Tidal Stream |  |  | 10 | n/a |  |  |  | n/a | n/a |  | n/a | Abandoned | Abandoned | Project be sited in an area of 25 metre deep open sea known as the Skerries, off the north-west coast of Anglesey | Offshore | Offshore | Wales |  | 226550 | 395030 | DECC (S36) | 18C201 | [5 empty] | 2011-03-24 | [6 empty] | 2013-02-27
A0089 | 2438 | 2010-06-18 |  | WestWave | Shoreline Wave |  |  | 3 | n/a |  |  |  | n/a | n/a |  | n/a | Planning Application Withdrawn | Application Withdrawn | 10 nautical miles off St. Ives on the north Cornwall coast. | Offshore | Offshore | England |  | 151558 | 43565 | DECC (S36) | [7 empty] | 2009-04-29
B0116 | 2445 | 2018-04-25 | Seatricity | Seatricity Turbine (Billia Croo - EMEC) | Shoreline Wave |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Billia Croo Test site, Orkney | Orkney Islands | Offshore | Scotland |  |  |  | Scottish Government (S36) | [19 empty] | 2011-01-01
EN00338 | 2452 | 2018-09-04 | Wello | Wello Penguin Device (Billia Croo - EMEC) | Shoreline Wave |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fall of Warness, Off Eday, Orkney Islands | Orkney Islands | Offshore | Scotland |  | 323401 | 983560 | Scottish Government (S36) | [6 empty] | 2007-06-29 | [6 empty] | 2007-09-28 | [5 empty] | 2008-05-27
EN00538 | 2456 | 2013-02-27 | Voith Hydro Ocean Current Technologies | Siadar Wave Energy Generating Scheme | Shoreline Wave |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Siadar, Isle of Lewis, Western Isles | Offshore | Offshore | Scotland |  | 137340 | 954775 | Scottish Government (S36) | [6 empty] | 2008-04-21 | [6 empty] | 2009-01-22
A0184 | 2457 | 2018-07-04 | Wave Hub | Hayle Wave Hub (Test Site) | Shoreline Wave |  |  | 23 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 10 miles off shore Hayle, Cornwall coast | Offshore | Offshore | England |  | 154466 | 39557 | DECC (S36) | S36 | [5 empty] | 2005-02-17 | [6 empty] | 2009-07-15 |  |  |  |  | 2010-06-01 | 2010-09-01
EN00543 | 2461 | 2016-08-25 |  | Milford Haven Wave Dragon Pre-Commercial Demonstrator | Shoreline Wave |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Approximately 2 km west from St Ann's Head at Long Point, Pembrokeshire | Offshore | Offshore | Wales |  | 177960 | 203160 | DECC (S36) | [6 empty] | 2007-02-16
AA797 | 2462 | 2019-10-17 | Lewis Wave Power Limited | Lewis Oyster Wave Array | Shoreline Wave |  |  | 50 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | North West Coast, Isle of Lewis | Comhairle nan Eilean Siar | Offshore | Scotland |  | 140262 | 958398 | Marine Scotland | [6 empty] | 2012-03-22 | [6 empty] | 2013-05-22 |  |  |  | 2017-06-27
B0585 | 2470 | 2020-06-25 | Scottish Power Renewables/Vattenfall/OPR | East Anglia 3 | Wind Offshore |  |  | 1400 | n/a |  |  |  | 7 | 172 | 247 | n/a | Planning Permission Granted | Awaiting Construction | East Anglia Offshore Wind Three, Underground Cabling Between Bramford And Bawdsey, Lowestoft | Offshore | Offshore | England |  | 685500 | 257000 | DECC (S36) | EN010056 |  |  |  |  | 3 | 2015-11-18 | [6 empty] | 2017-08-07
B0850 | 2472 | 2020-06-04 | Orsted (formerly Dong Energy) | Hornsea 3 | Wind Offshore |  |  | 2400 | n/a |  |  |  | 8 | 300 |  | n/a | Planning Application Submitted | Application Submitted |  | Offshore | Offshore | England |  | 626000 | 426000 | DECC (S36) | [5 empty] | 3 | 2018-05-16
N00440W | 2475 | 2008-12-05 | Celtpower | Cirrus Shell Flat Array | Wind Offshore |  |  | 284 | n/a |  |  |  | 3.15 | 90 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 7km Cleveleys | Offshore | Offshore | England |  | 323355 | 443490 | DECC (S36) | [5 empty] | 1 |  | 2008-12-05
N00544W | 2476 | 2010-03-24 | EDF | Cromer | Wind Offshore |  |  | 108 | n/a |  |  |  | 4 | 30 |  | n/a | Abandoned | Abandoned | 7km Cromer | Offshore | Offshore | England |  | 630840 | 351080 | DECC (S36) | [5 empty] | 1
N00554W | 2477 | 2010-01-27 | E.On / Energie 2 | Scarweather Sands | Wind Offshore |  |  | 108 | n/a |  |  |  | 3 | 30 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 5.5km Sker Point (nr Porthcawl) | Offshore | Offshore | Wales |  | 272400 | 171520 | DECC (S36) | [5 empty] | 1 |  | 2010-01-27
B0997 | 2479 | 2018-07-04 | Statoil | Hywind Scotland Pilot Park (Hywind 2) Demonstrator | Wind Offshore |  |  | 30 | n/a |  |  |  | 6 | 5 |  | n/a | Operational | Operational | Buchan Deeps, 20km off Peterhead | Offshore | Offshore | Scotland |  | 433500 | 846500 | Marine Scotland | [5 empty] | Demo | 2015-03-27 | [6 empty] | 2015-10-30 |  |  |  |  | 2017-04-27 | 2017-10-27
A0250 | 2484 | 2020-06-04 | Vattenfall/Scottish Power Renewables | The East Anglia Array - Norfolk Vanguard | Wind Offshore |  |  | 1800 | n/a |  |  |  | 5 | 360 | 145 | n/a | Planning Application Submitted | Application Submitted | North Sea, off the East Anglia coast | Offshore | Offshore | England |  | 708047 | 312194 | DECC (S36) | [5 empty] | 3 | 2018-07-11
EN00028 | 2485 | 2017-05-31 | Talisman Energy | Beatrice Demonstrator | Wind Offshore |  |  | 10 | n/a |  |  |  | 5 | 2 |  | n/a | Operational | Operational | Beatrice Offshore Platform | Offshore | Offshore | Scotland |  | 347955 | 929690 | Scottish Government (S36) | [6 empty] | 2006-01-23 | [6 empty] | 2006-06-15 |  |  |  |  | 2006-09-01 | 2007-07-17
N00546W | 2486 | 2019-06-04 | Blyth Harbor Wind Ltd | Blyth Offshore | Wind Offshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Decommissioned | Decommissioned | 1km off Blyth Harbour | Offshore | Offshore | England |  | 432608 | 582536 | DECC (S36) | [13 empty] | 1998-09-22 |  |  |  |  | 2000-08-01 | 2000-12-01
N00445W | 2487 | 2018-02-27 | Orsted (formerly Dong Energy) | Burbo Bank | Wind Offshore |  |  | 90 | n/a |  |  |  | 3.6 | 25 |  | n/a | Operational | Operational | Burbo Flats, Liverpool Bay, approximately 6.4km (4.0 miles) from the Sefton coastline and 7.2km (4.5 miles) from North Wirral. | Offshore | Offshore | England |  | 321476 | 399706 | DECC (S36) | [5 empty] | 1 | 2002-04-12 | [6 empty] | 2006-07-14 |  |  |  |  | 2006-08-01 | 2007-10-18
A0438 | 2488 | 2017-11-20 | Orsted (formerly Dong Energy) | Gunfleet Sands - (Demo) Extension | Wind Offshore |  |  | 12 | n/a |  |  |  | 6 | 2 |  | n/a | Operational | Operational | off the Essex coast | Offshore | Offshore | England |  | 620650 | 205297 | DECC (S36) | [5 empty] | Demo | [7 empty] | 2012-04-17 |  |  |  |  | 2012-05-15 | 2013-04-19
N00457W | 2489 | 2017-11-20 | Orsted (formerly Dong Energy) | Gunfleet Sands II | Wind Offshore |  |  | 64.8 | n/a |  |  |  | 3.6 | 18 |  | n/a | Operational | Operational | 5 Miles from the Essex coast at Frinton-on-Sea | Offshore | Offshore | England |  | 624262 | 208150 | DECC (S36) | [5 empty] | 2 | 2007-06-18 | [6 empty] | 2008-02-28 |  |  |  |  | 2009-04-01 | 2009-07-24
01041W4 | 2490 | 2018-05-01 | Orsted (formerly Dong Energy) | Gunfleet Sands Offshore Wind Scheme | Wind Offshore |  |  | 108 | n/a |  |  |  | 3.6 | 30 |  | n/a | Operational | Operational | Gunfleet Sands 4 miles offshore from Holland-on-Sea Nr Clacton-on-Sea Essex | Offshore | Offshore | England |  | 622317 | 208468 | DECC (S36) | [5 empty] | 1 | 2002-03-01 | [6 empty] | 2004-03-01 |  |  |  |  | 2009-04-01 | 2009-07-24
N00562W | 2491 | 2017-08-24 | Green Investment Bank | Inner Dowsing | Wind Offshore |  |  | 97.2 | n/a |  |  |  | 3.6 | 27 |  | n/a | Operational | Operational | 5.2km Ingoldmells | Offshore | Offshore | England |  | 563561 | 368447 | DECC (S36) | [5 empty] | 1 | 2002-09-11 | [6 empty] | 2003-09-23 |  |  |  |  | 2008-03-01 | 2008-04-20
N00439W | 2492 | 2017-10-27 | Vattenfall | Kentish Flats | Wind Offshore |  |  | 90 | n/a |  |  |  | 3 | 30 |  | n/a | Operational | Operational | Saltend, Thames Estuary, North Sea | Offshore | Offshore | England |  | 615015 | 178055 | DECC (S36) | [5 empty] | 1 | 2002-08-15 | [6 empty] | 2003-03-01 |  |  |  |  | 2004-06-01 | 2005-09-10
N00437W | 2493 | 2017-08-24 | Green Investment Bank | Lynn | Wind Offshore |  |  | 97.2 | n/a |  |  |  | 3.6 | 27 |  | n/a | Operational | Operational | 5.2km Skegness | Offshore | Offshore | England |  | 564095 | 362638 | DECC (S36) | [5 empty] | 1 | 2003-10-29 | [6 empty] | 2004-08-14 |  |  |  |  | 2008-03-01 | 2008-03-15
N00436W | 2494 | 2017-08-23 | Greencoat (formerly Npower Renewables) | North Hoyle | Wind Offshore |  |  | 60 | n/a |  |  |  | 2 | 30 |  | n/a | Operational | Operational | 7.5km Prestatyn & Rhyl | Offshore | Offshore | Wales |  | 303823 | 392138 | DECC (S36) | [5 empty] | 1 | 2001-04-05 | [6 empty] | 2002-07-31 |  |  |  |  | 2003-04-03 | 2003-12-01
N00434W | 2495 | 2017-08-23 | RWE Npower | Rhyl Flats | Wind Offshore |  |  | 90 | n/a |  |  |  | 3.6 | 25 |  | n/a | Operational | Operational | 8km Abergele, five miles off the North Wales coast in Liverpool Bay | Offshore | Offshore | Wales |  | 290990 | 388002 | DECC (S36) | [5 empty] | 1 | 2002-03-25 | [6 empty] | 2003-01-01 |  |  |  |  | 2007-09-01 | 2009-12-28
N00561W | 2496 | 2017-08-18 | E.ON UK | Robin Rigg East | Wind Offshore |  |  | 90 | n/a |  |  |  | 3 | 30 |  | n/a | Operational | Operational | 9.5km Maryport/8.5km off Rock Cliffe | Offshore | Offshore | Scotland |  | 291005 | 542348 | Scottish Government (S36) | [5 empty] | 1 | 2002-06-14 | [6 empty] | 2003-06-16 |  |  |  |  | 2006-12-01 | 2010-04-28
N00462W | 2497 | 2017-08-18 | E.ON UK | Robin Rigg West | Wind Offshore |  |  | 84 | n/a |  |  |  | 3 | 28 |  | n/a | Operational | Operational | 9.5km Maryport/8.5km off Rock Cliffe | Offshore | Offshore | Scotland |  | 288785 | 540522 | Scottish Government (S36) | [5 empty] | 1 | 2002-06-14 | [6 empty] | 2003-06-16 |  |  |  |  | 2006-12-01 | 2009-07-18
N00438W | 2498 | 2016-02-29 | E.ON UK | Scroby Sands | Wind Offshore |  |  | 60 | n/a |  |  |  | 2 | 30 |  | n/a | Operational | Operational | 3km NE Great Yarmouth, Norfolk | Offshore | Offshore | England |  | 656417 | 311874 | DECC (S36) | [5 empty] | 1 | 2001-03-05 | [6 empty] | 2002-12-01 |  |  |  |  | 2003-10-01 | 2004-03-01
N00452W | 2499 | 2018-05-01 | Vattenfall | Thanet | Wind Offshore |  |  | 300 | n/a |  |  |  | 3 | 100 |  | n/a | Operational | Operational | 11km off North Foreland Kent | Offshore | Offshore | England |  | 652658 | 176367 | DECC (S36) | [5 empty] | 2 | 2005-11-08 | [6 empty] | 2006-12-18 |  |  |  |  | 2009-11-01 | 2010-09-16
N00550W | 2500 | 2020-06-18 | Orsted (formerly Dong Energy) | Walney 1 | Wind Offshore |  |  | 183.6 | n/a |  |  |  | 3.6 | 51 |  | n/a | Operational | Operational | 14km off Walney Island, Irish Sea | Offshore | Offshore | England |  | 300833 | 461449 | DECC (S36) | [5 empty] | 2 | 2006-03-31 | [6 empty] | 2007-11-07 |  |  |  |  | 2010-03-10 | 2011-05-30
A0249 | 2502 | 2020-06-18 | Orsted (formerly Dong Energy) | Hornsea 2 - Optimus and Breesea | Wind Offshore |  |  | 1400 | n/a |  |  |  | 8.48 | 165 |  | n/a | Under Construction | Under Construction |  | Offshore | Offshore | England |  | 632326 | 457349 | The Planning Inspectorate - National Infrastructure | [5 empty] | 3 | 2015-01-30 | [6 empty] | 2016-08-16 |  |  |  |  | 2019-09-01
A0371 | 2504 | 2016-06-28 | Vattenfall | Kentish Flats 2 | Wind Offshore |  |  | 49.5 | n/a |  |  |  | 3.3 | 15 |  | n/a | Operational | Operational | Kentish Flats Offshore extension | Offshore | Offshore | England |  | 614105 | 176834 | DECC (S36) | S36 |  |  |  |  | 2.5 | 2012-06-01 | [6 empty] | 2013-02-19 |  |  |  |  | 2014-11-26 | 2015-09-14
A0440 | 2505 | 2019-04-30 | Vattenfall | European Offshore Wind Deployment Centre (EOWDC) (Aberdeen Bay - Demonstration site) | Wind Offshore |  |  | 93.2 | n/a |  |  |  | 8.4 | 11 |  | n/a | Operational | Operational |  | Offshore | Offshore | Scotland |  | 395693 | 806148 | Scottish Government (S36) | [5 empty] | Demo | 2011-08-31 | [6 empty] | 2013-03-26 |  |  |  |  | 2018-04-07 | 2018-09-07
AA183 | 2506 | 2020-06-18 | Orsted (formerly Dong Energy) | Walney 2 | Wind Offshore |  |  | 183.6 | n/a |  |  |  | 3.6 | 51 |  | n/a | Operational | Operational | 14km off Walney Island, Irish Sea | Offshore | Offshore | England |  | 294836 | 466177 | DECC (S36) | [5 empty] | 2 | 2006-03-31 | [6 empty] | 2007-11-07 |  |  |  |  | 2011-04-09 | 2012-04-06
B0551 | 2507 | 2015-01-09 | London Array Ltd | London Array Phase 2 | Wind Offshore |  |  | 240 | n/a |  |  |  | 2.93 | 341 |  | n/a | Abandoned | Abandoned | 12 miles (20km) off the Kent and Essex coasts | Offshore | Offshore | England |  | 611280 | 179120 | DECC (S36)/Marine Management Organisation | [5 empty] | 2 | 2011-10-25
EN00407 | 2508 | 2013-11-26 | Npower | Atlantic Array One - Bristol Channel Zone | Wind Offshore |  |  | 1200 | n/a |  |  |  | 5 | 240 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Between Ilfracombe in North Devon and Swansea, The nearest turbine to land would be 13 miles off shore. | Offshore | Offshore | England |  | 221400 | 166500 | DECC (S36) | [5 empty] | 3 | 2013-07-12 | 2013-11-25
N00435W | 2509 | 2017-08-23 | Vattenfall | Ormonde Offshore | Wind Offshore |  |  | 150 | n/a |  |  |  | 5 | 30 |  | n/a | Operational | Operational | 10km off Barrow on Furness, Heysham | Offshore | Offshore | England |  | 306000 | 466842 | DECC (S36) | [5 empty] | 1 | 2005-07-12 | [6 empty] | 2008-09-04 |  |  |  |  | 2010-06-01 | 2012-02-22
N00443W | 2510 | 2019-10-02 | Airtricity / Fluor Ltd | Greater Gabbard Wind Farm | Wind Offshore |  |  | 504 | n/a |  |  |  | 3.6 | 140 |  | n/a | Operational | Operational | Near the Suffolk Coast (26km out to sea) | Offshore | Offshore | England |  | 670237 | 231640 | DECC (S36) | [5 empty] | 2 | 2005-10-17 | [6 empty] | 2007-02-20 |  |  |  |  | 2009-07-01 | 2012-09-07
N00447W | 2511 | 2018-11-06 | Siemens Gamesa Renewable Energy | London Array Phase 1 | Wind Offshore |  |  | 630 | n/a |  |  |  | 3.6 | 175 |  | n/a | Operational | Operational | 12 miles (20km) off the Kent and Essex coasts | Offshore | Offshore | England |  | 642078 | 197218 | DECC (S36) | [5 empty] | 2 | 2005-06-01 |  | 2006-12-15 |  |  |  | 2007-09-05 | 2007-09-05 |  |  |  |  | 2011-03-01 | 2013-04-06
N00453W | 2512 | 2019-11-05 | Vattenfall | Sheringham Shoal | Wind Offshore |  |  | 317 | n/a |  |  |  | 3.6 | 88 |  | n/a | Operational | Operational | between 17 and 22 kilometres off the Norfolk coast, north of the seaside town of Sheringham. | Offshore | Offshore | England |  | 610671 | 364425 | DECC (S36) | [5 empty] | 2 | 2006-05-30 | [6 empty] | 2008-08-07 |  |  |  |  | 2009-06-30 | 2012-10-29
N00455W | 2513 | 2018-05-01 | GIB | Centrica (Lincs) | Wind Offshore |  |  | 270 | n/a |  |  |  | 3.6 | 75 |  | n/a | Operational | Operational | 8 Km of Skegness | Offshore | Offshore | England |  | 567020 | 368144 | DECC (S36) | [5 empty] | 2 | 2007-01-24 | [6 empty] | 2008-10-21 |  |  |  |  | 2010-03-01 | 2013-07-24
N00460W | 2514 | 2015-05-18 | EDF Energy - Northern Offshore Windfarm Ltd | Teeside Offshore Wind Farm | Wind Offshore |  |  | 62.1 | n/a |  |  |  | 2.3 | 27 |  | n/a | Operational | Operational | Coast of Coatham Sands at Redcar, the nearest within a mile of the beach | Offshore | Offshore | England |  | 458470 | 528174 | DECC (S36) | R/2004/0305/FF |  |  |  |  | 1 | 2005-03-22 | [6 empty] | 2007-09-17 |  |  |  |  | 2012-02-01 | 2013-08-31
N00463W | 2515 | 2019-10-02 | Orsted (formerly Dong Energy)/ Macquarie Group | Race Bank (Phase 1) | Wind Offshore |  |  | 286.5 | n/a |  |  |  | 6 | 46 | 154 | n/a | Operational | Operational | Race Bank Greater Wash | Offshore | Offshore | England |  | 573300 | 363000 | DECC (S36) | [5 empty] | 2 | 2009-01-23 | [6 empty] | 2012-07-06 |  |  |  |  | 2016-07-07 | 2017-06-08
N00559W | 2516 | 2012-07-06 | Centrica | Docking Shoal A | Wind Offshore |  |  | 540 | n/a |  |  |  | 5 | 108 |  | n/a | Planning Permission Refused | Application Refused | 17km off the North Norfolk Coast | Offshore | Offshore | England |  | 588560 | 366879 | DECC (S36) | [5 empty] | 2 | 2008-12-09 |  | 2012-07-06
A0476 | 2517 | 2020-06-18 | SSE/Equinor (formerly Statoil, formerly Forewind) | Dogger Bank C (was Teesside A) | Wind Offshore |  |  | 1200 | n/a |  |  | 1200 | 12 | 100 | 260 | n/a | Planning Permission Granted | Awaiting Construction | 125km off coast of Yorkshire | Offshore | Offshore | England |  | 675550 | 599192 | The Planning Inspectorate - National Infrastructure | [5 empty] | 3 | 2014-03-28 | [6 empty] | 2015-08-05
N00449W | 2519 | 2018-04-03 | Scottish Power Renewables & Orsted (formerly Dong Energy) | West of Duddon Sands | Wind Offshore |  |  | 389 | n/a |  |  |  | 3.6 | 108 |  | n/a | Operational | Operational | Off Duddon Sands, Cumbria. East Irish Sea | Offshore | Offshore | England |  | 304230 | 455334 | DECC (S36) | [5 empty] | 2 | 2006-04-01 | [6 empty] | 2008-09-04 |  |  |  |  | 2013-05-21 | 2014-10-30
A0251 | 2520 | 2019-12-06 | E.ON UK | Rampion Offshore Wind Farm (Hastings Zone) | Wind Offshore |  |  | 400 | n/a |  |  |  | 5 | 116 | 140 | n/a | Operational | Operational | off the Sussex coastline | Offshore | Offshore | England |  | 528790 | 83836 | DECC (S36) | [5 empty] | 3 | 2013-03-25 | [6 empty] | 2014-07-16 |  |  |  |  | 2016-01-25 | 2017-11-26
A0275 | 2521 | 2019-05-31 | Scottish & Southern Energy (SSE) / Repsol / CIP | Beatrice | Wind Offshore |  |  | 588 | n/a |  |  | 664 | 7 | 84 |  | n/a | Operational | Operational | Offshore Scottish borders | Offshore | Offshore | Scotland |  | 344074 | 911416 | Scottish Government (S36) | [5 empty] | STW | 2012-04-25 | [6 empty] | 2014-03-19 |  |  |  |  | 2017-04-02 | 2019-08-05
A0277 | 2522 | 2019-06-25 | EDF Renewables Power | Neart na Gaoithe | Wind Offshore |  |  | 450 | n/a |  |  | 448 | 7 | 54 |  | n/a | Abandoned | Abandoned | Offshore Scottish borders (15KM off Forth Estuary, Kirkcaldy, Fife, KY1) | Offshore | Offshore | Scotland |  | 384615 | 708641 | Marine Scotland |  |  |  |  | 42570 | STW | 2012-07-30 | [6 empty] | 2017-05-16
A0439 | 2523 | 2018-07-04 | EDF Energy Renewables | Blyth Offshore Wind Test Site | Wind Offshore |  |  | 41.5 | n/a |  |  |  | 8.3 | 5 |  | n/a | Operational | Operational | between 1.8km and 13.8km off the east coast of Blyth in Northumberland | Offshore | Offshore | England |  | 440591 | 586033 | DECC (S36)/Marine Management Organisation | [5 empty] | Demo | 2012-03-01 | [6 empty] | 2013-11-08 |  |  |  |  | 2016-10-22 | 2017-10-22
B0262 | 2524 | 2020-06-25 | Scottish Power Renewables | East Anglia 1 (EA 1) | Wind Offshore |  |  | 714 | n/a |  |  | 714 | 5 | 102 |  | n/a | Under Construction | Under Construction | Offshore, East of England | Offshore | Offshore | England |  | 685500 | 257000 | DECC (S36) | [5 empty] | 3 | 2012-11-21 | [6 empty] | 2014-06-17 |  |  |  |  | 2018-05-24
B0263 | 2525 | 2020-06-18 | Orsted (formerly Dong Energy) | Hornsea 1 - Heron & Njord | Wind Offshore |  |  | 1200 | n/a |  |  | 1200 | 7 | 174 |  | n/a | Operational | Operational |  | Offshore | Offshore | England |  | 626000 | 426000 | DECC (S36) | [5 empty] | 3 | 2013-08-23 | [6 empty] | 2014-12-10 |  |  |  |  | 2018-01-26 | 2020-06-02
A0370 | 2526 | 2019-10-02 | RWE Npower Renewables | Galloper Wind Farm | Wind Offshore |  |  | 353 | n/a |  |  |  | 6.3 | 56 |  | n/a | Operational | Operational | Greater Gabbard extension | Offshore | Offshore | England |  | 678139 | 227875 | The Planning Inspectorate - National Infrastructure | s36 |  |  |  |  | 2.5 | 2011-11-21 | [6 empty] | 2013-05-24 |  |  |  |  | 2016-07-29 | 2018-03-30
A0017 | 2527 | 2020-07-02 | Red Rock Power (ICOL) | Inch Cape | Wind Offshore |  |  | 784 | n/a |  |  |  | 7.12 | 72 | 250 | n/a | Planning Permission Granted | Awaiting Construction | Offshore - Scottish Borders (15-22 KM off the east Angus coastline) | Offshore | Offshore | Scotland |  | 387786 | 734231 | Marine Scotland | [5 empty] | STW | 2013-07-04 | [6 empty] | 2017-05-16
B0258 | 2528 | 2018-11-08 | Catapult | Levenmouth demonstration turbine (Fife Energy Park) | Wind Offshore |  |  | 7 | n/a |  |  |  | 6 | 1 |  | n/a | Operational | Operational | Fife Energy Park (Test Site) off the coast of Methil in Fife | Offshore | Offshore | Scotland |  | 340600 | 696860 | Scottish Government (S36) | [5 empty] | 3 | 2009-12-02 | [6 empty] | 2011-11-18 |  |  |  |  | 2013-10-08 | 2014-03-31
B0267 | 2530 | 2020-07-02 | SSE / Seagreen Wind Energy Ltd | Seagreen Alpha | Wind Offshore |  |  | 525 | n/a |  |  | 227 | 9.2 | 57 |  | n/a | Planning Permission Granted | Awaiting Construction | Firth of Forth Wind Zone 2, Dundee, Tayside | Offshore | Offshore | Scotland | DD4 0AD | 404600 | 749300 | Marine Scotland |  |  |  |  | 42570 | 3 | 2012-10-23 | [6 empty] | 2017-05-16
N00551W | 2532 | 2020-07-02 | Innogy | Triton Knoll | Wind Offshore |  |  | 860 | n/a |  |  |  | 9.5 | 90 |  | n/a | Under Construction | Under Construction | Greater Wash region, approximately 33km off the Lincolnshire coast | Offshore | Offshore | England |  | 591183 | 372179 | The Planning Inspectorate - National Infrastructure | [5 empty] | 2 | 2012-02-24 | [6 empty] | 2013-07-11 |  |  |  |  | 2018-09-10
A0374 | 2533 | 2020-06-04 | Orsted (formerly Dong Energy) | Walney 3 | Wind Offshore |  |  | 660 | n/a |  |  | 660 | 6 | 110 | 222 | n/a | Operational | Operational | 14km off Walney Island, Irish Sea | Offshore | Offshore | England |  | 286289 | 467410 | DECC (S36) | [5 empty] | 2.5 | 2013-07-30 | [6 empty] | 2014-11-07 |  |  |  | 2019-11-07 | 2017-04-01 | 2018-09-13
A0246 | 2534 | 2020-07-02 | Moray East (formerly MORL)/ EDPR | MacColl Offshore Windfarm (Moray East) | Wind Offshore |  |  | 313.5 | n/a |  |  |  | 9.5 | 33 |  | n/a | Under Construction | Under Construction | Smith Bank, Moray Firth - 13miles off Lybster | Offshore | Offshore | Scotland |  | 353328 | 897834 | Scottish Government (S36) | [5 empty] | 3 | 2012-08-28 | [6 empty] | 2014-03-19 |  |  |  |  | 2019-06-06
B0265 | 2535 | 2015-11-03 | Eneco & EDF | Navitus Bay | Wind Offshore |  |  | 970 | n/a |  |  |  | 5 | 121 |  | n/a | Planning Permission Refused | Application Refused | off the Dorset and Hampshire coasts, to the west of the Isle of Wight. | Offshore | Offshore | England |  | 411540 | 54803 | The Planning Inspectorate - National Infrastructure | [5 empty] | 3 | 2014-05-08 |  | 2015-09-11
C0475 | 2536 | 2020-07-02 | Moray East (formerly MORL)/ EDPR | Telford Offshore Windfarm (Moray East) | Wind Offshore |  |  | 313.5 | n/a |  |  |  | 9.5 | 33 |  | n/a | Under Construction | Under Construction | Smith Bank, Moray Firth - 13miles off Lybster | Offshore | Offshore | Scotland |  | 353646 | 924989 | Scottish Government (S36) | [5 empty] | 3 | 2012-08-28 | [6 empty] | 2014-03-19 |  |  |  |  | 2019-06-06
C0476 | 2537 | 2020-07-02 | Moray East (formerly MORL)/ EDPR | Stevenson Offshore Windfarm (Moray East) | Wind Offshore |  |  | 323 | n/a |  |  |  | 9.5 | 34 |  | n/a | Under Construction | Under Construction | Smith Bank, Moray Firth - 13miles off Lybster | Offshore | Offshore | Scotland |  | 331721 | 907867 | Scottish Government (S36) | [5 empty] | 3 | 2012-08-28 | [6 empty] | 2014-03-19 |  |  |  |  | 2019-06-06
N00558W | 2538 | 2020-01-02 | Statoil / Statkraft | Dudgeon East | Wind Offshore |  |  | 402 | n/a |  |  | 402 | 6 | 67 |  | n/a | Operational | Operational | Greater wash | Offshore | Offshore | England |  | 575000 | 361000 | DECC (S36) | [5 empty] | 2 | 2009-06-12 | [6 empty] | 2012-07-06 |  |  |  |  | 2016-03-17 | 2017-10-15
AA066 | 2539 | 2018-05-02 | Orsted (formerly Dong Energy) | Burbo Bank Extension (Burbo Bank 2) | Wind Offshore |  |  | 258 | n/a |  |  | 258 | 8 | 32 |  | n/a | Operational | Operational | Burbo Flats, Liverpool Bay, approximately 6.4km (4.0 miles) from the Sefton coastline and 7.2km (4.5 miles) from North Wirral. | Offshore | Offshore | England |  | 315815 | 398892 | DECC (S36) | [5 empty] | 2.5 | 2013-04-19 | [6 empty] | 2014-09-26 |  |  |  |  | 2016-06-10 | 2017-04-27
IF1002 | 2540 | 2020-07-02 | SSE / Seagreen Wind Energy Ltd | Seagreen Bravo | Wind Offshore |  |  | 525 | n/a |  |  | 227 | 9.2 | 57 |  | n/a | Planning Permission Granted | Awaiting Construction | Firth of Forth Wind Zone 2, Dundee, Tayside | Offshore | Offshore | Scotland | DD4 0AD | 511436 | 746346 | Marine Scotland |  |  |  |  | 42570 | 3 | 2012-10-23 | [6 empty] | 2017-05-16
A0248 | 2541 | 2020-06-18 | SSE/Equinor (formerly Statoil, formerly Forewind) | Dogger Bank A & B (was Creyke Beck A & B) | Wind Offshore |  |  | 2400 | n/a |  |  | 2400 | 12 | 200 | 260 | n/a | Under Construction | Under Construction | 125km off coast of Yorkshire | Offshore | Offshore | England |  | 629000 | 681000 | The Planning Inspectorate - National Infrastructure | [5 empty] | 3 | 2013-08-29 | [6 empty] | 2015-02-17 |  |  |  | 2020-03-11 | 2020-01-13
N00441W | 2543 | 2019-10-02 | RWE | Gwynt y Mor | Wind Offshore |  |  | 576 | n/a |  |  |  | 3.6 | 160 |  | n/a | Operational | Operational | Liverpool Bay (13-15km offshore) | Offshore | Offshore | Wales |  | 292082 | 396482 | DECC (S36) | [5 empty] | 2 | 2005-11-01 | [6 empty] | 2008-12-03 |  |  |  |  | 2012-03-01 | 2015-06-18
N00448W | 2544 | 2016-10-03 | E.ON Humber Wind Ltd/ Balfour Beatty Investments and Equitix. | Humber Gateway A | Wind Offshore |  |  | 219 | n/a |  |  |  | 3 | 73 |  | n/a | Operational | Operational | 8km from Yorkshire Coast | Offshore | Offshore | England |  | 566400 | 390760 | DECC (S36) | [5 empty] | 2 | 2008-04-01 | [6 empty] | 2011-02-09 |  |  |  |  | 2013-08-30 | 2015-05-30
N00556W | 2545 | 2018-04-05 | Orsted (formerly Dong Energy) | Westermost Rough A | Wind Offshore |  |  | 210 | n/a |  |  |  | 6 | 35 |  | n/a | Operational | Operational | 25 km north of Spurn Head at the River Humber estuary. | Offshore | Offshore | England |  | 571600 | 358680 | DECC (S36) | [5 empty] | 2 | 2009-11-17 | [6 empty] | 2011-11-29 |  |  |  |  | 2014-02-28 | 2015-05-26
N00461W | 2546 | 2017-11-20 | Orsted (formerly Dong Energy) | Barrow | Wind Offshore |  |  | 90 | n/a |  |  |  | 3 | 30 |  | n/a | Operational | Operational | 7km Walney Island, near Barrow-in-Furness | Offshore | Offshore | England |  | 314978 | 455827 | DECC (S36) | [5 empty] | 1 | 2002-05-10 | [6 empty] | 2003-03-12 |  |  |  |  | 2005-05-01 | 2006-04-01
01015W4 | 2549 | 2005-08-03 | Ecotricity | Stockton Wind Turbine | Wind Onshore |  |  | 1.47 | n/a |  |  |  | 0 | 2 |  | n/a | Planning Permission Refused | Application Refused | East of Layden Lane Track Norwich Norfolk | Norfolk | Eastern | England |  | 639100 | 293300 | South Norfolk Council | 07/98/0343/f | [5 empty] | 1998-03-09 |  | 2001-05-02
01016W4 | 2550 | 2006-05-02 | Western Windpower / Ecotricity | Brundish Wind Turbine | Wind Onshore |  |  | 1.47 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | East of Brundish Road Stockton Norfolk | Norfolk | Eastern | England |  | 639700 | 294700 | South Norfolk Council | 07/98/0342/F | [5 empty] | 1998-03-09 |  | 2001-05-02
01022W5 | 2554 | 2009-10-27 | ECONET LTD | Yare Estuary Wind Turbine | Wind Onshore |  |  | 1.47 | n/a |  |  |  | 0.37 | 4 |  | n/a | Abandoned | Abandoned | South Denes Road, Great Yarmouth, Norfolk | Norfolk | Eastern | England |  | 653400 | 303800 | Great Yarmouth Borough Council | [6 empty] | 1999-05-21 | [6 empty] | 2000-04-28
01023W5 | 2555 | 2013-05-09 | Ecotricity | South Beach Wind Turbine (Somerton) | Wind Onshore |  |  | 1.47 | n/a |  |  |  | 1.47 | 1 |  | n/a | Operational | Operational | Somerton, Great Yarmouth, Norfolk | Norfolk | Eastern | England |  | 646953 | 318736 | Great Yarmouth Borough Council | [6 empty] | 1999-05-21 |  | 2000-04-28 | [10 empty] | 2000-07-22
01038W4 | 2556 | 2008-12-04 | LRZ Ltd (Taken over by NOVERA) | Swaffham 1 - Ecotech Wind Park | Wind Onshore |  |  | 1.47 | n/a |  |  |  | 1.47 | 1 |  | n/a | Operational | Operational | East of West Acre Road Swaffham Norfolk | Norfolk | Eastern | England |  | 581585 | 309935 | Breckland Council | [6 empty] | 1998-03-02 | [6 empty] | 1999-02-19 | [5 empty] | 1999-08-16
04011W3 | 2559 | 2006-05-18 | Cynllun Trydan Gwynt | Mynydd Gorddu Wind Farm | Wind Onshore |  |  | 10.2 | n/a |  |  |  | 0.54 | 19 |  | n/a | Operational | Operational | Mynydd Gorddu Elerch Tal-y-Bont Dyfed | Dyfed | Wales | Wales |  | 266200 | 287200 | Ceredigion County Council | [6 empty] | 1991-01-04 | [6 empty] | 1991-09-12 | [5 empty] | 1998-04-18
04022W4 | 2560 | 2003-12-09 | Powergen Renewables Developments Ltd | Nant Carfan Wind Farm | Wind Onshore |  |  | 20.816 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Machynlleth Powys | Powys | Wales | Wales |  | 290400 | 308000 | Powys County Council | [6 empty] | 1999-04-20 |  | 2002-05-23
04029W5 | 2561 | 2011-06-29 | CELTPOWER LTD | Hirddywell Windfarm | Wind Onshore |  |  | 14.837 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Southwest Of Newtown, nr Llangurig, Powys | Powys | Wales | Wales |  | 302500 | 280000 | Powys County Council | M/2000/0705 | [5 empty] | 2000-08-30 | 2007-04-20
04043W4 | 2563 | 2009-04-22 | Renewable Development Company Ltd, KENTECH Ltd | Cefn Croes Wind Farm | Wind Onshore |  |  | 58.5 | n/a |  |  |  | 1.5 | 39 |  | n/a | Operational | Operational | Canolbarth Forest, Devils Bridge Ceredigion | Dyfed | Wales | Wales |  | 281000 | 280000 | DECC (S36) | AD00737 | [5 empty] | 2000-07-24 | [6 empty] | 2001-12-10 | [5 empty] | 2005-01-25
04050W3 | 2564 | 2011-10-30 | RWE npower | Carno 'B' Wind Farm | Wind Onshore |  |  | 16.8 | n/a |  |  |  | 0.6 | 28 |  | n/a | Operational | Operational | Trannon Moor, Carno, Powys | Powys | Wales | Wales |  | 291053 | 295836 | Powys County Council | [6 empty] | 1993-12-30 | [6 empty] | 1995-08-18 | [5 empty] | 1996-10-01
04051W3 | 2565 | 2011-10-30 | RWE npower | Carno 'A' Wind Farm | Wind Onshore |  |  | 16.8 | n/a |  |  |  | 0.6 | 28 |  | n/a | Operational | Operational | Cwm Cledan Carno Powys | Powys | Wales | Wales |  | 293000 | 295000 | Powys County Council | [6 empty] | 1993-08-16 | [6 empty] | 1995-08-18 | [5 empty] | 1996-10-01
04053W3 | 2566 | 2010-02-03 | Vestas | Cemmaes 'B' Wind Farm | Wind Onshore |  |  | 3.4 | n/a |  |  |  | 0.56 | 6 |  | n/a | Operational | Operational | Mynydd y Cemmaes Cemmaes Machynlleth Powys | Powys | Wales | Wales |  | 287000 | 308000 | Powys County Council | M/1996/0550 | [5 empty] | 1996-09-04 | [6 empty] | 1999-03-16 | [5 empty] | 2002-02-01
04054W3 | 2567 | 2003-12-09 | RWE npower | Trysglwyn Wind Farm | Wind Onshore |  |  | 5.6 | n/a |  |  |  | 0.4 | 14 |  | n/a | Operational | Operational | Trysglwyn Fawr Rhosybol Isle of Anglesey Gwynedd | Gwynedd | Wales | Wales |  | 244000 | 389000 | Isle of Anglesey County Council | [6 empty] | 1992-08-08 |  | 1993-12-10 | [10 empty] | 1996-05-01
04057W4 | 2568 | 2018-10-03 | Private Developer | Hafoty Ucha '2' and '3' Wind Turbine | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Operational | Operational | 3 km South of Cerrigydrudion Llangwm | Clwyd | Wales | Wales |  | 293500 | 345500 | Conwy County Borough Council | 0/25079 | [5 empty] | 2001-07-02 | [6 empty] | 2001-10-17 | [5 empty] | 2002-12-15
04066W3 | 2570 | 2014-12-02 | Windjen | Mynydd Glyn Lws Wind Farm | Wind Onshore |  |  | 3.581 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Mynydd Glyn Lws Betws-yn-Rhos Clwyd | Clwyd | Wales | Wales |  | 289000 | 371200 | Conwy County Borough Council | [6 empty] | 1995-03-27 |  | 2000-11-27
0406AW4 | 2573 | 2005-03-29 | WINDJEN POWER LTD | Mynydd Llanelian Wind Farm | Wind Onshore |  |  | 6.488 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | 5 km South of Colwyn Bay, Conwy | Clwyd | Wales | Wales |  | 284500 | 374500 | Conwy County Borough Council | [6 empty] | 2001-02-02 |  | 2001-06-15
04076W3 | 2574 | 2003-02-10 | Mersey Docks and Harbour Company and Windcluster Limited | Royal Seaforth Dock Wind Farm | Wind Onshore |  |  | 3 | n/a |  |  |  | 0.5 | 6 |  | n/a | Operational | Operational | Royal Seaforth Dock Port of Liverpool Bootle, Sefton Merseyside | Merseyside | North West | England |  | 331100 | 397000 | Sefton Council | [6 empty] | 1995-10-12 |  | 1997-08-22 | [10 empty] | 1999-04-24
04079W4 | 2576 | 2010-09-14 | Vestas | Cemmaes 'C' Wind Farm | Wind Onshore |  |  | 15.3 | n/a |  |  |  | 0.85 | 18 |  | n/a | Operational | Operational | Cemmaes Machynlleth Powys | Powys | Wales | Wales |  | 286800 | 306000 | Powys County Council | M/2000/0846 | [5 empty] | 2000-10-15 | [6 empty] | 2001-04-06 | [5 empty] | 2002-02-23
04087W4 | 2578 | 2005-04-13 | South Western Power / Renewable Energy Systems (RES) / NOVERA | Prysan Wind Farm | Wind Onshore |  |  | 9.9 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Prysan Farm, Rhuddlan, Bach, Llanddyfnan, Anglesey | Gwynedd | Wales | Wales |  | 249000 | 380000 | Isle of Anglesey County Council | [6 empty] | 1995-12-18 |  | 1996-08-06
04103W3 | 2579 | 2003-03-10 | RWE npower | Mynydd Yr Hendre Wind Farm | Wind Onshore |  |  | 29.051 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Mynydd Yr Hendre Cefn Coch Newton Powys | Powys | Wales | Wales |  | 299200 | 301500 | Powys County Council | [6 empty] | 1999-02-01 |  | 2002-05-23
04104W3 | 2580 | 2002-05-10 | MANWEB Generation Holdings/ National Windpower | Llyn Alwen Wind Farm | Wind Onshore |  |  | 19.251 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Llyn Alwen Pentrefoelas Clwyd | Clwyd | Wales | Wales |  | 290400 | 356500 | Conwy County Borough Council | [7 empty] | 2002-05-10
04105W3 | 2581 | 2003-03-13 | MANWEB Generation Holdings Ltd/ National Windpower | Moel Rhiwlug Wind Farm | Wind Onshore |  |  | 19.233 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Moel Rhiwlug Pentrefoelas Clwyd | Clwyd | Wales | Wales |  | 288200 | 355300 | Conwy County Borough Council | [7 empty] | 2003-03-13
04107W3 | 2582 | 2005-06-04 | MANWEB Generation Holdings | Llanbabo Wind Farm | Wind Onshore |  |  | 20.4 | n/a |  |  |  | 2.25 | 9 |  | n/a | Operational | Operational | Llanbabo Wind Farm Land tp the north of Llyn Alaw Isle of Anglesey Gwynedd | Gwynedd | Wales | Wales |  | 236000 | 387000 | Isle of Anglesey County Council | [6 empty] | 1994-08-05 | [6 empty] | 1996-12-19 | [5 empty] | 1997-10-01
05007W5 | 2584 | 2004-02-05 | Ecotricity | Windmill Hill | Wind Onshore |  |  | 1.47 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Tinkley Lane, Stonehouse, Gloucestershire | Gloucestershire | South West | England |  | 381900 | 200500 | Stroud District Council | [6 empty] | 2000-10-06 |  | 2001-05-08
06014W5 | 2586 | 2002-01-18 | RWE npower | Tow Law Wind Farm | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 0.9 | 3 |  | n/a | Operational | Operational | Tow Law, Crook, County Durham | Durham | North East | England |  | 411500 | 541000 | Durham County Council | [6 empty] | 1999-07-27 | [6 empty] | 2000-06-07 | [5 empty] | 2001-12-30
06015W4 | 2587 | 2009-06-10 | Border Wind Farms Ltd /AMEC | Kirkheaton Wind Farm | Wind Onshore |  |  | 1.767 | n/a |  |  |  | 0.6 | 3 |  | n/a | Operational | Operational | West Farm, Kirkheaton, Northumberland | Northumberland | North East | England |  | 400800 | 576900 | Northumberland County Council | [6 empty] | 1997-11-04 |  | 1999-01-21 |  |  |  | 1999-01-21 | 1999-01-21 | [5 empty] | 2000-05-22
06015W5 | 2588 | 2010-12-06 | Your Energy | Moorsyde Wind Farm | Wind Onshore |  |  | 16.1 | n/a |  |  |  | 3 | 7 |  | n/a | Appeal Refused | Application Refused | Near Chillingham, Northumberland | Northumberland | North East | England |  | 394000 | 645000 | Northumberland County Council | 04/B/1107 | [5 empty] | 2005-01-13 |  | 2008-03-27 |  |  | 2008-10-19
06019W3 | 2591 | 2009-10-07 | Border Windfarm Limited / AMEC | Great Eppleton Wind Farm | Wind Onshore |  |  | 2.953 | n/a |  |  |  | 0.75 | 4 |  | n/a | Operational | Operational | Great Eppleton Farm North Lane Hetton le Hole Tyne and Wear | Tyne and Wear | North East | England |  | 436900 | 548200 | Sunderland City Council | [6 empty] | 1995-08-02 | [6 empty] | 1996-07-25 | [5 empty] | 1997-04-01
06046W3 | 2599 | 2011-10-30 | National Windpower | High Moor Wind Farm | Wind Onshore |  |  | 14.698 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | High Moor Barningham Durham | Durham | North East | England |  | 404300 | 507500 | Durham County Council | [6 empty] | 1996-04-26 |  | 1998-11-12
06068W5 | 2600 | 2009-06-10 | ANGOLD ASSOCIATES | Moneylaws Hill | Wind Onshore |  |  | 11.186 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Nr Coldstream, Northumberland | Northumberland | North East | England |  | 387300 | 634700 | Northumberland County Council | [7 empty] | 2009-06-10
07006W3 | 2602 | 2011-10-30 | Micon Wind Turbines | Lowick Beacon Windfarm | Wind Onshore |  |  | 1.186 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Lowick Beacon Lowick Green near Ulverston Cumbria | Cumbria | North West | England |  | 328600 | 484000 | South Lakeland District Council | 5951340 | [5 empty] | 1995-06-19 |  | 1997-10-06
07032W4 | 2605 | 2011-10-30 | Colham Energy Ltd | Firbank Wind Farm | Wind Onshore |  |  | 9.674 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Firbank Fell Nr Lambrigg Cumbria | Cumbria | North West | England |  | 360800 | 494000 | South Lakeland District Council | [6 empty] | 1998-09-25 |  | 1998-12-08
07035W4 | 2606 | 2009-12-20 | Renewable Development Company Ltd | Whinash Wind Farm | Wind Onshore |  |  | 67.5 | n/a |  |  |  | 2.5 | 27 |  | n/a | Planning Permission Refused | Application Refused | Bretherdale, Tebay, Cumbria | Cumbria | North West | England |  | 357100 | 503800 | DECC (S36) | [6 empty] | 2003-09-29 |  | 2006-03-02
07037W5 | 2609 | 2013-10-08 | S B ENERGY LTD | Reaps Moss Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 1 | 9 |  | n/a | Planning Permission Refused | Application Refused | Off A681, Bacup, Lancashire | Lancashire | North West | England |  | 389000 | 422800 | Rossendale Borough Council | [6 empty] | 1999-06-01 |  | 2000-02-21
07046W3 | 2613 | 2011-10-30 | Great Orton Wind Farms (II) Ltd | Great Orton Wind Farm (Extension) | Wind Onshore |  |  | 2.349 | n/a |  |  |  | 0.4 | 6 |  | n/a | Operational | Operational | Great Orton Airfield, near Wiggonby, Carlisle, Cumbria | Cumbria | North West | England |  | 331300 | 553400 | Allerdale Borough Council | [6 empty] | 1998-02-26 | [6 empty] | 1998-06-23 | [5 empty] | 2000-02-01
07056W3 | 2617 | 2016-08-01 | The Wind Company | Harlock Hill Wind Farm | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 0.5 | 5 |  | n/a | Operational | Operational | Harlock Hill Wind Farm , Pennington , Near Ulverston , Cumbria | Cumbria | North West | England | LA12 0 | 325300 | 479400 | South Lakeland District Council | [6 empty] | 1995-02-03 | [6 empty] | 1996-05-03 | [5 empty] | 1997-01-01
07060W4 | 2618 | 2009-05-06 | Wharrels Hill Windfarm Ltd/ National Windpower | Wharrels Hill Wind Farm | Wind Onshore |  |  | 10.4 | n/a |  |  |  | 1.3 | 8 |  | n/a | Operational | Operational | Wharrels Hill Bothel Cumbria | Cumbria | North West | England |  | 318000 | 537200 | Allerdale Borough Council | 2/2001/0008 | APP/G0908/A/01/1075972 |  |  |  |  | 2000-12-23 |  | 2002-06-19 | [9 empty] | 2007-04-01 | 2007-08-07
07071W4 | 2619 | 2004-09-02 | Wind Turbine Developments Ltd | Warcock Hill 1MW Project | Wind Onshore |  |  | 1 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Coal Clough Wind Farm , Cliviger , Burnley | Lancashire | North West | England |  | 389500 | 428500 | Burnley Borough Council | [6 empty] | 2000-01-24 |  | 2000-05-25
07086W3 | 2620 | 2011-10-30 | RWE npower | Gunson Height Wind Farm | Wind Onshore |  |  | 7.837 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Gunson Height Kirkby Moor Kirkby Ireleth Cumbria | Cumbria | North West | England |  | 325700 | 482200 | South Lakeland District Council | [6 empty] | 1996-01-05 |  | 1997-10-06
07124W3 | 2624 | 2011-10-30 | Windprospect / Windcluster | Siddick Wind Farm | Wind Onshore |  |  | 4.2 | n/a |  |  |  | 0.6 | 7 |  | n/a | Operational | Operational | Siddick Wind Farm Siddick Workington Cumbria | Cumbria | North West | England |  | 300600 | 532100 | Allerdale Borough Council | [6 empty] | 1995-04-21 | [6 empty] | 1995-12-11 | [5 empty] | 1996-08-01
07125W3 | 2625 | 2011-04-11 | Windprospect / Windcluster | Oldside Wind Farm | Wind Onshore |  |  | 5.4 | n/a |  |  |  | 0.6 | 9 |  | n/a | Operational | Operational | Oldside Wind Farm Workington Cumbria | Cumbria | North West | England |  | 299700 | 530500 | Allerdale Borough Council | [6 empty] | 1995-10-31 | [6 empty] | 1996-01-10 | [5 empty] | 1996-09-01
07129W3 | 2626 | 2011-04-11 | The Wind Company | Haverigg Extension Wind Farm | Wind Onshore |  |  | 2.372 | n/a |  |  |  | 0.6 | 4 |  | n/a | Operational | Operational | Kirksanton Airfield Part of Hemplands Farm Haverigg Millom Cumbria | Cumbria | North West | England |  | 313700 | 479500 | Copeland Borough Council | 4/91/0463/0 | [5 empty] | 1991-05-29 | [6 empty] | 1991-08-08 | [5 empty] | 1998-07-01
09053W5 | 2628 | 2011-10-30 | PERTWOOD PARTNERS | Summerslade Down Wind Cluster | Wind Onshore |  |  | 2.209 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Warminster, Wiltshire | Wiltshire | South West | England |  | 387630 | 137910 | Wiltshire Council | [6 empty] | 1998-10-14 |  | 1999-05-17
10004W4 | 2629 | 2005-04-14 | NOVERA / Renewable Energy Systems (RES) | Corston Windfarm | Wind Onshore |  |  | 7.921 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Corston Windfarm, Castlemartin, Pembrokeshire | Dyfed | Wales | Wales |  | 193000 | 199500 | Pembrokeshire County Council | [6 empty] | 1995-10-05 |  | 1996-03-05
10009W4 | 2630 | 2004-08-26 | WINDJEN POWER LTD | Blaen Bowi Wind Farm | Wind Onshore |  |  | 3.877 | n/a |  |  |  | 1.3 | 3 |  | n/a | Operational | Operational | Moelfre Capel Iwan Dyfed, Carmarthenshire | Dyfed | Wales | Wales |  | 232500 | 236000 | Carmarthenshire County Council | W03608 | [5 empty] | 2000-06-27 | [6 empty] | 2001-01-04 | [5 empty] | 2002-07-30
10010W5 | 2631 | 2013-10-08 | AMEC | Ogmore & Garw | Wind Onshore |  |  | 11.954 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Nant Y Moel, Bridgend, Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 291400 | 194500 | Bridgend County Borough Council | P/01/887 | [5 empty] | 2001-09-28 |  | 2002-03-13
10011W4 | 2632 | 2005-03-29 | WINDJEN POWER LTD | Llethercynnon Farm Wind Farm | Wind Onshore |  |  | 7.07 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Nr Garthbrengy, Powys | Powys | Wales | Wales |  | 305300 | 236100 | Powys County Council | B/01/0111 | [5 empty] | 2000-04-18 |  | 2003-01-22
10011W5 | 2633 | 2010-08-31 | AMEC | Werfa | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 2.5 | 19 |  | n/a | Appeal Refused | Application Refused | Nant Y Moel, Bridgend, Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 292300 | 194500 | Bridgend County Borough Council | P/01/887/FUL | [5 empty] | 2001-09-28 |  | 2002-03-13 |  |  | 2004-08-25
10019W3 | 2636 | 2011-10-30 | Micon Wind Turbines (UK) Limited | Parc-Cynog Wind Farm | Wind Onshore |  |  | 3.558 | n/a |  |  |  | 0.7 | 5 |  | n/a | Operational | Operational | Parc-Cynog Farm Pendine Carmarthenshire | Dyfed | Wales | Wales |  | 225500 | 209500 | Carmarthenshire County Council | [6 empty] | 1998-05-05 |  | 2000-02-01 | [10 empty] | 2001-02-01
10050W5 | 2638 | 2001-10-29 | THREE WAY WIND LTD/ TXU Europower Ltd | Rhoscrowther Wind Cluster | Wind Onshore |  |  | 2.186 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Angle, Pembroke, Dyfed | Dyfed | Wales | Wales |  | 191300 | 200500 | Pembrokeshire County Council | [6 empty] | 1999-11-30 |  | 2001-04-12
10095W3 | 2640 | 2001-07-04 | RWE npower | Jordanston Wind Farm | Wind Onshore |  |  | 9.8 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Land at Jordanston south of Fishguard Dyfed | Dyfed | Wales | Wales |  | 192300 | 232800 | Pembrokeshire County Council | 97/520 | [5 empty] | 1997-09-30 |  | 2001-09-01
10099W3 | 2641 | 2005-04-14 | RWE npower | Trenewydd Wind Farm | Wind Onshore |  |  | 6.349 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Mynydd Trenewydd near Fishguard Dyfed | Dyfed | Wales | Wales |  | 200700 | 232500 | Pembrokeshire County Council | [6 empty] | 1999-02-01 |  | 1999-10-01
10148W3 | 2642 | 2002-06-26 | South Wales Power / SWALEC | Gelligaer 'A' Wind Farm | Wind Onshore |  |  | 9.8 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Gelligaer 'A' Wind Farm Mynydd Fochriw Fochriw Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 310000 | 203500 | Merthyr Tydfil County Borough Council | P/99/0295 | [6 empty] | 2002-06-26
10149W3 | 2643 | 2005-04-14 | South Wales Power / SWALEC / National Windpower | Cilciffeth 'A' Wind Farm | Wind Onshore |  |  | 7.837 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Mynydd Cilciffeth near Fishguard Dyfed | Dyfed | Wales | Wales |  | 200700 | 232500 | Pembrokeshire County Council | [6 empty] | 1999-02-01 |  | 1999-10-01
10156W3 | 2645 | 2002-06-26 | South Wales Power / SWALEC | Gelligaer 'B' Wind Farm | Wind Onshore |  |  | 9.8 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Gelligaer B Wind Farm Mynydd Fochriw Fochriw Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 310000 | 203500 | Merthyr Tydfil County Borough Council | T/99/0295 | [6 empty] | 2002-06-26
10157W3 | 2646 | 2005-04-14 | South Wales Power / SWALEC / National Windpower | Cilciffeth 'B' Wind Farm | Wind Onshore |  |  | 7.837 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Mynydd Cilciffeth near Fishguard Dyfed | Dyfed | Wales | Wales |  | 201000 | 232500 | Pembrokeshire County Council | [6 empty] | 1999-02-01 |  | 1999-10-01
11001W4 | 2648 | 2005-02-16 | Worthyvale Manor Partnership | Worthy Vale Manor | Wind Onshore |  |  | 10.14 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Worthyvale Manor Camelford Cornwall | Cornwall | South West | England |  | 211000 | 87500 | Cornwall Council | [6 empty] | 1993-11-08 |  | 1996-06-28
11008W3 | 2649 | 2005-02-16 | RWE npower | Davidstow Wind Farm | Wind Onshore |  |  | 7.837 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Davidstow Trewinnow Farm Trevivian Davidstow Cornwall | Cornwall | South West | England |  | 216000 | 85000 | Cornwall Council | [7 empty] | 2005-02-16
11008W4 | 2650 | 2005-02-16 | Otterham Wind Farm Ltd - Powergen Renewables | Otterham Down Wind Farm | Wind Onshore |  |  | 7.419 | n/a |  |  |  | 0 | 5 |  | n/a | Planning Permission Refused | Application Refused | Rose Park Farm Otterham Down Camelford North Cornwall | Cornwall | South West | England |  | 215700 | 90500 | Cornwall Council | 2002/0998 | [5 empty] | 2002-05-20 |  | 2003-01-21
11021W3 | 2653 | 2010-03-03 | John Laing Environmental Assets Group | Moel Maelogen A | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Operational | Operational | Moel Maelogen Nr Llanrwst Conwy Gwynedd | Gwynedd | Wales | Wales |  | 284700 | 361300 | Conwy County Borough Council | [6 empty] | 1999-08-20 | [6 empty] | 1999-12-15 | [5 empty] | 2003-01-30
11030W5 | 2654 | 2003-03-14 | THE OLD RACECOURSE WINDFARM LTD | The Old Racecourse | Wind Onshore |  |  | 2.202 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Bratton Fleming, North Devon | Devon | South West | England |  | 266200 | 137700 | North Devon District Council | 29679 | [5 empty] | 2000-08-01 |  | 2001-12-18
11049W5 | 2655 | 2003-03-14 | Farm Energy | Hore Down Windfarm | Wind Onshore |  |  | 2.202 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Ilfracombe, North Devon | Devon | South West | England |  | 252600 | 143600 | North Devon District Council | 29678 | [5 empty] | 2000-08-01 |  | 2001-12-19
12013W4 | 2659 | 2009-04-22 | Powergen Renewables Developments Ltd | Out Newton Wind Farm | Wind Onshore |  |  | 8.979 | n/a |  |  |  | 1.3 | 7 |  | n/a | Operational | Operational | Southfield Farms Hull | Humberside | Yorkshire and Humber | England |  | 538800 | 421200 | East Riding of Yorkshire Council | 341/10033 | [5 empty] | 1998-11-04 |  | 2000-09-11 | [10 empty] | 2002-01-31
12041W4 | 2662 | 2005-08-05 | Renewable Energy Systems (RES) | Eastfield Farm Wind Farm | Wind Onshore |  |  | 11.4 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Hollym Holderness | Humberside | Yorkshire and Humber | England |  | 534500 | 424000 | East Riding of Yorkshire Council | 347/10029A | [5 empty] | 1998-09-08 |  | 2000-09-11
12042W4 | 2663 | 2004-12-08 | Eastern Wind Farms Ltd/ RES | Great Hill Wind Farm | Wind Onshore |  |  | 10.093 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Littleborough Rochdale | Greater Manchester | North West | England |  | 393500 | 416500 | Rochdale Borough Council | [6 empty] | 1999-06-02 |  | 2000-03-22
12043W4 | 2664 | 2013-10-08 | Renewable Energy Systems (RES) | Hogshead Wind Farm | Wind Onshore |  |  | 7.093 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Bacup Lancashire | Lancashire | North West | England |  | 389200 | 422200 | Rossendale Borough Council | [6 empty] | 1999-06-01 |  | 2000-02-21
12057W3 | 2667 | 2011-10-30 | Hepworth Building Products Limited | Hepworth Clay Pipeworks Wind Farm | Wind Onshore |  |  | 3.419 | n/a |  |  |  | 0 | 3 |  | n/a | Planning Permission Refused | Application Refused | Hepworth Clay Pipeworks Land off Flint Lane Crow Edge, Stocksbridge South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 418500 | 404500 | Barnsley Council | [6 empty] | 1994-07-01 |  | 1996-12-03
A0008 | 2668 | 2012-07-04 | Private Developer | Pentre Tump | Wind Onshore |  |  | 9.224 | n/a |  |  |  | 3.07 | 3 |  | n/a | Planning Permission Refused | Application Refused | Radnor, Presteigne, Powys. LD8 | Powys | Wales | Wales |  | 319500 | 257500 | Powys County Council | RAD/2002/0397 | [5 empty] | 2002-09-11 |  | 2010-02-17
A0011 | 2670 | 2011-02-07 | Bolsterstone Plc | Newlands Farm Wind | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Appeal Refused | Application Refused | Carelton, Carlisle, Cumbria. CA4 0AE | Cumbria | North West | England |  | 343894 | 552176 | Carlisle City Council | 08/0707 | APP/E0915/A/09/2101659 |  |  |  |  | 2008-07-10 |  | 2008-10-13 |  |  | 2010-03-15
A0012 | 2671 | 2012-05-18 | Ventient (formerly Infinis) | Burnhead Wind Farm | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 2 | 19 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Dalmellington, Charlmerston, Ayr, Strathclyde, KA6 7PN | Strathclyde | Scotland | Scotland |  | 246766 | 606923 | East Ayrshire Council | 09/0180/FL | [5 empty] | 2009-03-30 | 2012-04-19
A0016 | 2672 | 2013-06-03 | Brockholes Farm | Brockholes Wind Cluster | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Brockholes Farm, Grantshouse, Duns, Borders. TD11 3RL | Borders | Scotland | Scotland |  | 382080 | 663751 | Scottish Borders Council | 09/00516/FUL | [5 empty] | 2009-04-14 | [6 empty] | 2010-05-10 |  |  |  |  | 2012-02-28 | 2013-02-18
A0027 | 2673 | 2011-10-17 | Falck Renewables | Kilbraur Windfarm Farlary - Extension | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Operational | Operational | Dunrobin Glen, Golspie, The Highlands. KW10 6SE | Highland | Scotland | Scotland |  | 283124 | 902064 | Scottish Government (S36) | 09/00111/S36SU | [5 empty] | 2009-03-13 | [6 empty] | 2009-12-01 |  |  |  |  | 2010-12-01 | 2011-09-01
A0028 | 2674 | 2011-10-25 | Pennant Wind Energy Ventures | Maesgwyn | Wind Onshore |  |  | 26 | n/a |  |  |  | 2 | 13 |  | n/a | Operational | Operational | Maesgwyn, Glynneath, Neath, West Glamorgan. SA11 | West Glamorgan | Wales | Wales |  | 285500 | 205500 | Neath Port Talbot County Borough Council | P/2006/1261 | [5 empty] | 2006-10-01 | [6 empty] | 2009-05-05 |  |  |  |  | 2010-07-01 | 2011-04-14
A0034 | 2677 | 2012-01-06 | Private Developer | Floods Ferry Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Appeal Refused | Application Refused | Land North Of Floods Ferry Farm Floods Ferry Road March Cambridgeshire PE15 0UW | Cambridgeshire | Eastern | England |  | 535656 | 293166 | Fenland District Council | F/YR09/0272/F | 10/00032/REF |  |  |  |  | 2009-04-17 |  | 2010-01-04 |  |  | 2011-07-06
A0042 | 2678 | 2009-05-20 | Chamberlain | Clares Farm Close | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Woolston, Warrington, Cheshire. WA1 4QE | Cheshire | North West | England |  | 365599 | 389200 | Warrington Borough Council | 2009/14106 | [6 empty] | 2009-05-20
A0056 | 2680 | 2013-04-19 |  | Spicer Hill Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | 34 Spicer Hill, Whitley Road, Penistone, Sheffield, South Yorks. S36 7G | South Yorkshire | Yorkshire and Humber | England |  | 420500 | 404500 | Barnsley Council | 2009/0572 | [5 empty] | 2009-04-27 | [6 empty] | 2010-04-01 | [5 empty] | 2013-02-15
A0057 | 2681 | 2011-12-15 | Airtricity Developments | Nether braco Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Airdrie Road, Caldercruix, Airdrie, Strathclyde | Strathclyde | Scotland | Scotland | ML6 8NY | 284592 | 667142 | North Lanarkshire Council | C/08/00462/FUL | [5 empty] | 2008-03-31 | 2011-10-27
A0065 | 2682 | 2009-07-03 |  | Strensham Wind Cluster | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Pershore, Worcestershire | Hereford and Worcester | West Midlands | England |  | 387500 | 241540 | Tewkesbury Borough Council | [6 empty] | 2008-10-31 |  | 2009-05-06
A0066 | 2683 | 2011-09-13 |  | Ford Motor Company Ltd (Extension) | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Thames Avenue, Dagenham. RM9 6SA | Greater London | London | England |  | 549268 | 183277 | Barking and Dagenham London Borough Council | U0009.09 | [5 empty] | 2009-04-02 | [6 empty] | 2009-07-16 |  |  |  |  | 2010-01-01 | 2011-08-12
A0073 | 2684 | 2011-12-06 | A7 Energy | Dusty Drum (Resubmission) | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Carmyllie, Arbroath, Tayside | Tayside | Scotland | Scotland | DD11 2QS | 355120 | 742154 | Angus Council | 09/00494/FUL | [5 empty] | 2009-05-18 |  | 2009-12-01
A0081 | 2685 | 2010-06-09 | Skelmonae Windfarm Ltd | Cloffrickford | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Auchnagatt (Denmore), Ellon, Grampian. AB41 8YD | Grampian | Scotland | Scotland |  | 391476 | 839598 | Aberdeenshire Council | APP/2009/1278 | [6 empty] | 2010-06-09
A0082 | 2686 | 2012-04-05 |  | Breaker Hill | Wind Onshore |  |  | 19.5 | n/a |  |  |  | 1.3 | 15 |  | n/a | Planning Permission Refused | Application Refused | The site is located 8km South of Girvan between Pinwherry and Colmonell | Strathclyde | Scotland | Scotland |  | 218030 | 587200 | South Ayrshire Council | 09/00979/APP | [5 empty] | 2009-09-04 |  | 2012-03-15
A0083 | 2687 | 2011-12-20 | FMC Technologies | FMC Technologies | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.75 | 2 |  | n/a | Operational | Operational | Pitreavie Crescent, Pitreavie Business Park, Dunfermline, KY11 8UT | Fife | Scotland | Scotland |  | 310010 | 685787 | Fife Council | 09/00301/WFULL | [5 empty] | 2009-02-12 | [6 empty] | 2009-12-22 |  |  |  |  | 2011-04-01 | 2011-12-07
A0084 | 2688 | 2012-02-23 |  | Grise | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Appeal Refused | Application Refused | Skelton, Cumbria, CA11 | Cumbria | North West | England |  | 349366 | 530215 | Eden District Council | 06/0075 | APP/H0928/A/09/2093576/NWF |  |  |  |  | 2006-01-01 |  | 2009-01-06 |  |  | 2010-03-15
A0107 | 2689 | 2011-05-15 |  | Chase Farm | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Appeal Refused | Application Refused | Bardney Road, Baumber, Horncastle, Lincs | Lincolnshire | East Midlands | England | LN9 5NE | 521562 | 373717 | East Lindsey District Council | S/011/01270/09 | APP/D2510/A/10/2121089 |  |  |  |  | 2009-07-17 |  |  |  |  | 2010-12-16
A0125 | 2690 | 2010-01-25 | Grange Wind Farm Ltd | Flixborough Grange Farmhouse | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Planning Permission Refused | Application Refused | Flixborough, Scunthorpe, Humberside. DN15 8 | Humberside | Yorkshire and Humber | England |  | 487532 | 412203 | North Lincolnshire Council | WF/2009/0573 | [5 empty] | 2009-05-11 |  | 2009-08-19
A0128 | 2691 | 2010-06-09 | Boyndie Wind Farm | Boyndie Airfield Extension | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Boyndie, Banff, Grampian | Grampian | Scotland | Scotland | AB45 2LR | 361206 | 863606 | Aberdeenshire Council | APP/2008/2761 | [5 empty] | 2008-08-05 | [6 empty] | 2009-08-14 | [5 empty] | 2010-01-04
A0133 | 2692 | 2010-12-06 | West Coast Energy | Pressendye | Wind Onshore |  |  | 16.1 | n/a |  |  |  | 2.3 | 7 |  | n/a | Appeal Refused | Application Refused | Cushnie, Alford, Grampian. AB33 8AE | Grampian | Scotland | Scotland |  | 357661 | 816269 | Aberdeenshire Council | APP/2008/0237 | PPA-110-2014 |  |  |  |  | 2008-02-05 |  | 2009-08-13 |  |  | 2010-11-12
A0139 | 2693 | 2011-09-13 | Oosterhof & Co | Hill of Corskie | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Appeal Refused | Application Refused | Gartly, Huntly, Grampian. AB54 4 | Grampian | Scotland | Scotland |  | 348723 | 833198 | Aberdeenshire Council | APP/2008/2833 | P/PPA-110/2030 |  |  |  |  | 2008-08-29 |  | 2009-11-10 |  |  | 2010-05-17
A0150 | 2694 | 2011-11-29 | M H Leyland Ltd | Blue Gates Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Colchester Main Road, Alresford, Colchester | Essex | Eastern | England | CO7 8DE | 606950 | 222545 | Tendring District Council | 09/00508/FUL | [5 empty] | 2009-06-05 | [6 empty] | 2009-09-11 | [5 empty] | 2010-03-01
A0152 | 2695 | 2017-02-21 | Ecotricity / Next Generation | Celcon Blocks Ltd | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Heck and Pollington Lane, Pollington, Goole, Humbs | Humberside | Yorkshire and Humber | England | DN14 0BA | 460597 | 420445 | East Riding of Yorkshire Council | 09/02681/STPLF | 12/00045/REFUSE |  |  |  |  | 2009-08-04 |  | 2012-01-16 | 2012-05-18 |  |  | 2012-10-17 | 2012-10-17 |  |  |  |  | 2015-04-15 | 2016-04-15
A0170 | 2696 | 2011-06-23 | Private Developer | Hillcrest Farm | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Balephetrish, Tiree, Scarinish, Strathclyde. PA77 6UY | Strathclyde | Scotland | Scotland |  | 101097 | 746972 | Argyll and Bute Council | 09/01037/DET | [5 empty] | 2009-07-06 | 2011-06-21
A0171 | 2697 | 2010-10-28 | Hammers Hill Energy Ltd | Hammar's Hill | Wind Onshore |  |  | 4.25 | n/a |  |  |  | 0.9 | 5 |  | n/a | Operational | Operational | Evie, Orkney | Orkney Islands | Scotland | Scotland |  | 338644 | 1023698 | Orkney Islands Council | 08/138/PPF | [5 empty] | 2008-03-11 | [6 empty] | 2009-01-06 |  |  |  |  | 2009-09-01 | 2010-09-20
A0175 | 2698 | 2011-03-31 | Nanclach Ltd | Tomatin | Wind Onshore |  |  | 25.5 | n/a |  |  |  | 1.5 | 17 |  | n/a | Planning Permission Refused | Application Refused | Inverness, Highlands, IV33 | Highland | Scotland | Scotland |  | 278423 | 829823 | Highland Council | 09/00439/FUL | [5 empty] | 2009-06-24 |  | 2010-08-30
A0177 | 2699 | 2013-10-08 | ABO Wind UK | Easter Muirhead Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Permission Refused | Application Refused | North of Saline, Dunfermline, Fife | Fife | Scotland | Scotland | KY12 9UG | 298665 | 694024 | Fife Council | 09/01359/WEIA | [5 empty] | 2009-06-12 |  | 2010-02-17
A0178 | 2700 | 2012-03-08 | Scotfarms Ltd | Woodlands Farm - Elion | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Appeal Refused | Application Refused | Udny, Ellon, Grampian | Grampian | Scotland | Scotland | AB41 6SP | 387836 | 823758 | Aberdeenshire Council | APP/2008/4051 | P/PPA/110/2038 |  |  |  |  | 2008-12-04 |  | 2009-12-16 |  |  | 2010-06-25
A0179 | 2701 | 2010-06-09 | Private Developer | Mains of Cairnbrogie | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Appeal Refused | Application Refused | Oldmeldrum, Inverurie, Grampian | Grampian | Scotland | Scotland | AB51 0BR | 385047 | 828018 | Aberdeenshire Council | APP/2008/4093 | P/PPA/110/2018 |  |  |  |  | 2008-12-03 |  | 2008-12-03 |  |  | 2009-11-27
A0179a | 2702 | 2010-12-06 | Private Developer | Mains of Cairnbrogie 2 | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Appeal Refused | Application Refused | Oldmeldrum, Inverurie, Grampian | Grampian | Scotland | Scotland | AB51 0BR | 385355 | 829356 | Aberdeenshire Council | APP/2010/0305 | PPA-110-2018 |  |  |  |  | 2010-02-05 |  | 2010-05-20 |  |  | 2010-02-19
A0188 | 2703 | 2010-06-09 | Airtricity Developments | Mile Hill | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Kingoldrum, Kirriemuir, Tayside, Angus. DD8 5HX | Tayside | Scotland | Scotland |  | 336170 | 753405 | Angus Council | 08/00426/F | [6 empty] | 2010-06-09
A0189 | 2704 | 2012-04-26 | FMC Corp UK Ltd | F M C Land, Pitreavie Business Park | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Queensferry Road, Pitreavie Crescent, Dunfermline, Fife. KY11 8UD | Fife | Scotland | Scotland |  | 310145 | 685510 | Fife Council | 09/00301/WFUL | [5 empty] | 2009-02-13 | [6 empty] | 2009-12-22 | [5 empty] | 2011-10-31
A0191 | 2705 | 2010-08-06 | Derbyshire wind Energy | Rushley Lodge Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | off Wirestone Lane, Middle Moor, Matlock, Derbyshire. DE4 5LZ | Derbyshire | East Midlands | England |  | 431631 | 361642 | Derbyshire Dales District Council | 09/00060/FUL | [5 empty] | 2009-01-26 |  | 2009-05-15 |  |  | 2010-04-22
A0196 | 2706 | 2015-06-29 | Partnerships for Renewables | Haverigg Prison | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 | 120.5 | n/a | Planning Permission Refused | Application Refused | Haverigg Prison, Cumbria | Cumbria | North West | England | LA18 5LU | 313864 | 484173 | Copeland Borough Council | 4/12/2251/0F1 | [5 empty] | 2012-05-09 |  | 2014-09-01
A0197 | 2707 | 2012-09-05 | RWE npower | Raera Forest | Wind Onshore |  |  | 48 | n/a |  |  |  | 3 | 16 |  | n/a | Planning Permission Refused | Application Refused | Lochigilphead Road, Oban | Strathclyde | Scotland | Scotland |  | 184857 | 689479 | Argyll and Bute Council | [6 empty] | 2009-12-17 |  | 2010-12-17
A0205 | 2708 | 2010-06-09 | Green Cat Renewables | Strath of Brydock - Extension | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Operational | Operational | Strath of Brydock, Alvah, Banff | Grampian | Scotland | Scotland |  | 365391 | 859727 | Aberdeenshire Council | APP/2008/2404 | [5 empty] | 2008-11-15 | [6 empty] | 2009-10-16 | [5 empty] | 2009-12-01
A0228 | 2710 | 2012-08-15 | TCI Renewables | Pigeon Top | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Abandoned | Abandoned | Dooish, Drumquin, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 48085 | 535005 | Northern Ireland Planning Service | K/2009/0081 | [5 empty] | 2009-01-10 |  | 2009-12-03 |  |  |  | 2010-12-13 | 2010-12-13
A0237 | 2711 | 2018-10-02 | Scottish Power Renewables | Hare Hill (East Ayrshire) | Wind Onshore |  |  | 13.2 | n/a |  |  |  | 0.66 | 20 |  | n/a | Operational | Operational | New Cumnock, East Ayreshire | Strathclyde | Scotland | Scotland |  | 265320 | 609703 | East Ayrshire Council | [6 empty] | 1996-02-10 | [6 empty] | 1998-10-12 | [5 empty] | 2000-11-01
A0243 | 2712 | 2011-02-07 | Peel Energy | Former Broughton Lodge Resubmission | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Great Broughton, Cockermouth, Cumbria. CA13 0LD | Cumbria | North West | England |  | 308954 | 531519 | Allerdale Borough Council | 2/2009/0880 | [5 empty] | 2009-12-21 |  | 2011-01-11
A0261 | 2713 | 2019-08-05 | Npower Renewables | Kirkby Moor | Wind Onshore |  |  | 4.8 | n/a |  |  |  | 0.4 | 12 |  | n/a | Operational | Operational | approximately 4km from Ulverston, within a Site of Special Scientific Interest | Cumbria | North West | England |  | 326111 | 485242 | South Lakeland District Council | Unknown | [18 empty] | 1993-01-01
A0298 | 2714 | 2010-11-02 | Cumbria Wind Farms | Neslam Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Sempringham Fen, Sleaford | Lincolnshire | East Midlands | England | NG34 0NH | 515447 | 332967 | South Kesteven District Council | S09/0296 | [5 empty] | 2009-02-03 | 2009-09-16
A0299 | 2715 | 2010-03-24 |  | Bambers II | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 0.76 | 6 |  | n/a | Operational | Operational | Mile Lane, Mablethorpe, Lincolnshire | Lincolnshire | East Midlands | England |  | 549195 | 382820 | East Lindsey District Council | N/187/01107/05 | [5 empty] | 2005-05-04 | [6 empty] | 2005-09-08 | [5 empty] | 2006-11-01
A0302 | 2716 | 2013-10-08 | Scottish Power Renewables | Callagheen Ext | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Killy Beg and Killy More Townlands (to the south side of public road from existing Callagheen wind farm) | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 8654 | 521115 | Northern Ireland Planning Service | L/2007/1772/F | [5 empty] | 2007-12-15 | 2010-04-01
A0306 | 2717 | 2011-03-29 | Ted Walsh & Associates | Farkland | Wind Onshore |  |  | 51 | n/a |  |  |  | 3 | 17 |  | n/a | Planning Application Withdrawn | Application Withdrawn | on the south western slopes of Altahullion Hill, 8km from Claudy and south east of Dungiven. | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 77172 | 572135 | Northern Ireland Planning Service | B/2007/0562/F | [5 empty] | 2007-12-12 | 2010-11-11
A0310 | 2718 | 2011-04-04 | Lisnamuck Wind Farm Limited | Lisnamuck Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land approximately 750m south of 13B Lisnamuck Road, Blackhill, Coleraine | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 102741 | 581858 | Northern Ireland Planning Service | C/2008/0163/F | [5 empty] | 2008-02-21 | 2010-10-01
A0312 | 2719 | 2011-04-04 | Gaelectric Developments | Cappagh | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Cappagh Road, 5km South of Pomeroy and 13km North West of Dungannon, Co. Tyrone, BT70 2PD | Co. Tyrone | Northern Ireland | Northern Ireland |  | 81507 | 527745 | Northern Ireland Planning Service | M/2008/0476/F | [5 empty] | 2008-04-14 | 2010-12-07
A0315 | 2720 | 2012-04-16 | Bell Architects Ltd | Slieve Croob | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land approx 300m SW of Existing BT Tower, Slieve Croob, Dromara, Dromore. | Co. Down | Northern Ireland | Northern Ireland |  | 136636 | 505059 | Northern Ireland Planning Service | Q/2007/0914/F | [5 empty] | 2007-12-27 |  | 2012-02-13
A0317 | 2721 | 2010-07-29 | Northern Ireland Renewables | Corkey Wind Farm Ext | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 583m North of 42 Reservoir Road, Corkey | Co. Antrim | Northern Ireland | Northern Ireland |  | 126055 | 580730 | Northern Ireland Planning Service | D/2008/0404/F | [6 empty] | 2010-07-29
A0326 | 2722 | 2011-06-23 | Alan Twatt (Potatoes) Ltd | Cairncake | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Cuminestown, Turriff, Aberdeenshire. AB53 5YR | Grampian | Scotland | Scotland |  | 377451 | 821875 | Aberdeenshire Council | APP/2010/0755 | [5 empty] | 2010-03-15 |  | 2011-06-09
A0346 | 2723 | 2011-05-05 | West Coast Energy Ltd/Falck Renewables | Millennium Extension II | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | Millennium Windfarm, on The Achlain and Invergarry amd Aberchalder Estates, Glengarry Invergarry, Inverness-Shire, (nr Glen Moriston, Fort Augustus) | Highland | Scotland | Scotland |  | 225679 | 810840 | Scottish Government (S36) | [6 empty] | 2009-01-06 | [6 empty] | 2009-08-10 |  |  |  |  | 2010-04-01 | 2011-04-01
A0347 | 2724 | 2010-08-06 | Private Developer | Cairnmore Farm | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Operational | Operational | 3km south-east of Rhynie in Aberdeenshire | Grampian | Scotland | Scotland |  | 351086 | 825261 | Aberdeenshire Council | APP/2008/1486 | [5 empty] | 2008-04-18 | [6 empty] | 2009-10-27 |  |  |  |  | 2010-04-01 | 2010-07-10
A0351 | 2725 | 2012-08-14 | Scottish and Southern Energy (SSE) | Harrow's Law Resubmission | Wind Onshore |  |  | 39 | n/a |  |  |  | 2.3 | 17 |  | n/a | Appeal Refused | Application Refused | Harrows Law Dunsyre | Strathclyde | Scotland | Scotland |  | 304200 | 653700 | South Lanarkshire Council | CL/10/0095 | [5 empty] | 2010-03-05 |  | 2011-06-27 |  |  | 2012-05-23
A0386 | 2729 | 2011-08-19 | Prowind | Hogs Hill | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | South of the village of Haunton | Staffordshire | West Midlands | England |  | 422363 | 309765 | Lichfield District Council | 10/00750/FULMEI | [5 empty] | 2010-06-28 | 2011-03-14
A0455 | 2737 | 2011-09-13 |  | Weston Hills | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Weston Park Farms, Darnalls Hall, Weston, Hitchin, Herts | Hertfordshire | Eastern | England | SG4 7AL | 526179 | 230831 | North Hertfordshire District Council | 08/00047/1 | [5 empty] | 2008-09-04 |  | 2009-04-23
A0492 | 2739 | 2011-06-14 | Noble Foods | Lodge Farm (Lincolnshire) | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Sleaford Rd, Beckingham, Lincoln, Lincolnshire LN5 0RB | Lincolnshire | East Midlands | England |  | 489572 | 353607 | North Kesteven District Council | 11/0238/FUL | [5 empty] | 2011-03-03 | 2011-06-03
A0501 | 2740 | 2011-12-02 | Renewable Energy Systems (RES) | Rayburn Lake Wind Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | North East Of Park Head Farm Netherwitton Morpeth Northumberland | Northumberland | North East | England |  | 410905 | 592927 | Northumberland County Council | C/09/00154/RENEIA | [5 empty] | 2009-08-27 | 2011-11-01
A0538 | 2741 | 2013-03-22 | Greenspan Electric St Fergus Ltd | St Fergus Moss Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Land at St Fergus Moss, St Fergus, Peterhead | Grampian | Scotland | Scotland |  | 405416 | 853549 | Aberdeenshire Council | APP/2010/2118 | [5 empty] | 2010-06-28 | [6 empty] | 2012-02-23 |  |  |  |  | 2012-03-31 | 2012-12-18
AA005 | 2742 | 2011-06-07 | Scotrenewables (Scotland) Ltd | West Hill, Flotta | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | West Hill, Flotta, Orkney | Orkney Islands | Scotland | Scotland |  | 335252 | 993820 | Orkney Islands Council | 04/224/PPF | [5 empty] | 2004-04-26 | [6 empty] | 2007-12-18 | [5 empty] | 2010-07-01
AA010 | 2744 | 2011-02-28 | Novera Energy | Todd Hill Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Permission Refused | Application Refused | Agricultural land north of Pigden and east of Stanton, 6km northwest of Morpeth | Northumberland | North East | England |  | 415500 | 589000 | Northumberland County Council | 09/00083/CCMEIA | [5 empty] | 2008-12-01 |  | 2010-06-01
AA015 | 2747 | 2011-12-02 | Yorkshire Water | Chelker Reservoir (Retention of Turbines) | Wind Onshore |  |  | 1.2 | n/a |  |  |  | 0.3 | 4 |  | n/a | Operational | Operational | Land adjacent to Chelker Reservoir, nr Skipton | North Yorkshire | Yorkshire and Humber | England |  | 405730 | 451820 | Craven District Council | 24/2001/0997 | [5 empty] | 2001-01-24 | [6 empty] | 2001-05-30 | [5 empty] | 2004-05-01
AA025 | 2748 | 2010-06-18 | Stamford Renewables | Granary farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Church Road, Ringsfield, Beccles, Suffolk, NR34 8LE | Suffolk | Eastern | England |  | 640725 | 288329 | Waveney District Council | DC/10/0088/FUL | [6 empty] | 2010-06-18
AA026 | 2749 | 2010-06-18 | Stamford Renewables | Laurels Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Bungay Road, Barsham, Suffolk | Suffolk | Eastern | England |  | 638664 | 289263 | Waveney District Council | DC/10/0091/FUL | [6 empty] | 2010-06-18
AA027 | 2750 | 2010-06-18 | SRL | Devonshire Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Ringsfield, Beccles, Suffolk | Suffolk | Eastern | England |  | 641328 | 288986 | Waveney District Council | DC/10/0048/FUL | [6 empty] | 2010-06-18
AA028 | 2751 | 2010-04-20 | Private Developer | Valley view farm | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Red Lodge Road, Tilton On The Hill, Leicestershire, LE7 9LJ | Leicestershire | East Midlands | England |  | 474409 | 305978 | Harborough District Council | 10/00020/FUL | [5 empty] | 2010-01-04 |  | 2010-04-14
AA035 | 2753 | 2012-05-04 | Severn Trent Water | Stoke Bardolph Farm | Wind Onshore |  |  | 3.4 | n/a |  |  |  | 1.7 | 2 |  | n/a | Planning Permission Refused | Application Refused | Stoke Bardolph Farm, Nottinghamshire | Nottinghamshire | East Midlands | England |  | 464294 | 342475 | Gedling Borough Council | 2010/0289 | [5 empty] | 2010-04-01 |  | 2012-04-04
AA037 | 2755 | 2011-02-28 | Private Developer | Queniborough wind farm | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Permission Refused | Application Refused | off Ridgemere Lane, Queniborough, Leicester | Leicestershire | East Midlands | England |  | 464708 | 311376 | Charnwood Borough Council | P/09/2464/2 | [5 empty] | 2010-02-22 |  | 2011-02-04
AA059 | 2757 | 2013-04-19 |  | Whitelee Windfarm Extension phase 2 | Wind Onshore |  |  | 109 | n/a |  |  |  | 3 | 39 |  | n/a | Operational | Operational | north of the Irvine Valley on Eaglesham Moor | Strathclyde | Scotland | Scotland |  | 254220 | 640867 | Scottish Government (S36) | WHX/02/040/0162 | [5 empty] | 2009-05-29 | [6 empty] | 2009-12-12 |  |  |  |  | 2010-12-01 | 2013-01-15
AA061 | 2758 | 2010-06-01 | Private Developer | Hill of Balquhindachy extension | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Operational | Operational | Methlick, Ellon | Grampian | Scotland | Scotland | AB41 7BY | 385642 | 842482 | Aberdeenshire Council | APP/2007/1191 | [5 empty] | 2007-03-20 | [6 empty] | 2008-09-09 | [5 empty] | 2010-07-09
AA098 | 2759 | 2012-01-30 | Wind Prospect | Stoneyard Lane Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Appeal Refused | Application Refused | near Oldbury on Severn, South Gloucestershire, | Avon | South West | England |  | 363525 | 194472 | South Gloucestershire Council | [6 empty] | 2010-09-10 |  | 2011-03-18 |  |  | 2012-01-24
AA102 | 2760 | 2012-12-07 | East Fife Wind Energy | Devon Wood | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | between Kennoway and Kingskettle, Fife | Fife | Scotland | Scotland |  | 335385 | 705734 | Fife Council | 10/02183/EIA | 12/00056/REF |  |  |  |  | 2010-06-29 |  | 2012-04-18 |  |  | 2012-11-22
AA111 | 2761 | 2015-11-24 | Scottish Power Renewables | East Kingswell | Wind Onshore |  |  | 26 | n/a |  |  |  | 3.7 | 7 |  | n/a | Planning Permission Refused | Application Refused | Eaglesham Moor, East Ayrshire | Strathclyde | Scotland | Scotland |  | 251895 | 645950 | East Ayrshire Council | 10/0485/PP | [5 empty] | 2010-05-25 |  | 2010-12-01
AA112 | 2762 | 2012-11-26 | EDF Energy | Withy Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | s/oHuntspill River, Puriton, Bridgwater, Somerset, TA6 | Somerset | South West | England |  | 333071 | 143838 | Sedgemoor District Council | 54/11/00004 | [5 empty] | 2011-03-09 |  | 2012-04-24
AA126 | 2763 | 2012-01-25 | Private Developer | South Cassingray | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Appeal Refused | Application Refused | Farm Cadgers Road Largoward Leven Fife KY9 1JD | Fife | Scotland | Scotland |  | 348377 | 707425 | Fife Council | 10/02616/FULL | 11/00018/8WEEK |  |  |  |  | 2010-07-20 |  | 2011-12-21 |  |  | 2011-07-18
AA128 | 2764 | 2011-01-05 | Sea & Land Power and Energy Ltd | Hemsby Wind Farm - Resubmision | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Permission Refused | Application Refused | between the villages of Hemsby and Ormesby St Margaret in Norfolk | Norfolk | Eastern | England |  | 648799 | 316278 | Great Yarmouth Borough Council | 06/09/0592/F | 40351 |  |  |  |  | 2009-09-08 |  | 2009-12-23
AA170 | 2765 | 2012-01-27 | Lomond Energy | Spurlens Rig Wind Cluster | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Permission Refused | Application Refused | near Leadburn, Scottish Borders | Borders | Scotland | Scotland |  | 324748 | 654014 | Scottish Borders Council | 10/01669/FUL | [5 empty] | 2010-12-07 |  | 2011-11-30
AA174 | 2766 | 2011-09-13 | Private Developer | Grove Farm (wind) | Wind Onshore |  |  | 6.8 | n/a |  |  |  | 3.4 | 2 |  | n/a | Planning Permission Refused | Application Refused | Ingham, Brumstead, Norfolk | Norfolk | Eastern | England |  | 637988 | 326797 | North Norfolk District Council | PF/09/1060 | [5 empty] | 2009-10-27 |  | 2010-11-25
AA184 | 2767 | 2019-09-16 | Corolis Energy/ ESB | Chirmorie Wind Farm | Wind Onshore |  |  | 76 | n/a |  |  |  | 3.6 | 21 | 146.5 | n/a | Planning Permission Granted | Awaiting Construction | Near Barrhill, South Ayrshire | Strathclyde | Scotland | Scotland |  | 222552 | 579875 | Scottish Government (S36) | EC00002071 | [5 empty] | 2015-11-30 | [6 empty] | 2018-03-16 |  |  |  | 2021-03-16
AA221 | 2771 | 2011-12-07 | Energy4All | Cartland Muir Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | 3km South West of Carluke town Centre, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 286389 | 646411 | South Lanarkshire Council | CL/11/0266 | [5 empty] | 2011-06-21 |  | 2011-12-01
AA226 | 2772 | 2011-12-16 | Kelda Water Services | Chelker Reservoir Repower | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Skipton Road, Addingham, Ilkley, LS29 0JU | North Yorkshire | Yorkshire and Humber | England |  | 405958 | 451783 | Craven District Council | 24/2011/11383 | [5 empty] | 2011-02-11 | 2011-07-04
AA352 | 2774 | 2012-02-23 | Eye Wind Power Ltd | J.W. Baldwin Wind Farm | Wind Onshore |  |  | 6.8 | n/a |  |  |  | 3.4 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | South east of Eye Airfield, Suffolk | Suffolk | Eastern | England |  | 613137 | 274854 | Mid Suffolk District Council | 0385/11 | [6 empty] | 2012-02-23
AA356 | 2775 | 2011-10-24 | British Telecom | Junction House | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land North of Pesspool Lane, Easington Village | Durham | North East | England |  | 439790 | 543568 | Durham County Council | PL/5/2010/0473 | [5 empty] | 2011-02-09 |  | 2011-10-04
AA384 | 2776 | 2011-06-01 | Npower Renewables | Taff Ely Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 0.45 | 20 |  | n/a | Operational | Operational | 10 kilometres (km) north east of Bridgend | Mid Glamorgan | Wales | Wales |  | 298574 | 186630 | Bridgend County Borough Council | [19 empty] | 1993-10-01
AA408 | 2779 | 2013-04-19 | The Carrach Wind Farm LLP | Carrach Wind Farm | Wind Onshore |  |  | 7.2 | n/a |  |  |  | 0.8 | 9 |  | n/a | Appeal Refused | Application Refused | Land At Welton And Kinclune Hills, Kingoldrum | Tayside | Scotland | Scotland |  | 329985 | 756577 | Angus Council | 11/00554/FULL | 12/00017/REFUSE |  |  |  |  | 2011-06-21 |  | 2012-08-30 |  |  | 2013-01-10
AA432 | 2780 | 2016-04-04 | Airvolution Energy | Mossmorran Wind Farm | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Land At To The West Of Chemical Works, Mossmorran, Fife | Fife | Scotland | Scotland |  | 318109 | 689419 | Fife Council | 11/01807/FULL | [5 empty] | 2011-04-01 | [6 empty] | 2012-01-13 |  |  |  |  | 2015-09-01 | 2015-12-01
AA466 | 2782 | 2011-09-14 | Private Developer | Courtstone Wind Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Methlick Ellon AB41 7HH | Grampian | Scotland | Scotland |  | 384413 | 833537 | Aberdeenshire Council | APP/2006/3646 | [5 empty] | 2006-09-15 | [6 empty] | 2006-09-15 | [5 empty] | 2009-06-04
AA482 | 2783 | 2012-03-20 | Green Cat Renewables | Cairnbrogie Wind Farm (Resubmission) | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Oldmeldrum, Inverurie | Grampian | Scotland | Scotland | AB51 0BR | 385451 | 829484 | Aberdeenshire Council | APP/2011/1917 | [5 empty] | 2011-06-07 |  | 2012-03-05
AA490 | 2784 | 2011-11-14 | Volkswind UK Ltd | Spaldington Common Windfarm | Wind Onshore |  |  | 16.1 | n/a |  |  |  | 2.3 | 7 |  | n/a | Appeal Refused | Application Refused | Land North West Of Ivy House Farm, Holme Road, Spaldington, East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 477416 | 433237 | East Riding of Yorkshire Council | 09/04568/STPLFE | 10/00115/REFUSE |  |  |  |  | 2009-11-19 |  | 2010-09-22 |  |  | 2011-09-29
AA521 | 2785 | 2016-05-27 | Renewable Energy Systems (RES) | Brown's Holt Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 | 140 | n/a | Planning Application Withdrawn | Application Withdrawn | Land North Of Yawthorpe, Brown''s Holt, Corringham, Gainsborough, Lincolnshire | Lincolnshire | East Midlands | England | DN21 5RH | 489644 | 391996 | West Lindsey District Council | 132109 | [5 empty] | 2015-02-13 | 2016-05-27
AA586 | 2788 | 2012-03-14 | Pennant Wind Energy Ventures | Burnside Wind Cluster ( Resubmission) | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land to North West of Blackhills Farm Cushnie Alford | Grampian | Scotland | Scotland |  | 351022 | 808117 | Aberdeenshire Council | APP/2011/3185 | [5 empty] | 2011-11-03 | 2012-01-23
AA599 | 2789 | 2016-08-03 | Ventus Renewables | Land North-West Of Seater Farm | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 | 62 | n/a | Planning Permission Refused | Application Refused | Land 190M NW Of Seater Farm, Bower, Wick, Highlands | Highland | Scotland | Scotland | KW1 4 | 324756 | 960627 | Highland Council | 15/02818/FUL | [5 empty] | 2015-07-22 |  | 2016-07-26
AA632 | 2790 | 2012-05-25 | Associated British Ports & Siemens Plc | Green Port Hull Wind Turbine | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | South Eastern Corner Of Alexandra Dock Kingston Upon Hull | Humberside | Yorkshire and Humber | England |  | 512878 | 428734 | Kingston upon Hull City Council | 11/01179/FULL | [5 empty] | 2011-12-14 | 2012-04-20
AA645 | 2791 | 2012-09-20 | Private Developer | Far Marsh Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Marsh Road Ottringham East Riding Of Yorkshire HU12 0AN | Humberside | Yorkshire and Humber | England |  | 523848 | 421320 | East Riding of Yorkshire Council | 11/05896/STPLFE | [5 empty] | 2012-01-03 | 2012-04-04
AA665 | 2792 | 2013-05-16 | Damside Wind Farm Ltd | Damside Wind Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Planning Permission Refused | Application Refused | Barnhill Farm, Farm Dura Road, Allanton, Shotts, Lanarkshire | Strathclyde | Scotland | Scotland | ML7 5DJ | 287869 | 657078 | North Lanarkshire Council | 12/00808/FUL | [5 empty] | 2012-07-20 |  | 2013-03-07
AA708 | 2794 | 2012-09-24 | Macwindgen Limited | Douglas Top | Wind Onshore |  |  | 51 | n/a |  |  |  | 3 | 17 |  | n/a | Planning Application Withdrawn | Application Withdrawn | in the townlands of Douglas, Mistyburn, and Glenwhirry, Douglad Road, Ballymena, Co. Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 138345 | 558313 | Northern Ireland Planning Service | G/2011/0182/F | N/A |  |  |  |  | 2011-04-13 | 2012-04-25
AA734 | 2796 | 2012-04-19 | ABO Wind | Lairg Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Land To South Of Toroboll Lairg Highland | Highland | Scotland | Scotland |  | 261293 | 903916 | Highland Council | 06/00376/FULSU | N/A |  |  |  |  | 2006-09-05 | [6 empty] | 2008-04-08 | [5 empty] | 2012-01-01
AA878 | 2800 | 2013-09-04 | Partnerships for Renewables | Carron Valley (Cairnoch Hill) Wind Farm | Wind Onshore |  |  | 45 | n/a |  |  |  | 3 | 15 |  | n/a | Appeal Refused | Application Refused | Land Some 1100M North Of Cairnoch Polmaise Road To Carron Reservoir Stirling | Stirling | Scotland | Scotland |  | 269168 | 685499 | Stirling Council | 12/00515/FUL | 13/00001/REF |  |  |  |  | 2012-08-08 |  | 2012-12-11 |  |  | 2013-07-04
AA934 | 2801 | 2013-04-08 | Private Developer | Balnacake Farm | Wind Onshore |  |  | 1.2 | n/a |  |  |  | 0.4 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Aldbar, Brechin, Angus | Tayside | Scotland | Scotland |  | 356003 | 757613 | Angus Council | 12/00779/FULL | [5 empty] | 2012-08-30 | 2013-01-07
AA937 | 2802 | 2012-09-27 | Caithness Power | Upper Smerral Wind Cluster | Wind Onshore |  |  | 3.2 | n/a |  |  |  | 0.8 | 4 |  | n/a | Planning Permission Refused | Application Refused | Land SE Of Houstry Upper Smerral Latheron | Highland | Scotland | Scotland |  | 316373 | 934062 | Highland Council | 10/03501/FUL | [5 empty] | 2010-08-27 |  | 2012-04-23
B0061 | 2804 | 2011-08-03 |  | G24 Innovations Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Wentloog Environmental Centre, WENTLOOG AVENUE, WENTLOOG | South Glamorgan | Wales | Wales |  | 323460 | 179215 | Cardiff Council | 07/02286/E | [5 empty] | 2007-09-26 | [6 empty] | 2008-01-15 | [5 empty] | 2011-07-12
B0064 | 2805 | 2012-03-21 | R H Bott & Son Ltd | High Elms Lane Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land East Of Walkern Road and North and West Of High Elms Lane, Benington | Hertfordshire | Eastern | England |  | 529350 | 220930 | East Hertfordshire District Council | 3/11/1190/FP | [5 empty] | 2011-07-05 |  | 2011-10-26
B0083 | 2809 | 2012-07-23 | Private Developer | Treworgans Wind Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Appeal Refused | Application Refused | Land At Treworgans Cubert Cornwall | Cornwall | South West | England |  | 178563 | 59625 | Cornwall Council | NR/10/00063/WIND | 11/00164/REF |  |  |  |  | 2010-03-03 |  | 2011-08-19 |  |  | 2012-07-04
B0091 | 2810 | 2011-08-25 |  | Ballochmartin Farm Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Site To South West Of Ballochmartin Farm Millport Isle Of Cumbrae | Strathclyde | Scotland | Scotland |  | 217199 | 657010 | North Ayrshire Council | 11/00403/PP | [5 empty] | 2011-06-10 | 2011-07-18
B0247 | 2819 | 2012-09-27 | WSP Environmental | Glaxo Smith Kline Wind Turbine | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Site 2 & 3 Cobden Street Montrose | Tayside | Scotland | Scotland |  | 372235 | 757220 | Angus Council | 11/01184/EIAL | [5 empty] | 2011-12-14 |  | 2012-08-29
B0300 | 2821 | 2012-08-15 | Greenvale AP | Greenvale AP Wind Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Abandoned | Abandoned | Land North West Of Greenvale Produce Ltd Floods Ferry Road Doddington Cambridgeshire | Cambridgeshire | Eastern | England |  | 535485 | 293292 | Fenland District Council | F/YR11/0632/F | [5 empty] | 2011-07-18 | [6 empty] | 2011-12-19
B0301 | 2822 | 2012-01-31 | Mornflake Oats/ Hamlyns Oats | Mornflake Oats Wind Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Cairnton Road Boyndie Banff AB45 2LR | Grampian | Scotland | Scotland |  | 361543 | 863513 | Aberdeenshire Council | APP/2008/2874 | [5 empty] | 2008-08-05 | [6 empty] | 2011-04-06 | [5 empty] | 2012-01-18
B0437 | 2826 | 2012-08-02 |  | Newlands Farm 2 | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Carelton, Carlisle, Cumbria. CA4 0AE | Cumbria | North West | England |  | 343890 | 552215 | Carlisle City Council | 11/0597 | [5 empty] | 2011-07-15 |  | 2011-11-11
B0449 | 2827 | 2013-07-26 | Polar Energy (Finlarg) Ltd | Frawney Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Frawney Wind Farm In Field 1020M North Of Over Finlarg Farm Over Finlarg Lumleyden | Tayside | Scotland | Scotland |  | 341665 | 741770 | Angus Council | 12/00577/EIAL | [5 empty] | 2012-06-14 | 2013-06-07
B0451 | 2828 | 2012-12-07 | Green Cat Renewables | Clatto Farm Turbines | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Appeal Refused | Application Refused | Clatto Farm Cupar Fife KY15 7TG | Fife | Scotland | Scotland |  | 334844 | 706448 | Fife Council | 10/01469/EIA | 12/00052/REF |  |  |  |  | 2010-05-19 |  | 2012-04-18 |  |  | 2012-11-22
B0484 | 2830 | 2012-08-24 | Brett Martin Ltd | Wind Turbine 1 | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | 24 ROUGHFORT ROAD MALLUSK NEWTOWNABBEY BT36 4RB Northern Ireland | Co. Antrim | Northern Ireland | Northern Ireland |  | 141041 | 539963 | Northern Ireland Planning Service | U/2009/0250/F | [5 empty] | 2009-06-02 | [6 empty] | 2010-02-15 | [5 empty] | 2011-05-30
B0626 | 2839 | 2013-02-26 | Private Developer | Clochnahill Wind Farm | Wind Onshore |  |  | 5.2 | n/a |  |  |  | 1.3 | 4 |  | n/a | Operational | Operational | Clochnahill, Stonehaven AB39 2XY | Grampian | Scotland | Scotland |  | 382413 | 782503 | Aberdeenshire Council | APP/2006/3026 | [5 empty] | 2006-07-27 | [6 empty] | 2009-08-05 | [5 empty] | 2012-01-20
B0632 | 2840 | 2016-04-29 | Eneco / ScottishWater | Macritch Hill Wind Farm | Wind Onshore |  |  | 59.4 | n/a |  |  |  | 3 | 18 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Backwater Reservoir near Kirriemuir in Angus | Tayside | Scotland | Scotland |  | 325500 | 760500 | Scottish Government (S36) | [6 empty] | 2015-01-14 | 2016-04-28
B0654 | 2845 | 2017-10-31 | West Coast Energy | Crossburns Wind Farm | Wind Onshore |  |  | 75 | n/a |  |  |  | 3 | 25 |  | n/a | Appeal Refused | Application Refused | Urlar Estate, which is 4km southwest of Aberfeldy | Perth and Kinross | Scotland | Scotland |  | 283745 | 746530 | Scottish Government (S36) | EC00002093 | WIN-340-1 |  |  |  |  | 2014-10-01 |  | 2017-10-06 | 2015-11-19 |  | 2017-10-06
B0705 | 2847 | 2019-03-26 | Brookfield Renewable UK | Altercannoch Wind Farm | Wind Onshore |  |  | 27.7 | n/a |  |  |  | 3.4 | 8 | 131 | n/a | Appeal Refused | Application Refused | Altercannoch B7027, Main Street, Barrhill-Council Boundary, South From Barrhill, Barrhill, Girvan | Strathclyde | Scotland | Scotland | KA26 0QT | 224500 | 580000 | South Ayrshire Council | 15/01484/APPM | PPA-370-2066 |  |  |  |  | 2015-12-22 |  | 2017-11-16 | 2018-02-15 |  | 2019-03-01
B0710 | 2848 | 2017-04-04 | Coriolis Energy / ESB | Lower Alt Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3.5 | 12 | 136.5 | n/a | Planning Permission Refused | Application Refused | Land To The West Cabin Lane, Great Altcar, Liverpool | Lancashire | North West | England | L31 4LT | 334322 | 404502 | West Lancashire Borough Council | 2015/1055/FUL | [5 empty] | 2015-12-14 |  | 2016-11-11
B0771 | 2856 | 2013-07-04 | Macphie Of Glenbervie Ltd | Droop Hill Wind Farm | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Stonehaven AB39 3YA | Grampian | Scotland | Scotland |  | 375701 | 781631 | Aberdeenshire Council | APP/2006/3278 | [5 empty] | 2006-08-30 | 2013-03-25
B0778 | 2858 | 2020-01-15 | WilloWind Energy | Gass Wind Farm | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 | 126.5 | n/a | Planning Permission Granted | Awaiting Construction | Land to the north east of Glenluce | Dumfries and Galloway | Scotland | Scotland |  | 225226 | 566406 | Dumfries and Galloway Council | 14/P/1/0674 | [5 empty] | 2014-11-25 | [6 empty] | 2015-08-26
B0779 | 2859 | 2020-03-11 | Muirhall Energy (previously Kilmac Energy) | Glen Ullinish Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3 | 14 | 119 | n/a | Planning Permission Granted | Awaiting Construction | Land 1800M SE Of Balmenach, , Glen Ullinish, Struan, Isle Of Skye, Highlands, IV56 8F | Highland | Scotland | Scotland |  | 134850 | 842440 | Highland Council | 14/03964/FUL | [5 empty] | 2014-10-28 | [6 empty] | 2015-03-24
B0782 | 2860 | 2019-08-13 | Green Cat Renewables | Strathallan Wind Farm | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 | 93 | n/a | Appeal Granted | Awaiting Construction | Ld 900 Metres NE Of Greenacres, Braco, Strathallan Wind Farm, Dunblane | Perth and Kinross | Scotland | Scotland | FK15 9LN | 281033 | 713188 | Perth and Kinross Council | 15/01484/FLM | PPA-340-2110 |  |  |  |  | 2015-10-12 |  | 2017-04-12 | 2017-07-07 |  |  | 2019-01-15 | 2019-01-15 |  |  |  | 2022-01-15
B0793 | 2862 | 2013-10-03 | Skeabrae Renewables Ltd | Skeabrae Wind Energy Project | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | RAF Skeabrae, the redundant military aerodrome located west of Dounby in the West Mainland of Orkney | Orkney Islands | Scotland | Scotland |  | 327365 | 1020270 | Orkney Islands Council | 12/599/TPP | [5 empty] | 2012-08-15 | 2013-09-03
B0797 | 2865 | 2013-10-08 | Private Developer | Troywood Wind Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Troywood St Andrews Fife KY16 8QH | Fife | Scotland | Scotland |  | 355965 | 709247 | Fife Council | 09/02880/FULL | [6 empty] | 2013-10-08
B0823 | 2866 | 2013-08-16 | White Young Green Planning | Ballymena Wind Park Limited | Wind Onshore |  |  | 4.7 | n/a |  |  |  | 2.35 | 2 |  | n/a | Operational | Operational | Michelin Tyre PLC Raceview Road Ballymena BT42 4HZ Northern Ireland | Co. Antrim | Northern Ireland | Northern Ireland |  | 128574 | 562072 | Northern Ireland Planning Service | G/2009/0470/F | [5 empty] | 2009-07-24 | [6 empty] | 2010-04-14 | [5 empty] | 2013-01-24
B0845 | 2867 | 2013-08-16 | Auquhirie Land Company Ltd | St John Hill | Wind Onshore |  |  | 7.65 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | St John Hill Windfarm Near Roadside of Kinneff, Stonehaven | Grampian | Scotland | Scotland | AB39 2UE | 383502 | 778054 | Aberdeenshire Council | APP/2008/2570 | [5 empty] | 2008-07-10 | [6 empty] | 2009-12-10 | [5 empty] | 2013-03-07
B0895 | 2873 | 2020-02-27 | Njord Energy | Bryn Blaen Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 | 100 | n/a | Under Construction | Under Construction | land north of the village of Llangurig in Powys | Powys | Wales | Wales | SY18 6SL | 291676 | 281370 | Powys County Council | P/2014/1102 | APP/T6850/A/15/3133966 |  |  |  |  | 2014-12-04 |  |  | 2015-11-26 |  |  | 2016-08-23 | 2016-08-23 |  |  |  | 2021-08-23 | 2017-06-15
C0006 | 2874 | 2012-09-24 | Private Developer | Chadwick Wind Turbines | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 1.5 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land East of Chadwick's Farm, Lostock Lane, Westhoughton, Bolton, Lancashier BL5 3LX | Greater Manchester | North West | England |  | 364407 | 408553 | Bolton Metropolitan Borough Council | 87494/12 | [5 empty] | 2012-02-06 |  | 2012-06-22
C0065 | 2875 | 2013-04-29 | TCI Renewables | MARCH SEWAGE TREATMENT WORKS - WIND TURBINE | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Anglian Water Authority, Creek Road, March, Cambridgeshire PE15 8RY | Cambridgeshire | Eastern | England |  | 543872 | 299171 | Fenland District Council | F/YR07/0742/F | APP/D0515/A/08/2089046 |  |  |  |  | 2007-07-18 |  | 2008-05-02 |  |  |  | 2009-02-20 | 2009-02-20 |  |  |  |  | 2012-06-25 | 2012-09-01
C0209 | 2876 | 2013-07-03 | Bright Spark Energy | Cromarty Wind Farm | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Permission Refused | Application Refused | Davidston Farm, Eathie Farm, Cromarty, Highlands, IV11 8XX | Highland | Scotland | Scotland |  | 274994 | 864619 | Highland Council | 12/01650/FUL | 13/00010/REFRC |  |  |  |  | 2012-05-22 |  | 2013-01-24
C0232 | 2877 | 2012-09-26 | Pennant Wind Energy Ventures | Burnside Wind Cluster (Second Resubmission) | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | N/West Of Blackhills Farm, Cushnie, Alford, Grampian, AB33 8LQ | Grampian | Scotland | Scotland |  | 351022 | 808117 | Aberdeenshire Council | APP/2012/1695 | [5 empty] | 2012-06-18 |  | 2012-09-13
C0596 | 2879 | 2013-04-05 | Airvolution Energy | GLENSTOCKDALE Wind Turbines | Wind Onshore |  |  | 3 | n/a |  |  |  | 1.5 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | LAND TO SOUTH OF GLENSTOCKDALE SEVERAL, LESWALT | Dumfries and Galloway | Scotland | Scotland |  | 201602 | 560068 | Dumfries and Galloway Council | 12/P/1/0281 | [5 empty] | 2012-09-11 | 2012-11-01
C0656 | 2882 | 2013-02-07 | Private Developer | Coldhome Wind Turbines | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Coldhome, Insch, Grampian, AB52 6LQ | Grampian | Scotland | Scotland |  | 359109 | 830051 | Aberdeenshire Council | APP/2012/3367 | [5 empty] | 2012-10-31 | 2013-01-22
C0729 | 2884 | 2013-07-23 | DM Cargill Ltd | Bogmuir Farm Wind Turbine | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land To The South East of Bogmuir Farm, Fettercairn, Laurencekirk, AB30 1YP | Grampian | Scotland | Scotland |  | 365487 | 770789 | Aberdeenshire Council | APP/2012/3323 | [5 empty] | 2012-10-22 | 2013-04-02
C0826 | 2888 | 2018-04-03 | Greencoat | Brockaghboy Wind Farm - extension | Wind Onshore |  |  | 10 | n/a |  |  |  | 3 | 4 |  | n/a | Operational | Operational | west of Dowlins Bridge. in the townlands of Knockoneill and Dunavenny on the Drumbane Road. 7.5km south of Garvagh | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 87959 | 566906 | Northern Ireland Planning Service | H/2014/0241/F | [5 empty] | 2014-06-25 | [6 empty] | 2015-10-27 |  |  |  | 2018-10-27 | 2016-06-23 | 2017-09-01
C1328 | 2894 | 2013-10-02 | Private Developer | Witton Farm wind cluster | Wind Onshore |  |  | 3 | n/a |  |  |  | 1.5 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land 600M West Of Witton Farm Lethnot Edzell | Tayside | Scotland | Scotland |  | 355356 | 769976 | Angus Council | 13/00257/FULL | [5 empty] | 2013-03-26 | 2013-08-29
C1344 | 2895 | 2015-04-20 | Coriolis Energy | Scotland Corner wind farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Permission Refused | Application Refused | Scotland Corner Wind Farm, North Of St Columb Major, Cornwall | Cornwall | South West | England |  | 194296 | 67599 | Cornwall Council | PA14/08635 | [5 empty] | 2014-09-24 |  | 2015-04-10
C1401 | 2896 | 2017-10-04 | Tresdale Wind Farm | Tresdale Farm wind cluster | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 | 100 | n/a | Planning Permission Refused | Application Refused | Land 760M SE Of Tresdale Farm, Canisbay, Wick | Highland | Scotland | Scotland | KW1 4YH | 335008 | 972288 | Highland Council | 15/01261/FUL | [5 empty] | 2015-05-14 |  | 2017-09-18
C1439 | 2897 | 2013-10-04 | Private Developer | Blinkbonny - resubmission | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | (Blinkbonny Wind Turbines) Land South East Of Whitehill Mellerstain Scottish Borders | Borders | Scotland | Scotland |  | 332715 | 644386 | Scottish Borders Council | 13/00561/FUL | [5 empty] | 2013-06-13 | 2013-09-09
EN00034 | 2902 | 2010-11-03 | EDF Energies Nouvelles | Burnfoot Hill | Wind Onshore |  |  | 26 | n/a |  |  |  | 2 | 13 |  | n/a | Operational | Operational | Burnfoot Hill, Clackmannanshire | Clackmannanshire | Scotland | Scotland |  | 290135 | 703250 | Clackmannanshire Council | 06/00121/FULL | [5 empty] | 2006-03-20 | [6 empty] | 2007-03-28 |  |  |  |  | 2010-08-01 | 2010-10-26
EN00037 | 2903 | 2011-07-04 | Gamesa Energy | Harelaw Renewable Energy Park Wind Turbines | Wind Onshore |  |  | 80 | n/a |  |  |  | 2 | 40 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Harelaw, East Renfrewshire | Strathclyde | Scotland | Scotland |  | 246810 | 654150 | Scottish Government (S36) | 2009/0304/EBC | [6 empty] | 2011-07-04
EN00040 | 2905 | 2008-04-16 | AMEC | Logiealmond | Wind Onshore |  |  | 28 | n/a |  |  |  | 0 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Logiealmond, 13km North West of Perth | Tayside | Scotland | Scotland |  | 299185 | 731470 | Perth and Kinross Council | [7 empty] | 2008-04-16
EN00042 | 2906 | 2008-04-16 | Npower Renewables | Leithope Forest | Wind Onshore |  |  | 70 | n/a |  |  |  | 2 | 48 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Leithope Forest, Scottish Borders | Borders | Scotland | Scotland |  | 374225 | 608740 | Scottish Government (S36) | [7 empty] | 2008-04-16
EN00045 | 2909 | 2009-11-24 | Npower Renewables | Ballindalloch Muir | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.2 | 9 |  | n/a | Planning Permission Refused | Application Refused | Ballindalloch Muir, Balfron, Stirling | Stirling | Scotland | Scotland |  | 257737 | 690570 | Stirling Council | [6 empty] | 2007-12-20 |  | 2009-11-12
EN00060 | 2912 | 2006-04-07 | Atlantic Energy | Gartnagrenach | Wind Onshore |  |  | 24 | n/a |  |  |  | 1 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Gartnagrenach, Argyll and Bute | Strathclyde | Scotland | Scotland |  | 180460 | 659215 | Argyll and Bute Council | [7 empty] | 2006-04-07
EN00061 | 2913 | 2007-04-06 | Unknown | Corriechreive | Wind Onshore |  |  | 30 | n/a |  |  |  | 1 | 30 |  | n/a | Planning Permission Refused | Application Refused | Corriechreive | Strathclyde | Scotland | Scotland |  | 174300 | 653900 | Argyll and Bute Council | 95/05415/DET | [5 empty] | 1995-04-04 |  | 1995-12-12
EN00062 | 2914 | 2009-07-03 | Orkney Sustainable Energy | Gruf Hill | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 0 | 3 |  | n/a | Planning Permission Refused | Application Refused | Gruf Hill, Orkney | Orkney Islands | Scotland | Scotland |  | 332500 | 1006500 | Orkney Islands Council | 02/410/PPF | [5 empty] | 2002-10-17 |  | 2003-03-01
EN00063 | 2915 | 2006-04-27 | Private Developer | Blinkbonny Heights | Wind Onshore |  |  | 5 | n/a |  |  |  | 1 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Blinkbonny Heights, Scottish Borders | Borders | Scotland | Scotland |  | 367580 | 639180 | Scottish Borders Council | [7 empty] | 2006-04-27
EN00070 | 2918 | 2010-01-04 | Novera / West Coast Energy | Mount Boy | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Appeal Refused | Application Refused | Mountboy, Rossie Moor, Angus | Tayside | Scotland | Scotland |  | 366120 | 752345 | Angus Council | 07/00050/FUL | [5 empty] | 2007-01-10 |  | 2009-05-27 |  |  | 2009-06-26
EN00083 | 2919 | 2009-07-06 | Ecotricity | Inner Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | Inner Farm, Stoddens Lane, Edithmead, Highbridge, Sedgemoor | Somerset | South West | England |  | 332600 | 150148 | Sedgemoor District Council | 12/06/00007 | [5 empty] | 2006-03-22 |  | 2006-08-08
EN00084 | 2920 | 2011-09-27 | H J Banks and Co Ltd | Knoweside Hill | Wind Onshore |  |  | 19.5 | n/a |  |  |  | 1 | 15 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Knoweside Hill, Near Dunure | Strathclyde | Scotland | Scotland |  | 226720 | 613370 | South Ayrshire Council | [7 empty] | 2011-09-27
EN00102 | 2921 | 2009-07-06 | Yorkshire Water | Chelker Reservoir | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 0.3 | 4 |  | n/a | Operational | Operational | Land adjacent to Chelker Reservoir, nr Skipton | North Yorkshire | Yorkshire and Humber | England |  | 405730 | 451820 | Craven District Council | 5/24/96/A/EA | [12 empty] | 1991-07-12 | [5 empty] | 1992-06-01
EN00105 | 2922 | 2010-06-09 | Green Cat Renewables | Strath of Brydock | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Operational | Operational | Strath of Brydock Alvah Banff | Grampian | Scotland | Scotland |  | 365391 | 859727 | Aberdeenshire Council | APP/2006/3227 | [5 empty] | 2006-08-29 | [6 empty] | 2008-02-25 | [5 empty] | 2009-06-01
EN00106 | 2923 | 2010-10-28 | Green Cat Renewables | House O'Hill | Wind Onshore |  |  | 5 | n/a |  |  |  | 1.67 | 3 |  | n/a | Operational | Operational | Land Around House O'Hill Fraserburgh | Grampian | Scotland | Scotland |  | 397560 | 859107 | Aberdeenshire Council | APP/2008/1722 | [5 empty] | 2008-05-15 | [6 empty] | 2009-06-05 |  |  |  |  | 2009-08-01 | 2010-10-04
EN00110 | 2925 | 2015-12-17 |  | Ovenden Moor | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 0.4 | 23 |  | n/a | Decommissioned | Decommissioned | Ovenden Moor, Wainstalls, Halifax | West Yorkshire | Yorkshire and Humber | England |  | 404260 | 430870 | Calderdale Metropolitan Borough Council | 91/00026 | [12 empty] | 1992-07-02 | [5 empty] | 1993-06-01
EN00115 | 2926 | 2010-06-09 | Gamesa Energy | Trane Renewable Energy Park | Wind Onshore |  |  | 11.9 | n/a |  |  |  | 0.85 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land to the north of Gilfach Farm, off the Heathlands, Gilfach Goch | Mid Glamorgan | Wales | Wales |  | 298736 | 189408 | Rhondda Cynon Taff County Borough Council | 06/0790 | [6 empty] | 2010-06-09
EN00122 | 2927 | 2010-07-29 | EF Energy | Owenreagh Extension | Wind Onshore |  |  | 5.1 | n/a |  |  |  | 0.85 | 6 |  | n/a | Operational | Operational | Land near Craignagapple 10km South East of Strabane, County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 57401 | 558796 | Northern Ireland Planning Service | J/2004/1015/F | [5 empty] | 2004-01-01 | [6 empty] | 2005-10-01 | [5 empty] | 2008-08-01
EN00123 | 2928 | 2012-08-16 | Munich Re (previously Wind Prospect) | Bagmoor | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | 2km East of Flixborough | Humberside | Yorkshire and Humber | England |  | 488240 | 415400 | North Lincolnshire Council | [6 empty] | 2005-01-15 | [6 empty] | 2006-04-01 | [5 empty] | 2009-07-01
EN00132 | 2929 | 2010-07-29 | Canavan Associates | Rakelly | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Planning Permission Refused | Application Refused | NW of Bessy Bell, nr Newton Stewart | Co. Tyrone | Northern Ireland | Northern Ireland |  | 51775 | 546334 | Northern Ireland Planning Service | K/2005/2187/F | [5 empty] | 2005-12-01 |  | 2006-11-14
EN00135 | 2930 | 2011-04-27 | Aesica Pharmaceuticals | Aesica Pharmaceuticals (Re-Submission) | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Cramlington, Northumberland | Northumberland | North East | England |  | 426500 | 576500 | Northumberland County Council | B/06/00384/RES | [5 empty] | 2006-05-20 |  | 2007-02-01
EN00136 | 2931 | 2010-01-25 |  | Hillhead of Auquhirie | Wind Onshore |  |  | 6 | n/a |  |  |  | 0 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Hillhead of Auquhirie, Stonehaven | Grampian | Scotland | Scotland |  | 328500 | 785500 | Aberdeenshire Council | APP/2006/1777 | [5 empty] | 2006-05-09 | 2008-10-02
EN00137 | 2932 | 2009-12-04 | Croda Chemicals | Croda Chemicals Europe | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Operational | Operational | Croda International Plc Cowick Hall Snaith Goole East Yorkshire DN14 9AA | Humberside | Yorkshire and Humber | England |  | 465670 | 421110 | East Riding of Yorkshire Council | 16999M | [5 empty] | 2006-04-25 | [6 empty] | 2006-10-16 | [5 empty] | 2008-10-01
EN00138 | 2933 | 2007-04-11 | Nuon Renewables | Brownrigg Hall Wind Farm | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | Brownrigg Hall Edderside Cumbria | Cumbria | North West | England |  | 311000 | 544000 | Allerdale Borough Council | [6 empty] | 2006-07-11 |  | 2007-04-05
EN00141 | 2935 | 2009-10-23 |  | Eastman Chemicals, Workington | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Eastman Chemical Workington Ltd, Siddick, Workington, Cumbria, CA14 1LG | Cumbria | North West | England |  | 300775 | 531765 | Allerdale Borough Council | 2/2003/0721 | 2/2003/0721/A |  |  |  |  | 2003-06-24 |  | 2003-09-08 | [9 empty] | 2006-08-01 | 2006-10-01
EN00145 | 2936 | 2013-10-08 |  | Tooter Hill and Hogshead Hill | Wind Onshore |  |  | 3 | n/a |  |  |  | 0 | 9 |  | n/a | Planning Permission Refused | Application Refused | Tooter Hill Brandwood | Lancashire | North West | England |  | 389200 | 423100 | Rossendale Borough Council | [6 empty] | 1999-01-01 |  | 1999-06-15
EN00148 | 2937 | 2009-08-06 | BroomBank Farm | Broombank Farm | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Broombank Farm, Nairn | Highland | Scotland | Scotland |  | 292500 | 855500 | Highland Council | 06/00124/FUL | [5 empty] | 2006-07-01 |  | 2008-11-01
EN00153 | 2938 | 2010-12-07 | Npower Renewables | Lindhurst Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Operational | Operational | Lindhurst, South of Mansfield | Nottinghamshire | East Midlands | England |  | 456880 | 358150 | Ashfield District Council | 06/01014/FULM | [5 empty] | 2006-06-01 | [6 empty] | 2007-09-21 |  |  |  |  | 2010-01-01 | 2010-11-04
EN00158 | 2940 | 2010-06-09 | Scotia Wind Ltd | Craigengelt | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Operational | Operational | Craigengelt Hill, Stirling | Stirling | Scotland | Scotland |  | 272451 | 686495 | Stirling Council | 06/01052/DET | [5 empty] | 2006-12-01 | [6 empty] | 2008-02-12 |  |  |  |  | 2009-05-01 | 2010-03-31
EN00163 | 2941 | 2010-12-06 | Npower Renewables | Toft Hill Windfarm | Wind Onshore |  |  | 19 | n/a |  |  |  | 0 | 7 |  | n/a | Appeal Refused | Application Refused | near village of Gindon, approx 10km SW of Berwick upon Tweed | Northumberland | North East | England |  | 390657 | 643657 | Northumberland County Council | 06/B/1001 | [5 empty] | 2006-11-15 |  | 2008-03-27 |  |  | 2008-10-19
EN00165 | 2942 | 2010-06-09 | Yorkshire Water | Saltend Wind Turbine | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Operational | Operational | Hull Waste Water Treatment Works, Hull Road, Saltend, Hull, HU12 | Humberside | Yorkshire and Humber | England |  | 516400 | 429000 | East Riding of Yorkshire Council | 05/08754/STPLF | [5 empty] | 2005-12-07 | [6 empty] | 2006-03-06 | [5 empty] | 2007-11-01
EN00166 | 2943 | 2017-08-23 | Yorkshire Water | Loftsome Bridge | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1 | 2 |  | n/a | Operational | Operational | Loftsome Bridge Water Treatment Works, Water Treatment Works Acc Rd, Barmby On The Marsh, East Riding Of Yorkshire, DN14 6ET | Humberside | Yorkshire and Humber | England |  | 470140 | 429460 | Selby District Council | 06/05245/STPLF | [5 empty] | 2006-06-28 | [6 empty] | 2007-01-31 | [5 empty] | 2008-02-01
EN00167 | 2944 | 2009-10-23 | Nissan Manufacturing UK | Nissan Wind Farm | Wind Onshore |  |  | 3.96 | n/a |  |  |  | 0.66 | 6 |  | n/a | Operational | Operational | Nissan plant, Sunderland | Tyne and Wear | North East | England |  | 433385 | 557810 | Sunderland City Council | [6 empty] | 2004-10-20 | [6 empty] | 2005-08-01 | [5 empty] | 2005-11-01
EN00168 | 2945 | 2011-12-02 | Nuon Renewables | Airfield Farm (Podington) | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2 | 9 |  | n/a | Planning Permission Refused | Application Refused | Airfield Farm, adjacent to Santa Pod raceway, Podington, Bedfordshire | Bedfordshire | Eastern | England | NN29 7XA | 495500 | 260500 | Bedford Borough Council | 05/02589/FUL | [5 empty] | 2005-10-20 |  | 2007-07-06
EN00169 | 2946 | 2011-06-29 | E.ON UK | Aire & Calder Wind Farm | Wind Onshore |  |  | 45 | n/a |  |  |  | 3 | 15 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Nr Sneid, land south of M62, north of Aire & Calder navigation, nr Pollington | Humberside | Yorkshire and Humber | England |  | 463440 | 419680 | East Riding of Yorkshire Council | 05/05933/STPLFE | [5 empty] | 2005-08-01 | 2010-11-25
EN00170 | 2947 | 2011-04-06 | Npower Renewables | Mynydd y Gwair Wind Farm | Wind Onshore |  |  | 57 | n/a |  |  |  | 3 | 19 |  | n/a | Appeal Refused | Application Refused | Mynydd y Gwair, Swansea | West Glamorgan | Wales | Wales |  | 265400 | 208320 | DECC (S36) | 2008/1781 | [5 empty] | 2008-09-02 |  | 2010-01-12 |  |  | 2011-02-21
EN00171 | 2948 | 2015-01-09 | Wind Electric | Delabole Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 0.4 | 10 |  | n/a | Decommissioned | Decommissioned | Delabole, Cornwall | Cornwall | South West | England |  | 208620 | 85190 | Cornwall Council | [19 empty] | 1991-11-01
EN00173 | 2949 | 2010-01-08 |  | Aesica Pharmaceuticals Limited | Wind Onshore |  |  | 6 | n/a |  |  |  | 0 | 2 |  | n/a | Planning Permission Refused | Application Refused | Windmill Industrial Estate , Shotton Lane , Cramlington , Northumberland | Northumberland | North East | England | NE23 3JL | 424025 | 578700 | Northumberland County Council | 06/00275/FUL | [5 empty] | 2006-05-22 |  | 2006-08-25
EN00174 | 2950 | 2017-11-02 | Nuon | Parc Cynog Extension | Wind Onshore |  |  | 8.4 | n/a |  |  |  | 1.3 | 6 |  | n/a | Operational | Operational | Parc Cynog, Pendine, Carms | Dyfed | Wales | Wales |  | 225230 | 209760 | Carmarthenshire County Council | W/12246 | [5 empty] | 2006-02-02 | [6 empty] | 2007-07-19 | [5 empty] | 2009-11-01
EN00175 | 2951 | 2009-04-23 | A7 Energy | Bogside | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 1 | 2 |  | n/a | Planning Permission Refused | Application Refused | Bogside Farm, near Gair Reservoirs, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 285695 | 652845 | South Lanarkshire Council | CL/05/0513 | [5 empty] | 2005-07-26 |  | 2008-06-23
EN00177 | 2952 | 2009-05-06 | Fenpower Limited | Ranson Moor (phase 1) | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Land North of ransonmoor Farm Benwick Road Doddington Cambs, Cambridgeshire, PE15 0TY | Cambridgeshire | Eastern | England |  | 537950 | 292470 | Fenland District Council | F/YR03/0990/F | [5 empty] | 2003-07-31 | [6 empty] | 2005-04-25 |  |  |  |  | 2006-09-01 | 2007-05-01
EN00178 | 2953 | 2018-06-04 | EcoGen Projects / Fenpower | Ranson Moor Wind Farm (Phase 2) | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Land North East Of Ransonmoor Farm Benwick Road Doddington March Cambridgeshire, PE15 0TY | Cambridgeshire | Eastern | England |  | 538360 | 292250 | Fenland District Council | F/YR06/0594/F | [5 empty] | 2006-05-18 | [6 empty] | 2007-02-23 | [5 empty] | 2007-05-01
EN00182 | 2954 | 2006-09-07 | H Buckley & Sons Ltd | Pool Hill | Wind Onshore |  |  | 2 | n/a |  |  |  | 1 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Pool Hill, Pool Hill Lane, Denby Dale, Huddersfield | West Yorkshire | Yorkshire and Humber | England |  | 424646 | 408845 | Kirklees Council | 2005/62/93609 | [5 empty] | 2005-08-15 | 2006-03-16
EN00184 | 2955 | 2014-12-29 | ESBI | West Durham Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 2 | 12 |  | n/a | Operational | Operational | Land to the north of Tow Law, Co Durham | Durham | North East | England |  | 412000 | 541000 | Durham County Council | 1/2005/0095/DMFP | [5 empty] | 2005-01-01 | [6 empty] | 2005-12-01 | [5 empty] | 2009-05-01
EN00185 | 2956 | 2010-06-09 | Renewable Energy Systems (RES) | Dyffryn Brodyn Wind Farm | Wind Onshore |  |  | 5.5 | n/a |  |  |  | 0.5 | 11 |  | n/a | Operational | Operational | Dyffryn Brodyn Wind Farm, near Llanboidy, north of St Clears | Dyfed | Wales | Wales |  | 221900 | 226800 | Carmarthenshire County Council | [13 empty] | 1994-01-01 | [5 empty] | 1994-12-01
EN00196 | 2957 | 2013-10-08 |  | Gortgall | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2 | 8 |  | n/a | Planning Permission Refused | Application Refused | Belmore Mountain, townland of Gortgall in the parish of Boho, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 29418 | 504979 | Northern Ireland Planning Service | L/2006/1197 | [5 empty] | 2006-03-01 |  | 2009-07-21
EN00199 | 2958 | 2010-07-29 |  | Mullaghturk Mountain | Wind Onshore |  |  | 10.5 | n/a |  |  |  | 1.5 | 7 |  | n/a | Planning Permission Refused | Application Refused | Mullaghturk Mountain - Approximately 11km south west of Draperstown and 16km north west of Cookstown. | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 81000 | 541911 | Northern Ireland Planning Service | H/2004/1395/F | [5 empty] | 2004-12-23 |  | 2007-10-25
EN00200 | 2959 | 2013-10-08 | Fermanagh Wind Energy | Old Barr | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Old Barr Derrygonnelly Co. Fermanagh | Co. Down | Northern Ireland | Northern Ireland |  | 131721 | 506525 | Northern Ireland Planning Service | L/2004/2483/F | [6 empty] | 2013-10-08
EN00203 | 2960 | 2011-04-01 | Antrim Wind Energy | Elginny Hill | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Broughshane Ballymena Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 130502 | 567869 | Northern Ireland Planning Service | G/2006/0754/F | [5 empty] | 2006-09-21 | 2011-01-17
EN00205 | 2961 | 2006-07-13 | Broadview Renewables | Warwick Hall | Wind Onshore |  |  | 12 | n/a |  |  |  | 0 | 6 |  | n/a | Planning Permission Refused | Application Refused | Warwick Hall Winscales | Cumbria | North West | England |  | 313265 | 542990 | Allerdale Borough Council | [8 empty] | 2006-07-13
EN00214 | 2962 | 2013-10-08 | Npower Renewables | Nunn Wood | Wind Onshore |  |  | 24 | n/a |  |  |  | 0 | 12 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Wind Farm Between Harrold Road and London Road Harrold Road, Bozea, Wellingborough | Buckinghamshire | South East | England |  | 490500 | 255500 | Milton Keynes Council | WP/2006/0474/FM | [6 empty] | 2013-10-08
EN00218 | 2963 | 2008-11-06 | Ecotricity | City of Manchester Stadium | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Abandoned | Abandoned | City of Manchester Stadium, Manchester | Greater Manchester | North West | England |  | 386670 | 398897 | Manchester City Council | [6 empty] | 2005-09-14 | [6 empty] | 2006-09-29
EN00219 | 2964 | 2009-03-26 | Asda | Asda Grangemouth Depot | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Refused | Application Refused | West Mains and Bankside, Falkirk | Falkirk | Scotland | Scotland |  | 290430 | 681125 | Falkirk Council | P/07/0084/FUL | [5 empty] | 2007-02-07 |  | 2007-12-20
EN00224 | 2965 | 2009-10-05 | Green Cat Renewables | North Red Bog | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Operational | Operational | North Redbog Strichen Aberdeenshire AB43 6RQ | Grampian | Scotland | Scotland |  | 399555 | 855289 | Aberdeenshire Council | APP/2007/2794 | [5 empty] | 2007-07-06 | [6 empty] | 2008-03-07 | [5 empty] | 2008-06-23
EN00228 | 2967 | 2006-10-09 | Scottish and Southern Energy (SSE) | Glen Tarken | Wind Onshore |  |  | 30 | n/a |  |  |  | 0 | 20 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Glen Tarken Comrie Highlands | Tayside | Scotland | Scotland |  | 266870 | 726090 | Perth and Kinross Council | [7 empty] | 2006-10-09
EN00238 | 2968 | 2017-12-04 | Gravis Capital Management | Milton Keynes Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Operational | Operational | Petsoe Manor Farm, Near Emberton | Buckinghamshire | South East | England |  | 490000 | 249090 | Milton Keynes Council | 06/01349/FULEIS | [5 empty] | 2006-08-18 | [6 empty] | 2008-01-14 |  |  |  |  | 2010-04-01 | 2010-09-25
EN00266 | 2970 | 2006-11-28 | E.ON UK | Elsham Wind Farm | Wind Onshore |  |  | 30 | n/a |  |  |  | 0 | 15 |  | n/a | Appeal Refused | Application Refused | North of Elsham Industrial Estate | Humberside | Yorkshire and Humber | England |  | 505840 | 414380 | North Lincolnshire Council | WF/2004/1414 | GBC4/1987/0066 PA/2003/1922 |  |  |  |  | 2004-08-12 |  | 2005-06-24 |  |  | 2006-11-23
EN00278 | 2972 | 2018-09-20 | Wind Energy | Forse Wind Farm | Wind Onshore |  |  | 60 | n/a |  |  |  | 0 | 0 |  | n/a | Abandoned | Abandoned |  | Highland | Scotland | Scotland | KW3 6BX | 322170 | 934311 | Scottish Government (S36)
EN00279 | 2973 | 2018-09-20 | Wind Energy | Glen Calvie Wind Farm, Ardgay | Wind Onshore |  |  | 69 | n/a |  |  |  | 0 | 0 |  | n/a | Abandoned | Abandoned |  | Highland | Scotland | Scotland |  | 246550 | 887550 | Scottish Government (S36)
EN00281 | 2974 | 2018-09-20 | Wind Energy | Hanna Wind Farm | Wind Onshore |  |  | 81 | n/a |  |  |  | 2.7 | 30 |  | n/a | Abandoned | Abandoned | Mile Hill, near Glen Quharity | Tayside | Scotland | Scotland | DD8 5LR | 336170 | 753405 | Scottish Government (S36)
EN00284 | 2975 | 2018-09-20 | Infinergy | Hill of Fare Wind Farm | Wind Onshore |  |  | 150 | n/a |  |  |  | 0 | 0 |  | n/a | Abandoned | Abandoned | AB51 7LX | Grampian | Scotland | Scotland |  | 368550 | 802550 | Scottish Government (S36)
EN00287 | 2976 | 2018-09-20 | Wind Energy | Laudale Wind Farm | Wind Onshore |  |  | 75 | n/a |  |  |  | 0 | 0 |  | n/a | Abandoned | Abandoned | PH33 7AF | Highland | Scotland | Scotland |  | 174550 | 759550 | Scottish Government (S36)
EN00291 | 2978 | 2018-09-20 | Scottish and Southern Energy (SSE) | North Nesting Wind, Shetland | Wind Onshore |  |  | 250 | n/a |  |  |  | 0 | 0 |  | n/a | Abandoned | Abandoned | Old Schoolhouse, Brettabister, Shetland | Shetland | Scotland | Scotland |  | 445550 | 1159550 | Scottish Government (S36)
EN00303 | 2980 | 2010-06-09 | Talladh an Bheith & Craiganour Estates | Rannoch Wind Farm | Wind Onshore |  |  | 75 | n/a |  |  |  | 2.5 | 30 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Craiganour Estate 9km North-West of Kinloch Rannoch and 22km South of Dalwhinnie | Tayside | Scotland | Scotland |  | 257050 | 763350 | Scottish Government (S36) | [7 empty] | 2010-06-09
EN00315 | 2983 | 2010-05-21 |  | Broom Hill Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Broom Hill Farm Wolsingham Road Stanley Crook Durham | Durham | North East | England |  | 415500 | 539500 | Durham County Council | 3/2006/0087 | [5 empty] | 2006-02-02 | [6 empty] | 2006-12-08 | [5 empty] | 2009-02-16
EN00316 | 2984 | 2010-12-07 | Cornwall Light and Power | Beech Tree Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 0 | 3 |  | n/a | Appeal Refused | Application Refused | Beech Tree Farm , Goveton , Kingsbridge , TQ7 2DT (Land between Goveton and A381) | Devon | South West | England |  | 275500 | 46500 | South Hams District Council | 08_19/2525/07/F | [5 empty] | 2007-11-30 |  | 2008-02-14 |  |  | 2009-04-08
EN00318 | 2985 | 2011-04-05 | Princes soft drinks distribution | Princes Soft Drinks Distribution | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Princes Limited , Weaverthorpe Road , Bradford , West Yorkshire , BD4 6SX | West Yorkshire | Yorkshire and Humber | England |  | 419195 | 429866 | Bracknell Forest Borough Council | 08/02973/FUL | 09/00172/APPFUL |  |  |  |  | 2008-05-01 |  | 2009-05-18
EN00319 | 2986 | 2017-12-04 | Gravis Capital Management | Winscales Moor | Wind Onshore |  |  | 5.95 | n/a |  |  |  | 0.85 | 7 |  | n/a | Operational | Operational | Winscales Moor | Cumbria | North West | England |  | 303500 | 528500 | Allerdale Borough Council | 2/2006/1321 | [5 empty] | 2006-10-01 | [6 empty] | 2007-06-20 |  |  |  |  | 2008-12-01 | 2009-05-01
EN00330 | 2988 | 2011-09-13 | SLP Energy | Wind Farm Africa Alive | Wind Onshore |  |  | 4.1 | n/a |  |  |  | 2.05 | 2 |  | n/a | Operational | Operational | Whites Lane Kessingland Lowestoft Suffolk NR33 7T | Suffolk | Eastern | England |  | 651905 | 286095 | Waveney District Council | DC/06/1401/FUL | APP/002/2008 |  |  |  |  | 2006-12-18 |  | 2008-01-28 |  |  |  | 2008-05-01 | 2008-05-01 |  |  |  |  | 2011-05-01 | 2011-06-01
EN00331 | 2989 | 2012-04-05 |  | Slatbeg | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Planning Permission Refused | Application Refused | Fardross Townland, (Slatbeg) Fardross Mountains, Clogher | Co. Tyrone | Northern Ireland | Northern Ireland |  | 61563 | 510022 | Northern Ireland Planning Service | M/2006/1754/F | [5 empty] | 2006-12-15 |  | 2009-02-09
EN00332 | 2990 | 2011-04-04 | Wheel House Energy | Rathsherry | Wind Onshore |  |  | 11.7 | n/a |  |  |  | 1.3 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land in the townland of Rathsherry, West of Tullymore Road and North and South of Longmore Road, Broughshane. | Co. Antrim | Northern Ireland | Northern Ireland |  | 130136 | 568929 | Northern Ireland Planning Service | G/2006/0842 | [5 empty] | 2006-12-15 | 2011-02-16
EN00337 | 2991 | 2018-04-04 | Midefearn Renewables | Beinn Tharsuinn Extension (Beinn nan Oighrean) | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Beinn Tharsuinn Wind Farm, Edderton, Highland. | Highland | Scotland | Scotland |  | 266440 | 879840 | Highland Council | 07/00026/FULSU | [5 empty] | 2007-01-19 | [6 empty] | 2008-12-11 | [5 empty] | 2009-07-01
EN00341 | 2994 | 2008-12-05 | Ecotricity | Swaffham Extension | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Permission Refused | Application Refused | East Of West Acre Road, Swaffham, Norfolk | Norfolk | Eastern | England |  | 581400 | 310600 | Breckland Council | 3/07/0314/F | [5 empty] | 2007-04-27 |  | 2008-03-06
EN00343 | 2995 | 2008-04-22 | Npower Renewables | Hoff Moor | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Hoff Moor Appleby | Cumbria | North West | England |  | 363680 | 520480 | Eden District Council | [6 empty] | 2003-01-01 |  | 2007-02-22
EN00347 | 2997 | 2010-01-22 | Community Windpower | Millour Hill Community Windfarm | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Planning Permission Refused | Application Refused | Baidland Hill, North Ayrshire | Strathclyde | Scotland | Scotland |  | 225843 | 652080 | North Ayrshire Council | 06/01007/PP | [5 empty] | 2006-11-01 |  | 2009-01-13
EN00349 | 2998 | 2010-06-09 | Energiekontor UK | Withernwick (withdrawn) | Wind Onshore |  |  | 25 | n/a |  |  |  | 1 | 11 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land South North And North East Homer House Aldbrough Road Withernwick East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 520730 | 440330 | East Riding of Yorkshire Council | 07/02271/STPLFE | [5 empty] | 2007-04-05 | 2007-10-17
EN00354 | 2999 | 2010-05-21 | Green Cat Renewables | St John's Well | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | St John's Wells Fyvie Formartine Aberdeenshire | Grampian | Scotland | Scotland |  | 380570 | 837410 | Aberdeenshire Council | APP/2006/3851 | [5 empty] | 2006-10-02 | [6 empty] | 2007-03-20 | [5 empty] | 2009-07-15
EN00357 | 3001 | 2008-12-11 | Laughton Wind Farm | Laughton Wind Farm (Resubmission) | Wind Onshore |  |  | 28 | n/a |  |  |  | 0 | 8 |  | n/a | Appeal Refused | Application Refused | Mount Pleasant Farm , Scotton Rd , (1km east of Laughton and 8km northeast of the centre of Gainsborough) , Loughton | Lincolnshire | East Midlands | England |  | 487000 | 397000 | West Lindsey District Council | M06/P/0280 | APP/N2535/A/07/2048474/NWF |  |  |  |  | 2006-03-21 |  | 2007-11-29 |  |  | 2008-04-17
EN00359 | 3002 | 2012-03-15 | Npower Renewables | Hellrigg Wind farm - Resubmission | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.5 | 4 |  | n/a | Operational | Operational | Park Head Farm Silloth Carlisle | Cumbria | North West | England |  | 313585 | 551775 | Allerdale Borough Council | 2/2007/0076 | [5 empty] | 2007-01-29 |  | 2007-12-11 | [9 empty] | 2011-05-01 | 2011-09-14
EN00367 | 3004 | 2015-01-09 | REG Windpower (previously Cornwall Light and Power) | Goonhilly Downs - Wind | Wind Onshore |  |  | 5.6 | n/a |  |  |  | 0.4 | 14 |  | n/a | Decommissioned | Decommissioned | Goonhillydowns, Helston, Cornwall | Cornwall | South West | England | TR12 6LQ | 170750 | 20985 | Cornwall Council | [19 empty] | 1993-01-01
EN00372 | 3005 | 2015-01-09 | Scottish Power Renewables | Carland Cross | Wind Onshore |  |  | 6 | n/a |  |  |  | 0.4 | 15 |  | n/a | Decommissioned | Decommissioned | Carland Cross , Mitchell , Truro | Cornwall | South West | England |  | 184500 | 54500 | Cornwall Council | [6 empty] | 1991-05-30 | [6 empty] | 1992-04-29 | [5 empty] | 1992-08-27
EN00380 | 3007 | 2007-04-06 |  | Ballygroggan Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 0 | 30 |  | n/a | Planning Permission Refused | Application Refused | Ballygroggan Farm Machrihanish Campbeltown Argyll PA28 6PZ | Strathclyde | Scotland | Scotland |  | 161985 | 618865 | Argyll and Bute Council | 94/00771/DET | [5 empty] | 1994-07-04 |  | 1995-07-06
EN00382 | 3009 | 2009-12-01 | Argyll Wind Farm Ltd | Black Craig | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 3 | 16 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Black Craig To Blar Buidhe Glenfyne Argyll And Bute | Strathclyde | Scotland | Scotland |  | 211500 | 676500 | Argyll and Bute Council | 06/02000/DET | [6 empty] | 2009-12-01
EN00383 | 3010 | 2010-12-07 | West Coast Energy | Corlarach Hill | Wind Onshore |  |  | 42 | n/a |  |  |  | 0 | 16 |  | n/a | Appeal Refused | Application Refused | Corlarach Hill Argyll and Bute | Strathclyde | Scotland | Scotland |  | 213500 | 674500 | Argyll and Bute Council | 07/00851/DET | [5 empty] | 2007-06-01 |  | 2008-01-29 |  |  | 2009-05-27
EN00385 | 3012 | 2012-03-06 | Wind Prospect & Ridgewind | Kilchattan | Wind Onshore |  |  | 13.6 | n/a |  |  |  | 0.85 | 16 |  | n/a | Appeal Refused | Application Refused | Kilchattan Hill South Kintyre Argyll and Bute | Strathclyde | Scotland | Scotland |  | 172320 | 611990 | Argyll and Bute Council | 08/00138/DET | 11/00010/REFPLA |  |  |  |  | 2008-01-14 |  | 2011-03-28 |  |  | 2012-01-31
EN00388 | 3013 | 2007-04-06 | Enertrag Ltd | Ellands Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 0 | 6 |  | n/a | Planning Permission Refused | Application Refused | Barnwell Road, Hemington, Peterborough | Northamptonshire | East Midlands | England | PE8 5QJ | 508505 | 284075 | East Northamptonshire Council | EN/06/00292/FUL | [5 empty] | 2006-02-20 |  | 2006-05-17
EN00394 | 3015 | 2018-10-03 | Innogy | Bryn titli Windfarm | Wind Onshore |  |  | 9.9 | n/a |  |  |  | 0.45 | 22 |  | n/a | Operational | Operational | Bryntitli Platuae, North of Rhayader Powys | Powys | Wales | Wales |  | 293500 | 275500 | Powys County Council | R42978D | [5 empty] | 1993-03-12 | [6 empty] | 1993-08-09 | [5 empty] | 1994-06-01
EN00398 | 3017 | 2009-07-30 | Marshland Wind Farm Limited | Marshlands Farm | Wind Onshore |  |  | 57 | n/a |  |  |  | 3 | 19 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Marshlands Marshland St James West Norfolk | Norfolk | Eastern | England |  | 554120 | 307670 | DECC (S36) | [7 empty] | 2009-07-30
EN00402 | 3019 | 2011-02-09 | Good Energy Generation | Delabole (Repowering) | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Delebole North Cornwall | Cornwall | South West | England |  | 208800 | 85500 | Cornwall Council | [6 empty] | 2008-04-06 | [6 empty] | 2009-12-12 |  |  |  |  | 2010-07-01 | 2011-02-01
EN00406 | 3021 | 2012-07-04 | REG Windpower (previously Cornwall Light and Power) | Whittlesey | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Operational | Operational | McCain's Food, Funtham's Lane, Whittlesey, Peterborough | Cambridgeshire | Eastern | England | PE7 2PG | 524027 | 297139 | Fenland District Council | F/YR07/0413/F | [5 empty] | 2007-04-13 | [6 empty] | 2007-07-09 |  |  |  |  | 2007-11-01 | 2008-09-03
EN00408 | 3022 | 2009-04-29 | Energy4All | Membury | Wind Onshore |  |  | 2 | n/a |  |  |  | 0 | 1 |  | n/a | Planning Permission Refused | Application Refused | Baydon Meadow , Next to M4 , Membury | Berkshire | South East | England |  | 430455 | 175810 | West Berkshire Council | 07/01018/FUL | [5 empty] | 2007-05-11 |  | 2007-12-11
EN00415 | 3023 | 2009-03-26 |  | Baydon Meadow (Re-Submission) | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1 | 1 |  | n/a | Planning Permission Refused | Application Refused | Baydon Road Lambourne Hungerford Berkshire | Berkshire | South East | England |  | 432302 | 178781 | West Berkshire Council | [6 empty] | 2007-06-01 |  | 2007-12-11
EN00417 | 3024 | 2008-11-25 | Infinergy | Thackson's Well Wind Farm | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Planning Permission Refused | Application Refused | Thackson's Well , Normanton , South Kesteven | Lincolnshire | East Midlands | England | NG23 5EX | 483366 | 342151 | South Kesteven District Council | S07/1661 | S07/1661/01 |  |  |  |  | 2007-11-30 |  | 2008-03-28
EN00418 | 3025 | 2008-09-24 | SLP Energy | Pulham Airfield | Wind Onshore |  |  | 14 | n/a |  |  |  | 0 | 7 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Pulham Airfield Dorset | Norfolk | Eastern | England |  | 619320 | 283865 | South Norfolk Council | [7 empty] | 2008-09-24
EN00423 | 3027 | 2015-12-09 | Community Power Ltd | Bodmin Moor | Wind Onshore |  |  | 50 | n/a |  |  |  | 2.5 | 20 |  | n/a | Appeal Withdrawn | Application Refused | Davidstow , Cornwall | Cornwall | South West | England |  | 214075 | 84165 | Cornwall Council | E1/2008/01432 | 11/00031/REF |  |  |  |  | 2008-07-18 |  | 2010-07-26 | 2011-03-11 | 2011-09-27
EN00424 | 3028 | 2009-07-28 |  | Advanced Manufacturing Research Centre | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Operational | Operational | Advanced Manufacturing Park Wallis Way Catcliffe Rotherham S60 5TZ | South Yorkshire | Yorkshire and Humber | England |  | 441475 | 388039 | Rotherham Metropolitan Borough Council | [6 empty] | 2007-01-01 | [6 empty] | 2007-06-01 | [5 empty] | 2009-01-20
EN00426 | 3029 | 2011-04-04 | Ecotricity | Hendraburnick | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Hendraburnick Davidstow Cornwall | Cornwall | South West | England |  | 212500 | 87500 | Cornwall Council | 2007/01497 | [5 empty] | 2007-06-30 | 2009-07-07
EN00427 | 3030 | 2011-09-13 | Npower Renewables | East Skichen | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1 | 3 |  | n/a | Planning Permission Refused | Application Refused | East Skichen Monikie Nr Dundee Angus | Tayside | Scotland | Scotland |  | 351500 | 741500 | Angus Council | 07/00041/FUL | [5 empty] | 2007-01-29 |  | 2009-12-01
EN00433 | 3032 | 2011-09-12 | West Coast Energy | Berrier Hill | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2 | 9 |  | n/a | Appeal Refused | Application Refused | Near Greystoke | Cumbria | North West | England |  | 340470 | 530845 | Eden District Council | 07/0636 | [5 empty] | 2007-08-10 |  | 2009-01-02 |  |  | 2010-06-28
EN00434 | 3033 | 2009-03-27 | Ecotricity | North Dover Wind Park | Wind Onshore |  |  | 10 | n/a |  |  |  | 0 | 5 |  | n/a | Planning Permission Refused | Application Refused | Archers Court Road, East Langdon Dover | Kent | South East | England |  | 632255 | 145810 | Dover District Council | DOV/07/01148 | [5 empty] | 2007-09-15 |  | 2009-03-16
EN00438 | 3034 | 2013-10-08 | Solutia / Vestas | Solutia UK Ltd | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | Traston Road , Newport , South Wales | Gwent | Wales | Wales | NP14 4XF | 333375 | 185740 | Newport City Council | 08/1412 | [5 empty] | 2008-11-05 | [6 empty] | 2009-01-19 |  |  |  |  | 2009-09-01 | 2009-12-17
EN00439 | 3035 | 2009-03-26 | SLP Energy | Hemsby Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 10 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Hemsby | Norfolk | Eastern | England |  | 648680 | 316325 | Great Yarmouth Borough Council | [6 empty] | 2007-08-20 | 2007-12-01
EN00441 | 3036 | 2011-06-06 | North Harris Community Trust | North Harris Community Trust | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 0.85 | 3 |  | n/a | Abandoned | Abandoned | Ardhasaig Isle of Harris Monan Hebrides | Western Isles | Scotland | Scotland |  | 116360 | 906760 | Comhairle nan Eilean Siar Council | [6 empty] | 2006-07-01 | [6 empty] | 2008-02-18
EN00444 | 3037 | 2011-04-01 | Airtricity | Bagot's Park - resubmission | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Planning Permission Refused | Application Refused | Bagot's Park Abbots Bromley | Staffordshire | West Midlands | England |  | 408500 | 327500 | East Staffordshire Borough Council | PA/26905/010/JI | [5 empty] | 2007-10-31 |  | 2011-04-01
EN00447 | 3039 | 2009-03-23 |  | Westnewton (withdrawn) | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Aspatria | Cumbria | North West | England |  | 313500 | 544500 | Allerdale Borough Council | 2/2007/0909 | [5 empty] | 2007-09-05 | 2008-06-12
EN00449 | 3040 | 2011-09-13 |  | Home Farm (wind) | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Home Farm, Hundreds Lane, Long Sutton, Spalding, Lincolnshire | Lincolnshire | East Midlands | England |  | 545070 | 320700 | South Holland District Council | H10-1390-06 | [5 empty] | 2007-09-12 | 2010-04-30
EN00470 | 3043 | 2007-11-08 | Darnalls Hall Farm | Weston | Wind Onshore |  |  | 6 | n/a |  |  |  | 6 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Village of Weston, Pond Place, off Hatch Lane, half a mile from the Baldock by-pass | Hertfordshire | Eastern | England |  | 524750 | 232250 | North Hertfordshire District Council | [6 empty] | 2006-12-01 | 2006-12-31
EN00476 | 3044 | 2011-10-25 | Nuon Renewables | Nant Bach | Wind Onshore |  |  | 30 | n/a |  |  |  | 2.5 | 12 |  | n/a | Planning Permission Refused | Application Refused | Mwdwl Eithin near Llanfihangel Glyn Myfyr, Conwy | Gwynedd | Wales | Wales |  | 282500 | 368500 | Conwy County Borough Council | 0/32334 | [5 empty] | 2006-09-12 |  | 2007-11-14
EN00479 | 3045 | 2009-02-04 | Brackenbury Infant School | Brackenbury Infant School | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Brackenbury Infant School in Fortuneswell, Portland | Dorset | South West | England |  | 368550 | 73544 | Weymouth and Portland Borough Council | [7 empty] | 2009-02-04
EN00483 | 3046 | 2010-02-03 |  | Manor Park | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Manor Park, Derby Hospital | Derbyshire | East Midlands | England |  | 432525 | 335570 | Derby City Council | [7 empty] | 2010-02-03
EN00491 | 3048 | 2011-06-29 | Flimby Wind Energy Ltd | Land at Flimby Hall Farm | Wind Onshore |  |  | 9.5 | n/a |  |  |  | 3.16 | 3 |  | n/a | Abandoned | Abandoned | Flimby, Maryport, Cumbria | Cumbria | North West | England |  | 302500 | 533500 | Allerdale Borough Council | 2/2007/1255 | [5 empty] | 2007-12-05 | [6 empty] | 2008-10-14
EN00501 | 3050 | 2011-04-06 | Hallam Land Management | High Haswell Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Colliery Farm, Green Lane, High Haswell | Durham | North East | England |  | 436675 | 543772 | Durham County Council | PLAN/2007/0223 | [5 empty] | 2007-04-03 | [6 empty] | 2007-12-18 |  |  |  |  | 2011-01-01 | 2011-03-10
EN00502 | 3051 | 2011-05-15 |  | Bickham Moor Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Appeal Refused | Application Refused | Near Oakford, Mid Devon | Devon | South West | England |  | 286515 | 121510 | Mid Devon District Council | 07/02262/MFUL | APP/Y1138/A/08/2084526 |  |  |  |  | 2007-11-22 |  |  | 2008-09-09 |  | 2010-01-29
EN00504 | 3052 | 2010-05-03 | Tegni Cymru Cyf | Gorsedd BrÃ¢n Wind Fram | Wind Onshore |  |  | 35 | n/a |  |  |  | 2.7 | 13 |  | n/a | Appeal Refused | Application Refused | Clocaenog forest, Denbighshire | Clwyd | Wales | Wales |  | 297500 | 360500 | Denbighshire County Council | 25/2007/0642 | [5 empty] | 2007-05-31 |  | 2008-02-12 |  |  | 2009-11-18
EN00505 | 3053 | 2009-03-30 | Novera Energy | Fleeter Wood Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Abandoned | Abandoned | Fleeter Wood, Land adjacent to West House, Dearham, Maryport, Cumbria, CA15 7LD | Cumbria | North West | England |  | 308700 | 534457 | Allerdale Borough Council | 2/2007/1271 | [5 empty] | 2007-12-17 | [6 empty] | 2009-01-29
EN00515 | 3054 | 2008-05-13 | Parkham Farms and Power Ltd | Sedborough Farm | Wind Onshore |  |  | 2 | n/a |  |  |  | 1 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Sedborough Farm, Parkham, North Devon | Devon | South West | England |  | 239550 | 121750 | Torridge District Council | [7 empty] | 2008-05-13
EN00523 | 3055 | 2011-10-24 | Ecotricity / Next Generation | Silton Wind Park | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Silton, Gillingham | Dorset | South West | England |  | 378380 | 129675 | North Dorset District Council | 2/2008/0661 | [5 empty] | 2008-06-26 | 2009-07-12
EN00534 | 3056 | 2010-10-07 |  | Olympic Park Wind Turbine | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Abandoned | Abandoned | Marshgate Lane in Stratford in the Lower Lea Valley (Eton Manor in the north of the Olympic Park) | Greater London | London | England |  | 537719 | 184055 | Newham London Borough Council | [6 empty] | 2007-01-31 | [6 empty] | 2007-09-27
EN00551 | 3057 | 2009-12-04 | CELTPOWER LTD | Llandinam Windfarm | Wind Onshore |  |  | 31 | n/a |  |  |  | 0.3 | 103 |  | n/a | Operational | Operational | 10km south of Newtown | Powys | Wales | Wales |  | 302840 | 283645 | Powys County Council | [19 empty] | 1993-01-01
EN00553 | 3058 | 2011-09-13 | SLP Energy | Hawthorn Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Is located between the villages of Hawthorn, Murton and Cold Hesledon | Durham | North East | England |  | 440545 | 546075 | Durham County Council | PLAN/2008/0319 | [5 empty] | 2008-04-30 | 2008-09-04
EN00555 | 3059 | 2010-12-06 | Nuon Renewables | Poplar Lane Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Appeal Refused | Application Refused | North Shropshire midway between the villages of Woore and Norton in Hales. | Shropshire | West Midlands | England |  | 372050 | 340110 | Shropshire Council | 08/00831/EIA | 08/00831/EIA |  |  |  |  | 2008-04-01 |  | 2008-09-02 |  |  | 2009-07-15
EN00562 | 3060 | 2009-05-13 | R H Bott & Son Ltd | Benington Wind Farm | Wind Onshore |  |  | 6.75 | n/a |  |  |  | 2.25 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land north of the A602, south-east of Aston, and south-west of Benington | Hertfordshire | Eastern | England |  | 528710 | 223223 | East Hertfordshire District Council | 3/08/0889/FP | [5 empty] | 2008-05-15 |  | 2009-01-14
EN00563 | 3061 | 2012-07-04 | REG Windpower (previously Cornwall Light & Power) | Goonhilly Downs Wind Farm Repower | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | Goonhilly Downs Wind Farm, Bonython Manor, Cury Cross Lanes, Helston, Cornwall, TR12 7BA | Cornwall | South West | England |  | 171000 | 21600 | Cornwall Council | PA07/02103/FM | [5 empty] | 2007-12-21 | [6 empty] | 2008-08-04 |  |  |  |  | 2010-08-01 | 2010-11-01
EN00564 | 3062 | 2009-06-03 | Yorkshire Water | Chelker Reservoir & Wind Farm Repower | Wind Onshore |  |  | 1.2 | n/a |  |  |  | 0 | 2 |  | n/a | Planning Permission Refused | Application Refused | Near Addingham, N.Yorkshire, LS29 0JS | North Yorkshire | Yorkshire and Humber | England |  | 406190 | 451660 | Craven District Council | 24/2008/8665 | [5 empty] | 2008-05-06 |  | 2009-04-03
EN00565 | 3063 | 2014-12-19 | Asda | Asda Brackmills Distribution Depot | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Asda Distribution Site, Gowerton Road, Brackmills Industrial Estate, Northampton, Northamptonshire, NN4 7BW | Northamptonshire | East Midlands | England |  | 478050 | 257610 | Northamptonshire County Council | 07/0356/FULWNN | [5 empty] | 2007-12-07 |  | 2008-11-04
EN00572 | 3064 | 2010-07-30 | Evelop UK Limited (previously known as Breeze Renewable Energy) | Sheephouse Heights Windfarm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Permission Refused | Application Refused | 2km North West of Stocksbridge and 10km south west of Barnsley, S36 1JJ | South Yorkshire | Yorkshire and Humber | England |  | 425305 | 399056 | Barnsley Council | 2008/0838 | [5 empty] | 2008-05-30 |  | 2009-12-16
EN00590 | 3066 | 2011-06-22 | Bolsterstone Plc | Brixworth Windfarm | Wind Onshore |  |  | 13 | n/a |  |  |  | 2.15 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land adjacent to Harborough Road, between Brixworth and Hanging Houghton | Northamptonshire | East Midlands | England |  | 474345 | 273050 | Daventry District Council | DA/2008/1252 | [5 empty] | 2008-08-29 | 2009-03-11
EN00592 | 3067 | 2011-09-13 | Claymoss Properties Limited | Maer Hills Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Abandoned | Abandoned | Maer Hills , Nantwich Road , Blackbrook , Newcastle | Staffordshire | West Midlands | England |  | 377538 | 339757 | Newcastle Under Lyme Borough Council | 08/00550/FUL | [5 empty] | 2008-06-12 | [6 empty] | 2009-02-16
EN00598 | 3068 | 2011-02-09 |  | MSD Cramlington | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Shotton Lane, Cramlington, Northumberland, NE23 3JU | Northumberland | North East | England |  | 424206 | 578852 | Northumberland County Council | 06-00551-FUL | APP/N2915/A07/2051193/NWF |  |  |  |  | 2006-12-12 |  | 2007-07-31 |  |  |  | 2008-07-24 | 2008-07-24 |  |  |  |  | 2010-09-01 | 2011-01-20
EN00610 | 3069 | 2009-05-20 | Energiekontor UK | Brightenber Hill | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Planning Permission Refused | Application Refused | LAND ADJACENT TO BRIGHTENBER HILL NR STAINTON HALL GARGRAVE SKIPTON BD23 3PA | North Yorkshire | Yorkshire and Humber | England |  | 388691 | 452767 | Craven District Council | 05/2008/8885 | [5 empty] | 2008-07-21 |  | 2009-02-18
EN00615 | 3070 | 2011-09-13 | Scottish and Southern Energy (SSE) | Durran Mains | Wind Onshore |  |  | 19.5 | n/a |  |  |  | 1.5 | 13 |  | n/a | Planning Permission Refused | Application Refused | Land at Mains of Durran Castletown Thurso Highland | Highland | Scotland | Scotland |  | 319500 | 963500 | Highland Council | 08/00386/FULCA | [5 empty] | 2008-08-26 |  | 2010-11-22
EN00616 | 3071 | 2011-10-24 | Partnerships for Renewables/University of Reading | Rushy Mead (University of Reading) | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Planning Permission Refused | Application Refused | Rushy Mead, South of Reading (University owned land) | Berkshire | South East | England |  | 475080 | 169160 | Wokingham Borough Council | F/2010/2266 | [5 empty] | 2010-10-08 |  | 2011-04-28
EN00619 | 3073 | 2008-12-11 | Mercedes-Benz | Mercedes-Benz Technology Centre | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Mercedes-Benz Technology Centre Morgan Drive Brixworth, Northamptonshire NN6 9GZ | Northamptonshire | East Midlands | England |  | 475330 | 271357 | Daventry District Council | DA/2008/0997 | [6 empty] | 2008-12-11
EN00620 | 3074 | 2009-05-20 | The Eden Project | Eden Project | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Eden Project Bodelva PL242SG Bodelva PL242SG | Cornwall | South West | England |  | 205255 | 55155 | Cornwall Council | 08/01411 | [6 empty] | 2009-05-20
EN00628 | 3075 | 2010-05-21 | Private Developer | Skelmonae Wind Farm | Wind Onshore |  |  | 3.2 | n/a |  |  |  | 0.9 | 4 |  | n/a | Operational | Operational | Skelmonae Methlick Ellon AB41 7JR | Grampian | Scotland | Scotland |  | 388702 | 836734 | Aberdeenshire Council | APP/2007/2823 | [5 empty] | 2007-07-06 | [6 empty] | 2009-02-24 | [5 empty] | 2009-12-20
EN00629 | 3076 | 2009-07-07 | Private Developer | Cloffrickford Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 0 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Cloffrickford, Skilmafilly and Denmore Auchnagatt Ellon | Grampian | Scotland | Scotland |  | 390935 | 839895 | Aberdeenshire Council | APP/2008/3667 | [6 empty] | 2009-07-07
EN00647 | 3077 | 2009-06-01 |  | Carn Vean | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Carn Vean, Tretheague Mill, Stithians, Truro, Cornwall | Cornwall | South West | England | TR3 7BY | 172528 | 35961 | Cornwall Council | PA08/01190/F | [5 empty] | 2008-06-26 | [6 empty] | 2008-09-11 | [5 empty] | 2008-10-30
EN00649 | 3078 | 2010-12-06 | Dewlay Cheese Company | Dewlay Cheese Wind Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Dew Lay Products Limited Garstang Pass Road, Garstang, Preston PR3 0PR. | Lancashire | North West | England |  | 348440 | 443850 | Wyre Borough Council | 08/00676/FULMAJ | [5 empty] | 2008-06-27 |  | 2008-09-04 | [9 empty] | 2010-10-01 | 2010-11-01
ENA0002 | 3079 | 2010-06-09 | Renewable Energy Systems (RES) | Coal Clough Wind Farm | Wind Onshore |  |  | 9.6 | n/a |  |  |  | 0.4 | 24 |  | n/a | Operational | Operational | Burnley | Lancashire | North West | England |  | 390207 | 428154 | Burnley Borough Council | 91/0920 & APP/2005/0867 | [5 empty] | 1991-11-25 | [6 empty] | 1992-07-03 | [5 empty] | 1993-02-01
ENA0054 | 3080 | 2013-10-08 | Amec Wind | Werfa Wind Farm | Wind Onshore |  |  | 14.25 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Werfa, Bridgend | Mid Glamorgan | Wales | Wales |  | 291000 | 195000 | Bridgend County Borough Council | 01/887/FUL | [5 empty] | 2001-09-28 |  | 2002-03-19
IF1179 | 3081 | 2013-08-27 | Roseneath Peninsula West Community Development Trust | Cove Community Wind Farm | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Barbour Farm, Knockderry Farm And Clynder Woodland Cove Helensburgh Argyll And Bute | Strathclyde | Scotland | Scotland |  | 222579 | 685157 | Argyll and Bute Council | 12/02695/PP | [5 empty] | 2012-12-20 | 2013-08-20
IF1212 | 3082 | 2013-08-27 | Pure Renewable Energy Limited | Dearne Head Wind Farm (Resubmission) | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Planning Permission Refused | Application Refused | Broadstone Road, Cumberworth, Huddersfield, HD8 8YF | West Yorkshire | Yorkshire and Humber | England |  | 419689 | 407232 | Kirklees Council | 2012/62/93935/E | [5 empty] | 2013-01-10 |  | 2013-08-23
IF1230 | 3083 | 2013-05-02 | REG Windpower | Mendennick Wind Farm | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | St John, Torpoint, Cornwall | Cornwall | South West | England | PL11 | 240686 | 53013 | Cornwall Council | PA12/12027 | [5 empty] | 2013-01-15 | 2013-04-10
IF1280 | 3085 | 2013-07-03 | Private Developer | Priestside Farm | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Planning Permission Refused | Application Refused | Auchentiber Road Kilmacolm PA13 4SP | Strathclyde | Scotland | Scotland |  | 232752 | 672241 | Inverclyde Council | 13/0036/IC | [5 empty] | 2013-02-04 |  | 2013-04-23
IF1434 | 3086 | 2013-10-03 | WhiteRock Energy UK Ltd | Cowdenhead Wind Turbines | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.75 | 2 |  | n/a | Planning Permission Refused | Application Refused | STANDHILL FARM, ARMADALE | Lothian | Scotland | Scotland |  | 296852 | 667243 | West Lothian Council | 0146/FUL/13 | [5 empty] | 2013-03-05 |  | 2013-09-11
N00002W | 3087 | 2010-01-06 | Private Developer | High Pow Farm | Wind Onshore |  |  | 3.884 | n/a |  |  |  | 1.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | High Pow Farm Boltons Low Houses Nr. Wigton Cumbria | Cumbria | North West | England |  | 323550 | 544400 | Allerdale Borough Council | 2/03/1023 | [5 empty] | 2003-09-04 | 2004-10-06
N00003W | 3088 | 2011-09-11 | Ecotricity | Lowick Beacon | Wind Onshore |  |  | 4.186 | n/a |  |  |  | 1.4 | 3 |  | n/a | Planning Permission Refused | Application Refused | Lowick Beacon (village common) | Cumbria | North West | England |  | 328700 | 484000 | South Lakeland District Council | 5/00/2278 | [5 empty] | 2000-08-29 |  | 2001-03-30
N00005W | 3089 | 2010-01-06 | Ecotricity | Lynch Knoll Wind Farm (Extension) | Wind Onshore |  |  | 1.47 | n/a |  |  |  | 0.5 | 3 |  | n/a | Appeal Withdrawn | Application Refused | Lynch Knoll Wind Farm , Partfield Farm , Tinkley Lane, Nympsfield , Stonehous | Gloucestershire | South West | England |  | 381600 | 200400 | Stroud District Council | S. 00/1628 | [5 empty] | 2000-10-09 |  | 2000-12-10 |  | 2001-04-09
N00007W | 3090 | 2001-11-27 | National Energy Laboratories (NEL) | Myres Hill | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Operational | Operational | Galloway | Strathclyde | Scotland | Scotland |  | 256840 | 646620 | East Renfrewshire Council | 99/0406/TP | [5 empty] | 1999-05-01 | [6 empty] | 2001-08-31 | [5 empty] | 2001-11-01
N00011W | 3092 | 2012-07-04 | REG Windpower (previously Cornwall Light & Power) | High Sharpley Wind Farm | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Operational | Operational | High Sharpley and South Sharpley Farms Near Seaham County Durham | Durham | North East | England |  | 442644 | 549702 | Durham County Council | 02/221 | [5 empty] | 2002-04-09 | [6 empty] | 2002-06-13 | [5 empty] | 2006-12-01
N00014W | 3093 | 2009-11-05 | NEL | National Wind Turbine Test Site | Wind Onshore |  |  | 4.651 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | National Wind Turbine Test site Myres Hill Eaglesham | Strathclyde | Scotland | Scotland |  | 256500 | 646500 | East Renfrewshire Council | 1999/0406/TP | [5 empty] | 1999-08-19 | [6 empty] | 2000-08-01 | [5 empty] | 2001-02-15
N00015W | 3094 | 2010-01-25 | Kenetech International | Goodbush Hill | Wind Onshore |  |  | 24 | n/a |  |  |  | 0.4 | 60 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Goodbush Hill, Near Strathaven | Strathclyde | Scotland | Scotland |  | 270000 | 645000 | South Lanarkshire Council | P/96/29 | [6 empty] | 2010-01-25
N00016W | 3095 | 2009-04-30 | Private Developer | Penbreck & Carmacoup Forest | Wind Onshore |  |  | 27 | n/a |  |  |  | 1.5 | 18 |  | n/a | Planning Permission Refused | Application Refused | Penbreck & Carmacoup Forest Near Glespin | Strathclyde | Scotland | Scotland |  | 280659 | 628236 | South Lanarkshire Council | CI/01/0010 | [5 empty] | 2000-11-20 |  | 2003-01-20
N00019W | 3096 | 2009-07-09 | RWE npower | Little Cheyne Court Wind Farm | Wind Onshore |  |  | 59.8 | n/a |  |  |  | 2.3 | 26 |  | n/a | Operational | Operational | Little Cheyne Court, Romney Marsh Near Lydd Kent | Kent | South East | England |  | 598310 | 122060 | DECC (S36) | YO2/1278/SH | [5 empty] | 2002-11-28 |  | 2005-10-18 |  |  |  | 2005-10-18 | 2005-10-18 |  |  |  |  | 2008-07-01 | 2009-06-01
N0001W1 | 3097 | 2010-02-23 | Colham Energy Ltd, plus Airtricty extrension | Bessy Bell Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 0.5 | 10 |  | n/a | Operational | Operational | Bessy Bell Mountain Baronscourt Estate Newtownstewart, County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 49687 | 547922 | Northern Ireland Planning Service | K/2006/1678/F | [5 empty] | 1994-06-21 | [6 empty] | 1994-11-16 | [5 empty] | 1995-10-01
N00023W | 3099 | 2010-03-09 | AMEC | Aultmore Wind Farm | Wind Onshore |  |  | 62 | n/a |  |  |  | 0 | 31 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Aultmore Forest, Keith, Morayshire | Grampian | Scotland | Scotland |  | 345000 | 860000 | Scottish Government (S36) | IEC 3/68 (S.E. ref) | [5 empty] | 2003-10-27 | 2004-03-03
N00026W | 3101 | 2009-04-22 | Snow Mountain Investment Ltd | Long Hill Road | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Foundry Way Longhill Road March | Cambridgeshire | Eastern | England |  | 541686 | 299303 | Fenland District Council | S/YR01/1212/F | [5 empty] | 2001-07-03 | [6 empty] | 2003-04-07 | [5 empty] | 2005-01-01
N00027W | 3102 | 2011-06-29 | Ab Energy | Bagot's Park | Wind Onshore |  |  | 18 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Bagot's Park Estate , Abbots Bromley , Staffordshire | Staffordshire | West Midlands | England |  | 408000 | 327000 | East Staffordshire Borough Council | pa/26905/004 | [6 empty] | 2011-06-29
N0002W1 | 3103 | 2017-08-29 | B9 Energy Services Ltd/ ScottishPower Renewables | Corkey Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 0.5 | 10 |  | n/a | Operational | Operational | Slievenahanaghen Mountain (Accessed via Corkey Road) Cloughmills County Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 126222 | 580523 | Northern Ireland Planning Service | [6 empty] | 1993-11-22 | [6 empty] | 1994-06-29 | [5 empty] | 1994-12-01
N00034W | 3104 | 2007-09-11 | AMEC | Clashindarroch | Wind Onshore |  |  | 129 | n/a |  |  |  | 0 | 40 |  | n/a | Appeal Refused | Application Refused | Huntly, Aberdeenshire | Grampian | Scotland | Scotland |  | 348500 | 831500 | Scottish Government (S36) | IEC3/67 | [5 empty] | 2003-08-18 |  | 2006-05-01 |  |  | 2007-09-11
N00037W | 3105 | 2010-02-03 | SLP Energy | Ness point Wind Turbine 1 | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Land off North Beach Industrial Estate Off Wilde Street Nesspoint Lowestoft | Suffolk | Eastern | England |  | 655480 | 293595 | Waveney District Council | W14512/1 | [5 empty] | 2001-10-31 | [6 empty] | 2002-09-27 | [5 empty] | 2004-12-01
N0003W1 | 3106 | 2017-08-29 | B9 Energy Services Ltd/ ScottishPower Renewables | Elliot's Hill Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 0.5 | 10 |  | n/a | Operational | Operational | Elliot's Hill Tildarg near Ballyclare County Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 134974 | 546006 | Northern Ireland Planning Service | [6 empty] | 1993-11-18 | [6 empty] | 1994-10-26 | [5 empty] | 1995-04-01
N00041W | 3107 | 2014-12-02 | Private Developer | Cheverton Down Farm Re-submission | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Appeal Refused | Application Refused | Limerstone Down, Brightsone Forest, Brightstone | Isle of Wight | South East | England |  | 443800 | 83800 | Isle of Wight Council | P/00021/09 | [5 empty] | 2001-05-21 |  | 2009-12-22 |  |  | 2011-08-30
N00044W | 3108 | 2017-05-18 | Innogy (formerly RWE npower) | Causeymire | Wind Onshore |  |  | 48.3 | n/a |  |  |  | 2 | 24 |  | n/a | Operational | Operational | Causey Mire, Caithness, Highlands | Highland | Scotland | Scotland |  | 336736 | 951086 | Highland Council | 01/00361/FULCA | [5 empty] | 2001-11-01 | [6 empty] | 2002-11-19 | [5 empty] | 2004-06-01
N00045W | 3109 | 2009-05-06 | Scottish and Southern Energy (SSE) | Hadyard Hill | Wind Onshore |  |  | 120 | n/a |  |  |  | 2.3 | 52 |  | n/a | Operational | Operational | Hadyard Hill , East of Girvan , South Ayrshire | Strathclyde | Scotland | Scotland |  | 226478 | 599253 | Scottish Government (S36) | 03/01745/DEEM | [5 empty] | 2003-05-27 | [6 empty] | 2003-12-29 |  |  |  |  | 2006-05-01 | 2006-05-08
N00046W | 3110 | 2013-05-09 | Powergen | Hare Hill (B) | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 1.35 | 2 |  | n/a | Operational | Operational | Hare Hill, Durham | Durham | North East | England |  | 437735 | 540895 | Durham County Council | [6 empty] | 1994-04-01 | [6 empty] | 1997-03-01 | [5 empty] | 2004-07-02
N00048W | 3111 | 2005-06-10 | Ron Shanks Waste Management Ltd | Stoneyhill | Wind Onshore |  |  | 30.6 | n/a |  |  |  | 0.9 | 34 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Just west of Stoneyhill , Peterhead , Aberdeenshire | Grampian | Scotland | Scotland |  | 364500 | 858500 | Aberdeenshire Council | N020466PF | [6 empty] | 2005-06-10
N0004W1 | 3112 | 2017-08-29 | B9 Energy Services Ltd/ ScottishPower Renewables | Rigged Hill Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 0.5 | 10 |  | n/a | Operational | Operational | Rigged Hill, 11km east of Limavady, County Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 92064 | 580329 | Northern Ireland Planning Service | [6 empty] | 1993-11-19 | [6 empty] | 1994-07-01 | [5 empty] | 1994-11-01
N00050W | 3113 | 2015-01-05 | Greencoat UK Wind | Bin Mountain | Wind Onshore |  |  | 9 | n/a |  |  |  | 1.5 | 6 |  | n/a | Operational | Operational | Lough Hill Castle Craig, Curraghmacall Drummahon, | Co. Tyrone | Northern Ireland | Northern Ireland |  | 38520 | 541806 | Northern Ireland Planning Service | J/2004/0295/F | [5 empty] | 2001-05-04 | [6 empty] | 2006-02-01 |  |  |  |  | 2006-12-01 | 2007-02-01
N00051W | 3114 | 2010-04-07 | Fred Olsen Renewables | Crystal Rig Phase 1 | Wind Onshore |  |  | 62.5 | n/a |  |  |  | 2.5 | 25 |  | n/a | Operational | Operational | Crystal Rig, Scottish Borders | Borders | Scotland | Scotland |  | 368350 | 665650 | Scottish Government (S36) | 01/00269/FUL | [5 empty] | 2001-04-01 | [6 empty] | 2003-01-22 | [5 empty] | 2004-06-30
N00054W | 3115 | 2006-07-05 | Your Energy | Wellow Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 0 | 6 |  | n/a | Planning Permission Refused | Application Refused | Wellow West Wight Isle of Wight | Isle of Wight | South East | England |  | 437851 | 87354 | Isle of Wight Council | [6 empty] | 2006-05-26 |  | 2006-11-02
N00056W | 3116 | 2011-12-14 | Scottish Power Renewables | Black Law | Wind Onshore |  |  | 124 | n/a |  |  |  | 2.3 | 54 |  | n/a | Operational | Operational | Black Law, Climpy | Strathclyde | Scotland | Scotland |  | 289500 | 653500 | Scottish Government (S36) | [6 empty] | 2002-05-22 | [6 empty] | 2004-02-13 | [5 empty] | 2004-05-31
N00057W | 3117 | 2004-08-06 | Airtricity | Ardrossan | Wind Onshore |  |  | 24 | n/a |  |  |  | 2 | 12 |  | n/a | Operational | Operational | Near Ardrossan North Ayreshire | Strathclyde | Scotland | Scotland |  | 223500 | 642500 | North Ayrshire Council | N/02/00378/PP | [5 empty] | 2002-05-24 | [6 empty] | 2003-01-13 | [5 empty] | 2003-12-19
N0005W1 | 3118 | 2010-02-23 | EF Energy | Owenreagh Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 0.5 | 10 |  | n/a | Operational | Operational | Land near Craignagapple 10km South East of Strabane County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 57111 | 559168 | Northern Ireland Planning Service | [6 empty] | 1995-10-30 | [6 empty] | 1996-04-04 | [5 empty] | 1997-01-01
N00060W | 3119 | 2015-01-05 | Greencoat UK Wind | Braes O'Doune | Wind Onshore |  |  | 72 | n/a |  |  |  | 2 | 36 |  | n/a | Operational | Operational | Stirling, 2 km to the north of Braes of Doune | Stirling | Scotland | Scotland |  | 272590 | 710500 | Scottish Government (S36) | S/02/01320/NST | [5 empty] | 2002-10-31 | [6 empty] | 2004-10-05 |  |  |  |  | 2006-05-01 | 2006-09-01
N00067W | 3120 | 2009-10-05 | Vestas | Thorfinn Wind Farm - NM1500 | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Burgar Hill, Orkney | Orkney Islands | Scotland | Scotland |  | 334600 | 1025700 | Orkney Islands Council | 02/020/PPF | [5 empty] | 1998-10-23 | [6 empty] | 1999-11-22 | [5 empty] | 2000-04-01
N00069W | 3121 | 2010-01-11 | Airtricity | Greenock Wind Farm | Wind Onshore |  |  | 55 | n/a |  |  |  | 0 | 22 |  | n/a | Appeal Refused | Application Refused | Greenock Wind Farm Inverclyde | Strathclyde | Scotland | Scotland |  | 227500 | 676500 | Scottish Government (S36) | [6 empty] | 2003-05-05 |  | 2005-04-01 |  |  | 2007-08-04
N0006W1 | 3122 | 2013-10-08 | Sean Quinn Group | Slieve Rushen Phase 1 Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 0.5 | 10 |  | n/a | Operational | Operational | Slieve Rushen Derrylin 20km south of Enniskillen, County Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 33019 | 491811 | Northern Ireland Planning Service | [6 empty] | 1992-05-15 | [6 empty] | 1992-11-02 | [5 empty] | 1995-12-01
N00070W | 3123 | 2008-04-16 | Airtricity | Kilpatrick Hills | Wind Onshore |  |  | 60 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Kilpatrick Hills, near Glasgow | Strathclyde | Scotland | Scotland |  | 247500 | 676500 | Scottish Government (S36) | [7 empty] | 2008-04-16
N00073W | 3125 | 2011-06-29 | Corus | Tees Wind North | Wind Onshore |  |  | 45 | n/a |  |  |  | 2.5 | 18 |  | n/a | Abandoned | Abandoned | Corus site , Middleborough , Teeside | Cleveland | North East | England |  | 456000 | 524000 | Redcar and Cleveland Borough Council | R/2001/936/FF | [5 empty] | 2001-12-16 | [6 empty] | 2002-07-16
N00076W | 3126 | 2009-10-23 | Private Developer | Boulfruich | Wind Onshore |  |  | 13 | n/a |  |  |  | 0.85 | 15 |  | n/a | Operational | Operational | Houstry Dunbeath Caithness | Highland | Scotland | Scotland |  | 315500 | 935500 | Highland Council | CA2001306 | [5 empty] | 2001-09-17 | [6 empty] | 2002-05-29 | [5 empty] | 2005-08-01
N00077W | 3127 | 2015-11-24 | Scottish Power Renewables | Inverliever | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 0 | 17 |  | n/a | Planning Permission Refused | Application Refused | Inverliever Forest Former Estate | Strathclyde | Scotland | Scotland |  | 191000 | 712000 | Argyll and Bute Council | 04/02070/DET | [5 empty] | 2002-11-19 |  | 2005-08-24
N00078W | 3128 | 2010-09-15 | Wind Prospect | Bicker Fen | Wind Onshore |  |  | 26.7 | n/a |  |  |  | 2 | 13 |  | n/a | Operational | Operational | Bicker Fen , Bicker , Boston , Lincolnshire | Lincolnshire | East Midlands | England |  | 519870 | 339325 | Boston Borough Council | B/03/0189 | [5 empty] | 2003-03-10 | [6 empty] | 2004-10-15 |  |  |  |  | 2006-06-01 | 2008-07-28
N00079W | 3129 | 2009-05-06 | Powergen / Wind Prospects | Stags Holt | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Operational | Operational | March Cambridgeshire | Cambridgeshire | Eastern | England |  | 544000 | 299000 | Fenland District Council | F/YR01/1269/F | [5 empty] | 2001-12-21 | [6 empty] | 2002-05-23 |  |  |  |  | 2007-04-01 | 2007-10-01
N00081W | 3130 | 2015-01-05 | Greencoat UK Wind | Tappaghan | Wind Onshore |  |  | 19.512 | n/a |  |  |  | 1.5 | 13 |  | n/a | Operational | Operational | Lack, Tappaghan Mountains, Northern Ireland | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 31856 | 531807 | Northern Ireland Planning Service | L/2002/1042/F | [5 empty] | 2002-08-01 | [6 empty] | 2003-11-03 | [5 empty] | 2005-02-01
N00082W | 3131 | 2013-10-08 | B9 Wind Farm Developments | Garrane | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 1 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Close to border, Mullaghfad, Corraleek, Fermanagh Northern Ireland | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 36019 | 519875 | Northern Ireland Planning Service | L/2001/1346/F | [6 empty] | 2013-10-08
N00083W | 3132 | 2009-05-06 | Fenland Windfarms Ltd | Glass Moor | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Glass Moor Near Pondersbridge Cambridgeshire | Cambridgeshire | Eastern | England |  | 528421 | 292867 | Fenland District Council | S/YR02/1327 | [5 empty] | 2002-11-25 | [6 empty] | 2003-05-30 | [5 empty] | 2005-12-01
N00084W | 3133 | 2009-05-06 | Wind Prospect | Gedney Marsh | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | Gedney Marsh Gedney Drove End Lincolnshire | Lincolnshire | East Midlands | England |  | 542014 | 328596 | South Holland District Council | H06/0035/03 | [5 empty] | 2003-01-14 | [6 empty] | 2003-09-27 |  |  |  |  | 2006-05-01 | 2008-07-15
N00088W | 3135 | 2009-05-06 | RDC Scotland (Renewable Development Co.) | Ben Aketil | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Operational | Operational | Ben Aketil Feorlig Dunvegan | Highland | Scotland | Scotland |  | 132500 | 846500 | Highland Council | SL2002275 | [5 empty] | 2002-08-30 | [6 empty] | 2005-09-05 | [5 empty] | 2007-09-01
N00091W | 3136 | 2008-04-24 | Airtricity | Bracco / Black Hill | Wind Onshore |  |  | 72.5 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Site located by the M8 between Glasgow and Edinburgh | Strathclyde | Scotland | Scotland |  | 283434 | 665432 | Scottish Government (S36) | [7 empty] | 2008-04-24
N00092W | 3137 | 2009-06-10 | G. Y. McNay Trust (a front for National Wind Power) | Wandystead | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 0 | 0 |  | n/a | Appeal Refused | Application Refused | Land Adjacent to A697, Edlingham | Northumberland | North East | England |  | 409250 | 606590 | Northumberland County Council | A/2002/0013 | Q2908/A/02?1099718 |  |  |  |  | 2002-01-07 |  | 2002-06-26 |  |  | 2004-05-01
N00093W | 3138 | 2005-11-14 | Mark Caudwell Ltd | Orby Windfarm | Wind Onshore |  |  | 30 | n/a |  |  |  | 0 | 20 |  | n/a | Planning Permission Refused | Application Refused | Marsh Lane , Orby , Skegness , Lincolnshire | Lincolnshire | East Midlands | England | PE24 5JA | 551500 | 367500 | East Lindsey District Council | 134/2016/02 | APP/D2510-A-03-1121492 |  |  |  |  | 2002-12-06 |  | 2003-06-05
N00096W | 3139 | 2008-04-22 | Lewis WindPower (a joint venture between British Energy Renewables and AMEC WIND) | Lewis Wind Farm (Barvas Moor) | Wind Onshore |  |  | 652 | n/a |  |  |  | 3.09 | 176 |  | n/a | Planning Permission Refused | Application Refused | North Lewis Isle of Lewis | Western Isles | Scotland | Scotland |  | 142695 | 934003 | Scottish Government (S36) | [6 empty] | 2004-11-03 |  | 2008-04-21
N00097W | 3140 | 2005-09-29 | Matthew Partridge | Baydon Meadows | Wind Onshore |  |  | 1.302 | n/a |  |  |  | 0 | 1 |  | n/a | Planning Permission Refused | Application Refused | Baydon Road Lambourne Hungerford Berkshire | Berkshire | South East | England |  | 432302 | 178781 | West Berkshire Council | 02/02495/FUL | [5 empty] | 2002-11-27 |  | 2003-11-12
N00100W | 3141 | 2005-08-12 | Saxon Fisheries Ltd | Ash Wind Farm | Wind Onshore |  |  | 2 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | North of Ash Near Westmarsh Dover | Kent | South East | England |  | 627500 | 161500 | Dover District Council | DOV03/9 | [5 empty] | 2003-01-03 |  | 2003-02-27
N00101W | 3142 | 2015-11-24 | Scottish Power Renewables | Hunterstone | Wind Onshore |  |  | 30 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Fairlie North Ayreshire | Strathclyde | Scotland | Scotland |  | 221045 | 655240 | North Ayrshire Council | N/03/0076/PP | P/PPA/310/88 |  |  |  |  | 2003-01-30 |  | 2003-12-08
N00102W | 3143 | 2003-09-02 | The Huntsham Estate | Nine Ash Cross | Wind Onshore |  |  | 4.081 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Tiverton | Devon | South West | England |  | 295242 | 112463 | Mid Devon District Council | 4/52/2002/2879 | [6 empty] | 2003-09-02
N00103W | 3144 | 2011-06-29 | National Wind Power | Cricket St Thomas | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 0 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Cricket St Thomas Winsham Parish Estate | Somerset | South West | England |  | 337500 | 108500 | South Somerset District Council | 02/01865/FUL | [6 empty] | 2011-06-29
N00104W | 3145 | 2004-11-26 | Eco-Energy Group | Old Quarrington (A) | Wind Onshore |  |  | 2 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Land near Old Quarrington Durham City | Durham | North East | England |  | 432500 | 537500 | Durham County Council | 4/02/549 | [5 empty] | 2002-06-14 |  | 2002-08-09
N00109W | 3146 | 2010-06-09 | Renewable Energy Systems (RES) | Cambusmore | Wind Onshore |  |  | 49.535 | n/a |  |  |  | 1.5 | 33 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Dornoch, Highlands | Highland | Scotland | Scotland |  | 279641 | 889390 | Highland Council | SU2003383 | [6 empty] | 2010-06-09
N00110W | 3147 | 2009-05-06 | RWE npower | Knabs Ridge Windfarm | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Land between Skipton Road and Penny Pot Lane, Selliscliffe, Harrogate | North Yorkshire | Yorkshire and Humber | England |  | 423069 | 455946 | Harrogate Borough Council | 6.99.144.B.EIAMAG | [5 empty] | 2004-04-23 |  | 2004-11-04 | [9 empty] | 2007-03-01 | 2008-04-22
N00112W | 3148 | 2004-12-02 | Private Developer | Cairn Brae Wind Turbine | Wind Onshore |  |  | 1.302 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Pyworthy Torridge | Devon | South West | England |  | 231500 | 102500 | Torridge District Council | 1/1683/2002 | [6 empty] | 2004-12-02
N00113W | 3149 | 2012-05-03 | Renewable Energy Systems (RES) | Kelburn | Wind Onshore |  |  | 28 | n/a |  |  |  | 2 | 14 |  | n/a | Operational | Operational | Largs North Ayrshire | Strathclyde | Scotland | Scotland |  | 224000 | 655000 | North Ayrshire Council | N/04/00786/PP | [5 empty] | 2004-07-09 |  | 2007-02-26 |  |  |  | 2009-08-10 | 2009-08-10 |  |  |  |  | 2010-11-01 | 2012-05-02
N00114W | 3150 | 2005-11-15 | Parker Farms of Leicester / National Wind Power | Choseley Farm | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Chosely Farm | Norfolk | Eastern | England |  | 574300 | 340740 | King's Lynn and West Norfolk Borough Council | 2/02/0125/F | [6 empty] | 2005-11-15
N00116W | 3151 | 2004-08-17 | West Coast Windfarms Ltd | Monashee | Wind Onshore |  |  | 15 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Drake Myre Grantshouse | Borders | Scotland | Scotland |  | 380651 | 665727 | Scottish Borders Council | 02/01319FUL | [5 empty] | 2002-08-14 | 2004-03-30
N00117W | 3152 | 2005-10-27 | Private Developer | Cefn Coed | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Cefn Coed, Glyn Ceriog Llangollen, Wrexham LL20 7BY | Clwyd | Wales | Wales |  | 320526 | 336486 | Wrexham County Borough Council | P/2002/0538 | [5 empty] | 2002-05-22 |  | 2002-09-09
N00119W | 3153 | 2005-04-16 | Private Developer | Lluest Wen Energy Centre | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Land at Ffermdy Lluest Wen , Llangynwyd , Maesteg | Mid Glamorgan | Wales | Wales |  | 284000 | 189000 | Bridgend County Borough Council | 02/0704/FUL/DCD | [5 empty] | 2002-06-28 |  | 2002-10-01
N00120W | 3154 | 2005-11-15 | Ecotricity | Sedgeford | Wind Onshore |  |  | 10.8 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Off Sedgeford Road King's Lynn and West Norfolk | Norfolk | Eastern | England |  | 570780 | 335130 | King's Lynn and West Norfolk Borough Council | 2/02/1616/F | [6 empty] | 2005-11-15
N00121W | 3155 | 2015-03-31 | REG Windpower | Ramsey 1 | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 1.8 | 1 |  | n/a | Operational | Operational | Rear of Packing Station St Mary's Road Ramsey Cambs | Cambridgeshire | Eastern | England |  | 528800 | 284900 | Huntingdonshire District Council | 0300478/FUL | [5 empty] | 2003-03-11 | [6 empty] | 2004-04-23 | [5 empty] | 2008-09-30
N00122W | 3156 | 2005-11-29 | Private Developer | Penpell Wind Cluster | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 0 | 2 |  | n/a | Planning Permission Refused | Application Refused | Penpell Farm , Par , Cornwall | Cornwall | South West | England | PL24 2SA | 207780 | 55000 | Cornwall Council | 301146 | APP/Q0830/A/05/1189328 |  |  |  |  | 2003-06-12 |  | 2005-04-01
N00123W | 3157 | 2009-12-04 | Ecotricity | Bambers Farm | Wind Onshore |  |  | 9.6 | n/a |  |  |  | 0.6 | 8 |  | n/a | Operational | Operational | Mile Lane, Mablethorpe, Lincolnshire | Lincolnshire | East Midlands | England |  | 549195 | 382820 | East Lindsey District Council | N/110/00269/03 | [5 empty] | 2003-02-18 |  | 2003-06-15 | [10 empty] | 2004-11-01
N00124W | 3158 | 2011-08-05 | Ecotricity | Ford Wind Park - Dagenham | Wind Onshore |  |  | 5.92 | n/a |  |  |  | 2.96 | 2 |  | n/a | Operational | Operational | Ford Motor Company Estate Kent Avenue Dagenham | Greater London | London | England |  | 549327 | 182167 | Barking and Dagenham London Borough Council | DC/03/00/201 | [5 empty] | 2003-03-07 | [6 empty] | 2003-07-16 | [5 empty] | 2004-06-17
N00126W | 3159 | 2004-09-22 | Ecotricity | Swaffham Plashes II | Wind Onshore |  |  | 1.791 | n/a |  |  |  | 1.79 | 1 |  | n/a | Operational | Operational | Old Sporle Road Swaffham | Norfolk | Eastern | England |  | 582760 | 310085 | Breckland Council | 3PL/2001/1505/F | [5 empty] | 2001-12-11 | [6 empty] | 2002-09-30 | [5 empty] | 2003-07-15
N00127W | 3160 | 2010-12-07 | Ecotricity | Shipdham Wind Park | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Refused | Application Refused | Wood Farm Church Lane Shipdham | Norfolk | Eastern | England |  | 595832 | 307429 | Breckland Council | 3PL/2002/0004 | [5 empty] | 2002-01-03 |  | 2002-12-17
N00129W | 3161 | 2009-05-06 | Ecotricity | Shooters Bottom Wind Park | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Shooters Bottom, Chewton Mendip, | Somerset | South West | England |  | 359380 | 150740 | Mendip District Council | 116407-000 | [5 empty] | 2003-09-15 |  | 2005-05-24 |  |  |  | 2006-05-18 | 2006-05-18 | [5 empty] | 2008-06-16
N00130W | 3162 | 2011-06-29 | Private Developer | Rockery Farm | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Abandoned | Abandoned | Broadway Bourn CB3 7TA | Cambridgeshire | Eastern | England |  | 533065 | 258036 | South Cambridgeshire District Council | S1569/02/F | [5 empty] | 2002-08-02 | [6 empty] | 2007-06-17
N00133W | 3164 | 2008-12-05 | National Wind Power | Cheverton Down | Wind Onshore |  |  | 1.2 | n/a |  |  |  | 0.6 | 2 |  | n/a | Abandoned | Abandoned | Isle of Wight | Isle of Wight | South East | England |  | 444250 | 84250 | Isle of Wight Council | [6 empty] | 2001-05-31 | [6 empty] | 2002-11-20
N00137W | 3166 | 2005-10-18 | Orkney Sustainable Energy | Hill of Garvock Wind Energy Project | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | East Bradieston Farm Laruencekirk | Grampian | Scotland | Scotland |  | 370000 | 770000 | Aberdeenshire Council | SO 30676PF | [6 empty] | 2005-10-18
N00143W | 3167 | 2013-10-08 | Airtricity | Slieve Beagh | Wind Onshore |  |  | 30 | n/a |  |  |  | 2 | 12 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Slieve Beagh, Outside Clogher, County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 68890 | 516118 | Northern Ireland Planning Service | M/2003/0999/F | [6 empty] | 2013-10-08
N00144W | 3168 | 2017-08-02 | Bessy Bell Windfarm | Bessy Bell Extension | Wind Onshore |  |  | 9 | n/a |  |  |  | 1.3 | 6 |  | n/a | Operational | Operational | Bessy Bell Moutain , 5km south of Newtownstewart, 17km south of Strabane and 9km northwest of Omagh | Co. Tyrone | Northern Ireland | Northern Ireland |  | 50592 | 547973 | Northern Ireland Planning Service | [6 empty] | 2003-06-03 | [6 empty] | 2005-01-10 | [5 empty] | 2008-04-24
N00147W | 3170 | 2011-06-29 | AMEC | Minch Moor | Wind Onshore |  |  | 21.6 | n/a |  |  |  | 1.8 | 12 |  | n/a | Planning Permission Refused | Application Refused | Walkerburn Scottish Borders | Borders | Scotland | Scotland |  | 336300 | 633500 | Scottish Borders Council | 03/00627/FUL | [5 empty] | 2003-04-11 |  | 2010-08-09
N00150W | 3171 | 2009-05-06 | Hainsford Energy | Caton Moor Windfarm Repowering | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Littledale, Caton Lancashire | Lancashire | North West | England |  | 357298 | 463963 | Lancaster City Council | 21331 | 02/01331/FUL |  |  |  |  | 2002-11-07 |  | 2003-09-10 |  |  |  | 2004-10-01 | 2004-10-01 |  |  |  |  | 2006-05-01 | 2006-06-01
N00152W | 3172 | 2017-05-03 | John Laing Environmental Assets Group | Moel Maelogen A Phase 2 | Wind Onshore |  |  | 11.7 | n/a |  |  |  | 1.3 | 8 |  | n/a | Operational | Operational | Moel Maelogen, Nr Llanrwst, Conwy, Gwynedd | Gwynedd | Wales | Wales |  | 284700 | 361300 | Conwy County Borough Council | 0/27445 | [5 empty] | 2003-06-12 | [6 empty] | 2004-11-26 | [5 empty] | 2008-10-01
N00153W | 3173 | 2005-08-26 | Windworks (National Wind Power) | Stumpy Post | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 0 | 1 |  | n/a | Planning Permission Refused | Application Refused | Kingsbridge South Devon | Devon | South West | England |  | 274210 | 47240 | South Hams District Council | 08/0175/03/F | [5 empty] | 2003-03-07 |  | 2003-05-28
N00154W | 3174 | 2004-11-26 | Eco-Energy Group | Old Quarrington (B) | Wind Onshore |  |  | 2 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Land near Old Quarrington Durham City | Durham | North East | England |  | 432500 | 537500 | Durham County Council | 4/02/550 | [5 empty] | 2002-06-14 |  | 2002-11-13
N00155W | 3175 | 2011-06-29 | Lower Winterbourne Wind Farm Ltd | Part Bushes Farm | Wind Onshore |  |  | 24.75 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Part Bushes Farm, Riverside Farm and Tomson Farm Anderson and Winterbourne Zelston | Dorset | South West | England |  | 387240 | 97840 | North Dorset District Council | 2-2003-0765 | [5 empty] | 2003-08-01 |  | 2004-10-26
N00156W | 3176 | 2005-08-26 | Windworks (National Wind Power) | Island Park Lodge | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Island Park Lodge Caravan and Camping Park Kingsbridge Devon | Devon | South West | England |  | 273200 | 44700 | South Hams District Council | 08/0180/02 | [5 empty] | 2002-01-28 | 2002-05-24
N00159W | 3177 | 2018-02-27 | Munich Re (previously Peel) | Scout Moor Windfarm | Wind Onshore |  |  | 65 | n/a |  |  |  | 2.5 | 26 |  | n/a | Operational | Operational | Land at Scout Moor , off Edenfield Road , Rochdale | Lancashire | North West | England |  | 382400 | 419200 | DECC (S36) | [6 empty] | 2003-06-30 | [6 empty] | 2005-05-25 |  |  |  |  | 2007-09-01 | 2008-06-01
N00162W | 3178 | 2009-05-30 | Wind Prospect | Morris Fen (Wind) | Wind Onshore |  |  | 16 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Morris Fen , Near Thorney (NEE) , Peterborough | Cambridgeshire | Eastern | England |  | 530000 | 305000 | Peterborough City Council | 03/01247/FUL | [5 empty] | 2003-09-05 |  | 2004-04-23
N00163W | 3179 | 2005-09-26 | Private Developer | The Haven | Wind Onshore |  |  | 1.2 | n/a |  |  |  | 1.2 | 1 |  | n/a | Operational | Operational | The Haven Oxhill Farm Blackmor Park Malvern Worcestershire | Hereford and Worcester | West Midlands | England |  | 378300 | 247900 | Malvern Hills District Council | 02\01784\FUL | [5 empty] | 2002-12-18 | [6 empty] | 2003-02-20 | [5 empty] | 2003-11-05
N00166W | 3180 | 2015-11-24 | Scottish Power Renewables | Clatto | Wind Onshore |  |  | 30 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Kennoway Fife | Fife | Scotland | Scotland |  | 335000 | 705000 | Fife Council | 03/03397/EEIA | P/PPA/250/507 |  |  |  |  | 2003-09-24 |  | 2004-11-01
N00169W | 3181 | 2007-11-07 | Private Developer | The Stables (Edgeworth) | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | The Stables Uglow Farm Broadhead Road Edgeworth BL7 0JN | Lancashire | North West | England |  | 374100 | 416800 | Blackburn with Darwen Borough Council | 10/03/0689 | [5 empty] | 2003-07-18 |  | 2004-10-21
N00172W | 3182 | 2006-05-09 | Scotrenewables | Hill of Lieurary | Wind Onshore |  |  | 8 | n/a |  |  |  | 0 | 3 |  | n/a | Planning Permission Refused | Application Refused | Hill of Lieurary Westfield Thurso Caithness | Highland | Scotland | Scotland |  | 308500 | 961500 | Highland Council | CA2003323 | P/PPA/270/369 |  |  |  |  | 2003-07-10 |  | 2005-09-16
N00173W | 3183 | 2009-05-06 | Renewable Development Company (RDC) | Strathbora | Wind Onshore |  |  | 46 | n/a |  |  |  | 0 | 19 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Strath Brora Rogart Sutherland | Highland | Scotland | Scotland |  | 272100 | 911100 | Highland Council | SU2003332 | [6 empty] | 2009-05-06
N00174W | 3184 | 2005-10-26 |  | Mynydd James Wind Farm | Wind Onshore |  |  | 31.2 | n/a |  |  |  | 1.3 | 24 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Coitoi Mountain , Blaenau Gwent | Gwent | Wales | Wales |  | 321022 | 209556 | Blaenau Gwent County Borough Council | 2003/0494 | [6 empty] | 2005-10-26
N00179W | 3186 | 2010-01-06 | National Wind Power | The Hollies | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Operational | Operational | The Hollies High Lane Croft Skegness pe24 4sh | Lincolnshire | East Midlands | England |  | 549995 | 362998 | East Lindsey District Council | S/039/711/02 | [5 empty] | 2002-07-02 |  | 2004-10-29 | [9 empty] | 2007-09-01 | 2008-01-01
N00180W | 3187 | 2004-09-09 | Glen Devon Energy Ltd | Balado Windfarm | Wind Onshore |  |  | 5.5814 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Balado Kinross | Tayside | Scotland | Scotland |  | 309500 | 702500 | Perth and Kinross Council | 02-01464-FUL | P/PPA/340/283 |  |  |  |  | 2002-08-30 |  | 2004-01-01
N00181W | 3188 | 2010-01-04 | Your Energy | Laughton Wind Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Planning Permission Refused | Application Refused | Mount Pleasant Farm, Scotton Rd, (1km east of Laughton and 8km northeast of the centre of Gainsborough), Loughton | Lincolnshire | East Midlands | England |  | 487500 | 397500 | West Lindsey District Council | M03/P/1152 | [5 empty] | 2003-11-03 |  | 2004-08-25
N00184W | 3189 | 2013-10-08 | Ecotricity | Symphony Farm | Wind Onshore |  |  | 3.907 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Symphony Farm, Cucklington, South Somerset | Somerset | South West | England |  | 376500 | 127500 | South Somerset District Council | 03480FUL | [5 empty] | 2003-10-01 |  | 2004-03-09
N00186W | 3190 | 2010-10-28 | West Coast Energy (agents for Tullo Wind Ltd and GE Wind) | Tullo Farm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Operational | Operational | Tullo Farm, Laurencekirk, Aberdeenshire Garvock Laurencekirk | Grampian | Scotland | Scotland |  | 387283 | 785873 | Aberdeenshire Council | APP/2003/0756 | [5 empty] | 2003-10-13 | [6 empty] | 2004-06-30 |  |  |  |  | 2010-04-01 | 2010-09-07
N00192W | 3191 | 2017-12-04 | Gravis Capital Management | Garves Mountain Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Operational | Operational | Garves Mountain Farm, Tullaghans Road (access adjacent to no. 91), Dunloy. Ballymoney | Co. Antrim | Northern Ireland | Northern Ireland |  | 108200 | 577000 | Northern Ireland Planning Service | D/2003/0329/F | [5 empty] | 2003-06-11 | [6 empty] | 2006-11-20 |  |  |  |  | 2009-01-01 | 2009-01-01
N00199W | 3193 | 2010-01-05 | Enertrag | Guestwick | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Permission Refused | Application Refused | Guestwick, Skitfield Road | Norfolk | Eastern | England |  | 606098 | 327057 | Broadland District Council | 20041819 | [5 empty] | 2004-11-15 |  | 2005-03-31
N00200W | 3194 | 2007-09-03 | Bristol Port Authority | Avonmouth Port | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Avonmouth Port | Avon | South West | England |  | 351335 | 179980 | Bristol City Council | 05/03131/F | [5 empty] | 2005-08-08 | [6 empty] | 2005-12-16 | [5 empty] | 2007-08-20
N00202W | 3195 | 2007-07-31 | Renewable Energy Systems (RES) | Crow Holt Windfarm | Wind Onshore |  |  | 20 | n/a |  |  |  | 0 | 10 |  | n/a | Planning Permission Refused | Application Refused | Crow Holt Grove Retford | Nottinghamshire | East Midlands | England |  | 475250 | 379250 | Bassetlaw District Council | 24/05/00003 | [5 empty] | 2005-03-31 |  | 2007-07-12
N00203W | 3196 | 2010-01-05 | Lincolnshire Windpower Limited | Withern | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Stain Lane Withern Lincs | Lincolnshire | East Midlands | England |  | 545100 | 383980 | East Lindsey District Council | N/212/02279/05 | [5 empty] | 2005-09-21 |  | 2006-06-12
N00204W | 3197 | 2011-06-29 | Star Energy | Welton Gathering Centre | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Welton Gathering Centre Barfields Lane Sudbroke | Lincolnshire | East Midlands | England |  | 504380 | 374990 | West Lindsey District Council | M03/p/1291 | [6 empty] | 2011-06-29
N00205W | 3198 | 2011-06-29 | Star Energy | Nettleham Oil Production Facility | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Nettleham Oil Production Facility , Off Greenwell Lane , Nettleham | Lincolnshire | East Midlands | England |  | 499940 | 374140 | West Lindsey District Council | M03/p/1292 | [6 empty] | 2011-06-29
N00206W | 3199 | 2009-02-04 | Star Energy | Stainton Oil Production Facility | Wind Onshore |  |  | 28 | n/a |  |  |  | 2 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Stainton Oil Production Facility , Ashing Lane , Dunholme | Lincolnshire | East Midlands | England |  | 505510 | 378860 | West Lindsey District Council | M03/p/1293 | [6 empty] | 2009-02-04
N00211W | 3200 | 2015-06-04 | Tetro Energy Ltd (ECO2) | Dummuie | Wind Onshore |  |  | 12.25 | n/a |  |  |  | 1.75 | 7 |  | n/a | Operational | Operational | East Dummuie Huntly | Grampian | Scotland | Scotland |  | 358600 | 840300 | Aberdeenshire Council | APP/2003/0084 | [5 empty] | 2003-08-20 |  | 2004-02-20 | [9 empty] | 2006-06-01 | 2007-01-01
N00213W | 3201 | 2016-06-27 | Falck Renewables | Earlsburn | Wind Onshore |  |  | 37.5 | n/a |  |  |  | 2.5 | 14 |  | n/a | Operational | Operational | Hart Hill, Fintry , Stirling | Stirling | Scotland | Scotland |  | 269652 | 688422 | Stirling Council | 03/00936/DET | [5 empty] | 2003-11-17 | [6 empty] | 2004-07-01 |  |  |  |  | 2006-07-01 | 2007-02-01
N00215W | 3202 | 2009-10-23 | Renewable Development Company (RDC) | Kilbraur Windfarm | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 2.5 | 19 |  | n/a | Operational | Operational | Rogart, Sutherland (former Strath Brora Site) | Highland | Scotland | Scotland |  | 278550 | 907550 | Highland Council | SU2004125 | [5 empty] | 2003-09-04 | [6 empty] | 2006-04-01 |  |  |  |  | 2007-09-01 | 2008-06-14
N00218W | 3203 | 2009-03-20 | Private Developer | South Shebster | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | South Shebster Caithness | Highland | Scotland | Scotland |  | 301750 | 962750 | Highland Council | [6 empty] | 2005-12-19 |  | 2009-01-20
N00222W | 3205 | 2011-08-08 | Scottish and Southern Energy (SSE) | Achany Wind Farm | Wind Onshore |  |  | 38 | n/a |  |  |  | 2 | 19 |  | n/a | Operational | Operational | Albany Estate, Achany, Lairg, Highlands, IV27 4 | Highland | Scotland | Scotland |  | 252350 | 904150 | Highland Council | [6 empty] | 2005-10-28 |  | 2006-08-01 |  |  |  | 2007-09-14 | 2007-09-14 |  |  |  |  | 2009-04-01 | 2010-10-11
N00224W | 3206 | 2008-04-16 | British Energy | Scoolary | Wind Onshore |  |  | 120 | n/a |  |  |  | 0 | 48 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Scoolary Caithness | Highland | Scotland | Scotland |  | 329500 | 968500 | Scottish Government (S36) | [7 empty] | 2008-04-16
N00226W | 3207 | 2009-10-23 | Private Developer | Bilbster Wind Farm | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Operational | Operational | Flex Hill, Flex Hill Wind Cluster, Bilbster, Caithness | Highland | Scotland | Scotland |  | 327150 | 951850 | Highland Council | CA200417 | [5 empty] | 2004-01-23 | [12 empty] | 2008-02-01
N00231W | 3208 | 2013-10-08 | BHEARA Ltd | Merthyr Common | Wind Onshore |  |  | 24.302 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Land at Merthyr Common, North of Pengarnddu Industrial Estate, Pengarndduville | Mid Glamorgan | Wales | Wales |  | 307500 | 210500 | Merthyr Tydfil County Borough Council | P/04/0361 | [5 empty] | 2004-08-12 |  | 2005-11-15
N00232W | 3209 | 2008-12-04 | Ecotricity | Spring Farm (wind) | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Spring Farm Bramshall | Staffordshire | West Midlands | England |  | 405814 | 333093 | East Staffordshire Borough Council | [7 empty] | 2008-12-04
N00233W | 3210 | 2009-05-06 | Ecotricity / Prudential | Green Park | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Plot 12 , South Oak Way , Green Park , Reading , Berkshire | Berkshire | South East | England |  | 470640 | 169375 | Wokingham Borough Council | F/2004/1418 | [5 empty] | 2004-03-17 | [6 empty] | 2004-07-28 | [5 empty] | 2005-10-01
N00239W | 3211 | 2011-10-25 | Awel Aman Tawe | Mynydd Y Gwrhyd Windfarm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | Mynydd Y Gwrhyd | West Glamorgan | Wales | Wales |  | 272659 | 210474 | Neath Port Talbot County Borough Council | P2004/1381 | [5 empty] | 2004-09-04 |  | 2005-09-01 |  |  | 2006-10-04
N00240W | 3212 | 2010-12-07 | Hainsford Energy | Enyas Hill | Wind Onshore |  |  | 6 | n/a |  |  |  | 0 | 3 |  | n/a | Planning Permission Refused | Application Refused | Enyas Hill , Rendall , Orkney | Orkney Islands | Scotland | Scotland |  | 340640 | 1020280 | Orkney Islands Council | 04/16/350/PPS | P/PPA/330/32 |  |  |  |  | 2004-07-01 |  | 2005-01-05
N00244W | 3213 | 2010-07-30 | WINDJEN POWER LTD | Dunion Hill Wind Farm | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Planning Permission Refused | Application Refused | Land South West of Dunion Hill, Jedburgh, Scottish Borders | Borders | Scotland | Scotland |  | 361570 | 617476 | Scottish Borders Council | 05/02336/FUL | 08/00011/REF |  |  |  |  | 2006-01-24 |  | 2007-09-11
N00245W | 3214 | 2015-01-05 | Greencoat UK Wind | Carcant Windfarm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Innerleithen | Borders | Scotland | Scotland |  | 336250 | 652850 | Scottish Borders Council | 05/01884/FUL | [5 empty] | 2005-10-10 | [6 empty] | 2006-09-15 |  |  |  |  | 2010-04-01 | 2010-11-02
N00246W | 3215 | 2005-11-08 | RDC Scotland Ltd | Sell Moor Windfarm | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Lauder | Borders | Scotland | Scotland |  | 348050 | 644450 | Scottish Borders Council | 04/00350/FUL | [5 empty] | 2004-03-01 |  | 2005-08-31
N00248W | 3216 | 2005-06-29 | Hargreaves Resources | Chalmerston | Wind Onshore |  |  | 50 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Dalmellington , East Ayrshire | Strathclyde | Scotland | Scotland |  | 249750 | 608750 | East Ayrshire Council | 04/0406/FL | [6 empty] | 2005-06-29
N00249W | 3217 | 2007-04-06 | Ecogen and Eurus Energy UK | Largie Windfarm II | Wind Onshore |  |  | 21 | n/a |  |  |  | 0 | 19 |  | n/a | Planning Permission Refused | Application Refused | Largie, Central Kintyre Ridge, Near Tayinloan | Strathclyde | Scotland | Scotland |  | 173827 | 650398 | Argyll and Bute Council | 04/01606/DET | [5 empty] | 2004-08-12 |  | 2007-03-08
N00253W | 3218 | 2011-08-08 | E.ON UK | Butterwick Moor | Wind Onshore |  |  | 20.5 | n/a |  |  |  | 2.05 | 10 |  | n/a | Operational | Operational | Butterwick Moor , Sedgefield | Durham | North East | England |  | 439000 | 530000 | Durham County Council | 7/2006/0796/DM | [5 empty] | 2007-01-02 | [6 empty] | 2007-06-17 |  |  |  |  | 2010-09-01 | 2011-04-01
N00255W | 3219 | 2010-12-07 | British Energy Renewables Ltd | Knowehead | Wind Onshore |  |  | 60 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Near Dunning, Perthshire | Tayside | Scotland | Scotland |  | 316500 | 723500 | Scottish Government (S36) | 04/01664/FUL | P/PPA/340/486 |  |  |  |  | 2004-08-09 |  | 2005-07-04
N00256W | 3220 | 2009-09-04 | Scottish Power Renewables | Hagshaw Hill Wind Farm Extension | Wind Onshore |  |  | 26 | n/a |  |  |  | 1.3 | 20 |  | n/a | Operational | Operational | Extension to current Windfarm at Hagshaw Hill | Strathclyde | Scotland | Scotland |  | 279000 | 632000 | South Lanarkshire Council | [6 empty] | 2005-01-10 | [6 empty] | 2005-12-28 | [5 empty] | 2008-10-01
N00261W | 3221 | 2005-09-16 | E. ON UK Renewables | Denshaw Windfarm | Wind Onshore |  |  | 10.5 | n/a |  |  |  | 0 | 7 |  | n/a | Planning Permission Refused | Application Refused | Land off Huddersfield Road, Denshaw | Greater Manchester | North West | England |  | 397658 | 410494 | Oldham Council | PA46136-03 | [5 empty] | 2003-12-04 |  | 2006-02-23
N00262W | 3222 | 2006-05-26 | Hargreaves Resources | Spireslack Windfarm | Wind Onshore |  |  | 59.6 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | West of Hagshaw Hill | Strathclyde | Scotland | Scotland |  | 276500 | 630500 | Scottish Government (S36) | [7 empty] | 2006-05-26
N00265W | 3223 | 2009-04-27 | EDF Energy | Southern Law | Wind Onshore |  |  | 5.2 | n/a |  |  |  | 1.3 | 4 |  | n/a | Operational | Operational | Southern Law Farm Trimdon Grange | Durham | North East | England |  | 436500 | 536500 | Durham County Council | 4/04/958 | [5 empty] | 2004-08-13 |  | 2005-07-01 | [9 empty] | 2007-09-01 | 2008-07-10
n00268w | 3226 | 2004-09-30 | EDF Energy | Stanley Moss | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Refused | Application Refused | Nr Sunniside | Durham | North East | England |  | 415200 | 538600 | Durham County Council | [6 empty] | 2004-02-16 |  | 2004-06-03
N00269W | 3227 | 2010-01-11 | Catamount Energy Ltd c/o Force 9 | Abercairney | Wind Onshore |  |  | 66 | n/a |  |  |  | 2.75 | 24 |  | n/a | Appeal Refused | Application Refused | Nr Crieff, Gilmerton | Tayside | Scotland | Scotland |  | 283880 | 727080 | Scottish Government (S36) | [6 empty] | 2004-01-09 |  | 2006-10-05 |  |  | 2006-09-09
N00271W | 3228 | 2009-04-17 | RWE npower | Lochelbank Wind Farm | Wind Onshore |  |  | 51 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | North of Glenfarg | Tayside | Scotland | Scotland |  | 311440 | 713477 | Perth and Kinross Council | [7 empty] | 2009-04-17
N00286W | 3229 | 2010-03-03 | Westbury Windfarms | Llangwyryfon | Wind Onshore |  |  | 9.35 | n/a |  |  |  | 0.85 | 11 |  | n/a | Operational | Operational | Llangwyryfon, Southeast Aberystwyth Ceredigion | Dyfed | Wales | Wales |  | 261752 | 269577 | Ceredigion County Council | A01/1330 | [5 empty] | 2001-12-01 | [6 empty] | 2003-03-01 | [5 empty] | 2004-02-01
N00289W | 3230 | 2011-11-02 | Your Energy | Cambridge Wind Farm | Wind Onshore |  |  | 32 | n/a |  |  |  | 2 | 16 |  | n/a | Appeal Refused | Application Refused | L and South West of Huntingdon, Bosworth and Conningham | Cambridgeshire | Eastern | England |  | 534322 | 266052 | South Cambridgeshire District Council | S/1663/04/F | S/1663/04/F |  |  |  |  | 2004-08-10 |  | 2005-04-07 |  |  | 2006-12-08
N00290W | 3231 | 2010-07-06 | Wind Prospect & Ridgewind | Montreathmont Moor | Wind Onshore |  |  | 38 | n/a |  |  |  | 2 | 11 |  | n/a | Appeal Refused | Application Refused | Nr Friockheim | Tayside | Scotland | Scotland |  | 359200 | 753700 | Angus Council | 07/01632/FUL | 947/08 |  |  |  |  | 2005-02-07 |  | 2008-06-09 |  |  | 2009-05-26
N00291W | 3232 | 2010-04-06 | Your Energy | Pates Hill | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Operational | Operational | West Calder Lothian, EH55 | Lothian | Scotland | Scotland |  | 299130 | 659300 | West Lothian Council | 0653/FUL/07 | [5 empty] | 2005-07-21 | [6 empty] | 2006-06-01 |  |  |  |  | 2009-06-01 | 2010-01-20
N00292W | 3233 | 2012-07-04 | REG Windpower (previously Cornwall Light and Power) | Roskrow Wind Turbines | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Operational | Operational | Roskrow Barton Farm, Roskrow, Penryn, Cornwall, TR10 9AP | Cornwall | South West | England |  | 176500 | 35500 | Cornwall Council | PA02/01417 | PA02/01417 |  |  |  |  | 2002-12-01 |  | 2004-02-25 |  |  |  | 2004-02-25 | 2004-02-25 | [5 empty] | 2007-12-01
N00296W | 3234 | 2010-06-09 | A7 Energy, 42 Shepherd St, London | Edder Acres Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.3 | 2 |  | n/a | Appeal Refused | Application Refused | Shotton , Shotton colliery to the north and Bracken hill industrial estate to west off an unclassified road on the B1280 | Durham | North East | England |  | 439400 | 539700 | Durham County Council | HIST/2004/1823 | APP/H1325/A/06/2008033 |  |  |  |  | 2004-12-21 |  | 2005-10-13 | 2006-02-13 |  | 2006-06-02
N00299W | 3235 | 2010-06-09 | AMEC | Kyle Windfarm | Wind Onshore |  |  | 255 | n/a |  |  |  | 3 | 85 |  | n/a | Planning Permission Refused | Application Refused | Kyle forest, B714 road between New Cumnock and Dalmellington | Strathclyde | Scotland | Scotland |  | 249500 | 611500 | Scottish Government (S36) | IEC3/73 | [5 empty] | 2004-10-29 |  | 2008-10-24
N00309W | 3236 | 2009-10-23 | A7 Energy | Greendykeside | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Greendykeside Farm , Longriggend , Airdrie , Lanarkshire | Strathclyde | Scotland | Scotland | ML6 7TT | 281134 | 670403 | North Lanarkshire Council | 04/01624/FUL | [5 empty] | 2004-09-13 | [6 empty] | 2005-05-11 | [5 empty] | 2007-11-01
N00310W | 3237 | 2009-07-24 | Salsburgh Windco Ltd | Salsburgh | Wind Onshore |  |  | 24 | n/a |  |  |  | 0 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Jersay Farm South of Salsburgh | Strathclyde | Scotland | Scotland |  | 282515 | 661635 | North Lanarkshire Council | 05/00132/FUL | [6 empty] | 2009-07-24
N00317W | 3240 | 2011-09-12 | Windjen Power Ltd / Dulas Ltd | Blaen Bowi Wind Farm (Extension) | Wind Onshore |  |  | 9.1 | n/a |  |  |  | 3 | 3 |  | n/a | Appeal Refused | Application Refused | BLAEN BOWI WIND FARM LAN FARM CAPEL IWAN NEWCASTLE EMLYN | Dyfed | Wales | Wales | SA38 9NN | 232500 | 236000 | Carmarthenshire County Council | W/09828 | [5 empty] | 2005-04-26 |  | 2007-09-28 |  |  | 2009-06-10
N00320W | 3241 | 2019-11-05 | Foresight Group | Gruig Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Operational | Operational | Gruig, Corkey, nr Cloughmills, Co. Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 126155 | 577763 | Northern Ireland Planning Service | D/2004/0790/F | [5 empty] | 2004-10-18 | [6 empty] | 2007-06-25 | [5 empty] | 2009-01-27
N00321W | 3242 | 2010-02-23 | B9 Energy / RES | Wolf Bog Wind Farm | Wind Onshore |  |  | 8.75 | n/a |  |  |  | 1.75 | 5 |  | n/a | Operational | Operational | Wolf Bog, Tildarg, nr Ballyclare, Co. Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 137865 | 553129 | Northern Ireland Planning Service | G/2004/1532/F | [5 empty] | 2004-05-01 | [6 empty] | 2005-11-02 | [5 empty] | 2007-11-01
N00322W | 3243 | 2011-10-24 | ESB | Curryfree Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | Curryfree , South of Newbuildings / Drumahoe and north of Dunamanagh, Co. Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 59555 | 572350 | Northern Ireland Planning Service | A/2004/1243/F | [5 empty] | 2004-11-24 | [6 empty] | 2008-05-12 |  |  |  |  | 2009-12-01 | 2011-08-01
N00323W | 3244 | 2019-01-03 | B9 Energy / RES | Altahullion Phase II | Wind Onshore |  |  | 11.7 | n/a |  |  |  | 1.3 | 9 |  | n/a | Operational | Operational | Altahullion Wind Farm, Dungiven, Co. Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 80176 | 575395 | Northern Ireland Planning Service | B/2004/0795/F | [5 empty] | 2004-11-22 | [6 empty] | 2006-04-06 |  |  |  |  | 2006-12-01 | 2007-09-01
N00325W | 3245 | 2017-08-23 | Greencoat (formerly Infinis/SSE) | Slieve Divena Phase 1 Wind Farm | Wind Onshore |  |  | 30 | n/a |  |  |  | 2.5 | 12 |  | n/a | Operational | Operational | Slieve Divena Sixmilecross Beragh Ballygawley County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 69602 | 524593 | Northern Ireland Planning Service | K/2005/0597/F | [5 empty] | 2005-03-01 | [6 empty] | 2007-05-17 | [5 empty] | 2009-03-10
N00326W | 3246 | 2006-11-07 | Renewable Energy Systems (RES) | Rhos Garn | Wind Onshore |  |  | 20 | n/a |  |  |  | 0 | 10 |  | n/a | Planning Permission Refused | Application Refused | Land to north of Talgarreg, and south of Mydroilyn. | Dyfed | Wales | Wales |  | 244550 | 252303 | Ceredigion County Council | A050648 | [5 empty] | 2005-06-01 |  | 2006-09-13
N00331W | 3247 | 2012-07-04 | REG Windpower (previously Cornwall Light and Power) | Loscar Farm | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 1.3 | 3 |  | n/a | Operational | Operational | Loscar Farm, Packman Lane, Harthill | South Yorkshire | Yorkshire and Humber | England |  | 451000 | 380000 | Rotherham Metropolitan Borough Council | [6 empty] | 2004-11-01 | [6 empty] | 2008-03-28 |  |  |  |  | 2010-01-01 | 2011-01-01
N00334W | 3248 | 2009-04-27 | EDF Energy | Langley Moor | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Burnhope Standagainstall Plantation, Long Edge, Burnhope, County Durham | Durham | North East | England |  | 420928 | 547703 | Durham County Council | [6 empty] | 2005-01-28 | [6 empty] | 2005-06-30 | [5 empty] | 2008-08-13
N00336W | 3249 | 2011-06-29 | E.ON UK | Escrick Park Community Power Project | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Escrick park community power project Glade road Esrick York | North Yorkshire | Yorkshire and Humber | England |  | 463935 | 439075 | Selby District Council | 8/11/72A | [6 empty] | 2011-06-29
N00348W | 3250 | 2010-12-07 | Zepher | Cwmpenanner | Wind Onshore |  |  | 24.2 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Cwm Penanner, Cerrid-Y-Drudion Corwen Conwy | Gwynedd | Wales | Wales |  | 291830 | 346415 | Gwynedd Council | 0/28528 | [5 empty] | 2004-01-04 |  | 2004-11-26
N00353W | 3251 | 2011-04-11 | Private Developer | Land approx 75m South of 141 | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Operational | Operational | Land approx 75m South of 141 Greencastle Road, Omagh | Co. Tyrone | Northern Ireland | Northern Ireland |  | 72186 | 544257 | Northern Ireland Planning Service | K/2005/0183/F | [5 empty] | 2005-02-03 | [6 empty] | 2005-04-26 | [5 empty] | 2007-07-01
N00355W | 3252 | 2013-10-08 | Airtricity Developments (UK) | Belmore Mountain | Wind Onshore |  |  | 30 | n/a |  |  |  | 3 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Belmore Mountain, Co Fermanagh (townlands of Gortahurk West, Carricknaseer, Moneyouragan, Tonardrum, Carrickmacsparrow and Gortatole, all within the civil parish of Cleenish) and lands at Cloughane Bridge, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 17498 | 505910 | Northern Ireland Planning Service | L/2005/0377/F | [6 empty] | 2013-10-08
N00356W | 3253 | 2016-05-10 | Wind Farm Developments / RES UK & Ireland | Hunter's Hill | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Operational | Operational | Hunter's Hill, (In the townlands of Tattymoyle Lower, Edergole, Killygordon and Tattanafinnell), Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 53811 | 517991 | Northern Ireland Planning Service | K/2005/0387/F | [5 empty] | 2005-02-24 | [6 empty] | 2008-12-01 |  |  |  |  | 2008-12-02 | 2010-09-22
N00359W | 3254 | 2010-03-09 | Northern Wind Power | Gortmonly Wind Energy | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Gortmonly Wind Energy project in townlands of Gortmonly, Dullerton & Eden, accessing onto Gortmonly Road, Bready, Strabane, Co. Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 55387 | 573642 | Northern Ireland Planning Service | J/2005/0213/F | [6 empty] | 2010-03-09
N00361W | 3255 | 2010-09-24 | Scottish Power Renewables | Lynemouth Windfarm | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Abandoned | Abandoned | North of Ashington | Northumberland | North East | England |  | 430000 | 590000 | Northumberland County Council | CM/20060877 | [5 empty] | 2006-10-13 |  | 2007-05-30 |  |  |  | 2008-02-20 | 2008-02-20
N00363W | 3256 | 2012-01-30 | Green Power | Broadmeadows | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 |  | n/a | Appeal Refused | Application Refused | Selkirk | Borders | Scotland | Scotland |  | 341000 | 631500 | Scottish Borders Council | 04/02501/FUL | 11/00028/REF |  |  |  |  | 2004-12-23 |  | 2011-06-13 |  |  | 2012-01-25
N00366W | 3258 | 2011-10-25 | Scottish Power Renewables | Arecleoch Windfarm | Wind Onshore |  |  | 120 | n/a |  |  |  | 2 | 60 |  | n/a | Operational | Operational | Arecleoch and Kilgallioch Forest near Barrhill | South Ayrshire | Scotland | Scotland |  | 221500 | 578500 | Scottish Government (S36) | [6 empty] | 2006-04-03 | [6 empty] | 2008-06-01 |  |  |  |  | 2009-09-01 | 2011-06-14
N00367W | 3259 | 2006-05-10 | West Coast Energy (for RDC/Falk) | Limmer Hill | Wind Onshore |  |  | 99 | n/a |  |  |  | 3 | 33 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Limmer Hill, Near Rigside Nr Abington | Strathclyde | Scotland | Scotland |  | 289000 | 630000 | Scottish Government (S36) | CL/05/0563 | [6 empty] | 2006-05-10
N00368W | 3260 | 2011-08-16 | Force 9 Energy | Mark Hill | Wind Onshore |  |  | 56 | n/a |  |  |  | 2.3 | 24 |  | n/a | Operational | Operational | Mark's Hill, Barrhill | Strathclyde | Scotland | Scotland |  | 225000 | 585000 | Scottish Government (S36) | [6 empty] | 2005-08-19 | [6 empty] | 2008-06-01 |  |  |  |  | 2009-10-01 | 2011-06-01
N00374W | 3262 | 2011-07-01 | Your Energy | Parham Airfield (wind) | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Abandoned | Abandoned | Parham Airfield between Great Glenham and Marlesford | Suffolk | Eastern | England |  | 632000 | 261000 | Suffolk Coastal District Council | C05/0400 | [5 empty] | 2005-03-01 | [6 empty] | 2005-10-05
N00380W | 3263 | 2016-08-01 | Screggagh Windfarm | Screggagh | Wind Onshore |  |  | 19.5 | n/a |  |  |  | 2.5 | 8 |  | n/a | Operational | Operational | Screggagh, Screggagh & Stranisk townlands, Fintona. Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 54566 | 520549 | Northern Ireland Planning Service | K/2005/0810/F | [5 empty] | 2005-04-18 | [6 empty] | 2008-05-13 |  |  |  |  | 2009-07-01 | 2011-03-21
N00386W | 3264 | 2010-06-09 | Private Developer | Westmill Wind Farm | Wind Onshore |  |  | 6.5 | n/a |  |  |  | 1.3 | 5 |  | n/a | Operational | Operational | Westmill Farm , Highworth Road , Watchfield , Swindon , Oxon | Oxfordshire | South East | England | SN6 8TH | 423218 | 190825 | Vale of White Horse District Council | WAT/1611/9/00 | [5 empty] | 2000-09-01 | [6 empty] | 2005-07-07 | [5 empty] | 2008-01-01
N00388W | 3265 | 2007-11-16 | Private Developer | Clochnahill Windfarm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Clochnahill Farm Temple of Fiddes Mearns Aberdeenshire | Grampian | Scotland | Scotland |  | 381637 | 782918 | Aberdeenshire Council | ENQ/2005/0667 | [5 empty] | 2006-05-08 |  | 2007-03-20
N00396W | 3267 | 2010-08-02 | Harworth Power | Bleak House | Wind Onshore |  |  | 6.5 | n/a |  |  |  | 2.2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Bleak House 1130m east of Wimbley Rd 1100m north of Cannock Road (A5190) | Staffordshire | West Midlands | England |  | 402734 | 310882 | East Staffordshire Borough Council | CH/08/0001 | [6 empty] | 2010-08-02
N00404W | 3268 | 2009-10-05 | E.ON UK | Auchencorth Moss | Wind Onshore |  |  | 45 | n/a |  |  |  | 2 | 18 |  | n/a | Planning Permission Refused | Application Refused | Auchencorth Moss Penicuik Midlothian | Lothian | Scotland | Scotland |  | 321080 | 656760 | Midlothian Council | 06/00067/FUL | [5 empty] | 2006-01-27 |  | 2008-02-12
N00407W | 3270 | 2008-06-25 | Mark Caudwell Ltd | Orby Windfarm (Resubmission) | Wind Onshore |  |  | 54 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Orby Marsh , Hogsthorpe, Skegness | Lincolnshire | East Midlands | England |  | 551500 | 367500 | DECC (S36) | N/84/2334/05 | [6 empty] | 2008-06-25
N00409W | 3271 | 2005-12-13 | Lomond Energy | Tillyrie | Wind Onshore |  |  | 4.186 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Land At Tillyrie Farm Milnathort Kinross KY13 0RW | Tayside | Scotland | Scotland |  | 310500 | 708500 | Perth and Kinross Council | 500517 | [5 empty] | 2005-03-18 |  | 2005-12-13
N00422W | 3272 | 2010-03-03 | Private Developer | Lodge Farm 1 | Wind Onshore |  |  | 1 | n/a |  |  |  | 1 | 1 |  | n/a | Operational | Operational | Lodge Farm, Hubberston, Milford Haven | Dyfed | Wales | Wales |  | 188700 | 207500 | Pembrokeshire County Council | 04/1243/PA | [5 empty] | 2005-01-07 | [6 empty] | 2005-10-01 | [5 empty] | 2006-08-01
N00424W | 3273 | 2006-05-26 | RWE npower | Snowgoat Glen Wind Farm II | Wind Onshore |  |  | 13 | n/a |  |  |  | 0 | 10 |  | n/a | Planning Permission Refused | Application Refused | Near Dunning Perth and Kinross | Tayside | Scotland | Scotland |  | 300500 | 710500 | Perth and Kinross Council | 05/01043 | [5 empty] | 2005-06-01 |  | 2005-11-30
N00429W | 3274 | 2010-06-09 | Airtricity | Invercassley Windfarm | Wind Onshore |  |  | 55 | n/a |  |  |  | 2 | 23 |  | n/a | Appeal Refused | Application Refused | Invercassley Near Lairg Sutherland Highland | Highland | Scotland | Scotland |  | 242193 | 905694 | Scottish Government (S36) | 05/00400/FULSU | [5 empty] | 2005-10-28 |  | 2006-12-13 |  |  | 2007-12-28
N00432W | 3275 | 2012-03-08 | West Coast Energy/Yelland Wind Energy Ltd | Yelland Wind Farm | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | West of A386 on Bowerland Road | Devon | South West | England |  | 250500 | 86500 | West Devon Borough Council | 7276/2005/OKE | [5 empty] | 2005-09-01 |  | 2006-11-08
N00433W | 3276 | 2004-02-05 | Ecotricity | Partfield Farm | Wind Onshore |  |  | 5.581 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Partfield Farm, Nympsfield | Avon | South West | England |  | 365081 | 174670 | South Gloucestershire Council | S.00/1628 | [5 empty] | 2000-10-09 | 2001-05-08
N00444W | 3277 | 2010-01-06 | RWE npower | Carno 'A'and 'B' Wind Farm, (Extension) | Wind Onshore |  |  | 15.6 | n/a |  |  |  | 1.3 | 12 |  | n/a | Operational | Operational | Cwm Cledan , Carno , Powys | Powys | Wales | Wales |  | 293000 | 295000 | Powys County Council | M2003/1156 | [5 empty] | 2003-10-10 | [6 empty] | 2006-07-10 | [5 empty] | 2009-03-01
N00450W | 3278 | 2011-02-09 | Renewable Energy Systems (RES) | Careston Estate | Wind Onshore |  |  | 52 | n/a |  |  |  | 2 | 26 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Careston Estate, Angus | Tayside | Scotland | Scotland |  | 353500 | 760500 | Scottish Government (S36) | [7 empty] | 2011-02-09
N00451W | 3279 | 2011-10-31 | Scottish and Southern Energy (SSE) | Waterhead Moor | Wind Onshore |  |  | 72.5 | n/a |  |  |  | 2.5 | 29 |  | n/a | Planning Application Withdrawn | Application Withdrawn | North of Largs, Ayreshire | Strathclyde | Scotland | Scotland |  | 226029 | 665781 | Scottish Government (S36) | [7 empty] | 2011-10-31
N00454W | 3280 | 2009-06-10 | Force 9 Energy/Catamount | Barmoor | Wind Onshore |  |  | 27 | n/a |  |  |  | 0 | 9 |  | n/a | Planning Permission Refused | Application Refused | NE of Ford | Northumberland | North East | England |  | 398000 | 638000 | Northumberland County Council | 06/B/0148 | [5 empty] | 2006-03-02 |  | 2008-03-27
N00534W | 3282 | 2005-07-27 | Timet UK | Timet UK | Wind Onshore |  |  | 1.977 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Warnarlwydd, Swansea | West Glamorgan | Wales | Wales |  | 260000 | 195000 | City and County Council of Swansea | 2003/1860 | [5 empty] | 2003-09-15 |  | 2004-08-16
N00535W | 3283 | 2006-05-26 | RWE npower | Snowgoat Glen Wind Farm | Wind Onshore |  |  | 23.488 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Near Dunning Perth and Kinross | Tayside | Scotland | Scotland |  | 300500 | 710500 | Perth and Kinross Council | 04/01049/FUL | [6 empty] | 2006-05-26
N00536W | 3284 | 2006-05-02 | Scottish and Southern Energy (SSE) | Broubster Forest | Wind Onshore |  |  | 116 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Nr Reay | Highland | Scotland | Scotland |  | 301550 | 959550 | Scottish Government (S36) | [7 empty] | 2006-05-02
N00537W | 3285 | 2010-06-09 | Messrs James and Ronald Innes | Achairn | Wind Onshore |  |  | 6.15 | n/a |  |  |  | 2.05 | 3 |  | n/a | Operational | Operational | West of Wick, Caithness | Highland | Scotland | Scotland |  | 329950 | 950650 | Highland Council | CA2004366 | [5 empty] | 2004-08-11 | [6 empty] | 2006-03-01 |  |  |  |  | 2009-04-01 | 2009-05-20
N00540W | 3287 | 2006-05-09 | Orkney Sustainable Energy | Hill of Garvock Wind Energy Project (2) | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Planning Permission Refused | Application Refused | East Bradieston Farm Laruencekirk | Grampian | Scotland | Scotland |  | 370000 | 770000 | Aberdeenshire Council | APP2004/1412 | P/PPA/110/504 |  |  |  |  | 2004-04-22 |  | 2004-10-26
N00541W | 3288 | 2008-06-11 | Scottish and Southern Energy (SSE) | Muckla Moor | Wind Onshore |  |  | 249 | n/a |  |  |  | 0 | 83 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 4km NW of Herra | Shetland | Scotland | Scotland |  | 443750 | 1167550 | Scottish Government (S36) | [7 empty] | 2008-06-11
N00545W | 3289 | 2005-10-27 | CATAMOUNT CYMRU CYF (agent ENTEC UK Ltd) Force 9 Energy | Blaengwen Farm | Wind Onshore |  |  | 30.233 | n/a |  |  |  | 3 | 10 |  | n/a | Planning Permission Refused | Application Refused | Pencader , Carms. | Dyfed | Wales | Wales | SA39 94P | 246387 | 233404 | Carmarthenshire County Council | W/09205 | [5 empty] | 2005-01-27 |  | 2005-11-24
N00548W | 3290 | 2009-05-06 | EDF Energy | High Hedley Hope 2 (Extension) | Wind Onshore |  |  | 5.2 | n/a |  |  |  | 1.3 | 4 |  | n/a | Operational | Operational | High Hedley Farm, Tow Law, Bishop Auckland, County Durham | Durham | North East | England |  | 415700 | 541000 | Durham County Council | [6 empty] | 2004-08-12 | [6 empty] | 2005-07-06 | [5 empty] | 2008-06-25
S0001W2 | 3292 | 2013-07-30 | CRE Energy/ Scottish Power | Beinn an Tuirc | Wind Onshore |  |  | 30 | n/a |  |  |  | 0.37 | 46 |  | n/a | Operational | Operational | Nr. Carradale | Strathclyde | Scotland | Scotland |  | 173950 | 636900 | Argyll and Bute Council | [6 empty] | 1998-04-20 | [6 empty] | 1999-04-28 | [5 empty] | 2001-12-23
S0002W1 | 3293 | 2004-08-06 | Micon Wind Turbines (UK) Ltd | West Garty Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 0 | 16 |  | n/a | Planning Permission Refused | Application Refused | West Garty Estate Near Helmsdale Sutherland | Highland | Scotland | Scotland |  | 297000 | 914000 | Highland Council | [6 empty] | 1995-10-09 |  | 1999-07-19
S0002W2 | 3294 | 2010-02-03 | CRE Energy/ Scottish Power | Cnoc Donn Arnicle | Wind Onshore |  |  | 15 | n/a |  |  |  | 0.57 | 26 |  | n/a | Operational | Operational | Situated next to Beinn an Tuirc Kintyre | Strathclyde | Scotland | Scotland |  | 175200 | 637600 | Argyll and Bute Council | [6 empty] | 1998-04-20 | [6 empty] | 1999-04-28 | [5 empty] | 2001-10-01
S0003W1 | 3295 | 2006-04-27 | RWE npower | Beinn Ghlas Wind Farm | Wind Onshore |  |  | 7.837 | n/a |  |  |  | 0.55 | 14 |  | n/a | Operational | Operational | Land at Carn Gaibhre, Argyle and Bute | Strathclyde | Scotland | Scotland |  | 196500 | 726000 | Argyll and Bute Council | [6 empty] | 1997-05-07 | [6 empty] | 1998-08-21 | [5 empty] | 1999-06-25
S0004W1 | 3296 | 2011-04-11 | RWE npower | Bendealt Wind Farm, Highland | Wind Onshore |  |  | 9 | n/a |  |  |  | 0.5 | 18 |  | n/a | Operational | Operational | Novar Estate | Highland | Scotland | Scotland |  | 255500 | 871000 | Highland Council | [6 empty] | 1995-05-17 | [6 empty] | 1996-08-27 | [5 empty] | 1997-09-01
S0005W1 | 3297 | 2009-12-03 | RWE npower | Meall an Tuirc Wind Farm | Wind Onshore |  |  | 17 | n/a |  |  |  | 0 | 34 |  | n/a | Operational | Operational | Novar Estate | Highland | Scotland | Scotland |  | 255500 | 871500 | Highland Council | [6 empty] | 1995-05-17 | [6 empty] | 1996-08-27 | [5 empty] | 1997-09-01
S0005W2 | 3298 | 2011-08-08 | RWE npower | An Suidhe | Wind Onshore |  |  | 19.3 | n/a |  |  |  | 0.9 | 23 |  | n/a | Operational | Operational | Dalmally, Strathclyde. PA33 On the eastern shore of Loch Awe | Strathclyde | Scotland | Scotland |  | 200483 | 707563 | Argyll and Bute Council | 05/01711/VARCON | [5 empty] | 2005-08-22 | [6 empty] | 2005-10-21 |  |  |  |  | 2007-06-01 | 2010-08-04
S0006W2 | 3299 | 2011-02-10 | PowerGen and Natural Power | Roughside Hill | Wind Onshore |  |  | 30 | n/a |  |  |  | 1.25 | 24 |  | n/a | Operational | Operational | Roughside Moss, Peebles | Borders | Scotland | Scotland |  | 333000 | 646200 | Scottish Borders Council | 00/00371/FUL | [5 empty] | 2000-03-23 | [6 empty] | 2000-08-14 | [5 empty] | 2002-09-15
S0007W2 | 3300 | 2013-10-08 | PowerGen and Natural Power Consultants Ltd | Bowbeat Wind Farm | Wind Onshore |  |  | 31.2 | n/a |  |  |  | 1.3 | 24 |  | n/a | Operational | Operational | Roughside Hill and Emily Bank, Peebles | Lothian | Scotland | Scotland |  | 329600 | 647500 | Midlothian Council | [6 empty] | 2000-03-23 | [6 empty] | 2000-08-14 | [5 empty] | 2002-09-05
S0010W1 | 3301 | 2011-04-11 | Trigen | Hagshaw Hill Wind Farm | Wind Onshore |  |  | 7.8 | n/a |  |  |  | 0.6 | 13 |  | n/a | Operational | Operational | The site lies 4km west of Douglas | Strathclyde | Scotland | Scotland |  | 278980 | 630740 | South Lanarkshire Council | [6 empty] | 1994-05-13 | [6 empty] | 1994-11-02 | [5 empty] | 1995-11-01
S0012W1 | 3302 | 2011-10-30 | Windcluster Ltd | Laggan Windcluster | Wind Onshore |  |  | 2.977 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Land at Island and Corrary Farms | Strathclyde | Scotland | Scotland |  | 132700 | 657200 | Argyll and Bute Council | 01/95/00461 | [5 empty] | 1995-05-18 |  | 1999-06-11
S0028W3 | 3305 | 2004-07-27 | Private Developer | Meall Mhor Wind Farm | Wind Onshore |  |  | 2.233 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Kintarbert, Argyll | Strathclyde | Scotland | Scotland |  | 183500 | 674400 | Argyll and Bute Council | 00/01330/DET | [6 empty] | 2004-07-27
S0030W3 | 3306 | 2010-02-02 | Arnish Electric Ltd / Farm Energy | Arnish Moor | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Operational | Operational | Nr Stornaway, Isle of Lewis | Western Isles | Scotland | Scotland |  | 139155 | 929460 | Comhairle nan Eilean Siar Council | [6 empty] | 2001-06-01 | [6 empty] | 2001-09-01 |  |  |  |  | 2006-12-01 | 2006-12-01
S0034W3 | 3307 | 2009-10-05 | Orkney Sustainable Energy | Burgar Hill | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | Evie, Orkney | Orkney Islands | Scotland | Scotland |  | 334300 | 1026200 | Orkney Islands Council | [6 empty] | 1997-02-13 | [6 empty] | 1997-07-07 | [5 empty] | 2006-12-01
S0035W3 | 3308 | 2009-10-05 | Vestas | Thorfinn Wind Farm - NM2000 | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 1.15 | 2 |  | n/a | Operational | Operational | Burgar Hill and the Wards, Evie, Orkney | Orkney Islands | Scotland | Scotland | KW17 2PJ | 334790 | 1025240 | Orkney Islands Council | 02/189/PPF | [5 empty] | 1998-10-23 | [6 empty] | 1999-11-22 | [5 empty] | 2000-04-01
S0036W3 | 3309 | 2010-06-09 | Fivestone Ltd (subsidiary of Abbey Produce) | Hill of Lybster | Wind Onshore |  |  | 4.9 | n/a |  |  |  | 1.3 | 4 |  | n/a | Operational | Operational | Forss Phase 2, Caithness | Highland | Scotland | Scotland |  | 302000 | 969500 | Highland Council | CA2001030 | [5 empty] | 2000-04-28 | [6 empty] | 2001-06-22 | [5 empty] | 2003-02-08
S0038W3 | 3310 | 2009-10-05 | Shetland Aerogenerators | Burradale Hill | Wind Onshore |  |  | 3.68 | n/a |  |  |  | 0.75 | 5 |  | n/a | Operational | Operational | Lerwick, Shetland, N Isles | Shetland | Scotland | Scotland |  | 442500 | 1142500 | Shetland Islands Council | [6 empty] | 1993-10-08 | [6 empty] | 1994-02-03 | [5 empty] | 2000-12-16
S0045W3 | 3311 | 2016-02-15 | Green Investment Bank (Blackrock) | Glens of Foudland | Wind Onshore |  |  | 26 | n/a |  |  |  | 1.3 | 20 |  | n/a | Operational | Operational | Bognie Estate, Upper Milburn, Aberdeenshire | Grampian | Scotland | Scotland |  | 361900 | 837400 | Aberdeenshire Council | SO10069PF | [5 empty] | 2001-01-23 | [6 empty] | 2001-10-04 | [5 empty] | 2005-07-22
A0014 | 3313 | 2013-11-06 | John Laing Environmental Assets Group | Castle Pill - Repowering | Wind Onshore |  |  | 3.2 | n/a |  |  |  | 0.8 | 4 |  | n/a | Operational | Operational | Steynton, Pembroke, Dyfed | Dyfed | Wales | Wales | SA7 1 | 191995 | 206665 | Pembrokeshire County Council | 05/0394/PA | APP/N6845/A/05/1188977 |  |  |  |  | 2005-06-22 |  | 2005-12-19 |  |  |  | 2005-12-19 | 2005-12-19 | [5 empty] | 2009-06-01
B1035 | 3316 | 2014-12-16 | Airvolution Energy | Ysgellog 2 Wind Farm | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Bodewryd Farm, Rhosgoch, Builth Wells, Powys | Gwynedd | Wales | Wales |  | 240353 | 391092 | Isle of Anglesey County Council | 38C301A/EIA/RE | [5 empty] | 2014-03-24 |  | 2015-01-13
B1037 | 3317 | 2020-05-21 | BayWa r.e. (formerly Forsa) | Whitelaw Brae Wind Farm | Wind Onshore |  |  | 50.4 | n/a |  |  |  | 3.6 | 14 | 133.5 | n/a | Appeal Granted | Awaiting Construction | Whitelaw Brae Wind Farm, Tweedsmuir, Biggar, Strathclyde | Scottish Borders | Scotland | Scotland | ML12 6QS | 306039 | 621476 | Scottish Government (S36) | EC00002090 | WIN-140-4 |  |  |  |  | 2015-01-19 |  |  | 2015-11-25 |  |  | 2017-12-07 | 2017-12-07
B0503 | 3318 | 2013-12-09 | West Coast Energy | West Dorset Wind Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | farmland south west of Milborne St Andrew, north of Tolpuddle and north east of Puddletown | Dorset | South West | England |  | 379205 | 95885 | West Dorset District Council | 1/D/13/000183 | [5 empty] | 2013-02-06 | 2013-10-24
C2138 | 3319 | 2016-05-04 | Estuary Energy | Perry's Farm Wind Farm | Wind Onshore |  |  | 6.8 | n/a |  |  |  | 3.4 | 2 | 135 | n/a | Planning Permission Refused | Application Refused | Land north of National Grid Grain LNG facility and west of B2001 Grain Road, Isle of Grain | Kent | South East | England |  | 586220 | 176394 | Medway Council | MC/15/2035 | [5 empty] | 2015-06-15 |  | 2016-01-21
C1563 | 3320 | 2013-11-14 | Gartly Wind Partnership | Hill of Corksie - resubmission | Wind Onshore |  |  | 7.2 | n/a |  |  |  | 0.9 | 8 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Hill of Corskie Gartly Huntly | Grampian | Scotland | Scotland |  | 354484 | 832718 | Aberdeenshire Council | APP/2013/2063 | [5 empty] | 2013-07-03 | 2013-10-08
C1708 | 3321 | 2015-01-05 | Windflow UK | New Holland | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Operational | Operational | Land Near New Holland, Stratheast Road, Holm, Orkney, Orkney Isles | Orkney Islands | Scotland | Scotland | KW17 2SA | 350053 | 1003214 | Orkney Islands Council | 13/261/TPP | [5 empty] | 2013-07-29 | [6 empty] | 2013-11-06 | [5 empty] | 2014-10-20
B0067 | 3324 | 2013-12-24 | REG Windpower | High Pow Extension | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Percy Hill, Boltongate, Wigton, Cumbria | Cumbria | North West | England |  | 324221 | 543085 | Allerdale Borough Council | 2/2013/0519 | [5 empty] | 2013-07-12 | 2013-12-23
B1041 | 3325 | 2019-06-13 | Seegronan Windfarm | Seegronan Wind Farm Extension | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Appeal Granted | Awaiting Construction | Killeter , Strabane , Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 122608 | 534966 | Northern Ireland Planning Service | J/2013/0187/F | 2014/A0180 |  |  |  |  | 2013-07-09 |  |  | 2014-12-03 |  |  | 2017-06-30 | 2017-06-30 |  |  |  | 2022-06-30
B1043 | 3326 | 2016-05-27 | Scottish and Southern Energy (SSE) | Bessy Bell 3 Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.3 | 10 |  | n/a | Appeal Refused | Application Refused | Bessy Bell Mountain Baronscourt Estate Newtownstewart, County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 49687 | 547922 | Northern Ireland Planning Service | J/2013/0080/F | 2013/A0220 |  |  |  |  | 2013-03-28 |  |  | 2014-02-01 |  | 2016-05-16
12019W3 | 3334 | 2013-12-19 | West Coast Energy | Sober Hill Wind Farm | Wind Onshore |  |  | 1.465 | n/a |  |  |  | 0.25 | 6 |  | n/a | Planning Permission Refused | Application Refused | Sober Hill Wind Farm North Newbald Humberside | Humberside | Yorkshire and Humber | England |  | 492444 | 438545 | East Riding of Yorkshire Council | [6 empty] | 1995-09-01 |  | 1995-12-14
A0262 | 3335 | 2013-12-18 | Cornwall Light and Power | Sancton Hill | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | nr Market Weighton, Sancton, York, North Yorkshire | Humberside | Yorkshire and Humber | England | YO43 4RH | 491554 | 439660 | East Riding of Yorkshire Council | 08/05723/STPFE | [5 empty] | 2008-12-12 |  | 2009-03-19
IF1447 | 3338 | 2013-12-13 | Private Developer | MELIN, Pen Y Bank | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | CASTLE MORRIS, Haverfordwest | Dyfed | Wales | Wales | SA62 5EL | 189824 | 229416 | Pembrokeshire County Council | 12/1100/PA | [5 empty] | 2013-02-27 |  | 2013-10-02
C2477 | 3339 | 2015-01-08 | Tellus Energy Ltd | Arbikie Wind Cluster | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land 900M West Of Rossie School Mountboy Montrose | Tayside | Scotland | Scotland |  | 365471 | 753772 | Angus Council | 13/01069/EIAL | [5 empty] | 2013-12-09 | 2014-12-18
C0700 | 3340 | 2014-01-19 | Private Developer | Ascog Farm Wind Turbines | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Appeal Refused | Application Refused | Ascog Farm, Balmory Road, Ascog, Isle Of Bute, Argyll And Bute | Strathclyde | Scotland | Scotland | PA20 9LL | 210349 | 663052 | Argyll and Bute Council | 12/02202/PP | PPA-130-2032 |  |  |  |  | 2012-10-29 |  | 2013-05-23 |  |  | 2013-12-04
C2409 | 3342 | 2016-08-02 | Green Cat Renewables | Blair Data Centre | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 | 100 | n/a | Appeal Refused | Application Refused | Blair Farm, Glasgow Road, Kilmarnock | East Ayrshire | Scotland | Scotland | KA3 6ES | 248677 | 647358 | East Ayrshire Council | 15/0173/PP | PPA-190-2057 |  |  |  |  | 2015-03-31 |  |  | 2016-03-17 |  | 2016-07-12
C2396 | 3343 | 2016-05-27 | Vento Ludens | Brown Muir Wind Farm (resubmission) | Wind Onshore |  |  | 36 | n/a | 0.9 |  |  | 3 | 12 | 126 | n/a | Appeal Refused | Application Refused | Land At Brown Muir Blackhills Elgin Moray | Grampian | Scotland | Scotland |  | 327075 | 854781 | Moray Council | 14/02090/EIA | PPA-300-2044 |  |  |  |  | 2014-11-10 |  | 2015-09-18 | 2015-12-15 |  | 2016-05-26
C2401 | 3345 | 2014-12-23 | Wpd Scotland Limited | Cnoc Morail | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 | 99.5 | n/a | Planning Permission Refused | Application Refused | Land 1200M NW Of Acharole 18 West Watten Watten | Highland | Scotland | Scotland |  | 322300 | 952950 | Highland Council | 14/04375/FUL | [5 empty] | 2014-11-21 |  | 2016-01-19
B0358 | 3347 | 2014-01-31 | West Coast Energy | Dodd Hill | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | Dodd Hill, Tealing, Angus | Tayside | Scotland | Scotland |  | 345500 | 739500 | Angus Council | 12/00490/EIAL | [5 empty] | 2012-05-23 |  | 2013-03-14 |  |  | 2013-12-06
C2144 | 3348 | 2014-01-30 | Gartly Wind Partnership | Hill of Corskie - resubmission 2 | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 0.9 | 5 |  | n/a | Planning Permission Refused | Application Refused | Hill of Corskie Gartly Huntly | Grampian | Scotland | Scotland |  | 354445 | 832682 | Aberdeenshire Council | APP/2013/3216 | [5 empty] | 2013-10-14 |  | 2014-01-06
C2210 | 3349 | 2014-01-30 | Viridis Wind Turbines | Hoddlesden Moss | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Hoddlesden Moss Hoddlesden Darwen | Lancashire | North West | England |  | 372388 | 420215 | Blackburn with Darwen Borough Council | 10/13/0829 | [5 empty] | 2013-10-17 | 2014-01-02
B0607 | 3350 | 2014-01-30 | Lomond Energy | Milnathort Community Wind Cluster | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Appeal Refused | Application Refused | Land At Tillyrie Hill Milnathort | Tayside | Scotland | Scotland |  | 310140 | 708595 | Perth and Kinross Council | 12/01765/FLL | 13/00012/REF |  |  |  |  | 2012-10-03 |  | 2013-08-07 |  |  | 2014-01-07
C2481 | 3352 | 2015-01-08 | Partnerships for Renewables | Pannington Hall | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land South of Pannington Hall, Pannington Hall Lane, Wherstead | Suffolk | Eastern | England |  | 613950 | 240910 | Babergh District Council | B/13/01476 | [5 empty] | 2013-12-09 |  | 2014-12-17
C2479 | 3353 | 2014-11-06 | Ore Valley Housing Association | Wester Durie Farm | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land South Of Wester Durie Farm Durie Leven Fife | Fife | Scotland | Scotland |  | 336257 | 701912 | Fife Council | 13/03643/EIA | [5 empty] | 2013-12-06 |  | 2014-08-22
B0324 | 3354 | 2016-04-15 | Bernard Matthews | Weston Airfield Wind Turbines | Wind Onshore |  |  | 3.6 | n/a |  |  |  | 1.8 | 2 |  | n/a | Operational | Operational | The Old Airfield, Airfield Lane, Weston Longville | Norfolk | Eastern | England | NR9 5JF | 609009 | 315326 | Broadland District Council | 20101283 | APP/K2610/A/11/2156693 |  |  |  |  | 2010-08-17 |  | 2012-01-23 |  |  |  | 2012-01-23 | 2012-01-23 |  |  |  |  | 2014-01-26 | 2015-03-15
AA799 | 3355 | 2014-03-03 | Kelda Water Services | Penny Pot Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Planning Application Withdrawn | Application Withdrawn | land next to Scargill Reservoir | North Yorkshire | Yorkshire and Humber | England |  | 423929 | 455429 | Harrogate Borough Council | [6 empty] | 2012-07-27 | 2014-02-06
B1256 | 3356 | 2015-11-05 | Airvolution Energy | Washpit Drove | Wind Onshore |  |  | 4.7 | n/a |  |  |  | 2.35 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | between Swaffham and Sporle | Norfolk | Eastern | England |  | 583110 | 310388 | Breckland Council | 3PL/2014/0106/F | [5 empty] | 2014-02-17 | 2015-10-06
B1257 | 3357 | 2016-06-23 | Airvolution Energy | J2a | Wind Onshore |  |  | 4.7 | n/a |  |  |  | 2.35 | 2 |  | n/a | Abandoned | Abandoned | east of the M90 at Junction 2a | Fife | Scotland | Scotland |  | 314375 | 687820 | Fife Council | 14/00316/EIA | [5 empty] | 2014-01-31
01018W4 | 3358 | 2015-01-09 | ECONET LTD | Blood Hill Wind Farm | Wind Onshore |  |  | 2.25 | n/a |  |  |  | 0.15 | 10 |  | n/a | Decommissioned | Decommissioned | Blood Hill nr. Coronation Farm , Somerton , Great Yarmouth , Norfolk | Norfolk | Eastern | England |  | 646900 | 318800 | Great Yarmouth Borough Council | [6 empty] | 1998-03-17 |  | 1999-08-06 | [10 empty] | 2000-07-24
C1265 | 3359 | 2017-07-12 | Orton Park Wind Energy | Orton Park Farm | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Operational | Operational | Orton Park Farm, Orton Park, Carlisle | Cumbria | North West | England | CA5 6JU | 335490 | 553153 | Carlisle City Council | 13/0323 | [5 empty] | 2013-04-25 | [6 empty] | 2013-07-19 |  |  |  |  | 2016-06-15 | 2017-06-15
C1509 | 3361 | 2017-02-23 | Private Developer | PROMISED LAND FARM | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Operational | Operational | PROMISED LAND FARM, CRANK ROAD, KINGS MOSS, ST HELENS, LANCASHIRE, WA11 8RW | Merseyside | North West | England |  | 351169 | 401881 | St Helens Council | P/2013/0373 | [5 empty] | 2013-05-15 | [6 empty] | 2013-10-15 |  |  |  |  | 2014-09-22 | 2014-10-22
C1682 | 3362 | 2014-12-05 | Ventus Renewables Ltd | Ardlawhill Wood Wind Turbines - resubmission | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land at Ardlawhill Wood New Aberdour Fraserburgh | Grampian | Scotland | Scotland |  | 387725 | 861054 | Aberdeenshire Council | APP/2013/2188 | [5 empty] | 2013-07-16 |  | 2014-11-06
C1688 | 3363 | 2014-03-03 | Longhill Wind Farm Ltd | PATES HILL WIND FARM Extension | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | PATESHILL WIND FARM, HARBURN, WEST CALDER | Lothian | Scotland | Scotland |  | 298919 | 658264 | West Lothian Council | 0466/FUL/13 | [5 empty] | 2013-07-11 | 2014-01-31
C2220 | 3364 | 2014-03-03 | Intelligent Land Investments | Low Ugadale Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.75 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land North West Of Low Ugadale Farm Campbeltown Argyll And Bute | Strathclyde | Scotland | Scotland |  | 177137 | 629136 | Argyll and Bute Council | 13/01146/PP | [5 empty] | 2013-10-16 | 2014-01-24
C2637 | 3367 | 2015-01-06 | Crofts Farm Renewables Ltd | Crofts Farm | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land 625M To The North Of Crofts Farm Carmyllie | Tayside | Scotland | Scotland |  | 357247 | 744495 | Angus Council | 14/00049/FULL | [5 empty] | 2014-01-23 |  | 2014-12-22
C2650 | 3368 | 2018-05-17 | Private Developer | Nethercott Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Operational | Operational | Land At Nethercott Farm Tetcott Holsworthy Devon | Devon | South West | England | EX22 6RG | 235330 | 96451 | Torridge District Council | 1/0036/2014/FULM | [5 empty] | 2014-01-15 | [6 empty] | 2014-07-03 |  |  |  | 2017-07-03 | 2016-08-15 | 2016-12-15
EN00516 | 3369 | 2016-08-23 | Empowering Wind | Riverside Stadium | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Planning Permission Expired | Planning Permission Expired | Middlesbrough Football Club, Riverside Stadium, Middlesbrough | Cleveland | North East | England | TS3 6RS | 450661 | 520605 | Middlesbrough Council | M/FP/0849/08/P | [5 empty] | 2008-05-16 | [6 empty] | 2008-07-07 |  |  |  | 2016-08-23
IF1329 | 3370 | 2015-04-28 | Messrs Stevenson, Watson and Brunton | Bonerbo Wind Turbines (resubmission) | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Operational | Operational | Balmonth And Drumrack Farms Bonerbo Dunino Fife | Fife | Scotland | Scotland |  | 353841 | 707688 | Fife Council | 12/02748/FULL | [5 empty] | 2012-07-10 | [6 empty] | 2013-05-14 |  |  |  |  | 2014-02-11 | 2014-12-15
C2765 | 3371 | 2020-06-25 | Renewable Energy Systems (RES) | Aberarder Wind Farm | Wind Onshore |  |  | 49.9 | n/a |  |  |  | 3 | 12 | 130 | n/a | Appeal Granted | Awaiting Construction | Land 4.5km South East Of Aberarder House Aberarder Inverness | Highland | Scotland | Scotland | IV2 6UE | 264839 | 820696 | Highland Council | 15/00737/FUL | PPA-270-2158 |  |  |  |  | 2015-03-03 |  | 2016-04-19 | 2016-07-14 |  |  | 2017-04-07 | 2017-04-07
B0714 | 3372 | 2015-10-29 | Renewable Energy Systems (RES) | Barville Farm Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Appeal Refused | Application Refused | Tilmanstone | Kent | South East | England |  | 630120 | 149980 | Dover District Council | 13/00914 | APP/X2220/W/14/3000041 |  |  |  |  | 2013-10-26 |  | 2014-08-15 | 2014-10-01 |  | 2015-10-12
C2732 | 3373 | 2020-01-15 | Wind Harvest | Beinn Mheadhonach | Wind Onshore |  |  | 4 | n/a |  |  |  | 1 | 4 | 99.5 | n/a | Planning Permission Granted | Awaiting Construction | Land 1600M NE Of Sumardale Cro, Struan, Isle Of Skye, Highlands | Highland | Scotland | Scotland | IV56 8FY | 139317 | 837466 | Highland Council | 18/03214/FUL | [5 empty] | 2018-07-10 | [6 empty] | 2019-08-20 |  |  |  | 2022-08-20
C2664 | 3374 | 2014-12-05 | Dykehead Renewables Ltd | Dykehead Farm wind turbine 3 | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Dykehead Farm Chapelton ML10 6SL | Strathclyde | Scotland | Scotland |  | 266054 | 647976 | South Lanarkshire Council | EK/14/0014 | [5 empty] | 2014-01-23 | 2014-04-01
B1277 | 3375 | 2017-11-30 | Scottish and Southern Energy (SSE) | Hadyard Hill extension | Wind Onshore |  |  | 88 | n/a |  |  |  | 4 | 22 | 126.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Hadyard Hill , east of Girvan , South Ayrshire | Strathclyde | Scotland | Scotland |  | 227000 | 599000 | Scottish Government (S36) | EC00003118 | [5 empty] | 2015-04-22 | 2017-11-21
C2740 | 3378 | 2015-01-05 | Princes Gate Spring Water | Princes Gate Spring Water | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Operational | Operational | Princes Gate Spring Water, Ludchurch, Narberth, | Dyfed | Wales | Wales | SA67 8JD | 214885 | 211552 | Pembrokeshire County Council | 11/0712/PA | [5 empty] | 2011-11-18 | [6 empty] | 2013-07-09 | [5 empty] | 2014-09-03
B1267 | 3380 | 2014-03-21 | North British Windpower Ltd | Phase 1 Bettyhill Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | Skelpick Estate, Thurso KW14 7TA | Highland | Scotland | Scotland |  | 272326 | 962920 | Highland Council | 07/00448/FULSU | [5 empty] | 2007-11-09 | [6 empty] | 2011-08-31 | [5 empty] | 2013-06-04
C2313 | 3381 | 2015-10-29 | Renewable Energy Systems (RES) | Thornton Lane | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Appeal Refused | Application Refused | Land at Thornton Lane, Eastry, Sandwich | Kent | South East | England | CT13 0ET | 629616 | 153332 | Dover District Council | 13/00927 | APP/X2220/W/14/3000040 |  |  |  |  | 2013-11-02 |  | 2014-06-10 | 2014-10-01 |  | 2015-10-12
B0354 | 3382 | 2017-06-22 | Sibelco/ Golconda | Sibelco Brassington | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Manystones Lane Brassington Derbyshire | Derbyshire | East Midlands | England |  | 424985 | 354923 | Derbyshire Dales District Council | 11/00291/FUL | [5 empty] | 2011-04-11 | [6 empty] | 2012-03-21 |  |  |  |  | 2015-02-15 | 2016-09-15
C2795 | 3383 | 2018-10-25 | Green Energy Wind | Neilston Additional Wind Turbine | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Planning Permission Granted | Awaiting Construction | Field East Of Neilston Community Windfarm Neilston East Renfrewshire | Strathclyde | Scotland | Scotland |  | 245747 | 653929 | East Renfrewshire Council | 2014/0130/TP | [5 empty] | 2014-03-05 | [6 empty] | 2015-11-04 |  |  |  | 2018-11-04
B1304 | 3385 | 2014-12-05 | Renewable Energy Systems (RES) | Crutherland Farm Wind Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Crutherland Farm, East Kilbride | Strathclyde | Scotland | Scotland |  | 266312 | 651530 | South Lanarkshire Council | EK/14/0111 | [5 empty] | 2014-04-22 |  | 2014-11-07
B0801 | 3387 | 2020-05-28 | Scottish Power Renewables | Beinn an Tuirc Windfarm Phase 3 | Wind Onshore |  |  | 49.9 | n/a |  |  |  | 2 | 19 |  | n/a | Under Construction | Under Construction | Beinn An Tuirc Windfarm, Land At Meall Buidhe And South, A Chruach West Of Saddell Kin, Campbeltown, Strathclyde, Scotland | Strathclyde | Scotland | Scotland | PA28 | 172270 | 633925 | Argyll and Bute Council | 15/03057/PP | [5 empty] | 2015-11-03 | [6 empty] | 2017-02-23 |  |  |  | 2020-02-23 | 2020-02-01
C0716 | 3388 | 2018-04-30 | North British Wind / Invenergy | Balunton Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 | 125 | n/a | Planning Application Withdrawn | Application Withdrawn | Balunton Wind Farm, Glentrool, Newton Stewart | Dumfries and Galloway | Scotland | Scotland | DG8 6 | 234665 | 580679 | Dumfries and Galloway Council | 15/P/1/0189 | [5 empty] | 2015-08-12 | 2018-04-18
07057W4 | 3390 | 2011-04-11 | Lambrigg Windfarm Ltd | Lambrigg Wind Farm | Wind Onshore |  |  | 6.5 | n/a |  |  |  | 1.3 | 5 |  | n/a | Operational | Operational | Lambrigg Fell, Off A684, Roan Edge Cumbria | Cumbria | North West | England |  | 358800 | 493600 | South Lakeland District Council | 5/98/1478 | [5 empty] | 1998-06-23 | [6 empty] | 1999-07-02 | [5 empty] | 2001-09-22
07130W3 | 3391 | 2019-12-06 | Cannock Renewables | Askam | Wind Onshore |  |  | 4.62 | n/a |  |  |  | 0.66 | 7 |  | n/a | Operational | Operational | Land North East of Far Old Park Farm , Ireleth , Askam-in-Furness | Cumbria | North West | England |  | 323000 | 477100 | Barrow in Furness Borough Council | [6 empty] | 1995-03-13 |  | 1997-10-06 | [10 empty] | 1999-07-13
11029W3 | 3392 | 2003-12-19 | Natural Power | Bears Down Wind Farm | Wind Onshore |  |  | 9.791 | n/a |  |  |  | 0.6 | 16 |  | n/a | Operational | Operational | Bears Down Reservoir St Colomb Cornwall | Cornwall | South West | England |  | 190360 | 67560 | Cornwall Council | [6 empty] | 2000-05-15 | [6 empty] | 2000-06-27 | [5 empty] | 2001-08-31
A0416 | 3393 | 2011-09-13 |  | Granary farm - Resubmission | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Church Road, Ringsfield, Beccles, Suffolk, NR34 8LE | Suffolk | Eastern | England |  | 640469 | 287976 | Waveney District Council | DC/10/0910/FUL | [5 empty] | 2010-07-08 |  | 2010-10-25
A0418 | 3394 | 2011-09-13 |  | Devonshire Farm - Resubmission | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Permission Refused | Application Refused |  | Suffolk | Eastern | England |  | 641328 | 288986 | Waveney District Council | DC/10/0909/FUL | [5 empty] | 2010-07-08 |  | 2010-10-25
AA115 | 3395 | 2012-04-05 | Scottish and Southern Energy (SSE) | Bransford Bridge | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Planning Permission Refused | Application Refused | n/w of Junction 1, M6, Churchover, Rugby, Warwickshire, CV23 | Warwickshire | West Midlands | England |  | 449894 | 280895 | Rugby Borough Council | R10/2303 | [5 empty] | 2011-06-06 |  | 2011-09-07
AA123 | 3396 | 2018-04-03 | Green Cat Renewables | Welton Of Creuchies | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Alyth, Blairgowrie | Tayside | Scotland | Scotland |  | 321622 | 750192 | Perth and Kinross Council | 10/00876/FLL | [5 empty] | 2010-05-17 |  | 2011-03-21 | 2011-06-29 |  |  | 2012-07-06 | 2012-07-06 |  |  |  |  | 2017-07-19 | 2018-01-23
AA138 | 3397 | 2012-01-27 | Standingfauld Wind Energy Limited | Standingfauld Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Appeal Refused | Application Refused | S/Of Standingfauld Farm, Muthill, Crieff, Tayside, PH5 2BU | Tayside | Scotland | Scotland |  | 286763 | 713456 | Perth and Kinross Council | 09/02212/FLM | 11/00017/REF |  |  |  |  | 2009-12-21 |  | 2011-05-02 |  |  | 2011-12-15
B1307 | 3398 | 2016-04-28 | Macphie Of Glenbervie Ltd | Droop Hill Wind Farm x | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Stonehaven AB39 3YA | Grampian | Scotland | Scotland |  | 375708 | 781360 | Aberdeenshire Council | APP/2009/1484 | [5 empty] | 2009-05-28 | [6 empty] | 2013-04-24 |  |  |  |  | 2013-09-08 | 2014-07-01
A0219 | 3400 | 2011-05-05 | Crimp Wind farm | Crimp Wind Farm - Resubmit | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Morwenstow, Kilkhampton, North Cornwall | Cornwall | South West | England |  | 225180 | 115445 | Cornwall Council | 2008/02196 | [6 empty] | 2011-05-05
A0360 | 3401 | 2011-06-23 | Private Developer | Cairn Hill | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Permission Refused | Application Refused | Cairnhill, Aberdeenshire | Aberdeen | Scotland | Scotland |  | 268245 | 598692 | Aberdeenshire Council | APP/2010/1147 | [5 empty] | 2010-04-09 |  | 2010-11-12
A0361 | 3402 | 2011-11-28 | Scottish and Southern Energy (SSE) | Burnside of Idoch | Wind Onshore |  |  | 3.2 | n/a |  |  |  | 0.8 | 4 |  | n/a | Appeal Refused | Application Refused | Turriff, Aberdeenshire | Grampian | Scotland | Scotland | AB53 8DY | 377164 | 848646 | Aberdeenshire Council | APP/2010/0405 | PPA-110-2070 |  |  |  |  | 2010-02-12 |  | 2010-11-12 |  |  | 2011-02-14
A0363 | 3403 | 2011-09-14 | Private Developer | Denhill | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | St Katherine's, Inverurie, Aberdeenshire | Grampian | Scotland | Scotland | AB51 8SU | 379611 | 835693 | Aberdeenshire Council | APP/2006/3651 | [5 empty] | 2006-09-15 | [6 empty] | 2009-06-05 |  |  |  |  | 2010-05-01 | 2011-06-01
A0364 | 3404 | 2011-09-13 | Private Developer | Haddo | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Methlick, Ellon, Aberdeenshire | Grampian | Scotland | Scotland | AB41 7DX | 381628 | 837639 | Aberdeenshire Council | APP/2006/3637 | [5 empty] | 2006-09-15 | [6 empty] | 2009-06-24 |  |  |  |  | 2010-05-01 | 2011-05-25
A0368 | 3405 | 2011-09-05 | Private Developer | Gairnieston Farm | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Turriff, Aberdeenshire | Grampian | Scotland | Scotland | AB53 5RP | 374750 | 856031 | Aberdeenshire Council | APP/2007/3775 | [5 empty] | 2007-09-19 | [6 empty] | 2009-07-31 |  |  |  |  | 2010-05-01 | 2010-11-01
AA236 | 3406 | 2014-02-10 | Airvolution Energy | Scottow Estate Wind Farm | Wind Onshore |  |  | 3.6 | n/a |  |  |  | 1.8 | 2 |  | n/a | Planning Permission Refused | Application Refused | Coltishall, Norfolk | Norfolk | Eastern | England |  | 628078 | 322038 | North Norfolk District Council | PF/13/0033 | [5 empty] | 2013-01-09 |  | 2013-04-15
AA287 | 3407 | 2012-02-23 | Greenspan Electric Cairnmore Ltd | Cairnmore Extension | Wind Onshore |  |  | 4.25 | n/a |  |  |  | 0.85 | 5 |  | n/a | Planning Permission Refused | Application Refused | Rhynie, Huntly, Aberdeenshire | Grampian | Scotland | Scotland |  | 348337 | 827042 | Aberdeenshire Council | APP/2011/0545 | [5 empty] | 2011-02-22 |  | 2012-01-05
AA001 | 3408 | 2010-05-21 |  | Burgar Hill (land Near), Evie | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Evie, Orkney | Orkney Islands | Scotland | Scotland |  | 334300 | 1026200 | Orkney Islands Council | 07/422/PPF | [5 empty] | 2007-07-09 | [6 empty] | 2008-12-04 | [5 empty] | 2009-11-01
AA546 | 3410 | 2011-11-08 | Renewable Energy Ventures | Burnside Wind Cluster | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land to West of Blackhills Farm Cushnie Alford | Grampian | Scotland | Scotland |  | 350765 | 807913 | Aberdeenshire Council | APP/2011/0174 | [5 empty] | 2011-02-07 | 2011-06-10
AA447 | 3411 | 2012-08-31 | Volkswind UK Ltd | Blackburn Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3.5 | 6 |  | n/a | Planning Permission Refused | Application Refused | Grantshouse Duns Scottish Borders TD11 3LF | Borders | Scotland | Scotland |  | 378080 | 667225 | Scottish Borders Council | 11/01077/FUL | [5 empty] | 2011-08-01 |  | 2012-08-06
AA600 | 3413 | 2012-03-29 | Kelda Water Services | Chelker Reservoir Repower (Resubmission) | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Planning Permission Refused | Application Refused | Chelker Reservoir, Addingham, Ilkley, West Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 405530 | 451821 | Craven District Council | 24/2011/12076 | [5 empty] | 2011-10-07 |  | 2012-03-13
AA613 | 3414 | 2012-05-21 | Private Developer | Upper Kinknockie Wind Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.75 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Clola Peterhead AB42 5AX | Grampian | Scotland | Scotland |  | 400759 | 841098 | Aberdeenshire Council | APP/2011/3763 | [5 empty] | 2011-11-24 | 2012-04-18
AA621 | 3415 | 2015-05-07 | Falkirk Tod Hill Wind Limited | Tod Hill Farm Wind Turbines | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Operational | Operational | Todhill Farm Larbert | Falkirk | Scotland | Scotland | FK5 4SH | 284064 | 683742 | Falkirk Council | P/11/0326/FUL | PPA-240-2022 |  |  |  |  | 2011-06-17 |  | 2011-12-21 | 2011-12-19 |  |  | 2012-06-06 | 2012-06-06 |  |  |  | 2015-06-06 | 2014-04-01 | 2015-01-22
B0703 | 3417 | 2019-03-26 | Boralex/Infinergy | Shepherd's Rig Wind Farm | Wind Onshore |  |  | 78.6 | n/a |  |  |  | 4 | 30 | 149.5 | n/a | Planning Application Submitted | Application Submitted | Shepherds Rig Windfarm 5KM E/O, Carsphairn, Castle Douglas, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG7 | 262319 | 593591 | Scottish Government (S36) | ECU00000735 | [5 empty] | 2018-12-17
B0889 | 3418 | 2016-05-04 | EDF & Wind Prospect | Saddle Hill Wind Farm | Wind Onshore |  |  | 35 | n/a |  |  |  | 2.5 | 14 | 115 | n/a | Planning Permission Refused | Application Refused | Kirly | Tayside | Scotland | Scotland |  | 320386 | 755598 | Angus Council | 14/00947/EIAM | [5 empty] | 2014-11-24 |  | 2016-04-06
C0407 | 3419 | 2013-04-08 | Kempstone Hill Wind Energy | Kempstone Hill Wind Turbines | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Site at Kempstone Hill Stonehaven AB39 3QB | Grampian | Scotland | Scotland |  | 388047 | 789689 | Aberdeenshire Council | APP/2012/2595 | [5 empty] | 2012-08-01 | 2012-12-21
C0727 | 3424 | 2013-07-23 | Ventus Renewables Ltd | Ardlawhill Wood Wind Turbines | Wind Onshore |  |  | 1.35 | n/a |  |  |  | 0.675 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Ardlawhill Wood, New Aberdour, Fraserburgh | Grampian | Scotland | Scotland |  | 387779 | 862308 | Aberdeenshire Council | APP/2012/3495 | [5 empty] | 2012-10-30 | 2013-04-17
C1141 | 3425 | 2014-01-30 | Ventus Renewables Ltd | Lower Rumster wind turbine | Wind Onshore |  |  | 1 | n/a |  |  |  | 1 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land 700M North West Of Lower Rumster Lybster | Highland | Scotland | Scotland |  | 321250 | 936500 | Highland Council | 13/01201/FUL | 13/00045/RBREF |  |  |  |  | 2013-04-02 |  | 2013-10-28
C1315 | 3426 | 2013-07-10 | Sorbie Windfarm Ltd | Sorbie Farm wind cluster | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Sorbie Farm Ardrossan Ayrshire KA22 7NP | Strathclyde | Scotland | Scotland |  | 224637 | 644638 | North Ayrshire Council | 13/00236/PP | [5 empty] | 2013-05-02 | 2013-06-25
C1630 | 3427 | 2017-01-23 | Polar Energy (Finlarg) Ltd | Frawney Wind Farm - resubmission | Wind Onshore |  |  | 4 | n/a |  |  |  | 0.8 | 5 |  | n/a | Abandoned | Abandoned | Frawney Wind Farm In Field 1020M North Of Over Finlarg Farm Over Finlarg Lumleyden | Tayside | Scotland | Scotland |  | 341650 | 742250 | Angus Council | 13/00532/EIAL | 13/00028/NONDET |  |  |  |  | 2013-06-13 |  | 2013-10-25 |  |  |  | 2014-01-13 | 2014-01-13
C1657 | 3428 | 2015-01-07 | Aggregate Industries UK | Torr Works | Wind Onshore |  |  | 3.6 | n/a |  |  |  | 0.9 | 4 |  | n/a | Appeal Refused | Application Refused | Land adjacent Torr Works | Somerset | South West | England |  | 371222 | 145186 | Mendip District Council | 2013/1244 | APP/Q3305/A/14/2227407 |  |  |  |  | 2013-06-24 |  | 2014-04-16 | 2014-11-04 |  | 2016-01-25
C1658 | 3429 | 2018-11-19 | Urban Wind | Moorhouse Farm | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Operational | Operational | Land North West Of Shepherds House Moorhouse Coldingham Scottish Borders | Borders | Scotland | Scotland |  | 384415 | 667894 | Scottish Borders Council | 13/00615/FUL | [5 empty] | 2013-06-18 | [6 empty] | 2014-09-11 |  |  |  | 2017-09-11 | 2016-08-15 | 2018-05-15
C1798 | 3430 | 2019-07-23 | EDF Energy Renewables (formerly Partnerships for Renewables) | Heathland Wind Farm | Wind Onshore |  |  | 57.8 | n/a |  |  |  | 3.4 | 17 |  | n/a | Planning Permission Granted | Awaiting Construction | Heathland Plantation, near Forth in South Lanarkshire | Strathclyde | Scotland | Scotland |  | 296479 | 656713 | Scottish Government (S36) | EC00003124 | [5 empty] | 2016-02-16 | [6 empty] | 2018-10-26 |  |  |  | 2023-10-26
C2520 | 3431 | 2016-12-01 | Ecotricity | Inch Moor Wind Farm | Wind Onshore |  |  | 51.2 | n/a |  |  |  | 3.2 | 16 | 126.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Land North, South And East Of 1 Kettleshiel Farm Cottages, Greenlaw | Borders | Scotland | Scotland |  | 371263 | 653521 | Scottish Government (S36) | EC00003183 | [5 empty] | 2015-08-14 | 2016-11-24
EN00109 | 3432 | 2009-10-23 |  | Royd Moor | Wind Onshore |  |  | 5.9 | n/a |  |  |  | 0.45 | 13 |  | n/a | Operational | Operational | Royd Moor, Penistone | South Yorkshire | Yorkshire and Humber | England |  | 422000 | 404000 | Barnsley Council | [19 empty] | 1993-12-01
C1820 | 3433 | 2016-03-18 | Greencoat UK Wind/Bay Wa .r.e/ SunGift | Stroupster Wind Farm - additional turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Stroupster, Caithness | Highland | Scotland | Scotland |  | 333969 | 965435 | Highland Council | 13/04144/FUL | [5 empty] | 2013-11-05 | [6 empty] | 2014-01-20 |  |  |  |  | 2014-07-01 | 2015-10-15
C2122 | 3435 | 2020-06-04 | Scottish and Southern Energy (SSE) | Gordonbush (extension) | Wind Onshore |  |  | 47 | n/a |  |  |  | 4.3 | 11 | 149.9 | n/a | Under Construction | Under Construction | near Brora in Sutherland. | Highland | Scotland | Scotland |  | 284604 | 912697 | Scottish Government (S36) | EC00003105 | [5 empty] | 2015-06-01 | [6 empty] | 2017-09-29 |  |  |  | 2022-09-29 | 2020-05-01
C2297 | 3436 | 2020-06-05 | Wind Harvest | Hill Of Lychrobbie | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Appeal Granted | Awaiting Construction | Land At Hill Of Lychrobbie Dunbeath | Highland | Scotland | Scotland |  | 316974 | 932057 | Highland Council | 13/04194/FUL | PPA-270-2154 |  |  |  |  | 2013-11-07 |  | 2016-03-30 | 2016-06-23 |  |  | 2017-01-26 | 2017-01-26
C2320 | 3437 | 2017-01-16 | Constantine Wind Energy | Little Belhus Restoration Site | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 | 76.5 | n/a | Operational | Operational | Land Between M25 And West Road, West Road, South Ockendon | Essex | Eastern | England |  | 558111 | 182855 | Thurrock Council | 13/01099/FUL | [5 empty] | 2013-11-15 | [6 empty] | 2015-05-14 |  |  |  | 2018-05-14 | 2016-07-04 | 2016-09-23
EN00297 | 3440 | 2010-10-28 | Fred Olsen Renewables | Crystal Rig Wind Farm Phase 2a | Wind Onshore |  |  | 138 | n/a |  |  |  | 2.3 | 60 |  | n/a | Operational | Operational | Dundfar Common, Eastern Lammermuirs | Borders | Scotland | Scotland |  | 367000 | 667500 | Scottish Government (S36) | [6 empty] | 2007-07-17 | [6 empty] | 2008-07-30 |  |  |  |  | 2010-03-01 | 2010-10-25
EN00300 | 3441 | 2010-06-09 | Savills | Tullich Wind Farm | Wind Onshore |  |  | 180 | n/a |  |  |  | 3 | 60 |  | n/a | Planning Application Withdrawn | Application Withdrawn |  | Strathclyde | Scotland | Scotland |  | 185135 | 726960 | Scottish Government (S36) | [7 empty] | 2010-06-09
EN00323 | 3442 | 2011-09-12 |  | Langham Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Appeal Refused | Application Refused | Land between Anderby and Chapel St Leonards | Lincolnshire | East Midlands | England |  | 554000 | 375000 | East Lindsey District Council | N/005/02812/06 | APP/D2510/10/2130539 |  |  |  |  | 2007-01-05 |  |  |  |  | 2011-09-29
EN00503 | 3443 | 2010-12-06 |  | Three Moors Wind Farm | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 9 |  | n/a | Appeal Refused | Application Refused | Paul's Moor, Wester Bullarford, West Moor North of Knowstone South Molton EX364QH | Devon | South West | England |  | 279047 | 123555 | North Devon District Council | 45489 | [5 empty] | 2007-11-06 |  | 2008-09-04 |  |  | 2009-01-29
IF1119 | 3444 | 2013-11-25 | Scottish and Southern Energy (SSE) | Bu Wind Farm Repowering | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Abandoned | Abandoned | Stronsay, Orkney, Islands, KW17 | Orkney Islands | Scotland | Scotland |  | 362249 | 1021849 | Orkney Islands Council | 12/725/TPP | [5 empty] | 2012-11-06 | [6 empty] | 2013-04-12
IF1128 | 3445 | 2014-01-19 | Mitchell Farming Partnerships (3R Energy) | Hazelside farm | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Glespin, Lanark, ML11 0SD | Strathclyde | Scotland | Scotland |  | 281162 | 630183 | South Lanarkshire Council | CL/12/0493 | [5 empty] | 2012-11-15 | 2013-05-31
IM0028 | 3446 | 2014-02-24 | Moss Side Farm Ltd | Moss Side Farm | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.1 | 1 |  | n/a | Planning Permission Refused | Application Refused | Moss Side Farm, Sandhaven, Fraserburgh | Grampian | Scotland | Scotland | AB43 7EY | 395023 | 865722 | Aberdeenshire Council | APP/2013/2454 | [5 empty] | 2013-07-29 |  | 2013-10-01
N00059W | 3447 | 2011-09-12 | Scottish Power Renewables | Dounreay Windfarm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 0 | 10 |  | n/a | Appeal Refused | Application Refused | Adjacent to Dounreay Nuclear Power Development Establishment, Borrowston Mains, Forss, Thurso, Caithness | Highland | Scotland | Scotland |  | 298725 | 966390 | Highland Council | 02/00166/FULCA | [5 empty] | 2002-04-25 |  | 2003-09-19 |  |  | 2005-03-04
N00080W | 3448 | 2010-07-27 | AMEC/ Border Winds | Clachan Flats Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 1.67 | 9 |  | n/a | Operational | Operational | North of the head of Loch Fyne Ardkinlas | Strathclyde | Scotland | Scotland |  | 217950 | 714520 | Argyll and Bute Council | 02/00/953/DET | [5 empty] | 2002-05-15 | [6 empty] | 2004-07-08 |  |  |  |  | 2006-05-01 | 2008-12-01
N00094W | 3449 | 2008-12-05 | Ecotricity | Fen Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 0.8 | 20 |  | n/a | Operational | Operational | Fen Farm, Fen Lane, Conisholme, South Lincolnshire | Lincolnshire | East Midlands | England |  | 537585 | 393825 | East Lindsey District Council | N/36/1046/03 | [5 empty] | 2003-07-24 |  | 2004-11-29 | [9 empty] | 2007-02-01 | 2008-04-17
N00111W | 3450 | 2018-06-04 | Gresham House | Darracott Moor | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Operational | Operational | Torrington, Devon, EX38 | Devon | South West | England |  | 223500 | 117500 | North Devon District Council | 1/1345/2002/24 | APP-W1145-A-03-1119641 |  |  |  |  | 2002-07-18 |  | 2003-02-25 |  |  |  | 2004-05-13 | 2004-05-13 |  |  |  |  | 2006-10-01 | 2011-05-06
S0009W1 | 3451 | 2004-08-23 | Eurus Energy / Ecogen | Largie Wind Farm | Wind Onshore |  |  | 14.86 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Tangy Farm, Kilkenzie Argyll and Bute | Strathclyde | Scotland | Scotland |  | 173000 | 639000 | Argyll and Bute Council | 94/00772/DET | [5 empty] | 1994-08-24 |  | 1998-11-17
N00389W | 3453 | 2009-02-04 | A7 Energy / Green Energy | Lochhead Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Land at Lochhead Farm , Stonehouse | Strathclyde | Scotland | Scotland |  | 275500 | 646500 | South Lanarkshire Council | HM/05/0147 | [5 empty] | 2005-04-01 | [6 empty] | 2006-05-01 | [5 empty] | 2009-07-01
EN00579 | 3454 | 2011-03-01 | Banks Renewables | Moor House Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Planning Permission Refused | Application Refused | Moor House Farm, East of Darlington | Durham | North East | England |  | 431700 | 525000 | Darlington Borough Council | 09/00741/FUL | [5 empty] | 2009-10-10 |  | 2010-11-12
EN00518 | 3455 | 2010-12-07 | Banks Development | Pontefract Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Appeal Refused | Application Refused | Went Edge, South Pontefract | West Yorkshire | Yorkshire and Humber | England |  | 445500 | 421500 | Wakefield Council | 07/01338/FUL | 09/00024/REF |  |  |  |  | 2007-05-03 |  | 2008-02-01 |  |  | 2010-06-22
EN00092 | 3456 | 2010-04-08 | Banks Group | Steadings Wind Farm | Wind Onshore |  |  | 66 | n/a |  |  |  | 2 | 21 |  | n/a | Planning Permission Refused | Application Refused | Steadings, nr Kirkwhelpington, Northumberland | Northumberland | North East | England |  | 399500 | 584500 | DECC (S36) | 06/0075/CPC | [5 empty] | 2006-04-12 |  | 2010-03-25
N00251W | 3457 | 2010-10-28 | Scottish and Southern Energy (SSE) | Toddleburn | Wind Onshore |  |  | 27.6 | n/a |  |  |  | 2.3 | 12 |  | n/a | Operational | Operational | Oxton | Borders | Scotland | Scotland |  | 345050 | 653150 | Scottish Borders Council | 04/017744/FUL | [5 empty] | 2004-09-02 |  | 2005-08-31 | [9 empty] | 2010-04-01 | 2010-10-12
N00543W | 3458 | 2011-04-06 | Crimp Power Ltd (West Coast Energy) | Crimp Wind Farm - resubmission | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Morwenstow, Kilkhampton, North Cornwall | Cornwall | South West | England |  | 225180 | 115445 | Cornwall Council | 2004/02831 | [5 empty] | 2004-12-13 |  | 2007-04-06 |  |  |  | 2008-04-02 | 2008-04-02 |  |  |  |  | 2010-08-01 | 2011-04-01
A0527 | 3462 | 2012-04-04 | BT | Wingates Moor Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Wingates Moor Longframlington Morpeth Northumberland NE65 8RP | Northumberland | North East | England |  | 413034 | 597920 | Northumberland County Council | 11/00158/RENEIA | [5 empty] | 2011-03-17 |  | 2012-03-22
AA282 | 3463 | 2011-10-24 | BT | Threapland Lees | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Bothel, Cumbria | Cumbria | North West | England |  | 316144 | 539113 | Allerdale Borough Council | 2/2009/0788 | [5 empty] | 2009-10-30 | 2010-09-07
06011W5 | 3466 | 2010-08-14 | Border Wind | Hedley Hope | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | High Hedley Farm, Tow Law, Bishop Auckland, County Durham | Durham | North East | England |  | 415700 | 541000 | Durham County Council | 99/429 | [5 empty] | 1999-06-07 | [6 empty] | 2001-05-23 | [5 empty] | 2001-12-30
N00047W | 3467 | 2012-01-18 | Border Wind / Scottish and Southern (SSE) | Tangy Wind Farm/Tangy 1 | Wind Onshore |  |  | 12.75 | n/a |  |  |  | 0.85 | 15 |  | n/a | Operational | Operational | Kilkenzie , Cambeltown | Strathclyde | Scotland | Scotland |  | 168500 | 628500 | Argyll and Bute Council | 94/0739/DET | [5 empty] | 2001-06-12 | [6 empty] | 2002-02-15 | [5 empty] | 2002-12-26
A0349 | 3468 | 2012-03-02 | British Telecom | Great Shelfin Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | LAND AT GREAT SHELFIN FARM MULLACOTT CROSS ILFRACOMBE DEVON EX34 8ND | Devon | South West | England |  | 252221 | 144377 | North Devon District Council | 49825 | [5 empty] | 2010-03-12 | 2012-01-24
N00151W | 3470 | 2004-11-23 | Community Power Ltd | Ton Marw Farm | Wind Onshore |  |  | 7.256 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Mynydd, Ton Marw Farm, Margam , Port Talbot | West Glamorgan | Wales | Wales |  | 273670 | 190300 | Neath Port Talbot County Borough Council | 02/0538 | [5 empty] | 2002-08-12 |  | 2002-10-04
B0578 | 3471 | 2013-07-10 | Community Windpower | Claughton Moor (Re-Submission 2) | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Planning Permission Refused | Application Refused | Farleton, Old Road, Claughton, Lancashire | Lancashire | North West | England |  | 358326 | 463852 | Lancaster City Council | 13/00128/FUL | [5 empty] | 2013-02-06 |  | 2013-06-25
B0502 | 3472 | 2014-01-30 | Community Windpower | Davidstow Wind Farm (re-submission) | Wind Onshore |  |  | 48 | n/a |  |  |  | 3 | 16 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Davidstow Trewinnow Farm Trevivian Davidstow Cornwall | Cornwall | South West | England |  | 214500 | 84500 | Cornwall Council | PA13/03743 | [5 empty] | 2013-08-19 | 2014-01-29
N00415W | 3473 | 2011-03-30 | Community Windpower | Leapmoor Forest | Wind Onshore |  |  | 30 | n/a |  |  |  | 3 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Leapmoor Forest Nr Inverkip Inverclyde | Strathclyde | Scotland | Scotland |  | 221985 | 670030 | Inverclyde Council | IC/2006/231/F | [5 empty] | 2006-07-01 | 2009-05-11
A0167 | 3474 | 2019-06-10 | Community Windpower (Community Wind Power) | Cowans Law | Wind Onshore |  |  | 49.9 | n/a |  |  |  | 2 | 25 |  | n/a | Planning Permission Refused | Application Refused | Hemphill Road, Moscow, Galston, Ayrshire. KA4 8PP | Strathclyde | Scotland | Scotland |  | 249387 | 641441 | East Ayrshire Council | 08/0645/F | [5 empty] | 2008-07-28 |  | 2010-06-24
A0169 | 3475 | 2019-06-10 | Community Windpower (Community Wind Power) | Claughton Moor Community Wind Farm | Wind Onshore |  |  | 49.9 | n/a |  |  |  | 2.5 | 20 |  | n/a | Appeal Withdrawn | Application Refused | Claughton, Lancashire | Lancashire | North West | England | LA2 9PR | 355355 | 464289 | Lancaster City Council | 09/01068/FUL | 10/00022/REF |  |  |  |  | 2009-11-02 |  | 2010-03-15 |  | 2011-03-09
AA064 | 3476 | 2019-06-10 | Community Windpower (Community Wind Power) | Cowans Law - resubmitted | Wind Onshore |  |  | 49.9 | n/a |  |  |  | 2.5 | 20 |  | n/a | Planning Permission Refused | Application Refused | Hemphill Road, Moscow, Galston, Ayrshire. KA4 8PP | Strathclyde | Scotland | Scotland |  | 249387 | 641441 | East Ayrshire Council | 10/0345/PP | [5 empty] | 2010-04-16 |  | 2010-11-04
B0762 | 3477 | 2016-08-03 | Community Windpower (Community Wind Power) | Blackshaw Community Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3.5 | 6 | 125 | n/a | Appeal Refused | Application Refused | Blackshaw Farm, West Kilbride, Strathclyde | North Ayrshire | Scotland | Scotland | KA23 9PG | 222675 | 649140 | North Ayrshire Council | 15/00200/PPM | PPA-310-2022 |  |  |  |  | 2015-04-16 |  | 2015-11-11 | 2016-01-26 |  | 2016-07-12
N00029W | 3479 | 2009-05-06 | Co-op | Coldham Hall | Wind Onshore |  |  | 14 | n/a |  |  |  | 1.75 | 8 |  | n/a | Operational | Operational | Coldham Hall Nr the Coldham Estate Cambridgeshire | Cambridgeshire | Eastern | England |  | 543324 | 302675 | Fenland District Council | F/YR02/0143/F | [5 empty] | 2002-01-25 | [6 empty] | 2002-10-26 | [5 empty] | 2005-08-01
B0483 | 3480 | 2012-08-24 | Co-operative Energy | Whitemill Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Operational | Operational | Coldham Estate, Coldham, Wisbech | Cambridgeshire | Eastern | England | PE14 0LX | 545100 | 301570 | Fenland District Council | F/YR07/1184/F | [5 empty] | 2007-11-02 | [6 empty] | 2008-11-25 | [5 empty] | 2012-05-02
EN00639 | 3481 | 2009-12-07 | Cornwall Light and Power | Cheverton Down Re-submission | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Cheverton Down, Shorwell, Isle of Wight | Isle of Wight | South East | England |  | 444500 | 84500 | Isle of Wight Council | P/00021/09 | [5 empty] | 2009-01-27 |  | 2009-12-04
07036W5 | 3482 | 2013-10-08 | Coronation Power | Crook Hill (Rochdale MBC) | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Abandoned | Abandoned | Nr Watergrove Reservoir, Littleborough, Greater Manchester | Greater Manchester | North West | England |  | 393000 | 419300 | Rochdale Borough Council | 07/D48920 | [5 empty] | 2007-03-20 | [6 empty] | 2009-07-31
07041W5 | 3483 | 2011-11-02 | Coronation Power | Todmorden Moor | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Appeal Refused | Application Refused | Todmorden, Yorkshire | West Yorkshire | Yorkshire and Humber | England |  | 389600 | 422700 | Calderdale Metropolitan Borough Council | 07/00349/WDF | [5 empty] | 2007-02-19 |  | 2007-11-23 |  |  | 2009-10-12
B0019 | 3484 | 2012-09-27 | Coronation Power | TRUTHAN BARTON WIND FARM - Resubmission | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.25 | 5 |  | n/a | Appeal Refused | Application Refused | Truthan Barton, St Erme, Truro, Cornwall | Cornwall | South West | England | TR4 9BB | 183722 | 51211 | Cornwall Council | PA11/03197 | 11/00188/REF |  |  |  |  | 2011-05-03 |  | 2011-09-28 |  |  | 2012-08-23
B0176 | 3485 | 2011-10-24 | Coronation Power | TRUTHAN BARTON WIND FARM | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Planning Permission Refused | Application Refused | Truthan Barton, St Erme, Truro, Cornwall | Cornwall | South West | England | TR4 9BB | 183722 | 51211 | Cornwall Council | C1/EA30/0377/09/M | [5 empty] | 2009-03-10 |  | 2011-01-20
N00538W | 3487 | 2016-05-10 | CRE Energy/ Scottish Power | Green Knowes | Wind Onshore |  |  | 27 | n/a |  |  |  | 1.5 | 18 |  | n/a | Operational | Operational | Land at Green Knowes, by Glendevon | Tayside | Scotland | Scotland |  | 296850 | 707550 | Perth and Kinross Council | 04/01651/FUL | [5 empty] | 2004-08-04 |  | 2006-06-15 |  |  |  | 2008-06-13 | 2008-06-13 |  |  |  |  | 2008-06-14 | 2008-09-29
N00557W | 3488 | 2010-06-09 | CRE Energy/ Scottish Power | Green Knowes Extension (Revised Application) | Wind Onshore |  |  | 31.5 | n/a |  |  |  | 1.75 | 18 |  | n/a | Appeal Withdrawn | Application Refused | Land At Green Knowes By Glendevon , Dollar , Clackmannanshire | Tayside | Scotland | Scotland |  | 296850 | 707550 | Perth and Kinross Council | 05/01061/FUL | [5 empty] | 2005-05-31 |  | 2005-12-06 |  | 2006-08-22
N00055W | 3489 | 2010-05-20 | CRE Energy/ Scottish Power | Whitelee | Wind Onshore |  |  | 322 | n/a |  |  |  | 2.3 | 140 |  | n/a | Operational | Operational | Eaglesham Moor, Whitelee Forest, Fenwick Moor, East Kilbride, South of Glasgow | Strathclyde | Scotland | Scotland |  | 256800 | 645435 | Scottish Government (S36) | 2002/0001/EB | [5 empty] | 2002-01-23 | [6 empty] | 2006-04-01 |  |  |  |  | 2006-12-01 | 2007-12-14
07022W4 | 3490 | 2011-10-30 | Cumbria Wind Farms | Hilltop Wind Farm | Wind Onshore |  |  | 8.837 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Hilltop Farm Brocklebank Westward Wigton Cumbria | Cumbria | North West | England |  | 329500 | 541500 | Allerdale Borough Council | [6 empty] | 1999-06-22 |  | 2000-07-05
07035W5 | 3491 | 2006-07-13 | Cumbria Wind Farms | Great Orton | Wind Onshore |  |  | 3.96 | n/a |  |  |  | 0.66 | 6 |  | n/a | Operational | Operational | Near Carlisle Cumbria | Cumbria | North West | England |  | 331000 | 553500 | Allerdale Borough Council | [6 empty] | 1998-02-26 | [6 empty] | 1999-06-15 | [5 empty] | 1999-12-21
N00004W | 3492 | 2009-09-07 | Cumbria Wind Farms | Winscales Phase I and II | Wind Onshore |  |  | 8.8 | n/a |  |  |  | 0.8 | 11 |  | n/a | Operational | Operational | Winscales, Workington, Cumbria | Cumbria | North West | England |  | 303000 | 527000 | Allerdale Borough Council | 2/97/0902 | [5 empty] | 1997-11-18 | [6 empty] | 1999-06-07 | [5 empty] | 2004-12-01
07021W4 | 3493 | 2009-06-23 | Cumbria Wind Farms (Wind Development UK) | Fairfield Farm Wind Farm | Wind Onshore |  |  | 5.884 | n/a |  |  |  | 0 | 10 |  | n/a | Appeal Refused | Application Refused | Fairfield Farm Pica Distington near Workington Cumbria | Cumbria | North West | England |  | 301500 | 521500 | Copeland Borough Council | 04/95/0559 | [5 empty] | 1995-08-11 |  | 1996-04-01 |  |  | 1997-01-24
06009W5 | 3494 | 2009-12-10 | E.ON UK | Holmside Hall | Wind Onshore |  |  | 2.75 | n/a |  |  |  | 1.37 | 2 |  | n/a | Operational | Operational | Burnhope, Stanley, County Durham | Durham | North East | England |  | 420800 | 550300 | Durham County Council | 2002/304 | [5 empty] | 2002-03-31 | [6 empty] | 2003-01-16 | [5 empty] | 2004-06-01
06010W5 | 3495 | 2009-12-09 | E.ON UK | High Volts Wind Farm | Wind Onshore |  |  | 5.5 | n/a |  |  |  | 1.83 | 3 |  | n/a | Operational | Operational | Potters Farm, Elwick, Hartlepool, Cleveland | Cleveland | North East | England |  | 445200 | 533400 | Hartlepool Borough Council | [6 empty] | 2001-05-15 | [6 empty] | 2002-03-27 | [5 empty] | 2003-12-01
06012W5 | 3496 | 2009-05-08 | E.ON UK | Hare Hill | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Operational | Operational | Harehill Farm, Haswell Plough, County Durham | Durham | North East | England |  | 437735 | 540895 | Durham County Council | [6 empty] | 2000-02-11 | [6 empty] | 2000-05-25 | [5 empty] | 2004-07-01
A0235 | 3497 | 2011-04-07 | E.ON UK | Corriemoillie Forest | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 2.5 | 19 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Gorston, Garve, Ross-shire. IV23 | Highland | Scotland | Scotland |  | 232885 | 863033 | Highland Council | 09/00693/FULRC | [5 empty] | 2009-12-02 | 2010-10-05
A0499 | 3498 | 2011-04-06 | E.ON UK | Ancroft Northmoor Wind Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Southeast Of Ancroft Northmoor And Southwest Of Allerdean Grange Berwick-upon-Tweed Northumberland | Northumberland | North East | England |  | 397453 | 645210 | Northumberland County Council | C/09/00063/CCMEIA | [6 empty] | 2011-04-06
N00098W | 3499 | 2003-12-10 | E.ON UK | White Hill | Wind Onshore |  |  | 12 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | West of Crown Point Car Park , Crown Point Road , Burnley | Lancashire | North West | England |  | 384000 | 428800 | Burnley Borough Council | 12/02/656 | APP/Z2315/A/03/1114592 |  |  |  |  | 2002-12-11 |  | 2003-03-18
AA995 | 3502 | 2019-12-10 | E.ON Renewables | Enoch Hill | Wind Onshore |  |  | 54.4 | n/a |  |  |  | 3.4 | 16 | 130 | n/a | Appeal Granted | Awaiting Construction | around 14km south west of New Cumnock | Strathclyde | Scotland | Scotland |  | 258401 | 609144 | Scottish Government (S36) | EC00005256 | WIN-190-5 |  |  |  |  | 2015-09-28 |  |  | 2017-11-21 |  |  | 2019-09-13 | 2019-09-13 |  |  |  | 2022-09-13
AA996 | 3503 | 2019-12-10 | E.ON Renewables | Benbrack | Wind Onshore |  |  | 84 | n/a |  |  |  | 3.3 | 18 |  | n/a | Appeal Granted | Awaiting Construction | Near Carsphairn and Dalmellington | East Ayrshire | Scotland | Scotland |  | 253199 | 599440 | Scottish Government (S36) | EC00002082 | WIN-170-2002 |  |  |  |  | 2014-11-20 |  |  | 2015-11-19 |  |  | 2017-09-15 | 2017-09-15 |  |  |  | 2022-09-15
A0067 | 3504 | 2011-06-24 | E.ON UK | Great Eppleton Farm Repowering | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Hetton, Houghton-le-Spring, Tyne & Wear, DH5 9NL | Tyne and Wear | North East | England |  | 436900 | 548200 | Sunderland City Council | 07/00086/FUL | [5 empty] | 2007-03-01 | [6 empty] | 2007-08-10 |  |  |  |  | 2009-10-01 | 2010-03-01
A0462 | 3505 | 2011-08-04 | E.ON UK | A1 Wind Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Great Stainton | Durham | North East | England |  | 432831 | 521770 | Darlington Borough Council | [7 empty] | 2011-08-04
N00028W | 3506 | 2006-05-05 | E.ON UK | Falahill | Wind Onshore |  |  | 6.744 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Falahill Farm Falahill Heriot Midlothian | Borders | Scotland | Scotland |  | 339180 | 655435 | Scottish Borders Council | 04/02420/FUL | [5 empty] | 2004-12-10 |  | 2006-05-08
EN00262 | 3507 | 2011-06-06 | E.ON UK Renewables Developments Ltd | Haswell Moor | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Haswell Moor Easington County Durham | Durham | North East | England |  | 438085 | 541365 | Durham County Council | PLAN/2006/0869 | [5 empty] | 2006-11-23 | [6 empty] | 2007-12-18 |  |  |  |  | 2010-10-01 | 2010-12-12
07067W4 | 3508 | 2011-11-02 | Ecogen | Humble Hill Wind Farm | Wind Onshore |  |  | 78.479 | n/a |  |  |  | 0 | 0 |  | n/a | Appeal Refused | Application Refused | Humble Hill Kielder Forest Hexham Northumberland | Northumberland | North East | England |  | 365000 | 581000 | DECC (S36) | [6 empty] | 1993-04-13 |  | 2002-05-02 |  |  | 2002-05-02
10074W4 | 3509 | 2003-09-29 | Ecogen | Blaencorrwg Wind Farm | Wind Onshore |  |  | 19.309 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Gwaun Blaencorrwg Nr Glyncorrwg Port Talbot West Glamorgan | West Glamorgan | Wales | Wales |  | 290000 | 201500 | Neath Port Talbot County Borough Council | 93/9291 | [5 empty] | 1994-07-25 |  | 1994-11-03
EN00634 | 3510 | 2009-05-08 | Ecotricity | Worksop - B&Q | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Manton Wood, Worksop, Nottinghamshire | Nottinghamshire | East Midlands | England |  | 461695 | 378487 | Bassetlaw District Council | 1/2/07/528 | [5 empty] | 2007-09-07 | [6 empty] | 2007-11-01 |  |  |  |  | 2008-12-01 | 2009-01-21
EN00374 | 3511 | 2018-07-04 | Otter Power | Cold Northcott | Wind Onshore |  |  | 6.6 | n/a |  |  |  | 0.3 | 22 |  | n/a | Operational | Operational | Launceston Cornwall | Cornwall | South West | England |  | 220040 | 85965 | Cornwall Council | [19 empty] | 2002-06-01
A0117 | 3512 | 2011-12-06 | Energiekontor UK | Monkwith Wind Farm (Resubmission) | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Appeal Refused | Application Refused | Hogsea Lane, Tunstall, Hull, Humberside. HU12 0HL | Humberside | Yorkshire and Humber | England |  | 528934 | 431197 | East Riding of Yorkshire Council | 09/02000/STPLFE | 10/00069/REFUSE |  |  |  |  | 2009-06-12 |  | 2010-01-21 |  |  | 2011-01-07
EN00039 | 3513 | 2009-12-02 | Energiekontor UK | Gathercauld | Wind Onshore |  |  | 15.6 | n/a |  |  |  | 0 | 13 |  | n/a | Planning Permission Refused | Application Refused | Gathercauld, Ceres, Fife | Fife | Scotland | Scotland |  | 342500 | 709500 | Fife Council | 07/01813/EEIA | [5 empty] | 2007-06-01 |  | 2009-06-17
EN00150 | 3514 | 2010-06-09 | Energiekontor UK | Auchtermuchty Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | Rossie, Fife | Fife | Scotland | Scotland |  | 325240 | 713880 | Fife Council | [6 empty] | 2006-06-01 |  | 2008-01-01
EN00342 | 3515 | 2007-03-08 | Energiekontor UK | Monkwith Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 0 | 7 |  | n/a | Planning Permission Refused | Application Refused | West Of Pastures Lane Tunstall East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 530050 | 433050 | East Riding of Yorkshire Council | 07/01140/STPLFE | [5 empty] | 2007-02-23 |  | 2007-10-18
B0337 | 3516 | 2018-11-15 | Peel Wind Farms | Beaw Field Wind Farm | Wind Onshore |  |  | 57.8 | n/a |  |  |  | 3.5 | 17 | 145 | n/a | Planning Permission Granted | Awaiting Construction | Heatherlea, Yell, Shetland | Shetland | Scotland | Scotland | ZE2 9BA | 450461 | 1182092 | Scottish Government (S36) | EC00003121 | [5 empty] | 2016-04-14 | [6 empty] | 2017-11-30 |  |  |  | 2022-11-30
A0143 | 3518 | 2011-09-12 | Enertrag UK | Little Linton Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Appeal Refused | Application Refused | Cambridge Road, Linton, Cambridge. CB21 4JD | Cambridgeshire | Eastern | England |  | 555459 | 247455 | South Cambridgeshire District Council | S/0232/09/F | APP/W0530/A/09/2108277 |  |  |  |  | 2009-03-04 |  | 2009-06-25 |  |  | 2010-10-27
EN00245 | 3519 | 2010-12-06 | Enertrag UK | Hempnall | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Appeal Refused | Application Refused | Land at Busseys Loke, Hempnall Norfolk | Norfolk | Eastern | England |  | 625671 | 295267 | South Norfolk Council | 07/2008/0917/F | [5 empty] | 2008-06-01 |  | 2008-08-05 |  |  | 2009-12-08
07018W4 | 3520 | 2011-10-30 | Farm Energy (The Wind Company Ltd) | Barkin House Wind Farm | Wind Onshore |  |  | 4.744 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Gatebeck Nr Kendal Cumbria | Cumbria | North West | England |  | 358200 | 485800 | South Lakeland District Council | [6 empty] | 1998-09-22 |  | 1999-04-07
12008W4 | 3521 | 2005-08-05 | Farm Energy (The Wind Company Ltd) | Outstray Farm Wind Project | Wind Onshore |  |  | 1.779 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Sunk Island Humberside | Humberside | Yorkshire and Humber | England |  | 533000 | 418700 | East Riding of Yorkshire Council | 362/10019 | [6 empty] | 2005-08-05
EN00124 | 3522 | 2013-10-08 | Fermanagh Wind Energy | Tullinoid | Wind Onshore |  |  | 6 | n/a |  |  |  | 1 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Derrygonnelly, Co. Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 22072 | 517530 | Northern Ireland Planning Service | L/2004/0472/F | [5 empty] | 2004-03-31 | 2011-01-18
AA494 | 3524 | 2011-10-06 | Green Cat Renewables | Upper Ardgrain Wind Farm | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Ellon, Aberdeenshire | Grampian | Scotland | Scotland |  | 396508 | 835110 | Aberdeenshire Council | APP/2007/4747 | [5 empty] | 2007-11-20 | [6 empty] | 2010-04-27 | [5 empty] | 2010-10-01
N00254W | 3526 | 2014-12-02 | Green Power International | Little Law Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 1.5 | 18 |  | n/a | Appeal Refused | Application Refused | Auchterarder, Perthshire | Tayside | Scotland | Scotland |  | 299950 | 709050 | Perth and Kinross Council | 04/01321/FUL | PPA-340-484 |  |  |  |  | 2004-06-18 |  | 2005-06-22 | 2005-12-21 |  | 2007-08-08
EN00243 | 3527 | 2007-07-30 | Harworth Power | Stonish Hill | Wind Onshore |  |  | 14 | n/a |  |  |  | 0 | 7 |  | n/a | Planning Permission Refused | Application Refused | near Bilsthorpe Chestnut Farm, Stonish Hill, Eakring | Nottinghamshire | East Midlands | England |  | 466000 | 362000 | Newark and Sherwood District Council | [6 empty] | 2005-12-01 |  | 2006-11-01
A0075 | 3528 | 2011-04-01 | Infinergy | Strone Saul Hill | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Planning Permission Refused | Application Refused | Glen Massan, Dunoon, Strathclyde. PA23 8RA | Strathclyde | Scotland | Scotland |  | 212934 | 685526 | Argyll and Bute Council | 09/00569/DET | [5 empty] | 2009-04-28 |  | 2010-08-10
S0026W3 | 3529 | 2010-02-03 | Longearth Ltd / Farm Energy | Rothiesholm | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Operational | Operational | Rothiesholm, Stronsay, Orkney | Orkney Islands | Scotland | Scotland |  | 362283 | 1023560 | Orkney Islands Council | 01/006/PPF | [5 empty] | 2001-01-01 | [6 empty] | 2001-05-01 | [5 empty] | 2002-04-10
EN00082 | 3532 | 2009-10-01 | Mackies | Hill of Easterton | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Hill of Easterton, 1km North Of Mackies Ice Cream Dairy, Westertown, Rothienorman, Inverurie, AB51 8US | Grampian | Scotland | Scotland |  | 376449 | 831808 | Aberdeenshire Council | [13 empty] | 2003-10-16 | [5 empty] | 2005-01-01
N00416W | 3533 | 2010-06-09 | Mersey Docks and Harbour Company | Port of Liverpool - wind | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Operational | Operational | Alexandra Dock, Port of Liverpool, Regent Road, Bootle | Merseyside | North West | England |  | 333356 | 395230 | Sefton Council | 05F/2712 | [5 empty] | 2005-08-17 | [6 empty] | 2005-12-08 | [5 empty] | 2009-02-01
N00053W | 3534 | 2017-05-31 | Natural Power Consultants | Rothes Wind (Cairn Uish) | Wind Onshore |  |  | 50.6 | n/a |  |  |  | 2.3 | 22 |  | n/a | Operational | Operational | Cairn Uish, 10km south of Elgin, Moray | Grampian | Scotland | Scotland |  | 318500 | 850500 | Scottish Government (S36) | [6 empty] | 2001-09-27 | [6 empty] | 2003-01-21 | [5 empty] | 2004-11-01
N00190W | 3535 | 2004-08-11 | Natural Power Consultants | Cairn Uish Wind Farm Extension | Wind Onshore |  |  | 21 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Cairn Uish, 10km south of Elgin, Moray | Grampian | Scotland | Scotland |  | 318500 | 850500 | Moray Council | IEC3/98 | [6 empty] | 2004-08-11
N00242W | 3536 | 2013-10-08 | Natural Power Consultants | Crystal Rig Extension II | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Operational | Operational | Lammermuir Hills on the East Lothian Council/Scottish Borders Council border approximately 11km from Dunbar and 16.5km from Duns. | Borders | Scotland | Scotland |  | 366000 | 669000 | Scottish Government (S36) | [6 empty] | 2004-05-01 | [6 empty] | 2005-05-25 |  |  |  |  | 2008-08-01 | 2010-10-25
S0025W3 | 3537 | 2011-06-29 | Natural Power Consultants / Powergen | Little Kilmain | Wind Onshore |  |  | 2.2338 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | East Ayrshire | Strathclyde | Scotland | Scotland |  | 246200 | 611000 | East Ayrshire Council | 00/0530/FL | [6 empty] | 2011-06-29
A0037 | 3538 | 2012-03-06 | Novera Energy | Glenkerie Wind Farm | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 11 |  | n/a | Operational | Operational | Kingledores Farm, Broughton, Biggar, Strathclyde. ML12 6QL | Borders | Scotland | Scotland |  | 310453 | 628117 | Scottish Borders Council | 07/02478/FUL | [5 empty] | 2007-12-20 | [6 empty] | 2008-09-08 |  |  |  |  | 2011-04-01 | 2012-02-01
EN00161 | 3539 | 2010-06-09 | Novera Energy | Lissett Airfield Wind Farm | Wind Onshore |  |  | 29.95 | n/a |  |  |  | 2.5 | 12 |  | n/a | Operational | Operational | 1.5km west of Lisset, East Yorkshire | Humberside | Yorkshire and Humber | England |  | 512263 | 458139 | East Riding of Yorkshire Council | 06/05618/STPLFE | [5 empty] | 2006-07-10 | [6 empty] | 2007-02-22 | [5 empty] | 2009-02-20
A0151 | 3540 | 2011-03-01 | Npower | Charity Farm | Wind Onshore |  |  | 32 | n/a |  |  |  | 2 | 16 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Swine Fleet Road, Goole Fields, Goole, Humbs. DN14 8AU | Humberside | Yorkshire and Humber | England |  | 475408 | 420604 | East Riding of Yorkshire Council | 09/02564/STPLFE | [6 empty] | 2011-03-01
A0068 | 3541 | 2011-10-31 | Npower Renewables | Saxby Wold (Brigg Road) | Wind Onshore |  |  | 45 | n/a |  |  |  | 2.3 | 18 |  | n/a | Appeal Withdrawn | Application Refused | Barton-on-Humber | Humberside | Yorkshire and Humber | England | DN18 5DT | 503067 | 421294 | North Lincolnshire Council | WF/2009/0657 | APP/Y2003/A/11/2156490/NWF |  |  |  |  | 2009-06-01 |  | 2011-01-07 |  | 2011-10-04
N00191W | 3542 | 2005-11-25 | Npower Renewables | Park Head Farm | Wind Onshore |  |  | 7.8 | n/a |  |  |  | 0 | 6 |  | n/a | Planning Permission Refused | Application Refused | Park Head Farm Silloth Carlisle | Cumbria | North West | England |  | 313485 | 551675 | Allerdale Borough Council | 2/2004/0841 | [5 empty] | 2004-06-25 |  | 2004-10-07
N00274W | 3543 | 2011-09-13 | Npower Renewables | Hellrigg Wind Farm | Wind Onshore |  |  | 7.791 | n/a |  |  |  | 1.3 | 6 |  | n/a | Planning Permission Refused | Application Refused | Park Head Farm Silloth Carlisle | Cumbria | North West | England |  | 313535 | 551725 | Allerdale Borough Council | 2/2004/0843 | [5 empty] | 2004-06-25 |  | 2004-10-07
N00275W | 3544 | 2006-05-09 | Npower Renewables | Hill of Snowy Slack | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 11 |  | n/a | Planning Application Withdrawn | Application Withdrawn | At Kil Drummuie Mr Lumbersdone | Grampian | Scotland | Scotland |  | 345374 | 818784 | Aberdeenshire Council | M/APP/2004/4603 | [6 empty] | 2006-05-09
N00413W | 3545 | 2010-01-04 | Npower Renewables | Alt Dearg | Wind Onshore |  |  | 42 | n/a |  |  |  | 2.8 | 15 |  | n/a | Planning Permission Refused | Application Refused | Alt Dearg Wind Farm By Stronachullin Farm Ardrishaig | Strathclyde | Scotland | Scotland |  | 183256 | 678053 | Argyll and Bute Council | 06/01158/DET | [5 empty] | 2006-06-01 |  | 2007-11-14
N00285W | 3546 | 2005-08-26 | Npower Renewables | Beech Tree Farm Wind Turbines | Wind Onshore |  |  | 4.884 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Beech Tree Farm Goveton Kingsbridge TQ7 2DT (Land between Goveton and A381) | Devon | South West | England |  | 275235 | 47661 | South Hams District Council | 819/2140/04/F | [5 empty] | 2004-10-27 | 2006-12-04
A0254 | 3547 | 2011-09-12 | Nuon UK | Draughton Maidwell Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 1.3 | 7 |  | n/a | Appeal Refused | Application Refused | Land to the north of Draughton Harrington, Draughton, Northamptonshire | Northamptonshire | East Midlands | England |  | 477012 | 278134 | Daventry District Council | DA/2009/0168 | [5 empty] | 2009-04-01 |  | 2010-01-27 |  |  | 2010-09-20
EN00412 | 3548 | 2012-08-07 | Orkney Sustainable Energy | Methlick Farmers Wind Energy Project | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | Methlick, Aberdeenshire | Grampian | Scotland | Scotland |  | 385500 | 837500 | Aberdeenshire Council | Various | [5 empty] | 2006-10-01 | [6 empty] | 2007-07-01 |  |  |  |  | 2011-03-01 | 2011-12-01
EN00112 | 3549 | 2010-07-06 | Pennant Walters | Hirwaun Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 2 | 12 |  | n/a | Appeal Refused | Application Refused | South of Hirwaun | Mid Glamorgan | Wales | Wales |  | 295787 | 202855 | Rhondda Cynon Taff County Borough Council | 06/1415 | [5 empty] | 2006-07-14 |  | 2007-10-12 |  |  | 2008-11-27
C1032 | 3550 | 2017-02-28 | PNE Wind UK Ltd (Brookfield) | Shennanton Wind Farm | Wind Onshore |  |  | 30 | n/a | 0.9 | n/a |  | 2.5 | 12 | 100 | n/a | Appeal Refused | Application Refused | Shennanton Wind Farm, Kirkcowan. Newton Stewart | Dumfries and Galloway | Scotland | Scotland | DG8 0EG | 232665 | 564874 | Dumfries and Galloway Council | 15/P/1/0031 | PPA-170-2109 |  |  |  |  | 2015-02-16 |  |  | 2015-02-12 |  | 2017-02-02
IF1345 | 3551 | 2013-09-18 | PNE Wind UK Ltd (Brookfield) | Hill of Braco | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Hatton Peterhead AB42 0RR | Grampian | Scotland | Scotland |  | 403893 | 840984 | Aberdeenshire Council | APP/2013/0505 | [5 empty] | 2013-02-28 | 2013-08-27
04037W3 | 3552 | 2003-12-08 | Powergen | Rheidol Wind Farm | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.3 | 8 |  | n/a | Operational | Operational | Rheidol Wind Farm , Banc Bwa Drain , Goginan , Aberystwyth | Dyfed | Wales | Wales | SW23 3PQ | 272400 | 280500 | Ceredigion County Council | [6 empty] | 1991-08-01 | [6 empty] | 1996-08-06 | [5 empty] | 1997-02-06
N00423W | 3553 | 2009-06-11 | Powergen /E.ON-UK | Lamonby Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Lamonby, Penrith, Cumbria | Cumbria | North West | England |  | 340500 | 535500 | Eden District Council | 05/0758 | [6 empty] | 2009-06-11
S0003W2 | 3554 | 2019-08-05 | Powergen Renewables | Deucheran Hill | Wind Onshore |  |  | 15.75 | n/a |  |  |  | 1.75 | 9 |  | n/a | Operational | Operational | Deucheran Hill Nr. Muasdale | Strathclyde | Scotland | Scotland |  | 177000 | 643000 | Argyll and Bute Council | 99/00925/DET | [5 empty] | 1999-06-01 | [6 empty] | 2001-05-22 | [5 empty] | 2001-11-30
04043W5 | 3556 | 2005-04-01 | Renewable Development Company Ltd | Bryn Du | Wind Onshore |  |  | 16.416 | n/a |  |  |  | 0.42 | 39 |  | n/a | Operational | Operational | Bryn Du Hills, South Of A44 At Pont Rydgaled, Powys , (LLangurig area) | Powys | Wales | Wales |  | 284000 | 281000 | Powys County Council | [6 empty] | 2000-07-24 | [6 empty] | 2001-12-10 | [5 empty] | 2005-04-01
07089W5 | 3560 | 2011-06-29 | Renewable Development Company Ltd | Corbie Shank | Wind Onshore |  |  | 150 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Craik Forest , West Of A7 North Of Langholm | Dumfries and Galloway | Scotland | Scotland |  | 334520 | 595639 | Scottish Government (S36) | [7 empty] | 2011-06-29
N00403W | 3561 | 2010-01-04 | Renewable Development Company Ltd | Mellock Hill Wind Farm | Wind Onshore |  |  | 48 | n/a |  |  |  | 2 | 24 |  | n/a | Planning Permission Refused | Application Refused | Ochill Hills, nr. Crook of Devon Perthshire | Tayside | Scotland | Scotland |  | 302500 | 706500 | Perth and Kinross Council | 04/02000 | [5 empty] | 2004-10-01 |  | 2005-06-20
N00427W | 3562 | 2006-05-15 | Renewable Development Company Ltd | Mellock Hill Wind Farm II | Wind Onshore |  |  | 35 | n/a |  |  |  | 2 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Ochill Hills, nr. Crook of Devon Perthshire | Tayside | Scotland | Scotland |  | 302500 | 706500 | Perth and Kinross Council | [7 empty] | 2006-05-15
06019W4 | 3563 | 2011-06-29 | Renewable Energy Systems (RES) | Debdon Farm Wind Farm | Wind Onshore |  |  | 10.105 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | Armstrong Estates Near Rothbury Northumberland | Northumberland | North East | England |  | 409000 | 604000 | Northumberland County Council | A/2006/0348 | [5 empty] | 2006-07-03 |  | 2006-09-05
07031W5 | 3564 | 2003-09-26 | Renewable Energy Systems (RES) | Black Scout Wind Farm | Wind Onshore |  |  | 1.953 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Permission Refused | Application Refused | The Long Causeway, Burnley Way, Burnley, Lancashire | Lancashire | North West | England |  | 389500 | 427500 | Burnley Borough Council | [6 empty] | 2000-01-24 |  | 2000-05-25
N00022W | 3566 | 2004-01-06 | Renewable Energy Systems (RES) | Lendrum's Bridge Wind Farm ( Extension 2) | Wind Onshore |  |  | 7.26 | n/a |  |  |  | 0.66 | 11 |  | n/a | Operational | Operational | Lendrum's Bridge Murley RoadFivemiletown County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 65919 | 512041 | Northern Ireland Planning Service | [6 empty] | 1997-09-12 | [6 empty] | 1998-05-11 | [5 empty] | 2002-12-20
N2051W2 | 3568 | 2010-02-23 | Renewable Energy Systems (RES) | Lendrum's Bridge Wind Farm | Wind Onshore |  |  | 5.94 | n/a |  |  |  | 0.66 | 9 |  | n/a | Operational | Operational | Lendrum's Bridge Murley Road, Fivemiletown County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 63672 | 512074 | Northern Ireland Planning Service | [6 empty] | 1997-09-12 | [6 empty] | 1998-05-11 | [5 empty] | 2000-02-01
S0008W1 | 3569 | 2003-06-27 | Renewable Energy Systems (RES) | Gartymore Wind Farm | Wind Onshore |  |  | 10.5 | n/a |  |  |  | 0 | 14 |  | n/a | Planning Permission Refused | Application Refused | Gartymore Estate | Highland | Scotland | Scotland |  | 298800 | 915500 | Highland Council | [6 empty] | 1995-10-19 |  | 1999-07-19
S0043W3 | 3570 | 2013-09-12 | Renewable Energy Systems (RES) | Dun Law | Wind Onshore |  |  | 17.16 | n/a |  |  |  | 0.66 | 26 |  | n/a | Operational | Operational | Dun Law, 5km north west of Oxton, Lammermuir Hills | Borders | Scotland | Scotland |  | 347069 | 657344 | Midlothian Council | 96/01130/FUL | [5 empty] | 1996-05-17 | [6 empty] | 1997-07-31 | [5 empty] | 2000-08-21
S0050W3 | 3573 | 2006-10-09 | Renewable Energy Systems (RES) | Meikle Carewe | Wind Onshore |  |  | 14 | n/a |  |  |  | 1 | 14 |  | n/a | Planning Permission Refused | Application Refused | Rickarton Farms, Stonehaven, Aberdeenshire | Grampian | Scotland | Scotland |  | 383200 | 792000 | Aberdeenshire Council | S000295PF | [5 empty] | 2000-03-20 |  | 2001-12-04
S0053W3 | 3574 | 2009-05-06 | Renewable Energy Systems (RES) | Black Hill (Borders) | Wind Onshore |  |  | 28.6 | n/a |  |  |  | 1.3 | 22 |  | n/a | Operational | Operational | Longformacus Duns Berwickshire | Borders | Scotland | Scotland |  | 373000 | 656300 | Scottish Borders Council | 01/00058/FUL | [5 empty] | 2001-01-22 | [6 empty] | 2001-07-02 |  |  |  |  | 2006-05-01 | 2007-02-14
N00071W | 3575 | 2010-02-23 | Renewable Energy Systems (RES) / BP Energy | Altahullion | Wind Onshore |  |  | 26 | n/a |  |  |  | 1.3 | 20 |  | n/a | Operational | Operational | Alta Hullion Drum Dun Given Co. Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 77906 | 574708 | Northern Ireland Planning Service | [6 empty] | 2001-06-01 | [6 empty] | 2001-10-01 | [5 empty] | 2003-05-01
EN00373 | 3578 | 2009-09-21 | Renewable Energy Systems (RES) | Four Burrows Wind Farm | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 0.3 | 15 |  | n/a | Operational | Operational | Blackwater, Truro, Cornwall | Cornwall | South West | England |  | 176615 | 47930 | Cornwall Council | PA14/1456/94 | [5 empty] | 1994-11-22 | [6 empty] | 1995-03-09 | [5 empty] | 1998-03-01
N00241W | 3579 | 2013-09-12 | Renewable Energy Systems (RES) | Dun Law Extension | Wind Onshore |  |  | 29.75 | n/a |  |  |  | 0.85 | 35 |  | n/a | Operational | Operational | Dun Law (between Fala and Carfraemill 20 miles S-E of Edinburgh | Borders | Scotland | Scotland |  | 347276 | 655153 | Scottish Borders Council | [6 empty] | 2005-04-27 | [6 empty] | 2006-01-16 |  |  |  |  | 2009-05-01 | 2009-09-20
N00421W | 3581 | 2011-06-06 | RWE npower | Lochelbank Wind Farm II | Wind Onshore |  |  | 9.6 | n/a |  |  |  | 0.8 | 12 |  | n/a | Operational | Operational | North of Glenfarg, Perth, Tayside | Tayside | Scotland | Scotland | PH2 9QQ | 311440 | 713477 | Perth and Kinross Council | 4505/00752 | P/PPA/340/491 |  |  |  |  | 2005-04-25 |  | 2005-12-01 |  |  |  | 2007-08-15 | 2007-08-15 |  |  |  |  | 2010-08-01 | 2011-05-25
C0354 | 3582 | 2018-10-30 | RWE Npower Renewables | Brechfa Forest East Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 |  | n/a | Abandoned | Abandoned | Forestry Commission Wales Land and Agricultural Land South of Rhydcymerau (B4337) and North of Abergorlech (B4310) | Dyfed | Wales | Wales |  | 257354 | 236610 | Carmarthenshire County Council | E/24195 | [5 empty] | 2011-01-07 | [6 empty] | 2013-12-17
N00258W | 3583 | 2010-04-28 | Scottish and Southern Energy (SSE) | Harrow's Law | Wind Onshore |  |  | 111 | n/a |  |  |  | 3 | 37 |  | n/a | Planning Application Withdrawn | Application Withdrawn | OS ref NT0553 No address for this project | Strathclyde | Scotland | Scotland |  | 305000 | 653000 | Scottish Government (S36) | [7 empty] | 2010-04-28
N00061W | 3584 | 2004-08-11 | Scottish Power Renewables | Ardeer | Wind Onshore |  |  | 22 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Stevenston, Ayrshire | Strathclyde | Scotland | Scotland |  | 227500 | 642500 | North Ayrshire Council | N/01/00766/PP | [6 empty] | 2004-08-11
N00062W | 3585 | 2004-07-27 | Scottish Power Renewables | Cruach Mhor | Wind Onshore |  |  | 33.302 | n/a |  |  |  | 0.95 | 35 |  | n/a | Operational | Operational | Cruach Mhor, Cowal, Glen Dareul, Agyll, Bute | Strathclyde | Scotland | Scotland |  | 203500 | 687400 | Argyll and Bute Council | 01/01553/DET | [5 empty] | 2001-09-18 | [6 empty] | 2002-06-06 | [5 empty] | 2004-01-31
AA086 | 3587 | 2015-11-24 | Scottish Power Renewables | Lenchwick | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Planning Permission Refused | Application Refused | Land East of Bishampton Bank, Sheriffs Lench | Hereford and Worcester | West Midlands | England |  | 401493 | 249760 | Wychavon District Council | 10/01074 | [5 empty] | 2010-05-04 |  | 2011-01-31
AA079 | 3589 | 2013-10-08 | Severn Trent Water | Roundhill Sewage Works Wind Turbines | Wind Onshore |  |  | 6.8 | n/a |  |  |  | 3.4 | 2 |  | n/a | Appeal Refused | Application Refused | Roundhill Sewage Farm, Whittington Hall Lane, Kinver, Stourbridge, West Midlands | Staffordshire | West Midlands | England | DY7 6PH | 387627 | 283802 | Wyre Forest District Council | 10/0232/LPAC | 11/00019/REF |  |  |  |  | 2010-04-22 |  | 2010-06-09 |  |  | 2011-09-01
04056W4 | 3592 | 2010-04-26 | Tegni | Wern Ddu Wind Farm | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | NW Corwen, Gwyddelwern, Corwen, Denbighshire | Clwyd | Wales | Wales |  | 305800 | 348500 | Denbighshire County Council | 6/2004/278/PS | [5 empty] | 2004-04-23 |  | 2005-01-26 | [9 empty] | 2009-11-01 | 2010-03-01
S0011W1 | 3593 | 2011-04-11 | Trigen | Hagshaw Hill (S15) Wind Farm, Lanarkshire | Wind Onshore |  |  | 7.8 | n/a |  |  |  | 0.6 | 13 |  | n/a | Operational | Operational | The site lies 4km west of Douglas | Strathclyde | Scotland | Scotland |  | 278965 | 630750 | South Lanarkshire Council | [6 empty] | 1994-05-13 | [6 empty] | 1994-11-02 | [5 empty] | 1995-11-01
A0245 | 3594 | 2012-03-15 | Vento Ludens | Muirake | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Cornhill, Banff, Grampian. AB45 2BQ | Grampian | Scotland | Scotland |  | 356817 | 858161 | Aberdeenshire Council | APP/2009/3565 | [5 empty] | 2009-11-02 | [6 empty] | 2010-09-08 | [5 empty] | 2011-12-13
N00371W | 3597 | 2008-04-16 | West Coast Energy | Nutberry | Wind Onshore |  |  | 60 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 6km NE of Coalburn | Strathclyde | Scotland | Scotland |  | 274500 | 633500 | Scottish Government (S36) | CL/05/0667 | [6 empty] | 2008-04-16
EN00353 | 3598 | 2016-05-10 | West Coast Energy /Falck Renewables | Millennium Extension | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 | 125 | n/a | Operational | Operational | Millennium Windfarm on The Achlain and Invergarry amd Aberchalder Estates Glengarry Invergarry Inverness-Shire | Highland | Scotland | Scotland |  | 225200 | 810300 | Highland Council | [6 empty] | 2007-03-10 | [6 empty] | 2008-01-12 |  |  |  |  | 2008-01-13 | 2008-12-01
N00125W | 3599 | 2013-10-08 | Wind Developments | Carricknabrattoge | Wind Onshore |  |  | 12.1 | n/a |  |  |  | 1.1 | 11 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Carrowmaculla, Eshmeen & Tully, Lisnaskea , Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 33764 | 521579 | Northern Ireland Planning Service | L/2002/1183/F | [6 empty] | 2013-10-08
B1042 | 3600 | 2018-09-27 | Wind NI Ltd | Ballykeel Wind Farm | Wind Onshore |  |  | 16.1 | n/a |  |  |  | 2.3 | 7 |  | n/a | Planning Permission Granted | Awaiting Construction | Larne | Co. Antrim | Northern Ireland | Northern Ireland |  | 154000 | 557000 | Northern Ireland Planning Service | F/2013/0244/F |  |  |  | 42915 |  | 2013-12-19 | [6 empty] | 2016-12-13
AA033 | 3601 | 2011-08-09 | Wind Prospect | King's Street | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Permission Refused | Application Refused | King's Street, Brineton, Staffordshire. | Staffordshire | West Midlands | England |  | 381531 | 315066 | South Staffordshire Council | 10/00963/FUL | [5 empty] | 2010-12-13 |  | 2011-04-06
N00333W | 3602 | 2014-12-18 | EDF/China General Nuclear Power Corporation | Rusholme Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 2 | 12 |  | n/a | Operational | Operational | Newland Wind Farm, Land at Pease Farm, Rushmere Grange, Newland | North Yorkshire | Yorkshire and Humber | England |  | 469500 | 426500 | Selby District Council | 8/26/62/PA | [5 empty] | 2004-07-02 | [6 empty] | 2006-10-16 |  |  |  |  | 2010-08-01 | 2010-10-04
01007W5 | 3603 | 2005-11-01 | Wind Prospect | Darcey Lode | Wind Onshore |  |  | 1.96 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Sears Farm, Manea, Cambridgeshire | Cambridgeshire | Eastern | England |  | 549300 | 294300 | Fenland District Council | DARCEY LODE F/99/0411/F | [6 empty] | 2005-11-01
01008W5 | 3604 | 2006-04-24 | Wind Prospect | Honey Hill | Wind Onshore |  |  | 1.96 | n/a |  |  |  | 0 | 0 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Honey Hill Farm, Chatteris, Cambridgeshire | Cambridgeshire | Eastern | England |  | 545000 | 287900 | Fenland District Council | F/99/0412/f | [6 empty] | 2006-04-24
N00247W | 3605 | 2010-05-21 | Wind Prospect | Longpark | Wind Onshore |  |  | 38 | n/a |  |  |  | 2 | 19 |  | n/a | Operational | Operational | Stow | Borders | Scotland | Scotland |  | 348050 | 642050 | Scottish Borders Council | 04/00317/FUL | P/PPA/140/251 |  |  |  |  | 2004-02-16 |  | 2005-08-31 | [9 empty] | 2009-06-01 | 2009-09-01
N00284W | 3606 | 2009-05-06 | Wind Prospect | Walkway | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Operational | Operational | Sedgefield | Durham | North East | England |  | 439000 | 530000 | Durham County Council | [6 empty] | 2004-11-01 | [6 empty] | 2005-02-20 | [5 empty] | 2008-05-15
01006W5 | 3607 | 2011-04-11 | Wind Prospect / TXU | Coldham | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Cws Coldham Estate, March, Cambridgeshire | Cambridgeshire | Eastern | England |  | 542000 | 302000 | Fenland District Council | F/99/0410/F | [5 empty] | 1999-08-02 | [6 empty] | 2004-10-07 | [5 empty] | 2005-11-01
N00280W | 3608 | 2017-12-04 | Wind Prospect Developments | Red Tile | Wind Onshore |  |  | 24 | n/a |  |  |  | 2 | 12 |  | n/a | Operational | Operational | Land Adjacent to Broadpool Farm High Fen Straight Drove Warboys Huntingdon | Cambridgeshire | Eastern | England |  | 534086 | 283221 | Huntingdonshire District Council | 0302827FUL | [5 empty] | 2003-10-15 | [6 empty] | 2005-02-07 |  |  |  |  | 2006-05-01 | 2006-12-01
B0240 | 3609 | 2017-12-04 | Wind Prospect Developments | Deeping St Nicholas Wind Farm | Wind Onshore |  |  | 16.4 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Vine House Farm Worths Farm and Porters Farm, Deeping St Nicholas | Lincolnshire | East Midlands | England |  | 519905 | 316471 | South Holland District Council | H03-0161-02 | APP/A2525/A/02/1099738 |  |  |  |  | 2002-02-11 |  | 2002-09-13 |  |  |  | 2003-05-18 | 2003-05-18 | [5 empty] | 2006-08-01
IF1247 | 3610 | 2013-05-21 | Wind Prospect Developments | Mount Lothian Wind Farm | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Moss Penicuik | Lothian | Scotland | Scotland |  | 326843 | 655899 | Midlothian Council | 13/00063/DPP | [5 empty] | 2013-01-30 | 2013-05-17
07126W3 | 3611 | 2009-06-23 | Windprospect | Lowca Wind Farm | Wind Onshore |  |  | 4.744 | n/a |  |  |  | 0.67 | 7 |  | n/a | Operational | Operational | Lowca Near Workington Cumbria | Cumbria | North West | England |  | 298600 | 523600 | Copeland Borough Council | 4/98/0486 | [5 empty] | 1998-06-26 |  | 1998-10-14 |  |  |  | 1999-03-19 | 1999-03-19 | [5 empty] | 2000-04-01
07128W3 | 3612 | 2009-06-23 | Windprospect | Drigg Wind Cluster | Wind Onshore |  |  | 2.953 | n/a |  |  |  | 0 | 5 |  | n/a | Appeal Refused | Application Refused | Land adjacent to Shore Road Drigg Seascale Cumbria | Cumbria | North West | England |  | 305500 | 498900 | Copeland Borough Council | 4/96/0560 | [5 empty] | 1996-07-29 |  | 1996-11-07 |  |  | 1997-12-30
EN00233 | 3613 | 2011-06-06 | Windprospect | Fairfield Farm | Wind Onshore |  |  | 6.5 | n/a |  |  |  | 1.3 | 5 |  | n/a | Operational | Operational | Fairfield Farm Pica Distington | Cumbria | North West | England |  | 301826 | 521459 | Copeland Borough Council | 4/2006/2684 | [5 empty] | 2006-09-29 |  | 2007-04-04 |  |  |  | 2008-05-20 | 2008-05-20 |  |  |  |  | 2010-08-01 | 2011-03-02
N00001W | 3614 | 2011-04-11 | Windprospect | Haverigg Repowering (Haverigg II) | Wind Onshore |  |  | 1.15 | n/a |  |  |  | 0.22 | 5 |  | n/a | Operational | Operational | Kirksanton Airfield Part of Hemplands Farm Haverigg Millom Cumbria | Cumbria | North West | England |  | 313700 | 479500 | Copeland Borough Council | 4/02/0505/0 | [5 empty] | 2002-04-29 | [6 empty] | 2002-08-15 | [5 empty] | 2004-05-01
N00426W | 3615 | 2009-06-23 | Windprospect | Fairfield Farm (Re-Submission) | Wind Onshore |  |  | 7.8 | n/a |  |  |  | 0 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Pica, Whitehaven CA14 4PZ | Cumbria | North West | England |  | 301500 | 521500 | Copeland Borough Council | 4/05/2738/0FI | [6 empty] | 2009-06-23
A0365 | 3616 | 2011-04-07 | Private Developer | Auchenten | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Appeal Refused | Application Refused | Hatton, Peterhead, Aberdeenshire. AB42 0QS | Grampian | Scotland | Scotland |  | 404112 | 835283 | Aberdeenshire Council | APP/2009/3610 | PPA-110-2074 |  |  |  |  | 2009-11-05 |  | 2010-10-08 |  |  | 2011-03-10
C2808 | 3617 | 2014-06-02 | Babworth Estate | Babworth Estate | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Smeath Road Retford Nottinghamshire | Nottinghamshire | East Midlands | England |  | 471060 | 383584 | Bassetlaw District Council | 14/00237/FUL | [5 empty] | 2014-03-13 |  | 2014-05-08
B1325 | 3619 | 2018-04-03 | Octopus Investments/Blue Energy | Beinneun Windfarm Extension | Wind Onshore |  |  | 23.8 | n/a |  |  |  | 3.4 | 7 | 136 | n/a | Operational | Operational | 8km west of Invergarry | Highland | Scotland | Scotland |  | 220442 | 804419 | Scottish Government (S36) | EC00002095 | [5 empty] | 2014-10-14 | [6 empty] | 2015-06-02 |  |  |  | 2018-06-02 | 2015-07-15 | 2017-02-16
AA504 | 3620 | 2014-01-30 | Bidwells | Bodinfinnoch Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Appeal Refused | Application Refused | Bodinfinnoch Farm, Keith, Moray | Grampian | Scotland | Scotland |  | 339685 | 849303 | Moray Council | 11/01509/APP | [5 empty] | 2011-09-08 |  | 2012-12-07 |  |  | 2013-11-21
C1707 | 3621 | 2014-06-06 | Renewable Energy Ventures | Burnside Wind Cluster (3rd Resubmission) | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land to the West of Blackhills Farm, Cushnie, Alford | Grampian | Scotland | Scotland | AB33 8LQ | 350816 | 808129 | Aberdeenshire Council | APP/2013/2279 | [5 empty] | 2013-07-24 |  | 2014-05-16
B0029 | 3622 | 2012-09-14 | WCE | Cairnborrow | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Planning Permission Refused | Application Refused | Huntly, Aberdeenshire | Grampian | Scotland | Scotland |  | 344946 | 842224 | Aberdeenshire Council | APP/2011/1639 | [5 empty] | 2011-06-02 |  | 2012-08-31
B1324 | 3623 | 2018-05-30 | Muirhall Energy | Caplich Wind Farm | Wind Onshore |  |  | 68 | n/a |  |  |  | 3.4 | 23 |  | n/a | Appeal Refused | Application Refused | Land 450M NW Of Beinn An Eoin Bheag Caplich Lairg | Highland | Scotland | Scotland |  | 237000 | 906000 | Scottish Government (S36) | EC00002088 | WIN-270-7 |  |  |  |  | 2015-01-10 |  |  | 2016-06-01 |  | 2018-04-27
C2916 | 3624 | 2018-10-30 | Private Developer | Cornabo | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Appeal Granted | Awaiting Construction | Land To The South West Of Cornabo Monymusk Aberdeenshire AB51 7JL | Grampian | Scotland | Scotland | AB51 7JL | 364449 | 817874 | Aberdeenshire Council | APP/2014/1338 | PPA-110-2241 |  |  |  |  | 2014-04-11 |  | 2014-10-03 | 2014-10-21 |  |  | 2015-03-23 | 2015-03-23 |  |  |  | 2018-03-23
C2450 | 3625 | 2019-07-18 | Force 9 Energy LLP and EDF Energy | Craigton and Spittalhill Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 | 125 | n/a | Planning Permission Expired | Planning Permission Expired | Land 2 Kilometres North West Of Wester Cringate, Polmaise Road To Carron Reservoir Stirling | Stirling | Scotland | Scotland |  | 266452 | 688768 | Stirling Council | 13/00728/FUL | PPA-390-2039 |  |  |  |  | 2013-12-05 |  | 2015-03-24 | 2015-06-23 |  |  | 2015-11-17 | 2015-11-17 |  |  |  | 2018-11-17
B0080 | 3626 | 2012-10-02 |  | Cross House Farm Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Cross House Farm, Kirkland | Lancashire | North West | England |  | 348212 | 444289 | Wyre Borough Council | 11/00861/FULMAJ | [5 empty] | 2011-12-01 |  | 2012-09-06
N00168WR | 3627 | 2017-07-19 | Scottish Power Renewables | Ewe Hill (extension) | Wind Onshore |  |  | 36.8 | n/a |  |  |  | 2.3 | 16 |  | n/a | Operational | Operational | Near Langham and Lockerbie | Dumfries and Galloway | Scotland | Scotland |  | 315000 | 580000 | Scottish Government (S36) | [6 empty] | 2004-03-31 | [6 empty] | 2014-05-16 |  |  |  |  | 2016-03-30 | 2017-01-15
B1321 | 3629 | 2020-04-22 | ABO Wind | Green Burn Wind Farm | Wind Onshore |  |  | 33 | n/a |  |  |  | 3 | 11 | 115 | n/a | Appeal Granted | Awaiting Construction | land at Blackhall Farm and Shieldrum Farm, approximately 11km north-west of Alyth and 5km north-east of Bridge of Cally in Perth and Kinross | Tayside | Scotland | Scotland |  | 315871 | 755635 | Perth and Kinross Council | 15/01691/FLM | PPA-340-2109 |  |  |  |  | 2015-10-07 |  | 2017-03-15 | 2017-06-13 |  |  | 2018-02-20 | 2018-02-20 |  |  |  | 2023-02-20
C1889 | 3630 | 2015-03-25 | Castlemilk and Carmunnock Community Windpark Trust | Castlemilk and Carmunnock Community Windpark Trust | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land to the East of Muir Farm, Cathkin Road, Rutherglen | Strathclyde | Scotland | Scotland | G76 9EZ | 261804 | 657558 | South Lanarkshire Council | EK/13/0248 | [5 empty] | 2013-08-19 |  | 2013-11-20
C2609 | 3631 | 2014-05-22 | Private Developer | Chapelton Farm | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Planning Permission Refused | Application Refused | Chapelton Farm, Girvan, South Ayrshire | Strathclyde | Scotland | Scotland | KA26 9JU | 224460 | 605122 | South Ayrshire Council | 13/01506/APP | [5 empty] | 2014-01-13 |  | 2014-05-01
B1034 | 3632 | 2015-09-02 | Airvolution Energy | Church House Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Appeal Withdrawn | Application Withdrawn | Church House Farm, Cumbria | Cumbria | North West | England |  | 304127 | 504780 | Copeland Borough Council | 4/14/2105/0F1 | APP/Z0923/W/15/3067569 |  |  |  |  | 2014-03-31 |  |  | 2015-07-20 | 2015-08-20
C2874 | 3633 | 2020-01-16 | Mitchell Farming Partnerships (3R Energy) | Hazelside farm - resubmission | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Under Construction | Under Construction | side Farm, Lanark, Strathclyde | Strathclyde | Scotland | Scotland | ML11 0SD | 281251 | 630930 | South Lanarkshire Council | CL/14/0132 | [5 empty] | 2014-04-01 | [6 empty] | 2014-12-18 |  |  |  | 2017-12-18 | 2016-02-15
B1323 | 3634 | 2015-09-02 | EDF Energy Renewables | High Wood Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 | 126.5 | n/a | Planning Application Withdrawn | Application Withdrawn | High Wood Wind Farm, Dalton, Driffield, Humberside | Humberside | Yorkshire and Humber | England | YO25 | 494404 | 454025 | East Riding of Yorkshire Council | 15/00315/STPLFE | [5 empty] | 2015-02-02 | 2015-08-03
C2949 | 3635 | 2015-07-01 | West Coast Energy | Hill of Nigg | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 | 115 | n/a | Planning Permission Refused | Application Refused | Land South of Wester Rarichie Darm, Fearn | Highland | Scotland | Scotland |  | 283725 | 872535 | Highland Council | 15/00093/FUL | [5 empty] | 2015-01-13 |  | 2015-06-05
C2260 | 3636 | 2014-03-19 | Private Developer | Hillhead of Bonnykelly - resubmission | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Hillhead, Bonnykelly, New Pitsligo, Fraserburgh | Grampian | Scotland | Scotland | AB43 6PN | 384710 | 853697 | Aberdeenshire Council | APP/2013/3204 | [5 empty] | 2013-10-24 |  | 2014-02-27
B1011 | 3637 | 2015-12-02 | RWE Renewables | Kirkby Moor Repowering | Wind Onshore |  |  | 18 | n/a | 0.9 | n/a |  | 3 | 6 | 115 | n/a | Planning Permission Refused | Application Refused | Land at Kirkby Moor Wind Farm, Kirkby-In-Furness, Cumbria | Cumbria | North West | England | LA1 7 | 324960 | 483215 | South Lakeland District Council | SL/2014/1220 | [5 empty] | 2015-02-28 |  | 2015-11-26
IF1124 | 3638 | 2020-05-26 | Stamford Renewable Power | Laurels Farm - second resubmission | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Appeal Granted | Awaiting Construction | Laurels Farm, Shipmeadow, Beccles, NR34 8HD | Suffolk | Eastern | England | NR34 8HD | 638340 | 289150 | Waveney District Council | DC/12/1332/FUL | [5 empty] | 2012-11-29 |  | 2013-04-09 |  |  |  | 2014-04-02 | 2014-04-02
C2875 | 3639 | 2019-10-31 | Private Developer | Linburn Farm (resubmission 2) | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Planning Permission Expired | Planning Permission Expired | Linburn Farm B743 From U751 Tardoes Crossflat To U731 Greenock Water Muirkirk East Ayrshire | Strathclyde | Scotland | Scotland |  | 266311 | 628312 | East Ayrshire Council | 14/0229/PP | PPA-190-2045 |  |  |  |  | 2014-03-18 |  | 2015-03-02 | 2015-04-21 |  |  | 2015-11-05 | 2015-11-05 |  |  |  | 2018-11-05
C1593 | 3640 | 2014-05-14 | Private Developer | Linburn Farm (resubmission) | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Linburn Farm B743 From U751 Tardoes Crossflat To U731 Greenock Water Muirkirk East Ayrshire | Strathclyde | Scotland | Scotland |  | 266311 | 628312 | East Ayrshire Council | 13/0416/PP | [5 empty] | 2013-06-17 | 2014-03-10
EN00430 | 3641 | 2011-06-29 | Ecotricity | Lotus Manufacturing | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land at Group Lotus PLC, Potash Lane, Hethel, Wymondham, South Norfolk | Norfolk | Eastern | England |  | 615050 | 300820 | South Norfolk Council | 2007/1427 | [5 empty] | 2007-06-28 |  | 2007-10-09
B0505 | 3642 | 2017-03-31 | Whirlwind Renewables | Bonwick | Wind Onshore |  |  | 17 | n/a |  |  |  | 3.4 | 5 | 132 | n/a | Planning Permission Refused | Application Refused | Low Bonwick Farm Skipsea Road Bewholme East Riding Of Yorkshire YO25 8EE | Humberside | Yorkshire and Humber | England | YO25 8EE | 516050 | 452071 | East Riding of Yorkshire Council | 15/00517/STPLFE | [5 empty] | 2015-03-05 |  | 2017-02-27
C3001 | 3643 | 2015-05-22 | Greencoat UK Wind | Maerdy extension | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Abandoned | Abandoned | Land between Maerdy Coal Tip and Tynewydd Forest | Mid Glamorgan | Wales | Wales |  | 295856 | 199544 | Rhondda Cynon Taff County Borough Council | 14/0556/10 | [5 empty] | 2014-05-01 | [6 empty] | 2014-12-22 |  |  |  | 2015-02-09
C2884 | 3644 | 2014-11-06 | Muirden Energy | Mains Of Collithie | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land To South West Of Mains Of Collithie Gartly Huntly | Grampian | Scotland | Scotland | AB54 4PW | 350669 | 834804 | Aberdeenshire Council | APP/2014/1032 | [5 empty] | 2014-03-05 |  | 2014-08-25
C1436 | 3645 | 2016-04-29 | Seneca Global Energy | Melton Waste Park | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 | 119 | n/a | Abandoned | Abandoned | Land South West Of Melton Waste Park Gibson Lane South Melton East Riding Of Yorkshire HU14 3HH | Humberside | Yorkshire and Humber | England |  | 496525 | 425211 | East Riding of Yorkshire Council | 13/01806/STPLFE | [5 empty] | 2013-06-14 | [6 empty] | 2013-12-19
B0606 | 3646 | 2013-09-20 | Community Windpower | Millour Hill Community Windfarm (Extension) | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Site To North Of Baidland Hill, Dalry, Ayrshire | Strathclyde | Scotland | Scotland |  | 225820 | 652480 | North Ayrshire Council | 12/00526/PP | [5 empty] | 2012-09-20 |  | 2013-06-05
B0713 | 3647 | 2016-05-26 | Eneco | Moy Wind Farm (2nd Application) | Wind Onshore |  |  | 66 | n/a |  |  |  | 3.3 | 20 |  | n/a | Operational | Operational | Tomatin, Invernessshire | Highland | Scotland | Scotland | IV13 7YD | 276947 | 835012 | Scottish Government (S36) | [6 empty] | 2013-04-22 | [6 empty] | 2014-01-24 |  |  |  |  | 2014-04-22 | 2016-05-12
04037W4 | 3648 | 2014-06-06 | Zond (UK) Ltd (Enron Wind Overseas Development) | Mynydd y Gwynt Wind Farm | Wind Onshore |  |  | 89.1 | n/a |  |  |  | 3.3 | 27 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Mynydd y Gwynt, Lllangurig, Llanidloes, Powys | Powys | Wales | Wales |  | 283850 | 284250 | DECC (S36) | S36 | [5 empty] | 2014-04-24 | 2014-05-22
C2535 | 3650 | 2014-05-19 | Clearwinds | Redhill Farms | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Site to South West of East Redhill, Rothienorman, Inverurie | Grampian | Scotland | Scotland |  | 367983 | 836360 | Aberdeenshire Council | APP/2013/3856 | [5 empty] | 2013-12-10 |  | 2014-05-19
B1318 | 3651 | 2016-02-16 | Green Cat Renewables | Rosehill Wind Turbines | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Land Some 550 Metres East Of Rosehill Rosehill Road Tower Plean | Stirling | Scotland | Scotland |  | 286252 | 686188 | Stirling Council | 12/00708/FUL | 13/00017/REF |  |  |  |  | 2012-10-31 |  | 2013-09-10 |  |  |  | 2014-04-24 | 2014-04-24 |  |  |  |  | 2015-05-15 | 2015-12-15
C1391 | 3652 | 2013-09-23 | Volkswind UK Ltd | Spaldington Common wind cluster - resubmission | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land South West Of Ivy House Farm Holme Road Spaldington East Riding Of Yorkshire DN14 7GX | Humberside | Yorkshire and Humber | England |  | 478066 | 432596 | East Riding of Yorkshire Council | 13/00698/STPLFE | [5 empty] | 2013-04-08 |  | 2013-09-23
B0608 | 3654 | 2012-12-18 | J & G Energy Ltd | Yonderton Farm (Re-submission) | Wind Onshore |  |  | 1 | n/a |  |  |  | 1 | 1 |  | n/a | Planning Permission Refused | Application Refused | Hatton, Peterhead, Aberdeenshire | Grampian | Scotland | Scotland | AB42 0QS | 403578.5 | 837831.4 | Aberdeenshire Council | APP/2011/3206 | [5 empty] | 2011-09-20 |  | 2012-08-31
AA682 | 3655 | 2012-06-15 | Yowlie Energy Ltd | Yowlie Wind Cluster | Wind Onshore |  |  | 3.2 | n/a |  |  |  | 0.8 | 4 |  | n/a | Planning Permission Refused | Application Refused | Douglashead Farm, Tarves, Ellon | Grampian | Scotland | Scotland | AB41 7LU | 390214 | 831922 | Aberdeenshire Council | APP/2011/4273 | [5 empty] | 2012-01-10 |  | 2012-05-01
B0883 | 3657 | 2017-04-26 | NTR | Twin Rivers | Wind Onshore |  |  | 28.7 | n/a |  |  |  | 2.05 | 14 |  | n/a | Operational | Operational | Moor Lane, Whitgift, East Riding of Yorkshire | Humberside | Yorkshire and Humber | England |  | 472545 | 412960 | East Riding of Yorkshire Council | 04/00505/STPLFE | [5 empty] | 2004-01-20 | [6 empty] | 2009-01-05 |  |  |  |  | 2015-05-15 | 2016-08-03
06017W4 | 3659 | 2013-10-08 | Border Wind Farms Ltd | Blyth Harbour Wind Farm | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.3 | 9 |  | n/a | Operational | Operational | Blyth Harbour North Blyth Cambois Bedlington Northumberland | Northumberland | North East | England |  | 432290 | 581345 | Northumberland County Council | 91/00011/181OTH | [5 empty] | 1991-05-23 | [6 empty] | 1992-03-06 | [5 empty] | 1992-12-01
10035W4 | 3660 | 2013-11-06 | John Laing Environmental Assets Group | Penrhys Wind Farm/Ferndale Power Factory | Wind Onshore |  |  | 6.4 | n/a |  |  |  | 0.8 | 8 |  | n/a | Operational | Operational | Penrhys Rhondda Mid Glamorgan | Mid Glamorgan | Wales | Wales |  | 299700 | 195700 | Rhondda Cynon Taff County Borough Council | 03/0226 | App/L6940/A/04/754 |  |  |  |  | 2003-02-11 |  | 2004-01-09 |  |  |  | 2005-03-01 | 2005-03-01 |  |  |  |  | 2010-04-01 | 2011-06-08
13004W5 | 3662 | 2012-07-04 | Scottish and Southern Energy (SSE) | Gordonbush | Wind Onshore |  |  | 70 | n/a |  |  |  | 2 | 35 |  | n/a | Operational | Operational | Gordonbush Estate, Brora, Sutherland, Highlands | Highland | Scotland | Scotland |  | 284500 | 909500 | Scottish Government (S36) | [6 empty] | 2003-06-17 | [6 empty] | 2008-04-09 |  |  |  |  | 2010-07-01 | 2012-06-12
A0001 | 3663 | 2018-10-03 | Renewable Energy Systems (RES) | Llanbrynmair Wind Farm | Wind Onshore |  |  | 69 | n/a |  |  |  | 2.3 | 30 |  | n/a | Planning Application Submitted | Application Submitted | Llanbrynmair , Powys | Powys | Wales | Wales | SY19 7 | 293294 | 308952 | DECC (S36) |  |  |  |  | 42368 |  | 2009-01-09
A0013 | 3664 | 2014-02-27 | Wessex Water Engineering Services | Avonmouth Wind Power | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2.05 | 4 |  | n/a | Operational | Operational | Bristol Sewage Treatment Work, Bristol, BS11 0YS | Avon | South West | England |  | 353358 | 179393 | Bristol City Council | 08/04925/F | [5 empty] | 2008-12-08 | [6 empty] | 2009-03-25 |  |  |  |  | 2012-12-03 | 2014-02-06
A0024 | 3666 | 2013-06-04 | Ventient (formerly Infinis) | Gordonstown Hill Wind Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | Gordonstown Hill Kirkton Of Auchterless, Turiff, Grampian, AB53 8BG | Grampian | Scotland | Scotland |  | 371136 | 841396 | Aberdeenshire Council | APP/2008/4244 | [5 empty] | 2008-12-24 | [6 empty] | 2009-07-02 |  |  |  |  | 2012-07-23 | 2013-03-31
A0043 | 3667 | 2013-04-19 | Branna Industrial & Technical Services Ltd | The Rosti Factory | Wind Onshore |  |  | 2.2 | n/a |  |  |  | 2.2 | 1 |  | n/a | Operational | Operational | Middleton Avenue, Strutherhil Industrial Estate, Larkhill, Strathclyde. ML9 2TL | Strathclyde | Scotland | Scotland |  | 276956 | 649658 | South Lanarkshire Council | HM/09/0173 | [5 empty] | 2009-04-21 | [6 empty] | 2010-11-24 | [5 empty] | 2013-02-18
A0074 | 3668 | 2012-02-24 | Ben Aketil Wind Energy Ltd | Ben Aketil Extension | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Operational | Operational | Near Dunvegan, Isle of Skye. IV55 8 | Highland | Scotland | Scotland |  | 132500 | 846500 | Highland Council | 09/00115/FULSL | [5 empty] | 2009-04-16 | [6 empty] | 2010-02-04 |  |  |  |  | 2010-04-01 | 2011-01-01
A0076 | 3669 | 2014-05-29 | RWE npower | Rowantree Wind Farm | Wind Onshore |  |  | 69 | n/a |  |  |  | 3 | 23 |  | n/a | Planning Permission Refused | Application Refused | Oxton, Lauder, Borders | Borders | Scotland | Scotland | TD2 | 347000 | 650000 | Scottish Government (S36) | [6 empty] | 2009-12-31 |  | 2014-05-16
A0077 | 3670 | 2019-11-05 | Storas Uibhist | Lochcarnan Community Windfarm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Lochcarnan, Isle of South Uist. HS8 5 | Western Isles | Scotland | Scotland |  | 77451 | 828569 | Comhairle nan Eilean Siar Council | 08/00561/FUL | [5 empty] | 2008-12-04 | [6 empty] | 2011-12-21 |  |  |  |  | 2012-03-21 | 2013-02-18
A0079 | 3671 | 2013-04-19 | Renewable Energy Systems (RES) | The Grange Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Operational | Operational | Middle Road, Tydd St. Mary, Wisbech, Cambridge | Lincolnshire | East Midlands | England | PE13 5QZ | 546300 | 319200 | South Holland District Council | H21-0439-09 | [5 empty] | 2009-06-17 |  | 2010-04-16 |  |  |  | 2010-10-15 | 2010-10-15 |  |  |  |  | 2012-09-01 | 2013-03-01
A0085 | 3672 | 2013-03-04 | Roy Humphrey Group | Humphrey Group | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | Eye Airfield Industrial Estate, Ipswich Road, Brome, Eye, Suffolk, IP23 8AW | Suffolk | Eastern | England |  | 613107 | 275558 | Mid Suffolk District Council | 0724/10 | [5 empty] | 2010-03-12 | [6 empty] | 2010-07-20 |  |  |  |  | 2013-01-09 | 2013-02-25
A0087 | 3673 | 2017-04-18 | REG Windpower | Rodbaston | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Rodbaston, Farm Drive, Rodbaston Campus, Stafford | Staffordshire | West Midlands | England | ST19 5PH | 392176 | 311645 | South Staffordshire Council | 09/00524/FUL | [5 empty] | 2009-07-16 | [6 empty] | 2010-12-15 |  |  |  |  | 2016-02-01 | 2017-01-15
A0094 | 3674 | 2015-03-25 | EDF | Boundary Lane | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Shotley Quarter, Whittonstall, Nr Consett, Co Durham. DH8 9 | Durham | North East | England |  | 404708 | 550336 | Northumberland County Council | 09/00092/CCMEIA | [5 empty] | 2009-06-16 | [6 empty] | 2011-02-17 |  |  |  |  | 2012-09-01 | 2013-03-31
A0097 | 3675 | 2015-03-25 |  | Mars Petcare | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Abandoned | Abandoned | Oakwell Way, Birstall, Batley WF17 9LU | West Yorkshire | Yorkshire and Humber | England |  | 423215 | 427292 | Kirklees Council | 2009/62/93375/E1 | APP/Z4718/A/10/2128426 |  |  |  |  | 2009-12-02 |  | 2010-04-01 |  |  |  | 2010-09-06 | 2010-09-06
A0098 | 3676 | 2015-03-25 |  | Nutberry Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | Cumberhead, Lesmahagow, Lanark, Strathclyde. ML11 0HN | Strathclyde | Scotland | Scotland |  | 279021 | 635662 | South Lanarkshire Council | CL/06/0662 | P/PPA/380/435 |  |  |  |  | 2006-09-28 |  | 2008-09-09 |  |  |  | 2011-04-05 | 2011-04-05 |  |  |  |  | 2011-12-01 | 2013-09-30
A0108 | 3677 | 2013-08-23 | Banks Renewables | Penny Hill Lane | Wind Onshore |  |  | 19.8 | n/a |  |  |  | 3.3 | 6 |  | n/a | Operational | Operational | Ulley, Sheffield, South Yorks. S26 3YA | South Yorkshire | Yorkshire and Humber | England |  | 446825 | 387627 | Rotherham Metropolitan Borough Council | RB2009/0824 | [5 empty] | 2009-07-22 | [6 empty] | 2010-05-27 |  |  |  |  | 2012-07-26 | 2013-03-31
A0109 | 3678 | 2016-07-28 | Tobermore Concrete Products | Magherafelt | Wind Onshore |  |  | 1 | n/a |  |  |  | 1 | 1 |  | n/a | Operational | Operational | 2 Lisnamuck Road, Tobermore, Magherafelt, Co Londonderry. BT45 5QF | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 101186 | 551482 | Northern Ireland Planning Service | H/2009/0420/F | [5 empty] | 2009-07-15 | [6 empty] | 2010-11-11 |  |  |  | 2015-11-11 | 2015-11-01 | 2015-06-12
A0119 | 3679 | 2018-08-30 | ProWind GMBH | Scalm Park / Bishopwood | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.3 | 7 |  | n/a | Appeal Withdrawn | Application Refused | Wistow Common, Selby, North Yorks | North Yorkshire | Yorkshire and Humber | England | YO8 3RD | 456564 | 433071 | Selby District Council | 09/0464/FUL | APP/N2739/A/13/2201308 | APP/N2739/A/13/2201308 | Recovered Appeal |  |  | 2009-07-01 |  | 2013-01-14 | 2013-10-22 | 2015-11-06
A0121 | 3680 | 2013-04-19 | Ecotricity | The Michelin Tyre Factory - Ballymena | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Raceview Road, Broughshane, Woodside Road, Ballymena, Co Antrim. BT42 4J | Co. Antrim | Northern Ireland | Northern Ireland |  | 130743 | 561194 | Northern Ireland Planning Service | G/2009/0470/FUL | [5 empty] | 2009-07-24 | [6 empty] | 2010-02-07 |  |  |  |  | 2012-09-11 | 2013-02-25
A0131 | 3681 | 2013-10-08 | West Knock Farm | West Knock Wind Cluster | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Mintlaw, Stuartfield, Peterhead, Grampian. AB42 5DJ | Grampian | Scotland | Scotland |  | 398494.2 | 844839.7 | Aberdeenshire Council | APP/2009/2439 | [5 empty] | 2009-07-27 | [6 empty] | 2011-04-21 | [5 empty] | 2011-10-04
A0134 | 3682 | 2012-05-09 | Infinis, previously Broadview Energy Developments | Low Spinney Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Gilmorton Lane, Ashby Magnor, Lutterworth, Leicestershire. LE17 5NB | Leicestershire | East Midlands | England |  | 455816 | 289705 | Harborough District Council | 09/00174/FUL | [5 empty] | 2009-02-11 | [6 empty] | 2009-09-03 |  |  |  |  | 2011-01-01 | 2011-09-29
A0140 | 3683 | 2013-06-27 | Private Developer | Hill of Tillymorgan | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Culsalmond, Insch, Grampian. AB52 | Grampian | Scotland | Scotland |  | 363363 | 828345 | Aberdeenshire Council | APP/2008/0147 | [5 empty] | 2008-03-03 | 2013-05-15
A0141 | 3684 | 2013-06-04 | Ventient (formerly Infinis) | Westfield | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | Near Kingassie, Lochgelly, Fife. KY5 0J | Fife | Scotland | Scotland |  | 319640 | 695487 | Fife Council | 09/01861/EIA | [5 empty] | 2009-07-31 | [6 empty] | 2012-06-22 |  |  |  |  | 2012-07-30 | 2013-03-31
A0145 | 3685 | 2012-12-07 | Nuon UK | Swinford Wind Farm | Wind Onshore |  |  | 27.5 | n/a |  |  |  | 0.4 | 11 |  | n/a | Operational | Operational | Lutterworth Road, Swinford, Lutterworth, Leicestershire. LE17 6BA | Leicestershire | East Midlands | England |  | 456804 | 279647 | Harborough District Council | 08/00506/FUL | 09/00011/NONDET |  |  |  |  | 2008-04-09 |  | 2009-09-01 |  |  |  | 2009-12-30 | 2009-12-30 |  |  |  |  | 2011-12-01 | 2012-11-21
A0148 | 3686 | 2013-06-25 | Fivestone Ltd | Burnt House Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Burnt House Road, Whittlesey, Burnthouse Sidings, Peterborough, Cambs | Cambridgeshire | Eastern | England | PE7 2HP | 533458 | 295082 | Fenland District Council | F/YR09/0392/F | 10/00019/REF |  |  |  |  | 2009-06-10 |  | 2010-01-04 |  |  |  | 2011-07-08 | 2011-07-08 |  |  |  |  | 2013-01-01 | 2013-06-19
A0157 | 3687 | 2015-11-03 | Acciona Energy | Cemmaes 3 Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 2.3 | 12 |  | n/a | Appeal Withdrawn | Application Refused | east of Cwm Llinau on Mynydd Y Cemmaes ,AES, Llanbrynmair, Powys | Powys | Wales | Wales | SY19 | 289301 | 299128 | Powys County Council | P/2008/0249 | [5 empty] | 2008-02-29 |  | 2013-01-22 | 2014-03-04 | 2015-10-22
A0163 | 3688 | 2015-03-25 | Community Windpower (Community Wind Power) | Calder Water Community Wind Farm | Wind Onshore |  |  | 28 | n/a |  |  |  | 2 | 14 |  | n/a | Operational | Operational | Harshaw Hill, Drumclog, Strathaven, Strathclyde. ML10 6QN | Strathclyde | Scotland | Scotland |  | 260869 | 640428 | South Lanarkshire Council | EK/09/0290 | [5 empty] | 2009-08-26 | [6 empty] | 2011-11-29 | [5 empty] | 2013-09-01
A0164 | 3689 | 2015-03-25 | Vattenfall | Whitton Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Permission Refused | Application Refused | Morebattle, Kelso, The Borders | Borders | Scotland | Scotland | TD5 8QX | 376026 | 622331 | Scottish Borders Council | 09/01162/FUL | [5 empty] | 2009-08-27 |  | 2013-07-08
A0166 | 3690 | 2015-03-25 | Community Windpower | Millour Hill Community Windfarm (Re-submission) | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Operational | Operational | Baidland Hill, North Ayrshire | Strathclyde | Scotland | Scotland |  | 225843 | 652080 | North Ayrshire Council | 09/00424/PPM | [5 empty] | 2009-06-25 | [6 empty] | 2009-12-16 |  |  |  |  | 2011-04-01 | 2012-05-01
A0180 | 3691 | 2015-03-19 | Strathdee Energy | Netherton of Windyhills | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Grange Crossroads, Keith, Grampian | Grampian | Scotland | Scotland | AB55 6NL | 348948 | 857294 | Moray Council | 09/00763/FUL | [5 empty] | 2009-06-15 | [6 empty] | 2010-10-15 |  |  |  |  | 2013-11-01 | 2014-11-01
A0185 | 3692 | 2012-11-28 | SLP Engineering Ltd | North of A19 Services | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 1.25 | 2 |  | n/a | Appeal Refused | Application Refused | West of Dalton Park, Murton, Seaham, County Durham. SR7 9HU | Durham | North East | England |  | 440303 | 546909 | Durham County Council | PL/5/2009/0357 | APP/X1355/A/10/2136431 |  |  |  |  | 2009-09-03 |  | 2010-10-09 |  |  | 2011-03-22
A0200 | 3693 | 2013-04-19 | Private Developer | Gallowhill | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Operational | Operational | West Manse, Westray, KW17 2DR | Orkney Islands | Scotland | Scotland |  | 344124 | 1043753 | Orkney Islands Council | 08/491/PPF | [5 empty] | 2008-10-13 | [6 empty] | 2009-03-02 | [5 empty] | 2013-02-18
A0207 | 3694 | 2018-05-01 | Foresight/Belltown | Frodsham Marsh | Wind Onshore |  |  | 50.35 | n/a |  |  |  | 2.65 | 19 |  | n/a | Operational | Operational | Land between Manchester Ship Canal and M56 | Cheshire | North West | England |  | 348857 | 378461 | DECC (S36) | [6 empty] | 2010-02-25 | [6 empty] | 2012-10-19 |  |  |  |  | 2015-08-06 | 2016-11-15
A0225 | 3695 | 2018-09-04 | RWE Npower Renewables | Brechfa Forest West | Wind Onshore |  |  | 57.4 | n/a |  |  |  | 2.05 | 28 |  | n/a | Operational | Operational | centred around the Afon Pib Valley, east of Alltwalis and the second area around Banc Llywelau, south of Rhydcymerau. | Dyfed | Wales | Wales |  | 254202 | 231259 | The Planning Inspectorate - National Infrastructure | P2011/0085 | [5 empty] | 2011-11-04 | [6 empty] | 2013-03-12 |  |  |  |  | 2016-11-24 | 2018-01-18
A0226 | 3696 | 2012-11-07 | Npower Renewables | Hill of Stroupster | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Aukengill, Highland | Highland | Scotland | Scotland |  | 337895 | 972856 | Highland Council | 07/00244/FUL | [6 empty] | 2012-11-07
A0239 | 3698 | 2015-01-07 | Green Cat Renewables | Greenhill Croft | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Bonnykelly, New Pitsligo, Fraserburgh, Grampian | Grampian | Scotland | Scotland | AB43 6NP | 388080 | 856083 | Aberdeenshire Council | APP/2009/3456 | [5 empty] | 2009-10-21 | [6 empty] | 2010-10-11 |  |  |  |  | 2011-10-01 | 2012-03-01
A0240 | 3699 | 2014-02-27 | Severn Trent Water | Severn Trent STW | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Fillingate, Wanlip, Leicester | Leicestershire | East Midlands | England | LE7 4PF | 459710 | 311517 | Charnwood Borough Council | P/09/2402/2 | APP/X2410/A/10/2134009 |  |  |  |  | 2009-12-21 |  | 2010-04-30 |  |  |  | 2011-03-16 | 2011-03-16 |  |  |  |  | 2013-11-01 | 2014-02-26
A0244 | 3700 | 2016-05-31 | Falck Renewables | Spaldington Airfield | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | Holme Road, Spaldington, East Riding, Yorkshire. DN14 7NB | Humberside | Yorkshire and Humber | England |  | 479158 | 433880 | East Riding of Yorkshire Council | 09/04550/STPLFE | 10/00102/REFUSE |  |  |  |  | 2009-11-18 |  | 2010-09-22 |  |  |  | 2011-09-29 | 2011-09-29 |  |  |  |  | 2013-06-01 | 2016-05-11
A0256 | 3701 | 2015-03-25 | Octopus Investements/Blue Energy (previously Auquhirie Land Company Ltd) | Hillhead of Auquhirie, Resubmission | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Hillhead of Auquhirie, Stonehaven | Grampian | Scotland | Scotland |  | 328500 | 785500 | Aberdeenshire Council | APP/2009/3567 | [5 empty] | 2009-11-04 | [6 empty] | 2011-01-10 |  |  |  |  | 2012-09-01 | 2013-01-16
A0257 | 3702 | 2015-03-25 | Scottish Power Renewables | Middleton Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | East Refrewshire, G77 6 | Strathclyde | Scotland | Scotland |  | 253158 | 656019 | East Renfrewshire Council | 2008/0096/TP | [5 empty] | 2008-02-11 | [6 empty] | 2011-08-16 |  |  |  |  | 2012-05-29 | 2013-09-04
A0264 | 3703 | 2015-03-25 | Renewable Energy Generation | Orchard End (Resubmission) | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | land at Orchard End, near Pilling, Eagland Hill, Preston | Lancashire | North West | England |  | 343216 | 445233 | Wyre Borough Council | 09/00352/FULMAJ | APP/U2370/A/10/2129772 |  |  |  |  | 2009-05-12 |  | 2009-12-02 |  |  |  | 2010-12-16 | 2010-12-16 |  |  |  |  | 2012-08-01 | 2013-06-17
A0267 | 3704 | 2012-12-17 | Ecotricity | Berkeley Vale | Wind Onshore |  |  | 16 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Permission Refused | Application Refused | Standle Farm, Standle Lane, Stinchcombe, Dursley, Gloucestershire, GL11 6BH | Gloucestershire | South West | England |  | 371927 | 199110 | Stroud District Council | S.10/1638/FUL | S.11/041/REF |  |  |  |  | 2010-08-25 |  | 2011-04-12
A0272 | 3705 | 2015-08-24 | Pennant Walters | Mynydd Bwllfa Wind Farm - Resubmission | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2.5 | 9 |  | n/a | Operational | Operational | South of Hirwaun | Mid Glamorgan | Wales | Wales |  | 295787 | 202855 | Rhondda Cynon Taff County Borough Council | 09/0393/10 | A/11/2161275 AP.1030 |  |  |  |  | 2009-05-05 |  | 2011-05-18 |  |  |  | 2012-06-01 | 2012-06-01 |  |  |  |  | 2014-02-01 | 2015-05-08
A0280 | 3706 | 2012-08-22 | Novera Energy | Mynydd Clogau Wind Farm - Extension | Wind Onshore |  |  | 16 | n/a |  |  |  | 0.85 | 19 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Mynydd Clogau, Mynydd Bwrch-y-gors and Mynydd Cerrigllwydion, near Adfa, Newtown, Powys | Powys | Wales | Wales |  | 303300 | 298800 | Powys County Council | P/2008/0450 | [5 empty] | 2008-03-10 | 2012-06-18
A0281 | 3707 | 2018-05-01 | Foresight | Tirgwynt | Wind Onshore |  |  | 24.6 | n/a |  |  |  | 2.05 | 12 |  | n/a | Operational | Operational | Mynydd yr Hendre & Mynydd Pistyll Du Near Carno, Powys | Powys | Wales | Wales |  | 299943 | 302442 | Powys County Council | M/2007/0931 | [5 empty] | 2007-09-24 | [6 empty] | 2010-10-12 |  |  |  |  | 2015-12-24 | 2017-02-15
A0282 | 3708 | 2012-01-24 | Pennant Wind Energy Ventures (PWEV) and Eco2 | Pendragon Fach Wind Farm | Wind Onshore |  |  | 5.2 | n/a |  |  |  | 1.3 | 4 |  | n/a | Appeal Refused | Application Refused | Mynydd James to the east of Blaina and north of Cwmtillery | Gwent | Wales | Wales |  | 321585 | 207912 | Blaenau Gwent County Borough Council | 2006/0380 | [5 empty] | 2006-06-12 |  | 2010-04-01 |  |  | 2010-04-01
A0286 | 3710 | 2012-03-07 | Acciona Energy | Waun Garno | Wind Onshore |  |  | 16.5 | n/a |  |  |  | 1.5 | 11 |  | n/a | Planning Permission Refused | Application Refused | Land at Waun Garno Llawr y Glyn, Trefeglwys, Caersws, Powys | Powys | Wales | Wales |  | 295457 | 293336 | Powys County Council | P/2008/0532 | [5 empty] | 2008-04-09 |  | 2012-03-06
A0287 | 3711 | 2017-10-04 | Renewables Infrastructure Group (TRIG) | Garreg Lwyd | Wind Onshore |  |  | 34 | n/a |  |  |  | 2 | 23 | 136.5 | n/a | Operational | Operational | Garreg Lwyd Hill Between Felindre & Llanbadarn Fynydd, Llandrindod Wells, Powys | Powys | Wales | Wales | LD1 6YF | 312758 | 280228 | Powys County Council | P/2008/0785 | APP/T6850/A/13/2209593 |  |  |  |  | 2008-05-27 |  | 2013-09-05 | 2014-03-04 |  |  | 2015-05-14 | 2015-05-14 |  |  |  |  | 2016-01-11 | 2017-02-22
A0304 | 3712 | 2014-12-05 | Tyrone Wind Energy Ltd | Whisker Hill | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Tullywhisker, Sion Mills, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 45772 | 553840 | Northern Ireland Planning Service | J/2007/0700/F | [5 empty] | 2007-10-29 |  | 2014-11-20
A0308 | 3713 | 2017-08-11 | Gaelectric Developments/ CGN Europe Energy | Crockbrack | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | (north of Loughmarve Road and west of Gortscraheen Road, with access via Loughmallon Road), Limehill, Pomeroy, County Tyrone. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 80213 | 535661 | Northern Ireland Planning Service | I/2008/0157/F | [5 empty] | 2008-02-11 | [6 empty] | 2012-06-19 |  |  |  | 2017-06-19 | 2015-01-15 | 2017-03-20
A0313 | 3714 | 2013-04-05 | Acorn Energy B7 Ltd | Aghamore | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Permission Refused | Application Refused | Site 1070m South West of no.22 Aghamore Road, Castlederg | Co. Tyrone | Northern Ireland | Northern Ireland |  | 34484 | 543356 | Northern Ireland Planning Service | J/2008/0278/F | [5 empty] | 2008-05-01 |  | 2012-10-25
A0318 | 3715 | 2016-02-24 | Mullynaveagh Wind Limited | Mullynaveagh | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Abandoned | Abandoned | Land approximately 550m north west of 23 Tannaghlane Road, Caledon, County Tyrone, BT68 4XU. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 85034 | 508509 | Northern Ireland Planning Service | M/2008/1327/F | [5 empty] | 2008-12-15 | [6 empty] | 2010-12-09 |  |  |  | 2015-12-09
A0319 | 3716 | 2015-01-05 | Lowlands Health & Energy Ltd | Connaught Road | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Operational | Operational | Approx 130m NW of 44 Connaught Road, Randalstown | Co. Antrim | Northern Ireland | Northern Ireland | BT41 2NX | 123057 | 549749 | Northern Ireland Planning Service | T/2008/0358/F | [5 empty] | 2008-06-02 | [6 empty] | 2012-03-01 |  |  |  | 2017-03-01 |  | 2012-10-11
A0321 | 3717 | 2012-12-03 | Northern Wind Power | Crockagarron Ext | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Lands to the East of Whitebridge Road and South of Gleneeny Road, on lands at Crockagarron in the Townland of Gleneeny, Co Tyrone. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 76240 | 528915 | Northern Ireland Planning Service | K/2009/0182/F | [5 empty] | 2009-03-04 | [6 empty] | 2010-12-08 |  |  |  |  | 2012-04-01 | 2012-06-01
A0327 | 3718 | 2015-01-07 | Green Cat Renewables | Castle of Auchry Farm | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Cuminestown, Turriff, Aberdeenshire | Grampian | Scotland | Scotland | AB53 5UR | 373109 | 821437 | Aberdeenshire Council | APP/2010/0067 | [5 empty] | 2010-01-13 | [6 empty] | 2012-08-14 |  |  |  |  | 2013-09-01 | 2013-11-01
A0337 | 3719 | 2014-01-27 | Carbon Free Developments Ltd | Moy Wind Farm | Wind Onshore |  |  | 40 | n/a |  |  |  | 2 | 20 |  | n/a | Abandoned | Abandoned | Tomatin, Invernessshire | Highland | Scotland | Scotland | IV13 7YD | 276947 | 835012 | Highland Council | 11/01205/FUL | PPA-270-2063 |  |  |  |  | 2011-04-05 |  | 2012-02-29 |  |  |  | 2012-02-29 | 2012-02-29
A0342 | 3720 | 2017-12-14 | Stiles Harold Williams Ltd | Queensway South | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Expired | Planning Permission Expired | Marline Fields, Queensway, St Leonards-on-Sea, East Sussex, TN38 8AW | East Sussex | South East | England |  | 578283 | 112153 | Hastings Borough Council | HS/FA/08/00849 | [5 empty] | 2009-01-12 | [6 empty] | 2009-07-06 |  |  |  | 2012-07-06
A0350 | 3721 | 2012-11-19 | TCI Renewables | Upper Vaunces Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Appeal Refused | Application Refused | Land east of Semere Green Road (forming part of Upper Vaunces Farm) | Norfolk | Eastern | England |  | 618623 | 283747 | South Norfolk Council | 2010/0383 | APP/L2630/A/10/2143349/NWF |  |  |  |  | 2010-03-09 |  | 2010-12-20 |  |  | 2012-10-15
A0353 | 3722 | 2014-01-06 | Lovie Ltd | Little Byth | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 1.5 | 3 |  | n/a | Operational | Operational | New Byth, Turriff. AB53 5XR | Grampian | Scotland | Scotland |  | 382764 | 857480 | Aberdeenshire Council | APP/2009/1044 | [5 empty] | 2009-04-08 | [6 empty] | 2009-12-24 | [5 empty] | 2012-12-31
A0355 | 3723 | 2015-01-07 | Green Cat Renewables | Yonderton Farm | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Operational | Operational | Hatton, Peterhead, Aberdeenshire | Grampian | Scotland | Scotland | AB42 0QS | 403588 | 837834 | Aberdeenshire Council | APP/2010/1564 | [5 empty] | 2010-05-14 | [6 empty] | 2010-07-23 |  |  |  |  | 2014-08-01 | 2014-12-01
A0401 | 3725 | 2012-08-06 | Galliford Try Renewables (GTR) | Shepham Lane | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | LAND OFF SHEPHAM LANE, NORTH OF A27, POLEGATE, BN24 5BT | East Sussex | South East | England |  | 560069 | 105580 | Wealden District Council | WD/2011/2137/MEA | [5 empty] | 2011-09-30 | 2012-07-17
A0404 | 3726 | 2014-03-31 | Resonance | Oakdale Business Park | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Blackwood, Gwent | Gwent | Wales | Wales |  | 319119 | 199334 | Caerphilly County Borough Council | 11/0552/FULL | [5 empty] | 2011-07-18 | [6 empty] | 2011-10-06 |  |  |  |  | 2013-08-23 | 2013-12-24
A0412 | 3728 | 2013-01-25 |  | Dearne Head Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Windmill Lane, High Flats, Huddersfield | West Yorkshire | Yorkshire and Humber | England |  | 418876 | 407311 | Kirklees Council | 2010/62/91751/E2 | [5 empty] | 2010-06-11 | 2012-12-18
A0415 | 3729 | 2012-04-02 | Windpower Wales | Llys Dymper | Wind Onshore |  |  | 49.5 | n/a |  |  |  | 2.94 | 17 |  | n/a | Planning Application Withdrawn | Application Withdrawn | on the Hiraethog Moor, to the south of Gwytherin and the west of Llansannan | Clwyd | Wales | Wales |  | 288420 | 358757 | Conwy County Borough Council | 0/37722 | [5 empty] | 2011-03-07 | 2011-09-29
A0417 | 3730 | 2012-05-31 | Stamford Renewables | Laurels Farm - Resubmission | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Appeal Withdrawn | Application Refused | Bungay Road, Barsham | Suffolk | Eastern | England |  | 638664 | 289263 | Waveney District Council | DC/10/0908/FUL | APP/023/2011 |  |  |  |  | 2010-07-08 |  | 2010-10-25 |  | 2012-02-17
A0419 | 3731 | 2012-12-07 | Ecotricity / Next Generation | Silton Wind Farm - Resubmission | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Appeal Refused | Application Refused | land between West Bourton and Whistley Farm, near Silton, North Dorset | Dorset | South West | England |  | 378380 | 129675 | North Dorset District Council | 2/2010/0731/PLNG | [5 empty] | 2010-08-04 |  | 2011-03-01 |  |  | 2012-11-08
A0432 | 3732 | 2014-06-06 |  | Boddington Reservoir | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Upper Boddington, Northamptonshire. NN1 | Northamptonshire | East Midlands | England |  | 449381 | 253123 | Daventry District Council | DA/2011/0150 | [5 empty] | 2011-03-07 | [6 empty] | 2011-12-15 |  |  |  |  | 2013-08-23 | 2014-04-24
A0433 | 3733 | 2013-03-06 | Resonance | HMP Standford Hill | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Standford Hill, Church Road, Eastchurch, Sheerness | Kent | South East | England | ME12 4AA | 598426 | 170070 | Swale Borough Council | SW/10/1567 | [5 empty] | 2010-12-21 | [6 empty] | 2011-11-11 |  |  |  |  | 2012-12-06 | 2013-02-08
A0436 | 3734 | 2018-05-23 | Partnerships for Renewables/AGR | Sharpness Docks | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Dock Lane, Sharpness, Berkley, Gloucestershire | Gloucestershire | South West | England |  | 366743 | 202889 | Stroud District Council | S.11/2448/FUL | [5 empty] | 2011-12-05 | [6 empty] | 2014-05-19 |  |  |  | 2017-05-19 | 2016-11-15 | 2017-01-15
A0443 | 3735 | 2013-12-18 | REG Windpower (previously Cornwall Light and Power) | Sancton Hill - Resubmission | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | nr Market Weighton, Sancton, York, North Yorkshire YO43 4RH | Humberside | Yorkshire and Humber | England |  | 491554 | 439660 | East Riding of Yorkshire Council | 10/02080/STPLFE | [5 empty] | 2010-05-17 | [6 empty] | 2011-02-10 |  |  |  |  | 2011-11-01 | 2012-06-12
A0444 | 3736 | 2013-07-17 | REG Windpower | Denzell Downs | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Abandoned | Abandoned | near St Eval and St Mawgan, Cornwall | Cornwall | South West | England |  | 189020 | 66439 | Cornwall Council | PA11/01429 | [5 empty] | 2011-02-28 | [6 empty] | 2011-10-03
A0445 | 3737 | 2013-08-23 |  | Hallburn Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Appeal Refused | Application Refused | Longtown, Carlisle. CA6 5TW | Cumbria | North West | England |  | 341558 | 568718 | Carlisle City Council | 11/0118 | [5 empty] | 2011-03-15 |  | 2011-08-19 |  |  | 2013-05-22
A0446 | 3738 | 2016-10-24 | Peel Energy | Port of Sheerness Wind Farm (was Lappel Bank) | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2.05 | 4 | 125 | n/a | Operational | Operational | Sheerness Docks, Sheerness, Kent | Kent | South East | England | ME12 1RS | 591061 | 175143 | Swale Borough Council | SW/08/0896 | [5 empty] | 2008-08-26 | [6 empty] | 2009-03-11 |  |  |  |  | 2015-08-06 | 2016-09-20
A0447 | 3739 | 2017-08-01 | REG Power Management (John Laing/Peel Energy) | Stonish Hill Re-submission (Bilsthorpe) | Wind Onshore |  |  | 10.25 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Former Bilsthorpe Colliery Eakring Road Bilsthorpe Nottinghamshire | Nottinghamshire | East Midlands | England |  | 466000 | 362000 | Newark and Sherwood District Council | 07/00856/FULEIA | APP/B3030/A/08/2072487/NWF |  |  |  |  | 2007-06-08 |  | 2008-03-06 |  |  |  | 2009-03-16 | 2009-03-16 |  |  |  |  | 2012-06-25 | 2013-03-31
A0449 | 3740 | 2014-06-06 | Partnerships for Renewables | Wheal Jane Sustainability Wind Farm | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Appeal Refused | Application Refused | Wheal Jane (disused tin mine), Baldhu Truro Cornwall | Cornwall | South West | England | TR3 6ED | 177271 | 42454 | Cornwall Council | PA11/08372 | 13/00160/REF |  |  |  |  | 2011-10-13 |  | 2012-10-16 |  |  | 2014-04-25
A0454 | 3741 | 2013-07-08 | E.ON UK | Stags Holt Extension | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Franks Farm, Stags Holt, Coldham Bank Road, March, Cambridgeshire, PE15 0BS | Cambridgeshire | Eastern | England |  | 544000 | 299000 | Fenland District Council | F/YR07/0602/F | [5 empty] | 2007-06-04 | [6 empty] | 2008-10-07 | [5 empty] | 2010-12-31
A0461 | 3742 | 2013-08-21 | Druim Ba Sustainable Energy | Druim Ba Wind Farm | Wind Onshore |  |  | 69 | n/a |  |  |  | 3 | 23 |  | n/a | Appeal Refused | Application Refused | Kiltarlity, approximately 16 kilometres from Inverness. | Highland | Scotland | Scotland |  | 228919 | 834228 | Scottish Government (S36) | [6 empty] | 2011-03-16 |  | 2011-09-20 |  |  | 2013-07-16
A0479 | 3744 | 2013-04-02 | Nottingham University | Nottingham University - Wind | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Grove Farm, off Thane Road | Nottinghamshire | East Midlands | England |  | 455428 | 336470 | Nottingham City Council | 11/02419/PFUL3 | [5 empty] | 2011-08-12 |  | 2013-02-25
A0528 | 3745 | 2018-09-20 | Garth Wind (North Yell Development Council) | North Yell Wind Farm (Garth Community Wind Farm) | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 0.9 | 5 |  | n/a | Operational | Operational | Garth, near Gurcher, Yell, Shetland Islands. ZE2 9DF | Shetland | Scotland | Scotland |  | 454471 | 1198506 | Shetland Islands Council | PL2009/151 | [5 empty] | 2009-05-27 | [6 empty] | 2011-04-22 |  |  |  |  | 2016-12-20 | 2017-04-03
A0539 | 3746 | 2013-05-10 | Corrimony Energy Ltd & Soirbheas | Glenurquhart and Strathglass Wind Farm project | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Hill Ground At Corrimony Farm, Glenurquhart, Inverness | Highland | Scotland | Scotland |  | 234250 | 824290 | Highland Council | 10/02132/FUL | [5 empty] | 2010-05-12 | [6 empty] | 2010-11-18 |  |  |  |  | 2012-08-01 | 2013-04-19
A0540 | 3747 | 2014-10-31 | Private Developer | Damhead Farm | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Land At Damhead Farm Bowhouse Road Airdrie North Lanarkshire, ML6 8PW | Strathclyde | Scotland | Scotland |  | 279061 | 663992 | North Lanarkshire Council | 07/00809/FUL | [5 empty] | 2007-05-11 | [6 empty] | 2010-01-14 | [5 empty] | 2013-05-17
A0541 | 3748 | 2013-05-03 | Energiekontor UK | Hyndburn Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 2 | 12 |  | n/a | Operational | Operational | Hyndburn Wind Farm on Oswaldtwistle Moor | Lancashire | North West | England |  | 374424 | 424281 | Hyndburn Borough Council | 11/09/0512 | [5 empty] | 2009-12-01 | [6 empty] | 2010-10-17 |  |  |  |  | 2012-04-01 | 2012-10-19
A0542 | 3749 | 2014-03-06 | Ventient (formerly Infinis) | Tedder Hill Wind cluster | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | near Roos, East Riding of Yorkshire | Humberside | Yorkshire and Humber | England |  | 530221 | 430242 | East Riding of Yorkshire Council | 06/03729/STPLF | 09/00029/REFUSE |  |  |  |  | 2006-05-11 |  | 2008-09-12 |  |  |  | 2010-01-28 | 2010-01-28 |  |  |  |  | 2012-10-30 | 2013-08-30
AA002 | 3751 | 2018-08-17 | Private Developer | Evie Wind Energy Project | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Granted | Awaiting Construction | Burgar Hill (southern end), Evie, Orkney | Orkney Islands | Scotland | Scotland |  | 335035 | 1025025 | Orkney Islands Council | 09/045/PPF | [5 empty] | 2009-01-28 | [6 empty] | 2009-10-07
AA008 | 3752 | 2012-04-24 | Scottish Power Renewables | Lynemouth Windfarm (Resubmission) | Wind Onshore |  |  | 26 | n/a |  |  |  | 2 | 13 |  | n/a | Operational | Operational | Land adjacent to Rio Tinto Alcan Smelter, Lynemouth (2km north of Ashington) | Northumberland | North East | England |  | 429400 | 589799 | DECC (S36) | CM/20060984 | [5 empty] | 2006-11-20 |  | 2007-05-11 |  |  |  | 2009-01-08 | 2009-01-08 |  |  |  |  | 2010-07-01 | 2012-04-12
AA009 | 3753 | 2011-11-29 | Npower Renewables | Kirkharle Wind Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 3 | 8 |  | n/a | Planning Permission Refused | Application Refused | Land to north east of Bavington Hill Head Farm, Capheaton and Land to West of Northside Farm, Harle, Northumberland | Northumberland | North East | England |  | 399500 | 580520 | Northumberland County Council | 20081063 | [5 empty] | 2008-11-18 |  | 2010-09-30
AA011 | 3754 | 2013-06-04 | Ventient (formerly Infinis) | Wingates Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | Wingates, Longhorsley, Morpeth, Northampronshire. NE65 8 | Northumberland | North East | England |  | 413034 | 597920 | Northumberland County Council | C/09/00084/CCMEIA | [5 empty] | 2008-12-05 | [6 empty] | 2011-05-04 |  |  |  |  | 2012-08-01 | 2013-03-31
AA042 | 3755 | 2013-05-17 | Infinergy | Vectis wind farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Planning Permission Refused | Application Refused | Vectis wind farm, land south of Wellow/east of Holmfield Avenue west of Stoneovers and off Broad Lane Shalcombe Yarmouth Isle Of Wight PO41 | Isle of Wight | South East | England |  | 438721 | 87123 | Isle of Wight Council | P/00706/11 | [5 empty] | 2011-07-15 |  | 2012-07-23
AA044 | 3756 | 2014-01-24 | Honda / Ecotricity | Honda wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | South Marston, Swindon | Wiltshire | South West | England |  | 418528 | 187782 | Swindon Borough Council | S/10/1073 | [5 empty] | 2010-07-13 |  | 2011-10-19
AA046 | 3757 | 2013-06-04 | Private Developer | Wathegar wind farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Land At Wathegar Bilbster, Wick, Caithness | Highland | Scotland | Scotland |  | 328540 | 950761 | Highland Council | 10/00042/FULCA | [5 empty] | 2010-02-09 | [6 empty] | 2010-05-21 |  |  |  |  | 2012-06-01 | 2013-03-31
AA047 | 3758 | 2013-02-26 | Ormsary and Stronachullin Estates (Allt Dearg Wind Farmers LLP) | Allt Dearg Wind Farmers LLP | Wind Onshore |  |  | 10.8 | n/a |  |  |  | 0.9 | 12 |  | n/a | Operational | Operational | Cruach a'Phubuill, 9km south of Ardishaig, South Knapdale, Argyll | Strathclyde | Scotland | Scotland |  | 182893 | 676616 | Argyll and Bute Council | 10/02151/PP | [5 empty] | 2011-01-17 | [6 empty] | 2011-04-05 |  |  |  |  | 2011-12-01 | 2012-09-25
AA050 | 3761 | 2013-08-16 | RWE NPower Renewables | Hameldon Hill extension | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Hameldon Hill, Accrington Road, Burnley, Lancashire | Lancashire | North West | England | BB11 5QQ | 379914 | 430561 | Burnley Borough Council | APP/2009/0756 | [5 empty] | 2009-12-30 | [6 empty] | 2010-12-17 |  |  |  |  | 2013-04-17 | 2013-04-25
AA063 | 3762 | 2014-01-21 | Novera Energy | Hill of Fishrie | Wind Onshore |  |  | 11.3 | n/a |  |  |  | 2.3 | 5 |  | n/a | Planning Permission Refused | Application Refused | Bracklamore, Aberdeenshire, Grampian | Grampian | Scotland | Scotland | AB43 | 382373 | 858231 | Aberdeenshire Council | APP/2011/2249 | [5 empty] | 2011-07-13 |  | 2013-11-29
AA070 | 3763 | 2012-10-19 | Community Windpower | Rullie Community Windfarm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | N/West Of Burnhouse Farm, Denny, Central, FK6 6QY | Falkirk | Scotland | Scotland |  | 277921 | 685092 | Falkirk Council | P/11/0800/FUL | [5 empty] | 2011-12-16 | 2012-09-28
AA074 | 3764 | 2016-05-20 | Ecotricity | Dalby | Wind Onshore |  |  | 7.2 | n/a |  |  |  | 0.8 | 9 | 76.5 | n/a | Operational | Operational | Paddys Lane, Old Dalby, Melton Mowbray, Leicestershire | Leicestershire | East Midlands | England | LE14 3LY | 465199 | 323653 | Melton Borough Council | 10/00333/FUL | [5 empty] | 2010-05-19 | [6 empty] | 2010-12-17 |  |  |  |  | 2015-02-01 | 2016-03-15
AA076 | 3765 | 2014-12-18 | EDF/China General Nuclear Power Corporation | Glass moor Extension | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | S/E Of Yewtree Farm, Glassmoor Bank, Whittlesey, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB23 | 528421 | 292867 | Fenland District Council | F/YR11/0094/F | [5 empty] | 2011-01-31 | [6 empty] | 2012-04-10 |  |  |  |  | 2012-09-01 | 2013-03-31
AA085 | 3766 | 2013-01-18 | Falck Renewables | Moorhouse (Eaglesham) | Wind Onshore |  |  | 47.5 | n/a |  |  |  | 2.5 | 19 |  | n/a | Appeal Refused | Application Refused | Muirshield Road, Eaglesham, Glasgow, Strathclyde, G76 | Strathclyde | Scotland | Scotland |  | 254372 | 653147 | East Renfrewshire Council | 2010/0241/TP | APPEAL 0503 |  |  |  |  | 2010-04-16 |  | 2012-04-24 |  |  | 2012-12-17
AA090 | 3767 | 2020-01-16 | FCC Environment | Gallymoor Landfill Site | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Planning Permission Granted | Awaiting Construction | Gallymoor landfill site, Holme on Spalding Moor, East Riding | Humberside | Yorkshire and Humber | England | YO43 4LY | 484205 | 440042 | East Riding of Yorkshire Council | 11/00537/STPLF | [5 empty] | 2011-02-11 | [6 empty] | 2012-07-10
AA095 | 3769 | 2012-11-20 | Partnerships for Renewables | Forthbank | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | south east of Alloa | Clackmannanshire | Scotland | Scotland |  | 289572 | 690869 | Clackmannanshire Council | 10/00288/FULL | [5 empty] | 2010-11-17 |  | 2012-10-09
AA105 | 3770 | 2014-02-20 | Broadview Energy | Bicton Wind Farm | Wind Onshore |  |  | 23 | n/a |  |  |  | 5.75 | 4 |  | n/a | Appeal Refused | Application Refused | between Stow Longa and Kimbolton. | Cambridgeshire | Eastern | England |  | 510060 | 270129 | Huntingdonshire District Council | 1001201FUL | 1100004REFUSL |  |  |  |  | 2010-07-10 |  | 2011-01-20 |  |  | 2012-03-13
AA108 | 3771 | 2014-01-31 | Npower Renewables | Nun Wood (Milton Keynes) | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Appeal Refused | Application Refused | Land Between London Road And Harrold Road | Bedfordshire | Eastern | England |  | 492103 | 258283 | Milton Keynes Council | 08/02118/FULEIS | 11/00011/NONDET |  |  |  |  | 2009-01-23 |  | 2009-05-15 |  |  | 2013-12-17
AA121 | 3772 | 2018-04-03 | Octopus Investments/Blue Energy | Cour Wind Farm | Wind Onshore |  |  | 20.5 | n/a |  |  |  | 2.1 | 10 |  | n/a | Operational | Operational | Carradale Argyll And Bute | Strathclyde | Scotland | Scotland |  | 181005 | 648528 | Argyll and Bute Council | 10/00909/PP | [5 empty] | 2010-05-21 | [6 empty] | 2012-10-17 |  |  |  |  | 2015-11-19 | 2016-12-01
AA124 | 3773 | 2014-01-31 | Npower Renewables | Nun Wood (Bedford) | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Appeal Refused | Application Refused | Land West Of New Road (Nun Wood) Harrold Bedfordshire | Bedfordshire | Eastern | England |  | 493895 | 257158 | Bedford Borough Council | 09/00137/MAF | K0235/A/11/2149434 |  |  |  |  | 2009-01-29 |  | 2011-02-15 |  |  | 2013-12-17
AA125 | 3774 | 2014-01-31 | Npower Renewables | Nun Wood (Wellingborough) | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Appeal Refused | Application Refused | Harrold Road Bozeat Wellingborough Northamptonshire NN29 7LP | Northamptonshire | East Midlands | England |  | 491484 | 258740 | Wellingborough Borough Council | WP/2008/0603 | K0235/A/11/2149434 |  |  |  |  | 2008-12-31 |  | 2011-11-15 |  |  | 2013-12-17
AA130 | 3775 | 2014-11-25 | Prowind Cottam Windfarm | Cottam Wind Farm | Wind Onshore |  |  | 27.6 | n/a |  |  |  | 2.3 | 12 |  | n/a | Appeal Refused | Application Refused | Headstead Bank, Cottam, Retford, Notts | Nottinghamshire | East Midlands | England |  | 479861 | 379960 | Bassetlaw District Council | 12/09/00001 | APP/A3010/A/11/2146094 |  |  |  |  | 2009-03-03 |  | 2010-07-29 | 2011-03-24 |  | 2011-10-24
AA132 | 3776 | 2018-11-19 | J & A Wilson Ltd | Upper Wheedlemont Farm | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Operational | Operational | Rhynie Huntly | Grampian | Scotland | Scotland | AB54 4LL | 347391 | 826203 | Aberdeenshire Council | APP/2009/3583 | [5 empty] | 2009-11-04 | [6 empty] | 2012-10-04 |  |  |  |  | 2017-07-24 | 2017-11-11
AA139 | 3777 | 2014-05-29 | EDF Energy | Beck Burn | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Appeal Refused | Application Refused | between Gretna and west of Longtown. | Cumbria | North West | England |  | 334570 | 569072 | Carlisle City Council | 10/1102 | [5 empty] | 2010-12-13 |  | 2011-12-16 |  |  | 2013-05-22
AA141 | 3778 | 2013-11-06 | Lomond Energy | Merkins Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Planning Permission Refused | Application Refused | Auchincarroch Road Jamestown Alexandria West Dunbartonshire | Strathclyde | Scotland | Scotland |  | 242392 | 680091 | West Dunbartonshire Council | DC12/028 | [5 empty] | 2012-01-30 |  | 2013-10-23
AA150 | 3779 | 2013-04-05 | Totnes Renewable Energy Society | Totnes Community Wind Farm | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | East of A381, South of Langridge Cross, Harberton, Totnes | Devon | South West | England |  | 278764 | 58138 | South Hams District Council | 23/1990/12/F | [5 empty] | 2012-08-14 |  | 2013-02-14
AA155 | 3780 | 2012-10-10 | Wind Prospect | Foxton Lane | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Sedgefield, Co Durham | Durham | North East | England |  | 436006 | 525698 | Durham County Council | 7/2010/0236/DM | [5 empty] | 2010-07-14 |  | 2012-10-10
AA167 | 3782 | 2013-02-07 | Banks Development | Losk Lane | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Glapwell Lane, Palterton, Chesterfield, Derbyshire | Derbyshire | East Midlands | England |  | 447598 | 367841 | Bolsover District Council | 10/00463/FULEA | [5 empty] | 2010-10-01 |  | 2013-02-01
AA168 | 3783 | 2013-01-02 | Renewable Energy Systems (RES) | Forss Extension (Forss III) | Wind Onshore |  |  | 6.5 | n/a |  |  |  | 1.3 | 5 |  | n/a | Appeal Refused | Application Refused | Thurso, Caithness | Highland | Scotland | Scotland |  | 302174 | 969703 | Highland Council | 10/04434/FUL | 12/00002/RBREF |  |  |  |  | 2010-10-28 |  | 2011-10-19 |  |  | 2012-07-19
AA172 | 3784 | 2013-05-22 | Green Cat Renewables | Shielburn Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Newton Of Fortrie, Fortrie Turriff AB53 4HL | Grampian | Scotland | Scotland |  | 367618 | 845637 | Aberdeenshire Council | APP/2009/4072 | [5 empty] | 2009-12-17 | [6 empty] | 2012-10-24 | [5 empty] | 2013-03-30
AA175 | 3785 | 2013-10-25 | Wind Ventures | Treading Wind Farm - Fenland | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Appeal Refused | Application Refused | Between Gorefield, Cambs and Sutton St Edmund, Lincs | Cambridgeshire | Eastern | England |  | 538519 | 312747 | Fenland District Council | F/YR11/0113/F | [5 empty] | 2011-01-21 |  | 2012-07-03 |  |  | 2013-10-09
AA180 | 3786 | 2013-06-17 | Wind Ventures | Harbour Cross Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | to the north-east of Meddon, Torridge | Devon | South West | England |  | 228520 | 118885 | Torridge District Council | 1/0506/2012/FULM | [5 empty] | 2012-06-15 | 2013-04-26
AA182 | 3787 | 2017-07-31 | Octopus Investments/Blue Energy | Beinneun | Wind Onshore |  |  | 85 | n/a |  |  |  | 3.4 | 25 |  | n/a | Operational | Operational | 8km west of Invergarry | Highland | Scotland | Scotland |  | 220442 | 804419 | Scottish Government (S36) | [6 empty] | 2011-11-04 | [6 empty] | 2012-11-04 |  |  |  |  | 2015-07-15 | 2017-02-16
AA195 | 3788 | 2012-11-28 | Scottish and Southern Energy (SSE) | Birniehill | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 1.5 | 3 |  | n/a | Planning Permission Refused | Application Refused | near Hareshaw, North Lanarkshire | Strathclyde | Scotland | Scotland |  | 282010 | 660419 | North Lanarkshire Council | 07/01341/FUL | [5 empty] | 2007-07-19 |  | 2012-10-09
AA201 | 3789 | 2018-08-24 | Orkney Sustainable Energy | Akla | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Planning Permission Expired | Planning Permission Expired | Orphir, Orkney | Orkney Islands | Scotland | Scotland |  | 334769 | 1007788 | Orkney Islands Council | 10/631/PP | [5 empty] | 2010-12-08 | [6 empty] | 2012-12-17 |  |  |  | 2015-12-17
AA213 | 3790 | 2016-05-31 | Renewable Energy Systems (RES) | Bryn Llywelyn | Wind Onshore |  |  | 48.3 | n/a |  |  |  | 2.3 | 21 |  | n/a | Appeal Lodged | Application Refused | Llanllwni, Carmarthenshire, SA39 9ED | Carmarthenshire | Wales | Wales |  | 251901 | 236695 | Carmarthenshire County Council | E/23947 | APP/M6825/A/16/3149642 |  |  |  |  | 2010-12-14 |  | 2012-12-18 | 2016-04-29
AA214 | 3791 | 2012-11-29 | Infinis, previously Broadview Energy | Seamer Wind Farm - Hambleton | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Land Adjacent Hilton Road, Seamer, Middlesbrough | Cleveland | Yorkshire and Humber | England |  | 447872 | 511421 | Hambleton District Council | 09/00859/FUL | APP/G2713/A/09/2114490 |  |  |  |  | 2009-03-27 |  | 2009-09-18 | [9 empty] | 2011-10-01 | 2012-11-01
AA216 | 3792 | 2016-02-16 | Blue Energy | Fanny House Farm/Heysham Moss | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 110 | n/a | Operational | Operational | Oxcliffe Road, Heaton With Oxcliffe, Morecambe, Lancashire | Lancashire | North West | England | LA3 3EF | 342996 | 460568 | Lancaster City Council | 11/00073/FUL | [5 empty] | 2011-01-27 | [6 empty] | 2012-10-16 |  |  |  |  | 2014-01-01 | 2015-02-01
AA218 | 3793 | 2014-04-10 | Severn Trent Water | Newthorpe Wind Turbine | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Sewage Treatment Works, Halls Lane, Giltbrook, Nottinghamshire | Nottinghamshire | East Midlands | England | NG16 2DE | 447216 | 344836 | Broxtowe Borough Council | 10/00717/FUL | [5 empty] | 2010-12-03 | [6 empty] | 2011-07-15 |  |  |  |  | 2013-04-23 | 2014-04-08
AA223 | 3794 | 2015-12-02 | FCC Environment | Lillyhall Wind Farm | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Secretary of State - Refusal | Application Refused | Lillyhall Landfill Site, Cumbria | Cumbria | North West | England |  | 302697 | 524950 | Allerdale Borough Council | 02/2012/9011 | APP/H0900/A/14/2224323 |  |  |  |  | 2012-10-30 |  | 2014-02-28 | 2015-04-14 | [5 empty] | 2015-11-03
AA224 | 3795 | 2014-05-06 | Chelveston Renewable Energy Ltd | Chelveston Renewable Energy Park Wind Farm (Bedford) | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Operational | Operational | Chelveston Airfield, East Northamptonshore | Northamptonshire | East Midlands | England |  | 499823 | 268732 | Bedford Borough Council | 10/00484/MAF | 11/00037/REF |  |  |  |  | 2010-03-24 |  | 2011-03-29 |  |  |  | 2012-06-29 | 2012-06-29 |  |  |  |  | 2013-08-01 | 2014-02-15
AA235 | 3796 | 2013-10-08 | Wind Ventures | Treading Wind Farm - South Holland | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Sutton St Edmund, Spalding, Lincs | Cambridgeshire | Eastern | England |  | 539094 | 312521 | South Holland District Council | H19-0081-11 | [5 empty] | 2011-02-08 |  | 2012-09-19
AA249 | 3797 | 2013-09-13 | Ridgewind | Gilston Wind Farm (Lothian) | Wind Onshore |  |  | 18.45 | n/a |  |  |  | 2.05 | 9 |  | n/a | Appeal Refused | Application Refused | south of the village of Fala and just to the west of the existing Dun Law wind farm | Lothian | Scotland | Scotland |  | 344033 | 659490 | Midlothian Council |  | 13/00003/APREF |  |  |  |  | 2011-12-21 |  | 2012-12-12 |  |  | 2013-08-29
AA267 | 3799 | 2014-03-18 | Future Spectrum Ltd | Torrance Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Operational | Operational | Blairmuckhill Road, Harthill, North Lanarkshire | Strathclyde | Scotland | Scotland | EH48 3AW | 290842 | 665671 | North Lanarkshire Council | 10/00973/FUL | [5 empty] | 2010-08-30 | [6 empty] | 2011-02-24 |  |  |  |  | 2013-02-04 | 2013-12-30
AA269 | 3800 | 2012-12-07 | Community Windpower | Claughton Moor (Re-Submission) | Wind Onshore |  |  | 39 | n/a |  |  |  | 3 | 13 |  | n/a | Appeal Withdrawn | Application Refused | Farleton, Old Road, Claughton | Lancashire | North West | England |  | 357730 | 465992 | Lancaster City Council | 10/01151/FUL | 11/00013/8WEEK |  |  |  |  | 2010-11-09 |  | 2011-06-20 |  | 2011-09-14
AA335 | 3801 | 2012-11-28 | Parsons Brinckerhoff | Newbiggin Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Darlington Back Lane, Whinney Hill, Stockton-on-Tees | Durham | North East | England |  | 436512 | 519274 | Darlington Borough Council | 11/00128/FUL | [5 empty] | 2011-02-28 |  | 2012-10-30
AA339 | 3802 | 2013-12-09 | Greenside Wind Energy Ltd | Land at Overside and Greenwellheads Farms | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Crimond, Fraserburgh, AB42 3HJ | Grampian | Scotland | Scotland |  | 406123 | 854692 | Aberdeenshire Council | APP/2011/1024 | [5 empty] | 2011-03-30 | [6 empty] | 2011-09-13 | [5 empty] | 2013-11-01
AA345 | 3803 | 2013-04-19 | Lancaster University | Lancaster University (wind) | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Bailrigg Lane, Lancaster, Lancashire | Lancashire | North West | England |  | 349007 | 457081 | Lancaster City Council | 10/01061/FUL | [5 empty] | 2010-10-13 | [6 empty] | 2011-08-11 |  |  |  |  | 2012-01-01 | 2013-02-18
AA348 | 3804 | 2013-09-19 | Seren Energy | Myreton Crossroads | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Operational | Operational | Keith Moray AB55 6NJ | Grampian | Scotland | Scotland |  | 349741 | 856864 | Moray Council | 09/00247/FUL | 10/00005/REF |  |  |  |  | 2009-02-09 |  | 2009-12-10 |  |  |  | 2010-07-19 | 2010-07-19 |  |  |  |  | 2012-03-01 | 2013-07-05
AA350 | 3805 | 2012-08-17 | GEM Electric | Hillhead of Bonnykelly | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | New Pitsligo, Fraserburgh | Grampian | Scotland | Scotland | AB43 6PN | 385037 | 854223 | Aberdeenshire Council | APP/2010/4039 | [5 empty] | 2010-12-22 |  | 2012-06-28
AA383 | 3806 | 2015-01-07 | Green Cat Renewables | Auchinderran Wind Farm | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 | 80 | n/a | Operational | Operational | Auchinderran Farm, Aberchirder, Aberdeenshire | Grampian | Scotland | Scotland |  | 361419 | 854774 | Aberdeenshire Council | APP/2010/3417 | [5 empty] | 2010-11-11 | [6 empty] | 2012-11-08 |  |  |  |  | 2014-08-01 | 2014-12-01
AA389 | 3807 | 2018-07-03 | Broadview Energy | The Limes Wind Turbines | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Operational | Operational | to the west of Staithes Road at Salt End, Hull. | Humberside | Yorkshire and Humber | England |  | 516489 | 429822 | East Riding of Yorkshire Council | 11/01980/STPLFE | [5 empty] | 2011-05-09 | [6 empty] | 2012-11-19 |  |  |  |  | 2014-05-12 | 2015-01-15
AA390 | 3808 | 2013-10-22 | RWE Npower Renewables | Wainfleet Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Wainfleet St Mary Fen, near Wainfleet Bank, | Lincolnshire | East Midlands | England |  | 545510 | 357600 | East Lindsey District Council | S/195/02532/10 | [5 empty] | 2011-05-20 | 2013-01-21
AA391 | 3809 | 2016-04-28 | LocoGen | Milton of Fisherie Wind Cluster | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | King Edward, Banff AB45 3PX | Grampian | Scotland | Scotland |  | 375067 | 859014 | Aberdeenshire Council | APP/2011/1659 | [5 empty] | 2011-05-25 | [6 empty] | 2012-11-02 |  |  |  |  | 2015-04-01 | 2016-02-01
AA407 | 3810 | 2014-02-25 | Blantyre Muir Wind Energy Ltd | Blantyre Muir Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Operational | Operational | Near Laigh Muirhouses Farm Muttonhole Road Hamilton | Strathclyde | Scotland | Scotland |  | 268888 | 651781 | South Lanarkshire Council | HM/07/0563 | [5 empty] | 2007-08-16 | [6 empty] | 2009-11-03 | [5 empty] | 2013-12-30
AA419 | 3811 | 2013-09-06 | E.ON Climate & Renewables | Corsbie Moor Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Appeal Refused | Application Refused | Corsbie Moor Wind Farm | Borders | Scotland | Scotland |  | 358800 | 644725 | Scottish Borders Council | 11/00888/FUL | 12/00046/REF |  |  |  |  | 2011-06-29 |  | 2012-09-03 |  |  | 2013-08-28
AA420 | 3812 | 2013-01-25 | Mackies Limited | Hill of Easterton Extension 2 | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Hill of Easterton, 1km North Of Mackies Ice Cream Dairy, Westertown, Rothienorman, Inverurie, AB51 8US | Grampian | Scotland | Scotland |  | 375650 | 831396 | Aberdeenshire Council | APP/2011/2120 | [5 empty] | 2011-06-15 |  | 2012-12-24
AA425 | 3813 | 2018-07-19 | EDF Energy Renewables | Sheraton Wind Farm (Hartlepool) | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Abandoned | Abandoned |  | Cleveland | North East | England |  | 445133 | 534979 | Hartlepool Borough Council | H/2011/0674 | [5 empty] | 2012-01-24
AA428 | 3814 | 2015-04-22 | Cetis | Lilbourne Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Lilbourne Fields Farm & Lilbourne Lodge Farm, Yelvertoft Road, Lilbourne, Northamptonshire | Northamptonshire | East Midlands | England | CV23 0SZ | 456786 | 277685 | Daventry District Council | DA/2009/0731 | APP/Y2810/A/11/2164759 |  |  |  |  | 2009-10-15 |  | 2011-10-12 |  |  |  | 2012-07-06 | 2012-07-06 |  |  |  |  | 2014-02-18 | 2014-12-15
AA434 | 3815 | 2012-08-31 | Aeolian Stallingborough Ltd | Stallingborough Wind farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | land off North Moss Lane, Stallingborough, North East Lincolnshire. | Humberside | Yorkshire and Humber | England |  | 521426 | 413366 | North East Lincolnshire Council | DC/827/08/IMM | [5 empty] | 2008-07-23 | 2012-08-13
AA444 | 3816 | 2013-10-25 | Atmos Consulting Ltd | Kingdom of Fife Community Wind Park | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Planning Permission Refused | Application Refused | Land To North Of Halbeath Roundabout, Fife | Fife | Scotland | Scotland |  | 313183 | 689409 | Fife Council | 11/03990/EIA | [5 empty] | 2011-07-25 |  | 2013-10-01
AA446 | 3817 | 2016-11-15 | Private Developer | Harap Road | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | S/o Harap Road, Garmondsway, Ferryhill, County Durham | Durham | North East | England |  | 435759 | 533135 | Durham County Council | 7/2011/0293/DM | [5 empty] | 2011-08-05 |  | 2016-07-26
AA449 | 3818 | 2014-03-20 | Eneco | Tullo Wind Farm North Extension (Shiels Wind Farm) | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Laurencekirk | Grampian | Scotland | Scotland | AB30 1NB | 375080 | 772580 | Aberdeenshire Council | APP/2011/2389 | [5 empty] | 2011-07-28 | [6 empty] | 2012-02-29 |  |  |  |  | 2013-04-30 | 2014-04-01
AA456 | 3819 | 2016-08-16 | Melrose Farms | Easter Melrose Wind Energy Project | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Operational | Operational | Gamrie, Banff | Grampian | Scotland | Scotland |  | 375187 | 863494 | Aberdeenshire Council | APP/2011/2473 | [5 empty] | 2011-08-02 | [6 empty] | 2012-11-28 |  |  |  |  | 2015-05-15 | 2015-12-01
AA459 | 3820 | 2013-07-04 | Private Developer | Kirkibost Wind Farm | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Planning Permission Refused | Application Refused | Bernera, Isle of Lewis | Western Isles | Scotland | Scotland |  | 118264 | 934800 | Comhairle nan Eilean Siar Council | 11/00380/PPD | [5 empty] | 2011-08-08 |  | 2013-01-28
AA468 | 3821 | 2016-11-18 | Infinergy | Burton Wold Wind Farm Extension (Southern) | Wind Onshore |  |  | 8.55 | n/a |  |  |  | 2.8 | 3 | 136.5 | n/a | Abandoned | Abandoned | Glendon Farm (land at), Near Burton Latimer, | Northamptonshire | East Midlands | England |  | 492034 | 273320 | Kettering Borough Council | KET/2011/0506 | [5 empty] | 2011-08-24 | [6 empty] | 2012-04-02
AA475 | 3822 | 2013-07-03 | Green Cat Renewables | Ardlebank Farm Wind Cluster | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Permission Refused | Application Refused | Ballintuim, Blairgowrie | Tayside | Scotland | Scotland | PH10 7NQ | 311269 | 755467 | Perth and Kinross Council | 11/01485/FLL | [5 empty] | 2011-09-05 |  | 2013-06-04
AA478 | 3823 | 2014-06-06 | Wind Prospect Developments | Thornholme Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Appeal Refused | Application Refused | Thornholme Fields, Rudston Road, Burton Agnes, East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 510942 | 465046 | East Riding of Yorkshire Council | 11/03999/STPLFE | 13/00002/REFUSE |  |  |  |  | 2011-09-07 |  | 2012-12-19 |  |  | 2014-05-21
AA480 | 3824 | 2013-08-23 | Wind Prospect Developments | Strensham Wind Cluster (resubmission) | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Brockeridge Common, Brockeridge, Twyning, Tewkesbury, Gloucestershire | Gloucestershire | South West | England |  | 389705 | 238516 | Tewkesbury Borough Council | 09/01189/FUL | [5 empty] | 2011-04-04 | 2013-02-05
AA496 | 3825 | 2014-03-03 | Barnwell Manor Wind Energy Ltd | Barnwell Manor Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Appeal Refused | Application Refused | Area North Of Catshead Woods, Brigstock Road, Sudborough, Northamptonshire | Northamptonshire | East Midlands | England |  | 496672 | 283688 | East Northamptonshire Council | 10/00068/FUL | 11/00011/REF |  |  |  |  | 2010-02-09 |  | 2011-01-24 |  |  | 2014-02-18
AA514 | 3826 | 2015-06-16 | A & P Tyne Hebburn | A&P Tyne | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Expired | Planning Permission Expired | Hebburn, Wagonway Road, Hebburn, South Tyneside | Tyne and Wear | North East | England | NE31 1TP | 430963 | 565671 | South Tyneside Metropolitan Borough Council | ST/0186/08/FUL | [5 empty] | 2008-02-05 | [6 empty] | 2009-04-06 |  |  |  | 2012-04-06
AA515 | 3827 | 2014-04-30 | TCI Renewables | Newton Marsh Wind Project | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Newton Marsh Sewage Treatment Works, Tetney, North-East Lincolnshire | Lincolnshire | East Midlands | England |  | 533327 | 403278 | East Lindsey District Council | N/178/03348/07 | APP/D2510/A/08/2090543 |  |  |  |  | 2008-01-29 |  | 2008-05-20 |  |  |  | 2009-05-28 | 2009-05-28 |  |  |  |  | 2012-06-25 | 2014-04-30
AA516 | 3828 | 2015-03-02 | Bernard Matthews Green Energy | North Pickenham Airfield | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | North Pickenham Road, Breckland | Norfolk | Eastern | England |  | 585114 | 306597 | Breckland Council | 3PL/2009/0881/F | [5 empty] | 2009-09-22 | [6 empty] | 2010-09-24 | [5 empty] | 2014-04-01
AA529 | 3830 | 2013-09-20 | Tegni Cymru | Bedlinog Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | LAND AT BEDLINOG FARM, BEDLINOG CF46 6SN | Mid Glamorgan | Wales | Wales |  | 310232 | 202385 | Rhondda Cynon Taff County Borough Council | 11/1150/03 | [5 empty] | 2011-09-22 | 2013-09-11
AA552 | 3831 | 2014-06-06 | Gamesa Energy | Watford Gap Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | south of Watford, and north-west of the village of Long Buckby, and to the east of the M1 motorway | Northamptonshire | East Midlands | England |  | 460304 | 267730 | Daventry District Council | DA/2011/0850 | [5 empty] | 2011-10-13 |  | 2014-04-23
AA561 | 3832 | 2015-06-16 | Airvolution Energy | Wythegill Wind Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Land at Wythegill Syke, Seaton, Workington, Cumbria | Cumbria | North West | England | CA15 8RX | 301881 | 532072 | Allerdale Borough Council | 2/2011/0259 | [5 empty] | 2011-04-14 |  | 2011-12-15 |  |  |  | 2012-10-11 | 2012-10-11 |  |  |  |  | 2015-03-15 | 2015-06-15
AA574 | 3833 | 2013-08-19 | Vento Ludens | Brown Muir Wind Farm | Wind Onshore |  |  | 57 | n/a |  |  |  | 3 | 19 |  | n/a | Planning Application Withdrawn | Application Withdrawn | within Moray, 5km north-west of Rothes and to the east of the A941 | Grampian | Scotland | Scotland |  | 327075 | 854781 | Scottish Government (S36) | [6 empty] | 2012-06-20 | 2013-08-15
AA577 | 3834 | 2013-02-06 | Npower Renewables | Fforch Nest Wind Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 2.6 | 6 |  | n/a | Abandoned | Abandoned | land north of glynogwr, Blackmill, Bridgend | Mid Glamorgan | Wales | Wales |  | 296600 | 191300 | Rhondda Cynon Taff County Borough Council | 06/1688/03 | [5 empty] | 2006-08-23 | [6 empty] | 2009-08-25
AA580 | 3835 | 2013-06-04 | Renewable Energy Systems (RES) | Roos Wind Farm (Resubmission) | Wind Onshore |  |  | 17.1 | n/a |  |  |  | 1.9 | 9 |  | n/a | Operational | Operational | Land To The West Of Ivy House Rectory Road Roos East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 527376 | 430105 | East Riding of Yorkshire Council | 08/05692/STPLFE | 09/00134/REFUSE |  |  |  |  | 2009-01-20 |  | 2009-08-11 |  |  |  | 2010-05-13 | 2010-05-13 |  |  |  |  | 2012-03-01 | 2013-04-02
AA593 | 3836 | 2015-05-22 | Private Developer | Yonderton Wind Cluster | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Backhill Of Yonderton Craigston Turriff AB53 5PT | Grampian | Scotland | Scotland |  | 375188 | 855296 | Aberdeenshire Council | APP/2010/3054 | [5 empty] | 2010-11-09 | [6 empty] | 2012-11-02 |  |  |  |  | 2014-04-01 | 2014-10-15
AA601 | 3837 | 2013-02-25 | Scottish and Southern Energy (SSE) | Spurness Wind Farm Repowering | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Spurness, Sanday | Orkney Islands | Scotland | Scotland |  | 360531 | 1033828 | Orkney Islands Council | 11/102/TPP | [5 empty] | 2011-03-04 | [6 empty] | 2011-07-21 |  |  |  |  | 2012-02-01 | 2012-12-01
AA623 | 3838 | 2014-12-05 | Auchmacoy Estate | Auchmacoy Estate Wind Cluster | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Site North of Mill of Kinmuck Auchmacoy Estate Auchmacoy Ellon AB41 8RB | Grampian | Scotland | Scotland |  | 399183 | 830796 | Aberdeenshire Council | APP/2011/3710 | [5 empty] | 2011-11-29 | 2014-11-11
AA626 | 3839 | 2014-03-18 | Burnhead Wind Farm Ltd | Burnhead Wind Farm (Resubmission) | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Appeal Refused | Application Refused | Chalmerston, Dalmellington | Strathclyde | Scotland | Scotland |  | 246456 | 608729 | East Ayrshire Council | 11/0868/PP | 13/0015/REF |  |  |  |  | 2011-11-01 |  | 2013-01-18 |  |  | 2013-10-10
AA634 | 3840 | 2015-03-05 | Green Cat Renewables | St Johns Wells Wind Cluster Extension | Wind Onshore |  |  | 3.2 | n/a |  |  |  | 0.8 | 4 |  | n/a | Operational | Operational | St Johns Wells, Fyvie, Turriff AB53 8PX | Grampian | Scotland | Scotland |  | 379960 | 836480 | Aberdeenshire Council | APP/2009/4121 | [5 empty] | 2010-01-11 | [6 empty] | 2012-06-22 |  |  |  |  | 2013-10-30 | 2015-03-01
AA639 | 3841 | 2013-10-03 | Glaxosmithkline | GlaxoSmithKline Wind Project | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Shewalton Road Riverside Business Park Irvine Ayrshire KA11 5AP | Strathclyde | Scotland | Scotland |  | 234144 | 636959 | North Ayrshire Council | 09/00878/PP | [5 empty] | 2010-01-06 | [6 empty] | 2012-05-01 | [5 empty] | 2013-06-30
AA642 | 3842 | 2014-02-26 | KL Technology Limited | K L Technologies Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | K L Technology Ltd Estuary Road King's Lynn Norfolk PE30 2HS | Norfolk | Eastern | England |  | 561043 | 321955 | King's Lynn and West Norfolk Borough Council | 11/02164/F | [5 empty] | 2011-12-22 | [6 empty] | 2012-09-05 | [5 empty] | 2013-10-30
AA669 | 3844 | 2013-10-08 | Lingo Wind Energy Ltd | Lingo Wind Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | Lingo Farm, Lingo, Fife | Fife | Scotland | Scotland |  | 351189 | 709127 | Fife Council | 12/00129/EIA | PPA-250-2153 |  |  |  |  | 2012-01-23 |  | 2013-01-31 |  |  | 2013-10-04
AA670 | 3845 | 2017-07-14 | RM Brown & Son Ltd | Skeddoway Farm Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Strathore Road, Thornton, Fife | Fife | Scotland | Scotland |  | 328104 | 697699 | Fife Council | 11/04896/FULL | [5 empty] | 2011-09-28 | [6 empty] | 2013-02-01 |  |  |  |  | 2014-09-01 | 2014-12-01
AA689 | 3846 | 2020-03-23 | RockbySea | Coire Na Cloiche Wind Farm | Wind Onshore |  |  | 29.9 | n/a |  |  | 30 | 2.3 | 13 |  | n/a | Operational | Operational | Land At Sidhean A'Choin Bhain, Strathrusdale, Alness | Highland | Scotland | Scotland | IV17 0YQ | 258937 | 878023 | Highland Council | 12/00479/FUL | [5 empty] | 2012-02-16 | [6 empty] | 2013-04-25 |  |  |  |  | 2017-08-24 | 2020-03-01
AA699 | 3847 | 2013-02-27 | Messrs Stevenson, Watson and Brunton | Bonerbo Wind Turbines | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Appeal Refused | Application Refused | Land At Bonerbo, Balmonth And Drumrack Farms Fife | Fife | Scotland | Scotland |  | 353656 | 707646 | Fife Council | 12/00482/FULL | 12/00042/NONDET |  |  |  |  | 2012-02-28 |  |  |  |  | 2012-12-24
AA706 | 3848 | 2015-12-09 | Windpower Wales | Llys Dymper Wind Farm Resubmission | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Appeal Withdrawn | Application Refused | Land at Llys Dymper, Gwytherin, Llanrwst, Conwy | Clwyd | Wales | Wales |  | 288420 | 358757 | Conwy County Borough Council | 0/38695 | APP/T6905/A/14/2228788 |  |  |  |  | 2012-02-16 |  | 2014-04-09 | 2015-01-23 | 2015-03-09
AA714 | 3849 | 2013-04-12 | Ballylaw Windfarm Limited | Ballylaw | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | land approximately 670m south of 44 Lowertown Road, Artigarvan, Strabane, Co Tyrone, BT82 0LF | Co. Tyrone | Northern Ireland | Northern Ireland |  | 54979 | 566264 | Northern Ireland Planning Service | J/2011/0128/F | N/A |  |  |  |  | 2011-04-08 | 2013-03-20
AA719 | 3850 | 2017-12-01 | NTR PLC | Altaveedan Wind Farm | Wind Onshore |  |  | 17.9 | n/a |  |  |  | 2.35 | 6 |  | n/a | Operational | Operational | in the townlands of Shelton South, Aldorough, Altaveedan North, Altaveedan South and Turnavedog near Loughguile, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 128388 | 584976 | Northern Ireland Planning Service | D/2010/0356/F | N/A |  |  |  |  | 2010-12-03 | [6 empty] | 2013-10-28 |  |  |  | 2018-10-28 | 2015-09-15 | 2017-04-24
AA721 | 3851 | 2019-05-16 | Beltonanean Renewable Energy | Beltonanean Wind Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Expired | Planning Permission Expired | Beltonanean Mountain, Beltonanean TD, Cookstown, Co. Tyrone. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 84923 | 543359 | Northern Ireland Planning Service | I/2010/0211/F | [5 empty] | 2010-05-17 | [6 empty] | 2012-05-17 |  |  |  | 2017-05-17
AA723 | 3852 | 2017-07-14 | Northern Ireland Renewables | Corkey Wind Farm Extension (Resubmission) | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | 583m north of 42 Reservoir Road, Knockagallen, Corkey. | Co. Antrim | Northern Ireland | Northern Ireland |  | 126713 | 580597 | Northern Ireland Planning Service | D/2010/0060/F | N/A |  |  |  |  | 2010-02-19 | [6 empty] | 2012-02-10 |  |  |  | 2017-02-10 | 2017-04-13 | 2017-07-13
AA791 | 3853 | 2013-02-26 | Falck Renewables Wind Ltd | Clach Liath Wind Farm | Wind Onshore |  |  | 42.5 | n/a |  |  |  | 2.5 | 17 |  | n/a | Planning Permission Refused | Application Refused | Land To The East Of Meall Na Speireig Clach Liath Evanton Ross-shire | Highland | Scotland | Scotland |  | 251454 | 867305 | Highland Council | 12/01689/FUL | [5 empty] | 2012-04-30 |  | 2013-02-13
AA999 | 3855 | 2016-10-25 | 2020 Renewables/ NTR | Ardoch and Over Enoch Wind Farm (Over Enoch) | Wind Onshore |  |  | 4.2665 | n/a |  |  |  | 2.3 | 2 | 110 | n/a | Operational | Operational | Over Enoch Road, Eaglesham, East Renfrewshire | Strathclyde | Scotland | Scotland | G76 0PN | 258600 | 648600 | East Renfrewshire Council | 2011/0630/TP | [5 empty] | 2011-09-27 | [6 empty] | 2012-04-13 |  |  |  |  | 2013-11-05 | 2014-11-12
B0014 | 3856 | 2013-05-10 | Airvolution Energy | Ystgellog Farm Wind Farm | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Ysgellog Farm, Rhosgoch, Builth Wells, Powys, LD2 | Gwynedd | Wales | Wales |  | 240490 | 391238 | Isle of Anglesey County Council | 11C557B | [5 empty] | 2010-10-24 | [6 empty] | 2011-06-21 |  |  |  |  | 2012-10-05 | 2013-04-30
B0025 | 3857 | 2017-05-17 | Renewables Infrastructure Group | NEILSTON WIND FARM | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | N/w Of Nether Carswell Farm, Drumgrain Tip, Kingston Road, Neilston, Glasgow, Strathclyde, G44 | Strathclyde | Scotland | Scotland |  | 245292 | 653952 | East Renfrewshire Council | 2009/0744/TP | [5 empty] | 2009-11-19 | [6 empty] | 2011-05-16 |  |  |  |  | 2012-03-01 | 2013-05-13
B0062 | 3859 | 2013-07-03 | Lanchester Properties | Greencroft Estate Turbines | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Land to east of Greencroft Estates, Tower Road, Annfield Plain, Stanley | Durham | North East | England |  | 416236 | 550574 | Durham County Council | CMA/1/51 | [5 empty] | 2011-06-28 | [6 empty] | 2011-11-01 | [5 empty] | 2013-03-01
B0098 | 3862 | 2015-01-05 | Thames Water Utilities | Crossness Sewage Works Turbine | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Belvedere Road, London | Greater London | London | England | SE2 9AR | 548777 | 180312 | Bexley London Borough Council | 08/03936/FULMIN | [5 empty] | 2010-11-24 | [6 empty] | 2010-12-16 |  |  |  |  | 2013-11-30 | 2014-02-16
B0128 | 3863 | 2015-08-04 | Muirden Energy | Mormond Hill Windfarm | Wind Onshore |  |  | 27.6 | n/a |  |  |  | 2.3 | 12 |  | n/a | Appeal Refused | Application Refused | Mormond Hill, Memsie, Fraserburgh | Grampian | Scotland | Scotland | AB43 7AX | 396106 | 856589 | Aberdeenshire Council | APP/2011/3223 | PPA-110-2258 |  |  |  |  | 2011-11-07 |  | 2014-11-07 | 2015-02-06 |  | 2015-07-30
B0131 | 3864 | 2016-02-04 | Ecotricity | Straid Farm Wind Park | Wind Onshore |  |  | 36.8 | n/a |  |  |  | 2.6 | 14 | 100 | n/a | Appeal Refused | Application Refused | Straid Farm, Lendalfoot, South Ayrshire | Strathclyde | Scotland | Scotland | KA26 0JF | 213789 | 590485 | South Ayrshire Council | 12/00090/APPM | PPA-370-2048 |  |  |  |  | 2011-08-01 |  | 2015-05-13 | 2015-07-09 |  | 2016-01-26
B0148 | 3865 | 2014-02-27 | REG Windpower | Pentre Tump - Resubmission | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 1.5 | 3 |  | n/a | Appeal Refused | Application Refused | Radnor, Presteigne, Powys. LD8 | Powys | Wales | Wales |  | 319500 | 257500 | Powys County Council | P/2012/0779 | [5 empty] | 2012-07-13 |  | 2012-12-13 |  |  | 2014-01-28
B0155 | 3866 | 2014-06-02 | Force 9 Energy | Mull Hill Windfarm | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2.5 | 9 |  | n/a | Appeal Refused | Application Refused | Mull Hill, Meall Tarsuinn, Nr Monzie | Tayside | Scotland | Scotland |  | 288270 | 728235 | Perth and Kinross Council | 11/02151/FLM | 13/00010/REF |  |  |  |  | 2011-12-23 |  | 2013-05-23 |  |  | 2014-04-23
B0159 | 3868 | 2020-01-24 | 3R Energy (formerly Lantern Bidco) | Poniel Wind Turbines | Wind Onshore |  |  | 9 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Granted | Awaiting Construction | Land at Poniel South Lanarkshire | Strathclyde | Scotland | Scotland |  | 284063 | 633619 | South Lanarkshire Council | CL/12/0043 | [5 empty] | 2012-02-01 | [6 empty] | 2015-01-27
B0160 | 3869 | 2014-01-30 | Wind Ventures | Tranwell Airfield Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Planning Permission Refused | Application Refused | Tranwell Airfield, Morpeth | Northumberland | North East | England |  | 418720 | 582441 | Northumberland County Council | 12/03731/RENEIA | [5 empty] | 2012-12-12 |  | 2014-01-30
B0177 | 3871 | 2014-01-10 | Peel Energy | Port Of Heysham Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Heysham Port North Quay Heysham Harbour Heysham Morecambe Lancashire LA3 2XF | Lancashire | North West | England |  | 339900 | 460342 | Lancaster City Council | 11/00816/FUL | [5 empty] | 2011-09-05 | 2013-10-29
B0205 | 3872 | 2014-03-13 | Ventient (formerly Infinis) | Tibberchindy Wind Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Planning Permission Refused | Application Refused | Coiliochbhar Hill, nr Tibberchindy Farmhouse 5km west of Alford, Aberdeenshire | Grampian | Scotland | Scotland |  | 350924 | 814910 | Aberdeenshire Council | APP/2012/3405 | [5 empty] | 2012-10-15 |  | 2014-02-04
B0221 | 3873 | 2016-06-27 | Muirhall Energy | Muirhall Extension | Wind Onshore |  |  | 6.8 | n/a |  |  |  | 3.4 | 2 |  | n/a | Operational | Operational | Stellashaw Moss, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 299342 | 652838 | South Lanarkshire Council | CL/12/0074 | [5 empty] | 2012-02-21 | [6 empty] | 2012-09-10 | [5 empty] | 2014-04-30
B0241 | 3874 | 2013-05-14 | Prowind | Hogs Hill Resubmission | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land At Hogs Hill, Off Main Road And Syerscote Lane Haunton Tamworth Staffordshire | Staffordshire | West Midlands | England |  | 422363 | 309765 | Lichfield District Council | 12/00078/FULM | [5 empty] | 2012-06-11 |  | 2013-04-09
B0244 | 3875 | 2012-08-29 | West Coast Energy | Corse Hill Wind Farm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Planning Permission Refused | Application Refused | Land At Nether Kelly, Nether Kelly, Arbroath | Tayside | Scotland | Scotland |  | 360091 | 737632 | Angus Council | 11/01093/EIAL | [5 empty] | 2011-11-15 |  | 2012-08-07
B0245 | 3876 | 2013-03-05 | Green Cat Renewables | Finavon Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Appeal Refused | Application Refused | Hill of Finavon, Finavon Estate, DD8 3QG | Tayside | Scotland | Scotland |  | 349070 | 754820 | Angus Council | 12/00002/EIAL | 12/00011/NONDET |  |  |  |  | 2012-01-04 |  |  |  |  | 2012-10-26
B0250 | 3877 | 2015-08-03 | Energia Renewables | Clondermot Turbines | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Trench Road, Derry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 60124 | 576620 | Northern Ireland Planning Service | A/2007/0153/F | [5 empty] | 2007-02-21 | [6 empty] | 2010-01-18 |  |  |  | 2015-01-18 | 2014-06-01 | 2015-04-14
B0291 | 3880 | 2014-02-27 | Scottish and Southern Energy (SSE) | Dalnessie Wind Farm | Wind Onshore |  |  | 67.5 | n/a |  |  |  | 2.5 | 27 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Dalnessie, Lairg, Sutherland | Highland | Scotland | Scotland |  | 262860 | 917380 | Scottish Government (S36) | [6 empty] | 2012-03-01 | 2014-02-26
B0299 | 3881 | 2014-03-03 | Good Energy Generation | Holm and Hollymill Wind Turbines | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land at Holm and Hollymill, King Edward, Banff | Grampian | Scotland | Scotland | AB45 3PB | 371312 | 856656 | Aberdeenshire Council | APP/2012/0151 | [5 empty] | 2012-01-20 |  | 2014-01-31
B0302 | 3882 | 2013-04-19 | West Coast Energy | Daviot Wind Farm | Wind Onshore |  |  | 32.5 | n/a |  |  |  | 2.5 | 13 |  | n/a | Appeal Refused | Application Refused | Lairgandour Daviot Inverness IV2 6XN | Highland | Scotland | Scotland |  | 273500 | 837000 | Highland Council | 12/00036/FUL | 12/00032/REFIN |  |  |  |  | 2012-01-05 |  | 2012-06-25 |  |  | 2013-02-11
B0331 | 3883 | 2014-02-27 | Scottish and Southern Energy (SSE) | Fairburn Extension | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Fairburn, Marybank | Highland | Scotland | Scotland |  | 242550 | 852250 | Scottish Government (S36) | [6 empty] | 2013-07-03 | 2014-02-26
B0334 | 3884 | 2013-07-11 | Element Power | Monashee Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn |  | Borders | Scotland | Scotland |  | 380760 | 662025 | Scottish Borders Council | 12/00431/FUL | [5 empty] | 2012-04-06 | 2013-06-25
B0394 | 3886 | 2017-05-31 | The Renewables Infrastructure Group (TRIG) | Freasdail Wind Farm | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2 | 11 |  | n/a | Operational | Operational | Land East Of Loch Freasdail And North Of Loch Cruinn Whitehouse By Tarbert Argyll And Bute | Strathclyde | Scotland | Scotland |  | 182440 | 659197 | Argyll and Bute Council | 12/02150/PP | 13/00022/REFPLA |  |  |  |  | 2012-10-25 |  | 2013-09-25 |  |  |  | 2014-04-15 | 2014-04-15 |  |  |  |  | 2016-02-20 | 2017-02-08
B0436 | 3887 | 2017-07-18 | Welsh Water | Nash Waste Water Treatment Works Turbine | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | West Nash Road, Nash NP18 2YH | Gwent | Wales | Wales |  | 333598 | 184016 | Newport City Council | 11/1287 | [5 empty] | 2011-12-08 | [6 empty] | 2012-07-04 |  |  |  |  | 2017-02-07 | 2017-03-15
B0440 | 3888 | 2018-10-25 | Green Cat Renewables | Govals Wind Farm | Wind Onshore |  |  | 4.8 | n/a |  |  |  | 0.8 | 6 |  | n/a | Appeal Granted | Awaiting Construction | Govals Farm, Forfar | Tayside | Scotland | Scotland |  | 341760 | 743783 | Angus Council | 12/00570/EIAL | PPA-120-2027 |  |  |  |  | 2012-06-07 |  | 2013-05-15 |  |  |  | 2013-12-06 | 2013-12-06
B0496 | 3889 | 2014-02-20 | Airvolution Energy | Mossmorran Wind Farm -resubmission | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land At To The West Of Chemical Works, Mossmorran, Fife | Fife | Scotland | Scotland |  | 318109 | 689419 | Fife Council | 12/02692/FULL | [5 empty] | 2012-06-18 | 2013-11-19
B0554 | 3890 | 2015-01-20 | Blue Energy | Marston Vale Country Park Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | The Marston Vale Millennium Country Park, Station Road, Marston Moretaine, Bedford, MK43 0PR | Bedfordshire | Eastern | England |  | 500498 | 241710 | Central Bedfordshire Council | CB/11/04077/FULL | [5 empty] | 2011-11-11 | [6 empty] | 2012-02-01 |  |  |  |  | 2013-10-23 | 2014-05-01
B0563 | 3891 | 2018-02-27 | Forsa (formerly 2020 Renewables/Velocita) | Druim Leathann Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3 | 14 | 126 | n/a | Planning Permission Expired | Planning Permission Expired | 2km west of Tolsta and 16km north east of Stornoway | Western Isles | Scotland | Scotland |  | 151276 | 946709 | Comhairle nan Eilean Siar Council | 13/00215/PPDM | [5 empty] | 2013-04-30 | [6 empty] | 2013-12-05 |  |  |  | 2016-12-31
B0601 | 3892 | 2019-11-21 | S & JD Robertson Group Ltd | Work Farm Wind Turbines | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Planning Permission Granted | Awaiting Construction | Work Farm (Land Near), Work Road, St Ola, Orkney | Orkney Islands | Scotland | Scotland |  | 347667 | 1012871 | Orkney Islands Council | 12/699/TPP | [5 empty] | 2012-10-12 | [6 empty] | 2013-01-31 |  |  |  | 2016-01-31
B0668 | 3893 | 2018-03-15 | Spencer Group | Energy Works Hull - Wind Turbine | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Operational | Operational | Cleveland Street (former Adm Cocoa Plant), Dalton Street, Kingston Upon Hull, Humberside | Humberside | Yorkshire and Humber | England | HU8 8BB | 510170 | 430424 | Kingston upon Hull City Council | 11/00615/CM | [5 empty] | 2011-06-27 | [6 empty] | 2011-10-20 |  |  |  |  | 2015-11-15 | 2018-03-01
B0672 | 3894 | 2014-03-03 | EDF | Maumhill Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Planning Permission Refused | Application Refused | Land South West Of, Wheatley Road, Sturton Le Steeple, Retford, Notts | Nottinghamshire | East Midlands | England |  | 476365 | 383705 | Bassetlaw District Council | 46/11/00035 | [5 empty] | 2011-12-23 |  | 2013-02-28
B0681 | 3896 | 2016-01-04 | Awel Aman Tawe Community Energy | Mynydd Y Gwrhyd Windfarm (resubmission) | Wind Onshore |  |  | 4.7 | n/a |  |  |  | 2.35 | 2 |  | n/a | Operational | Operational | Mynydd Y Gwrhyd | West Glamorgan | Wales | Wales |  | 272659 | 210474 | Neath Port Talbot County Borough Council | P2010/1225 | [5 empty] | 2010-12-10 | [6 empty] | 2013-03-21 |  |  |  |  | 2016-03-14 | 2017-12-01
B0682 | 3897 | 2015-12-17 | Severn Trent Water | Severn Trent Water - Stoke Bardolph Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Stoke Lane, Stoke, Bardolph, Nottinghamshire | Nottinghamshire | East Midlands | England | NG14 5HL | 464294 | 342475 | Gedling Borough Council | 2012/1472 | [5 empty] | 2012-12-12 | [6 empty] | 2013-09-19 |  |  |  |  | 2015-03-15 | 2015-12-15
B0686 | 3898 | 2015-02-13 | Broadview Energy | Bicton Wind Farm (resubmission) | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Secretary of State - Refusal | Application Refused | between Stow Longa and Kimbolton. | Cambridgeshire | Eastern | England |  | 509905 | 270168 | Huntingdonshire District Council | 1300512FUL | [5 empty] | 2013-04-12 |  | 2013-09-18 | [6 empty] | 2015-02-13
B0711 | 3899 | 2016-02-05 | Renewable Energy Systems (RES) | Swift Wind Farm (Bransford Bridge) | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Appeal Refused | Application Refused | n/w of Junction 1, M6, Churchover, Rugby, Warwickshire, CV23 | Warwickshire | West Midlands | England |  | 450681 | 281599 | Rugby Borough Council | R12/2009 | APP/E3715/A/14/2227479 |  |  |  |  | 2013-11-22 |  | 2014-04-23 | 2014-10-23 |  | 2016-01-18
B0718 | 3900 | 2015-10-05 | Airvolution Energy | Hafod-y-Dafal | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Appeal Refused | Application Refused | Near Cwm, Blaenau Gwent | Gwent | Wales | Wales |  | 319898 | 204044 | Blaenau Gwent County Borough Council | C/2013/0295 | APP/X6910/A/15/2230097 |  |  |  |  | 2013-10-01 |  | 2014-07-30 | 2015-03-04 |  | 2015-09-23
B0748 | 3901 | 2020-05-28 | EDF & AMEC (Lewis Wind Power) | Uisenis/Eishken (Muaitheabhal) (Southern Extension) | Wind Onshore |  |  | 21.6 | n/a |  |  |  | 3.6 | 6 | 150 | n/a | Planning Permission Granted | Awaiting Construction | Eishken on Lewis, Eishkein Estate, Pairc/Park, Isle of Lewis | Western Isles | Scotland | Scotland |  | 128788 | 911062 | Scottish Government (S36) | EC00002096 | [5 empty] | 2013-06-11 | [6 empty] | 2015-09-08 |  |  |  | 2018-09-08
B0759 | 3902 | 2014-05-20 | Ayre Energy/Aquatera Ltd | Barns of Ayre Wind Turbines (2) | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Operational | Operational | Deerness, Orkney | Orkney Islands | Scotland | Scotland |  | 358890 | 1004047 | Orkney Islands Council | 10/594/PP | [5 empty] | 2010-11-09 | [6 empty] | 2011-03-12 |  |  |  |  | 2012-09-01 | 2013-07-01
B0992 | 3903 | 2016-09-01 | West Coast Energy | Braint Wind Farm | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Planning Permission Refused | Application Refused | On Land At Bryn Eryr Uchaf, Porthaethwy, Menai Bridge, Gwynedd | Gwynedd | Wales | Wales | LL59 5SA | 253066 | 375343 | Isle of Anglesey County Council | 41C125B/EIA/RE | [5 empty] | 2013-08-14 |  | 2015-07-27
B1014 | 3904 | 2016-10-03 | Renewable Energy Partnerships Ltd | Newton Down | Wind Onshore |  |  | 5 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Bridgend | Mid Glamorgan | Wales | Wales |  | 284252 | 179465 | Bridgend County Borough Council | P/12/368/FUL | [5 empty] | 2012-05-18 |  | 2012-07-13 |  |  |  | 2013-05-24 | 2013-05-24 |  |  |  |  | 2016-04-07 | 2016-09-29
C0007 | 3905 | 2016-10-31 | Ventient (formerly Infinis) | North Steads Wind Farm | Wind Onshore |  |  | 18.5 | n/a |  |  |  | 3 | 9 |  | n/a | Operational | Operational | Situated between Widdrington and Red Row to the west of the A1068 | Northumberland | North East | England |  | 423943 | 596828 | Northumberland County Council | 12/00290/RENEIA | [5 empty] | 2012-01-30 | [6 empty] | 2012-11-06 |  |  |  |  | 2016-07-20 | 2016-07-04
C0014 | 3906 | 2013-02-26 | Green Cat Renewables | CLACHAN SEIL WIND FARM | Wind Onshore |  |  | 8.1 | n/a |  |  |  | 0.9 | 9 |  | n/a | Planning Permission Refused | Application Refused | Clachan Seil, Clachan Seil, Oban, Argyll | Strathclyde | Scotland | Scotland | PA34 | 179486 | 720695 | Argyll and Bute Council | 11/02447/PP | [5 empty] | 2012-02-02 |  | 2012-11-02
C0032 | 3907 | 2013-05-01 | Lomond Energy | CRAIGANNET WIND FARM | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Appeal Refused | Application Refused | 885 Metres Nw/O Craigannet Farm, Fintry, Glasgow, Strathclyde, G33 | Strathclyde | Scotland | Scotland |  | 271498 | 684905 | Stirling Council | 12/00056/FUL | PPA-390-2022 |  |  |  |  | 2012-02-02 |  | 2012-08-31 |  |  | 2012-11-21
C0036 | 3908 | 2016-08-11 | Latheron, Lybster & Clyth Community Development Company | Rumster Forest Community Wind Farm | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Abandoned | Abandoned | Gaultiquoy, Rumster Forest, Lybster, Highlands, KW3 | Highland | Scotland | Scotland |  | 320706 | 940695 | Highland Council | 11/04522/FUL | [5 empty] | 2011-12-21 | [6 empty] | 2015-08-07 |  |  |  | 2018-08-07
C0159 | 3909 | 2013-09-13 | Ridgewind | Gilston Wind Farm (Borders) | Wind Onshore |  |  | 14.35 | n/a |  |  |  | 2.05 | 7 |  | n/a | Appeal Refused | Application Refused | south of the village of Fala and just to the west of the existing Dun Law wind farm | Borders | Scotland | Scotland |  | 344033 | 659490 | Scottish Borders Council | 11/01680/FUL | 13/00010/REF |  |  |  |  | 2011-12-21 |  | 2012-12-10 |  |  | 2013-08-29
C0163 | 3910 | 2015-07-01 | Fraserburgh Harbour Commissioners | Fraserburgh Harbour Wind Turbines | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Fraserburgh Harbour, Shore Street, Fraserburgh, Aberdeenshire, AB43 9BR | Grampian | Scotland | Scotland |  | 399868 | 866975 | Aberdeenshire Council | APP/2012/1101 | [5 empty] | 2012-04-13 | 2015-04-29
C0329 | 3911 | 2017-04-04 | LocoGen/ Green Cat Renewables | Hill of Tillymorgan (Kirkton Farm) Wind turbines (resubmission) | Wind Onshore |  |  | 9.6 | n/a |  |  |  | 3.2 | 3 |  | n/a | Operational | Operational | Hill of Tillymorgan, Culsalmond, Insch | Grampian | Scotland | Scotland | AB52 6TT | 363363 | 828345 | Aberdeenshire Council | APP/2011/0855 | [5 empty] | 2011-03-16 | [6 empty] | 2013-04-30 |  |  |  |  | 2015-07-01 | 2016-12-01
C0490 | 3912 | 2016-01-04 | Freelight (Shetland) | Culterfield Windfarm | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Planning Permission Expired | Planning Permission Expired | Culterfield, Cunningsburgh, Shetland | Shetland | Scotland | Scotland | ZE2 9HB | 442762 | 1129706 | Shetland Islands Council | 2012/271/PPF | [5 empty] | 2012-08-09 | [6 empty] | 2012-12-03 |  |  |  | 2015-12-03
C0524 | 3913 | 2013-11-21 | Wind Prospect Developments | Frandy Hill | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Appeal Refused | Application Refused | Site South Of The Upper And Lower Glendevon Resevoirs Glendevon | Tayside | Scotland | Scotland |  | 292500 | 703500 | Perth and Kinross Council | 11/01952/FLL | 13/00004/NONDET |  |  |  |  | 2011-12-09 |  |  |  |  | 2013-04-11
C0654 | 3914 | 2013-08-30 | Energiekontor UK | HORN BURN WIND FARM - WIND TURBINES | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Appeal Refused | Application Refused | Se/O Reston Hill Farmhouse, Horn Burn Wind Farm, Eyemouth, Borders, TD14 | Borders | Scotland | Scotland |  | 390000 | 659500 | Scottish Borders Council | 12/01348/FUL | 13/00011/NONDET |  |  |  |  | 2012-10-30 |  |  |  |  | 2013-08-29
C0657 | 3915 | 2018-05-23 | PI Renewables 2 Ltd | LADEHEAD FARM - WIND TURBINES | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 1.3 | 3 |  | n/a | Operational | Operational | Ladehead Farm Lesmahagow | Strathclyde | Scotland | Scotland | ML11 0HZ | 279142 | 641223 | South Lanarkshire Council | CL/12/0461 | [5 empty] | 2012-10-19 | [6 empty] | 2015-01-22 |  |  |  | 2018-01-22 | 2016-06-15 | 2016-09-15
C0704 | 3916 | 2014-12-05 | Private Developer | Tangy Farm Wind Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Tangy, Kilkenzie, Campbeltown, Argyll And Bute | Strathclyde | Scotland | Scotland | PA28 6QD | 168309 | 628129 | Argyll and Bute Council | 12/02458/PP | [5 empty] | 2012-11-16 | 2014-03-24
C0860 | 3917 | 2015-08-11 | Airvolution Energy | Garlenick Estate 2 - Wind Turbines | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Garlenick Estate Grampound Cornwall | Cornwall | South West | England |  | 194662 | 49203 | Cornwall Council | PA12/09852 | [5 empty] | 2012-11-01 | [6 empty] | 2013-01-31 |  |  |  |  | 2014-04-01 | 2015-06-18
C0862 | 3918 | 2016-04-22 | George Richards Farms Partnership | Goonabarn Farm Wind Turbines | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Operational | Operational | Goonabarn Farm Summercourt Newquay Cornwall TR8 5BL | Cornwall | South West | England |  | 189473 | 54165 | Cornwall Council | PA13/00848 | [5 empty] | 2013-02-12 | [6 empty] | 2013-07-04 |  |  |  |  | 2016-01-01 | 2016-04-01
C1020 | 3919 | 2018-11-27 | West Garty Renewables | West Garty Windfarm (resubmission) | Wind Onshore |  |  | 54 | n/a |  |  |  | 3 | 18 | 120 | n/a | Appeal Refused | Application Refused | West Garty Estate, Helmsdale, East Sutherland | Highland | Scotland | Scotland | KW8 6HP | 294780 | 915304 | Scottish Government (S36) | EC00002075 | WIN-270-6 |  |  |  |  | 2014-12-01 |  |  | 2016-05-17 |  | 2018-10-19
C1044 | 3920 | 2014-02-14 | Private Developer | Boy's Hill Wind Cluster | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land to North West of Denside, Glenfarquhar, Auchenblae, Laurencekirk | Grampian | Scotland | Scotland | AB30 1UJ | 371671 | 781186 | Aberdeenshire Council | APP/2012/4218 | [5 empty] | 2013-01-10 |  | 2013-10-21
C1154 | 3921 | 2015-11-05 | Peterborough Wind Energy | Gores Wind Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Gores Farm Whittlesey Road Thorney Peterborough | Cambridgeshire | Eastern | England | PE6 0RF | 526500 | 302350 | Peterborough City Council | 13/00431/FUL | [5 empty] | 2013-04-05 | 2015-10-28
C1161 | 3922 | 2014-11-06 | North Uist Development Company | Locheport wind turbines | Wind Onshore |  |  | 1.8 | n/a |  |  |  | 0.9 | 2 |  | n/a | Planning Permission Refused | Application Refused | Locheport Isle Of North Uist | Western Isles | Scotland | Scotland |  | 81406 | 864703 | Comhairle nan Eilean Siar Council | 13/00155/PPD | [5 empty] | 2013-04-04 |  | 2014-10-09
C1199 | 3923 | 2018-10-29 | Newton Of Fortrie LLP/Muirden Energy | Hill of Carlincraig wind turbines | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Granted | Awaiting Construction | Land at Hill of Carlincraig Land to the South-East of Newton of Fortrie Farm Turriff AB53 4HL | Grampian | Scotland | Scotland | AB53 4HL | 368325 | 844794 | Aberdeenshire Council | APP/2013/0987 | [5 empty] | 2013-04-01 | [6 empty] | 2015-07-02 |  |  |  | 2018-07-02
C1356 | 3924 | 2015-11-25 | The Farm Energy Partnership LLP | Bloodhills - repowering | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Operational | Operational | Bloodhills Farm, Bloodhills East Somerton Great Yarmouth NR29 4DU | Norfolk | Eastern | England |  | 647642 | 318446 | Great Yarmouth Borough Council | 06/13/0093/F | [5 empty] | 2013-02-12 | [6 empty] | 2013-05-14 |  |  |  |  | 2014-07-15 | 2015-06-15
C1585 | 3925 | 2016-10-25 | 2020 Renewables/ NTR | Ardoch and Over Enoch Wind Farm (Ardoch) | Wind Onshore |  |  | 7.1665 | n/a |  |  |  | 2.5 | 3 | 110 | n/a | Operational | Operational | Ardoch Farm, Over Enoch Road, Eaglesham, East Renfrewshire | Strathclyde | Scotland | Scotland | G76 0PL | 258534 | 649697 | East Renfrewshire Council | 2012/0331/TP | [5 empty] | 2012-05-24 | [6 empty] | 2012-07-09 |  |  |  |  | 2013-11-05 | 2014-11-12
C2276 | 3926 | 2018-04-27 | Renewable Energy Systems (RES) | Culachy Wind Farm | Wind Onshore |  |  | 44 | n/a | 0.9 | n/a |  | 3.4 | 13 | 149.5 | n/a | Appeal Refused | Application Refused | Culachy Estate Land 6KM SE Of, Newtown, Invergarry, Highlands | Highland | Scotland | Scotland | PH35 4 | 237225 | 804335 | Highland Council | 14/04782/FUL | PPA-270-2151 |  |  |  |  | 2015-01-15 |  | 2015-12-18 | 2016-03-17 |  | 2018-04-27
EN00022 | 3927 | 2014-03-04 | Bristol City Council - Energy Management Unit | Avonmouth Port II | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | Former Shell Tanker Site Severn Road Avonmouth Bristol | Avon | South West | England |  | 353360 | 182375 | Bristol City Council | 08/03724/FB | [5 empty] | 2008-08-29 | [6 empty] | 2009-01-14 |  |  |  |  | 2013-04-30 | 2013-09-30
EN00089 | 3928 | 2012-08-23 | E.ON Renewables | Tween Bridge Windfarm | Wind Onshore |  |  | 44 | n/a |  |  |  | 2 | 22 |  | n/a | Operational | Operational | Tween Bridge, Thorne, Doncaster, South Yorks | South Yorkshire | Yorkshire and Humber | England | DN8 5 | 470500 | 414500 | DECC (S36) | 04/0314/P/CIR2 | [5 empty] | 2004-01-23 | [6 empty] | 2008-02-28 |  |  |  |  | 2011-05-01 | 2012-02-27
EN00094 | 3929 | 2016-08-16 | Melness Crofters Estate | Melness | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 |  | n/a | Abandoned | Abandoned | Near Melness , Sutherland | Highland | Scotland | Scotland |  | 256500 | 962000 | Highland Council | 06/00271/FULSU | [5 empty] | 2006-07-12 | [6 empty] | 2008-10-22
EN00096 | 3930 | 2016-02-24 | North British Windpower | Druim Fada | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Permission Expired | Planning Permission Expired | Loch Eil , Fort William , Lochaber | Highland | Scotland | Scotland |  | 207500 | 780500 | Highland Council | 09/00074/FULLO | [5 empty] | 2009-02-01 | [6 empty] | 2012-08-09 |  |  |  | 2015-08-09
EN00114 | 3931 | 2018-06-04 | Gresham House | Mynydd Portref | Wind Onshore |  |  | 9.35 | n/a |  |  |  | 0.85 | 11 |  | n/a | Operational | Operational | N of Brynna, E of existing Taff Ely Wind Farm | Mid Glamorgan | Wales | Wales |  | 298897 | 185178 | Rhondda Cynon Taff County Borough Council | 06/1325 | [5 empty] | 2006-06-26 | [6 empty] | 2008-07-01 | [5 empty] | 2012-03-26
EN00117 | 3932 | 2013-06-05 | Pennant Walters | Fforch Nest Wind Farm pt2 | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Operational | Operational | Mynydd Maesteg and Mynydd Pwllyrhebog, Ogmore and Rhondda Valleys | Mid Glamorgan | Wales | Wales |  | 296500 | 190800 | Rhondda Cynon Taff County Borough Council | 06/1842/10 | [5 empty] | 2006-03-31 | [6 empty] | 2011-05-04 |  |  |  |  | 2011-10-30 | 2013-05-24
EN00125 | 3933 | 2017-01-04 | Energia Renewables | Gortfinbar | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | Sixmilecross/Carrickmore, Omagh | Co. Tyrone | Northern Ireland | Northern Ireland |  | 75490 | 528123 | Northern Ireland Planning Service | K/2006/1089/F | [5 empty] | 2006-04-03 | [6 empty] | 2009-05-07 |  |  |  |  | 2015-09-01 | 2016-12-22
EN00127 | 3934 | 2017-01-03 | Gaelectric Developments/ CGN Europe Energy | Carn Hill | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Lands north of Slievetrue Road, Carn Hill/Rea Hill, Newtownabbey, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 148254 | 544393 | Northern Ireland Planning Service | U/2006/0054/F | [5 empty] | 2006-02-17 | [6 empty] | 2010-02-12 |  |  |  |  | 2012-05-01 | 2013-05-08
EN00134 | 3935 | 2016-09-30 | DIF | Wadlow Wind Farm | Wind Onshore |  |  | 26 | n/a |  |  |  | 2 | 13 |  | n/a | Operational | Operational | Nr West Wratting, South Cambridgeshire | Cambridgeshire | Eastern | England |  | 558500 | 254500 | South Cambridgeshire District Council | S/1018/06/F | [5 empty] | 2006-05-15 |  | 2007-06-06 |  |  |  | 2009-11-09 | 2009-11-09 |  |  |  |  | 2011-08-01 | 2012-09-01
EN00155 | 3936 | 2014-01-22 | Npower Renewables | Bradwell Wind Farm (Repower) | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Operational | Operational | Bradwell on Sea, Maldon | Essex | Eastern | England |  | 595000 | 205000 | Maldon District Council | 06/00291/FUL | [5 empty] | 2006-03-30 |  | 2006-07-07 | [9 empty] | 2012-04-01 | 2013-09-30
EN00159 | 3937 | 2012-05-17 | Banks Renewables | Hazlehead | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | to the rear of Hepworth's factory, Crow Edge | South Yorkshire | Yorkshire and Humber | England |  | 417915 | 403915 | Barnsley Council | 2006/1575 | [5 empty] | 2006-09-05 | [6 empty] | 2007-03-08 |  |  |  |  | 2010-08-01 | 2011-12-16
EN00160 | 3938 | 2013-02-25 | Npower Renewables | Kiln Pit Hill Windfarm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | land to the east of A68, approx 1km SE of Kiln Pit Hill | Northumberland | North East | England |  | 405590 | 554583 | Northumberland County Council | 20060052 | [5 empty] | 2006-02-15 | [6 empty] | 2009-01-02 |  |  |  |  | 2011-11-01 | 2012-08-01
EN00172 | 3939 | 2013-09-04 | Nuon | Mynydd Waun Fawr Wind Farm | Wind Onshore |  |  | 37.5 | n/a |  |  |  | 2.5 | 15 |  | n/a | Planning Application Withdrawn | Application Withdrawn | South of Llanerfyl, Powys | Powys | Wales | Wales |  | 301500 | 305000 | Powys County Council | M/2007/0972 | [5 empty] | 2007-10-08 | 2013-07-16
EN00183 | 3940 | 2015-09-14 | Vattenfall | Llanbadarn Fynydd Wind Farm | Wind Onshore |  |  | 51 | n/a |  |  |  | 3 | 17 |  | n/a | Planning Permission Refused | Application Refused | 2.5km North of Llanbadarn Fynydd, Powys | Powys | Wales | Wales |  | 309500 | 282000 | DECC (S36) | [6 empty] | 2007-12-03 |  | 2015-09-07
EN00206 | 3941 | 2014-11-19 | Otter Power | Otterham Down Wind Farm (Resubmission) | Wind Onshore |  |  | 3.2 | n/a |  |  |  | 0.8 | 4 |  | n/a | Operational | Operational | Otterham, Camelford | Cornwall | South West | England |  | 215700 | 90500 | Cornwall Council | 2006/01274 | [5 empty] | 2006-06-20 | [6 empty] | 2009-10-13 |  |  |  |  | 2011-05-01 | 2011-08-17
EN00209 | 3942 | 2015-01-05 | Greencoat UK Wind | Sixpenny Wood Windfarm | Wind Onshore |  |  | 33 | n/a |  |  |  | 3.3 | 10 |  | n/a | Operational | Operational | Between Eastrington, Gilberdyke, Kilpin and Laxton | Humberside | Yorkshire and Humber | England |  | 478500 | 427500 | East Riding of Yorkshire Council | 07/04680/STPLFE | 09/00053/CALLIN |  |  |  |  | 2007-07-20 |  | 2008-10-30 |  |  |  | 2009-12-08 | 2009-12-08 |  |  |  |  | 2012-02-01 | 2013-07-15
EN00211 | 3943 | 2015-01-05 | Greencoat UK Wind | Earl's Hall | Wind Onshore |  |  | 10.25 | n/a |  |  |  | 2.05 | 5 |  | n/a | Operational | Operational | Earls Hall Farm, Clacton on Sea, Essex | Essex | Eastern | England |  | 614550 | 216860 | Tendring District Council |  | 08/00098/REFUSE |  |  |  |  | 2007-03-22 |  | 2008-09-22 |  |  |  | 2009-11-19 | 2009-11-19 |  |  |  |  | 2012-02-28 | 2013-01-13
EN00230 | 3944 | 2012-11-02 | Private Developer | Mawdesley Moss | Wind Onshore |  |  | 2.25 | n/a |  |  |  | 0.75 | 3 |  | n/a | Operational | Operational | Cliff Farm Mawdesley Moss Chorley Lancashire | Lancashire | North West | England |  | 348500 | 415500 | Chorley Borough Council | 07/00568/FULMAJ | [5 empty] | 2007-05-01 |  | 2007-09-13 | [9 empty] | 2012-04-01 | 2012-08-01
EN00235 | 3945 | 2013-05-09 | Coronation Power | Crook Hill (Calderdale MBC) | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Abandoned | Abandoned | 4km north of Rochdale and 2km east of Whitworth, on the high ground of Shore Moor to the north of the village of Wardle and Watergrove Reservoir | Greater Manchester | North West | England |  | 392720 | 419080 | Calderdale Metropolitan Borough Council | 07/00632/WDF | [5 empty] | 2007-03-20 | [6 empty] | 2009-10-14
EN00237 | 3946 | 2014-05-06 | Chelveston Renewable Energy | Chelveston Renewable Energy Park Wind Farm (East Northamptonshire) | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | Chelveston Airfield East Northamptonshore | Northamptonshire | East Midlands | England |  | 499885 | 268015 | East Northamptonshire Council | 10/00415/FUL | 11/00018/REF |  |  |  |  | 2010-03-03 |  | 2011-03-07 |  |  |  | 2012-06-29 | 2012-06-29 |  |  |  |  | 2013-08-01 | 2014-02-15
EN00241 | 3947 | 2013-05-08 | Harworth Power | Bewick Drift | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | Land at former Lynemouth coal handling store north of existing Lynemouth Power Station | Northumberland | North East | England |  | 428275 | 591310 | Northumberland County Council | CM/20060877 | [5 empty] | 2006-10-15 |  | 2007-05-30 |  |  |  | 2008-02-01 | 2008-02-01 |  |  |  |  | 2012-10-01 | 2013-03-31
EN00246 | 3948 | 2013-11-07 | John Laing Environmental Assets Group/REG Power Management | Hall Farm Routh | Wind Onshore |  |  | 24.6 | n/a |  |  |  | 2.05 | 12 |  | n/a | Operational | Operational | Land North Of, Hall Farm Acc Rd To Crowshore Plantation, Routh, East Riding Of Yorkshire, HU17 9SL | Humberside | Yorkshire and Humber | England |  | 507865 | 443185 | East Riding of Yorkshire Council | 06/08470/STPLFE | 07/00128/REFUSE |  |  |  |  | 2006-10-25 |  | 2007-01-30 |  |  |  | 2009-02-17 | 2009-02-17 |  |  |  |  | 2012-06-14 | 2013-05-28
EN00250 | 3949 | 2012-11-06 | Eco2 | Fochriw Wind | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Dismantled Railway, Adjacent Gelligaer Common, Fochriw, Bargoed | Mid Glamorgan | Wales | Wales |  | 309940 | 204475 | Merthyr Tydfil County Borough Council | P/05/1706 | [5 empty] | 2005-12-19 | 2007-02-19
EN00265 | 3950 | 2013-01-07 | Wind Prospect | Wheelers Cross | Wind Onshore |  |  | 7.8 | n/a |  |  |  | 1.3 | 6 |  | n/a | Planning Permission Refused | Application Refused | Wheelers Common Bradworthy Devon | Devon | South West | England |  | 234495 | 113725 | Torridge District Council | 1/0336/2011/FULM | [5 empty] | 2011-04-07 |  | 2012-12-07
EN00295 | 3951 | 2013-08-30 | Fred Olsen Renewables | Rothes Wind Farm (Extension) (II) | Wind Onshore |  |  | 41.4 | n/a |  |  |  | 2.3 | 18 |  | n/a | Operational | Operational | Rothes Windfarm, at Cairn Uish near Elgin | Grampian | Scotland | Scotland |  | 318500 | 850500 | Moray Council | [6 empty] | 2007-12-10 | [6 empty] | 2010-01-12 |  |  |  |  | 2012-04-01 | 2013-04-15
EN00324 | 3952 | 2012-06-25 | Devon Light and Power | Cross Moor | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Refused | Application Refused | LAND AT CROSS MOOR KNOWSTONE SOUTH MOLTON EX363PT | Devon | South West | England |  | 281205 | 124365 | North Devon District Council | 43580 | [5 empty] | 2006-12-22 |  | 2012-03-16
EN00333 | 3953 | 2013-12-12 | Airtricity | Glenconway | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Operational | Operational | Land at Glenconway Hill off Baranailt Road, (Adjacent to Loughermore Forest and north of Altahullion windfarm), Limavady. | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 78301 | 576178 | Northern Ireland Planning Service | B/2006/0607/F | [5 empty] | 2006-12-15 | [6 empty] | 2009-02-17 |  |  |  |  | 2012-05-14 | 2013-11-07
EN00335 | 3954 | 2016-02-24 | TCI Renewables | Ballyreagh, Tempo | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Abandoned | Abandoned | Land approximately 350m North East of 44 Derryraghan Road, Ballyreagh, Tempo. | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 42016 | 513750 | Northern Ireland Planning Service | L/2006/2371/F | [5 empty] | 2006-12-15 | [6 empty] | 2009-05-11
EN00336 | 3955 | 2013-12-12 | Scottish and Southern Energy (SSE) | Glenconway 2 (formerly Altahullion Phase III) | Wind Onshore |  |  | 27.6 | n/a |  |  |  | 2.3 | 12 |  | n/a | Operational | Operational | Altahullion Phase III Wind Farm in the townlands of Drum, Glenconway and Ballymoney, near Dungiven | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 77926 | 575589 | Northern Ireland Planning Service | B/2007/0006/F | [5 empty] | 2007-01-11 | [6 empty] | 2010-09-26 |  |  |  |  | 2012-10-01 | 2013-11-07
EN00352 | 3956 | 2013-06-05 | Pennant Walters | Fforch Nest Wind Farm pt1 | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Operational | Operational | Land North of Glynogwr | Mid Glamorgan | Wales | Wales |  | 296600 | 191300 | Bridgend County Borough Council | P/06/1080/FUL | [5 empty] | 2006-08-31 | [6 empty] | 2011-05-04 |  |  |  |  | 2011-10-30 | 2013-05-24
EN00356 | 3957 | 2018-10-24 | Good Energy (previously nPower Renewables) | Hampole Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Land Near Hampole Wood Hampole Doncaster | South Yorkshire | Yorkshire and Humber | England |  | 449430 | 409145 | Doncaster Metropolitan Borough Council | 08/02695/FULA | [5 empty] | 2008-09-09 | [6 empty] | 2009-12-17 |  |  |  |  | 2013-06-17 | 2014-03-31
EN00363 | 3958 | 2013-04-04 | Ventient (formerly Infinis) | Blackstone Edge | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Blackstone Edge, Penistone | South Yorkshire | Yorkshire and Humber | England |  | 419565 | 405226 | Barnsley Council | 2008/0171 | [5 empty] | 2006-11-01 | [6 empty] | 2009-05-26 |  |  |  |  | 2012-07-01 | 2013-03-01
EN00397 | 3959 | 2012-05-03 | Airtricity Developments | Muirpark | Wind Onshore |  |  | 33 | n/a |  |  |  | 3 | 11 |  | n/a | Planning Permission Refused | Application Refused | Muirpark Farm, Stirling | Stirling | Scotland | Scotland |  | 273900 | 687800 | Stirling Council | 09/00170/FULL | [5 empty] | 2009-03-01 |  | 2012-05-03
EN00401 | 3960 | 2013-05-01 | Falck Renewables/RDC | Nigg Hill | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | Nigg Hill , Nigg , Rosshire , Highlands | Highland | Scotland | Scotland |  | 283320 | 872675 | Highland Council | 08/00066/FULRC | [5 empty] | 2008-01-24 |  | 2013-01-28
EN00410 | 3961 | 2016-12-04 | Energia Renewables | Glenbuck | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Glenbuck, Dunloy | Co. Antrim | Northern Ireland | Northern Ireland |  | 118000 | 577300 | Northern Ireland Planning Service | D/2005/0628/F | [5 empty] | 2005-06-06 | [6 empty] | 2007-04-22 |  |  |  |  | 2016-05-26 | 2016-12-22
EN00411 | 3962 | 2017-12-15 | Energia | Glenbuck II | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 3 | 5 |  | n/a | Operational | Operational | Glenbuck | Co. Antrim | Northern Ireland | Northern Ireland |  | 118000 | 577300 | Northern Ireland Planning Service | D/2006/0599/F | [5 empty] | 2006-11-01 | [6 empty] | 2011-06-27 |  |  |  |  | 2016-04-01 | 2017-03-01
EN00413 | 3963 | 2012-03-29 | Banks Renewables | Marr Windfarm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Marr, South Yorkshire | South Yorkshire | Yorkshire and Humber | England |  | 450491 | 404311 | Doncaster Metropolitan Borough Council | 07/00445/FULA | [5 empty] | 2006-12-20 | [6 empty] | 2007-07-17 |  |  |  |  | 2011-03-01 | 2012-01-18
EN00414 | 3964 | 2013-11-26 | TNEI Services Ltd | Nissan Motors Plant Extn | Wind Onshore |  |  | 1.98 | n/a |  |  |  | 0.6 | 3 |  | n/a | Operational | Operational | Nissan Motors Plant, Sunderland, Tyne and Wear | Tyne and Wear | North East | England |  | 433385 | 557810 | Sunderland City Council | 07/02462/FUL | [5 empty] | 2007-06-01 | [6 empty] | 2007-07-31 | [5 empty] | 2008-04-01
EN00420 | 3965 | 2012-09-20 | Wind Power Renewables | Potash Farm | Wind Onshore |  |  | 6.6 | n/a |  |  |  | 3.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land adjacent Potash Farm, Potash Lane, Wyverstone | Suffolk | Eastern | England |  | 602390 | 268485 | Mid Suffolk District Council | 1826/09 | [5 empty] | 2009-07-21 |  | 2009-10-20
EN00425 | 3966 | 2013-10-04 | Bernard Matthews | Bernard Matthews Wind Farm | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Scalesbrook Lane, Holton, Halesworth, Suffolk, IP19 8NJ | Suffolk | Eastern | England |  | 640495 | 280140 | Waveney District Council | DC/09/0491/FUL | [5 empty] | 2009-05-29 | 2010-02-17
EN00436 | 3967 | 2011-11-28 | Tegni Cymru | Aston Grange Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Appeal Refused | Application Refused | Aston Grange Farm, Acton Bridge , Cheshire | Cheshire | North West | England |  | 356320 | 377420 | Cheshire West and Chester Council | 05-1059-fum | V/07/00025/REF |  |  |  |  | 2005-06-20 |  | 2006-10-11 |  |  | 2008-11-05
EN00445 | 3968 | 2012-05-09 | Infinis, previously Broadview Energy | Hill of Fiddes | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Hill of Fiddes Udny Station Cultercullen | Grampian | Scotland | Scotland |  | 393495 | 824485 | Aberdeenshire Council | APP/2007/3578 | [5 empty] | 2007-09-03 | [6 empty] | 2008-04-01 |  |  |  |  | 2009-07-01 | 2010-02-20
EN00459 | 3969 | 2013-08-16 | TCI Renewables | Dunmore | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Operational | Operational | Town land of Dunmore approximately eight kilometres north east of Limavady, County Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 88015 | 585846 | Northern Ireland Planning Service | [6 empty] | 2007-12-12 |  | 2009-04-24 |  |  |  | 2010-10-29 | 2010-10-29 | [5 empty] | 2013-04-25
EN00477 | 3971 | 2015-01-05 | Greencoat UK Wind | Cotton Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Operational | Operational | Land between Graveley, Offord Darcy and Great Paxton | Cambridgeshire | Eastern | England |  | 523270 | 264130 | Huntingdonshire District Council | 0802296FUL | 0900067REFUSL |  |  |  |  | 2008-08-04 |  | 2009-11-17 |  |  |  | 2010-12-14 | 2010-12-14 |  |  |  |  | 2012-05-01 | 2013-03-31
EN00491b | 3972 | 2013-06-25 | Flimby Wind Energy Ltd | Land at Flimby Hall Farm (resubmission) | Wind Onshore |  |  | 6.15 | n/a |  |  |  | 2.05 | 3 |  | n/a | Operational | Operational | Flimby, Maryport, Cumbria | Cumbria | North West | England |  | 302500 | 533500 | Allerdale Borough Council | 2/2009/0418 | APP/G0908/A/09/2118993/NWF |  |  |  |  | 2009-06-09 |  | 2009-12-08 |  |  |  | 2010-06-18 | 2010-06-18 |  |  |  |  | 2012-04-01 | 2013-06-14
EN00492 | 3973 | 2012-12-06 | Burton Wold Wind Farm Extension Ltd | Burton Wold Wind Farm Extension | Wind Onshore |  |  | 16.1 | n/a |  |  |  | 2.3 | 7 |  | n/a | Abandoned | Abandoned | Felaw Maltings | Northamptonshire | East Midlands | England |  | 492500 | 274500 | Kettering Borough Council | KET/2007/1033 | [5 empty] | 2007-11-23 | [6 empty] | 2008-03-11
EN00508 | 3974 | 2014-01-21 | Acciona Energy | Dulais Valley | Wind Onshore |  |  | 13.5 | n/a |  |  |  | 1.5 | 9 |  | n/a | Planning Permission Refused | Application Refused | Farmland based at Hirfynydd, which is situated east of Crynant and south of Seven Sisters | West Glamorgan | Wales | Wales |  | 282243 | 205558 | Neath Port Talbot County Borough Council | P2008/0024 | [5 empty] | 2007-06-01 |  | 2013-11-12
EN00510 | 3975 | 2015-12-17 | AGR Renewables | Derwydd Bach Wind Farm | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Abandoned | Abandoned | Melin-Y-Wig, Corwe, Denbighshire | Clwyd | Wales | Wales |  | 302996 | 349751 | Denbighshire County Council | 04/2007/0964 | [5 empty] | 2007-07-20 | [6 empty] | 2011-07-21
EN00513 | 3976 | 2013-11-01 | Scottish Power Renewables | Carland Cross Wind Farm Repowering | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Operational | Operational | Carland Cross, Mitchell, Truro | Cornwall | South West | England |  | 184500 | 54500 | Cornwall Council | EA28/2038/08/B | [5 empty] | 2008-11-24 |  | 2009-03-19 |  |  |  | 2010-01-20 | 2010-01-20 |  |  |  |  | 2013-01-23 | 2013-10-30
EN00520 | 3977 | 2013-05-08 | Enertrag UK | Tivetshall St Mary Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Wind Farm at Land to the west of New Road, Tivetshall St Mary, Norfolk | Norfolk | Eastern | England |  | 616648 | 285618 | South Norfolk Council | 2010/0861 | [5 empty] | 2010-03-02 | 2013-03-04
EN00521 | 3978 | 2015-01-05 | Greencoat UK Wind | Yelvertoft Wind Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Land Adjacent Glebe Farm, Hillmorton Lane, Yelvertoft (Access Off Rugby Road, Crick), Northamptonshire | Northamptonshire | East Midlands | England |  | 457887 | 275532 | Daventry District Council | DA/2009/0350 | [5 empty] | 2009-05-15 |  | 2009-10-25 |  |  |  | 2010-07-20 | 2010-07-20 |  |  |  |  | 2012-06-01 | 2013-07-11
EN00527 | 3979 | 2013-02-22 | Cornwall Light and Power | Orchard End | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Abandoned | Abandoned | land at Orchard End, near Pilling, Eagland Hill, Preston | Lancashire | North West | England |  | 343216 | 445233 | Wyre Borough Council | 08/00204 | [5 empty] | 2008-03-01 |  | 2008-05-07 |  |  |  | 2010-12-16 | 2010-12-16
EN00532 | 3980 | 2013-02-25 | Eco2 /GreenCAT | Mains of Hatton | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Kirktown of Auchterless Aberdeenshire | Grampian | Scotland | Scotland |  | 396115 | 858370 | Aberdeenshire Council | APP/2006/4452 | [5 empty] | 2006-11-16 | [6 empty] | 2007-09-19 |  |  |  |  | 2011-11-01 | 2012-03-20
EN00541 | 3981 | 2013-04-22 | Scottish Power Renewables | Whitelee Windfarm Extension Phase 1 | Wind Onshore |  |  | 108 | n/a |  |  |  | 3 | 36 |  | n/a | Operational | Operational | Eaglesham Moor, to the south of Glasgow | Strathclyde | Scotland | Scotland |  | 256300 | 645000 | Scottish Government (S36) | [6 empty] | 2008-04-01 | [6 empty] | 2009-05-20 |  |  |  |  | 2010-12-01 | 2012-10-31
EN00549 | 3982 | 2017-07-04 | Scottish Equity Partners | Tilbury Docks | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Operational | Operational | Installed from the Dock entrance along to the GradeII listed Cruise Terminal, Tilbury Docks, Tilbury | Essex | Eastern | England |  | 562450 | 175735 | Thurrock Council | 07/01328/TTGFUL | [5 empty] | 2007-12-20 | [6 empty] | 2008-05-13 |  |  |  |  | 2012-09-28 | 2013-03-25
EN00552 | 3983 | 2020-06-25 | Scottish Power (formerly CeltPower Ltd/Eurus Energy) | Llandinam Windfarm Repowering and Extension | Wind Onshore |  |  | 102 | n/a |  |  |  | 3 | 34 |  | n/a | Planning Permission Granted | Awaiting Construction | 10km south of Newtown, | Powys | Wales | Wales |  | 303400 | 284070 | DECC (S36) | [6 empty] | 2008-05-08 | [6 empty] | 2015-09-07
EN00570 | 3984 | 2012-11-29 | Broadview Energy | Seamer Windfarm - Stockton on Tees | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Between the villages of Hilton and Seamer on the Stockton-on-Tees and North Yorkshire boundaries. | County Durham | North East | England |  | 448125 | 511235 | Stockton on Tees Borough Council | 09/0736/EIS | [5 empty] | 2009-03-27 | [6 empty] | 2009-08-25 |  |  |  |  | 2012-04-01 | 2012-11-01
EN00571 | 3985 | 2013-01-24 | REG Windpower (previously Cornwall Light & Power) | South Sharpley Wind Farm (Revised) | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | South Sharpley Farm, near Seaham, County Durham | Durham | North East | England |  | 438490 | 549675 | Durham County Council | PLAN/2008/0355 | [5 empty] | 2008-05-01 |  | 2009-12-24 |  |  |  | 2011-04-10 | 2011-04-10 |  |  |  |  | 2012-06-18 | 2013-01-23
EN00586 | 3986 | 2013-05-20 | Banks Renewables | Armistead Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | Land to the east of Crosslands Farm, near Old Hutton, Kendal South Lakeland, LA6 2QJ | Cumbria | North West | England |  | 358500 | 486900 | South Lakeland District Council | SL/2008/0318 | APP/M0933/A/08/2090274 |  |  |  |  | 2008-03-25 |  | 2008-11-10 |  |  |  | 2010-07-15 | 2010-07-15 |  |  |  |  | 2012-03-01 | 2013-02-11
EN00604 | 3987 | 2013-06-03 | Energiekontor UK | Withernwick | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Operational | Operational | Land North And North East Homer House Aldbrough Road Withernwick East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 520325 | 440375 | East Riding of Yorkshire Council | 08/01964/STPLFE | 08/00213/REFUSE |  |  |  |  | 2008-04-04 |  | 2008-09-02 | [9 empty] | 2012-04-01 | 2013-03-19
EN00605 | 3988 | 2016-06-16 | Urras Oighreachd Ghabhsainn | Loch Sminig Wind Project | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Operational | Operational | Either side of the road between Baile an Truiseil and Upper Barvas, Stornoway, Isle of Lewis, HS2 0QX | Western Isles | Scotland | Scotland |  | 137480 | 952680 | Comhairle nan Eilean Siar Council | 08/00407/PPD | [5 empty] | 2008-08-29 | [6 empty] | 2009-05-06 |  |  |  |  | 2013-06-03 | 2015-09-15
EN00611 | 3989 | 2020-01-02 | Innogy | Carnedd Wen Wind Farm | Wind Onshore |  |  | 150 | n/a |  |  |  | 3 | 50 |  | n/a | Planning Application Submitted | Application Submitted | Llanbrynmair Forest TAN 8 Strategic Search Area B | Powys | Wales | Wales |  | 293295 | 308953 | DECC (S36) |  |  |  |  | 42368 |  | 2008-12-11
EN00617 | 3990 | 2017-04-19 | Asda | ASDA Distribution Centre | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Expired | Planning Permission Expired | ASDA Distribution Centre Falkirk | Falkirk | Scotland | Scotland |  | 289760 | 681885 | Falkirk Council | P/07/0084/FUL - P/08/0511/FUL | [5 empty] | 2007-11-28 | [6 empty] | 2009-03-04 |  |  |  | 2017-01-01
EN00624 | 3991 | 2015-09-14 | Fferm Wynt Llaithddu Cyf | Fferm Wynt Llaithddu Cyf | Wind Onshore |  |  | 66.7 | n/a |  |  |  | 2.3 | 29 |  | n/a | Planning Permission Refused | Application Refused | Llaithddu, Powys | Powys | Wales | Wales |  | 304160 | 279920 | DECC (S36) | [6 empty] | 2008-05-07 |  | 2015-09-07
EN00636 | 3992 | 2014-01-20 | Aeolian Holderness Ltd | Burton Pidsea (Wadworth Hill) Wind Farm | Wind Onshore |  |  | 10.2 | n/a |  |  |  | 3.4 | 3 |  | n/a | Operational | Operational | Land North East Of Wadworth Hill House Greens Lane Burton Pidsea East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 524497 | 429743 | East Riding of Yorkshire Council | 08/02928/STPLFE | [5 empty] | 2008-05-29 | [6 empty] | 2009-09-03 |  |  |  |  | 2013-07-05 | 2014-01-10
EN00641 | 3993 | 2012-11-16 | Yorkshire Windpower | Ovenden Moor (Repower) | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Withens Road, Wainstalls, Halifax, West Yorks. HX2 7TZ | West Yorkshire | Yorkshire and Humber | England |  | 404000 | 430500 | Calderdale Metropolitan Borough Council | 09/00073/WDF | [5 empty] | 2009-03-25 | 2012-04-23
H0074 | 3994 | 2015-07-01 | Formartine | Hillhead of Turnerhall | Wind Onshore |  |  | 3 | n/a |  |  |  | 1.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land West of Hillhead of Turnerhall, Auchnagatt, Ellon | Grampian | Scotland | Scotland |  | 395137 | 834738 | Aberdeenshire Council | APP/2013/1562 | [5 empty] | 2013-06-27 |  | 2015-05-28
IF1034 | 3995 | 2014-04-01 | Strathdee Properties | Netherton Of Windyhills (extension) | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Keith, Grampian | Grampian | Scotland | Scotland | AB55 6NL | 349243 | 856794 | Moray Council | 12/01707/APP | [5 empty] | 2012-10-04 |  | 2014-02-26
IF1125 | 3996 | 2014-11-25 | RWE npower | River Valley Wind farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Secretary of State - Refusal | Application Refused | Land North West Of Welham Bridge West Howden Road Holme Upon Spalding Moor East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 478022 | 435199 | East Riding of Yorkshire Council | 12/04561/STPLFE | APP/E2001/A/13/2207817 |  |  |  |  | 2012-11-07 |  | 2013-08-13 | 2013-10-13 |  |  |  |  | 2013-12-04 | 2014-10-15
IF1136 | 3997 | 2016-11-30 | AGR Group | Great House Farm | Wind Onshore |  |  | 3 | n/a |  |  |  | 1.5 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Near Great House Farm, Undy, Usk, Gwent | Gwent | Wales | Wales | NP26 3EN | 345084 | 186873 | Monmouthshire County Council | DC/2012/00931 | [5 empty] | 2012-10-31 | 2016-11-17
IF1150 | 3998 | 2013-11-20 | Kelda Water Services | Gorpley Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Permission Refused | Application Refused | Land South West Of Gorpley Reservoir, Bacup Road, Todmorden | West Yorkshire | Yorkshire and Humber | England |  | 390530 | 422527 | Calderdale Metropolitan Borough Council | 12/01355/WDF | [5 empty] | 2012-11-09 |  | 2013-02-08
IF1159 | 3999 | 2014-03-31 | Willowind Developments | Corwar Wind Farm | Wind Onshore |  |  | 16.4 | n/a |  |  |  | 2.05 | 8 |  | n/a | Appeal Refused | Application Refused | Proposed Wind Farm A714 Barrhill - East To Council Boundary East Of Barrhill Barrhill South Ayrshire | Strathclyde | Scotland | Scotland |  | 229012 | 580345 | South Ayrshire Council | 12/01384/APP | 13/00018/REFUSA |  |  |  |  | 2012-12-10 |  | 2013-08-30 |  |  | 2014-02-19
IF1163 | 4000 | 2014-02-20 | Willowind Developments | Calla Wind Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Planning Permission Refused | Application Refused | Carnwath, Lanark, Strathclyde | Strathclyde | Scotland | Scotland | ML11 8LH | 298295 | 648984 | South Lanarkshire Council | CL/12/0535 | [5 empty] | 2012-12-06 |  | 2013-12-18
IF1178 | 4001 | 2014-02-07 | Gamesa Energy | Harelaw Renewable Energy Park (Resubmission) | Wind Onshore |  |  | 117 | n/a |  |  |  | 3 | 39 |  | n/a | Planning Permission Refused | Application Refused | Harelaw, East Renfrewshire | Strathclyde | Scotland | Scotland |  | 246810 | 654150 | Scottish Government (S36) | [6 empty] | 2009-05-19 |  | 2013-09-27
IF1270 | 4002 | 2015-06-01 | Airvolution Energy | Shotts wind farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 6 | 131 | n/a | Appeal Refused | Application Refused | West Benhar Road, Eastfield, Harthill Shotts, North Lanarkshire | Strathclyde | Scotland | Scotland | ML7 5TG | 289269 | 662272 | North Lanarkshire Council | 13/00072/FUL | [5 empty] | 2013-02-07 |  | 2014-05-23 | 2014-09-05 |  | 2015-05-22
IF1375 | 4003 | 2020-01-29 | Muirden Energy | Cogle Moss Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 | 100 | n/a | Appeal Granted | Awaiting Construction | Land 477M NE Of Blackpark Watten KW1 5UL | Highland | Scotland | Scotland |  | 327494 | 955985 | Highland Council | 15/02769/FUL | PPA-270-2166 |  |  |  |  | 2015-08-11 |  | 2017-01-10 | 2017-02-08 |  |  | 2017-08-29 | 2017-08-29
IF1376 | 4004 | 2014-06-06 | Orkney Renewable Energy | Rysa Wind Energy Project | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Rysa Lodge, Lyness, Stromness, Orkney, KW16 3NU | Orkney Islands | Scotland | Scotland |  | 330035 | 996335 | Orkney Islands Council | 13/072/TPP | [5 empty] | 2013-02-22 | 2014-04-30
IF1415 | 4005 | 2020-01-20 | Orkney Sustainable Energy | Herscha Wind energy Project (Extension) | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Planning Permission Granted | Awaiting Construction | Herscha HIll (Land to North of) Newland Cottage Auchenblae Laurencekirk | Grampian | Scotland | Scotland |  | 372896 | 780078 | Aberdeenshire Council | APP/2013/0587 | [5 empty] | 2013-03-04 | [6 empty] | 2015-05-20 |  |  |  | 2021-03-09
N00031W | 4006 | 2013-07-04 | E.ON UK | Camster | Wind Onshore |  |  | 50 | n/a |  |  |  | 2 | 25 |  | n/a | Operational | Operational | Lower Camster Lybster Caithness | Highland | Scotland | Scotland |  | 325800 | 947400 | Scottish Government (S36) | [6 empty] | 2005-01-05 | [6 empty] | 2009-01-13 |  |  |  |  | 2012-01-01 | 2013-02-09
N00036W | 4007 | 2012-12-06 | Renewable Energy Generation Limited - previously E.on | St. Breock Re-Power | Wind Onshore |  |  | 10.395 | n/a |  |  |  | 0.94 | 11 |  | n/a | Abandoned | Abandoned | St. Breock North Cornwall Cornwall | Cornwall | South West | England |  | 200000 | 70000 | Cornwall Council | 2002-1897 | [5 empty] | 2002-06-15 | [6 empty] | 2003-01-30
N00075W | 4008 | 2013-11-25 | Longearth Ltd/ Farm Energy | Bu Farm | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Operational | Operational | Rothiesholm, Bu Farm, Stronsay, Orkney | Orkney Islands | Scotland | Scotland |  | 362283 | 1023560 | Orkney Islands Council | [19 empty] | 2002-05-10
N00107W | 4009 | 2013-10-08 | Scottish and Southern Energy (SSE) | Drumderg | Wind Onshore |  |  | 36.8 | n/a |  |  |  | 2.3 | 16 |  | n/a | Operational | Operational | Drumderg Hill Near Alyth Perth | Tayside | Scotland | Scotland |  | 324500 | 748500 | Perth and Kinross Council | 03/01917/FUL | P/PPA/340/459 |  |  |  |  | 2003-11-06 |  | 2005-02-11 | [10 empty] | 2008-11-09
N00138W | 4010 | 2005-08-26 | Private Developer | Beech Farm | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | Beech Farm , Tavistock , West Devon | Devon | South West | England |  | 248500 | 74500 | West Devon Borough Council | 2934/2002/TAV | APP/Q1153/A/04/1170234 |  |  |  |  | 2002-04-16 |  | 2003-03-03
N00139W | 4011 | 2018-06-01 | Scottish and Southern Energy (SSE)/ Greencoat UK Wind | Clyde Wind Farm | Wind Onshore |  |  | 350 | n/a |  |  |  | 2.3 | 152 |  | n/a | Operational | Operational | Clyde Wind farm, Lowther Hills, between Crawford and Nether Howecleuch, NW of Lockerbie | Strathclyde | Scotland | Scotland |  | 302500 | 617500 | Scottish Government (S36) | [6 empty] | 2004-10-01 | [6 empty] | 2008-07-21 | [5 empty] | 2012-10-01
N00140W | 4012 | 2012-07-04 | Private Developer | Steadfold Lane | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Castle Cement Works Steadfold Lane Ketton | Northamptonshire | East Midlands | England |  | 500000 | 305000 | East Northamptonshire Council | FUL/2003/0357 | [5 empty] | 2003-05-07 | 2004-06-22
N00141W | 4013 | 2012-12-04 | RWE npower | Novar Wind Farm (Extension) | Wind Onshore |  |  | 36.8 | n/a |  |  |  | 2.3 | 16 |  | n/a | Operational | Operational | Novar Estate Evanton Ross-shire | Highland | Scotland | Scotland |  | 255500 | 871500 | Highland Council | 03/00426/FULRC | [5 empty] | 2003-05-14 | [6 empty] | 2005-06-20 |  |  |  |  | 2010-08-01 | 2012-09-17
N00164W | 4014 | 2020-06-04 | Renewable Energy Systems (RES) | Hill of Towie (Drummuir) | Wind Onshore |  |  | 48 | n/a |  |  |  | 2.3 | 21 |  | n/a | Operational | Operational | Hill of Towie, Knockan and McHattie's Cairn, Drummuir, Keith, Banffshire, Moray | Grampian | Scotland | Scotland |  | 320000 | 860000 | Moray Council | 02/02099/EIA | [5 empty] | 2002-11-15 |  | 2003-11-11 | [9 empty] | 2010-09-01 | 2012-06-01
N00168W | 4015 | 2016-10-26 | Scottish Power Renewables | Ewe Hill | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Near Langham and Lockerbie Dumfries | Dumfries and Galloway | Scotland | Scotland |  | 315000 | 580000 | Scottish Government (S36) | IEC3/107 | [5 empty] | 2004-04-07 | [6 empty] | 2010-06-07 |  |  |  |  | 2015-09-10 | 2016-05-30
N00187W | 4016 | 2012-12-06 | Private Developer | Over Enoch Farm | Wind Onshore |  |  | 6.5 | n/a |  |  |  | 1.3 | 5 |  | n/a | Abandoned | Abandoned | Over Enoch Farm Eaglesham East Renfrewshire | Strathclyde | Scotland | Scotland |  | 258200 | 650100 | East Renfrewshire Council | 2003/0350 | [5 empty] | 2003-05-08 | [6 empty] | 2004-09-02
N00188W | 4017 | 2011-12-02 | Private Developer | Ardoch Farm (East Renfrewshire) | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Abandoned | Abandoned | Ardoch Farm, Eaglesham, East Renfrewshire | Strathclyde | Scotland | Scotland | G76 0PL | 258500 | 649500 | East Renfrewshire Council | 2003/0022/TP | [5 empty] | 2003-01-15 | [6 empty] | 2004-09-02
N00209W | 4018 | 2011-12-06 | Cornwall Light and Power | French Farm (Revised application) | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | South French Drove, East of Scolding Drove, Ride Croft | Cambridgeshire | Eastern | England |  | 532953 | 307779 | Peterborough City Council | 04/00902/FUL | [5 empty] | 2004-06-08 | 2008-12-10
N00210W | 4019 | 2014-03-04 | Npower Renewables | Middlemoor | Wind Onshore |  |  | 54 | n/a |  |  |  | 3 | 18 |  | n/a | Operational | Operational | North Charlton Alnwick Northumberland | Northumberland | North East | England |  | 414765 | 622786 | DECC (S36) | ELEC/2005/0004 | [5 empty] | 2005-12-07 | [6 empty] | 2008-08-07 |  |  |  |  | 2012-03-01 | 2013-09-30
N00219W | 4020 | 2013-06-17 | Eurus Energy | Glenkirk | Wind Onshore |  |  | 93 | n/a |  |  |  | 3 | 31 |  | n/a | Planning Permission Refused | Application Refused | Glenkirk, Tomatin | Highland | Scotland | Scotland |  | 286450 | 831550 | Scottish Government (S36) | [6 empty] | 2005-09-26 |  | 2013-06-14
N00225W | 4021 | 2013-05-02 | Baillie Windfarm Ltd | Baillie Wind Farm | Wind Onshore |  |  | 52.5 | n/a |  |  |  | 2.5 | 21 |  | n/a | Operational | Operational | Bardnaheigh, Westfield, Thurso | Highland | Scotland | Scotland |  | 302550 | 965650 | Scottish Government (S36) | 04/00342/S36CA | [5 empty] | 2004-07-13 | [6 empty] | 2010-01-12 |  |  |  |  | 2011-07-01 | 2013-03-29
N00230W | 4022 | 2013-10-08 | REG Windpower (previously Cornwall Light and Power) | Braich Ddu | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Operational | Operational | Braich Ddu, Glanrafon Y Bala, Gwynedd | Gwynedd | Wales | Wales |  | 267500 | 301500 | Gwynedd Council | C04M/0038/04/MW | [5 empty] | 2004-03-11 | [6 empty] | 2004-09-13 | [5 empty] | 2007-08-31
N00243W | 4023 | 2017-12-04 | Greencoat UK Wind | Drone Hill | Wind Onshore |  |  | 28.6 | n/a |  |  |  | 1.3 | 22 |  | n/a | Operational | Operational | Coldingham East Berwickshire | Borders | Scotland | Scotland |  | 383719 | 667227 | Scottish Borders Council | 05/00425/FUL | [5 empty] | 2005-03-04 |  | 2007-11-12 | [9 empty] | 2011-04-01 | 2012-09-01
N00250W | 4024 | 2012-01-25 | Scottish and Southern Energy (SSE) | Tangy Wind Farm Extension/Tangy 2 | Wind Onshore |  |  | 5.95 | n/a |  |  |  | 0.85 | 7 |  | n/a | Operational | Operational | Kilkenzie , Campbelltown | Strathclyde | Scotland | Scotland |  | 177000 | 626200 | Argyll and Bute Council | 0401291/DET | [5 empty] | 2004-07-01 | [6 empty] | 2005-09-01 |  |  |  |  | 2006-05-01 | 2011-06-17
N00259W | 4025 | 2012-08-29 | Scottish and Southern Energy (SSE) | Pairc Windfarm | Wind Onshore |  |  | 94 | n/a |  |  |  | 3.6 | 26 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Pairc Isle of Lewis | Western Isles | Scotland | Scotland |  | 135566 | 915943 | Scottish Government (S36) | [7 empty] | 2012-08-29
N00263W | 4026 | 2017-10-30 | Vattenfall | Ray Wind Farm | Wind Onshore |  |  | 54.4 | n/a |  |  |  | 3.5 | 16 |  | n/a | Operational | Operational | Kirkwhelpington, Newcastle-upon-Tyne, Tyne and Wear | Northumberland | North East | England | NE19 2 | 395550 | 587550 | DECC (S36) | 06/00023/CPC | [5 empty] | 2005-12-12 | [6 empty] | 2010-11-11 |  |  |  |  | 2015-07-01 | 2017-02-05
N00270W | 4027 | 2013-12-24 | Scottish and Southern Energy (SSE) | Calliachar | Wind Onshore |  |  | 32.2 | n/a |  |  |  | 2.3 | 14 |  | n/a | Operational | Operational | Nr Aberfeldy, Amulree | Tayside | Scotland | Scotland |  | 285000 | 750000 | Perth and Kinross Council | S36 | [5 empty] | 2004-02-16 |  | 2007-09-11 | [9 empty] | 2012-06-01 | 2013-09-30
N00272W | 4028 | 2012-02-29 | Greenpower (Griffin) Ltd | Griffin Wind farm | Wind Onshore |  |  | 156 | n/a |  |  |  | 3 | 52 |  | n/a | Operational | Operational | Griffin Forest | Tayside | Scotland | Scotland |  | 293600 | 744600 | Scottish Government (S36) | [6 empty] | 2004-04-27 | [6 empty] | 2008-01-31 |  |  |  |  | 2010-07-01 | 2012-02-28
N00276W | 4029 | 2012-07-04 | REG Windpower (previously Cornwall Light and Power) | High Pow Farm (Resubmission) | Wind Onshore |  |  | 3.9 | n/a |  |  |  | 1.3 | 3 |  | n/a | Operational | Operational | High Pow Farm Boltons Low Houses Nr. Wigton Cumbria | Cumbria | North West | England |  | 323500 | 544500 | Allerdale Borough Council | 2/2004/0944 | APP/G0908/A/04/1172183 |  |  |  |  | 2004-07-16 |  | 2004-10-07 | [10 empty] | 2007-03-15
N00277W | 4030 | 2013-11-12 | Red Group | Hartwood | Wind Onshore |  |  | 30 | n/a |  |  |  | 2 | 15 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Nr Salsburg | Strathclyde | Scotland | Scotland |  | 283440 | 659680 | North Lanarkshire Council | 06/01001/FUL | [5 empty] | 2006-06-15 | 2013-09-06
N00278W | 4031 | 2014-03-06 | K E Projects AF | St. Johns Hill | Wind Onshore |  |  | 15.75 | n/a |  |  |  | 2.8 | 9 |  | n/a | Operational | Operational | Chapel of Barras nr Kinneff, South of Stonehaven | Grampian | Scotland | Scotland |  | 383500 | 777500 | Aberdeenshire Council | 2004/4666 | [5 empty] | 2004-12-22 |  | 2006-10-11 |  |  |  | 2007-11-26 | 2007-11-26 | [5 empty] | 2013-04-01
N00279W | 4032 | 2018-05-22 | Blue Energy | Blackcraig | Wind Onshore |  |  | 53 | n/a |  |  |  | 3 | 23 |  | n/a | Operational | Operational | Blackcraig Hill, 6km NE of Balmaclellan | Dumfries and Galloway | Scotland | Scotland |  | 270500 | 582500 | Scottish Government (S36) | 05/n/2005 | [5 empty] | 2005-09-30 | [6 empty] | 2011-03-22 |  |  |  |  | 2016-01-10 | 2018-03-02
N00293W | 4033 | 2013-04-19 | Devon Wind Power Ltd | Fullabrook Down Wind Farm | Wind Onshore |  |  | 66 | n/a |  |  |  | 3 | 22 |  | n/a | Operational | Operational | Fullabrook Down, Crackaway, Barton | Devon | South West | England |  | 253055 | 141846 | DECC (S36) | 38622 | [5 empty] | 2004-10-18 | [6 empty] | 2007-10-10 |  |  |  |  | 2008-07-01 | 2012-01-24
N00300W | 4034 | 2020-04-30 | Renewables Infrastructure Group | Little Raith Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.8 | 9 |  | n/a | Operational | Operational | South of A92 Nr Loch Gelly | Fife | Scotland | Scotland |  | 322245 | 692552 | Fife Council | 04/04266/WEIA | [5 empty] | 2004-12-02 | [6 empty] | 2007-03-08 |  |  |  |  | 2011-09-01 | 2012-11-27
N00301W | 4035 | 2011-12-01 | A7 Energy | Dusty Drum | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Dusty Drum, Carmyllie, Arbroath, Angus | Tayside | Scotland | Scotland | DD11 2QS | 355050 | 741050 | Angus Council | 05/01061/FUL | [5 empty] | 2005-07-01 | 2007-12-19
N00303W | 4036 | 2015-01-09 | Scottish and Southern Energy (SSE) | Spurness Wind Farm | Wind Onshore |  |  | 11 | n/a |  |  |  | 2.75 | 4 |  | n/a | Decommissioned | Decommissioned | Gump of Spurness , Sanday , Orkney | Orkney Islands | Scotland | Scotland |  | 360450 | 1035550 | Orkney Islands Council | [6 empty] | 2002-09-01 | [6 empty] | 2003-01-01 | [5 empty] | 2004-12-01
N00311W | 4037 | 2014-05-20 | Chancerygate | Willow Lane Wind Turbines | Wind Onshore |  |  | 11.047 | n/a |  |  |  | 1.1 | 10 |  | n/a | Abandoned | Abandoned | 2-4 Willow Lane Industrial Estate Mitcham Junction Near Merton | Greater London | London | England |  | 528336 | 167552 | Merton London Borough Council | [6 empty] | 2004-06-30 | [6 empty] | 2004-08-15
N00319W | 4038 | 2015-10-21 | DeWind | DeWind Wind Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Expired | Planning Permission Expired | Nottingham Road, Loughborough | Leicestershire | East Midlands | England |  | 454062 | 320064 | Charnwood Borough Council | P/04/2084/2 | [5 empty] | 2004-06-24 | [6 empty] | 2004-09-16 |  |  |  | 2007-09-16
N00328W | 4039 | 2013-06-03 | Pennant Wind Energy Ventures (PWEV) | Pant y wal | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 | 115 | n/a | Operational | Operational | Mynydd Maesteg, Mynydd Pwlle yr Helog, Ogmore Vale, Rhondda Valley | Mid Glamorgan | Wales | Wales |  | 295886 | 191521 | Bridgend County Borough Council | P/06/417/FUL | [5 empty] | 2006-03-31 |  | 2006-04-26 |  |  |  | 2011-05-04 | 2011-05-04 |  |  |  |  | 2012-04-01 | 2013-06-01
N00329W | 4040 | 2012-06-14 | Spittal Hill Windfarm | Spittal Hill | Wind Onshore |  |  | 75 | n/a |  |  |  | 2.5 | 30 |  | n/a | Planning Permission Refused | Application Refused | Near Spittal, Caithness , ND 168 557 | Highland | Scotland | Scotland |  | 316800 | 955700 | Scottish Government (S36) | 07/00217/S36CA | [5 empty] | 2007-04-24 |  | 2012-06-13
N00354W | 4041 | 2019-01-02 | Greencoat (formerly Energia Renewables) | Crighshane | Wind Onshore |  |  | 32.2 | n/a |  |  |  | 2 | 14 |  | n/a | Operational | Operational | Crighshane, South of Ballymongan Road, Killeter, Castlederg | Co. Tyrone | Northern Ireland | Northern Ireland |  | 29021 | 542409 | Northern Ireland Planning Service | J/2005/0133/F | [5 empty] | 2004-12-01 | [6 empty] | 2007-06-25 |  |  |  |  | 2011-05-01 | 2012-06-30
N00357W | 4042 | 2013-11-06 | Northern Wind Power | Townlands of Carrickatane | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Operational | Operational | Townlands of Carrickatane, Castlemellan, Cullion, Gortmellan & Taboe Glebe (Co. Tyrone) and Tirkeeveny & Killymallaght (Co. Derry), accessing onto Gortmellon Road, Cullion, BT47 3TA | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 66757 | 567963 | Northern Ireland Planning Service | J/2005/0211/F | [5 empty] | 2005-02-11 | [6 empty] | 2009-03-19 |  |  |  |  | 2011-12-01 | 2013-03-21
N00364W | 4043 | 2013-06-12 | Dunbeath Wind Energy Ltd (Agents are West Coast Energy) | Dunbeath | Wind Onshore |  |  | 66 | n/a |  |  |  | 3 | 22 |  | n/a | Planning Permission Refused | Application Refused | Caithness | Highland | Scotland | Scotland |  | 311500 | 930500 | Scottish Government (S36) | [6 empty] | 2005-08-12 |  | 2013-06-07
N00369W | 4044 | 2014-12-18 | EDF/China General Nuclear Power Corporation | Green Rigg | Wind Onshore |  |  | 36 | n/a |  |  |  | 2 | 18 |  | n/a | Operational | Operational | Near the A68 and Sweethope Lough | Northumberland | North East | England |  | 392000 | 582000 | Northumberland County Council | 20060040 | [5 empty] | 2006-01-12 |  | 2008-01-15 |  |  |  | 2010-03-26 | 2010-03-26 |  |  |  |  | 2011-12-01 | 2012-11-28
N00372W | 4045 | 2012-08-07 | Natural Power | Shira Wind Farm | Wind Onshore |  |  | 79 | n/a |  |  |  | 2.2 | 36 |  | n/a | Planning Application Withdrawn | Application Withdrawn | South of Dalmally in Argyll and Bute | Strathclyde | Scotland | Scotland |  | 184050 | 686550 | Scottish Government (S36) | 06/00554/ELSA36 | [5 empty] | 2006-03-14 | 2012-02-23
N00379W | 4046 | 2014-09-19 | Drumdarragh Windfarm Ltd | Drumadarragh Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Appeal Refused | Application Refused | Drumadarragh Hill, Ballyclare, County Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 138777 | 550194 | Northern Ireland Planning Service | U/2005/0281/F | [5 empty] | 2005-05-19 |  | 2013-11-15 |  |  | 2014-08-18
N00381W | 4047 | 2019-01-02 | Greencoat (formerly Energia Renewables) | Church Hill | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Church Hill, Meenamullan Road, Killeter, Castlederg, and Magherakeel, Killeter, Castlederg, Co Tyrone. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 31711 | 543769 | Northern Ireland Planning Service | J/2005/0358/F | [5 empty] | 2005-04-06 | [6 empty] | 2007-04-26 |  |  |  |  | 2011-05-01 | 2012-06-01
N00382W | 4048 | 2011-11-29 | ESB | Crockagarran | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | Lands to the East of Whitebridge Road and South of Gleneeny Road, on lands at Crockagarron in the Townland of Gleneeny, Co Tyrone. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 75726 | 528798 | Northern Ireland Planning Service | K/2005/0537/F | [5 empty] | 2005-07-08 | [6 empty] | 2007-06-25 |  |  |  |  | 2009-11-01 | 2010-09-29
N00383W | 4049 | 2013-02-27 | Wind Prospect | Stacain | Wind Onshore |  |  | 48 | n/a |  |  |  | 3 | 14 |  | n/a | Appeal Refused | Application Refused | Near Inverary, to the north-east of SrÃ²n MÃ³r hydroelectric station, near Lochan Shira. | Strathclyde | Scotland | Scotland |  | 215500 | 722500 | Scottish Government (S36) | 05/00770/DET | [5 empty] | 2005-04-01 |  | 2005-12-10 |  |  | 2009-10-15
N00387W | 4050 | 2013-11-21 | CLP Envirogas | Skares Windfarm | Wind Onshore |  |  | 4 | n/a |  |  |  | 1 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | GARLAFF LANDFILL SITE SKARES CUMNOCK Ayrshire KA182RB | Strathclyde | Scotland | Scotland |  | 252500 | 617500 | East Ayrshire Council | 05/0594/FL | [5 empty] | 2005-06-03 | 2013-08-26
N00391W | 4051 | 2013-03-06 | E.ON UK | Rosehall Hill Forest Windfarm | Wind Onshore |  |  | 24.7 | n/a |  |  |  | 1.3 | 19 |  | n/a | Operational | Operational | Lairg, Highlands. IV27 4EU | Highland | Scotland | Scotland |  | 249550 | 903550 | Highland Council | 05/00429/FULSU | [5 empty] | 2005-11-30 | [6 empty] | 2006-09-30 |  |  |  |  | 2011-08-01 | 2013-02-28
N00401W | 4053 | 2015-06-17 | Energia Renewables | Thornog Windfarm | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Thornog, Meenadoan townland, Drumquin. Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 41160 | 537686 | Northern Ireland Planning Service | K/2005/1786/F | [5 empty] | 2005-09-08 | [6 empty] | 2008-03-01 |  |  |  |  | 2014-06-13 | 2014-09-22
N00402W | 4054 | 2017-11-27 | Scottish and Southern Energy (SSE) | Slieve Divena Phase 2 Wind Farm | Wind Onshore |  |  | 18.8 | n/a |  |  |  | 2.5 | 8 |  | n/a | Operational | Operational | Slieve Divena Wind Farm Phase II in the townlands of Altcloghfin, Altamuskin and Shantavny Irish, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 | 69602 | 524593 | Northern Ireland Planning Service | K/2005/1691/F | [5 empty] | 2005-09-13 | [6 empty] | 2007-06-06 |  |  |  | 2018-02-20 | 2016-05-30 | 2017-02-16
N00408W | 4055 | 2013-05-02 | I & H Brown Ltd | Bankend Rig | Wind Onshore |  |  | 14.3 | n/a |  |  |  | 1.3 | 11 |  | n/a | Operational | Operational | Near Dungavel Reservoir | Strathclyde | Scotland | Scotland |  | 265553 | 633692 | South Lanarkshire Council | EK/06/0311 | [5 empty] | 2006-06-16 | [6 empty] | 2011-06-16 |  |  |  |  | 2012-01-09 | 2013-03-27
N00419W | 4056 | 2013-10-08 | Mackies | Hill of Easterton Extension | Wind Onshore |  |  | 2 | n/a |  |  |  | 1 | 2 |  | n/a | Operational | Operational | Hill of Easterton, 1km North Of Mackies Ice Cream Dairy, Westertown, Rothienorman, Inverurie, AB51 8US | Grampian | Scotland | Scotland |  | 376449 | 831808 | Aberdeenshire Council | APP/2005/3308 | [5 empty] | 2005-09-28 | [6 empty] | 2007-07-18 | [5 empty] | 2007-07-31
N00425W | 4057 | 2016-11-30 | Blackrock Real Assets | Batsworthy Cross | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 | 103 | n/a | Operational | Operational | Batsworthy Cross , Creacombe , North Devon | Devon | South West | England |  | 281500 | 120500 | North Devon District Council | 43272 | A/11/2162070/NWF |  |  |  |  | 2006-11-18 |  | 2011-07-20 |  |  |  | 2012-10-22 | 2012-10-22 |  |  |  |  | 2016-01-18 | 2016-04-07
N00459W | 4058 | 2012-01-25 | Airtricity | Slieve Kirk | Wind Onshore |  |  | 27.6 | n/a |  |  |  | 2.3 | 12 |  | n/a | Operational | Operational | Lands bounded by Bigwood Road, Kildoag Road & Castlewarren Road, within the townlands of Lisdillon, Kildoag in Co Derry, Knockbrack, Gosheden, Lackagh, Ardground, Legagh in Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 61258 | 571215 | Northern Ireland Planning Service | A/2004/1130/F | [5 empty] | 2004-10-29 | [6 empty] | 2009-03-10 |  |  |  |  | 2011-04-01 | 2011-10-01
N00549W | 4059 | 2016-02-15 | EDF Energy Renewables | Fallago Rig | Wind Onshore |  |  | 144 | n/a |  |  |  | 3 | 48 |  | n/a | Operational | Operational | Lammermuir Hills | Borders | Scotland | Scotland |  | 357000 | 660000 | Scottish Government (S36) | [6 empty] | 2005-05-16 |  | 2007-06-06 |  |  |  | 2010-11-09 | 2010-11-09 |  |  |  |  | 2011-03-01 | 2013-03-31
N00555W | 4060 | 2013-09-02 | Scottish and Southern Energy (SSE) | Cathkin Braes Wind Farm (Castlemilk) | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Operational | Operational | Site At Cathkin Braes/ Cathkin Road Carmunnock Glasgow | Strathclyde | Scotland | Scotland |  | 261220 | 658203 | Glasgow City Council | [6 empty] | 2012-09-03 | [6 empty] | 2013-01-15 | [5 empty] | 2013-05-29
N00560W | 4061 | 2017-08-31 | ESB (Cambrian Renewable Energy Ltd / Betws Common Holdings Ltd) | Mynydd y Betws | Wind Onshore |  |  | 34.5 | n/a |  |  |  | 2.3 | 15 |  | n/a | Operational | Operational | Mynydd y Betws, Betws, Ammanford | Dyfed | Wales | Wales |  | 267000 | 210000 | Carmarthenshire County Council | E/10446 | [5 empty] | 2005-06-22 | [6 empty] | 2007-06-17 |  |  |  |  | 2012-01-01 | 2013-04-01
S0046W3 | 4062 | 2014-12-18 | Green Cat Renewables | Ark Hill | Wind Onshore |  |  | 6.4 | n/a |  |  |  | 0.8 | 8 |  | n/a | Operational | Operational | Chamberwells, Glamis, Tayside | Tayside | Scotland | Scotland |  | 335700 | 742600 | Angus Council | 03/00831/FUL | [5 empty] | 2003-07-07 | [6 empty] | 2006-06-15 |  |  |  |  | 2012-08-17 | 2013-03-29
S0049W3 | 4063 | 2013-06-03 | Arnish Electric Ltd / Farm Energy Ltd | Pentland Road Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Pentland Road, Isle of Lewis | Western Isles | Scotland | Scotland |  | 135500 | 938700 | Comhairle nan Eilean Siar Council | 02/00404/PPD | [5 empty] | 2002-09-30 | [6 empty] | 2004-09-06 |  |  |  |  | 2012-03-01 | 2013-03-28
A0255 | 4064 | 2015-08-18 | Vattenfall | Nant Bach Re-submission | Wind Onshore |  |  | 27.5 | n/a |  |  |  | 2.5 | 11 |  | n/a | Abandoned | Abandoned | Mwdwl Eithin near Llanfihangel Glyn Myfyr, Conwy | Gwynedd | Wales | Wales |  | 282500 | 368500 | Conwy County Borough Council | 0/35170 | [5 empty] | 2008-07-12 | [6 empty] | 2009-03-11
A0307 | 4065 | 2018-11-27 | Slieveglass wind farm (Energia) | Slieveglass | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Bullock Park, Drumquin, Co. Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 40796 | 540968 | Northern Ireland Planning Service | J/2008/0088 | 2012/A0053 |  |  |  |  | 2008-01-28 |  | 2012-04-30 |  |  |  | 2013-06-12 | 2013-06-12 |  |  |  | 2018-06-12 | 2017-09-01 | 2018-08-10
A0316 | 4066 | 2015-03-19 | Erne Concrete Pumping | Molly Mountain | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Operational | Operational | Land at Molly Mountain near Derrylin | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 32559 | 492702 | Northern Ireland Planning Service | L/2008/1113/F | [5 empty] | 2008-08-15 | [6 empty] | 2013-02-01 |  |  |  |  | 2014-03-30 | 2014-12-03
A0340 | 4067 | 2016-12-22 | RES/ Aviva | Turncole Wind Farm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2 | 7 |  | n/a | Operational | Operational | Turncole Farm, The Marshes, Southminster, Essex | Essex | Eastern | England | CM0 7JJ | 598482 | 198640 | Maldon District Council | 10/01070/FUL | APP/X1545/A/12/2174982 |  |  |  |  | 2011-06-30 |  | 2011-10-25 |  |  |  | 2014-02-14 | 2014-02-14 |  |  |  |  | 2015-10-31 | 2016-12-22
A0472 | 4068 | 2017-08-01 | Severn Trent Water | Derby Sewage Treatment Works | Wind Onshore |  |  | 5 | n/a |  |  |  | 3.4 | 2 |  | n/a | Operational | Operational | Megaloughton Lane, Spondon, Derby | Derbyshire | East Midlands | England |  | 439567 | 334685 | Derby City Council | 09/10/01144 | [5 empty] | 2010-10-12 | [6 empty] | 2012-10-23 |  |  |  |  | 2013-05-22 | 2014-05-15
AA171 | 4069 | 2017-07-31 | Octopus Investements/Blue Energy | Grange Resubmission | Wind Onshore |  |  | 12.3 | n/a |  |  |  | 2.05 | 6 |  | n/a | Operational | Operational | Grange Farmhouse, Land adjacent to, Flixborough | Humberside | Yorkshire and Humber | England |  | 486042 | 416496 | North Lincolnshire Council | WF/2010/1242 | [5 empty] | 2010-11-02 |  | 2011-04-06 |  |  |  | 2014-01-07 | 2014-01-07 |  |  |  |  | 2015-01-01 | 2015-12-15
AA220 | 4070 | 2017-03-31 | RWE Npower Renewables | Goole Fields ll Wind Farm | Wind Onshore |  |  | 34.85 | n/a |  |  |  | 2.05 | 17 |  | n/a | Operational | Operational | approximately 2km south of Old Goole, immediately to the west of the consented Goole Fields Wind Farm. | Humberside | Yorkshire and Humber | England |  | 473632 | 420610 | East Riding of Yorkshire Council | 11/05923/STPLFE | [5 empty] | 2012-01-06 | [6 empty] | 2014-05-22 |  |  |  |  | 2015-08-14 | 2016-11-14
AA242 | 4071 | 2014-06-11 | Airvolution Energy | Muircleugh Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Lauder, Scottish Borders | Borders | Scotland | Scotland |  | 349594 | 645544 | Scottish Borders Council | 10/01641/FUL | [5 empty] | 2010-11-30 | 2011-02-17
AA252 | 4072 | 2016-10-31 | Vento Ludens | Edintore Wind Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Operational | Operational | Edintore, Keith, Moray | Grampian | Scotland | Scotland | AB55 5PJ | 342422 | 846573 | Moray Council | 10/02092/EIA | 12/00010/REF |  |  |  |  | 2010-12-11 |  | 2011-12-14 |  |  |  | 2012-08-28 | 2012-08-28 |  |  |  |  | 2015-09-24 | 2016-10-31
AA353 | 4073 | 2019-07-02 | RPMI Railpen (formerly BayWa) | Tralorg Wind Farm | Wind Onshore |  |  | 20 | n/a |  |  | 20 | 2.5 | 8 |  | n/a | Under Construction | Under Construction | 2km to the east of Girvan | Strathclyde | Scotland | Scotland |  | 221728 | 598656 | South Ayrshire Council | 11/01569/APPM | 13/00014/REFUSA |  |  |  |  | 2011-02-10 |  | 2013-03-22 |  |  |  | 2014-02-21 | 2014-02-21 |  |  |  |  | 2017-02-14
AA472 | 4074 | 2014-06-23 | J G Shanks & Son Ltd | Shaw Park Wind Farm | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Appeal Refused | Application Refused | Land North West And West Of Allanshaws Farmhouse, Galashiels, Scottish Borders | Borders | Scotland | Scotland |  | 348058 | 644345 | Scottish Borders Council | 11/01175/FUL | 14/00002/REF |  |  |  |  | 2011-08-30 |  | 2013-10-08 |  |  | 2014-06-19
AA474 | 4075 | 2016-03-22 | Shetland Aerogenerators | Gremista Wind Farm | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Operational | Operational | Luggies Knowe, Gremista, Lerwick | Shetland | Scotland | Scotland |  | 446287 | 1145628 | Shetland Islands Council | 2011/224/PPF | [5 empty] | 2011-08-31 | [6 empty] | 2012-02-24 |  |  |  |  | 2015-07-15 | 2015-11-15
AA522 | 4076 | 2019-12-11 | TCI Renewables | Common Barn Wind Farm | Wind Onshore |  |  | 6.15 | n/a |  |  | 6.15 | 3 | 3 |  | n/a | Operational | Operational | Church Farm, Southoe, Huntingdonshire | Cambridgeshire | Eastern | England |  | 516918 | 265736 | Huntingdonshire District Council | 1200803FUL | 1200061NONDET |  |  |  |  | 2012-05-15 |  | 2012-12-05 |  |  |  | 2013-07-11 | 2013-07-11 |  |  |  |  | 2018-01-15 | 2019-05-09
AA532 | 4077 | 2014-06-23 | PNE Wind UK Ltd (Brookfield) | Brunta Hill Wind Farm | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Appeal Refused | Application Refused | Land North East Of Blythe Farm (Brunta Hill), Lauder, Scottish Borders | Borders | Scotland | Scotland |  | 360744 | 652045 | Scottish Borders Council | 11/01444/FUL | 13/00044/REF |  |  |  |  | 2011-10-20 |  | 2013-08-05 |  |  | 2014-06-19
AA537 | 4078 | 2017-07-04 | Rev Ltd | Clentrie Wind Farm (Gevens) | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Clentrie Farm, Fife | Fife | Scotland | Scotland |  | 322212 | 692370 | Fife Council | 11/04794/EIA | [5 empty] | 2011-09-22 | [6 empty] | 2014-05-15 |  |  |  |  | 2016-02-01 | 2016-10-24
A0023 | 4079 | 2018-10-29 | Brookfield Renewable Energy Group (PNE Wind UK) | Penbreck & Carmacoup Forest (Resubmission) | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Planning Permission Granted | Awaiting Construction | Lanark, Strathclyde, ML11 | Strathclyde | Scotland | Scotland |  | 269500 | 627500 | South Lanarkshire Council | CL/08/0727 | [5 empty] | 2008-12-16 | [6 empty] | 2014-06-26
A0086 | 4080 | 2016-04-01 | WPR Wind Ltd | Nutsgrove Wind Farm | Wind Onshore |  |  | 14.35 | n/a |  |  |  | 2 | 7 |  | n/a | Abandoned | Abandoned | Land Near Nutsgrove Farm, Scolding Drove, Thorney, Peterborough | Cambridgeshire | Eastern | England | PE6 0TP | 532606 | 307038 | Peterborough City Council | 06/01051/FUL | 08/00040/NONDET |  |  |  |  | 2006-07-07 |  | 2008-09-05 |  |  |  | 2010-04-01 | 2010-04-01
A0095 | 4081 | 2016-05-23 | Energia Renewables | Thornog Windfarm Extension | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Thornog, Meenadoan townland, Drumquin. Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 41160 | 537686 | Northern Ireland Planning Service | K/2009/0243/F | [5 empty] | 2009-04-01 | [6 empty] | 2012-09-11 |  |  |  |  | 2014-06-13 | 2014-12-22
A0160 | 4082 | 2016-05-31 | Wind Power Wales | Brenig Wind Farm | Wind Onshore |  |  | 40 | n/a |  |  |  | 2.5 | 16 |  | n/a | Abandoned | Abandoned | Denbigh Moors, Denbigh, Clwyd. LL16 | Denbighshire | Wales | Wales |  | 304304 | 366301 | Denbighshire County Council | 25/2007/0565 | [5 empty] | 2007-04-26 | [6 empty] | 2008-01-23
A0220 | 4083 | 2014-07-02 | Gartree Wind Power Co-operative Ltd | Airfield Farm (Leicestershire) | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Planning Permission Refused | Application Refused | Gallow Field Road, Market Harborough, Leicestershire. LE16 7QX | Leicestershire | East Midlands | England |  | 471979 | 289392 | Harborough District Council | 09/01220/FUL | [5 empty] | 2009-09-30 |  | 2010-01-27
AA620 | 4084 | 2016-07-28 | Blue Energy | Kelmarsh Wind Farm (Resubmission) | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | Land To The South Of The A14 And North Of Haselbech, Kelmarsh, Northamptonshire | Northamptonshire | East Midlands | England |  | 470868 | 278823 | Daventry District Council | DA/2010/0100 | [5 empty] | 2010-02-08 |  | 2010-12-15 |  |  |  | 2011-12-19 | 2011-12-19 |  |  |  |  | 2014-04-01 | 2016-07-01
AA731 | 4085 | 2015-06-29 | Capital Dynamics | Torrance Farm Wind Park Extension | Wind Onshore |  |  | 5.7 | n/a |  |  |  | 3 | 2 |  | n/a | Operational | Operational | NETHERTON FARM Westcraigs Road Harthill Shotts North Lanarkshire | Strathclyde | Scotland | Scotland | ML7 5TT | 290908 | 666200 | North Lanarkshire Council | 12/00284/FUL | N/A |  |  |  |  | 2012-03-19 | [6 empty] | 2012-07-31 |  |  |  |  | 2014-12-18 | 2015-06-18
AA998 | 4086 | 2014-06-11 | Airvolution Energy | Muircleugh Farm Resubmission | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land To North And West Of Muircleugh Farmhouse, Lauders, Scottish Borders | Borders | Scotland | Scotland |  | 350731 | 644968 | Scottish Borders Council | 13/00044/FUL | [5 empty] | 2013-01-31 | 2013-10-24
B0031 | 4087 | 2014-07-03 | Wind Direct | Bradken UK | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Planning Permission Refused | Application Refused | Dawes Lane, Scunthorpe, South Humberside, DN16 1DN | Humberside | Yorkshire and Humber | England |  | 491385 | 411690 | North Lincolnshire Council | PA/2011/0497 | [5 empty] | 2011-05-09 |  | 2011-08-08
B0280 | 4088 | 2016-04-19 | Collier Quarrying Group | Goathill Quarry Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Operational | Operational | Goathill Quarry Easter Bucklyvie Cowdenbeath Fife | Fife | Scotland | Scotland | KY4 8ES | 317941 | 688959 | Fife Council | 11/05591/EIA | [5 empty] | 2011-11-01 | [6 empty] | 2013-06-21 |  |  |  |  | 2014-05-01 | 2015-12-27
B0288 | 4089 | 2014-07-03 | Wind Direct | Kingspan Factory Wind Turbines | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Kingspan Limited, 2-4 Greenfield Business Park 2, Ba, Greenfield, Holywell, CH8 7GJ | Clwyd | Wales | Wales |  | 320282 | 377547 | Flintshire County Council | 049300 | [5 empty] | 2011-12-19 |  | 2013-11-07
B0368 | 4090 | 2014-12-30 | Banks Renewables | Killington Wind Farm | Wind Onshore |  |  | 10.2 | n/a |  |  |  | 3.4 | 3 |  | n/a | Abandoned | Abandoned | Near M6 near Killington, Cumbria | Cumbria | North West | England |  | 359395 | 492235 | South Lakeland District Council | SL/2012/0845 |  | APP/M0933/V/14/2216125 |  |  |  | 2012-10-01 | [6 empty] | 2014-02-11 | 2014-03-01
B0675 | 4093 | 2015-07-27 | Clenergy | Skeddoway Farm Wind Turbine (Resubmission) | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Skeddoway Farm Strathore Road Strathore Thornton Fife | Fife | Scotland | Scotland |  | 328104 | 697699 | Fife Council | 13/00269/EIA | [5 empty] | 2013-02-04 | [6 empty] | 2014-01-09 |  |  |  |  | 2014-06-01 | 2014-12-01
B0676 | 4094 | 2017-05-04 | Capital Dynamics | Middle Balbeggie Wind Turbines | Wind Onshore |  |  | 6.4 | n/a |  |  |  | 3.2 | 2 |  | n/a | Operational | Operational | Land Surrounding Middle Balbeggie Balbeggie Avenue Balbeggie Thornton Fife | Fife | Scotland | Scotland |  | 327760 | 696279 | Fife Council | 12/04094/EIA | 13/00035/REF |  |  |  |  | 2012-09-28 |  | 2013-06-17 |  |  |  | 2014-01-29 | 2014-01-29 |  |  |  |  | 2015-06-15 | 2016-11-20
B0707 | 4095 | 2015-07-17 | EDF | Bullington Cross Wind Farm (7 of 14 turbines Winchester City Council) | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Appeal Withdrawn | Application Refused | Land At Bullington Cross, Upper Norton Farm, Sutton Scotney, Hants | Hampshire | South East | England | SO21 3QF | 448195 | 143500 | Winchester City Council | 13/00800/FUL | APP/L1765/W/14/3001602 |  |  |  |  | 2013-04-08 |  | 2014-06-17 | 2015-01-26 | 2015-07-13
B0708 | 4096 | 2015-07-17 | EDF | Bullington Cross Wind Farm (Basingstoke and Deane) | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Appeal Withdrawn | Application Refused | Land At Bullington Cross, Upper Norton Farm, Sutton Scotney, Hants | Hampshire | South East | England | SO21 3QF | 448195 | 143500 | Basingstoke and Deane Borough Council | 13/00046/FUL | APP/H1705/W/14/3001603 |  |  |  |  | 2013-04-08 |  | 2014-06-17 | 2015-01-26 | 2015-07-13
B1000 | 4097 | 2016-03-04 | Temporis Capital | Upper Holton Wind Farm | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Operational | Operational | Wind Farm, Upper Holton, Holton, Suffolk | Suffolk | Eastern | England |  | 640495 | 280140 | Waveney District Council | DC/13/0014/DRC | [5 empty] | 2013-01-07 | [6 empty] | 2013-02-12 |  |  |  | 2018-02-12 | 2014-06-01 | 2016-02-26
C0224 | 4098 | 2014-06-30 | Scottish Power Renewables | Bamff Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Appeal Refused | Application Refused | Bamff Wind Farm, Alyth, Blairgowrie, Tayside, PH11 8DN | Tayside | Scotland | Scotland |  | 324184 | 753874 | Perth and Kinross Council | 12/00963/FLL | [5 empty] | 2012-06-18 |  | 2013-04-26 |  |  | 2014-06-11
C1468 | 4099 | 2016-02-01 | Broadview Energy | Slyer's Lane | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 | 115 | n/a | Planning Permission Refused | Application Refused | Charminster, Dorset | Dorset | South West | England |  | 370100 | 93600 | West Dorset District Council | WD/D/14/002611 | [5 empty] | 2014-11-18 |  | 2016-01-29
C1525 | 4100 | 2015-01-13 | Woodmancott Wind Farm Ltd | Woodmancott Down | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Planning Permission Refused | Application Refused | Land At Woodmancott, Grid Ref: 457347 143175 Popham Milchedever Hampshire | Hampshire | South East | England |  | 457347 | 143175 | Basingstoke and Deane Borough Council | 13/00844/FUL | [5 empty] | 2013-06-14 |  | 2014-06-26
C1580 | 4101 | 2014-06-30 | Sharenergy | Criddon Hall Farm | Wind Onshore |  |  | 3 | n/a |  |  |  | 1.5 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Criddon Hall Farm Criddon Upton Cressett Bridgnorth | Shropshire | West Midlands | England | WV16 6UJ | 366292 | 291162 | Shropshire Council | 13/01983/FUL | [5 empty] | 2013-05-28 | 2014-06-24
C2076 | 4102 | 2015-03-12 | Wind Prospect Developments | Breaker Hill (resubmission) | Wind Onshore |  |  | 7.2 | n/a |  |  |  | 0.8 | 9 |  | n/a | Appeal Refused | Application Refused | The site is located 8km South of Girvan between Pinwherry and Colmonell | Strathclyde | Scotland | Scotland |  | 217500 | 588900 | South Ayrshire Council | 13/01310/APP | PPA-370-2043 |  |  |  |  | 2013-11-28 |  | 2014-06-19 | 2014-09-18 |  | 2015-02-02
C2577 | 4103 | 2016-01-06 | Airvolution Energy | Muircleugh Farm Resubmission 2 | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 | 110 | n/a | Appeal Refused | Application Refused | Land North, West And South West Of Muircleugh Farmhouse, Lauder, Scottish Borders | Borders | Scotland | Scotland | TD2 6RG | 350540 | 645212 | Scottish Borders Council | 14/01081/FUL | PPA-140-2054 |  |  |  |  | 2014-10-03 |  | 2015-03-31 | 2015-06-26 |  | 2015-12-08
EN00139 | 4104 | 2014-06-24 | The Renewables Infrastructure Group (TRIG) | Tallentire Hill | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | Hill Farm, Cockermouth, Cumbria. CA13 0PY | Cumbria | North West | England |  | 312500 | 535500 | Allerdale Borough Council | 2/2008/0261 | APP/G0908/A/10/2131842/NWF |  |  |  |  | 2008-03-19 |  | 2010-09-14 |  |  |  | 2011-02-04 | 2011-02-04 |  |  |  |  | 2012-07-06 | 2013-07-09
EN00152 | 4105 | 2014-07-04 | Wind Power Ltd | Newfield | Wind Onshore |  |  | 63 | n/a |  |  |  | 3 | 26 |  | n/a | Planning Permission Refused | Application Refused | Near Sibbaldbie , Lockerbie , Dumfriesshire | Dumfries and Galloway | Scotland | Scotland |  | 318080 | 577600 | Scottish Government (S36) | [6 empty] | 2009-10-01 |  | 2014-06-06
EN00162 | 4106 | 2020-03-11 | Muirhall Energy (formerly Infinis) | Greengairs Wind Farm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2 | 9 |  | n/a | Planning Permission Granted | Awaiting Construction | Greengairs Landfill Site Meikle Drumgray Road Greengairs North Lanarkshire | Strathclyde | Scotland | Scotland |  | 279673 | 669835 | North Lanarkshire Council | 07/00172/FUL | [5 empty] | 2007-02-07 | [6 empty] | 2008-08-14
EN00195 | 4107 | 2018-11-27 | Energia | Pollnalaght (Cornavarrow) | Wind Onshore |  |  | 38.4 | n/a |  |  |  | 3.2 | 12 |  | n/a | Operational | Operational | Pollnalaght, Drumquin, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 48480 | 532854 | Northern Ireland Planning Service | K/2006/1368/F | A2009/0268 |  |  |  |  | 2006-06-23 |  | 2009-10-13 |  |  |  | 2009-10-16 | 2009-10-16 |  |  |  |  | 2015-12-15 | 2018-06-15
EN00202 | 4108 | 2017-08-24 | Seegronan Windfarm | Seegronan | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Killeter , Strabane , Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 122608 | 534966 | Northern Ireland Planning Service | J/2006/0883/F | [5 empty] | 2006-08-24 | [6 empty] | 2011-01-13 |  |  |  | 2016-01-13 | 2016-03-22 | 2016-08-15
EN00217 | 4109 | 2014-06-24 | The Renewables Infrastructure Group (TRIG) | Meikle Carewe (Re-Submission) | Wind Onshore |  |  | 10 | n/a |  |  |  | 0.85 | 12 |  | n/a | Operational | Operational | Rickarton Farms, Stonehaven, Aberdeenshire | Grampian | Scotland | Scotland |  | 383200 | 792000 | Aberdeenshire Council | APP/2006/3934 | PPA-110-2053 |  |  |  |  | 2006-11-29 |  | 2010-05-20 | [9 empty] | 2012-07-26 | 2013-07-30
EN00273 | 4110 | 2018-04-03 | Statkraft UK | Andershaw | Wind Onshore |  |  | 36 | n/a |  |  |  | 2.5 | 14 |  | n/a | Operational | Operational | Andershaw Forest South of Douglas | Strathclyde | Scotland | Scotland | ML11 0SQ | 283500 | 625500 | South Lanarkshire Council | CL/07/0454 | [5 empty] | 2007-07-09 | [6 empty] | 2014-06-09 |  |  |  |  | 2015-10-28 | 2016-11-02
EN00311 | 4111 | 2017-01-04 | Energia Renewables | Eshmore | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Crockanavark, Eshmore and Altaglushan Townlands , Galbally, Dungannon. Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 80500 | 528499 | Northern Ireland Planning Service | M/2006/1802/F | [5 empty] | 2006-10-09 | [6 empty] | 2011-10-19 |  |  |  | 2016-10-19 | 2016-01-15 | 2016-12-22
EN00334 | 4112 | 2019-04-18 | Renewable Energy Systems (RES) | Castlecraig | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Operational | Operational | Castlecraig (Slieve Glass) in Castlecraig, Sloughan, Killoan and Curraghmacall townlands. The proposed site is approximately 5 km south of Killen and 5 km west of Drumquin beside Lough Hill. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 39597 | 540549 | Northern Ireland Planning Service | K/2006/1934/F | [5 empty] | 2006-12-15 | [6 empty] | 2011-06-01 |  |  |  |  | 2017-04-20 | 2018-08-15
EN00443 | 4113 | 2014-12-02 | Wind Direct | East Midlands Airport | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.25 | 4 |  | n/a | Operational | Operational | Castle Donington , Leicestershire | Leicestershire | East Midlands | England |  | 444390 | 325610 | North West Leicestershire District Council | 07/01405/AIR | [5 empty] | 2007-08-31 | [6 empty] | 2008-03-28 |  |  |  |  | 2011-04-16 | 2011-05-10
EN00448 | 4114 | 2014-06-26 | Greencoat UK Wind/Bay Wa .r.e/ SunGift | Kildrummy Windfarm | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Operational | Operational | Clashnarae Hill, Kildrummy, Alford | Grampian | Scotland | Scotland |  | 357655 | 815170 | Aberdeenshire Council | APP/2006/4911 | P/PPA/110/712 |  |  |  |  | 2006-12-19 |  | 2007-09-24 |  |  |  | 2009-08-06 | 2009-08-06 | [5 empty] | 2013-02-14
EN00557 | 4115 | 2014-07-03 | Wind Direct | Causeway Bridges Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Abandoned | Abandoned | Land adjacent to the M62, Causeway Bridges Farm, Alder Lane, Burtonwood, Warrington, WA5 4BN | Cheshire | North West | England |  | 358734 | 392095 | Warrington Borough Council | 2008/12807 | [5 empty] | 2008-04-28 | [6 empty] | 2008-05-29
EN00608 | 4116 | 2017-04-19 | Airvolution Energy | Airfield Farm (Podington) (Resubmission) | Wind Onshore |  |  | 8.55 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Airfield Farm, adjacent to Santa Pod raceway, Podington, Wellingborough | Bedfordshire | Eastern | England | NN29 7XA | 495095 | 260698 | Bedford Borough Council | 08/02692/MAF | 09/00037/NONDET |  |  |  |  | 2008-09-25 |  | 2010-02-23 |  |  |  | 2012-08-21 | 2012-08-21 |  |  |  |  | 2016-07-15 | 2017-02-15
EN00621 | 4117 | 2016-12-01 | Infinergy | Alaska Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | nr. Stokeford, Dorset | Dorset | South West | England |  | 387160 | 88159 | Purbeck District Council | 6/2008/0234 | [5 empty] | 2008-03-20 | 2008-12-17
N00033W | 4118 | 2017-11-27 | Scottish and Southern Energy (SSE) | Dunmaglass Wind Farm | Wind Onshore |  |  | 94 | n/a |  |  |  | 3 | 33 |  | n/a | Operational | Operational | Dunmaglass, Highlands, SW of Inverness | Highland | Scotland | Scotland |  | 264000 | 820120 | Scottish Government (S36) | [6 empty] | 2005-02-11 | [6 empty] | 2010-12-29 |  |  |  |  | 2014-06-01 | 2016-09-13
N00099W | 4119 | 2014-07-02 | Scottish Power Renewables | Harestanes | Wind Onshore |  |  | 136 | n/a |  |  |  | 2 | 68 |  | n/a | Operational | Operational | Mofatt Village Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 300000 | 595000 | Scottish Government (S36) | [6 empty] | 2004-03-17 |  | 2005-12-23 |  |  |  | 2007-09-10 | 2007-09-10 |  |  |  |  | 2012-10-18 | 2014-07-01
N00149W | 4120 | 2020-01-02 | EDF Energy Renewables | Corriemoillie (Resubmission) | Wind Onshore |  |  | 54.4 | n/a |  |  |  | 3.2 | 17 | 125 | n/a | Operational | Operational | Garve , Highlands | Highland | Scotland | Scotland |  | 234700 | 867700 | Highland Council | 10/04137/FUL | [5 empty] | 2010-10-05 | [6 empty] | 2011-03-23 |  |  |  |  | 2015-10-15 | 2017-04-26
N00216W | 4121 | 2016-01-18 | Greencoat UK Wind | Hill of Stroupster Windfarm | Wind Onshore |  |  | 29.9 | n/a |  |  |  | 2.5 | 12 |  | n/a | Operational | Operational | Stroupster, Caithness | Highland | Scotland | Scotland |  | 334250 | 966250 | Highland Council | 05/00273/FULCA | 06/00053/REFCA |  |  |  |  | 2005-06-07 |  | 2006-05-01 |  |  |  | 2010-04-08 | 2010-04-08 |  |  |  |  | 2013-11-30 | 2015-12-03
N00217W | 4122 | 2015-11-03 | RWE npower | Burn of Whilk | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2.5 | 9 |  | n/a | Operational | Operational | Burn of Whilk Hill of Yarrows Caithness | Highland | Scotland | Scotland |  | 329650 | 941550 | Highland Council | 06/00676/FULCA. | [5 empty] | 2007-02-23 | [6 empty] | 2011-03-30 |  |  |  |  | 2014-05-30 | 2015-08-07
N00223W | 4123 | 2015-01-05 | Eneco | Lochluichart | Wind Onshore |  |  | 51 | n/a |  |  |  | 3 | 17 |  | n/a | Operational | Operational | Loch Luichart, Garve | Highland | Scotland | Scotland |  | 232030 | 866235 | Scottish Government (S36) | [6 empty] | 2005-11-21 | [6 empty] | 2008-12-22 |  |  |  |  | 2012-02-01 | 2014-05-14
N00350W | 4124 | 2017-02-27 | Scottish and Southern Energy (SSE) | Tievenameenta | Wind Onshore |  |  | 34.5 | n/a |  |  |  | 2.3 | 15 |  | n/a | Operational | Operational | Tievenameenta, Co Tyrone (townlands of Crigshane, Ballymongan, Shanaghy, Tievenameenta, Crighdenis) | Co. Tyrone | Northern Ireland | Northern Ireland |  | 40010 | 548802 | Northern Ireland Planning Service | J/2005/0104/F | [5 empty] | 2005-02-25 | [6 empty] | 2009-08-27 |  |  |  |  | 2016-01-22 | 2017-02-15
AA075 | 4125 | 2016-02-29 | Wind Prospect Developments/ EDF | Burnhead | Wind Onshore |  |  | 26 | n/a |  |  |  | 2 | 13 |  | n/a | Operational | Operational | S/Of Stoneridge, Falkirk, Stirlingshire, FK1 | Stirling | Scotland | Scotland |  | 289158 | 670199 | Falkirk Council | P/10/0857/FUL | PPA-190-2031 |  |  |  |  | 2010-12-17 |  | 2011-11-22 |  |  |  | 2013-10-08 | 2013-10-08 |  |  |  |  | 2015-01-10 | 2016-02-29
AA087 | 4126 | 2014-07-03 | Wind Direct | Kinegar Quarry | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land South West Of Neuk Farm, Cockburnspath, Scottish Borders | Borders | Scotland | Scotland |  | 377377 | 671362 | Scottish Borders Council | 10/00364/FUL | [5 empty] | 2010-03-12 |  | 2010-09-15
B0178 | 4127 | 2014-06-27 | Banks Renewables | Weddicar Rigg Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Appeal Refused | Application Refused | LAND TO THE WEST OF STEEL BROW ROAD, (KNOWN AS WEDDICAR RIGG), ARLECDON, FRIZINGTON | Cumbria | North West | England |  | 301585 | 519345 | Copeland Borough Council | 4/11/2485/0F1 | APP/Z0923/A/12/2191361/NWF |  |  |  |  | 2011-10-06 |  | 2012-10-17 |  |  | 2013-12-12
B0199 | 4128 | 2020-05-28 | Community Windpower | Sneddon Law Community Wind Farm | Wind Onshore |  |  | 45 | n/a |  |  | 37.5 | 3 | 15 |  | n/a | Under Construction | Under Construction | Sneddon Law Off Hemphill Road Moscow East Ayrshire Near | Strathclyde | Scotland | Scotland | KA4 8PP | 249387 | 641441 | East Ayrshire Council | 11/0967/PP | [5 empty] | 2012-01-11 | [6 empty] | 2012-06-29 |  |  |  |  | 2018-09-15
B0561 | 4129 | 2014-07-03 | Eurowind | Lyth Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 2.4 | 10 |  | n/a | Appeal Refused | Application Refused | Lyth near Wick in Caithness | Highland | Scotland | Scotland |  | 327575 | 966130 | Highland Council | 13/01832/FUL | 14/00004/REFCA |  |  |  |  | 2013-05-18 |  | 2013-11-26 |  |  | 2014-05-20
C1191 | 4131 | 2015-07-17 | EDF | Bullington Cross Wind Farm (3 of 14 turbines Test Valley BC) | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Appeal Withdrawn | Application Refused | Land At Bullington Cross, Upper Norton Farm, Sutton Scotney, Hants | Hampshire | South East | England | SO21 3QF | 448195 | 143500 | Test Valley Borough Council | 13/00753/FULLN | APP/C1760/W/14/3001604 |  |  |  |  | 2013-04-25 |  | 2014-06-17 | 2015-01-26 | 2015-07-13
C3019 | 4132 | 2015-07-01 | Caddick Renewables Ltd | South East of Wadnal Lane | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Appeal Refused | Application Refused | South East of Wadnal Lane, Weston, Newark | Nottinghamshire | East Midlands | England | NG23 6TB | 477099 | 367397 | Newark and Sherwood District Council | 14/00837/FUL | APP/B3030/W/14/2223465 |  |  |  |  | 2014-05-21 |  |  | 2014-08-13 |  | 2015-06-29
C3023 | 4133 | 2017-01-17 | Frank A Smart & Son Ltd | Easter Tolmauds | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Operational | Operational | Easter Tolmauds, Torphins, Banchory, Grampian | Grampian | Scotland | Scotland | AB31 4PP | 362478 | 807524 | Aberdeenshire Council | APP/2014/1890 | PPA-110-2239 |  |  |  |  | 2014-05-20 |  | 2014-08-22 | 2014-10-15 |  |  | 2015-05-29 | 2015-05-29 |  |  |  | 2018-05-29 | 2016-02-01 | 2016-10-15
C3029 | 4134 | 2014-06-23 | One Earth Renewables Ltd | Croick Estate | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Croick Estate Ardgay | Highland | Scotland | Scotland |  | 239458 | 897816 | Highland Council | 14/01752/FUL | [5 empty] | 2014-05-16 | 2014-10-06
C3059 | 4135 | 2015-10-06 | Redpath Energy Limited | Charlton Mires | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land East Of South Charlton Village Northumberland | Northumberland | North East | England |  | 417215 | 620615 | Northumberland County Council | 14/01548/RENE | [5 empty] | 2014-06-02 |  | 2015-09-14
C3065 | 4136 | 2015-10-29 | Inicio-Fresco | Cairnandrew | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Appeal Refused | Application Refused | Land 500 Metres East/South-East Cairnandrew Longmanhill Banff Aberdeenshire AB45 3SR | Grampian | Scotland | Scotland |  | 375155 | 860228 | Aberdeenshire Council | APP/2014/1974 | PPA-110-2277 |  |  |  |  | 2014-05-28 |  | 2015-06-30 | 2015-08-04 |  | 2015-10-26
C3089 | 4137 | 2015-07-01 | Private Developer | Greenleys | Wind Onshore |  |  | 1.7 | n/a |  |  |  | 0.85 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Greenleys Benholm Johnshaven Aberdeenshire DD10 0HX | Grampian | Scotland | Scotland |  | 378671 | 771917 | Aberdeenshire Council | APP/2014/2088 | [5 empty] | 2014-06-09 | 2015-06-08
EN00113 | 4138 | 2014-06-26 | Greencoat UK Wind | Maerdy | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 |  | n/a | Operational | Operational | land NW of Maerdy and NE of Treherbert, Rhigos | Mid Glamorgan | Wales | Wales | CF44 9UF | 295189 | 200983 | Rhondda Cynon Taff County Borough Council | 11/0198/10 | [5 empty] | 2006-09-01 | [6 empty] | 2008-02-10 |  |  |  |  | 2012-07-09 | 2013-08-31
EN00129 | 4139 | 2017-05-04 | Altamuskin Windfarm (Energia) | Altamuskin | Wind Onshore |  |  | 7.05 | n/a |  |  |  | 2.35 | 3 | 110 | n/a | Operational | Operational | Altamooskan (Altamuskin) TD, Sixmilecross, Omagh, Co. Tyrone. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 70474 | 526049 | Northern Ireland Planning Service | K/2006/0164/F | [5 empty] | 2006-02-03 | [6 empty] | 2008-12-02 |  |  |  |  | 2016-03-01 | 2017-03-15
11060W4 | 4140 | 2015-07-23 | Private Developer | Woodlands Barton Wind Project | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Nr Roche St Austell Cornwall | Cornwall | South West | England |  | 200211 | 62170 | Cornwall Council | PA12/10296 | [5 empty] | 2012-11-14 | [6 empty] | 2013-02-11 |  |  |  |  | 2014-05-15 | 2014-09-01
A0036 | 4141 | 2014-07-21 |  | Westnewton | Wind Onshore |  |  | 6.15 | n/a |  |  |  | 2.05 | 3 |  | n/a | Operational | Operational | Warwick Hall Farm, Westnewton, Cumbria. CA7 3PF | Cumbria | North West | England |  | 313505 | 543564 | Allerdale Borough Council | 2/2008/0997 | APP/GO908/A/10/2132949 |  |  |  |  | 2008-12-24 |  | 2010-07-02 |  |  |  | 2011-02-04 | 2011-02-04 |  |  |  |  | 2013-09-17 | 2014-05-01
A0111 | 4142 | 2017-01-03 | Gaelectric Developments/ CGN Europe Energy | Windyhill Road (Dunbeg) Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3 | 14 |  | n/a | Operational | Operational | Picnic Area, Dunbeg Townland, Limavady, Co Londonderry. BT45 | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 88128 | 587145 | Northern Ireland Planning Service | B/2007/0560/FUL | 2009/A0363 |  |  |  |  | 2007-12-11 |  | 2010-03-18 |  |  |  | 2011-01-27 | 2011-01-27 |  |  |  |  | 2013-12-01 | 2014-11-14
A0113 | 4143 | 2017-01-03 | Gaelectric Developments/ CGN Europe Energy | Cloonty Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Operational | Operational | 122 Castlecat Road Derry Keighan, Cloonty Townland, Ballymoney, Co Antrim. BT53 8AP | Co. Antrim | Northern Ireland | Northern Ireland |  | 119820 | 589284 | Northern Ireland Planning Service | D/2009/0142/F | [5 empty] | 2009-06-08 | [6 empty] | 2013-03-27 |  |  |  | 2018-03-27 | 2015-10-15 | 2016-08-15
A0122 | 4144 | 2016-01-06 | ProWind Gateforth Wind Farm GMBH and Co KG | Wood Lane | Wind Onshore |  |  | 32.2 | n/a |  |  |  | 2.3 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Birkin, Knottingly, West Yorks | North Yorkshire | Yorkshire and Humber | England | WF11 9LU | 453795 | 427138 | Selby District Council | 09/0393/FUL | [5 empty] | 2009-07-01 | 2015-12-08
A0144 | 4145 | 2020-03-11 | Muirhall Energy (formerly Infinis) | Bullamoor | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 | 132 | n/a | Planning Permission Granted | Awaiting Construction | Northallerton, North Yorkshire. DL6 | North Yorkshire | Yorkshire and Humber | England |  | 439729 | 497509 | Hambleton District Council | 08/04984/FUL | [5 empty] | 2008-12-19 | [6 empty] | 2010-12-10
A0242 | 4146 | 2017-12-12 | Scottish Power Renewables | Holbeach Marsh Wind Farm, | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Abandoned | Abandoned | Spalding, Lincolnshire | Lincolnshire | East Midlands | England | PE12 8LR | 540324 | 328455 | South Holland District Council | H09-1016-09 | [5 empty] | 2009-12-25
A0266 | 4147 | 2020-01-22 | Ecotricity | Heckington Fens | Wind Onshore |  |  | 54 | n/a |  |  |  | 2.45 | 22 | 125 | n/a | Planning Permission Granted | Awaiting Construction | East Heckington, North Kesteven, Lincolnshire | Lincolnshire | East Midlands | England |  | 518784 | 346338 | DECC (S36) | S36 | [5 empty] | 2009-12-16 | [6 empty] | 2013-02-08
A0268 | 4148 | 2015-05-20 | Ecotricity | Black Ditch | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Secretary of State - Refusal | Application Refused | Pawlett Road, Near West Huntspill, Somerset | Somerset | South West | England |  | 331083 | 144487 | Sedgemoor District Council | 52/10/00018 | [5 empty] | 2010-12-01 |  | 2012-04-24 | 2012-10-29 |  | 2014-02-26 |  |  | 2013-10-11 | 2014-02-25
A0301 | 4149 | 2020-02-27 | DW Consultancy | Gronan | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Permission Granted | Awaiting Construction | Golandun Dolan, Killeter, Castlederg | Co. Tyrone | Northern Ireland | Northern Ireland |  | 34365 | 545082 | Northern Ireland Planning Service | J/2007/0667/F | [5 empty] | 2007-10-02 | [6 empty] | 2018-12-20 |  |  |  | 2023-12-20
A0303 | 4150 | 2014-07-15 | WYG | Koram Hill | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 600m East of Koram Television Mast, Koram Hill, Strabane | Co. Tyrone | Northern Ireland | Northern Ireland |  | 54979 | 558511 | Northern Ireland Planning Service | J/2007/0309/F | [5 empty] | 2007-05-10 | 2016-11-30
A0309 | 4151 | 2018-10-30 | DW Consultancy | Curraghamulkin (Dooish Wind Farm) | Wind Onshore |  |  | 30 | n/a |  |  |  | 3 | 10 | 130 | n/a | Operational | Operational | Coolavannagh TD, Curraghmulkin TD, Dooish TD, Drumquin | Co. Tyrone | Northern Ireland | Northern Ireland |  | 43843 | 534280 | Northern Ireland Planning Service | K/2008/0334/F | 2015/A0200 |  |  |  |  | 2008-03-12 |  | 2016-01-25 | 2016-01-22 |  |  | 2017-11-10 | 2017-11-10 |  |  |  |  | 2018-01-15 | 2018-07-15
A0311 | 4152 | 2018-11-27 | Energia | Teiges | Wind Onshore |  |  | 11 | n/a |  |  |  | 2.2 | 5 |  | n/a | Operational | Operational | Eshnanumera and Eshnasillog More townlands (adjacent to Lisnaskea Forest), Brookeborough TD, Co. Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 48958 | 503174 | Northern Ireland Planning Service | L/2008/0459/F | [5 empty] | 2008-03-31 | [6 empty] | 2014-12-12 |  |  |  | 2019-12-12 | 2017-08-24 | 2018-07-19
A0314 | 4153 | 2019-09-16 | ESB (Northern Wind Power) | Meenakeeran | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Planning Permission Granted | Awaiting Construction | Tullycar Road, Aghyaran, Castlederg | Co. Tyrone | Northern Ireland | Northern Ireland |  | 25980 | 548578 | Northern Ireland Planning Service | J/2008/0240/F | [5 empty] | 2008-04-14 | [6 empty] | 2016-01-18 |  |  |  | 2021-01-17
A0320 | 4154 | 2017-12-19 | Gaelectric Developments | Smulgedon | Wind Onshore |  |  | 16.1 | n/a |  |  |  | 2 | 7 |  | n/a | Abandoned | Abandoned | Land located at Smulgedon Hill, south of Legavallon Road, approx. 9km to the north-east of Dungiven, and 8km west of Garvagh, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 89022 | 572814 | Northern Ireland Planning Service | B/2009/0070/F | [5 empty] | 2009-02-18 | [6 empty] | 2012-10-02
A0322 | 4155 | 2017-01-03 | Gaelectric Developments/ CGN Europe Energy | Monnaboy Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2.5 | 4 |  | n/a | Operational | Operational | on land located east of 62 Monnaboy Road, Greysteel | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 3HP | 71649 | 577014 | Northern Ireland Planning Service | A/2009/0868/F | [5 empty] | 2009-11-06 | [6 empty] | 2012-10-12 |  |  |  | 2017-10-12 | 2015-01-15 | 2015-11-15
A0323 | 4156 | 2017-07-28 | Brookfield Renewable Energy Group | Crockandun | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | approximately 450m west south-west of junction of Cullion Road and Drumard Road, Draperstown, Magherafelt. | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT45 5NR | 92983 | 548733 | Northern Ireland Planning Service | H/2010/0009/F | [5 empty] | 2010-01-08 | [6 empty] | 2012-11-30 |  |  |  | 2017-11-30 | 2016-01-15 | 2017-03-09
A0397 | 4157 | 2018-10-02 | Scottish Power Renewables | Hare Hill Extension | Wind Onshore |  |  | 29.75 | n/a |  |  |  | 0.85 | 35 |  | n/a | Operational | Operational | New Cumnock, East Ayreshire | Strathclyde | Scotland | Scotland |  | 265320 | 609703 | East Ayrshire Council | 07/0809/FL | [5 empty] | 2007-09-04 | [6 empty] | 2014-11-28 |  |  |  |  | 2015-10-15 | 2016-09-15
A0405 | 4158 | 2019-06-26 | REG Windpower (previously Cornwall Light and Power) | Langthwaite Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Application Submitted | Application Submitted | Millom | Cumbria | North West | England |  | 315479 | 480072 | Copeland Borough Council | 4/12/2182/0F1 | [5 empty] | 2012-03-30
A0465 | 4159 | 2015-01-05 | Bristol Port Company | Avonmouth Port - extension | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Operational | Operational | St Andrews House, St Andrew's Rd, Avonmouth, Bristol, Avon | Avon | South West | England | BS11 9DQ | 351593 | 178451 | Bristol City Council | 10/02547/F | [5 empty] | 2010-05-12 | [6 empty] | 2010-10-14 |  |  |  |  | 2013-10-05 | 2014-04-01
A0467 | 4160 | 2016-06-27 | FCC Environment | Darrington Quarry | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Westfield Lane, Darrington, Pontefract, West Yorkshire WF8 3AQ | West Yorkshire | Yorkshire and Humber | England |  | 448042 | 420016 | Wakefield Council | 10/02488/FUL | [5 empty] | 2010-12-22 | 2016-06-24
A0469 | 4161 | 2014-07-30 | European Forest Resources Group | Fauch Hill Wind Farm | Wind Onshore |  |  | 69 | n/a |  |  |  | 3 | 23 |  | n/a | Planning Permission Refused | Application Refused | Colzium Hill Farm, West Lothian | Lothian | Scotland | Scotland |  | 308383 | 656467 | Scottish Government (S36) | [6 empty] | 2012-02-23 |  | 2014-07-08
A0531 | 4162 | 2014-07-30 | RWE npower | East Heslerton Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Appeal Refused | Application Refused | Ling Hall Farm West Heslerton Malton North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 492102 | 473219 | Ryedale District Council | 11/00270/MFULE | 13/00015/REF |  |  |  |  | 2011-03-18 |  | 2013-05-16 |  |  | 2014-05-28
A0544 | 4163 | 2015-01-20 | EDF | Barmoor South Wind Farm (Resubmission) | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Between Ford And Lowick Bowsden Berwick-upon-Tweed Northumberland | Northumberland | North East | England |  | 398519 | 638193 | Northumberland County Council | C/07/00180/CPC | [5 empty] | 2007-11-22 |  | 2007-12-17 |  |  |  | 2010-01-21 | 2010-01-21 |  |  |  |  | 2014-03-01 | 2015-01-19
AA073 | 4164 | 2016-08-16 | Blue Energy | Winwick | Wind Onshore |  |  | 12.3 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Land To North and West Of Winwick Warren, Cold Ashby Road, Winwick, Northampton, Northamptonshire, NN6 | Northamptonshire | East Midlands | England |  | 463950 | 274602 | Daventry District Council | DA/2010/0400 | APP/Y2810/A/11/2156527 |  |  |  |  | 2010-05-17 |  | 2012-07-13 |  |  |  | 2012-07-13 | 2012-07-13 |  |  |  |  | 2015-04-15 | 2016-06-30
AA088 | 4165 | 2020-01-16 | FCC Environment | Carnaby | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Permission Granted | Awaiting Construction | Household waste recycling site, Moor Lane, Carnaby, East Riding | Humberside | Yorkshire and Humber | England | YO16 4UT | 514817 | 465382 | East Riding of Yorkshire Council | 10/04753/STPLFE | [5 empty] | 2010-11-25 | [6 empty] | 2012-02-20
AA144 | 4166 | 2018-02-28 | Ecotricity | Stoke Heights Wind Farm | Wind Onshore |  |  | 30 | n/a |  |  |  | 2 | 15 | 120 | n/a | Planning Application Withdrawn | Application Withdrawn | Stoke Goldington, Milton Keynes, Buckinghamshire | Buckinghamshire | South East | England |  | 483476 | 248420 | Milton Keynes Council | 11/01193/FULEIS | [5 empty] | 2011-06-27 | 2014-01-01
AA189 | 4167 | 2016-10-03 | Infinis (formerly Novera Energy) | Sisters | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2.05 | 4 |  | n/a | Operational | Operational | west of Widdrington, approximately 8km north of Ashington, Northumberland | Northumberland | North East | England |  | 424367 | 595143 | Northumberland County Council | 11/02481/RENEIA | [5 empty] | 2011-09-28 | [6 empty] | 2013-02-06 |  |  |  |  | 2015-07-27 | 2016-07-30
AA241 | 4168 | 2015-02-16 | Airvolution Energy | East Youlstone Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | East Youlstone, Devon | Devon | South West | England |  | 228127 | 115941 | Torridge District Council | 1/0311/2011/FULM | [5 empty] | 2011-04-04 |  | 2011-07-04 |  |  |  | 2012-11-09 | 2012-11-09 |  |  |  |  | 2014-07-24 | 2015-02-15
AA319 | 4170 | 2015-05-07 | SAC Environment And Design | Hill of Skilmafilly Cloffrickford (Denmore) Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Auchnagatt, Ellon, AB41 8YD | Grampian | Scotland | Scotland |  | 390213 | 840362 | Aberdeenshire Council | APP/2011/0692 | [5 empty] | 2011-03-04 | [6 empty] | 2013-01-18 |  |  |  |  | 2013-12-09 | 2015-02-16
AA382 | 4171 | 2014-12-05 | Scottish and Southern Energy (SSE) | Crocknamona Wind Farm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Planning Permission Refused | Application Refused | Killyfuddy Road, Glengeen, Trillick | Co. Tyrone | Northern Ireland | Northern Ireland |  | 47559 | 521584 | Northern Ireland Planning Service | K/2010/0758/F | [5 empty] | 2010-12-20 |  | 2014-11-13
AA385 | 4172 | 2020-02-27 | RWE Npower Renewables | Headwind Taff Ely Wind Farm (Repowering) | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Planning Permission Granted | Awaiting Construction | 10 kilometres (km) north east of Bridgend | Mid Glamorgan | Wales | Wales |  | 298257 | 186256 | Rhondda Cynon Taff County Borough Council | 11/1468/10 | [5 empty] | 2011-12-23 | [6 empty] | 2013-04-23
AA394 | 4173 | 2015-03-04 | Scottish and Southern Energy (SSE) | Dunnaree Hill Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | approximately 2km southwest of Drumquin, and 13.2km west of Omagh in Co. Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 43699 | 536343 | Northern Ireland Planning Service | K/2011/0237/F | [5 empty] | 2011-04-13 | 2016-02-01
AA417 | 4174 | 2015-05-05 | Banks Renewables | Heysham South Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Lancaster Morecambe Bypass, Heaton With Oxcliffe, Lancashire | Lancashire | North West | England |  | 343444 | 460153 | Lancaster City Council | 11/00689/FUL | [5 empty] | 2011-07-28 | [6 empty] | 2012-11-28 |  |  |  |  | 2014-08-04 | 2015-04-24
AA427 | 4175 | 2016-11-30 | Aviva | Woolley Hill Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | North of the A14, between the villages of Ellington & Woolley | Cambridgeshire | Eastern | England |  | 515374 | 272655 | Huntingdonshire District Council | 1001741FUL | 1100021REFUSL |  |  |  |  | 2010-11-11 |  | 2011-07-19 |  |  |  | 2012-03-23 | 2012-03-23 |  |  |  |  | 2014-03-17 | 2014-04-30
AA443 | 4176 | 2015-05-28 | BT - Wind for Change | Skeffling Wind Farm | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn |  | Humberside | Yorkshire and Humber | England |  | 538586 | 420253 | East Riding of Yorkshire Council | 11/05745/STPLFE | [5 empty] | 2012-01-10 | 2015-03-19
AA493 | 4177 | 2020-06-04 | Baywind Co-op & Energy4All & Belltown Power | Furness Wind Farm/High Winds (Harlock Repowering) | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Operational | Operational | Standish Cote & Mean Moor, Pennington, Marton & Harlock Hill, Ulverston, Cumbria | Cumbria | North West | England | LA12 0 | 325251 | 479875 | South Lakeland District Council | B06/2011/0662 | [5 empty] | 2011-09-06 |  | 2013-05-21 |  |  |  | 2014-07-24 | 2014-07-24 |  |  |  |  | 2015-12-20 | 2016-11-17
AA509 | 4178 | 2018-06-01 | Scottish and Southern Energy (SSE)/ GIB | Clyde Wind Farm Extension (Clyde 2) | Wind Onshore |  |  | 172.8 | n/a |  |  |  | 3.2 | 54 |  | n/a | Operational | Operational | Upper Clyde Valley, surrounding Camps Reservoir | Strathclyde | Scotland | Scotland |  | 302328 | 624463 | Scottish Government (S36) | EC00003160 | [5 empty] | 2011-10-10 | [6 empty] | 2014-07-23 |  |  |  |  | 2015-07-20 | 2017-08-15
AA511 | 4179 | 2017-04-04 | NTR PLC | Quixwood Moor | Wind Onshore |  |  | 29.9 | n/a |  |  |  | 2.3 | 13 |  | n/a | Operational | Operational | Scottish Borders | Borders | Scotland | Scotland |  | 378028 | 663859 | Scottish Borders Council | 11/01662/FUL | [5 empty] | 2011-12-22 | [6 empty] | 2013-04-02 |  |  |  |  | 2016-01-06 | 2017-03-09
AA517 | 4180 | 2015-09-02 | REG Windpower | Bank House Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Croft, Lincolnshire | Lincolnshire | East Midlands | England |  | 550977 | 362260 | East Lindsey District Council | S/039/01184/12 | [5 empty] | 2012-06-29 | 2015-08-03
AA598 | 4181 | 2017-10-30 | Vattenfall | Hirddywel | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Planning Application Submitted | Application Submitted | 6.5km to south east of Llanidloes, Powys | Powys | Wales | Wales |  | 301261 | 280542 | Powys County Council | P/2010/0650 | [5 empty] | 2010-06-25
AA636 | 4182 | 2016-04-29 | E.ON Climate and Renewables UK Limited | Quantans Hill Wind Farm | Wind Onshore |  |  | 57 | n/a |  |  |  | 3 | 19 |  | n/a | Planning Application Withdrawn | Application Withdrawn |  | Dumfries and Galloway | Scotland | Scotland |  | 258465 | 593404 | Scottish Government (S36) | [6 empty] | 2014-01-26 | 2016-04-28
AA661 | 4183 | 2020-03-26 | RWE Npower Renewables | Neuadd Goch Bank Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Appeal Withdrawn | Application Refused | Dolfor, Newtown Powys | Powys | Wales | Wales |  | 308665 | 284309 | Powys County Council | P/2012/0040 | APP/T6850/A/14/2217488 |  |  |  |  | 2012-01-27 |  | 2014-07-14 | 2014-04-22 | 2020-03-01
AA680 | 4184 | 2018-11-26 | Fyne Futures | Auchadaduie Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Land South Of Auchadaduie Barr Glen Glenbarr Kintyre | Strathclyde | Scotland | Scotland |  | 169193 | 633969 | Argyll and Bute Council | 11/02525/PP | [5 empty] | 2012-01-18 | [6 empty] | 2014-07-21 |  |  |  | 2017-07-21 | 2018-01-15 | 2018-11-21
AA712 | 4185 | 2018-07-03 | North Power Ltd | Carneatly | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Ballycastle, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 126703 | 597217 | Northern Ireland Planning Service | E/2011/0088/F | N/A |  |  |  |  | 2011-04-12 | 2018-06-07
AA722 | 4186 | 2017-02-01 | Scottish and Southern Energy (SSE) | Binnawooda Wind Farm | Wind Onshore |  |  | 29.9 | n/a |  |  |  | 2.3 | 13 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land in townlands of Edanasop, Binnawooda, Lettercairn, Meencarriga, Drummahon and Scraghy approximately 3.73km North East of junction of B72 and Montaighroe Road. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 36918 | 540656 | Northern Ireland Planning Service | J/2010/0168/F | N/A |  |  |  |  | 2010-05-27 | 2016-12-20
AA793 | 4187 | 2018-06-21 | Ecotricity | Harringe Brooks Wind Park | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 | 125 | n/a | Planning Application Submitted | Application Submitted | Land 500M South West Otterpool Manor Barn (adj. Harringe Brooks Wood) Otterpool Lane Sellindge Kent | Kent | South East | England |  | 610455 | 136440 | Folkstone and Hythe District Council | Y12/0451/SH | [5 empty] | 2012-05-16
B0146 | 4188 | 2017-07-28 | Peel Holdings and UUGE | Scout Moor Windfarm (extension) | Wind Onshore |  |  | 36.8 | n/a |  |  |  | 2.3 | 16 | 115 | n/a | Secretary of State - Refusal | Application Refused | Land at Scout Moor , off Edenfield Road , Rochdale | Lancashire | North West | England |  | 382400 | 419200 | Rossendale Borough Council | 2015/0112 |  | APP/B2355/V/15/3139740 |  |  |  | 2015-04-22 | [7 empty] | 2015-11-30 | 2017-07-06
B0157 | 4189 | 2020-06-18 | Lantern Bidco | Dalquhandy Windfarm | Wind Onshore |  |  | 45 | n/a |  |  |  | 2 | 15 | 149.9 | n/a | Planning Permission Granted | Awaiting Construction | Land at Dalquhandy, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 214836 | 591232 | South Lanarkshire Council | CL/12/0042 | [5 empty] | 2012-02-01 | [6 empty] | 2015-01-27
B0249 | 4190 | 2019-11-21 | TCI Renewables | Cam Burn Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Abandoned | Abandoned | Land approximately 920 metres north west of 33 Craigmore Road, Coleraine, Co. Londonderry, BT51 4EX | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 99543 | 582056 | Northern Ireland Planning Service | C/2011/0459/F | [5 empty] | 2011-09-07 |  | 2015-10-08 |  |  |  |  | 2016-12-22 | 2015-10-30 |  | 2016-12-22
B0313 | 4191 | 2014-11-25 | Burcote Wind | Meikleton Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Appeal Refused | Application Refused | Land to South of Meikleton of Ardonald Cairnie Huntly AB54 4UB | Grampian | Scotland | Scotland |  | 345789 | 843302 | Aberdeenshire Council | APP/2012/3280 | PPA-110-2216 |  |  |  |  | 2012-10-03 |  | 2014-04-02 | 2014-04-30 |  | 2014-09-26
B0314 | 4192 | 2017-06-29 | Burcote Wind | Creggan Wind Farm | Wind Onshore |  |  | 54 | n/a |  |  |  | 3 | 18 |  | n/a | Appeal Refused | Application Refused | north-west of the village of Glenbarr in West Kintyre | Strathclyde | Scotland | Scotland |  | 166521 | 636785 | Scottish Government (S36) | EC00002102 | WIN-130-1 |  |  |  |  | 2013-12-13 |  |  | 2015-05-29 |  | 2017-06-23
B0328 | 4193 | 2017-04-18 | REG Windpower | Mynydd Brombil Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Brombil, Port Talbot | Neath Port Talbot | Wales | Wales |  | 279141 | 188569 | Neath Port Talbot County Borough Council | P2012/0638 | APP/Y6930/A/14/2226525 |  |  |  |  | 2012-08-29 |  |  | 2015-01-07 |  |  | 2015-07-08 | 2015-07-08 |  |  |  | 2020-07-08 | 2016-02-01 | 2017-01-15
B0330 | 4194 | 2017-04-18 | REG Windpower | Mynydd Portref Wind Farm extension | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational |  | Mid Glamorgan | Wales | Wales |  | 299608 | 185606 | Rhondda Cynon Taff County Borough Council | 12/0704/10 | [5 empty] | 2012-06-29 | [6 empty] | 2014-12-19 |  |  |  |  | 2016-04-11 | 2017-03-01
B0339 | 4195 | 2014-11-06 | Energiekontor UK | Belford Burn Windfarm | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2.5 | 9 |  | n/a | Planning Permission Refused | Application Refused | Sionside Farm, on land adjacent to the Middleton Burn site, just north of Belford Moor. , Northumberland | Northumberland | North East | England |  | 407870 | 633489 | Northumberland County Council | 13/02050/RENEIA | [5 empty] | 2013-07-09 |  | 2014-10-08
B0535 | 4196 | 2015-05-29 | Renewable Energy Systems (RES) | Longlands Lane | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Longlands Lane, Margam, nr junction 38 of the M4. | Gwent | Wales | Wales |  | 278940 | 186385 | Newport City Council | 12/1001 | [5 empty] | 2012-10-30 | [6 empty] | 2013-11-06 |  |  |  |  | 2014-09-30 | 2014-12-01
B0553 | 4197 | 2015-03-31 | RWE / npower renewables | Temple Hill Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Permission Refused | Application Refused | Hough Grange Farm, Hough-on-the-hill, Grantham | Lincolnshire | East Midlands | England | NG322AN | 489417 | 347100 | South Kesteven District Council | S13/2699 | [5 empty] | 2013-10-18 |  | 2015-03-17
B0635 | 4198 | 2020-01-24 | REG Windpower | Abergorki Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Permission Granted | Awaiting Construction | Craig yr Aber, Land North-East of Ffoch-orky, Treorchy, Rhondda Cynon Taf | Mid Glamorgan | Wales | Wales | CF42 6TF | 296106 | 199051 | Rhondda Cynon Taff County Borough Council | 13/0663/10 | [5 empty] | 2013-06-27 | [6 empty] | 2015-07-23
B0638 | 4199 | 2020-04-30 | EDF Energy Renewables (formerly Partnerships for Renewables/Camilty Wind Farm LLP) | Camilty Wind Farm | Wind Onshore |  |  | 20.4 | n/a |  |  |  | 3.4 | 6 | 132 | n/a | Appeal Granted | Awaiting Construction | Camilty Plantation, Harburn, West Calder | Lothian | Scotland | Scotland |  | 305615 | 659320 | West Lothian Council | 0219/FUL/13 | PPA-400-2055 |  |  |  |  | 2013-04-09 |  | 2015-02-05 | 2015-05-15 |  |  | 2016-01-14 | 2016-01-14
B0645 | 4200 | 2020-07-02 | BayWa r.e. (formerly Forsa) | Inverclyde Wind Farm (Corlic Hill) | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 |  | n/a | Under Construction | Under Construction | Corlic Hill, near Greenock & Port Glasgow | Strathclyde | Scotland | Scotland |  | 229563 | 672854 | Inverclyde Council | 13/0199/IC | PPA-280-2022 |  |  |  |  | 2013-07-08 |  | 2014-12-04 | 2015-03-03 |  |  | 2016-05-17 | 2016-05-17 |  |  |  |  | 2019-05-15
B0656 | 4202 | 2014-11-06 | Renewable Energy Systems (RES) | Rayburn Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | 5km south of Wingates and 2km north of Netherwitton, to the west of Rayburn Lake near Morpeth. | Northumberland | North East | England |  | 410526 | 592620 | Northumberland County Council | 13/03346/RENEIA | [5 empty] | 2013-11-08 |  | 2014-10-07
B0789 | 4204 | 2018-09-03 | Willow Wind Energy | Linfairn Wind Farm | Wind Onshore |  |  | 54.4 | n/a |  |  |  | 3.2 | 17 | 126.5 | n/a | Appeal Withdrawn | Application Refused | Straiton | Strathclyde | Scotland | Scotland |  | 238205 | 602124 | Scottish Government (S36) | EC00004192 | WIN-370-1 |  |  |  |  | 2013-09-29 |  | 2016-07-20 | 2016-07-26 | 2018-07-24
B0790 | 4205 | 2020-06-25 | GreenPower (International) Ltd | Millenderdale Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 7 |  | n/a | Appeal Refused | Application Refused | Millenderdale Farm U48 From Junction A77T At Lendalfoot - Via Knocklaugh To A714 Near Pinmore Station Lendalfoot South Ayrshire KA26 0JA | Strathclyde | Scotland | Scotland |  | 217151 | 590576 | South Ayrshire Council | 14/00764/APPM | PPA-370-2077 |  |  |  |  | 2014-06-18 |  | 2019-03-06 | 2019-05-22 |  | 2020-04-16
B0852 | 4206 | 2017-01-23 | Longcliffe Quarries | Ryder Point Quarry Wind Turbines | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | Ryder Point Quarry North Of Manystones Lane Brassington Derbyshire | Derbyshire | East Midlands | England |  | 425455 | 355000 | Derbyshire Dales District Council | 12/00723/FUL | [5 empty] | 2012-11-21 | [6 empty] | 2013-07-11 |  |  |  |  | 2015-04-15 | 2015-12-15
B0863 | 4207 | 2017-01-31 | ARC NI 3 Ltd/Windyfields (Renewable Energy International) | Lisnaharney Road Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3 | 14 |  | n/a | Appeal Refused | Application Refused | Lisnaharney, Omagh | Co. Tyrone | Northern Ireland | Northern Ireland |  | 60344 | 545265 | Northern Ireland Planning Service | K/2013/0181/F | 2013/A0228 |  |  |  |  | 2013-04-15 |  |  | 2014-08-01 |  | 2017-01-20
C0004 | 4210 | 2015-12-21 | John Laing Environmental Assets Group | Burton Wold Wind Farm - Northern Extension (resubmission) | Wind Onshore |  |  | 14.4 | n/a |  |  |  | 1.6 | 9 |  | n/a | Operational | Operational | Burton Wold Wind Farm, Wold Road, Burton Latimer | Northamptonshire | East Midlands | England | NN15 5PU | 491902 | 274577 | Kettering Borough Council | KET/2012/0556 | [5 empty] | 2012-08-29 | [6 empty] | 2012-11-09 |  |  |  |  | 2013-10-21 | 2014-08-01
C0131 | 4211 | 2017-05-02 | EDF Energy Renewables | Pearie Law Wind Farm | Wind Onshore |  |  | 19.2 | n/a |  |  |  | 3.2 | 6 |  | n/a | Operational | Operational | Pearie Law, West Calder, West Lothian, EH55 | Lothian | Scotland | Scotland |  | 302205 | 659690 | West Lothian Council | 0267/FUL/12 | PPA-400-2034 |  |  |  |  | 2012-04-17 |  | 2013-06-25 |  |  |  | 2014-07-08 | 2014-07-08 |  |  |  |  | 2015-09-15 | 2016-12-01
C0220 | 4212 | 2014-07-16 | Vento Ludens | Lodge Hill | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Lodge Hill, Boyndie, Banff, Grampian | Grampian | Scotland | Scotland | AB45 2TD | 360430 | 860500 | Aberdeenshire Council | APP/2012/1971 | [5 empty] | 2012-06-11 |  | 2014-06-06
C0221 | 4213 | 2020-03-11 | Muirhall Energy | Greengairs East Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 | 125 | n/a | Planning Permission Granted | Awaiting Construction | N/o Easterton, Airdrie Road Caldercruix, Airdrie, Lanarkshire, ML6 | Strathclyde | Scotland | Scotland |  | 280551 | 669203 | North Lanarkshire Council | 12/00602/FUL | [5 empty] | 2012-06-29 | [6 empty] | 2019-02-13 |  |  |  | 2022-02-13
C1378 | 4214 | 2014-07-30 | Eneco | Benhar Windfarm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Appeal Refused | Application Refused | Benhar Windfarm Land South Of West Benhar Road Eastfield Harthill ML7 5TG | Strathclyde | Scotland | Scotland |  | 289680 | 663200 | North Lanarkshire Council | 13/00501/FUL | [5 empty] | 2013-03-29 |  | 2013-11-25 |  |  | 2014-07-03
C1427 | 4215 | 2018-06-01 | Fred Olsen Renewables | Crystal Rig Wind Farm Phase III | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Crystal Rigg Wind Farm, Cranshaws Duns, Scottish Borders | Borders | Scotland | Scotland | TD11 3SR | 366700 | 670500 | Scottish Government (S36) | [6 empty] | 2013-06-14 | [6 empty] | 2015-06-18 |  |  |  |  | 2016-01-15 | 2016-12-22
C1465 | 4216 | 2016-05-27 | Apamore Services | Mullaghsandall Road wind farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Appeal Refused | Application Refused | lands approx. 700m south of no. 35 Mullaghsandall Road between Mullaghsandall Road and Starbog Road Kilwaughter Larne BT40 | Co. Antrim | Northern Ireland | Northern Ireland |  | 150477 | 557440 | Northern Ireland Planning Service | F/2013/0085/F | 2014/A0070 |  |  |  |  | 2013-04-22 |  | 2014-07-10 | 2014-07-22 |  | 2016-05-06
C1487 | 4217 | 2015-06-29 | Energiekontor UK | Asserby wind farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Permission Refused | Application Refused | LAND SOUTH OF WILLOW FARM, ASSERBY ROAD, ASSERBY | Lincolnshire | East Midlands | England |  | 549329 | 376844 | East Lindsey District Council | N/016/01046/14 | [5 empty] | 2014-06-26 |  | 2015-06-18
C1583 | 4218 | 2018-02-01 | Green Breeze Energy Ltd | Drumduff | Wind Onshore |  |  | 8.5 | n/a |  |  |  | 2.83 | 3 |  | n/a | Operational | Operational | DRUMDUFF, BLACKRIDGE | Lothian | Scotland | Scotland |  | 288877 | 669339 | West Lothian Council | 0138/FUL/14 | [5 empty] | 2014-02-26 | [6 empty] | 2015-06-18 |  |  |  | 2018-06-18 | 2017-01-15 | 2017-07-11
C1591 | 4219 | 2015-07-01 | Stony Hill Wind Farm Ltd | Stony Hill | Wind Onshore |  |  | 18 | n/a |  |  |  | 3.6 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Stony Hill/RedHill, Lenchie, Insch, AB52 6NE | Grampian | Scotland | Scotland |  | 358591 | 832151 | Aberdeenshire Council | APP/2013/2064 | [5 empty] | 2013-07-04 | 2015-05-19
B0032 | 4220 | 2020-06-04 | Scottish and Southern Energy (SSE) | Slieve Kirk Ext | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Planning Permission Granted | Awaiting Construction | Co Londonderry | Co. Tyrone | Northern Ireland | Northern Ireland |  | 61258 | 571215 | Northern Ireland Planning Service | A/2011/0202/F | [5 empty] | 2011-05-01 | [6 empty] | 2015-03-26 |  |  |  | 2020-03-26
B0063 | 4221 | 2016-01-26 | E.ON Climate and Renewables | The Isles Wind Farm | Wind Onshore |  |  | 48 | n/a |  |  |  | 2 | 24 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land 1.5km east of Newton Aycliffe, County Durham | Durham | North East | England |  | 431757 | 525383 | Durham County Council | DM/14/01210/FPA | [5 empty] | 2014-05-15 | 2016-01-21
B0135 | 4222 | 2015-10-29 | REG Windpower | Ingst Hill Wind Farm/ M48 Wind Farm | Wind Onshore |  |  | 5.2 | n/a |  |  |  | 2.6 | 2 |  | n/a | Appeal Withdrawn | Application Refused | Land At Valley Farm Ingst Hill Olveston Bristol South Gloucestershire | Avon | South West | England | BS35 4AP | 358284 | 187132 | South Gloucestershire Council | PT12/4071/F | APP/P0119/W/15/3100557 |  |  |  |  | 2012-12-05 |  | 2014-12-17 | 2015-07-27 | 2015-10-29
B0255 | 4223 | 2016-02-29 | EDF/Wind Prospect | Rhodders Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Operational | Operational | Site West Of Burnfoot Hill Tillicoultry Clackmannanshire | Clackmannanshire | Scotland | Scotland | FK13 6A | 289525 | 702720 | Clackmannanshire Council | 11/00299/FULL | 13/00001/REFUSE |  |  |  |  | 2011-11-07 |  | 2013-07-08 |  |  |  | 2014-01-21 | 2014-01-21 |  |  |  |  | 2015-08-01 | 2016-02-29
B0268 | 4224 | 2014-07-28 | Wind Ventures | Delph Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Vine House Farm Worths Farm and Porters Farm, Deeping St Nicholas | Lincolnshire | East Midlands | England |  | 539840 | 312820 | South Holland District Council | H14-0110-13 | [5 empty] | 2013-02-13 | 2016-03-09
B0282 | 4225 | 2018-06-04 | Gresham House | Harburnhead Wind Farm | Wind Onshore |  |  | 51.7 | n/a |  |  |  | 3 | 22 | 126 | n/a | Operational | Operational | West Calder, West Lothian | Lothian | Scotland | Scotland |  | 304070 | 658330 | Scottish Government (S36) | [6 empty] | 2011-12-20 | [6 empty] | 2014-07-09 |  |  |  |  | 2016-02-04 | 2016-12-01
B0283 | 4226 | 2014-11-06 | Eurowind UK | Nathro Hill Wind Farm | Wind Onshore |  |  | 61 | n/a |  |  |  | 3.6 | 17 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Careston Estate, Angus | Tayside | Scotland | Scotland |  | 346905 | 768465 | Scottish Government (S36) | [6 empty] | 2012-07-26 | 2014-10-15
B0290 | 4227 | 2017-10-03 | Temporis Capital | Dunsland Cross Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 3 | 3 |  | n/a | Operational | Operational | Land At Dunsland Cross South Of Brandis Corner Holsworthy Devon EX22 7YH | Devon | South West | England |  | 240884 | 103359 | Torridge District Council | 1/1250/2011/FULM | 13/00008/REF |  |  |  |  | 2012-01-13 |  | 2013-01-22 |  |  |  | 2013-01-22 | 2013-01-22 |  |  |  |  | 2016-01-29 | 2017-03-08
B0366 | 4228 | 2015-09-02 | Banks Renewables | High Cumnock Wind Farm | Wind Onshore |  |  | 27.2 | n/a |  |  |  | 3.4 | 8 |  | n/a | Appeal Refused | Application Refused | High Cumnock, East Ayrshire | Strathclyde | Scotland | Scotland |  | 260263 | 617355 | East Ayrshire Council | 13/0099/PP | PPA-190-2043 |  |  |  |  | 2013-02-15 |  | 2014-12-05 | 2015-03-04 |  | 2015-08-21
B0392 | 4229 | 2016-03-03 | Energiekontor UK | Brightenber Hill (Resubmission) | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Appeal Refused | Application Refused | Land adjacent to Brightenber Hill near Stainton Hall, Gargrave, Skopton | North Yorkshire | Yorkshire and Humber | England | BD23 3PA | 388691 | 452767 | Craven District Council | 05/2012/12568 | APP/C2708/A/12/2186488 |  |  | 41944 |  | 2012-04-17 |  | 2012-09-05 | 2014-12-16 |  | 2016-02-10
B0439 | 4230 | 2016-11-01 | Burcote Wind | Longburn Wind Farm | Wind Onshore |  |  | 72 | n/a |  |  |  | 3.6 | 20 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Carsphairn in Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 269700 | 593285 | Scottish Government (S36) | EC00002080 | [5 empty] | 2013-06-28 | 2015-11-05
B0452 | 4231 | 2015-02-05 | Renewable Energy Systems (RES) | Mynydd Marchywel Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Appeal Refused | Application Refused | between Rhos and Crynant | West Glamorgan | Wales | Wales |  | 276783 | 203988 | Neath Port Talbot County Borough Council | P2012/0999 | APP/Y6930/A/14/2215628 |  |  |  |  | 2012-12-06 |  | 2014-02-18 | 2014-07-08 |  | 2015-01-02
B0489 | 4232 | 2016-11-01 | Scottish Power Renewables | Whitelee Windfarm Extension Phase 3 | Wind Onshore |  |  | 12 | n/a |  |  |  | 2.3 | 5 |  | n/a | Appeal Refused | Application Refused | Eaglesham Moor, to the south of Glasgow | Strathclyde | Scotland | Scotland |  | 256300 | 645000 | Scottish Government (S36) |  | WIN-190-1 |  |  |  |  | 2012-08-13 |  |  | 2014-10-30 |  | 2016-10-19
B0490 | 4233 | 2017-01-04 | Capital Dynamics | Potato Pot Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Land at Potato Pot Branthwaite Workington Cumbria | Cumbria | North West | England |  | 303000 | 524100 | Allerdale Borough Council | 2/2012/0594 | APP/G0908/A/13/2189934/NWF |  |  |  |  | 2012-08-07 |  | 2013-01-25 |  |  |  | 2013-10-23 | 2013-10-23 |  |  |  |  | 2015-09-15 | 2016-09-15
B0582 | 4234 | 2017-03-24 | Ventient (formerly Infinis) | Musdale Wind Farm | Wind Onshore |  |  | 64 | n/a |  |  |  | 4 | 16 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Musdale Farm, Kilmore near Oban | Strathclyde | Scotland | Scotland |  | 195365 | 722175 | Scottish Government (S36) | [6 empty] | 2013-08-08 | 2015-05-22
C2391 | 4235 | 2017-04-04 | Community Windpower | Millour Hill Community Windfarm (Extension) resubmission | Wind Onshore |  |  | 6.4 | n/a |  |  |  | 3.2 | 2 |  | n/a | Operational | Operational | Site To North Of Baidland Hill Dalry Ayrshire | Strathclyde | Scotland | Scotland |  | 225498 | 652662 | North Ayrshire Council | 13/00647/PP | [5 empty] | 2013-11-21 | [6 empty] | 2014-06-18 |  |  |  |  | 2016-01-15 | 2016-03-31
C2468 | 4236 | 2020-02-28 | ERG Renew | Evishagaran Wind Farm | Wind Onshore |  |  | 35 | n/a |  |  |  | 2.5 | 14 |  | n/a | Abandoned | Abandoned | Gelvin Road, County Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 89743 | 574264 | Northern Ireland Planning Service | B/2013/0120/F | 2014/A0169 |  |  |  |  | 2013-06-07 |  | 2014-09-26 | 2014-11-24 |  |  | 2016-04-04 | 2016-04-04
C2469 | 4237 | 2016-08-03 | ABO Wind NI | Feystown Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Appeal Refused | Application Refused | Lands east of Feystown Road Glenarm; extending between an area situated approximately 750m east of 54 Feystown Road to lands adjacent to 92 Feystown Road. Within the townlands of Ault alias Gowkstown Clady and Dunteige Glenarm Co Antrim. | Co. Antrim | Northern Ireland | Northern Ireland |  | 147710 | 565013 | Northern Ireland Planning Service | F/2013/0101/F | 2014/A0285 |  |  |  |  | 2013-05-14 |  | 2014-12-22 | 2015-03-27 |  | 2016-07-06
C2470 | 4238 | 2016-11-01 | Slieveard Wind Farm Ltd | Slieveard Wind Farm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Appeal Withdrawn | Application Refused | Slieveard Mountain Glencordial and Rylagh townlands Omagh Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 61286 | 541024 | Northern Ireland Planning Service | K/2013/0102/F | 2015/A0158 |  |  |  |  | 2013-03-26 |  | 2015-07-16 | 2015-11-19 | 2016-10-04
C2484 | 4239 | 2015-09-02 | North Bucks Wind Energy Ltd | Salden Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Permission Refused | Application Refused | Land At Cowpasture Farm Drayton Road Newton Longville Buckinghamshire MK17 0BU | Buckinghamshire | South East | England |  | 484100 | 230478 | Aylesbury Vale District Council | 13/03455/APP | [5 empty] | 2013-12-12 |  | 2015-08-07
C2616 | 4240 | 2015-01-05 | West Coast Energy | Blantyre Muir Wind Farm extension | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Near Laigh Muirhouses Farm Muttonhole Road Hamilton | Strathclyde | Scotland | Scotland |  | 268888 | 651781 | South Lanarkshire Council | HM/10/0478 | [5 empty] | 2010-10-04 | [6 empty] | 2012-05-25 |  |  |  |  | 2012-06-04 | 2014-01-15
C2622 | 4241 | 2014-08-04 | Airvolution Energy | Park Farm (St Osyth) | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Refused | Application Refused | Park Farm, Clay Lane, St Osyth, Clacton On Sea | Essex | Eastern | England | CO16 8HG | 613511 | 216490 | Tendring District Council | 13/01467/FUL | [5 empty] | 2014-01-23 |  | 2014-05-15
EN00263 | 4243 | 2015-12-02 | Renewable Energy Systems (RES) | Rotsea Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land East Of Scurf Dyke Farm Watton Carrs Road Hutton Cranswick East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 506221 | 450719 | East Riding of Yorkshire Council | 13/03606/STPLFE | [5 empty] | 2013-11-15 |  | 2015-11-05
EN00299 | 4244 | 2019-07-23 | EDF Energy Renewables/ Infinergy | Dorenell Wind Farm (Previously Site A and B Scaut Hill) | Wind Onshore |  |  | 177 | n/a |  |  | 177 | 3 | 59 | 126 | n/a | Operational | Operational | Glenlivet Estate, Dufftown, Speyside, Moray | Grampian | Scotland | Scotland |  | 332000 | 829500 | Scottish Government (S36) | EC00003173 | [5 empty] | 2008-05-07 | [6 empty] | 2012-01-03 |  |  |  |  | 2016-08-15 | 2018-09-15
EN00313 | 4245 | 2017-07-03 | Gaelectric Developments/ CGN Europe Energy | Inishative | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Inishative Road, Sixmilecross, Omagh (Slievebeg. Land between Ballygawley and Pomeroy, approximately 1.5km north of Altmore Forest, Townland of Inishative) | Co. Tyrone | Northern Ireland | Northern Ireland |  | 76324 | 530621 | Northern Ireland Planning Service | K/2006/1793/F | [5 empty] | 2006-11-10 | [6 empty] | 2010-11-12 |  |  |  | 2015-11-12 | 2015-02-17 | 2017-03-13
EN00314 | 4246 | 2017-05-31 | Gaelectric Developments/ CGN Europe Energy | Corby Knowe | Wind Onshore |  |  | 5 | n/a |  |  |  | 1.6 | 3 |  | n/a | Operational | Operational | Tardee Mountain, 7km North East of Antrim and 4km South East of Kells | Co. Antrim | Northern Ireland | Northern Ireland |  | 131529 | 551929 | Northern Ireland Planning Service | T/2006/0832/F | [5 empty] | 2006-11-17 | [6 empty] | 2013-01-30 |  |  |  | 2018-01-30 | 2016-01-04 | 2017-05-31
EN00329 | 4247 | 2016-05-31 | Falck Renewables | Earlsburn North (Kingsburn) Wind Farm | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2.5 | 9 |  | n/a | Operational | Operational | Earlsburn, Gargunnock Hills | Stirling | Scotland | Scotland |  | 268000 | 690500 | Stirling Council | 08/00104/DET | [5 empty] | 2008-02-08 | [6 empty] | 2010-04-01 |  |  |  |  | 2014-06-01 | 2016-05-30
EN00455 | 4248 | 2016-02-15 | Renewable Energy Systems (RES) | Wryde Croft | Wind Onshore |  |  | 26 | n/a |  |  |  | 2 | 13 | 100 | n/a | Operational | Operational | Nutsgrove, South of Thorney. | Cambridgeshire | Eastern | England |  | 533235 | 306756 | Peterborough City Council | 07/01411/FUL | 08/00048/REFPP |  |  |  |  | 2006-07-01 |  | 2008-10-22 |  |  |  | 2010-04-01 | 2010-04-01 |  |  |  |  | 2014-09-01 | 2016-02-20
EN00458 | 4249 | 2018-04-03 | Greencoat | Brockaghboy Wind Farm | Wind Onshore |  |  | 37.5 | n/a |  |  |  | 2.5 | 15 |  | n/a | Operational | Operational | Land approximately 750m South East of Dowlin's Bridge, Drumbane Road, Garvagh, Coleraine, BT 51 5DR | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 95250 | 575500 | Northern Ireland Planning Service | C/2007/1186/F | [5 empty] | 2007-12-14 | [6 empty] | 2012-01-18 |  |  |  | 2017-01-18 | 2016-06-23 | 2017-09-01
EN00460 | 4250 | 2015-04-24 | Blue Energy | Wandylaw | Wind Onshore |  |  | 20.5 | n/a |  |  |  | 1.95 | 10 |  | n/a | Operational | Operational | The Ellingham Estate, 3.5km West of the Village of Ellingham | Northumberland | North East | England |  | 414989 | 625121 | Northumberland County Council | 06/B/0765 | [5 empty] | 2006-08-01 |  | 2007-10-24 |  |  |  | 2008-02-10 | 2008-02-10 |  |  |  |  | 2012-05-30 | 2013-07-30
EN00465 | 4251 | 2019-09-16 | ESB (Hibernian Wind) | Clunahill Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 6 |  | n/a | Planning Permission Granted | Awaiting Construction | Drumquin | Co. Tyrone | Northern Ireland | Northern Ireland |  | 45000 | 538000 | Northern Ireland Planning Service | K/2007/0547/F | [5 empty] | 2007-10-25 | [6 empty] | 2015-02-20 |  |  |  | 2020-02-20
EN00511 | 4252 | 2020-05-28 | Vattenfall | Aultmore Wind Farm -resubmission | Wind Onshore |  |  | 29 | n/a |  |  |  | 2.23 | 13 |  | n/a | Planning Permission Granted | Awaiting Construction | Aultmore Forest,Old Fir Hill, Drybridge, Buckie, Grampian. AB56 5JL | Grampian | Scotland | Scotland |  | 345000 | 860000 | Moray Council | 07/02375/EIA | [5 empty] | 2007-10-19 | [6 empty] | 2014-02-27
EN00535 | 4253 | 2016-04-22 | Scottish Power Renewables | Black Law Extension - 1a | Wind Onshore |  |  | 48.43 | n/a |  |  |  | 1.67 | 29 |  | n/a | Operational | Operational | Black Law, Climpy | Strathclyde | Scotland | Scotland |  | 289500 | 653500 | Scottish Government (S36) | [6 empty] | 2008-01-25 | [6 empty] | 2011-03-22 |  |  |  |  | 2014-09-30 | 2016-02-18
EN00581 | 4254 | 2016-05-26 | Bolsterstone Innovative Energy | Reeves Hill | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Permission Expired | Planning Permission Expired | Reeves Hill, Reeves Lane, near Knighton, Shropshire | Hereford and Worcester | West Midlands | England |  | 331940 | 269520 | Herefordshire Council | NW081479/F | APP/W1850/W/15/3137440 |  |  |  |  | 2008-05-19 |  |  | 2015-11-26 |  |  | 2016-04-26 | 2011-09-14 |  |  |  | 2016-05-12
EN00637 | 4255 | 2017-04-26 | Golden Square Energy | Crockbaravally Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Whitebridge Road Sixmilecross, Co. Tyrone BT79 9EH | Co. Tyrone | Northern Ireland | Northern Ireland |  | 73750 | 529250 | Northern Ireland Planning Service | K/2008/1153/F | [5 empty] | 2009-01-02 | [6 empty] | 2012-03-05 |  |  |  | 2017-03-05 | 2016-02-01 | 2017-02-24
IF1005 | 4256 | 2017-04-20 | Greencoat UK (formerly BayWa r.e.) | Bishopthorpe | Wind Onshore |  |  | 16.4 | n/a |  |  |  | 2 | 8 | 115 | n/a | Operational | Operational | Bishopthorpe Farm, Bishopthorpe, Tetney, Grimsby, Humberside | Lincolnshire | East Midlands | England |  | 532679 | 403330 | East Lindsey District Council | N/178/01969/12 | APP/D2510/A/14/2213150 |  |  |  |  | 2012-10-02 |  | 2014-02-05 | 2014-02-13 |  |  |  | 2015-03-20 |  |  | 2015-03-20 | 2018-03-20 | 2016-01-25 | 2017-01-30
IF1036 | 4257 | 2015-07-23 | WilloWind Energy Ltd | Starryshaw Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Planning Permission Refused | Application Refused | Starryshaw Wind Farm Land North Of Starryshaw Farm & Braehead Torbothie Road Stane Shotts North Lanarkshire | Strathclyde | Scotland | Scotland | ML7 5BW | 290021 | 661051 | North Lanarkshire Council | 13/00669/FUL | [5 empty] | 2013-04-23 |  | 2014-12-24
IF1233 | 4258 | 2020-05-26 | EDF | Stranoch Wind Farm | Wind Onshore |  |  | 72 | n/a |  |  |  | 2.6 | 28 | 135 | n/a | Planning Permission Granted | Awaiting Construction | New Luce, Newton Stewart, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 215493 | 571022 | Scottish Government (S36) | EC00005254 | [5 empty] | 2013-01-24 | [6 empty] | 2016-07-08
IF1406 | 4259 | 2014-08-04 | Airvolution Energy | Land South Of Demming Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Planning Permission Refused | Application Refused | Demming Fraisthorpe East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 513962 | 461263 | East Riding of Yorkshire Council | 13/00316/STPLFE | [5 empty] | 2013-03-07 |  | 2014-01-27
N00165W | 4260 | 2015-02-27 | Scottish and Southern Energy (SSE) | Keadby Wind Farm | Wind Onshore |  |  | 68 | n/a |  |  |  | 2 | 34 |  | n/a | Operational | Operational | Near Teadby Near Scunthorpe Lincolnshire | Humberside | Yorkshire and Humber | England |  | 481890 | 413515 | DECC (S36) | 2003/1630 | [5 empty] | 2003-10-24 | [6 empty] | 2008-02-28 |  |  |  |  | 2013-03-01 | 2015-02-26
N00229W | 4261 | 2014-07-21 | Statkraft | Berry Burn | Wind Onshore |  |  | 66.7 | n/a |  |  |  | 2.3 | 29 |  | n/a | Operational | Operational | Adjacent to Paul's Hill Site Altyre Estate BallindalF | Grampian | Scotland | Scotland |  | 311550 | 840550 | Scottish Government (S36) | [6 empty] | 2004-09-19 | [6 empty] | 2009-08-10 |  |  |  |  | 2012-12-05 | 2014-05-30
N00302W | 4262 | 2018-10-02 | InfraRed Capital Partners/ E.on | Afton Wind Farm | Wind Onshore |  |  | 50 | n/a |  |  |  | 2.75 | 25 | 120 | n/a | Operational | Operational | To the south west of New Cumnock adjacent to Afton reservoir | Strathclyde | Scotland | Scotland |  | 262100 | 604100 | Scottish Government (S36) | [6 empty] | 2004-11-03 | [6 empty] | 2014-10-16 |  |  |  |  | 2016-08-16 | 2018-02-15
N00306W | 4263 | 2017-10-31 | BlackRock (formerly Muirhall Energy) | Tormywheel | Wind Onshore |  |  | 30.75 | n/a |  |  |  | 2.6 | 15 |  | n/a | Operational | Operational | Fauldhouse | Lothian | Scotland | Scotland |  | 295290 | 658102 | West Lothian Council | 0551/FUL/11 | [5 empty] | 2005-02-04 | [6 empty] | 2007-06-07 |  |  |  |  | 2015-12-07 | 2017-03-17
N00358W | 4264 | 2017-06-30 | ESB (Northern Wind Power) | Eglish Mountain | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Eglish Mountain in the townlands of Ballyartan and Glenlough (Co. Derry) and Ballyneaner (Co. Tyrone), accessing onto Ballyartan Road, Killaloo, Londonderry BT47 3TA | Co. Tyrone | Northern Ireland | Northern Ireland |  | 65774 | 566796 | Northern Ireland Planning Service | A/2005/0223/F | [5 empty] | 2005-02-01 | [6 empty] | 2013-07-29 |  |  |  | 2018-07-29 | 2015-10-25 | 2017-01-13
N00384W | 4265 | 2020-05-26 | EDF | Braemore | Wind Onshore |  |  | 54 | n/a |  |  |  | 3 | 18 |  | n/a | Appeal Granted | Awaiting Construction | Braemore near Lairg | Highland | Scotland | Scotland |  | 255325 | 900934 | Scottish Government (S36) | EC00002100 | WIN-270-3 |  |  |  |  | 2010-12-17 |  |  | 2015-05-29 |  |  | 2017-10-27 | 2017-10-27 |  |  |  | 2022-10-27
N00400W | 4266 | 2016-11-30 | Aviva | Den Brook | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Operational | Operational | Den Brook, West Devon | Devon | South West | England |  | 268500 | 99500 | West Devon Borough Council | 8250/2005/OKE | APP/Q1153/A/06/2017162/NWF |  |  |  |  | 2005-11-10 |  | 2006-03-02 |  |  |  |  | 2007-03-21 |  |  |  |  | 2015-08-27 | 2016-11-17
N00418W | 4267 | 2016-11-18 | Infinergy | Tom Nan Clach Wind Farm | Wind Onshore |  |  | 39.1 | n/a |  |  |  | 3 | 13 | 125 | n/a | Abandoned | Abandoned | Approximately 8km North East Of Tomatin, Drynachan Nairnshire | Highland | Scotland | Scotland |  | 286470 | 834480 | Highland Council | 09/00439/FULIN | 10/00053/RBCREF |  |  |  |  | 2009-06-01 |  | 2010-08-23 |  |  |  | 2013-06-14 | 2013-06-14 |  |  |  |  | 2016-06-15
N00456W | 4268 | 2016-09-14 | EDF Energy Renewables | Royal Oak | Wind Onshore |  |  | 6.5 | n/a |  |  |  | 1.3 | 5 |  | n/a | Abandoned | Abandoned | Royal Oak Farm, Heighington, Darlington | Durham | North East | England |  | 420950 | 524500 | Darlington Borough Council | 05/00183/FULE | [5 empty] | 2005-02-22 | [6 empty] | 2014-01-10 |  |  |  | 2019-10-10
N00552W | 4269 | 2016-12-12 | Scottish Power Renewables | Dersalloch | Wind Onshore |  |  | 69 | n/a |  |  |  | 3 | 23 |  | n/a | Operational | Operational | Dersalloch Hill | Strathclyde | Scotland | Scotland |  | 242150 | 603950 | Scottish Government (S36) | [6 empty] | 2005-07-29 | [6 empty] | 2014-07-23 |  |  |  |  | 2015-09-24 | 2016-08-15
B0603 | 4270 | 2016-11-01 | Partnerships for Renewables Development Company Limited | Blairadam Wind Farm | Wind Onshore |  |  | 22.55 | n/a |  |  |  | 2.05 | 11 |  | n/a | Planning Permission Refused | Application Refused | Blairadam Forest, Dunfermline | Fife | Scotland | Scotland |  | 309104 | 694542 | Fife Council | 14/00008/EIA | [5 empty] | 2014-01-24 |  | 2016-10-27
B0610 | 4271 | 2015-09-27 | REG Windpower | French Farm 2 (Extension) | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 | 110 | n/a | Secretary of State - Refusal | Application Refused | French Farm, French Drove, Thorney, Peterborough, Cambridgeshire, PE6 0PQ | Cambridgeshire | Eastern | England |  | 528388 | 309240 | Peterborough City Council | 13/00933/FUL |  | APP/J0540/V/14/2220136 |  |  |  | 2013-06-28 | [6 empty] | 2014-02-06 | 2014-06-04 | 2015-09-24
B0688 | 4272 | 2017-01-27 | Point Power & Energy Ltd / SgurrEnergy | Point Wind / Beinn Ghrideag Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Operational | Operational | Point Wind Farm Pentland Road To Achmore Achmore Isle Of Lewis | Western Isles | Scotland | Scotland |  | 136899 | 933106 | Comhairle nan Eilean Siar Council | 08/00371/PPD | [5 empty] | 2008-08-13 | [6 empty] | 2012-04-26 |  |  |  |  | 2014-07-21 | 2015-07-17
B0706 | 4273 | 2015-03-09 | West Coast Energy/Carwath Farm Wind Energy Ltd | Carwath Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Planning Permission Refused | Application Refused | Carwath, Rosley, Wigton, Cumbria CA7 8BW | Cumbria | North West | England |  | 332425 | 546767 | Allerdale Borough Council | 2/2013/0227 | [5 empty] | 2013-04-08 |  | 2015-02-13
B0720 | 4274 | 2019-06-25 | Ecotricity | Dulater Hill Wind Farm | Wind Onshore |  |  | 57.8 | n/a |  |  |  | 3.4 | 17 | 125 | n/a | Appeal Refused | Application Refused | North of the A923, near Butterstone | Highland | Scotland | Scotland |  | 308935 | 748225 | Scottish Government (S36) |  | WIN-340-2 |  |  |  |  | 2014-06-30 |  |  | 2016-03-04 |  | 2019-05-24
B0897 | 4275 | 2018-10-03 | Njord Energy | Rhoscrowther Wind Farm | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.05 | 5 |  | n/a | Appeal Refused | Application Refused | near the Valero oil refinery south of Milford Haven | Dyfed | Wales | Wales |  | 190930 | 202471 | Pembrokeshire County Council | 13/0876/PA | APP/N6845/A/15/3025045 |  |  | 42930 |  | 2014-01-31 |  | 2015-01-21 | 2015-07-09 |  | 2018-04-30
B0898 | 4276 | 2016-12-23 | Njord Energy Ltd | Griffe Grange Wind Farm | Wind Onshore |  |  | 12.3 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | near the Valero oil refinery south of Milford Haven | Derbyshire | East Midlands | England |  | 423771 | 355087 | Derbyshire Dales District Council | 14/00224/FUL | APP/P1045/W/15/3130874 |  |  |  |  | 2014-04-09 |  | 2015-03-09 | 2015-09-30 |  | 2016-12-06
B0995 | 4277 | 2018-10-03 | Scottish and Southern Energy (SSE) | Tangy Wind Farm - repowering/Tangy 3 | Wind Onshore |  |  | 36.8 | n/a |  |  |  | 3.4 | 16 | 125 | n/a | Planning Permission Expired | Planning Permission Expired | Tangy, Kilkenzie, Campbeltown, Argyll And Bute | Strathclyde | Scotland | Scotland | PA28 6QD | 168500 | 628500 | Argyll and Bute Council | 14/02969/PP | [5 empty] | 2014-12-11 | [6 empty] | 2015-06-29 |  |  |  | 2018-06-29
B1049 | 4280 | 2015-07-01 | Wind Valley Co-operative | Slaithwaite Moor Community Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Slaithwaite Moor, off New Hey Road, Scammonden, Huddersfield | West Yorkshire | Yorkshire and Humber | England |  | 404725 | 414272 | Kirklees Council | 2013/93683 | [5 empty] | 2013-12-06 | 2015-06-29
B1057 | 4281 | 2016-03-17 | Muirhall Energy | Muirhall South | Wind Onshore |  |  | 8.25 | n/a |  |  |  | 3.2 | 3 | 147 | n/a | Operational | Operational | Stellashaw Moss, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 299342 | 652838 | South Lanarkshire Council | CL/14/0113 | PPA-380-2050 |  |  |  |  | 2014-03-18 |  | 2014-11-07 | 2014-12-22 |  |  | 2015-07-10 | 2015-07-10 |  |  |  |  | 2016-01-21 | 2016-03-17
B1058 | 4282 | 2020-06-25 | Renewable Energy Systems (RES) | Ora More Extension | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Granted | Awaiting Construction | Ora More Hill, in the Townlands of Killycreen East, Ora Beg and Mullylusty, near Boho and Belcoo, Co Fermanagh. | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 16972 | 509701 | Northern Ireland Planning Service | L/2013/0625/F | [5 empty] | 2013-11-21 | [6 empty] | 2015-12-17
B1059 | 4283 | 2015-09-27 | Derrynaveigh Wind Farm Ltd | Derrynaveigh Wind Farm | Wind Onshore |  |  | 5.6 | n/a |  |  |  | 0.8 | 7 |  | n/a | Planning Permission Refused | Application Refused | Land approximately 400m north of Drumbulcan Road, Irvinestown, Co. Fermanagh, Northern Ireland | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 35338 | 525898 | Northern Ireland Planning Service | L/2013/0623/F | [5 empty] | 2013-11-20 |  | 2015-09-24
B1060 | 4284 | 2015-12-09 | Garranbane Wind Farm Ltd | Garranbane Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Appeal Withdrawn | Application Refused | Land approximately 1.5km west of Tempo, Co Fermanagh. | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 43422 | 511738 | Northern Ireland Planning Service | L/2013/0622/F | 2015/A0098 |  |  |  |  | 2013-11-20 |  | 2015-07-20 | 2015-07-29 | 2015-11-24
B1061 | 4285 | 2019-06-28 | Renewable Energy Systems (RES) | Meenamullen Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | townland of Meenamullan near Killeter, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 31383 | 542597 | Northern Ireland Planning Service | J/2013/0287/F | [5 empty] | 2013-11-29 |  | 2019-06-11
B1271 | 4286 | 2016-02-26 | Renewable Energy Systems (RES) | Stonehaven Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Abandoned | Abandoned | Land East Of Bagworth Road Newbold Heath Newbold Verdon Leicestershire | Leicestershire | East Midlands | England |  | 444854 | 306031 | Hinckley and Bosworth Borough Council | 14/00381/FUL | [5 empty] | 2014-04-14 | [6 empty] | 2014-07-23
B1281 | 4287 | 2015-05-07 | Blue Energy (Auquhirie Extension) Limited | Brucklaywaird Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Brucklaywaird Farm, Stonehaven AB39 3XD | Grampian | Scotland | Scotland |  | 382253 | 783619 | Aberdeenshire Council | APP/2014/0254 | [5 empty] | 2014-02-11 |  | 2015-04-30
B1305 | 4288 | 2015-11-04 | Pennant Walters | Bodelith Isaf Wind Turbines | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Land near Bodelith Isaf, Llandderfel, Bala, Gwynedd | Gwynedd | Wales | Wales | LL23 7LA | 299535 | 339290 | Gwynedd Council | C14/0291/04/LL | [5 empty] | 2014-04-09 |  | 2015-10-19
B1376 | 4290 | 2016-08-03 | Private Developer | Dirnan Road Wind Turbine | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 |  | n/a | Appeal Refused | Application Refused | Land 860m North of 24c Dirnan Road, Cookstown | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 93528 | 545130 | Northern Ireland Planning Service | I/2014/0226/F | 2015/A0083 |  |  |  |  | 2014-07-02 |  | 2015-06-04 | 2015-07-02 |  | 2016-07-08
B1393 | 4291 | 2015-11-05 | British Sugar Plc | Newark Sugar Factory | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | Newark Sugar Factory, Great North Road, British Sugar Corporation Ltd, Newark, Nottinghamshire, East Midlands | Nottinghamshire | East Midlands | England | NG24 1DL | 479681 | 355620 | Newark and Sherwood District Council | 15/01228/FULM | [5 empty] | 2015-07-22 | 2015-09-14
B1409 | 4292 | 2016-04-04 | Private Developer | Smeath Road Wind Turbines | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Appeal Refused | Application Refused | Smeath Road Retford Nottinghamshire | Nottinghamshire | East Midlands | England |  | 471305 | 383536 | Bassetlaw District Council | 14/00853/RSB | APP/A3010/W/15/3133065 |  |  |  |  | 2014-07-07 |  | 2015-07-20 | 2015-09-15 |  | 2016-03-16
B1415 | 4294 | 2016-11-01 | Community Windpower | Sanquhar Community Windfarm 2 | Wind Onshore |  |  | 19.8 | n/a |  |  |  | 5 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | located approximately 7km Southwest of Sanquhar, 5km to the Southwest of Kirkconnel and 4km Southwest of the small steading of Drumbuie | Highland | Scotland | Scotland |  | 266103 | 604141 | Scottish Government (S36) | EC00002070 | [5 empty] | 2014-06-10 | 2014-08-18
B1416 | 4295 | 2017-02-02 | Arnold White Estates (AWE Renewables) | Double Arches Quarry Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Double Arches Quarry Eastern Way Heath And Reach Leighton Buzzard LU7 9LF | Bedfordshire | Eastern | England | LU7 9LF | 493952 | 229038 | Central Bedfordshire Council | CB/10/03034/FULL | [5 empty] | 2010-09-08 | [6 empty] | 2011-08-02 |  |  |  |  | 2014-12-01 | 2014-12-18
C0578 | 4296 | 2017-03-31 | Origin Energy CIC | NORTON COMMUNITY WIND TURBINES | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Planning Permission Refused | Application Refused | Greengate Road, Norton, Doncaster, South Yorkshire, DN6 | South Yorkshire | Yorkshire and Humber | England |  | 452852 | 414720 | Doncaster Metropolitan Borough Council | 12/02140/FUL | [5 empty] | 2012-08-23 |  | 2017-03-09
C0618 | 4297 | 2020-06-25 | Renewable Energy Systems (RES) | Craiggore windfarm | Wind Onshore |  |  | 23.5 | n/a |  |  |  | 1.8 | 10 |  | n/a | Under Construction | Under Construction | Craiggore windfarm in the townlands of Moneyguiggy and Craiggore Forest Belraugh Road Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 93059 | 577288 | Northern Ireland Planning Service | B/2012/0268/F | [5 empty] | 2012-10-15 | [6 empty] | 2015-03-05 |  |  |  | 2020-03-05 | 2019-09-19
C0781 | 4298 | 2016-01-04 | Energiekontor UK | Lissett Airfield Wind Farm Extension | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Withdrawn | Application Refused | North Pasture Farm Out Gates Gembling East Riding Of Yorkshire YO25 8HS | Humberside | Yorkshire and Humber | England |  | 512204 | 457206 | East Riding of Yorkshire Council | 13/03625/STPLFE | APP/E2001/W/15/3134552 |  |  |  |  | 2013-10-30 |  | 2015-08-06 | 2015-10-20 | 2015-12-22
C0787 | 4299 | 2017-05-19 | Wind Harvest | Lochend Wind Farm | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Land 978M SE Of 2 Lochend Holding Barrock | Highland | Scotland | Scotland |  | 326691 | 968145 | Highland Council | 13/02682/FUL | PPA-270-2108 |  |  |  |  | 2013-07-29 |  | 2014-03-31 | 2014-06-27 |  |  | 2014-12-11 | 2014-12-11 |  |  |  | 2017-12-11 | 2016-05-15 | 2017-05-15
C0814 | 4300 | 2020-06-04 | ERG | Creag Riabhach Wind Farm | Wind Onshore |  |  | 72.6 | n/a |  |  |  | 3.3 | 22 | 125 | n/a | Planning Permission Granted | Awaiting Construction | Creag Riabhach Lairg | Highland | Scotland | Scotland |  | 252589 | 928364 | Scottish Government (S36) | EC00002078 | [5 empty] | 2014-01-03 | [6 empty] | 2016-10-17
C0827 | 4301 | 2019-11-21 | TCI Renewables | Dunmore Wind Farm - extension | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 |  | n/a | Appeal Granted | Awaiting Construction | Largantea and Dunmore townlands Bolea Road 8km north-east of Limavady | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 88015 | 585846 | Northern Ireland Planning Service | B/2013/0241/F | 2017/A0023 |  |  |  |  | 2013-11-27 |  | 2017-04-28 | 2017-11-15 |  |  | 2018-06-15 | 2018-06-15
C1129 | 4302 | 2015-02-09 | North Devon Wind Energy Ltd | North Devon Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land To East Of Alverdiscott Substation Webbery Bideford Devon EX39 4PU | Devon | South West | England |  | 250810 | 124962 | Torridge District Council | 1/0288/2013/FULM | [5 empty] | 2013-04-08 |  | 2015-02-02
C1234 | 4303 | 2016-08-17 | Renewable Energy Ventures | KELLAS WIND FARM | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Operational | Operational | Kellas House Kellas Elgin Moray IV30 8TS | Grampian | Scotland | Scotland |  | 316592 | 853931 | Moray Council | 13/00615/EIA | [5 empty] | 2013-04-16 | [6 empty] | 2014-11-12 |  |  |  | 2017-11-12 | 2015-03-01 | 2015-08-01
C1347 | 4304 | 2014-11-06 | Harbourcross Wind Farm Ltd | Harbourcross wind farm (resubmission) | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | Harbourcross Land To The North East Of Meddon Devon | Devon | South West | England |  | 228520 | 118885 | Torridge District Council | 1/0412/2013/FULM | [5 empty] | 2013-05-22 |  | 2014-10-31
C1363 | 4305 | 2018-10-29 | Brookfield Renewable Energy Group (PNE Wind UK) | Meikle Hill wind farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Planning Permission Granted | Awaiting Construction | Meikle Hill Dallas Moray | Grampian | Scotland | Scotland |  | 315105 | 850668 | Moray Council | 14/01087/EIA | [5 empty] | 2014-06-16 | [6 empty] | 2015-06-24 |  |  |  | 2018-06-24
C1716 | 4306 | 2016-08-03 | Stevenson Hill Wind Energy | Hag Law | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Appeal Refused | Application Refused | Hag Law Wind Farm Land South East Of Halmyre Mains Farmhouse Romanno Bridge Scottish Borders | Borders | Scotland | Scotland |  | 319050 | 647944 | Scottish Borders Council | 14/00738/FUL | PPA-140-2053 |  |  |  |  | 2014-07-08 |  | 2015-02-03 | 2015-04-30 |  | 2016-07-08
C1758 | 4307 | 2019-07-23 | EDF Energy Renewables (formerly Partnerships for Renewables/Fauldhouse Wind Farm LLP) | West Benhar wind farm | Wind Onshore |  |  | 27.2 | n/a |  |  |  | 3.4 | 8 |  | n/a | Planning Permission Granted | Awaiting Construction | West Benhar Wind Farm North Of Rimmon Cottage Benhar Road Shotts | Strathclyde | Scotland | Scotland | ML7 5TF | 289560 | 661750 | North Lanarkshire Council | 13/01377/FUL | [5 empty] | 2013-07-25 | [6 empty] | 2015-09-11
C1759 | 4308 | 2014-12-16 | Woodlands Wind Farm Ltd | Woodlands Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Woodlands Farm Dingwall | Highland | Scotland | Scotland |  | 256263 | 861915 | Highland Council | 13/04703/FUL | [5 empty] | 2013-12-16 | 2014-10-15
C1760 | 4309 | 2015-08-04 | ARC NI 1 / Windy Fields | Windy Hill | Wind Onshore |  |  | 52.5 | n/a |  |  |  | 2.5 | 21 |  | n/a | Appeal Withdrawn | Application Withdrawn | lands at Windy Hill, in the townlands of Gortmore Avish Ballyhacket and Altikeeragh approximately 2km west of Ballyhackett Lane Castlerock | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 4SU | 91611 | 593580 | Northern Ireland Planning Service | C/2013/0248/F | 2014/A0062 |  |  |  |  | 2013-07-01 |  |  | 2014-11-01 | 2015-07-31
C1803 | 4310 | 2015-08-04 | Wienberger Ltd | Wienerberger Brick Works | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Appeal Refused | Application Refused | Wienerberger Brick Works Rush Lane, Dosthill | Warwickshire | West Midlands | England |  | 421723 | 299149 | North Warwickshire Borough Council | PAP/2013/0321 | APP/R3705/A/14/2221091 |  |  |  |  | 2013-07-09 |  | 2014-01-14 | 2014-07-02 |  | 2015-07-15
C1824 | 4311 | 2015-11-05 | Lantanier UK | Damwells Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | LAND AT DAMWELLS FARM, LIVESEY ROAD, LUDBOROUGH | Lincolnshire | East Midlands | England |  | 530000 | 397000 | East Lindsey District Council | N/107/00001/14 | [5 empty] | 2014-03-03 | 2015-10-01
C1915 | 4312 | 2020-03-11 | E.On / Eurus (TPG Wind) | Rhyd-y-Groes Wind Farm - repowering | Wind Onshore |  |  | 9.9 | n/a |  |  |  | 0.9 | 11 | 79 | n/a | Planning Permission Granted | Awaiting Construction | near Amlwch, Anglesey | Gwynedd | Wales | Wales |  | 240467 | 392683 | Isle of Anglesey County Council | 20C102L/EIA/RE | [5 empty] | 2015-04-12 | [6 empty] | 2016-10-21
C1970 | 4313 | 2015-12-02 | REG Windpower | Willow Hall Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Willow Hall Farm Willow Hall Lane Thorney Peterborough | Cambridgeshire | Eastern | England |  | 525542 | 301774 | Peterborough City Council | 14/01136/FUL | [5 empty] | 2014-06-27 | 2015-11-11
C2219 | 4314 | 2014-12-05 | Banks Renewables | Crofthill Wind Farm | Wind Onshore |  |  | 17 | n/a |  |  |  | 3.4 | 5 |  | n/a | Planning Permission Refused | Application Refused | Land at Crofthill, Auchengray | Strathclyde | Scotland | Scotland | ML11 8LW | 298208 | 652533 | South Lanarkshire Council | CL/13/0401 | [5 empty] | 2013-10-21 |  | 2014-11-04
C2303 | 4315 | 2020-04-02 | Energiekontor | Sorbie Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Granted | Awaiting Construction | Sorbie Farm Ardrossan Ayrshire | Strathclyde | Scotland | Scotland | KA22 7NP | 224637 | 644638 | North Ayrshire Council | 13/00627/PP | [5 empty] | 2013-10-30 | [6 empty] | 2014-06-27
C2344 | 4316 | 2018-05-29 | REG Windpower/ BlackRock | Hallburn Farm (resubmission) | Wind Onshore |  |  | 13.2 | n/a |  |  |  | 2.2 | 6 |  | n/a | Operational | Operational | Land at Hallburn Farm, Hallburn, Longtown, Carlisle, Cumbria | Cumbria | North West | England |  | 341558 | 568718 | Carlisle City Council | 13/0865 | [5 empty] | 2013-11-08 | [6 empty] | 2014-10-27 |  |  |  | 2017-10-27 | 2017-01-15 | 2018-02-15
C2838 | 4317 | 2014-07-14 | Midland Solar Grid | Cuddyhouse Road | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Site West Of M90 And South Of Cuddyhouse Road Kingseat Fife | Fife | Scotland | Scotland |  | 313507 | 690707 | Fife Council | 14/00374/FULL | [5 empty] | 2014-03-17 | 2014-06-19
C3157 | 4318 | 2020-04-01 | Energy Isles | Yell Wind Farm | Wind Onshore |  |  | 200 | n/a |  |  |  | 3 | 29 | 100 | n/a | Planning Application Submitted | Application Submitted | West Of Cullivoe South Of Gloup, Yell, Shetland | Shetland | Scotland | Scotland | ZE2 9DD | 449792 | 1202671 | Scottish Government (S36) | ECU00001844 | [5 empty] | 2019-04-25
C3206 | 4319 | 2015-10-29 |  | Hill of Tillymorgan extension | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Appeal Refused | Application Refused | Hill Of Tillymorgan Greystone Fisherford Rothienorman | Grampian | Scotland | Scotland |  | 365388 | 835665 | Aberdeenshire Council | APP/2014/2329 | PPA-110-2275 |  |  |  |  | 2014-06-26 |  | 2015-04-27 | 2015-07-24 |  | 2015-10-29
EN00130 | 4320 | 2017-08-30 | ESB (Northern Wind Power) | Crockdun | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | 214 Loughmacrory Road, Crockdun, Sixmilecross, Omagh, Co. Tyrone. | Co. Tyrone | Northern Ireland | Northern Ireland |  | 73770 | 531027 | Northern Ireland Planning Service | K/2006/0074/F | [5 empty] | 2006-01-20 | [6 empty] | 2010-09-13 |  |  |  | 2015-09-13 | 2016-07-14 | 2017-07-14
EN00146 | 4321 | 2015-05-18 | Coal Clough Wind Farm | Coal Clough Wind Farm Repowering | Wind Onshore |  |  | 16 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Coal Clough Wind Farm,The Long Causeway, Burnley | Lancashire | North West | England |  | 390207 | 428154 | Burnley Borough Council | APP/2009/0758 | [5 empty] | 2009-12-22 | [6 empty] | 2013-01-21 |  |  |  |  | 2014-05-14 | 2015-05-01
AA234 | 4322 | 2015-09-27 | Partnerships for Renewables | Saundby Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land To The South West Of Dog Island Off Ramper Road Saundby Nottinghamshire | Nottinghamshire | East Midlands | England |  | 480064 | 388623 | Bassetlaw District Council | 14/00645/FUL | [5 empty] | 2014-05-08 | 2015-09-24
AA533 | 4323 | 2014-09-05 | RWE Npower Renewables | Saxby Wold Wind Farm (Resubmission) | Wind Onshore |  |  | 36 | n/a |  |  |  | 2 | 18 |  | n/a | Appeal Refused | Application Refused | Land West of Brigg Road, Horkstow, | Humberside | Yorkshire and Humber | England |  | 501498 | 417416 | North Lincolnshire Council | WF/2011/0734 | [5 empty] | 2011-06-21 |  | 2012-02-08 |  |  | 2014-08-01
B1496 | 4324 | 2015-11-05 | Whirlwind Renewables | Sewstern Lane Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 6 | 110 | n/a | Planning Permission Refused | Application Refused | Thacksons Well Farm off Sewstern Lane | Lincolnshire | East Midlands | England |  | 483316 | 340875 | South Kesteven District Council | S15/0862 | [5 empty] | 2015-04-27 |  | 2015-10-30
A0305 | 4325 | 2017-12-19 | Tyrone Wind Energy Ltd | Shantavny Scotch | Wind Onshore |  |  | 16.1 | n/a |  |  |  | 2 | 7 |  | n/a | Operational | Operational | Omagh Road, Ballygawley Co. Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 2DL | 70407 | 520962 | Northern Ireland Planning Service | M/2007/1407/F | [5 empty] | 2007-10-29 | [6 empty] | 2012-02-24 |  |  |  | 2017-02-24 | 2016-08-01 | 2017-03-16
B0671 | 4326 | 2018-05-01 | Foresight | Shepham Lane (Resubmission) | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Land off Shepham Lane, North of A27, Polegate | East Sussex | South East | England | BN24 5BT | 560023 | 105784 | Wealden District Council | WD/2013/0346/MEA | APP/C1435/A/13/2208526 |  |  |  |  | 2013-02-18 |  | 2013-05-09 | 2013-12-18 |  |  | 2015-01-07 | 2015-01-07 |  |  |  | 2018-01-07 | 2016-08-16 | 2017-01-12
A0338 | 4327 | 2014-08-20 | West Coast Energy | Sober Hill Wind Farm (Resubmission) | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Operational | Operational | Land North Of Sober Hill Farm Stoneknowle Hill North Newbald East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 492444 | 438545 | East Riding of Yorkshire Council | 08/04816/STPLFE | [5 empty] | 2008-10-03 |  | 2009-04-03 |  |  |  | 2010-03-19 | 2010-03-19 |  |  |  |  | 2012-03-01 | 2013-09-01
B0644 | 4328 | 2016-04-04 | Srondoire Wind Farmers LLP | Srondoire Community Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Cruach A Phubuill, Adj Allt Dearg Windfarm, Ardrishaig, Lochgilphead, Argyll, PA31 8PE | Strathclyde | Scotland | Scotland |  | 182700 | 676700 | Argyll and Bute Council | 13/01427/PP | [5 empty] | 2013-07-10 | [6 empty] | 2013-12-11 |  |  |  |  | 2014-06-20 | 2015-12-20
C1202 | 4330 | 2019-06-24 | Whirlwind Renewables | Achlachan Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  | 10 | 2 | 5 | 115 | n/a | Operational | Operational | Achlachan Windfarm Watten | Highland | Scotland | Scotland |  | 315200 | 952100 | Highland Council | 13/01190/FUL | [5 empty] | 2013-04-11 | [6 empty] | 2013-11-13 |  |  |  | 2020-09-20 | 2016-10-15 | 2019-04-08
EN00386 | 4331 | 2017-04-04 | Infinis (formerly Novera Energy) | A'Chruach (Phase 1) | Wind Onshore |  |  | 48.3 | n/a |  |  |  | 2.3 | 21 |  | n/a | Operational | Operational | Land At A'Cruach Kilmichael Forest West Of Minard Argyll | Strathclyde | Scotland | Scotland |  | 194500 | 700500 | Argyll and Bute Council | 11/02520/PP | [5 empty] | 2011-12-22 | [6 empty] | 2012-06-27 |  |  |  |  | 2015-06-04 | 2016-06-29
A0168 | 4332 | 2020-06-04 | Community Windpower | Aikengall II, Wester Dod Community Wind Farm | Wind Onshore |  |  | 60.8 | n/a |  |  |  | 3.2 | 19 | 145 | n/a | Operational | Operational | East Lothian. | Lothian | Scotland | Scotland |  | 369468 | 669455 | Scottish Government (S36) | [6 empty] | 2009-09-02 | [6 empty] | 2013-03-01 |  |  |  |  | 2014-09-01 | 2017-11-15
A0395 | 4333 | 2020-03-11 | Alaska (formerly Purbeck Wind Farm LLP c/o Infinergy) | Alaska Wind Farm (Masters Pit Resubmission) | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Permission Granted | Awaiting Construction | Puddletown Road, East Stoke | Dorset | South West | England | BH20 6BA | 387544 | 87398 | Purbeck District Council | 6/2010/0082 | APP/B1225/A/11/2161905 |  |  |  |  | 2009-11-20 |  | 2011-04-06 |  |  |  | 2012-07-06 | 2012-07-06
C1030 | 4334 | 2016-02-05 | E.ON UK | Allt Rubha Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land Approximately 6.5 Km To The South West Of Lochgilphead | Strathclyde | Scotland | Scotland |  | 181727 | 681847 | Argyll and Bute Council | 15/03259/PP | [5 empty] | 2015-12-15 | 2016-03-31
EN00578 | 4335 | 2017-12-13 | Ecotricity | Alveston Wind Park | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 | 100 | n/a | Operational | Operational | Land off Old Gloucester Road, Nr Alveston, South Gloucestershire | Avon | South West | England | BS35 3TD | 365450 | 186055 | South Gloucestershire Council | PT08/1658/F | [5 empty] | 2008-06-02 | [6 empty] | 2008-11-13 |  |  |  |  | 2015-10-08 | 2017-12-07
B0438 | 4336 | 2015-09-15 | RWE | Ardchonnel Wind Farm | Wind Onshore |  |  | 45 | n/a |  |  |  | 3 | 15 |  | n/a | Appeal Refused | Application Refused |  | Strathclyde | Scotland | Scotland |  | 200876 | 710912 | Argyll and Bute Council | 13/02835/PP | PPA-130-2045 |  |  |  |  | 2013-12-13 |  | 2014-05-28 | 2014-08-26 |  | 2015-09-10
IF1187 | 4337 | 2017-10-25 | Falck Renewables | Auchrobert Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 2.5 | 12 |  | n/a | Operational | Operational | South Lanarkshire ML11 0HP | Strathclyde | Scotland | Scotland |  | 275154 | 638500 | South Lanarkshire Council | CL/12/0556 | [5 empty] | 2012-12-14 | [6 empty] | 2014-04-09 |  |  |  |  | 2015-04-01 | 2017-03-20
C3236 | 4338 | 2015-07-01 | Private Developer | Backfield Farm | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land To The South West Of Backfield Farm Drumlithie Stonehaven AB39 3YN | Grampian | Scotland | Scotland |  | 375360 | 782070 | Aberdeenshire Council | APP/2014/2433 | [5 empty] | 2014-07-03 | 2015-06-04
AA481 | 4339 | 2014-09-05 | ABO Wind | Barrel Law Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 |  | n/a | Appeal Refused | Application Refused | west of the A7, roughly 3 km north of the village of Roberton and 9km north-west of Hawick in the Scottish Borders | Borders | Scotland | Scotland |  | 343523 | 618249 | Scottish Borders Council | 12/00191/FUL | 13/00028/REF |  |  |  |  | 2012-02-15 |  | 2013-03-04 |  |  | 2014-08-19
IF1322 | 4340 | 2015-07-15 | WPD Beinn Mhor | Beinn Mhor | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Appeal Refused | Application Refused | Guisachan, Tomich, Strathglass | Highland | Scotland | Scotland |  | 229901 | 826242 | Highland Council | 14/01731/FUL | PPA-270-2120 |  |  |  |  | 2014-05-01 |  |  | 2015-02-23 |  | 2015-07-09
B1299 | 4341 | 2015-07-01 | REG Windpower | Berry Fen Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Berry Fen, Aldreth, Ely, Cambridgeshire | Cambridgeshire | Eastern | England |  | 543875 | 274445 | East Cambridgeshire District Council | 14/00728/ESF | [5 empty] | 2014-06-30 | 2015-06-26
B0364 | 4342 | 2019-03-26 | Banks Renewables | Birneyknowe Wind Farm | Wind Onshore |  |  | 60 | n/a |  |  |  | 4 | 15 |  | n/a | Appeal Refused | Application Refused | Hawick, Borders | Borders | Scotland | Scotland |  | 354811 | 611560 | Scottish Government (S36) | EC00002092 | WIN-140-7 |  |  |  |  | 2014-05-14 |  |  | 2017-05-12 |  | 2018-12-21
B1479 | 4343 | 2018-08-30 | Private Developer | Blaenffos Wind Turbines | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Appeal Refused | Application Refused | LAND AT BLAENFFOS, NEWCASTLE EMLYN, SA38 9JD | Dyfed | Wales | Wales |  | 231744 | 238006 | Carmarthenshire County Council | W/30455 | APP/M6825/A/15/3139520 |  |  |  |  | 2014-07-09 |  | 2015-06-08 | 2015-10-13 |  | 2016-08-10
B1467 | 4344 | 2015-04-07 | REG Windpower | Blandford Hill Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Planning Permission Refused | Application Refused | Blandford Hill, Winterborne, Whitechurch To Thornicombe Hill, Winterborne, Whitechurch, Dorset | Dorset | South West | England |  | 385111 | 100255 | North Dorset District Council | 2/2014/0768/PAEIA | [5 empty] | 2014-06-27 |  | 2015-03-17
A0263 | 4345 | 2015-12-01 | Ecogen | Boardinghouse Wind Farm | Wind Onshore |  |  | 10.25 | n/a |  |  |  | 2.05 | 5 |  | n/a | Operational | Operational | Knights End Road March Cambridgeshire | Cambridgeshire | Eastern | England |  | 539862 | 295018 | Fenland District Council | F/YR09/0562/F | 10/00038/REF |  |  |  |  | 2009-08-20 |  | 2010-04-14 |  |  |  | 2011-07-06 | 2011-07-06 |  |  |  |  | 2014-07-28 | 2015-10-01
A0464 | 4346 | 2014-09-05 | Eco2 | Bogenlea Farm | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Operational | Operational | New Byth, Turriff. AB53 5UY | Grampian | Scotland | Scotland |  | 382155 | 852949 | Aberdeenshire Council | APP/2009/1541 | [5 empty] | 2009-05-20 | [6 empty] | 2009-12-10 |  |  |  |  | 2013-10-01 | 2014-08-18
C2739 | 4347 | 2014-08-14 | FCC Environment | Brogborough Landfill Site | Wind Onshore |  |  | 5.4 | n/a |  |  |  | 0.9 | 6 |  | n/a | Planning Permission Refused | Application Refused | Brogborough Landfill Site, Woburn Road, Lidlington | Bedfordshire | Eastern | England |  | 497066 | 239966 | Central Bedfordshire Council | CB/14/00925/FULL | [5 empty] | 2014-03-18 |  | 2014-07-03
C0129 | 4348 | 2017-02-28 | Brownieleys Renewables/Muirden Energy | BROWNIELEYS - 3 WIND TURBINES | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.35 | 3 |  | n/a | Operational | Operational | Nw/O Brownieleys, Fordoun, Alford, Grampian, AB33 1JN | Grampian | Scotland | Scotland |  | 376967 | 772114 | Aberdeenshire Council | APP/2012/1121 | [5 empty] | 2012-04-13 |  | 2013-04-01 |  |  |  | 2013-10-01 | 2013-10-01 |  |  |  |  | 2016-07-15 | 2017-02-28
N00330W | 4349 | 2020-06-25 | Renewable Energy Systems (RES) | Cairn Duhie | Wind Onshore |  |  | 60 | n/a |  |  |  | 3 | 20 |  | n/a | Planning Permission Granted | Awaiting Construction | Nr Ferness Nairnshire | Highland | Scotland | Scotland |  | 298000 | 842300 | Scottish Government (S36) | EC00002087 | [5 empty] | 2013-11-05 | [6 empty] | 2017-10-06 |  |  |  | 2022-10-06
C2139 | 4350 | 2018-04-03 | Engie (GDF Suez) | Cairnborrow - resubmission | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 5 | 100 | n/a | Operational | Operational | Land at Cairnborrow Huntly | Grampian | Scotland | Scotland |  | 346153 | 841867 | Aberdeenshire Council | APP/2013/3282 | [5 empty] | 2013-10-09 | [6 empty] | 2014-08-25 |  |  |  |  | 2015-08-12 | 2017-02-09
C1935 | 4351 | 2019-09-27 | E.ON UK | Camster II | Wind Onshore |  |  | 38 | n/a |  |  |  | 2.7 | 14 | 126.5 | n/a | Planning Application Submitted | Application Submitted | Watten and Lybster | Highland | Scotland | Scotland | KW1 | 328795 | 948360 | Highland Council | 19/03015/FUL | [5 empty] | 2019-08-07
A0222 | 4352 | 2015-09-29 | Dillon Butters | Cleek Hall | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 5 |  | n/a | Abandoned | Abandoned | Turnham Lane, Cliffe, Selby, North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 465238 | 431714 | Selby District Council | 2009/0744/EIA | AP/2012/0008/REF |  |  |  |  | 2009-08-17 |  | 2011-11-09 |  |  |  | 2012-09-18 | 2012-09-18
AA510 | 4353 | 2020-01-06 | EDF Energy Renewables (formerly Partnerships for Renewables) | Cloich Forest Wind Farm | Wind Onshore |  |  | 54 | n/a |  |  |  | 3 | 18 | 115 | n/a | Planning Permission Expired | Planning Permission Expired | situated between the settlements of Peebles and Penicuik | Borders | Scotland | Scotland |  | 320696 | 647988 | Scottish Government (S36) | WIN-140-1 | WIN-140-1 |  |  |  |  | 2012-10-12 |  |  | 2016-02-17 |  |  | 2016-07-08 | 2016-07-08 |  |  |  | 2019-07-08
A0458 | 4354 | 2016-01-04 | Infrared Capital Partners | Crook Hill (Revised Application - Calderdale MBC) 1 of 2 | Wind Onshore |  |  | 13.6 | n/a |  |  |  | 3.4 | 4 |  | n/a | Operational | Operational | Crook Hill/Shore Moor, North Of Watergrove Reservoir, Rochdale | Greater Manchester | North West | England |  | 392720 | 419080 | Calderdale Metropolitan Borough Council | 08/01281/WDF | [5 empty] | 2008-08-04 | [6 empty] | 2009-10-12 |  |  |  |  | 2015-01-01 | 2015-12-01
C1444 | 4355 | 2019-12-16 | BayWa r.e. (formerly Forsa) | Crookedstane Farm | Wind Onshore |  |  | 11.4 | n/a |  |  |  | 2.3 | 4 | 126.5 | n/a | Planning Permission Granted | Awaiting Construction | Land at Crookedstane Farm Elvanfoot | Strathclyde | Scotland | Scotland |  | 296607 | 615168 | South Lanarkshire Council | CL/13/0206 | [5 empty] | 2013-06-13 | [6 empty] | 2016-01-19 |  |  |  | 2019-01-19
B0991 | 4356 | 2016-11-30 | Dulas | Cruach Brenfield Wind Farm | Wind Onshore |  |  | 59.4 | n/a |  |  |  | 3.3 | 18 |  | n/a | Planning Application Withdrawn | Application Withdrawn | forestry near to Ardrishaig in Argyll & Bute | Strathclyde | Scotland | Scotland |  | 183180 | 683850 | Scottish Government (S36) | EC00002094 | [5 empty] | 2014-05-22 | 2016-03-14
B0507 | 4359 | 2019-12-11 | Dell Wind Farm Ltd | Dell Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3 | 14 |  | n/a | Appeal Granted | Awaiting Construction | Dell Estate, Whitebridge, Inverness-shire, Highland | Highland | Scotland | Scotland |  | 249820 | 806535 | Highland Council | 14/02879/FUL | PPA-270-2183 |  |  |  |  | 2014-07-29 |  | 2017-10-12 | 2018-01-11 |  |  | 2019-08-22 | 2019-08-22 |  |  |  | 2024-08-22
EN00067 | 4360 | 2018-10-02 | Force 9 Energy / Catamount Energy/ Green Cat | Deuchries | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Deuchries Farm, Banff, Aberdeenshire | Grampian | Scotland | Scotland |  | 363290 | 855792 | Aberdeenshire Council | APP/2012/3229 | [5 empty] | 2012-11-13 | [6 empty] | 2014-04-17 |  |  |  |  | 2017-08-31 | 2017-12-15
B0115 | 4361 | 2017-04-18 | Renewable Energy Generation (REG) | Draperstown (Brackagh) Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Creagh Concrete Products Ltd, Brackagh Quarry, 29 Disert Road, Draperstown, Magherafelt | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 97617 | 556429 | Northern Ireland Planning Service | H/2009/0075/F | [5 empty] | 2009-02-09 | [6 empty] | 2010-06-28 |  |  |  | 2016-06-28 | 2016-05-26 | 2017-03-15
N00406W | 4362 | 2016-01-04 | John Laing Environmental Assets Group | Dungavel Hill | Wind Onshore |  |  | 29.9 | n/a |  |  |  | 2.3 | 13 |  | n/a | Operational | Operational | Dungavel, Strathaven, Strathclyde | Strathclyde | Scotland | Scotland | ML10 6 | 267954 | 636995 | South Lanarkshire Council | EK/06/0072 | [5 empty] | 2006-02-17 | [6 empty] | 2009-12-01 |  |  |  |  | 2014-05-01 | 2015-08-28
AA119 | 4363 | 2014-08-20 | The Renewables Infrastructure Group (TRIG) | Earlseat | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Operational | Operational | Earlseat Farm Standing Stane Road Kirkcaldy Fife KY1 4TH | Fife | Scotland | Scotland |  | 332961 | 698416 | Fife Council | 10/03539/EIA | [5 empty] | 2010-09-17 | [6 empty] | 2012-03-02 |  |  |  |  | 2013-10-30 | 2014-07-30
EN00298 | 4364 | 2016-11-30 | Wind Energy Ltd | Earlshaugh Wind Farm | Wind Onshore |  |  | 55.2 | n/a |  |  |  | 2.3 | 22 |  | n/a | Abandoned | Abandoned | Devil's Beef Tub near Moffat | Borders | Scotland | Scotland |  | 307500 | 614500 | Scottish Government (S36) | [6 empty] | 2008-06-25
AA457 | 4365 | 2014-09-03 | N R Gammie Partnership | Easter Tulloch Wind Farm (Tullo Extension) | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Operational | Operational | Land to North of Tullo Farm Laurencekirk | Grampian | Scotland | Scotland |  | 375955 | 771728 | Aberdeenshire Council | APP/2011/2603 | [5 empty] | 2011-08-09 | [6 empty] | 2012-09-21 |  |  |  |  | 2013-05-01 | 2014-06-30
B0542 | 4366 | 2014-08-11 | Energiekontor UK | Fenrother Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Appeal Refused | Application Refused |  | Northumberland | North East | England |  | 417730 | 592860 | Northumberland County Council | 12/02500/RENEIA | [5 empty] | 2012-08-09 |  | 2013-01-16 |  |  | 2014-08-07
A0010 | 4367 | 2015-07-14 | Bolsterstone Plc | Fewcott Wind Farm | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Abandoned | Abandoned | Willowbank Farm, Fewcott Road, Fritwell, Bicester, Oxon. OX27 7QA | Oxfordshire | South East | England |  | 452877 | 229216 | Cherwell District Council | 08/02495/F | [5 empty] | 2008-12-05 |  | 2009-04-23 |  |  |  | 2010-07-06 | 2010-07-06
A0348 | 4368 | 2017-03-24 | Ventient (formerly Infinis) | Galawhistle | Wind Onshore |  |  | 66 | n/a |  |  |  | 3 | 22 |  | n/a | Operational | Operational | 7km east of Muirkirk in East Ayrshire and 4km west of Douglas in South Lanarkshire | Strathclyde | Scotland | Scotland |  | 275440 | 629090 | Scottish Government (S36) | [6 empty] | 2010-03-12 | [6 empty] | 2012-08-08 |  |  |  | 2017-08-08 | 2015-06-18 | 2017-02-15
AA452 | 4369 | 2016-03-04 | Energiekontor UK | Gayton Le Marsh Wind Farm | Wind Onshore |  |  | 16.4 | n/a |  |  |  | 2.05 | 8 |  | n/a | Operational | Operational | Carlton Grange, Thacker Bank, Great Carlton, Gayton Le Marsh, Louth, Lincolnshire (3.3km to the northeast of Great Carlton and 2.4km south of Saltfleetby) | Lincolnshire | East Midlands | England | LN11 7TXL | 544232 | 387271 | East Lindsey District Council | N/063/01392/11 | APP/D2510/A/12/2176754/NWF |  |  |  |  | 2011-08-15 |  | 2012-05-25 |  |  |  | 2013-04-05 | 2013-04-05 |  |  |  |  | 2015-02-17 | 2016-02-26
B1510 | 4370 | 2015-05-21 | GlaxoSmithKline | GlaxoSmithKline Wind Project (Turbine 4) | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Shewalton Road Riverside Business Park Irvine Ayrshire KA11 5AP | Strathclyde | Scotland | Scotland |  | 235111 | 636360 | North Ayrshire Council | 12/00629/PP | [5 empty] | 2012-11-13 | [6 empty] | 2013-06-19 |  |  |  |  | 2014-01-01 | 2014-06-01
B0750 | 4371 | 2020-01-28 | Innogy | Glen Kyllachy Wind Farm | Wind Onshore |  |  | 49.9 | n/a |  |  |  | 2.5 | 20 | 110 | n/a | Appeal Granted | Awaiting Construction | 10 miles south of Inverness, 3 miles south-east of the B851 and 3 miles west of the A9 trunk road and village of Tomatin | Highland | Scotland | Scotland |  | 274500 | 827500 | Highland Council | 13/02441/FUL | PPA-270-2115 |  |  |  |  | 2013-06-28 |  | 2014-09-02 | 2014-11-21 |  |  | 2015-04-22 | 2015-04-22 |  |  |  | 2018-04-22
AA573 | 4372 | 2016-03-15 | Wind Energy (Glenmorie) Ltd | Glenmorie Wind Farm | Wind Onshore |  |  | 134 | n/a |  |  |  | 4 | 34 |  | n/a | Planning Permission Refused | Application Refused | located on the Glencalvie and the Kildermorie Estates to the south west of Bonar Bridge, at the head of Strathcarron. | Highland | Scotland | Scotland |  | 249782 | 881552 | Scottish Government (S36) |  |  |  |  | 42248 |  | 2011-11-11 |  | 2014-08-21
N00134W | 4373 | 2014-08-18 | RWE npower | Goole Fields | Wind Onshore |  |  | 32.8 | n/a |  |  |  | 2.05 | 16 |  | n/a | Operational | Operational | Goole Fields Parish , East Riding of Yorkshire | Humberside | Yorkshire and Humber | England |  | 473487 | 419400 | East Riding of Yorkshire Council | 03/01987 | [5 empty] | 2003-04-01 | [6 empty] | 2003-09-01 |  |  |  |  | 2012-03-01 | 2014-08-11
B0493 | 4374 | 2016-04-25 | Greenvale AP | Greenvale AP Wind Turbine - resubmission | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Land North West Of Greenvale Produce Ltd Floods Ferry Road Doddington Cambridgeshire | Cambridgeshire | Eastern | England |  | 535485 | 293292 | Fenland District Council | F/YR12/0514/F | [5 empty] | 2012-07-10 | [6 empty] | 2012-09-24 |  |  |  |  | 2014-05-01 | 2014-08-01
IF1261 | 4375 | 2014-09-01 | Hassiewells Renewables | Hassiewells | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Appeal Refused | Application Refused | Rothienorman, Inverurie, Grampian, AB51 8XX | Grampian | Scotland | Scotland |  | 366278 | 840295 | Aberdeenshire Council | APP/2013/0157 | APPEAL/2014/0001 |  |  |  |  | 2013-01-21 |  | 2014-05-07 |  |  | 2014-07-23
C3213 | 4376 | 2015-08-05 | Helensburgh Renewables | Helensburgh Community Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 0.8 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land To South East Of Tom Na H Airidh And North Of Drumfad Wood, Approximately 2km North Of Helensburgh Argyll And Bute | Strathclyde | Scotland | Scotland |  | 229370 | 685490 | Argyll and Bute Council | 14/01674/PP | [5 empty] | 2014-07-18 | 2015-07-28
B0896 | 4377 | 2020-02-27 | Njord Energy Ltd | Hendy Wind Farm | Wind Onshore |  |  | 14.35 | n/a |  |  |  | 2.5 | 7 |  | n/a | Appeal Granted | Awaiting Construction | Hendy | Powys | Wales | Wales |  | 313083 | 260357 | Powys County Council | P/2014/0672 | APP/T6850/A/17/3176128 |  |  |  |  | 2014-07-14 |  | 2017-05-18 | 2017-08-16 |  |  | 2018-10-25 | 2018-10-25
B1497 | 4378 | 2015-04-01 | Renewable Energy Systems (RES) | High Barns Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Planning Permission Refused | Application Refused | The Lodge Plough Road Great Bentley Colchester Essex CO7 8RP | Essex | Eastern | England |  | 610696 | 220752 | Tendring District Council | 14/00932/FUL | [5 empty] | 2014-07-16 |  | 2015-03-30
AA724 | 4380 | 2014-09-05 | Highfield Wind Energy Limited | Highfield Wind Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Withdrawn | Application Refused | Farmland South Of Litlington, South Camb, Royston, Hertfordshire | Cambridgeshire | Eastern | England |  | 531203 | 241510 | South Cambridgeshire District Council | S/0439/12/FL | N/A |  |  |  |  | 2012-03-12 |  | 2014-02-19 |  | 2014-09-02
B0420 | 4381 | 2017-04-04 | Muirden Energy | Hill of Glaschyle Wind Farm | Wind Onshore |  |  | 27.6 | n/a |  |  |  | 2.3 | 12 | 99.1 | n/a | Operational | Operational | Hill Of Glaschyle Logie Forres Moray | Grampian | Scotland | Scotland |  | 303306 | 847855 | Moray Council | 13/00053/EIA | 14/00001/REF |  |  |  |  | 2013-01-14 |  | 2013-12-18 |  |  |  | 2014-03-31 | 2014-03-31 |  |  |  |  | 2016-06-01 | 2016-12-01
B1260 | 4382 | 2015-07-01 | Community Windpower | Hill Rig Community Windfarm | Wind Onshore |  |  | 28 | n/a |  |  |  | 3.5 | 8 | 130 | n/a | Planning Permission Refused | Application Refused | Hill Rig Community Windfarm North of Lanark | Strathclyde | Scotland | Scotland |  | 289999 | 648659 | South Lanarkshire Council | CL/14/0292 | [5 empty] | 2014-07-21 |  | 2015-06-03
B1462 | 4384 | 2019-09-16 | Energiekontor UK | Hyndburn Wind Farm Extension | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2.05 | 4 | 122 | n/a | Planning Permission Granted | Awaiting Construction | Land at Oswaldtwistle Moor Off B6236, Haslingden Road, Accrington | Lancashire | North West | England |  | 374720 | 424770 | Hyndburn Borough Council | 11/14/0244 | [5 empty] | 2014-07-07 | [6 empty] | 2015-06-26
B0424 | 4385 | 2020-06-04 | Brookfield Renewable Energy Group (PNE Wind UK) | Kennoxhead Wind Farm | Wind Onshore |  |  | 95 | n/a |  |  |  | 3.4 | 19 | 180 | n/a | Planning Permission Granted | Awaiting Construction | Kennoxhead, south of Hagshaw Hill | Strathclyde | Scotland | Scotland |  | 277147 | 624403 | Scottish Government (S36) | [6 empty] | 2013-01-31 | [6 empty] | 2015-07-23
A0334 | 4386 | 2018-02-22 | Scottish Power Renewables | Kilgallioch wind farm | Wind Onshore |  |  | 239 | n/a |  |  |  | 2.5 | 96 |  | n/a | Operational | Operational | (Arecloch Phase 2) land five kilometres to the south of Barrhill, five kilometres to the northeast of New Luce and 11km to the northwest of Kirkcowan | Dumfries and Galloway | Scotland | Scotland |  | 220844 | 569576 | Scottish Government (S36) | [6 empty] | 2010-03-05 | [6 empty] | 2013-02-21 |  |  |  |  | 2015-07-28 | 2017-12-15
B1458 | 4387 | 2014-12-05 | TNEI Services | Kilton Wind Turbine | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Planning Permission Refused | Application Refused | Kilton, Thorpe Lane, Brotton, Saltburn by the Sea, Cleveland | Cleveland | North East | England |  | 469328 | 518552 | Redcar and Cleveland Borough Council | R/2014/0433/FF | [5 empty] | 2014-07-07 |  | 2014-11-27
B1301 | 4388 | 2015-02-09 | REG Windpower | Knightley Hall Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Permission Refused | Application Refused | Knightley Hall, west of Gnosall Road ST20 0JT | Staffordshire | West Midlands | England | ST20 0JT | 380949 | 322815 | Stafford Borough Council | 14/20653/FUL | [5 empty] | 2014-06-20 |  | 2015-01-19
B1302 | 4389 | 2020-01-28 | REG Windpower | Knockshinnoch Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Granted | Awaiting Construction | Knockshinnoch Rd, New Cumnock, Cumnock KA18 4NJ | Strathclyde | Scotland | Scotland |  | 260917 | 612721 | East Ayrshire Council | 14/0569/PP | [5 empty] | 2014-07-04 | [6 empty] | 2017-05-03 |  |  |  | 2020-05-03
AA018 | 4390 | 2017-02-02 | Banks Renewables | Lambs Hill | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Stillington Industrial Estate, Stockton, village of Stillington, to the north west of Stockton and around three miles east of the A1(M | County Durham | North East | England |  | 443682 | 516981 | Stockton on Tees Borough Council | 10/2549/EIS | [5 empty] | 2010-10-07 | [6 empty] | 2011-12-07 |  |  |  |  | 2016-02-26 | 2017-01-19
C1033 | 4391 | 2014-12-05 | PNE Wind UK Ltd (Brookfield) | Larbrax Wind Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 |  | n/a | Planning Application Withdrawn | Application Withdrawn | LARBRAX WIND FARM, LESWALT | Dumfries and Galloway | Scotland | Scotland |  | 197125 | 561845 | Dumfries and Galloway Council | 14/P/1/0393 | [5 empty] | 2014-07-01 | 2014-11-24
A0335 | 4392 | 2015-04-07 | Atmos | Leadhills Wind Farm | Wind Onshore |  |  | 49 | n/a |  |  |  | 3.5 | 14 |  | n/a | Planning Permission Refused | Application Refused | Leadhills, Biggar, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 286973 | 619632 | South Lanarkshire Council | CL/13/0167 | [5 empty] | 2013-05-20 |  | 2015-03-24
AA608 | 4393 | 2015-07-27 | Infinergy | Limekiln Wind Farm | Wind Onshore |  |  | 72 | n/a |  |  |  | 3 | 24 |  | n/a | Planning Permission Refused | Application Refused | 1.5km south of Reay, and 2.8km south/southwest of the existing Dounreay Power Station | Highland | Scotland | Scotland |  | 297705 | 961790 | Scottish Government (S36) | EC00003170 | [5 empty] | 2012-12-14 |  | 2015-07-23
C1520 | 4394 | 2019-12-16 | BayWa r.e. (formerly Forsa) | Lion Hill Wind Farm (Crookedstane Farm 2) | Wind Onshore |  |  | 11.4 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Permission Granted | Awaiting Construction | Lion Hill Wind Farm By Nunnerie Farm Elvanfoot Biggar | Strathclyde | Scotland | Scotland |  | 297700 | 610300 | South Lanarkshire Council | CL/13/0205 | [5 empty] | 2013-06-12 | [6 empty] | 2016-01-20 |  |  |  | 2019-01-20
AA473 | 4395 | 2017-02-02 | Infinergy | Lochluichart (Extension) | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Operational | Operational | Btwn Loch Luichart and Loch Glascarnoch, Lochluichart, Garve, Highlands, IV23. | Highland | Scotland | Scotland |  | 230678 | 869136 | Scottish Government (S36) | [6 empty] | 2011-08-31 | [6 empty] | 2012-10-02 |  |  |  |  | 2013-01-01 | 2014-05-14
C2903 | 4396 | 2014-09-01 | Lifetime Energy | Loganswell Farm | Wind Onshore |  |  | 16 | n/a |  |  |  | 0.25 | 66 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Loganswell Farm 443 Ayr Road Loganswell East Renfrewshire G77 6RY | Strathclyde | Scotland | Scotland |  | 252830 | 654759 | East Renfrewshire Council | 2014/0250/TP | [5 empty] | 2014-04-15 | 2014-09-18
AA655 | 4397 | 2014-09-03 | Partnerships for Renewables | Louth Canal Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Appeal Refused | Application Refused | Louth Canal, Tetney, Grimsby, Humberside | Lincolnshire | East Midlands | England | DN36 | 532972 | 400201 | East Lindsey District Council | N/133/00586/12 | APP/D2510/A/13/2200887 |  |  |  |  | 2012-03-26 |  | 2013-04-23 |  |  | 2014-08-29
B1478 | 4398 | 2015-05-07 | ReSence | Lygan Uchaf Farm Wind Turbine | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Lygan Uchaf Farm, Wern Road, Rhosesmor, Mold CH7 6PY | Clwyd | Wales | Wales |  | 319938 | 368144 | Flintshire County Council | 052344 | [5 empty] | 2014-07-07 |  | 2015-04-13
AA584 | 4399 | 2014-08-19 | Wind Prospect Developments | M1 Wind Farm | Wind Onshore |  |  | 7.2 | n/a |  |  |  | 0.8 | 9 |  | n/a | Operational | Operational | Land between Roade Courteenhall Hartwell and the M1 | Northamptonshire | East Midlands | England |  | 477964 | 252105 | South Northamptonshire Council | S/2011/1421/MAF | [5 empty] | 2011-11-08 | [6 empty] | 2013-05-09 | [5 empty] | 2014-06-30
C2444 | 4401 | 2015-11-30 | Wind Prospect Developments | Mount Lothian Wind Farm - resubmission | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Appeal Refused | Application Refused | Mount Lothian Moss Penicuik | Lothian | Scotland | Scotland |  | 326843 | 655899 | Midlothian Council | 14/00044/DPP | PPA-290-2025 |  |  |  |  | 2014-01-28 |  |  | 2014-08-26 |  | 2015-11-26
C3004 | 4402 | 2020-06-25 | Mynydd y Gwynt Ltd | Mynydd y Gwynt Wind Farm - Revised | Wind Onshore |  |  | 89.1 | n/a |  |  |  | 3.3 | 27 |  | n/a | Appeal Refused | Application Refused | Mynydd y Gwynt, Lllangurig, Llanidloes, Powys | Powys | Wales | Wales |  | 283850 | 284250 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2014-08-20 |  | 2015-11-23 | 2017-10-04 |  | 2018-02-22
B0996 | 4403 | 2019-05-29 | Airvolution Energy | New Rides Wind Farm | Wind Onshore |  |  | 8.8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | New Rides Farm, Leysdown Road, Sheerness | Kent | South East | England | ME12 4DD | 599282 | 170224 | Swale Borough Council | SW/13/1571 | APP/V2255/W/15/3014371 |  |  |  |  | 2014-01-27 |  | 2015-02-03 | 2015-06-25 |  |  | 2017-08-09 | 2017-08-09 |  |  |  |  | 2018-06-07 | 2018-12-01
B0034 | 4404 | 2016-10-19 | Wind Direct | Noble Foods | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 126.5 | n/a | Operational | Operational | Poultry Buildings, Strathore Farm, Strathore Road, Thornton, Fife | Fife | Scotland | Scotland |  | 328104 | 697428 | Fife Council | 11/02164/FULL | [5 empty] | 2011-05-10 | [6 empty] | 2011-11-15 |  |  |  |  | 2014-08-20 | 2014-12-01
B1055 | 4405 | 2015-10-06 | REG Windpower | Old River Don Wind Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Planning Permission Refused | Application Refused | Land off, Godnow Road, Crowle | Humberside | Yorkshire and Humber | England | DN17 4BN | 474885 | 413221 | North Lincolnshire Council | WF/2014/0710 | [5 empty] | 2014-06-30 |  | 2015-09-23
AA093 | 4406 | 2015-04-01 | Mark Caudwell Ltd | Orby Windfarm (June 2010 Resubmission) | Wind Onshore |  |  | 11.7 | n/a |  |  |  | 1.3 | 9 |  | n/a | Secretary of State - Refusal | Application Refused | Orby Marsh Lane, Hogsthorpe, Skegness | Lincolnshire | East Midlands | England |  | 551488 | 367553 | East Lindsey District Council | N/084/00642/10 | APP/D2510/A/11/2161066 |  |  |  |  | 2010-03-24 |  | 2011-03-18 | 2011-10-28 | [5 empty] | 2015-03-30
AA492 | 4407 | 2014-08-11 | Npower Renewables | Orchard Way Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Appeal Refused | Application Refused | Hill Farm, Little Linford Lane, To Haversham High Street, Haversham, Milton Keynes | Buckinghamshire | South East | England |  | 483216 | 243900 | Milton Keynes Council | 11/02028/FULEIS | 12/00048/NONDET |  |  |  |  | 2011-09-16 |  | 2012-11-13 |  |  | 2014-08-04
B0593 | 4408 | 2017-02-02 | Yorkshire Windpower | Ovenden Moor (Repower) (Re-submission) | Wind Onshore |  |  | 18 | n/a |  |  |  | 2.5 | 9 | 115 | n/a | Operational | Operational | Withens Road, Wainstalls, Halifax, West Yorks. HX2 7TZ | West Yorkshire | Yorkshire and Humber | England |  | 404000 | 430500 | Calderdale Metropolitan Borough Council | 12/00955/WDF | [5 empty] | 2012-08-02 | [6 empty] | 2012-11-16 |  |  |  |  | 2015-05-21 | 2017-01-24
C2978 | 4409 | 2017-08-21 | Pennant Walters (PYWX) | Pant y wal extension | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 | 125 | n/a | Operational | Operational | Mynydd Maesteg, Mynydd Pwlle yr Helog, Ogmore Vale, Rhondda Valley | Mid Glamorgan | Wales | Wales |  | 294649 | 188695 | Bridgend County Borough Council | P/14/293/FUL | [5 empty] | 2014-04-30 | [6 empty] | 2015-04-02 |  |  |  |  | 2016-03-14 | 2017-05-01
B0990 | 4410 | 2015-11-26 | EDF Energy Renewables | Park Spring Wind Farm | Wind Onshore |  |  | 8.55 | n/a |  |  |  | 2.85 | 3 |  | n/a | Operational | Operational | Ferry Moor Lane, Cudworth, Barnsley | South Yorkshire | Yorkshire and Humber | England |  | 439689 | 408763 | Barnsley Council | 2013/0860 | [5 empty] | 2013-10-07 | [6 empty] | 2014-04-09 |  |  |  |  | 2015-04-15 | 2015-11-20
C1160 | 4411 | 2017-07-24 | Renewable Energy Ventures | Brotherton (formerly Paul Matthew Hill wind turbines) | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Paul Matthew Hill, Johnshaven, Montrose, Grampian, DD10 0HW | Grampian | Scotland | Scotland |  | 377397 | 769309 | Aberdeenshire Council | APP/2013/1156 | APPEAL/2014/0005 |  |  |  |  | 2013-04-05 |  | 2014-02-07 |  |  |  | 2014-07-15 | 2014-07-15 |  |  |  |  | 2016-12-01 | 2017-05-01
B0329 | 4412 | 2018-05-29 | REG Windpower/ BlackRock | Pen Bryn Oer Wind Farm | Wind Onshore |  |  | 4 | n/a |  |  |  | 1.33 | 3 |  | n/a | Operational | Operational | Pen Bryn Oer, Merthyr Road, Rhymney | Mid Glamorgan | Wales | Wales |  | 312065 | 209235 | Caerphilly County Borough Council | 13/0483/FULL | APP/K6920/A/14/2221852 |  |  |  |  | 2013-06-28 |  | 2014-08-10 | 2014-07-08 |  |  | 2015-08-06 | 2015-08-06 |  |  |  | 2018-08-06 | 2017-01-15 | 2018-01-15
AA402 | 4413 | 2014-09-05 | Broadview Energy Limited | Pilrow | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 |  | n/a | Appeal Refused | Application Refused | immediately east of the M5 motorway, approximately 1km south of Rooks Bridge village, Somerset | Somerset | South West | England |  | 336173 | 151353 | Sedgemoor District Council | 24/12/00018 | [5 empty] | 2012-06-29 |  | 2013-04-08 |  |  | 2014-07-31
AA582 | 4414 | 2015-04-24 | REG Windpower | Ramsey Wind Farm Extension | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | St Marys Road, Ramsey | Cambridgeshire | Eastern | England |  | 527645 | 287235 | Huntingdonshire District Council | 1101865FUL | [5 empty] | 2011-11-08 | [6 empty] | 2013-05-22 |  |  |  |  | 2014-11-01 | 2015-04-23
A0149 | 4415 | 2017-08-31 | Capital Dynamics | Red Gap Moor Wind Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | Sunderland Road,Wolviston, Billingham, Cleveland | Cleveland | North East | England | TS22 5PA | 443942 | 528174 | Hartlepool Borough Council | H/2009/0231 | [5 empty] | 2009-05-20 | [6 empty] | 2011-03-31 |  |  |  |  | 2016-05-26 | 2017-02-15
B0658 | 4416 | 2014-09-03 | EDF Energy Renewables | Stoneton Wind Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land Running From The A423 South West Of Wormleighton To Land East And North East Of Wormleighton At Stoneton | Warwickshire | West Midlands | England |  | 445080 | 253380 | Stratford on Avon District Council | 12/01500/FUL | [5 empty] | 2012-06-20 | 2014-05-09
A0468 | 4417 | 2018-07-26 | Lewis WindPower (a joint venture between EDF and AMEC WIND) | Stornoway Wind Farm project (was Lewis Wind Farm - Resubmission) | Wind Onshore |  |  | 180 | n/a |  |  |  | 4.2857 | 42 | 145 | n/a | Planning Permission Granted | Awaiting Construction | North Lewis, Isle of Lewis | Western Isles | Scotland | Scotland |  | 142695 | 934003 | Scottish Government (S36) | EC00005238 | [5 empty] | 2011-06-30 | [6 empty] | 2012-09-07
N000230W | 4418 | 2020-06-04 | Scottish and Southern Energy (SSE) | Strathy South | Wind Onshore |  |  | 117 | n/a |  |  |  | 3.4 | 34 | 135 | n/a | Appeal Granted | Awaiting Construction | South of Strathy, Sutherland | Highland | Scotland | Scotland |  | 279050 | 952050 | Scottish Government (S36) | EC00003113 | WIN-270-2 |  |  |  |  | 2009-02-01 |  |  | 2014-09-03 |  |  | 2018-04-27 | 2018-04-27
A0457 | 4419 | 2015-06-22 | Todmorden Moor Wind Farm Ltd | Todmorden Moor - Resubmission | Wind Onshore |  |  | 12.29 | n/a |  |  |  | 3 | 5 |  | n/a | Operational | Operational | Todmorden, Yorkshire | West Yorkshire | Yorkshire and Humber | England |  | 389600 | 422700 | Calderdale Metropolitan Borough Council | 10/01057/WDF | [5 empty] | 2010-09-10 | [6 empty] | 2011-04-01 |  |  |  |  | 2013-02-25 | 2014-09-10
B1493 | 4420 | 2020-03-11 | Infinergy | Tom Nan Clach (redesign) | Wind Onshore |  |  | 39 | n/a |  |  | 39.1 | 3 | 13 | 125 | n/a | Operational | Operational | Approximately 8km North East Of Tomatin, Drynachan Nairnshire | Highland | Scotland | Scotland |  | 286401 | 835189 | Highland Council | 15/03286/FUL | PPA-270-2150 |  |  |  |  | 2015-08-27 |  | 2016-01-26 | 2016-03-15 |  |  | 2016-10-28 | 2018-04-24 |  |  |  |  | 2016-06-15 | 2019-03-01
B0597 | 4421 | 2014-09-02 | Wind Prospect Developments | Tressady Wind Farm | Wind Onshore |  |  | 32.5 | n/a |  |  |  | 2.5 | 13 |  | n/a | Appeal Refused | Application Refused | 5km north of Rogart and 2km west of Rilochan | Highland | Scotland | Scotland |  | 271639 | 908352 | Highland Council | 13/02749/FUL | 14/00009/REFSU |  |  |  |  | 2013-07-22 |  | 2014-02-25 |  |  | 2014-08-06
C0012 | 4422 | 2014-11-27 | Eneco | Tullo Wind Farm South (Ext.) | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Operational | Operational | Tullo Farm, Laurencekirk AB30 1HS | Grampian | Scotland | Scotland |  | 375388 | 770733 | Aberdeenshire Council | APP/2011/3694 | [5 empty] | 2011-11-28 | [6 empty] | 2012-09-13 |  |  |  |  | 2013-05-01 | 2014-07-01
C0332 | 4423 | 2018-03-15 | TCI Renewables | Upper Ballyrogan Wind Farm | Wind Onshore |  |  | 11.5 | n/a |  |  |  | 2.3 | 5 |  | n/a | Abandoned | Abandoned | land approximately 870m west of 40 Ballyrogan Road Garvagh Co Londonderry BT51 5EY | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 95704 | 577134 | Northern Ireland Planning Service | C/2012/0276/F | [5 empty] | 2012-07-10 | [6 empty] | 2013-04-11 |  |  |  | 2018-04-11
EN00625 | 4424 | 2015-12-17 | Broadview Energy | Watford Lodge | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | runs from Watford to West Hadon Road along norhtern side of railway | Northamptonshire | East Midlands | England |  | 460960 | 270200 | Daventry District Council | DA/2009/0620 | [5 empty] | 2008-08-19 |  | 2011-04-20 |  |  |  | 2011-12-21 | 2011-12-21 |  |  |  |  | 2014-12-01 | 2015-11-23
AA538 | 4425 | 2020-01-02 | BayWa r.e. | Wathegar 2 Wind Farm | Wind Onshore |  |  | 18.45 | n/a |  |  |  | 2.05 | 9 |  | n/a | Operational | Operational | Wathegar, Bilbster, Wick | Highland | Scotland | Scotland | KW1 5SG | 329103 | 950291 | Highland Council | 11/03671/FUL | [5 empty] | 2011-10-10 | [6 empty] | 2012-03-23 |  |  |  |  | 2016-12-13 | 2017-09-15
AA160 | 4427 | 2014-08-19 | Falck Renewables | West Browncastle | Wind Onshore |  |  | 30 | n/a |  |  |  | 2.5 | 12 |  | n/a | Operational | Operational | Strathaven, Strathclyde, ML10 6QW | Strathclyde | Scotland | Scotland |  | 261117 | 642821 | South Lanarkshire Council | EK/10/0358 | [5 empty] | 2010-10-13 | [6 empty] | 2012-07-09 |  |  |  |  | 2013-02-01 | 2014-06-30
B1259 | 4428 | 2015-11-05 | West Dorset Wind Energy | West Dorset Wind Farm - resubmission | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | farmland south west of Milborne St Andrew, north of Tolpuddle and north east of Puddletown | Dorset | South West | England |  | 379352 | 95380 | West Dorset District Council | WD/D/14/000885 | [5 empty] | 2014-05-27 | 2015-10-23
B0182 | 4429 | 2015-05-20 | Banks Renewables | Windy Bank Windfarm | Wind Onshore |  |  | 14 | n/a |  |  |  | 3.5 | 4 | 125 | n/a | Planning Permission Refused | Application Refused | Land to north of the village of Woodland, south of Windy Bank Road | Durham | North East | England |  | 407060 | 528190 | Durham County Council | CMA/6/48 | [5 empty] | 2011-08-05 |  | 2015-05-06
B1499 | 4430 | 2020-02-03 | Statkraft | Windy Rig Wind Farm | Wind Onshore |  |  | 40.8 | n/a |  |  |  | 3 | 12 | 125 | n/a | Abandoned | Abandoned | Windy Rig, Approx 8km NE Of, Carsphairn, Castle Douglas | Dumfries and Galloway | Scotland | Scotland | DG7 3 | 261700 | 600000 | Dumfries and Galloway Council | 15/P/2/0155 | [5 empty] | 2015-05-20 | [6 empty] | 2018-11-05 |  |  |  | 2023-11-05
N00068W | 4431 | 2018-02-27 | Fred Olsen Renewables | Brochloch Rig (formerly Windy Standard II) | Wind Onshore |  |  | 61.5 | n/a |  |  |  | 3 | 30 |  | n/a | Operational | Operational | Near New Cummock | Dumfries and Galloway | Scotland | Scotland |  | 260200 | 602000 | Scottish Government (S36) | 02/n/20002 | [5 empty] | 2001-12-14 | [6 empty] | 2007-03-13 |  |  |  |  | 2014-08-07 | 2017-06-15
C2584 | 4432 | 2019-11-19 | Energiekontor UK | Withernwick extension | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2.05 | 4 |  | n/a | Operational | Operational | Land North And North East Homer House Aldbrough Road Withernwick East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England |  | 520743 | 441870 | East Riding of Yorkshire Council | 14/01919/STPLFE | APP/E2001/W/15/3133812 |  |  |  |  | 2014-06-24 |  | 2015-06-10 | 2015-10-15 |  |  | 2016-12-19 | 2016-12-19 |  |  |  |  | 2018-09-15 | 2019-08-01
B1005 | 4433 | 2015-05-26 | EDF Energy Renewables | Withy End - resubmission | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | Land at, Withy End, Causeway, Woolavington, TA9 3NP | Somerset | South West | England |  | 333400 | 143400 | Sedgemoor District Council | 54/13/00023 | [5 empty] | 2013-12-23 |  | 2015-05-07
A0217 | 4434 | 2019-04-02 | Mongoose (formerly Energy Law Unlimited) | Pogbie Wind Farm 1 | Wind Onshore |  |  | 5.1 | n/a |  |  |  | 8.5 | 6 |  | n/a | Operational | Operational | Humbie, East Lammermuirs, East Lothian.EH36 5PN | Lothian | Scotland | Scotland |  | 347905 | 659047 | East Lothian Council | 08/00823/FUL | [5 empty] | 2008-09-01 | [6 empty] | 2009-09-02 |  |  |  |  | 2016-11-01 | 2019-03-29
A0259 | 4435 | 2014-09-25 | West Coast Energy | Barlockhart Moor | Wind Onshore |  |  | 8.12 | n/a |  |  |  | 2.03 | 4 |  | n/a | Operational | Operational | Barlockhart Farm, Glenluce, Newton Stewart, Wigtownshire DG8 0JG | Dumfries and Galloway | Scotland | Scotland |  | 221183 | 555886 | Dumfries and Galloway Council | 08/P/1/0202 | [5 empty] | 2008-08-28 |  | 2009-07-03 |  |  |  | 2011-01-26 | 2011-01-26 | [5 empty] | 2013-08-27
A0480 | 4437 | 2017-05-31 | Minnygap (formerly RES) | Minnygap (Resubmission) | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Operational | Operational | Nr Annandale , Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 303800 | 596000 | Dumfries and Galloway Council | 09/P/3/0340 | [5 empty] | 2009-06-29 |  | 2012-10-31 |  |  |  | 2014-06-20 | 2014-06-20 |  |  |  |  | 2015-11-01 | 2017-03-15
AA067 | 4438 | 2014-09-25 | Community Windpower (Community Wind Power) | Mayfield wind farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Nr Rhonehouse, Castle Douglas, Dumfries and Galloway, DG7 | Dumfries and Galloway | Scotland | Scotland |  | 272398 | 556519 | Dumfries and Galloway Council | 11/P/2/0001 | [5 empty] | 2011-02-09 | 2011-06-09
AA453 | 4439 | 2015-11-05 | Ecotricity | Shipdham Wind Park (Resubmission) | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Planning Permission Refused | Application Refused | north west of Shipdham and to the south east of Dafffy Green | Norfolk | Eastern | England |  | 595297 | 308331 | Breckland Council | 3PL/2011/0854/F |  |  |  | 42066 |  | 2011-08-02 |  | 2012-09-20
AA463 | 4440 | 2019-05-16 | Banks Renewables | Middle Muir Wind Farm | Wind Onshore |  |  | 51 | n/a |  |  | 60 | 3.4 | 15 |  | n/a | Operational | Operational | Middle Muir, Hamilton, Strathclyde (north of Crawfordjohn) | Strathclyde | Scotland | Scotland | ML3 | 286178 | 625826 | Scottish Government (S36) | CL/12/0056 | [5 empty] | 2012-02-07 | [6 empty] | 2014-09-26 |  |  |  |  | 2017-01-16 | 2019-05-16
AA503 | 4441 | 2018-04-04 | Community Windpower | Sanquhar Community Windfarm | Wind Onshore |  |  | 32.4 | n/a |  |  |  | 3.4 | 9 |  | n/a | Operational | Operational | located approximately 7km Southwest of Sanquhar, 5km to the Southwest of Kirkconnel and 4km Southwest of the small steading of Drumbuie | Dumfries and Galloway | Scotland | Scotland |  | 270311 | 607479 | Dumfries and Galloway Council | 10/P/3/0182 | [5 empty] | 2010-04-27 | [6 empty] | 2013-02-27 |  |  |  |  | 2015-05-15 | 2018-02-01
A0026 | 4442 | 2014-09-25 | G & M Hodge & Son Ltd | Keith Hill | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Planning Permission Refused | Application Refused | Humbie, Lothian | Lothian | Scotland | Scotland | EH36 5PN | 347360 | 661013 | East Lothian Council | 09/00010/FUL | [5 empty] | 2009-01-05 |  | 2009-09-02
A0072 | 4443 | 2014-09-25 | Private Developer | Townhead Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Gifford, Haddington, Lothian. EH41 4PG | Lothian | Scotland | Scotland |  | 355007 | 668342 | East Lothian Council | 09/00385/FUL | [5 empty] | 2009-05-11 | 2009-07-17
A0172 | 4445 | 2020-06-04 | Scottish Southern Energy | Balmurrie Fell Wind Farm | Wind Onshore |  |  | 9.1 | n/a |  |  |  | 1.3 | 7 |  | n/a | Operational | Operational | Balmurrie Fell, Newton Stewart, Dunfries & Galloway. DG8 | Dumfries and Galloway | Scotland | Scotland |  | 238626 | 555982 | Dumfries and Galloway Council | 09/P/1/0224 | [5 empty] | 2009-06-30 | [6 empty] | 2011-11-25 |  |  |  |  | 2012-03-01 | 2012-09-01
A0174 | 4446 | 2014-09-25 | E.ON UK | Hill of Ochiltree | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Planning Permission Refused | Application Refused | Near Bargrennan, Newton Stewart, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG8 | 232395 | 574885 | Dumfries and Galloway Council | 09/P/1/0417 | [5 empty] | 2009-12-01 |  | 2012-12-04
AA536 | 4447 | 2014-09-25 | Private Developer | Plascow wind cluster | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Planning Permission Refused | Application Refused | near Dalbeattie, Dumfries | Dumfries and Galloway | Scotland | Scotland |  | 286898 | 563544 | Dumfries and Galloway Council | 09/P/2/0359 | [5 empty] | 2009-11-16 |  | 2012-04-23
AA564 | 4448 | 2020-05-28 | EDF & AMEC (Lewis Wind Power) | Uisenis/Eishken (Muaitheabhal) (East Extension) | Wind Onshore |  |  | 21.6 | n/a |  |  |  | 3.6 | 6 | 150 | n/a | Planning Permission Granted | Awaiting Construction | Eishken on Lewis, Eishkein Estate, Pairc/Park, Isle of Lewis | Western Isles | Scotland | Scotland |  | 132947 | 913350 | Scottish Government (S36) | [6 empty] | 2009-08-05 | [6 empty] | 2011-12-08 |  |  |  | 2016-12-08
AA575 | 4449 | 2019-11-20 | The Renewables Infrastructure Group (TRIG) | Solwaybank Wind Farm (resubmission) | Wind Onshore |  |  | 30 | n/a |  |  | 37.5 | 2 | 15 |  | n/a | Under Construction | Under Construction | Allfornought Hill, Langholm, Dumfries & Galloway (8 km south-west of Langholm and 12 km north of Gretna) | Dumfries and Galloway | Scotland | Scotland | DG13 0A | 329413 | 578978 | Dumfries and Galloway Council | 11/P/4/0354 | [5 empty] | 2011-11-08 |  | 2014-03-05 |  |  |  | 2014-09-24 | 2014-09-24 |  |  |  |  | 2018-08-15
AA629 | 4450 | 2014-09-11 | Private Developer | Burnfoot Hill Extension | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Site South Of The Upper And Lower Glendevon Resevoirs Glendevon | Tayside | Scotland | Scotland |  | 290393 | 703943 | Perth and Kinross Council | 11/01930/FLL | [5 empty] | 2011-12-09 | [6 empty] | 2013-04-02 | [5 empty] | 2014-09-09
AA663 | 4451 | 2015-05-18 | RWE Npower Renewables | Ashmark Hill Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Appeal Refused | Application Refused | 3km south west of New Cumnock in East Ayrshire | Strathclyde | Scotland | Scotland |  | 260611 | 610655 | East Ayrshire Council | 11/0983/PP | PPA-190-2042 |  |  |  |  | 2012-01-24 |  | 2014-09-03 | 2014-11-14 |  | 2015-05-11
AA681 | 4452 | 2014-09-25 | Community Windpower | Mayfield Community Wind Farm (resubmission) | Wind Onshore |  |  | 20.4 | n/a |  |  |  | 3.4 | 6 |  | n/a | Appeal Refused | Application Refused | Nr Rhonehouse, Castle Douglas, Dumfries and Galloway, DG7. | Dumfries and Galloway | Scotland | Scotland |  | 272392 | 555914 | Dumfries and Galloway Council | 11/P/2/0478 | [5 empty] | 2011-12-16 |  | 2012-12-18 |  |  | 2013-06-09
AA688 | 4453 | 2016-10-04 | Force 9 Energy | Blackwood Wind Farm | Wind Onshore |  |  | 10.25 | n/a |  |  |  | 2.05 | 5 |  | n/a | Appeal Refused | Application Refused | LAND TO EAST OF BLACKCRAIG HILL, HIGH AULDGIRTH, DUMFRIES | Dumfries and Galloway | Scotland | Scotland |  | 291675 | 587398 | Dumfries and Galloway Council | 12/P/3/0060 | PPA-170-2118 |  |  |  |  | 2012-02-14 |  | 2016-05-26 | 2016-08-26 |  | 2016-08-26
AA740 | 4454 | 2020-03-11 | W Ramsay & Sons Ltd | Knockman Hill Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 1 | 5 |  | n/a | Planning Permission Granted | Awaiting Construction | Milnmark Farm, St Johns Town Of Dalry, Castle Douglas, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 266921 | 583507 | Dumfries and Galloway Council | 10/P/2/0021 | N/A |  |  |  |  | 2010-12-01 | [6 empty] | 2018-11-06
AA755 | 4455 | 2014-09-25 | 2020 Renewables | Loch Hill Wind Farm | Wind Onshore |  |  | 25.3 | n/a |  |  |  | 2.3 | 11 | 100 | n/a | Appeal Refused | Application Refused | St johns town of Dalry | Dumfries and Galloway | Scotland | Scotland |  | 266200 | 584260 | Dumfries and Galloway Council | 10/P/2/0427 | PPA-170-2083 |  |  |  |  | 2010-12-13 |  | 2013-09-27 |  |  | 2014-07-04
B0239 | 4457 | 2019-09-16 | Element Power | Twentyshilling Hill Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Abandoned | Abandoned | Sanquhar, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 279500 | 604500 | Dumfries and Galloway Council | 13/P/3/0260 | [5 empty] | 2013-05-28 | [6 empty] | 2015-07-01
B0293 | 4458 | 2015-10-05 | RWE Npower Renewables | Hemswell Cliff Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Appeal Refused | Application Refused | Hemswell Cliff, 13km east of Gainsborough | Lincolnshire | East Midlands | England |  | 495490 | 392000 | West Lindsey District Council | 128940 | APP/N2535/A/14/2217829 |  |  |  |  | 2012-08-03 |  | 2013-01-01 | 2014-05-16 |  | 2015-09-14
B0298 | 4459 | 2018-09-03 | Banks Renewables | Knockendurrick Wind Farm | Wind Onshore |  |  | 14 | n/a |  |  |  | 3.4 | 7 | 115 | n/a | Planning Permission Refused | Application Refused | KNOCKENDURRICK WIND FARM, IRELANDTON MOOR, TWYNHOLM, KIRKCUDBRIGHT | Dumfries and Galloway | Scotland | Scotland |  | 264095 | 557561 | Dumfries and Galloway Council | 13/P/2/0284 | [5 empty] | 2013-10-11 |  | 2018-08-17
B0325 | 4461 | 2016-08-03 | Community Windpower | AUCHLEAND FARM Wind Farm | Wind Onshore |  |  | 23.8 | n/a |  |  |  | 3.4 | 7 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Auchleand Farm, Wigtown | Dumfries and Galloway | Scotland | Scotland |  | 240184 | 558502 | Dumfries and Galloway Council | 13/P/1/0366 | [5 empty] | 2013-12-09 | 2016-07-05
B0333 | 4462 | 2017-12-01 | NTR | Airies Farm | Wind Onshore |  |  | 35 | n/a |  |  |  | 2.9 | 14 | 137 | n/a | Operational | Operational | Airies Farm, Glenluce | Dumfries and Galloway | Scotland | Scotland | DG8 8AL | 229266 | 548481 | Dumfries and Galloway Council | 12/P/1/0271 | [5 empty] | 2012-08-24 | [6 empty] | 2013-03-01 |  |  |  |  | 2016-02-08 | 2017-03-15
B0538 | 4464 | 2019-03-28 | I & H Brown NC Ltd | North Calliachar Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Abandoned | Abandoned | Land 2000 Metres North Of Calliachar Wind Farm, Amulree | Tayside | Scotland | Scotland |  | 285519 | 744254 | Perth and Kinross Council | 13/00653/FLM | PPA-340-2087 |  |  |  |  | 2013-04-16 |  | 2014-05-29 | 2014-08-08 |  |  | 2015-03-30 | 2015-03-30 |  |  |  | 2018-03-30
B0605 | 4465 | 2017-05-23 | Temporis Capital | Craig Wind Farm (Extension) | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Westerkirk | Dumfries and Galloway | Scotland | Scotland |  | 202000 | 557000 | Dumfries and Galloway Council | 09/P/4/0342 | [5 empty] | 2009-08-21 | [6 empty] | 2015-02-05 |  |  |  | 2018-01-05 | 2016-08-15 | 2017-05-15
B0647 | 4466 | 2018-10-31 | Falck Renewables | Mochrum Fell Wind Farm | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 |  | n/a | Appeal Granted | Awaiting Construction | Mochrum Fell, Corsock | Dumfries and Galloway | Scotland | Scotland |  | 272064 | 574913 | Dumfries and Galloway Council | 13/P/2/0327 | PPA-170-2102 |  |  |  |  | 2013-11-29 |  | 2015-06-26 | 2015-09-24 |  |  | 2016-07-05 | 2016-07-05
B0724 | 4470 | 2015-03-09 | Upper Vaunces Wind Farm | Upper Vaunces Wind Farm (Resubmission) | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Secretary of State - Refusal | Application Refused | Land east of Semere Green Road (forming part of Upper Vaunces Farm) | Norfolk | Eastern | England |  | 618862 | 283796 | South Norfolk Council | 2013/0725 | APP/L2630/A/13/2203839 |  |  |  |  | 2013-04-26 |  | 2013-08-21 | 2013-09-16 |  | 2015-01-15 |  |  |  | 2015-01-15
B0729 | 4471 | 2015-05-28 | Spittal Hill Windfarm | Spittal Hill (Resubmission) | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Appeal Refused | Application Refused | Land 1300M East Of Spittal Hill, Spittal | Highland | Scotland | Scotland |  | 317900 | 956030 | Highland Council | 13/04559/FUL | PPA-270-2119 |  |  |  |  | 2013-12-03 |  | 2014-09-11 | 2014-12-05 |  | 2015-05-12
B1298 | 4473 | 2015-10-29 | REG Windpower | Hay Close Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Appeal Withdrawn | Application Refused | Hay Close Farm, between Low Braithwaite and Calthwaite in Cumbria. | Cumbria | North West | England |  | 344644 | 541475 | Eden District Council | 14/0637 | APP/H0928/W/15/3017315 |  |  |  |  | 2014-07-18 |  | 2014-10-16 | 2015-06-29 | 2015-10-29
B1379 | 4475 | 2018-08-30 | Seneca Global Energy | Tofts Road Wind Turbine | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 7.5 | 1 | 175 | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Tofts Road West, Hartlepool | Cleveland | North East | England |  | 451380 | 528135 | Hartlepool Borough Council | H/2014/0254 | APP/H0724/V/15/3136466 | APP/H0724/V/15/3136466 |  |  |  | 2014-06-20 | 2018-08-30
B1380 | 4476 | 2018-08-30 | Seneca Global Energy | Graythorp Wind Turbine | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 7.5 | 1 | 206.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Graythorp Industrial Estate, Hartlepool | Cleveland | North East | England |  | 451496 | 527495 | Hartlepool Borough Council | H/2014/0252 | APP/H0724/V/15/3136429 | APP/H0724/V/15/3136429 |  |  |  | 2014-06-23 | 2018-08-30
B1425 | 4477 | 2016-08-03 | Ecotricity | California Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 | 110 | n/a | Appeal Refused | Application Refused | Land north of the A75, Between Gatehouse of Feet and, Creetown, Near Carsluith | Dumfries and Galloway | Scotland | Scotland | DG8 | 250945 | 554878 | Dumfries and Galloway Council | 15/P/2/0053 | PPA-170-2107 |  |  |  |  | 2015-02-20 |  |  | 2016-01-28 |  | 2016-07-19
B1469 | 4478 | 2014-09-30 | Messrs N & K A Tucker | Fullabrook Farm Wind Turbine | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Fullabrook Farm, Fullabrook, Iflacombe, Devon | Devon | South West | England | EX34 8NJ | 252500 | 140085 | North Devon District Council | 57572 | [5 empty] | 2014-07-07 | 2014-09-01
C0797 | 4481 | 2015-11-30 | P I Renewables Ltd | Carn Gorm Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3 | 14 |  | n/a | Appeal Refused | Application Refused | Land 4KM North East Of Garve | Highland | Scotland | Scotland |  | 242300 | 863500 | Highland Council | 13/04791/FUL | PPA-270-2117 |  |  |  |  | 2013-12-20 |  | 2014-09-05 | 2014-12-04 |  | 2015-11-09
C1118 | 4482 | 2014-09-25 |  | Spango Community Wind Farm | Wind Onshore |  |  | 49 | n/a |  |  |  | 3.5 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 4km north of Sanquhar | Dumfries and Galloway | Scotland | Scotland |  | 277050 | 614873 | Dumfries and Galloway Council | 13/P/3/0578 | [5 empty] | 2014-01-10 | 2014-06-30
C1235 | 4483 | 2017-05-19 | Wind Energy Direct | Lawrence Landfill | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 |  | n/a | Operational | Operational | Lawrence Landfill, Pope Hill, Johnston, Haverfordwest, Dyfed, SA62 3NX | Dyfed | Wales | Wales |  | 193075 | 212682 | Pembrokeshire County Council | 12/1206/PA | [5 empty] | 2013-04-12 |  | 2014-03-10 |  |  |  | 2014-08-26 | 2014-08-26 |  |  |  |  | 2016-08-15 | 2017-03-15
C1313 | 4484 | 2016-03-14 | Private Developer | Plascow wind cluster (resubmission) | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 0.8 | 3 |  | n/a | Operational | Operational | Plascow Farm, Dalbeattie, Dumfries and Galloway, DG5 | Dumfries and Galloway | Scotland | Scotland |  | 287380 | 563820 | Dumfries and Galloway Council | 13/P/2/0129 | [5 empty] | 2013-05-09 | [6 empty] | 2014-03-27 |  |  |  | 2017-03-27 | 2015-04-01 | 2015-07-15
C1410 | 4485 | 2017-06-21 | Pennant Walters (MAESX) Limited | Maesgwyn Wind Farm - extension | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 |  | n/a | Operational | Operational | Maesgwyn Wind Farm Between Onllwyn & Glynneath | West Glamorgan | Wales | Wales |  | 286568 | 205930 | Neath Port Talbot County Borough Council | P2014/0733 | [5 empty] | 2014-08-15 | [6 empty] | 2015-12-17 |  |  |  | 2020-12-17 | 2016-01-21 | 2016-03-29
C1491 | 4486 | 2018-02-28 | Renewable Energy Systems (RES) | Annabaglish Wind Farm | Wind Onshore |  |  | 35 | n/a |  |  |  | 2.5 | 14 |  | n/a | Appeal Refused | Application Refused | ANNABAGLISH, NEAR GLENLUCE | Dumfries and Galloway | Scotland | Scotland |  | 228450 | 557980 | Dumfries and Galloway Council | 13/P/1/0351 | PPA-170-2127 |  |  |  |  | 2013-10-31 |  | 2017-07-12 | 2017-10-11 |  | 2018-02-26
C1581 | 4487 | 2019-04-01 | Scottish Power Renewables | Wether Hill WindFarm (extension) | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 11 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | East and north of Wether Hill, Carsphairn, North west of Moniave, Castle Douglas | Dumfries and Galloway | Scotland | Scotland | DG7 3TQ | 270506 | 593932 | Dumfries and Galloway Council | 15/P/3/0502 | [5 empty] | 2015-12-21 | 2019-02-20
C2060 | 4489 | 2014-09-30 | Caithness Power | Upper Smerral Wind Cluster - resubmission | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 |  | n/a | Planning Permission Refused | Application Refused | Land 690M SE Of Newlands Of Houstry Dunbeath | Highland | Scotland | Scotland |  | 316370 | 934150 | Highland Council | 13/03555/FUL | [5 empty] | 2013-09-19 |  | 2014-05-26
C2318 | 4490 | 2015-07-01 | WK Extension Project Ltd | Little Raith Farm - extension | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Appeal Refused | Application Refused | Little Raith Farm, Gleniston, Auchtertool, Fife | Fife | Scotland | Scotland |  | 322245 | 692552 | Fife Council | 14/02444/EIA | PPA-250-2212 |  |  |  |  | 2014-07-18 |  |  | 2014-12-29 |  | 2015-06-30
C2438 | 4491 | 2020-03-11 | West Coast Energy | BARLOCKHART MOOR - extension | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2.1 | 4 |  | n/a | Planning Permission Granted | Awaiting Construction | BARLOCKHART MOOR, GLENLUCE | Dumfries and Galloway | Scotland | Scotland |  | 222700 | 557109 | Dumfries and Galloway Council | 13/P/1/0136 | [5 empty] | 2013-03-25 | [6 empty] | 2015-09-15 |  |  |  | 2018-09-15
C3003 | 4492 | 2020-02-07 | Forsa (formerly Buccleuch/2020) | Glenmuckloch Wind Farm | Wind Onshore |  |  | 25.6 | n/a |  |  |  | 3.2 | 8 | 133.5 | n/a | Planning Permission Granted | Awaiting Construction | LAND NORTH OF GLENMUCKLOCH SURFACE COAL MINE | Dumfries and Galloway | Scotland | Scotland | DG4 | 270269 | 615690 | Dumfries and Galloway Council | 15/P/3/0236 | [5 empty] | 2015-06-15 | [6 empty] | 2017-05-16 |  |  |  | 2020-05-16
C3151 | 4493 | 2016-10-20 | Wentworth and Harper | Halifax Farm | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 1.6 | 1 |  | n/a | Operational | Operational | Halifax Farm, Merrylees Road, Newbold Heath, Newbold Verdon, Leicester, Leicestershire | Leicestershire | East Midlands | England | LE9 9NR | 445759 | 304887 | Hinckley and Bosworth Borough Council | 14/00532/FUL | [5 empty] | 2014-06-02 | [6 empty] | 2014-09-18 |  |  |  |  | 2015-05-15 | 2015-09-01
C3196 | 4494 | 2014-09-25 | Private Developer | HOLLAMOOR FARM (wind) | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | LAND AT HOLLAMOOR FARM (OS GRID REFERENCES 254630/130550, 254877/130706 & 254958/130472) TAWSTOCK DEVON EX31 3NY | Devon | South West | England |  | 254630 | 130550 | North Devon District Council | 57728 | [5 empty] | 2014-06-27 | 2014-08-21
C3297 | 4495 | 2015-01-06 | wpd Rothmaise | Hill Of Rothmaise | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Appeal Refused | Application Refused | Site To The North Of Hill Of Rothmaise Rothienorman Inverurie | Grampian | Scotland | Scotland |  | 369350 | 834350 | Aberdeenshire Council | APP/2014/2740 | PPA-110-2276 |  |  |  |  | 2014-07-25 |  | 2015-05-26 | 2015-07-24 |  | 2015-12-17
C3302 | 4496 | 2015-12-02 | Infinite Renewables | Malthouse Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Malthouse Farm, Heol Las, Llantrisant, Pontyclun, Mid Glamorgan | Mid Glamorgan | Wales | Wales | CF72 8EG | 303640 | 185362 | Rhondda Cynon Taff County Borough Council | 14/0913/10 | [5 empty] | 2014-07-09 | 2015-11-04
C3307 | 4497 | 2016-06-13 | REsense c/o CO2Sense | Norton Fields Farm | Wind Onshore |  |  | 1.3 | n/a |  |  |  | 1.3 | 1 |  | n/a | Operational | Operational | Norton Fields Farm, Mucknell Farm Lane, Stoulton, Worcester | Hereford and Worcester | West Midlands | England | WR7 4RB | 390334 | 251792 | Wychavon District Council | 14/01569 | [5 empty] | 2014-07-18 | [6 empty] | 2014-12-03 |  |  |  | 2017-12-03 | 2015-06-15 | 2015-09-15
C3334 | 4498 | 2015-08-05 | J & L C Beattie Ltd | Brackenhills Farm | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 |  | n/a | Planning Permission Refused | Application Refused | Land To The North Of Brackenhills Cornhill Banff | Grampian | Scotland | Scotland |  | 358366 | 859859 | Aberdeenshire Council | APP/2014/2817 | [5 empty] | 2014-08-08 |  | 2015-07-02
C3354 | 4499 | 2014-12-05 | Infinite Renewables Limited | Redland Roof Tiles Ltd | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 |  | n/a | Planning Permission Refused | Application Refused | Gibbet Lane, Shawell, Leicestershire | Leicestershire | East Midlands | England | LE17 6AB | 453441 | 280638 | Harborough District Council | 14/01167/FUL | [5 empty] | 2014-08-21 |  | 2014-11-20
EN00035 | 4500 | 2014-09-25 | Renewable Energy Systems (RES) | Solway Bank | Wind Onshore |  |  | 42 | n/a |  |  |  | 2 | 21 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Solway Bank, Allfornought Hill, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 334490 | 586994 | Dumfries and Galloway Council | 09/P/4/0238 | [5 empty] | 2009-06-18 | 2010-07-01
EN00036 | 4501 | 2016-06-27 | John Laing Environmental Assets Group/ REG Power Management | Carscreugh Renewable Energy Park | Wind Onshore |  |  | 15.3 | n/a |  |  |  | 0.85 | 18 |  | n/a | Operational | Operational | Gelnluce, nr Luce Bay Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 225000 | 555000 | Dumfries and Galloway Council | 06/P/1/0113 | [5 empty] | 2006-05-01 |  | 2011-05-03 | [9 empty] | 2013-06-01 | 2014-01-15
EN00149 | 4502 | 2018-05-22 | Whiteside Hill Farm (Scotland) | Whiteside Hill | Wind Onshore |  |  | 25.3 | n/a |  |  |  | 2.3 | 11 |  | n/a | Operational | Operational | Whiteside Hill near Sanquhar | Dumfries and Galloway | Scotland | Scotland |  | 271440 | 608920 | Dumfries and Galloway Council | 06/P/3/0351 | [5 empty] | 2006-06-15 | [6 empty] | 2013-02-26 |  |  |  | 2018-02-26 | 2016-01-15 | 2018-04-30
EN00198 | 4504 | 2014-09-25 |  | Slieve Rushen Extension | Wind Onshore |  |  | 54 | n/a |  |  |  | 3 | 18 |  | n/a | Operational | Operational | Slieve Rushen Derrylin Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 33019 | 491811 | Northern Ireland Planning Service | L/2004/2058/F | [5 empty] | 2004-11-04 | [6 empty] | 2006-10-01 | [5 empty] | 2008-04-15
EN00201 | 4505 | 2018-08-30 | North British Wind Power | Margree Windfarm | Wind Onshore |  |  | 34 | n/a |  |  |  | 2 | 17 |  | n/a | Abandoned | Abandoned | Margree, 6km North East of St John's town of Dalry | Dumfries and Galloway | Scotland | Scotland |  | 267500 | 586500 | Dumfries and Galloway Council | 06/P/2/0391 | [5 empty] | 2006-09-25
EN00207 | 4506 | 2014-09-25 | Natural Power Consultants | Barnbackle Windfarm | Wind Onshore |  |  | 5 | n/a |  |  |  | 2 | 2 |  | n/a | Planning Permission Refused | Application Refused | Barnbackle Hill, 2km west of Lochfoot | Dumfries and Galloway | Scotland | Scotland |  | 287395 | 573140 | Dumfries and Galloway Council | 07/P/2/0006 | [5 empty] | 2007-01-08 |  | 2011-11-28
EN00208 | 4507 | 2014-09-25 | Natural Power Consultants | Doon Hill Windfarm | Wind Onshore |  |  | 4.9 | n/a |  |  |  | 2.45 | 2 |  | n/a | Appeal Refused | Application Refused | Doon Hill, Upper Porterbelly Farm, Kirkgunzeon | Dumfries and Galloway | Scotland | Scotland |  | 285285 | 566450 | Dumfries and Galloway Council | 07/P/2/0005 | PPA-170-2003 |  |  |  |  | 2007-01-15 |  | 2007-02-15 |  |  | 2009-09-30
EN00234 | 4508 | 2015-01-05 | Greencoat UK Wind | North Rhins | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 11 |  | n/a | Operational | Operational | North Rhins Stranraer Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 201980 | 557960 | Dumfries and Galloway Council | [6 empty] | 2007-01-15 | [6 empty] | 2008-03-14 |  |  |  |  | 2009-10-01 | 2010-01-20
EN00239 | 4509 | 2018-08-30 | North British Wind Power | Ulzieside | Wind Onshore |  |  | 40 | n/a |  |  |  | 2 | 20 |  | n/a | Abandoned | Abandoned | Ulzieside, 4km south west of Sanquhar | Dumfries and Galloway | Scotland | Scotland |  | 273560 | 605960 | Dumfries and Galloway Council | 06/P/3/0527 | [5 empty] | 2006-09-01
EN00242 | 4510 | 2014-09-25 | EDF / Your Energy | West Hinkley Wind Farm (withdrawn) | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Land to West of Hinkley Point Power Station, Stogursey, Bridgwater, Somerset | Somerset | South West | England |  | 319900 | 145592 | West Somerset District Council | 3/32/06/032 | [6 empty] | 2014-09-25
EN00286 | 4511 | 2014-10-02 | East Coast Viners | Jacksbank Wind Farm (Glenbervie) | Wind Onshore |  |  | 6.8 | n/a |  |  |  | 2.26 | 3 |  | n/a | Operational | Operational | Drumlithie, Stonehaven | Grampian | Scotland | Scotland | AB39 3YL | 376574 | 783246 | Aberdeenshire Council | APP/2010/0487 | [5 empty] | 2010-02-22 | [6 empty] | 2013-04-26 | [5 empty] | 2014-07-12
EN00576 | 4513 | 2016-08-25 | John Laing Environmental Assets Group | New Albion Wind Farm | Wind Onshore |  |  | 14.35 | n/a |  |  |  | 2.05 | 7 |  | n/a | Operational | Operational | Agricultural land at Towns Close Farm, between Pipewell and Rushton and close to the A6003 Road to Corby | Northamptonshire | East Midlands | England | NN14 1QT | 484680 | 284310 | Kettering Borough Council | KET/2009/0549 | [5 empty] | 2009-08-29 | [6 empty] | 2010-01-20 |  |  |  |  | 2015-01-01 | 2016-01-18
H0047 | 4514 | 2016-10-26 | Sunnyside Wind Farm | Sunnyside wind cluster | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 |  | n/a | Operational | Operational | Land at Sunnyside, Sanquhar | Dumfries and Galloway | Scotland | Scotland | DG4 6JP | 276612 | 611178 | Dumfries and Galloway Council | 13/P/3/0211 | [5 empty] | 2013-04-05 | [6 empty] | 2013-12-19 |  |  |  |  | 2015-06-15 | 2015-11-15
IF1214 | 4515 | 2015-07-29 | Renewable Energy Systems (RES) | Barcloy Hill Wind Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | Kirkcudbright, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 274300 | 553100 | Dumfries and Galloway Council | 12/P/2/0357 | PPA-170-2099 |  |  |  |  | 2012-12-21 |  | 2014-07-18 | 2014-10-17 |  | 2015-07-23
IF1353 | 4516 | 2018-09-01 | Sky Wind Energy | Keith Hill (resubmission) | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 0.9 | 5 |  | n/a | Operational | Operational | Humbie, East Lothian | Lothian | Scotland | Scotland | EH36 5PN | 348373 | 658532 | East Lothian Council | 10/00985/P | [5 empty] | 2010-11-15 | [6 empty] | 2011-04-01 |  |  |  |  | 2017-06-27 | 2017-12-19
N00090W | 4517 | 2014-09-25 | Airtricity | Minsca | Wind Onshore |  |  | 36.8 | n/a |  |  |  | 2.3 | 16 |  | n/a | Operational | Operational | 8km NE of Lockerbie Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 313821 | 581690 | Dumfries and Galloway Council | 03p40389 | [5 empty] | 2003-08-27 | [6 empty] | 2004-06-27 | [5 empty] | 2008-03-01
N00160W | 4518 | 2020-06-04 | Scottish and Southern Energy (SSE) | Artfield Fell | Wind Onshore |  |  | 19.5 | n/a |  |  |  | 1.3 | 15 |  | n/a | Operational | Operational | Artfield Fell Near New Luce NX230670 | Dumfries and Galloway | Scotland | Scotland |  | 222500 | 567500 | Dumfries and Galloway Council | 03-P-1-0195 | [5 empty] | 2003-09-24 | [6 empty] | 2004-02-01 | [5 empty] | 2005-06-23
N00167W | 4519 | 2014-09-25 | Scottish Power/CRE Energy | Wether Hill | Wind Onshore |  |  | 18.2 | n/a |  |  |  | 1.3 | 14 |  | n/a | Operational | Operational | Moniaive Dumfries | Dumfries and Galloway | Scotland | Scotland |  | 270000 | 594000 | Dumfries and Galloway Council | 03P30746 | [5 empty] | 2004-01-08 | [6 empty] | 2005-03-01 |  |  |  |  | 2006-08-01 | 2007-05-01
N00178W | 4520 | 2014-09-25 | Airtricity Scotland | Dalswinton | Wind Onshore |  |  | 30 | n/a |  |  |  | 2 | 15 |  | n/a | Operational | Operational | Nr village of Dalswinton Dumfries | Dumfries and Galloway | Scotland | Scotland |  | 295000 | 589000 | Dumfries and Galloway Council | 03P30610 | [5 empty] | 2003-10-13 | [6 empty] | 2005-01-20 |  |  |  |  | 2007-04-01 | 2008-03-15
N00193W | 4521 | 2014-09-25 | Renewable Energy Systems (RES) | Minnygap | Wind Onshore |  |  | 30 | n/a |  |  |  | 2 | 15 |  | n/a | Planning Permission Refused | Application Refused | Nr Annandale , Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 303800 | 596000 | Dumfries and Galloway Council | 05/P/4/0349 | [5 empty] | 2005-06-13 |  | 2007-11-26
N00201W | 4522 | 2014-09-25 | Your Energy | West Hinkley Wind Farm | Wind Onshore |  |  | 33 | n/a |  |  |  | 2.75 | 12 |  | n/a | Planning Permission Refused | Application Refused | Land to West of Hinkley Point Nuclear Power Station Near Bridgwater Somerset | Somerset | South West | England |  | 319959 | 145592 | West Somerset District Council | 3/32/04/022 | [5 empty] | 2004-08-03 |  | 2005-10-26
N00260W | 4523 | 2020-05-28 | EDF & AMEC (Lewis Wind Power) | Uisenis/Eishken (Muaitheabhal) Wind Farm | Wind Onshore |  |  | 118.8 | n/a |  |  | 189 | 3.6 | 33 | 145 | n/a | Planning Permission Granted | Awaiting Construction | Eishken on Lewis, Eishkein Estate, Pairc/Park, Isle of Lewis | Western Isles | Scotland | Scotland |  | 126600 | 913600 | Scottish Government (S36) | [6 empty] | 2004-12-01 | [6 empty] | 2010-01-14
N00305W | 4524 | 2015-01-07 | Craig Wind Farm Co | Craig Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Operational | Operational | Westerkirk | Dumfries and Galloway | Scotland | Scotland |  | 331995 | 586055 | Dumfries and Galloway Council | 03/P/4/0326 | PPA-170-117 |  |  |  |  | 2003-07-23 |  | 2003-12-24 |  |  |  | 2004-11-09 | 2004-11-09 | [5 empty] | 2007-10-01
N00312W | 4525 | 2014-10-01 | Scottish Power Renewables | Beinn an Tuirc Phase 2 | Wind Onshore |  |  | 43.7 | n/a |  |  |  | 2.3 | 16 |  | n/a | Operational | Operational | South of original Beinn and Tuirc Nr. Carradale | Strathclyde | Scotland | Scotland |  | 173950 | 636900 | Argyll and Bute Council | 05/01397/DET | [5 empty] | 2005-07-07 | [6 empty] | 2007-07-13 |  |  |  |  | 2010-04-01 | 2014-09-01
N00542W | 4526 | 2014-09-25 | Community Wind Power | Aikengall | Wind Onshore |  |  | 48 | n/a |  |  |  | 3 | 16 |  | n/a | Operational | Operational | Aikengall Nr Innerwick Dunbar East Lothian EH42 1SG | Lothian | Scotland | Scotland |  | 369468 | 669455 | East Lothian Council | 05/00216/FUL | [5 empty] | 2005-02-24 | [6 empty] | 2007-03-16 | [5 empty] | 2008-11-01
S0001W1 | 4527 | 2018-09-04 | Fred Olsen Renewables | Brochloch Rig 1 (formerly Windy Standard) | Wind Onshore |  |  | 21.6 | n/a |  |  |  | 0.6 | 36 |  | n/a | Operational | Operational | Windy Standard , Dumfries & Galloway | Dumfries and Galloway | Scotland | Scotland |  | 261500 | 602500 | Dumfries and Galloway Council | [6 empty] | 1995-07-24 | [6 empty] | 1996-03-07 | [5 empty] | 1996-10-01
S0006W1 | 4528 | 2014-09-25 | RWE npower | Craigenlee Wind Farm | Wind Onshore |  |  | 7.837 | n/a |  |  |  | 0.5 | 14 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Craigenlee Fell / Broad Moor , Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 202000 | 557000 | Dumfries and Galloway Council | [7 empty] | 2014-09-25
S0031W3 | 4529 | 2019-12-06 | Torrs Hill Windfarm Ltd | Torrs Hill | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Under Construction | Under Construction | 10km NW of New Galloway | Dumfries and Galloway | Scotland | Scotland |  | 252600 | 589000 | Dumfries and Galloway Council | 03/P/2/0252 | [5 empty] | 2003-06-09 | [6 empty] | 2004-03-23 |  |  |  |  | 2009-02-15
A0180a | 4530 | 2014-09-16 | Broadview Energy | Starbold Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Appeal Refused | Application Refused | Knightcote, Stratford on Avon | Warwickshire | West Midlands | England |  | 438458 | 256173 | Stratford on Avon District Council | 12/00330/FUL | APP/J3720/A/13/2193579/NWF |  |  |  |  | 2012-04-04 |  | 2013-02-13 | 2014-04-03 |  | 2014-10-01
AA560 | 4531 | 2014-12-31 | EDF | Dorcas Lane Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Secretary of State - Refusal | Application Refused | Land To South Of Dorcas Lane Off Newton Road Stoke Hammond Buckinghamshire | Buckinghamshire | South East | England |  | 486512 | 228171 | Aylesbury Vale District Council | 11/02798/APP | APP/J0405/A/13/2205701 |  |  |  |  | 2012-12-06 |  | 2013-03-20 | 2013-12-12 |  | 2014-12-23 |  |  |  | 2014-12-23
AA590 | 4532 | 2017-10-31 | Temporis Capital | Hawton Wind Farm | Wind Onshore |  |  | 9 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Cotham Road, Hawton, Nottinghamshire | Nottinghamshire | East Midlands | England | NG24 3SD | 479589 | 350765 | Newark and Sherwood District Council | 11/01588/FULM | APP/B3030/A/12/2183042 |  |  |  |  | 2011-12-05 |  | 2012-08-22 | 2012-10-10 |  |  | 2014-09-29 | 2014-09-29 |  |  |  | 2017-09-29 | 2016-09-16 | 2017-03-16
AA654 | 4533 | 2015-03-17 | Roseland Community Energy Trust | Roseland Community Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Secretary of State - Refusal | Application Refused | Roseland, Derby, Derbyshire, S44. | Derbyshire | East Midlands | England |  | 449656 | 367041 | Bolsover District Council | 12/00159/FULEA | APP/R1010/A/14/2212093 |  |  |  |  | 2012-04-25 |  | 2013-07-19 | 2014-01-30 |  |  |  |  | 2014-06-01 | 2015-03-16
AA707 | 4534 | 2015-09-27 | Meenablagh Wind Farm | Meenablagh Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.5 | 10 |  | n/a | Appeal Refused | Application Refused | Tullycar, Altamullan Townlands, Aghyaran, Castlederg, Co. Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 27873 | 548066 | Northern Ireland Planning Service | J/2011/0148/F | 2012/A0186 |  |  |  |  | 2011-04-12 |  | 2012-09-15 | 2012-10-18 |  | 2015-09-24
B0006 | 4535 | 2014-12-31 | Waste Recycling Group | Ironstone Quarry Wind Farm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Secretary of State - Refusal | Application Refused | Winterton Landfill Site Off Coleby Road, West Halton & Top Road, Winterton, Scunthorpe, Humberside | Humberside | Yorkshire and Humber | England | DN15 9AP | 491053 | 419649 | North Lincolnshire Council | WF/2011/0528 | APP/Y2003/A/13/2207858 |  |  |  |  | 2011-05-17 |  | 2013-06-05 | 2013-11-21 |  | 2014-12-23 |  |  |  | 2014-12-23
B0197 | 4536 | 2014-09-16 | TCI Renewables | Streetwood Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 3 |  | n/a | Secretary of State - Refusal | Application Refused | Land surrounding, Busseys Loke, Hempnall, Norfolk | Norfolk | Eastern | England |  | 625062 | 295076 | South Norfolk Council | 2013/0105 | 13/00042/AGNDET |  |  |  |  | 2013-01-21 |  |  | 2013-10-31 | [5 empty] | 2014-10-27
B0396 | 4537 | 2014-09-16 | Vento Ludens | Balnacoil Wind Farm | Wind Onshore |  |  | 45 | n/a |  |  |  | 3 | 15 |  | n/a | Planning Permission Refused | Application Refused | Balnacoil Lodge Brora KW9 6LX | Highland | Scotland | Scotland |  | 280598 | 911334 | Highland Council | 13/03312/FUL | 14/00019/REFBS |  |  |  |  | 2013-09-04 |  | 2014-03-18
C0260 | 4538 | 2014-12-11 | RWE Npower Renewables | RAF Molesworth Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Secretary of State - Refusal | Application Refused | sw/o Raf Molesworth, Warren Lane, Bythorn, Huntingdon, Cambridgeshire | Cambridgeshire | Eastern | England | PE28 0QU | 505470 | 276784 | Huntingdonshire District Council | 1200967FUL | APP/H0520/A/13/2197548 |  |  |  |  | 2012-06-18 |  | 2014-05-02 | 2014-06-28 |  | 2014-12-05 |  |  |  | 2014-12-05
EN00400 | 4539 | 2015-10-05 | Wind Ventures (Acciona Energy) | Hirfynydd | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 9 |  | n/a | Appeal Refused | Application Refused | Farmland to the East of Crynant and Seven Sisters adjoining forestry at Hirfynydd | West Glamorgan | Wales | Wales |  | 281375 | 205945 | Neath Port Talbot County Borough Council | P2008/0024 | APP/Y6930/A/13/2209942 |  |  |  |  | 2008-01-17 |  | 2013-11-12 | 2014-01-20 |  | 2015-09-04
C0750 | 4540 | 2015-07-01 | artine Partnership Ltd | Floors Farm Wind Turbines | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Refused | Application Refused | Floors Farm Auchterless Fortrie Turriff AB53 4HP | Grampian | Scotland | Scotland |  | 367379 | 842167 | Aberdeenshire Council | APP/2012/3956 | [5 empty] | 2012-11-30 |  | 2015-05-26
C1630a | 4541 | 2014-12-16 | Polar Energy (Finlarg) Ltd | Frawney Wind Farm - 2nd resubmission | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Planning Permission Refused | Application Refused | Frawney Wind Farm In Field 1020M North Of Over Finlarg Farm Over Finlarg Lumleyden | Tayside | Scotland | Scotland |  | 341650 | 742250 | Angus Council | 14/00442/EIAL | [5 empty] | 2014-06-04 |  | 2014-10-02
C2038 | 4542 | 2014-12-05 | Prowind UK | Cottam wind farm (resubmission) | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Cottam Wind Farm Headstead Bank Cottam Nottinghamshire | Nottinghamshire | East Midlands | England |  | 481025 | 381388 | Bassetlaw District Council | 13/00423/FUL | [5 empty] | 2013-09-03 | 2014-12-04
C2613 | 4543 | 2015-10-29 | Kelda Water Services | Gorpley Wind Farm - resubmission | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Appeal Withdrawn | Application Refused | Land South West Of Gorpley Reservoir, Bacup Road, Todmorden | West Yorkshire | Yorkshire and Humber | England |  | 389706 | 422678 | Calderdale Metropolitan Borough Council | 14/00126/WDF | APP/A4710/W/15/3008309 |  |  |  |  | 2014-02-05 |  | 2014-10-07 | 2015-04-29 | 2015-10-29
C2345 | 4544 | 2017-05-02 | EDF Energy Renewables | Beck Burn (resubmission) | Wind Onshore |  |  | 31 | n/a |  |  |  | 3.45 | 9 |  | n/a | Operational | Operational | Beck Burn Peat Works, Springfield, Longtown | Cumbria | North West | England | CA6 5NH | 334466 | 568940 | Carlisle City Council | 13/0866 | [5 empty] | 2013-11-08 | [6 empty] | 2015-04-30 |  |  |  | 2018-04-30 | 2016-04-23 | 2017-04-26
C2663 | 4545 | 2018-10-24 | Good Energy | Big Field Wind Farm | Wind Onshore |  |  | 25.3 | n/a |  |  |  | 2.3 | 11 |  | n/a | Appeal Refused | Application Refused | The Big Field Wind Farm Land At And Adjoining Creddacott Farm, Week St Mary, Holsworthy | Cornwall | South West | England | EX22 6UU | 223583 | 95997 | Cornwall Council | PA14/02107 | APP/D0840/W/15/3014917 |  |  | 43020 |  | 2014-03-06 |  | 2014-10-28 | 2015-06-16 |  | 2017-07-26
A0231 | 4546 | 2014-09-18 | Pennant Walters | Esgair Cwmowen | Wind Onshore |  |  | 51 | n/a |  |  |  | 3 | 17 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Cwnowen, Carno, Powys | Powys | Wales | Wales |  | 298818 | 299545 | DECC (S36) | [7 empty] | 2014-09-18
A0046 | 4547 | 2015-05-28 | Acciona Energy | Auchencairn Forest | Wind Onshore |  |  | 32 | n/a |  |  |  | 2.5 | 16 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Closeburn, Thornhill, Dumfries & Galloway | Dumfries and Galloway | Scotland | Scotland | DG3 5JU | 295163 | 592458 | Dumfries and Galloway Council | 11/P/3/0397 | [5 empty] | 2011-09-12 | 2015-05-08
B1033 | 4548 | 2015-04-07 | Airvolution Energy | Rawcliffe Bridge Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused | Rawcliffe Bridge, nr Goole | Humberside | Yorkshire and Humber | England |  | 471091 | 420792 | East Riding of Yorkshire Council | 13/04183/STPLFE | [5 empty] | 2014-02-04 |  | 2015-02-24
C3154 | 4549 | 2018-10-29 | Seneca Global Energy | Melton Common Wind Cluster | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 |  | n/a | Operational | Operational | Land West, South And South East Of Melton Waste Park Gibson Lane South Melton East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England | HU14 3LJ | 496427 | 425524 | East Riding of Yorkshire Council | 14/01499/STPLFE | [5 empty] | 2014-06-12 | [6 empty] | 2015-10-29 |  |  |  | 2018-10-29 | 2016-09-01 | 2017-03-15
B1002 | 4550 | 2015-09-02 | FCC Environment | Hundred Road Wind Turbines | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Appeal Withdrawn | Application Refused | March Landfill site on Hundred Road, Cambridgeshire | Cambridgeshire | Eastern | England |  | 524281 | 308071 | Fenland District Council | F/YR11/0444/F | APP/D0515/W/15/3032548 |  |  |  |  | 2011-06-08 |  | 2014-11-13 | 2015-06-30 | 2015-08-20
B1001 | 4551 | 2015-04-07 | Tapar | High Boar Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 | 110 | n/a | Planning Permission Refused | Application Refused | North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 425087 | 455635 | Harrogate Borough Council | 12/03934/EIAMAJ | [5 empty] | 2012-10-05 |  | 2015-04-01
A0258 | 4552 | 2020-03-11 | RWE Innogy UK | Clocaenog Forest Wind Farm | Wind Onshore |  |  | 96 | n/a |  |  | 96 | 3.6 | 27 |  | n/a | Under Construction | Under Construction | Clocaenog forest, Ruthin, Clwyd | Clwyd | Wales | Wales | LL15 | 300324 | 353682 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2013-04-23 | [6 empty] | 2014-09-12 |  |  |  | 2019-09-12 | 2018-03-19
B0336 | 4553 | 2014-01-08 | Partnerships for Renewables | Camp Hill Wind Farm | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 |  | n/a | Planning Permission Refused | Application Refused | land at HMP Camp Hill Parkhurst Road Newport Isle Of Wight | Isle of Wight | South East | England | PO30 | 448402 | 90959 | Isle of Wight Council | P/00491/12 | [5 empty] | 2013-10-11 |  | 2014-12-18
B0076 | 4554 | 2016-09-01 | Coriolis Energy and Falck Renewables | Ongar Hill Wind Farm | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 9 |  | n/a | Appeal Refused | Application Refused |  | Norfolk | Eastern | England |  | 558062 | 323565 | King's Lynn and West Norfolk Borough Council | 12/00321/FM | APP/V2635/W/15/3132154 |  |  |  |  | 2012-03-07 |  | 2015-02-03 | 2015-10-06 |  | 2016-06-14
B1056 | 4555 | 2015-12-02 | Crown Hill Wind Farm Limited | Crown Hill Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 4 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Fields OS 8300 0006 And 3400 Dalby Road Melton Mowbray | Leicestershire | East Midlands | England |  | 474607 | 315450 | Melton Borough Council | 14/00397/FUL | [5 empty] | 2014-05-12 | 2015-10-01
AA583 | 4556 | 2016-06-27 | Wind Prospect Developments | Fox Covert Wind Farm | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Secretary of State - Refusal | Application Refused | Cotham Road, Hawton, Nottinghamshire | Nottinghamshire | East Midlands | England |  | 479056 | 349071 | Newark and Sherwood District Council | 13/00889/FULM | APP/B3030/W/15/3003130 | APP/B3030/W/15/3003130 | Recovery |  |  | 2013-07-04 |  | 2014-10-09 | 2015-05-10 |  | 2015-09-29 |  |  | 2016-01-20 | 2016-06-30
AA709 | 4557 | 2017-05-04 | Altamuskin Windfarm (Energia) | Altamuskin Extension | Wind Onshore |  |  | 7.05 | n/a |  |  |  | 2.35 | 3 | 110 | n/a | Operational | Operational | Sixmilecross, Clogher, Co. Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 69316 | 525078 | Northern Ireland Planning Service | K/2011/0239/F | N/A |  |  |  |  | 2011-04-13 | [6 empty] | 2015-01-28 |  |  |  | 2020-01-28 | 2016-03-01 | 2017-03-15
AA710 | 4558 | 2018-02-23 | Energia (formerly Brookfield Renewable Energy Group) | Rathsherry (Revised Application) | Wind Onshore |  |  | 21 | n/a |  |  |  | 2.3 | 9 |  | n/a | Operational | Operational | lands in the townland of Rathsherry, east of Tullymore Road and south and north of Longmore Road, Broughshane, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland |  | 132735 | 569854 | Northern Ireland Planning Service | G/2011/0162/F | N/A |  |  |  |  | 2011-04-11 | [6 empty] | 2015-03-26 |  |  |  | 2020-03-26 | 2016-12-15 | 2018-02-15
AA711 | 4559 | 2018-10-02 | North Power Croaghan Ltd | Croaghan | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Macosquin, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 95946 | 586148 | Northern Ireland Planning Service | C/2011/0158/F | N/A |  |  |  |  | 2011-04-12 | 2018-08-22
AA713 | 4560 | 2016-05-04 | Cloghinarney Wind Farm | Cloghinarney | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Appeal Refused | Application Refused | east of Ballynulto Road, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland | BT42 4RJ | 136457 | 558762 | Northern Ireland Planning Service | G/2011/0155/F | 2014/A0089 |  |  |  |  | 2011-04-08 |  | 2014-07-29 | 2014-11-01 |  | 2016-04-12
AA716 | 4561 | 2020-06-04 | ABO Wind NI | Castlegore Wind Farm | Wind Onshore |  |  | 23.1 | n/a |  |  |  | 3.3 | 7 |  | n/a | Planning Permission Granted | Awaiting Construction | land at Whappstown and Castlegore, Kells, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 135970 | 553344 | Northern Ireland Planning Service | G/2011/0136/F | N/A |  |  |  |  | 2011-04-08 | [6 empty] | 2015-07-15 |  |  |  | 2020-07-15
AA717 | 4562 | 2019-12-20 | DW consultancy | Crighshane Extension | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Planning Permission Refused | Application Refused | Crighshane and Crighdenis townlands, Killeter, Castlederg, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 27586 | 543505 | Northern Ireland Planning Service | J/2011/0082/F | N/A |  |  |  |  | 2011-03-16 |  | 2019-09-26
AA718 | 4563 | 2018-10-26 | Brookfields (Antrim Wind Energy) | Elginny Hill Resubmission | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 11 |  | n/a | Operational | Operational | Carncoagh Hill, Elginny Hill, Clontrace Hill, Broughshane, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 131511 | 567821 | Northern Ireland Planning Service | G/2011/0041/F | N/A |  |  |  |  | 2011-03-15 | [6 empty] | 2014-11-13 |  |  |  | 2019-11-13 | 2017-03-15 | 2018-03-15
AA720 | 4564 | 2018-10-29 | Brookfield Renewable Energy Group | Craignapapple Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 9 |  | n/a | Planning Permission Granted | Awaiting Construction | Townland of Craignagapple aprx 650m west of Legalougha Bridge and approx 200m east of Owenmore Bridge 8.5km east of Strabane, BT82 0SR | Co. Tyrone | Northern Ireland | Northern Ireland |  | 58423 | 559543 | Northern Ireland Planning Service | J/2010/0481/F | N/A |  |  |  |  | 2010-12-09 | [6 empty] | 2018-01-15 |  |  |  | 2023-01-15
AA886 | 4565 | 2020-06-25 | Renewable Energy Systems (RES) | Barr Cregg Wind Farm | Wind Onshore |  |  | 12.6 | n/a |  |  |  | 1.8 | 7 |  | n/a | Secretary of State - Granted | Awaiting Construction | Ballymaclanigan and Slaghtmanus, near Claudy in County Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 70685 | 573368 | Northern Ireland Planning Service | A/2012/0401/F | 2015/A0102 |  |  |  |  | 2012-08-23 |  | 2015-07-15 | 2015-07-31 |  | 2017-06-26 |  | 2019-08-15 |  |  | 2019-08-15
B0253 | 4566 | 2018-11-22 | TCI Renewables | Whappstown Wind Farm | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Abandoned | Abandoned | Whappstown Road, Moorfields, Ballymena, Co. Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 136232 | 553823 | Northern Ireland Planning Service | G/2011/0052/F | [5 empty] | 2011-02-01 | [6 empty] | 2015-09-24
C1793 | 4567 | 2015-07-29 | Banks Renewables | Bandirran Wind Farm | Wind Onshore |  |  | 20.4 | n/a |  |  |  | 3.4 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn |  | Tayside | Scotland | Scotland |  | 320667 | 729493 | Perth and Kinross Council | 14/00097/FLM | [5 empty] | 2014-01-31 | 2015-07-23
C2720 | 4568 | 2015-07-20 | Force 9 Energy Partners LLP And EDF Energy ER | Creag A Bhaird | Wind Onshore |  |  | 29.9 | n/a |  |  |  | 2.3 | 13 | 115 | n/a | Appeal Refused | Application Refused | Creag A' Bhaird Wind Farm Amulree | Tayside | Scotland | Scotland |  | 292842 | 740501 | Perth and Kinross Council | 13/02362/FLM | PPA-340-2097 |  |  |  |  | 2014-02-06 |  | 2015-03-20 | 2015-06-16 |  | 2015-09-10
C3094 | 4569 | 2015-01-08 | Knowes Renewables Llp | Knowes Farm | Wind Onshore |  |  | 7.65 | n/a |  |  |  | 0.85 | 9 |  | n/a | Planning Permission Refused | Application Refused | Knowes Farm Dunning Perth | Tayside | Scotland | Scotland | PH2 0RB | 301710 | 713657 | Perth and Kinross Council | 14/00837/FLL | [5 empty] | 2014-05-26 |  | 2014-12-22
A0007 | 4570 | 2014-09-16 | Private Developer | Bryngydfa Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 |  | n/a | Planning Application Submitted | Application Submitted | Felindre (Northern Area SO135809, South Knighton) Powys LD7 1Y | Powys | Wales | Wales |  | 313500 | 280900 | Powys County Council | P/2009/0384 | [5 empty] | 2009-04-03
AA763 | 4571 | 2019-05-21 | Amegni Renewables | Carno 3 | Wind Onshore |  |  | 45 | n/a |  |  |  | 2.5 | 18 |  | n/a | Planning Permission Granted | Awaiting Construction | Carno, Powys, SY17 5JS | Powys | Wales | Wales |  | 294433 | 297106 | Powys County Council | P/2010/0762 | [5 empty] | 2010-07-15 | [6 empty] | 2017-05-26
B0504 | 4572 | 2015-08-05 | Banks Renewables | Bank Field Wind Farm | Wind Onshore |  |  | 17 | n/a |  |  |  | 3.4 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Bankfield north of Guisborough in North Yorkshire | Cleveland | North East | England |  | 459784 | 517650 | Redcar and Cleveland Borough Council | R/2013/0674/FFM | [5 empty] | 2013-10-01 | 2015-07-31
C2277 | 4573 | 2016-05-27 | Airvolution Energy | Wilton | Wind Onshore |  |  | 6.6 | n/a |  |  |  | 3.3 | 2 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Between Wilton and Yearby, Middlesbrough | Cleveland | North East | England |  | 459523 | 520546 | Redcar and Cleveland Borough Council | R/2014/0074/FFM | [5 empty] | 2014-02-19 | 2016-05-26
B0315 | 4574 | 2015-02-18 | Burcote Wind | Sandy Knowe Wind Farm | Wind Onshore |  |  | 90 | n/a |  |  |  | 3 | 30 |  | n/a | Planning Permission Refused | Application Refused | Upper Nithsdale | Dumfries and Galloway | Scotland | Scotland |  | 270140 | 610240 | Scottish Government (S36) | [6 empty] | 2012-12-07 |  | 2015-02-18
AA471 | 4575 | 2017-07-14 | Private Developer | Hoprigshiels Community Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Operational | Operational | Land North And South Of 1 Whinhouse, Hoprigshiels, Cockburnspath, Scottish Borders | Borders | Scotland | Scotland |  | 375631 | 669803 | Scottish Borders Council | 11/00664/FUL | [5 empty] | 2011-06-06 | [6 empty] | 2014-11-20 |  |  |  |  | 2016-01-11 | 2017-03-31
AA997 | 4576 | 2017-05-02 | Wind Prospect | Longpark Wind Farm Extension | Wind Onshore |  |  | 14 | n/a |  |  |  | 2.5 | 5 | 110 | n/a | Planning Application Withdrawn | Application Withdrawn | Bow Farm Stow Scottish Borders | Borders | Scotland | Scotland |  | 346733 | 642570 | Scottish Borders Council | 14/00417/S36 | [5 empty] | 2014-04-08 | 2017-03-16
B0068 | 4577 | 2018-10-29 | Energiekontor | Windy Edge Wind Farm | Wind Onshore |  |  | 27 | n/a |  |  |  | 2.3 | 9 | 125 | n/a | Appeal Granted | Awaiting Construction | Land North East And North West Of Farmhouse Braidlie (Windy Edge) Hawick Scottish Borders | Borders | Scotland | Scotland |  | 349251 | 592241 | Scottish Borders Council | 13/00789/FUL | PPA-140-2055 |  |  |  |  | 2013-07-04 |  | 2015-06-29 | 2015-09-25 |  |  | 2016-06-09 | 2016-06-09 |  |  |  | 2021-12-01
B0556 | 4578 | 2020-03-11 | Muirhall Energy (formerly Infinis) | Glenkerie Wind Farm Extension | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.5 | 6 |  | n/a | Appeal Granted | Awaiting Construction | Kingledores Farm, Broughton, Biggar, Strathclyde | Borders | Scotland | Scotland | ML12 6QL | 310453 | 628117 | Scottish Borders Council | 13/00552/FUL | PPA-140-2052 |  |  |  |  | 2013-05-14 |  | 2014-12-01 | 2015-03-05 |  |  | 2015-07-29 | 2015-07-29 |  |  |  | 2018-07-29
B0584 | 4579 | 2015-10-06 | Infinis/Cummings Hill Wind Farm Ltd | Cummings Hill Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 |  | n/a | Planning Application Withdrawn | Application Withdrawn | 5.5km south of Jedburgh and to the north of the village of Chesters | Borders | Scotland | Scotland |  | 363643 | 612331 | Scottish Borders Council | 14/00083/FUL | [5 empty] | 2014-01-30 | 2015-09-28
A0502 | 4580 | 2016-05-16 | Scottish Power Renewables | Black Law Extension - 1b | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Operational | Operational | Black Law, Climpy | Strathclyde | Scotland | Scotland |  | 289500 | 653500 | Scottish Government (S36) | [6 empty] | 2011-05-10 | [6 empty] | 2015-06-17 |  |  |  | 2020-06-17 | 2015-08-18 | 2016-02-18
AA145 | 4581 | 2015-08-05 | RWE npower | Allt Duine Wind Farm | Wind Onshore |  |  | 93 | n/a |  |  |  | 3 | 31 |  | n/a | Planning Permission Refused | Application Refused | North of Kincraig, Kingussie, Highlands | Highland | Scotland | Scotland |  | 277479 | 812002 | Scottish Government (S36) | EC00003192 | [5 empty] | 2011-02-21 |  | 2015-07-30
AA245 | 4582 | 2015-07-31 | Community Windpower | Girthgate Wind Farm | Wind Onshore |  |  | 81.6 | n/a |  |  |  | 3.4 | 24 |  | n/a | Appeal Withdrawn | Application Withdrawn | Approximately 3km to the west of Lauder and 5km east of Stow in Berwickshire, Scottish Borders. | Borders | Scotland | Scotland |  | 349456 | 647634 | Scottish Government (S36) | EC00005270 | WIN-140-2 |  |  |  |  | 2013-06-01 |  |  | 2014-11-10 | 2015-07-14
AA304 | 4583 | 2019-07-02 | WKN Windkraft Nord AG (WKN) | Sallachy Wind Farm | Wind Onshore |  |  | 66 | n/a |  |  |  | 2 | 22 |  | n/a | Planning Permission Refused | Application Refused | Loch Shin, Near Glencassley, Sutherland, Dornoch, Highlands | Highland | Scotland | Scotland |  | 240609 | 919737 | Scottish Government (S36) | [6 empty] | 2011-12-19 |  | 2015-11-17
AA491 | 4584 | 2020-06-04 | E.ON Renewables | Strathy Wood | Wind Onshore |  |  | 59.4 | n/a |  |  |  | 3 | 20 | 145 | n/a | Planning Application Submitted | Application Submitted | Near Strathy, Sutherland | Highland | Scotland | Scotland |  | 282146 | 955604 | Scottish Government (S36) | EC00005239 | [5 empty] | 2015-09-18
AA512 | 4585 | 2015-12-01 | Scottish and Southern Energy (SSE) | Glencassley Wind Farm | Wind Onshore |  |  | 69 | n/a |  |  |  | 3 | 23 |  | n/a | Planning Permission Refused | Application Refused | approximately 12km north-west of Lairg, in Sutherland | Highland | Scotland | Scotland |  | 243491 | 911736 | Scottish Government (S36) | [6 empty] | 2012-07-10 |  | 2015-11-17
B0393 | 4586 | 2020-05-28 | Vattenfall | South Kyle Wind Farm | Wind Onshore |  |  | 240 | n/a |  |  |  | 4.8 | 50 | 149.5 | n/a | Appeal Granted | Awaiting Construction | south of the B741, mainly within Kyle Forest and to the east of Dalmellington | Strathclyde | Scotland | Scotland |  | 254576 | 604980 | Scottish Government (S36) |  | WIN-190-3 |  |  |  |  | 2013-08-29 |  |  | 2015-02-05 |  |  | 2017-06-30 | 2017-06-30 |  |  |  | 2022-06-30
B1342 | 4588 | 2020-01-27 | Falck Renewables/West Coast Energy Ltd | Millennium South - Phase 3 | Wind Onshore |  |  | 35 | n/a |  |  |  | 3.5 | 10 |  | n/a | Appeal Granted | Awaiting Construction | Millennium Windfarm, on The Achlain and Invergarry amd Aberchalder Estates, Glengarry Invergarry, Inverness-Shire, (nr Glen Moriston, Fort Augustus) | Highland | Scotland | Scotland |  | 227236 | 807450 | Scottish Government (S36) | EC00002077 | WIN-270-4 |  |  |  |  | 2014-05-22 |  |  | 2015-06-25 |  |  | 2017-02-03 | 2017-02-03
C2078 | 4589 | 2020-06-25 | Renewable Energy Systems (RES) | Hill of Towie II Wind Farm | Wind Onshore |  |  | 48 | n/a |  |  |  | 3 | 16 |  | n/a | Appeal Granted | Awaiting Construction | Hill of Towie, Knockan and McHattie's Cairn, Drummuir, Keith, Banffshire, Moray | Grampian | Scotland | Scotland |  | 320000 | 860000 | Scottish Government (S36) |  | WIN-300-1 |  |  |  |  | 2013-10-31 |  |  | 2015-01-28 |  |  | 2017-06-16 | 2017-06-16 |  |  |  | 2020-06-16
EN00282 | 4590 | 2016-04-22 | Scottish Power Renewables | Harestanes Wind Farm Extension | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 |  | n/a | Planning Permission Refused | Application Refused | located within the Forest of Ae | Dumfries and Galloway | Scotland | Scotland |  | 300271 | 602061 | Scottish Government (S36) | [6 empty] | 2013-11-13 |  | 2015-12-17
C1511 | 4591 | 2020-02-04 | Community Windpower | Aikengall 3 Community Wind Farm | Wind Onshore |  |  | 75.5 | n/a |  |  |  | 3.6 | 18 | 145 | n/a | Appeal Granted | Awaiting Construction | Land North Of Nether Monynut Cottage Cockburnspath Scottish Borders | Borders | Scotland | Scotland |  | 371793 | 666791 | Scottish Government (S36) |  | WIN-140-3 |  |  |  |  | 2014-02-01 |  |  | 2015-04-23 |  |  | 2016-10-19 | 2016-10-19
IF1290 | 4592 | 2016-02-05 | Airvolution Energy | Agney Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Appeal Withdrawn | Application Withdrawn | Land 1085 Metres South West Lydd Model Flying Club Site Midley Wall Old Romney Kent | Kent | South East | England |  | 601240 | 122640 | Shepway District Council | Y13/0048/SH | APP/L2250/A/15/3014364 |  |  |  |  | 2013-01-22 |  |  | 2015-07-03 | 2016-01-29
AA305 | 4593 | 2017-07-19 | Scottish Power Renewables | Glen App | Wind Onshore |  |  | 22 | n/a |  |  |  | 2 | 11 |  | n/a | Operational | Operational | NE/o Cairnryan, Stranraer, Dumfries and Galloway | Strathclyde | Scotland | Scotland |  | 208880 | 571432 | South Ayrshire Council | 12/01156/APPM | [5 empty] | 2012-10-02 | [6 empty] | 2015-06-04 |  |  |  |  | 2016-10-13 | 2017-01-15
AA572 | 4594 | 2020-03-31 | Ventient (formerly Infinis) | Glentaggart Wind Farm | Wind Onshore |  |  | 17 | n/a |  |  |  | 3.4 | 5 |  | n/a | Planning Application Withdrawn | Application Withdrawn | to the south east of the settlement of Glespin in South Lanarkshire | Strathclyde | Scotland | Scotland |  | 286170 | 627590 | South Lanarkshire Council | CL/11/0461 | [5 empty] | 2011-10-26 | 2020-02-14
A0232 | 4595 | 2018-06-04 | Vattenfall (previously Nuon Renewables) | Pen Y Cymoedd | Wind Onshore |  |  | 228 | n/a |  |  |  | 3 | 76 |  | n/a | Operational | Operational | Land stretches from the Upper Afan Valley to end of Cynon Valley. | Neath Port Talbot | Wales | Wales |  | 282793 | 196557 | DECC (S36) | [6 empty] | 2009-11-19 | [6 empty] | 2012-05-08 |  |  |  |  | 2014-02-06 | 2017-05-19
AA165 | 4596 | 2014-09-19 | Peel Energy | Asfordby Wind Farm | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Appeal Refused | Application Refused | Asfordby Business Park, Melton Mowbray, Leicestershire | Leicestershire | East Midlands | England |  | 470767 | 320023 | Melton Borough Council | 10/00951/FUL | 13/00003/REF |  |  |  |  | 2010-12-21 |  | 2012-07-27 |  |  | 2014-03-08
AA513 | 4597 | 2019-01-02 | Scottish and Southern Energy (SSE) | Stronelairg Wind Farm | Wind Onshore |  |  | 228 | n/a |  |  |  | 3.6 | 66 | 135 | n/a | Operational | Operational | located approximately 11 kilometres to the south-east of Fort Augustus | Highland | Scotland | Scotland |  | 247166 | 806833 | Scottish Government (S36) | EC00005242 |  |  |  | 42360 |  | 2012-06-29 | [6 empty] | 2014-06-06 |  |  |  |  | 2017-04-20 | 2018-12-11
AA562 | 4598 | 2015-06-16 | Airvolution Energy | M1 J18 Wind Turbines | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Land Between Watling Street And M1, Celtic Way, Kilsby, Northamptonshire | Northamptonshire | East Midlands | England |  | 457472 | 272715 | Daventry District Council | DA/2011/0742 | [5 empty] | 2011-09-09 | [6 empty] | 2013-02-12 |  |  |  |  | 2014-07-07 | 2014-12-15
AA884 | 4599 | 2018-04-03 | Temporis Capital | Tullymurdoch Wind Farm | Wind Onshore |  |  | 14.4 | n/a |  |  |  | 2.05 | 7 |  | n/a | Operational | Operational | Alyth, Blairgowrie, Tayside | Tayside | Scotland | Scotland | PH10 | 319575 | 752228 | Perth and Kinross Council | 12/01423/FLL | PPA-340-2073 |  |  |  |  | 2012-08-13 |  | 2013-03-13 | 2013-08-13 |  |  | 2014-09-03 | 2014-09-03 |  |  |  | 2017-09-03 | 2017-08-24 | 2018-01-23
B0206 | 4600 | 2016-05-31 | Renewable Energy Systems (RES) | Penmanshiel Wind Farm | Wind Onshore |  |  | 28.7 | n/a |  |  |  | 2 | 14 |  | n/a | Operational | Operational | Land East Of Penmanshiel Farmhouse Grantshouse Scottish Borders | Borders | Scotland | Scotland |  | 380006 | 667129 | Scottish Borders Council | 11/01464/FUL | 12/00043/NONDET |  |  |  |  | 2011-10-27 |  | 2012-09-15 |  |  |  | 2013-10-16 | 2013-10-16 |  |  |  |  | 2015-05-06 | 2016-07-01
B0327 | 4601 | 2017-04-19 | Airvolution Energy | Kinegar Quarry (resubmission) | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | Land South West Of Neuk Farm Cockburnspath Scottish Borders | Borders | Scotland | Scotland |  | 377377 | 671362 | Scottish Borders Council | 12/00221/FUL | 12/00050/RREF |  |  |  |  | 2012-02-20 |  | 2012-10-03 |  |  |  | 2013-03-21 | 2013-03-21 |  |  |  |  | 2014-07-15 | 2017-03-15
B0363 | 4602 | 2015-05-27 | EDF Energy Renewables | Hollow Panson Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 2 | 6 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Chapmans Well, Devon | Devon | South West | England |  | 236195 | 93120 | Torridge District Council | 1/1171/2012/FULM | [5 empty] | 2012-12-21 | 2014-08-07
B0365 | 4603 | 2020-06-24 | Banks Renewables | Lethans Wind Farm | Wind Onshore |  |  | 88 | n/a |  |  |  | 4 | 22 | 152 | n/a | Abandoned | Abandoned | Lethans, East Ayrshire | Strathclyde | Scotland | Scotland |  | 268331 | 616048 | Scottish Government (S36) | EC00002086 | [5 empty] | 2015-03-13 | [6 empty] | 2018-03-23 |  |  |  | 2021-03-23
B0367 | 4604 | 2015-04-24 | REG & Blackrock | St. Breock Re-Power (Resubmission) | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.5 | 5 |  | n/a | Operational | Operational | St. Breock North Cornwall Cornwall | Cornwall | South West | England |  | 200000 | 70000 | Cornwall Council | PA12/02907 | [5 empty] | 2012-03-21 | [6 empty] | 2012-10-03 |  |  |  |  | 2014-06-01 | 2015-02-23
B0395 | 4605 | 2020-06-25 | Renewables Infrastructure Group / Renewable Energy Systems (RES) | Blary Hill Wind Farm | Wind Onshore |  |  | 35 | n/a |  |  |  | 2.5 | 14 | 110 | n/a | Under Construction | Under Construction | Land North Of Loch Arnicle (including C20 To The A83T) Barr Glen By Glenbarr Argyll And Bute | Strathclyde | Scotland | Scotland |  | 170381 | 636538 | Argyll and Bute Council | 14/01978/PP | PPA-130-2052 |  |  |  |  | 2014-08-22 |  | 2015-04-30 | 2015-06-01 |  |  | 2017-06-23 | 2017-06-23 |  |  |  | 2020-06-23 | 2020-05-25
B0539 | 4606 | 2015-01-26 | REG Windpower | Chapmans Howe Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 |  | n/a | Appeal Refused | Application Refused | Between Castle Douglas and Kirkcudbright | Dumfries and Galloway | Scotland | Scotland |  | 273463 | 553928 | Dumfries and Galloway Council | 13/P/2/0189 | PPA-170-2096 |  |  |  |  | 2013-06-28 |  |  | 2014-08-28 |  | 2015-01-12
B0587 | 4607 | 2018-01-31 | Peel Windfarms | Garleffan Wind Farm | Wind Onshore |  |  | 21.6 | n/a |  |  |  | 3.6 | 6 |  | n/a | Appeal Refused | Application Refused | opencast coal mines at Garleffan and Grievehill | Strathclyde | Scotland | Scotland |  | 262425 | 617645 | East Ayrshire Council | 13/0210/PP | PPA-190-2063 |  |  |  |  | 2013-04-02 |  | 2016-10-21 | 2017-01-20 |  | 2018-01-12
B0604 | 4608 | 2014-09-19 | REG Windpower | Outh Muir Wind Farm | Wind Onshore |  |  | 12.5 | n/a |  |  |  | 2.5 | 5 |  | n/a | Appeal Refused | Application Refused | Cleish Hills Outh Knockhill Fife | Fife | Scotland | Scotland |  | 306954 | 694854 | Fife Council | 13/01898/EIA | 14/00019/REF |  |  |  |  | 2013-07-02 |  | 2014-03-27 |  |  | 2014-09-04
B0679 | 4609 | 2019-11-05 | Scottish Enterprise/SSE | Hunterston Test Centre | Wind Onshore |  |  | 13 | n/a |  |  |  | 7 | 2 |  | n/a | Decommissioned | Decommissioned | Hunterston Construction Yard Fairlie Largs Ayrshire | Strathclyde | Scotland | Scotland |  | 218776 | 652956 | North Ayrshire Council | 11/00679/PPM | [5 empty] | 2011-09-29 | [6 empty] | 2012-02-14 |  |  |  |  | 2013-03-21 | 2015-12-15
B0743 | 4610 | 2017-05-02 | PNE Wind UK | Knockskae Wind Farm | Wind Onshore |  |  | 25.3 | n/a |  |  |  | 2.3 | 11 | 126 | n/a | Planning Permission Refused | Application Refused | Clauchrie Hill, approximately, 4KM south of Cloyntie, Maybole, Strathclyde, Scotland | South Ayrshire | Scotland | Scotland | KA19 7 | 235665 | 601509 | South Ayrshire Council | 15/01216/APPM | [5 empty] | 2015-11-04 |  | 2017-04-19
B0744 | 4611 | 2019-12-11 | Brookfield Renewable Energy Group (PNE Wind UK) | Polquhairn Wind Farm | Wind Onshore |  |  | 22.5 | n/a |  |  |  | 2.5 | 9 |  | n/a | Appeal Granted | Awaiting Construction | Polquhairn Wind Farm, SE of Sinclairston,, Cumnock East Ayrshire | Strathclyde | Scotland | Scotland | KA18 2RT | 246990 | 616752 | East Ayrshire Council | 14/0860/PP | PPA-190-2066 |  |  |  |  | 2014-12-02 |  | 2017-08-18 | 2017-11-16 |  |  | 2018-09-19 | 2018-09-19
B0747 | 4612 | 2016-11-30 | Renewable Energy Systems (RES) | Keirs Hill (Sclenteuch) Wind Farm | Wind Onshore |  |  | 57.8 | n/a |  |  |  | 3.4 | 17 |  | n/a | Appeal Refused | Application Refused | between Patna and Dalmellington | Strathclyde | Scotland | Scotland |  | 242200 | 607700 | Scottish Government (S36) |  | WIN-190-2 |  |  |  |  | 2013-11-29 |  | 2016-11-22 | 2015-01-28 |  | 2016-11-22
B1013 | 4614 | 2016-01-04 | Coronation Power | Rooley Moor | Wind Onshore |  |  | 39.6 | n/a |  |  |  | 3.3 | 12 |  | n/a | Appeal Withdrawn | Application Refused | Land To The East And West Of Rooley Moor Road Rochdale | Lancashire | North West | England |  | 386151 | 417612 | Rochdale Borough Council | 14/00877/FUL | APP/P4225/W/15/3129583 |  |  |  |  | 2014-08-29 |  | 2015-07-02 | 2015-08-26 | 2015-12-22
B1290 | 4615 | 2018-05-30 | Fred Olsen Renewables | Windy Standard III Wind Farm (Brockloch Rig Phase 2) | Wind Onshore |  |  | 67.5 | n/a |  |  |  | 2 | 25 |  | n/a | Appeal Lodged | Application Submitted | Near New Cummock | Dumfries and Galloway | Scotland | Scotland |  | 257695 | 600320 | Scottish Government (S36) | ECU00000335 | WIN-170-2003 |  |  |  |  | 2016-12-09 |  |  | 2018-05-02
B1420 | 4616 | 2015-11-03 | Eventus Duurzaam | Talladh-a-Bheithe Wind Farm | Wind Onshore |  |  | 75 | n/a |  |  |  | 3.125 | 24 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Craiganour Estate 9km North-West of Kinloch Rannoch and 22km South of Dalwhinnie | Tayside | Scotland | Scotland |  | 257050 | 763350 | Scottish Government (S36) | [6 empty] | 2014-06-23 | 2015-10-30
C1829 | 4617 | 2017-10-31 | Energiekontor UK | Fen Lane wind farm | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.5 | 7 |  | n/a | Appeal Refused | Application Refused | Land to the South of Fen Lane, West of Louth Canal, North of Fulstow (in Parishes of Fulstow and North Thoresby) | Lincolnshire | East Midlands | England |  | 532983 | 398632 | East Lindsey District Council | N/056/01036/14 | APP/D2510/W/15/3005975 |  |  |  |  | 2014-06-27 |  | 2017-10-25 | 2015-03-04 |  | 2017-10-25
EN00031 | 4619 | 2017-10-04 | Green Power | Carraig Gheal | Wind Onshore |  |  | 46 | n/a |  |  |  | 2.3 | 20 |  | n/a | Operational | Operational | Carraig Gheal, Argyll and Bute | Strathclyde | Scotland | Scotland |  | 196465 | 721170 | Scottish Government (S36) | [6 empty] | 2004-11-15 | [6 empty] | 2008-06-13 |  |  |  |  | 2011-03-01 | 2013-08-31
EN00041 | 4620 | 2015-08-24 | Greencoat UK Wind | Langhope Rig | Wind Onshore |  |  | 16 | n/a |  |  |  | 1.6 | 10 |  | n/a | Operational | Operational | Langhope Rig, Ettrick Forest, Scottish Borders | Borders | Scotland | Scotland |  | 340680 | 620050 | Scottish Borders Council | 06/01236/FUL | [5 empty] | 2006-06-30 |  | 2007-07-17 | [9 empty] | 2013-10-30 | 2015-03-26
EN00197 | 4621 | 2016-02-03 |  | Altgolan | Wind Onshore |  |  | 17.5 | n/a |  |  |  | 2.3 | 7 |  | n/a | Appeal Refused | Application Refused | Altgolan, Castlederg | Co. Antrim | Northern Ireland | Northern Ireland |  | 119268 | 533312 | Northern Ireland Planning Service | J/2006/0840/F | 2012/A0070 |  |  |  |  | 2006-08-21 |  | 2012-05-10 | 2012-08-01 |  | 2015-12-21
EN00210 | 4622 | 2019-06-25 | Viking Energy / Scottish and Southern | Viking Wind Farm | Wind Onshore |  |  | 370 | n/a |  |  |  | 3.5 | 103 |  | n/a | Abandoned | Abandoned | Lang Kames, Shetland Island | Shetland | Scotland | Scotland |  | 443800 | 1161960 | Scottish Government (S36) | [6 empty] | 2009-05-20 | [6 empty] | 2012-04-04
EN00575 | 4623 | 2015-06-29 | Vattenfall | Clashindarroch 2 (Revised) | Wind Onshore |  |  | 37 | n/a |  |  |  | 2.05 | 18 |  | n/a | Operational | Operational | Clashindarroch Forest, Huntly, Aberdeenshire | Grampian | Scotland | Scotland |  | 348000 | 831000 | Aberdeenshire Council | APP/2009/1380 | [5 empty] | 2009-06-01 | [6 empty] | 2010-12-14 |  |  |  |  | 2013-06-01 | 2015-06-26
EN00602 | 4624 | 2014-12-01 | Ecotricity | Galsworthy Wind Park | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 |  | n/a | Operational | Operational | Land At Galsworthy , Buckland Brewer And Bulkworthy | Devon | South West | England |  | 240435 | 115705 | Torridge District Council | 1/0375/2008/FUL | [5 empty] | 2008-04-04 | [6 empty] | 2008-09-11 |  |  |  |  | 2011-05-01 | 2014-11-28
N000231W | 4625 | 2016-01-04 | Scottish and Southern Energy (SSE) | Strathy North | Wind Onshore |  |  | 67.65 | n/a |  |  |  | 2.05 | 33 |  | n/a | Operational | Operational | Near Strathy Village, Sutherland | Highland | Scotland | Scotland |  | 281550 | 957550 | Scottish Government (S36) | [6 empty] | 2007-01-12 | [6 empty] | 2011-11-22 |  |  |  |  | 2014-01-31 | 2015-12-01
N00308w | 4626 | 2014-09-19 | Wind Hydrogen | Wings Law | Wind Onshore |  |  | 48 | n/a |  |  |  | 2 | 24 |  | n/a | Appeal Withdrawn | Application Refused | Ladyland Moor , Kilbirnie | Strathclyde | Scotland | Scotland |  | 230100 | 659400 | North Ayrshire Council | 07/00761/PP | 09/00018/REFUSE |  |  |  |  | 2007-08-03 |  | 2009-02-23 |  | 2010-12-14
N00214Wa | 4627 | 2016-02-22 | Fred Olsen Renewables | Mid Hill - Phase II | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 |  | n/a | Operational | Operational | Mid Hill, Fetteresso Stonehaven | Grampian | Scotland | Scotland |  | 370540 | 786500 | Scottish Government (S36) | SO30179PF | [5 empty] | 2003-02-12 | [6 empty] | 2005-06-03 |  |  |  |  | 2014-08-25 | 2014-12-02
B1513 | 4628 | 2020-06-19 | Banks Renewables | Kype Muir Wind Farm Extension | Wind Onshore |  |  | 75 | n/a |  |  |  | 5 | 15 | 220 | n/a | Under Construction | Under Construction | approximately 5 km south of the town of Strathaven | Strathclyde | Scotland | Scotland |  | 271915 | 639557 | Scottish Government (S36) | EC00002083 | [5 empty] | 2014-10-10 | [6 empty] | 2016-09-16 |  |  |  |  | 2020-01-31
B1514 | 4629 | 2015-03-17 | North Harris Trust | Monan Hill Wind Turbines | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 |  | n/a | Operational | Operational | 500m North Of Ceann An Ora Quarry Ardhasaig Isle Of Harris | Highland | Scotland | Scotland | HS3 3AJ | 114171 | 904933 | Comhairle nan Eilean Siar Council | 06/00290/FUL | [5 empty] | 2006-05-24 | [6 empty] | 2008-02-14 |  |  |  |  | 2014-07-01 | 2015-03-19
B1516 | 4631 | 2019-09-25 | Fred Olsen Renewables | Crystal Rig Wind Farm Phase IV | Wind Onshore |  |  | 48 | n/a |  |  |  | 4 | 11 |  | n/a | Appeal Lodged | Application Submitted | Crystal Rigg Wind Farm Cranshaws Duns Scottish Borders | Borders | Scotland | Scotland | TD11 3SR | 367100 | 667900 | Scottish Government (S36) | ECU00000607 | WIN-140-8 |  |  |  |  | 2018-05-30 |  |  | 2019-07-04
B1517 | 4632 | 2020-03-11 | Muirhall Energy | Loganhead Wind Farm | Wind Onshore |  |  | 25.6 | n/a |  |  |  | 3.2 | 8 | 130 | n/a | Planning Permission Granted | Awaiting Construction | Land Forming Part Of Loganhead Commercial Forestry, Approx 4km To The NW Of Langholm and 15km To The NE Of Lockerbie | Dumfries and Galloway | Scotland | Scotland |  | 330880 | 586580 | Dumfries and Galloway Council | 15/P/4/0273 | [5 empty] | 2015-10-02 | [6 empty] | 2019-04-03 |  |  |  | 2022-04-03
B1518 | 4633 | 2020-06-18 | Muirhall Energy | Crossdykes | Wind Onshore |  |  | 48 | n/a |  |  |  | 4.8 | 10 | 176.5 | n/a | Planning Permission Granted | Awaiting Construction | Land Forming Part Of Crossdykes Farm | Dumfries and Galloway | Scotland | Scotland |  | 325400 | 587500 | Dumfries and Galloway Council | 18/1706/FUL | [5 empty] | 2018-11-08 | [6 empty] | 2019-06-27
B1519 | 4634 | 2020-04-01 | Scottish and Southern Energy (SSE) | Doraville Wind Farm | Wind Onshore |  |  | 119 | n/a |  |  |  | 3.6 | 33 | 140 | n/a | Planning Application Submitted | Application Submitted | Doraville, County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 97000 | 534000 | Northern Ireland Planning Service | LA10/2015/0292/F | [5 empty] | 2015-07-06
A0135 | 4635 | 2017-01-18 | University of St Andrews | Kenly Wind Farm (University of St Andrew's) | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Abandoned | Abandoned | Kenly Farm, Boarhills, St. Andrews, Fife (5 miles from St Andrew's. University campus land) | Fife | Scotland | Scotland | KY16 8PW | 349269 | 717002 | Fife Council | 11/02799/EIA | [5 empty] | 2011-06-20 |  | 2012-10-01 |  |  |  | 2013-10-07 | 2013-10-07 |  |  |  | 2016-10-07
A0227 | 4636 | 2020-05-28 | Scottish Power Renewables | Halsary Wind Farm | Wind Onshore |  |  | 34 | n/a |  |  |  | 2.3 | 15 | 120 | n/a | Under Construction | Under Construction | Spittal, Caithness | Highland | Scotland | Scotland |  | 315749 | 950081 | Highland Council | 09/00399/FULCA | [5 empty] | 2009-11-09 | [6 empty] | 2013-09-19 |  |  |  |  | 2020-02-01
A0442 | 4637 | 2016-12-16 | REG Windpower (previously Cornwall Light and Power) | French Farm (resubmission) | Wind Onshore |  |  | 4 | n/a |  |  |  | 2.5 | 2 |  | n/a | Operational | Operational | French Farm, French Drove, Thorney, Peterborough, Cambridgeshire, PE6 0PQ | Cambridgeshire | Eastern | England |  | 528300 | 309000 | Peterborough City Council | 08/01365/FUL | APP/J5400/A/09/2116682 |  |  |  |  | 2008-11-06 |  | 2009-07-10 |  |  |  | 2010-09-10 | 2010-09-10 |  |  |  | 2015-09-10 | 2016-05-26 | 2016-11-24
AA143 | 4638 | 2017-04-04 | Renewable Energy Systems (RES) | Glenchamber Wind Farm | Wind Onshore |  |  | 27.5 | n/a |  |  |  | 2.5 | 11 |  | n/a | Operational | Operational | between New Luce, Kirkcowan and Glenluce | Dumfries and Galloway | Scotland | Scotland |  | 223765 | 566671 | Dumfries and Galloway Council | 10/P/1/0494 | [5 empty] | 2010-10-28 |  | 2011-09-30 |  |  |  | 2012-07-31 | 2012-07-31 |  |  |  |  | 2015-02-06 | 2016-06-01
AA164 | 4639 | 2016-08-01 | Broadview Energy | Spring Farm Ridge | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 |  | n/a | Secretary of State - Refusal | Application Refused | land to the north of Welsh Lane between Greatworth and Helmdon | Northamptonshire | East Midlands | England |  | 457363 | 243641 | South Northamptonshire Council | S/2010/1437/MAF | APP/Z2830/A/11/2165035/NWF |  |  | 41557 |  | 2010-10-19 |  | 2011-06-30 | 2013-04-11 |  | 2014-12-23 |  |  |  | 2014-12-23
AA202 | 4640 | 2018-04-03 | Scottish and Southern Energy (SSE) | Bhlaraidh (previously Balmacaan) | Wind Onshore |  |  | 110 | n/a |  |  |  | 3.43 | 32 | 135 | n/a | Operational | Operational | Near Invermoriston | Highland | Scotland | Scotland |  | 244194 | 817221 | Scottish Government (S36) | [6 empty] | 2012-06-29 | [6 empty] | 2014-01-17 |  |  |  |  | 2016-03-01 | 2017-09-15
AA424 | 4641 | 2015-04-30 | EDF Renewables | Sheraton Wind Farm (Durham) | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Planning Permission Refused | Application Refused |  | Durham | North East | England |  | 443920 | 536016 | Durham County Council | CMA/5/31 | [5 empty] | 2012-01-23 |  | 2014-12-01
AA442 | 4642 | 2018-05-01 | Banks Renewables | Moor House Wind Farm (resubmission) | Wind Onshore |  |  | 12 | n/a |  |  | 16.4 | 2.5 | 6 |  | n/a | Operational | Operational | Bishopton Lane, Great Burdon, Darlington | Durham | North East | England |  | 432599 | 520053 | Darlington Borough Council | 11/00160/FUL | [5 empty] | 2011-03-14 | [6 empty] | 2011-10-19 |  |  |  |  | 2017-01-16 | 2017-12-15
AA451 | 4643 | 2019-10-01 | Banks Renewables | Kype Muir Wind Farm | Wind Onshore |  |  | 88.4 | n/a |  |  | 104 | 3.4 | 26 |  | n/a | Operational | Operational | approximately 5 km south of the town of Strathaven | Strathclyde | Scotland | Scotland |  | 271915 | 639557 | Scottish Government (S36) | EK/11/0256 | [5 empty] | 2011-08-09 | [6 empty] | 2014-05-22 |  |  |  | 2019-05-22 | 2017-02-01 | 2019-09-15
AA476 | 4644 | 2017-12-20 | John Laing Environmental Assets Group | Llynfi Afan Renewable Energy Park | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Mynydd Y Gelli, Port Talbot, Bridgend | Neath Port Talbot | Wales | Wales |  | 288368 | 195006 | Bridgend County Borough Council | P/10/844/FUL | [5 empty] | 2010-11-15 | [6 empty] | 2013-07-18 |  |  |  |  | 2016-05-27 | 2017-09-14
AA559 | 4645 | 2017-04-04 | Falck Renewables | Assel Valley Wind Farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 2.3 | 11 |  | n/a | Operational | Operational | Pinmore, Girvan, Strathclyde | Strathclyde | Scotland | Scotland |  | 223370 | 595995 | South Ayrshire Council | 11/00564/APPM | 13/00008/8WEEK |  |  |  |  | 2011-06-01 |  | 2013-09-03 |  |  |  | 2013-09-03 | 2013-09-03 |  |  |  |  | 2015-05-15 | 2016-10-28
AA662 | 4646 | 2019-05-31 | Innogy | Bad a Cheo Wind Farm | Wind Onshore |  |  | 26.65 | n/a |  |  | 29.9 | 2.05 | 13 | 112 | n/a | Operational | Operational | Bad A Cheo Achkeepster Spittal | Highland | Scotland | Scotland |  | 316615 | 948900 | Highland Council | 12/02868/FUL | 13/00052/REFCA |  |  |  |  | 2012-07-25 |  | 2013-09-19 |  |  |  | 2014-05-06 | 2014-05-06 |  |  |  |  | 2017-03-15 | 2019-05-01
AA671 | 4647 | 2016-10-25 | Octopus Investments | Fraisthorpe Wind Farm | Wind Onshore |  |  | 29.7 | n/a |  |  |  | 3.3 | 9 |  | n/a | Operational | Operational | Land North East Of Manor Farm, Main Street, Fraisthorpe, East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England | YO15 3QP | 515938 | 462771 | East Riding of Yorkshire Council | 12/00640/STPLFE | 12/00066/NONDET |  |  |  |  | 2012-02-10 |  | 2012-05-31 |  |  |  | 2013-01-22 | 2013-01-22 |  |  |  |  | 2015-04-15 | 2016-06-15
AA948 | 4648 | 2019-04-30 | RWE Npower Renewables/ Innogy | Mynydd Y Gwair Wind Farm (resubmission) | Wind Onshore |  |  | 32.8 | n/a |  |  | 40 | 3 | 16 |  | n/a | Operational | Operational | Swansea, West Glamorgan | West Glamorgan | Wales | Wales |  | 266303 | 207394 | City and County Council of Swansea | 2012/1221 | [5 empty] | 2012-09-11 | [6 empty] | 2013-02-08 |  |  |  |  | 2017-02-08 | 2019-04-24
B0087 | 4649 | 2016-11-30 | Aviva | Jack's Lane Wind Farm | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Barwick Hall Farm Barwick Road Stanhoe King's Lynn Norfolk | Norfolk | Eastern | England | PE31 8PZ | 580919 | 335229 | King's Lynn and West Norfolk Borough Council | 10/01419/FM | 11/00038/REF |  |  |  |  | 2010-08-17 |  | 2011-08-02 |  |  |  | 2012-05-24 | 2012-05-24 |  |  |  |  | 2014-07-31 | 2015-04-01
B0497 | 4650 | 2020-03-11 | Energia | Pigeon Top (resubmission) | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 |  | n/a | Under Construction | Under Construction | Dooish, Drumquin, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 48085 | 535005 | Northern Ireland Planning Service | K/2011/0592/F | [5 empty] | 2011-09-26 | [6 empty] | 2012-11-15 |  |  |  | 2017-11-15 | 2015-12-17
C1559 | 4651 | 2016-01-04 | REG Windpower / BlackRock | Denzell Downs Wind Farm - resubmission | Wind Onshore |  |  | 10 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Higher Denzell Farm, St Mawgan, Newquay, Cornwall | Cornwall | South West | England | TR8 4HG | 189923 | 67094 | Cornwall Council | PA13/04805 | [5 empty] | 2013-06-27 | [6 empty] | 2013-12-12 |  |  |  |  | 2015-03-01 | 2015-11-24
EN00126 | 4652 | 2017-01-04 | Energia Renewables | Long Mountain | Wind Onshore |  |  | 27.6 | n/a |  |  |  | 2 | 12 |  | n/a | Operational | Operational | Dunloy, Co. Antrim | Co. Antrim | Northern Ireland | Northern Ireland |  | 115926 | 574530 | Northern Ireland Planning Service | D/2006/0104/F | [5 empty] | 2006-03-08 | [6 empty] | 2007-01-05 |  |  |  |  | 2016-01-15 | 2016-12-15
EN00128 | 4653 | 2017-07-04 | Gaelectric Developments/ CGN Europe Energy | Cregganconroe | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Loughmallon Road, Cregganconroe, Pomeroy | Co. Tyrone | Northern Ireland | Northern Ireland |  | 78733 | 536671 | Northern Ireland Planning Service | K/2006/0242/F | [5 empty] | 2006-09-29 | [6 empty] | 2010-09-08 |  |  |  | 2015-09-08 | 2015-02-17 | 2017-01-04
EN00131 | 4654 | 2017-05-03 | Natural Power | Ora More | Wind Onshore |  |  | 15 | n/a |  |  |  | 2.3 | 6 |  | n/a | Operational | Operational | Ora More Hill, in the Townlands of Killycreen East, Ora Beg and Mullylusty, near Boho and Belcoo, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 16972 | 509701 | Northern Ireland Planning Service | L/2005/3070/F | [5 empty] | 2005-12-15 | [6 empty] | 2011-03-30 |  |  |  | 2016-03-30 | 2015-11-15 | 2017-03-30
EN00261 | 4655 | 2016-02-24 | Infrared Capital Partners | Reaps Moss Wind Farm (resubmitted) | Wind Onshore |  |  | 10.2 | n/a |  |  |  | 3.4 | 3 | 125 | n/a | Operational | Operational | Reaps Moss , Bacup , East Lancashire | Lancashire | North West | England |  | 389065 | 422650 | Rossendale Borough Council | 2007/125 | [5 empty] | 2007-02-19 | [6 empty] | 2009-10-14 |  |  |  |  | 2014-10-01 | 2015-03-31
EN00264 | 4656 | 2017-10-05 | John Laing Environmental Assets Group | Llynfi Renewable Energy Park, Land at Mynydd Caerau | Wind Onshore |  |  | 18 | n/a |  |  |  | 2 | 12 |  | n/a | Operational | Operational | Glyncorrwg and Gelli Mountain , Croeserw , Neath and Port Talbot | Neath Port Talbot | Wales | Wales | SA13 3NN | 287930 | 195255 | Neath Port Talbot County Borough Council | P2010/1148 | [5 empty] | 2010-11-15 |  | 2012-04-03 |  |  |  | 2013-08-27 | 2013-08-27 |  |  |  |  | 2016-05-27 | 2017-09-14
EN00350 | 4657 | 2016-08-16 | Blue Energy | Chiplow | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2 | 5 |  | n/a | Operational | Operational | Bewteen the villages of Bagthorpe, Barmer and Syderstone in North West Norfolk | Norfolk | Eastern | England |  | 581259 | 332212 | King's Lynn and West Norfolk Borough Council | 10/00883/FM | 11/00026/REF |  |  |  |  | 2010-05-26 |  | 2011-05-10 |  |  |  | 2012-05-24 | 2012-05-24 |  |  |  |  | 2015-03-31 | 2016-04-30
EN00422 | 4658 | 2016-02-26 | Banks Renewables | Hook Moor | Wind Onshore |  |  | 10.25 | n/a |  |  |  | 2.05 | 3 | 125 | n/a | Operational | Operational | Land at Hook Moor , Micklefield , Leeds | West Yorkshire | Yorkshire and Humber | England |  | 443851 | 435273 | Leeds City Council | 08/01118/FU | APP/N4720/A/10/2121279 |  |  |  |  | 2008-02-26 |  | 2009-08-04 |  |  |  | 2011-12-09 | 2011-12-09 |  |  |  |  | 2015-03-11 | 2016-01-15
EN00589 | 4659 | 2016-01-04 | Infrared Capital Partners | Crook Hill (Revised Application - Rochdale MBC) 2 of 2 | Wind Onshore |  |  | 23.8 | n/a |  |  |  | 3.4 | 7 |  | n/a | Operational | Operational | Crook Hill/Shore Moor, North Of Watergrove Reservoir, Rochdale | Greater Manchester | North West | England |  | 392515 | 419340 | Rochdale Borough Council | 08/D51145 | [5 empty] | 2008-07-10 |  | 2008-10-29 |  |  |  | 2009-07-31 | 2009-07-31 |  |  |  |  | 2015-01-01 | 2015-12-01
IF1174 | 4660 | 2017-03-27 | Private Developer | Far Marsh Farm (Resubmission) | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 |  | n/a | Operational | Operational | Marsh Road, Ottringham, Hull, Humberside | Humberside | Yorkshire and Humber | England | HU12 0AN | 524667 | 421763 | East Riding of Yorkshire Council | 12/04962/STPLFE | [5 empty] | 2012-12-14 | [6 empty] | 2013-12-24 |  |  |  |  | 2016-10-15 | 2017-01-15
A0279 | 4661 | 2015-05-29 | John Laing Environmental Assets Group | Wear Point | Wind Onshore |  |  | 8.2 | n/a |  |  |  | 2.05 | 4 |  | n/a | Operational | Operational | Land at Wear Point, Waterston Industrial, Llanstadwell | Dyfed | Wales | Wales |  | 193041 | 204629 | Pembrokeshire County Council | 09/0544/PA | [5 empty] | 2009-10-02 | [6 empty] | 2010-05-25 |  |  |  |  | 2012-06-30 | 2014-07-07
AA051 | 4662 | 2015-01-05 | Blue Energy (formerly Ridgewind Ltd) | Middlewick wind farm | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 |  | n/a | Operational | Operational | Land Between Middlewick Farm And Wraywick Farm, The Marshes, Southminster, Essex | Essex | Eastern | England |  | 600140 | 200001 | Maldon District Council | 10/00004/FUL | APP/X1545/A/10/2140423/NWF |  |  |  |  | 2010-01-05 |  | 2010-08-06 |  |  |  | 2011-05-01 | 2011-05-01 |  |  |  |  | 2013-06-04 | 2014-07-31
EN00093 | 4663 | 2014-12-02 | Hainsford Energy | Blyth Harbour Wind Farm (re-power) | Wind Onshore |  |  | 3.4 | n/a |  |  |  | 3.4 | 1 |  | n/a | Operational | Operational | Blyth Harbour, North Blyth, Cambois, Bedlington, Northumberland | Northumberland | North East | England |  | 432585 | 580800 | Northumberland County Council | 07/00287/FULES | [5 empty] | 2007-07-06 | [6 empty] | 2008-07-21 |  |  |  |  | 2011-06-01 | 2012-09-01
EN00095 | 4664 | 2017-08-29 | Greencoat Capital | Corriegarth | Wind Onshore |  |  | 69.5 | n/a |  |  |  | 3 | 23 | 120 | n/a | Operational | Operational | Near Gorthleck , Inverness-shire | Highland | Scotland | Scotland |  | 257500 | 813500 | Highland Council | 07/00673/FULIN | [5 empty] | 2007-07-15 | [6 empty] | 2015-04-02 |  |  |  |  | 2015-05-08 | 2016-09-30
EN00345 | 4665 | 2014-09-16 | Carsington Wind Energy Limited | Carsington Pasture | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 |  | n/a | Operational | Operational | Carsington Pasture, Derbyshire Dales | Derbyshire | East Midlands | England |  | 424640 | 354200 | Derbyshire Dales District Council | 07/00083/FUL | 07/00015/INQUIR |  |  |  |  | 2007-01-29 |  | 2007-07-20 |  |  |  | 2008-09-17 | 2008-09-17 |  |  |  |  | 2012-05-15 | 2014-02-05
EN00603 | 4666 | 2014-09-16 | Co-operative Group | Langford Wind Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Operational | Operational | Edworth Road, Langford, Biggleswade, Bedfordshire, SG18 9PJ | Bedfordshire | Eastern | England |  | 520400 | 241520 | Central Bedfordshire Council | 09/00118/FULL | APP/P0240/A/11/2150950/NWF |  |  |  |  | 2009-02-11 |  | 2011-01-07 |  |  |  | 2012-01-19 | 2012-01-19 |  |  |  |  | 2013-02-17 | 2014-01-30
N00214W | 4667 | 2014-09-16 | Fred Olsen Renewables | Mid Hill I | Wind Onshore |  |  | 57.5 | n/a |  |  |  | 2.3 | 25 |  | n/a | Operational | Operational | Mid Hill, Fetteresso Stonehaven | Grampian | Scotland | Scotland |  | 370540 | 786500 | Scottish Government (S36) | SO30179PF | [5 empty] | 2003-02-12 | [6 empty] | 2005-06-03 |  |  |  |  | 2012-04-01 | 2013-12-01
N00430W | 4668 | 2012-01-26 | Airtricity | Ardrossan Extension | Wind Onshore |  |  | 6 | n/a |  |  |  | 2 | 3 |  | n/a | Operational | Operational | Near Ardrossan North Ayreshire | Strathclyde | Scotland | Scotland |  | 223500 | 642500 | North Ayrshire Council | 05/01151/PP | [5 empty] | 2005-12-01 | [6 empty] | 2007-11-26 |  |  |  |  | 2008-03-01 | 2008-11-01
N00058W | 4669 | 2011-04-11 | CRE Energy/ Scottish Power | Beinn Tharsuinn Windfarm Project | Wind Onshore |  |  | 29.75 | n/a |  |  |  | 1.75 | 17 |  | n/a | Operational | Operational | Beinn Tharsuinn,Nr Easter Andross, Easter Ross, Northern Highlands | Highland | Scotland | Scotland |  | 261700 | 881900 | Highland Council | RC2003784 & SU2003318 | [5 empty] | 2002-04-19 | [6 empty] | 2005-02-11 |  |  |  |  | 2005-05-01 | 2005-12-01
EN00358 | 4670 | 2010-04-06 | Statkraft and Catamount Energy Corporation | Blaengwen (Re-Submission) | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 |  | n/a | Operational | Operational | Pencader Carms. | Dyfed | Wales | Wales | SA39 94P | 246387 | 233404 | Carmarthenshire County Council | [6 empty] | 2006-07-06 | [6 empty] | 2007-03-27 |  |  |  |  | 2008-11-01 | 2009-11-30
N00145W | 4671 | 2016-06-28 | RDC Scotland Ltd/ Falck Renewables | Boyndie Airfield | Wind Onshore |  |  | 16.65 | n/a |  |  |  | 2 | 8 |  | n/a | Operational | Operational | Boyndie Airfield, Banff | Grampian | Scotland | Scotland |  | 361978 | 864118 | Aberdeenshire Council | APP/2003/1692 | [5 empty] | 2003-06-24 | [6 empty] | 2004-07-23 |  |  |  |  | 2005-09-01 | 2006-02-01
N00327W | 4672 | 2017-12-04 | Gravis Capital Management | Burton Wold Windfarm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2 | 10 |  | n/a | Operational | Operational | Felaw Maltings, Felaw Street, Ipswich | Northamptonshire | East Midlands | England | IP2 8SJ | 492500 | 274500 | Kettering Borough Council | KE/03/0559 | [5 empty] | 2004-03-23 | [6 empty] | 2004-03-23 |  |  |  |  | 2005-12-01 | 2006-04-01
N00043W | 4673 | 2013-10-08 | B9 / Renewable Energy Systems (RES) | Callagheen | Wind Onshore |  |  | 22.75 | n/a |  |  |  | 1.75 | 13 |  | n/a | Operational | Operational | Garrison, near borders | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 4942 | 519598 | Northern Ireland Planning Service | L2001/1514 | [5 empty] | 2001-12-27 |  | 2003-06-27 | [9 empty] | 2005-05-16 | 2005-12-01
A0004 | 4674 | 2014-12-02 | Vattenfall | Edinbane Wind Farm | Wind Onshore |  |  | 41.4 | n/a |  |  |  | 2.3 | 18 |  | n/a | Operational | Operational | Cruachan Brinn Mhicaskill, Edinbane, Portree, Highlands | Highland | Scotland | Scotland | IV51 9PW | 134353 | 850769 | Highland Council | 02/00089/FULSL | [5 empty] | 2002-02-28 | [6 empty] | 2007-05-16 |  |  |  |  | 2008-08-01 | 2010-06-21
N00220W | 4675 | 2011-08-08 | Scottish and Southern Energy (SSE) | Fairburn | Wind Onshore |  |  | 43 | n/a |  |  |  | 2.15 | 20 |  | n/a | Operational | Operational | Fairburn Marybank | Highland | Scotland | Scotland |  | 242550 | 852250 | Highland Council | 05/00436/FULRC | [5 empty] | 2005-05-10 | [6 empty] | 2008-01-01 |  |  |  |  | 2009-02-01 | 2010-06-07
N00032W | 4676 | 2020-06-04 | Innogy (formerly RWE npower) | Farr Wind Farm | Wind Onshore |  |  | 92 | n/a |  |  |  | 2.3 | 40 |  | n/a | Operational | Operational | Tomatin Inverness | Highland | Scotland | Scotland |  | 273500 | 829000 | Scottish Government (S36) | [6 empty] | 2002-09-12 | [6 empty] | 2004-10-05 |  |  |  |  | 2005-04-01 | 2005-10-01
N00013W | 4677 | 2009-05-06 | RWE npower | Ffynnon Oer Wind Farm | Wind Onshore |  |  | 32 | n/a |  |  |  | 2 | 16 |  | n/a | Operational | Operational | Near Glyncorrwg | West Glamorgan | Wales | Wales |  | 287500 | 199500 | Neath Port Talbot County Borough Council | 02/1322 | [5 empty] | 2002-11-05 | [6 empty] | 2003-05-27 | [5 empty] | 2005-12-01
EN00066 | 4678 | 2012-02-27 | Scotwind (Scottish Renewables) | Flotta | Wind Onshore |  |  | 1.75 | n/a |  |  |  | 1.75 | 1 |  | n/a | Operational | Operational | Flotta,Westhill, Orkney | Orkney Islands | Scotland | Scotland |  | 336770 | 995385 | Orkney Islands Council | 02/241/PPF | [5 empty] | 2002-05-31 | [6 empty] | 2002-09-01 | [5 empty] | 2010-06-01
N00065W | 4679 | 2016-05-10 | Renewable Energy Systems (RES) | Forss Wind Farm (Extension) | Wind Onshore |  |  | 5.2 | n/a |  |  |  | 1.3 | 4 |  | n/a | Operational | Operational | Ex Navy Base Forss, Dounreay Thurso Caithness | Highland | Scotland | Scotland | KW14 7YB | 302000 | 969500 | Highland Council | 01/00380/FULCA | [5 empty] | 2005-01-05 | [6 empty] | 2006-10-16 |  |  |  |  | 2007-01-01 | 2007-07-01
N00064W | 4680 | 2016-05-10 | B9 / Renewable Energy Systems (RES) | Lough Hill | Wind Onshore |  |  | 10.5 | n/a |  |  |  | 1.75 | 6 |  | n/a | Operational | Operational | Lough Hill East of Drumquin County Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland |  | 38467 | 541020 | Northern Ireland Planning Service | K/2004/1139/F | [5 empty] | 2004-07-01 | [6 empty] | 2005-12-23 |  |  |  |  | 2006-02-01 | 2006-08-01
N00298W | 4681 | 2009-10-23 | Ecotricity | Michelin Tyre Co Ltd - Dundee | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 |  | n/a | Operational | Operational | Baldovie Road, Dundee Dundee | Tayside | Scotland | Scotland |  | 345050 | 732750 | Dundee City Council | 03/00424/FUL | [5 empty] | 2003-05-30 | [6 empty] | 2004-09-26 | [5 empty] | 2006-05-20
N00195W | 4682 | 2010-04-26 | Renewable Development Company (RDC) Scotland (Ltd) for FALCK RENEWABLES | Millennium Windfarm | Wind Onshore |  |  | 40 | n/a |  |  |  | 2.5 | 16 | 125 | n/a | Operational | Operational | Millennium Windfarm on The Achlain and Invergarry amd Aberchalder Estates Glengarry Invergarry Inverness-Shire (nr Glen Moriston Fort Augustus) | Highland | Scotland | Scotland |  | 225679 | 810840 | Highland Council | 03/00505/FULL | [5 empty] | 2003-12-01 | [6 empty] | 2005-04-01 |  |  |  |  | 2006-06-01 | 2008-07-15
EN00064 | 4683 | 2011-08-16 | Lomond Energy | Muirhall | Wind Onshore |  |  | 12.3 | n/a |  |  |  | 3 | 6 |  | n/a | Operational | Operational | Stellashaw Moss, South Lanarkshire | Strathclyde | Scotland | Scotland |  | 300605 | 653760 | South Lanarkshire Council | CL/05/0209 | [5 empty] | 2005-03-30 | [6 empty] | 2008-10-10 | [5 empty] | 2011-01-01
04081W3 | 4684 | 2009-05-06 | Renewable Energy Systems (RES) | Mynydd Clogau Wind Farm | Wind Onshore |  |  | 14.45 | n/a |  |  |  | 0.85 | 17 |  | n/a | Operational | Operational | Mynydd Clogau, Mynydd Bwrch-y-gors and Mynydd Cerrigllwydion, near Adfa, Newtown, Powys | Powys | Wales | Wales |  | 303300 | 298800 | Powys County Council | 1998/0669 | [5 empty] | 1998-09-11 | [6 empty] | 2002-05-23 | [5 empty] | 2005-12-01
N00148W | 4685 | 2013-10-08 | Private Developer | New Barn Farm | Wind Onshore |  |  | 4.5 | n/a |  |  |  | 1.5 | 3 |  | n/a | Operational | Operational | Billington Road, Burnley, BB11 5QQ | Lancashire | North West | England |  | 380100 | 430800 | Burnley Borough Council | APP/2002/0516 | APP/Z2315/A/03/117063 |  |  |  |  | 2002-09-02 |  | 2003-03-18 |  |  |  | 2004-02-23 | 2004-02-23 |  |  |  |  | 2006-10-01 | 2007-02-01
EN00216 | 4686 | 2009-05-06 | Foresight Group | North Pickenham | Wind Onshore |  |  | 14.4 | n/a |  |  |  | 1.8 | 8 |  | n/a | Operational | Operational | near Hempnall South Norfolk | Norfolk | Eastern | England |  | 585000 | 307000 | Breckland Council | [6 empty] | 2004-03-01 | [6 empty] | 2004-10-01 | [5 empty] | 2006-10-01
N00052W | 4687 | 2017-10-04 | Fred Olsen Renewables | Paul's Hill and Extension | Wind Onshore |  |  | 65 | n/a |  |  |  | 2.3 | 28 |  | n/a | Operational | Operational | Paul's Hill, Bowlingalloch, Moray, (area is also known as Ballindalloch) (14km west of Charlestown, 13km north of Granthon on Spey) | Grampian | Scotland | Scotland |  | 311500 | 840500 | Scottish Government (S36) | IEC3/99 | [5 empty] | 2001-09-30 | [6 empty] | 2003-03-31 |  |  |  |  | 2004-01-01 | 2006-04-01
EN00194 | 4688 | 2015-01-05 | Greencoat UK Wind | Tappaghan Extension | Wind Onshore |  |  | 9 | n/a |  |  |  | 1.5 | 6 |  | n/a | Operational | Operational | Lack, Tappaghan Mountains, Northern Ireland | Co. Fermanagh | Northern Ireland | Northern Ireland |  | 31856 | 531807 | Northern Ireland Planning Service | L/2006/1553/F | [5 empty] | 2005-06-12 | [6 empty] | 2008-05-01 | [5 empty] | 2009-07-01
04069W4 | 4689 | 2012-08-16 | Munich Re (previously Windjen Power Ltd) | Tir Mostyn And Foel Goch Wind Farm | Wind Onshore |  |  | 21.25 | n/a |  |  |  | 0.85 | 25 |  | n/a | Operational | Operational | Nantglyn, Denbighshire | Clwyd | Wales | Wales |  | 300300 | 358800 | Denbighshire County Council | 25/710/99/PF | [5 empty] | 1999-09-22 | [6 empty] | 2002-12-19 | [5 empty] | 2005-06-01
A0091 | 4690 | 2017-07-04 | Cumbria Wind Farms | Trimdon Grange | Wind Onshore |  |  | 5.2 | n/a |  |  |  | 1.3 | 4 |  | n/a | Operational | Operational | Trimdon Grange, County Durham | Durham | North East | England |  | 436000 | 536300 | Durham County Council | [6 empty] | 2005-07-01 | [12 empty] | 2008-07-10
N00304W | 4691 | 2009-10-23 | Wind Prospect / Community Windpower | Wardlaw Wood | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 |  | n/a | Operational | Operational | Dalry Ayrshire | Strathclyde | Scotland | Scotland |  | 224900 | 651200 | North Ayrshire Council | N/02/00906/PP | [5 empty] | 2002-12-01 | [6 empty] | 2003-09-01 | [5 empty] | 2006-03-01
AA592 | 4692 | 2019-12-12 | EGS Energy/Eden Project Limited | Eden Project Geothermal Energy Facility | Hot Dry Rocks (HDR) |  |  | 7 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Bodelva Road, Bodelva Par, Cornwall | Cornwall | South West | England | PL24 2SG | 204273 | 55775 | Cornwall Council | PA10/04671 | [5 empty] | 2010-08-09 | [6 empty] | 2010-12-16
A0211 | 4693 | 2020-06-18 | Geothermal Engineering | United Downs Project (Geothermal) | Hot Dry Rocks (HDR) |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Redruth, Cornwall | Cornwall | South West | England |  | 174439 | 41603 | DECC (S36) | 10/00056/GEO | [5 empty] | 2010-03-08 | [6 empty] | 2010-08-13 |  |  |  |  | 2018-03-15
B1543 | 4694 | 2015-03-03 | Marks and Spencer plc | East Midlands Distribution Centre | Solar Photovoltaics |  |  | 6.1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Castle Donington, Leicestershire | Leicestershire | East Midlands | England | DE74 2HL | 443356 | 328304 | North West Leicestershire District Council | 11/00169/VCI | [5 empty] | 2011-02-22 | [6 empty] | 2011-04-04 |  |  |  | 2016-04-04 | 2014-10-28 | 2015-03-02
B1541 | 4695 | 2016-05-10 | Yorkshire Water | Esholt WWTW | Sewage Sludge Digestion |  |  | 3 | No | 0.5 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Apperley Lane, Bradford, West Yorkshire, BD10 0TW | West Yorkshire | Yorkshire and Humber | England | BD10 0WT | 419088 | 438904 | Bradford Metropolitan District Council | 11/03788/FUL | [5 empty] | 2011-09-30 | [6 empty] | 2012-03-30 |  |  |  |  | 2012-03-31 | 2014-10-03
| 4696 | 2016-05-27 | Raahead WT Limited | Land associated with Rawhead Farm | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 1.5 | 1 | 120 | n/a | Planning Application Withdrawn | Application Withdrawn | Muirhall Farm, Carnwath, Lanark, Strathclyde | Lanarkshire | Scotland | Scotland | ML11 8LL | 261479 | 648104 | South Lanarkshire Council | EK/14/0319 | [5 empty] | 2014-10-31 | 2016-02-24
| 4697 | 2016-05-27 | Lairfad WT Limited | Land associated with Lairfad | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 1.5 | 1 | 120 | n/a | Planning Application Withdrawn | Application Withdrawn | Lairfad, Millwell Road, East Kilbride | Lanarkshire | Scotland | Scotland | G75 9DP | 261947 | 647944 | South Lanarkshire Council | EK/14/0320 | [5 empty] | 2014-10-31 | 2016-02-24
C3450 | 4699 | 2020-06-08 | Scottish and Southern Energy (SSE) | Slough Heat & Power Station | EfW Incineration |  |  | 49.9 | Yes | 1 | n/a |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Slough Heat & Power Station, Edinburgh Avenue, Slough | Berkshire | South East | England | SL1 4TU | 495360 | 181442 | Slough Borough Council | P/00987/024 | [5 empty] | 2014-10-06 | [6 empty] | 2017-06-02 |  |  |  | 2022-06-02
| 4700 | 2016-09-01 | Green Energy UK Direct | Skinners Farm (resubmission) | Solar Photovoltaics |  |  | 6 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Skinners Farm, Skinners Lane, Edenbridge | Kent | South East | England | TN8 6LW | 545259 | 146617 | Sevenoaks District Council | 14/03361/FUL | APP/G2245/W/15/3011499 |  |  |  |  | 2014-10-28 |  | 2015-01-08 | 2015-06-01 |  | 2015-12-15
| 4701 | 2017-04-20 | TGC Renewables | Land at High Point Farm | Solar Photovoltaics |  |  | 4.5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | High Point Farm, Neen Sollars | Shropshire | West Midlands | England | DY14 9AD | 366415 | 270925 | Shropshire Council | 14/04463/FUL | APP/L3245/W/15/3019429 |  |  |  |  | 2014-10-22 |  | 2015-03-16 | 2015-07-06 |  |  | 2016-03-16 | 2016-03-16 |  |  |  |  | 2016-12-12 | 2017-03-31
C3447 | 4702 | 2015-05-28 | Viridis Wind Turbines | Hoddlesden Moss | Wind Onshore |  |  | 2.4 | n/a | 0.9 | 3.07 |  | 0.8 | 3 | 74 | n/a | Planning Permission Refused | Application Refused | Hoddlesden Moss, Hoddlesden, Darwen | Lancashire | North West | England | BB3 3PP | 372388 | 420215 | Blackburn with Darwen Borough Council | 10/14/1117 | [5 empty] | 2014-10-17 |  | 2015-04-21
C3463 | 4703 | 2016-04-14 | British Solar Renewables | Land at Newlands Farm | Solar Photovoltaics |  |  | 4.99 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Newlands Farm, Chickerell, West Dorset | Dorset | South West | England | DT3 4BG | 365099 | 81019 | West Dorset District Council | WD/D/14/002675 | [5 empty] | 2014-10-13 | [6 empty] | 2014-12-17 |  |  |  | 2017-12-17 | 2015-06-08 | 2016-02-15
| 4704 | 2015-05-28 | Barvills Solar Limited (BE Renewables) | Barvills Solar Farm | Solar Photovoltaics |  |  | 11.6 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Barvills Farm, Princess Margaret Road, East Tilbury, Tilbury | Essex | Eastern | England | RM18 8PA | 568324 | 177586 | Thurrock Council | 14/01124/FUL | [5 empty] | 2014-10-21 | 2015-03-16
C3461 | 4705 | 2017-06-27 | Stuart Howes & Son Ltd | Eckland Lodge Farm | Solar Photovoltaics |  |  | 2.87 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Eckland Lodge Farm, Desborough Road, Braybrooke | Northamptonshire | East Midlands | England | LE16 8HB | 478714 | 285119 | Kettering Borough Council | KET/2014/0655 | [5 empty] | 2014-10-22 | [6 empty] | 2015-07-29 |  |  |  | 2018-07-29 | 2016-11-14 | 2016-12-23
C3460 | 4706 | 2016-05-20 | Emsrayne Limited | Caddington Solar Farm (Phase 2) | Solar Photovoltaics |  |  | 4.99 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Millfield Farm, Millfield Lane, Caddington, Luton | Bedfordshire | Eastern | England | LU1 4AJ | 505561 | 218643 | Central Bedfordshire Council | CB/14/04064 | [5 empty] | 2014-10-21 | [6 empty] | 2015-02-02 |  |  |  | 2018-01-02 | 2016-01-15 | 2016-03-30
| 4707 | 2017-02-22 | Green Highland Renewables | Ceannacroc | Small Hydro |  |  | 1.6 | n/a | 0.7 | 10.96 |  | n/a | n/a | n/a | n/a | Operational | Operational | Ceannacroc Lodge, Glenmoriston, Inverness | Highland | Scotland | Scotland | IV63 7YN | 222790 | 811296 | Highland Council | 14/03963/FUL | [5 empty] | 2014-10-18 | [6 empty] | 2014-12-18 |  |  |  | 2017-12-18 | 2015-09-15 | 2017-01-15
C3434 | 4708 | 2016-06-30 | Sawston Solar Farm | Sawston Solar Farm (Land North of Dales Manor Business Park) (resubmission) | Solar Photovoltaics |  |  | 14 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land North of Dales Manor Business Park, West Way, Sawston, Cambridge | Cambridgeshire | Eastern | England |  | 549406 | 250809 | South Cambridgeshire District Council | S/2409/14/FL | APP/W0530/W/15/3013863 |  |  |  |  | 2014-10-14 |  | 2014-12-12 | 2015-10-06 |  | 2016-06-15
C3462 | 4709 | 2015-06-15 | Greater Manchester Waste Disposal Authority | Salford Road Solar Farm | Solar Photovoltaics |  |  | 2.2 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Former CMP/GNB Batteries Ltd, Salford Road, Bolton | Greater Manchester | North West | England | BL5 1DG | 370541 | 404661 | Bolton Metropolitan Borough Council | 92938/14 | [5 empty] | 2014-10-14 | [6 empty] | 2014-12-22 |  |  |  | 2017-12-22
C3440 | 4711 | 2016-07-01 | Elgin Energy EsCo | Ebnal Lodge Solar Farm | Solar Photovoltaics |  |  | 15 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Rhosygadfa, Gobowen, Oswestry | Shropshire | West Midlands | England | SY10 7A | 332011 | 334106 | Shropshire Council | 14/03946/FUL | APP/L3245/W/16/3142392 |  |  |  |  | 2014-10-10 |  | 2015-07-13 | 2016-02-03 |  | 2016-06-06
C3464 | 4712 | 2016-05-20 | Solar Ventures | Montys Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Montys Farm, Norton Fitzwarren, Taunton | Somerset | South West | England | TA4 1AA | 318295 | 126485 | Taunton Deane Borough Council | 25/14/0028 | [5 empty] | 2014-10-17 | [6 empty] | 2015-10-23 |  |  |  | 2018-10-23 | 2016-01-10 | 2016-03-20
C3444 | 4713 | 2016-06-27 | Primrose Solar / Mongoose Energy | Merston Solar Park | Solar Photovoltaics |  |  | 10 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Pagham Road, Merston, Chichester | West Sussex | South East | England | PO20 1ED | 489440 | 102825 | Chichester District Council | 14/02814/FUL | [5 empty] | 2014-10-03 | [6 empty] | 2015-03-19 |  |  |  | 2015-03-19 | 2015-12-01 | 2016-06-28
C3443 | 4715 | 2016-04-04 | Locogen | Limolands Farm Solar Array | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Limolands Farm, Vaggs Lane, Hordle, Lymington | Hampshire | South East | England | SO41 0FP | 426921 | 96715 | New Forest National Park Authority | 14/00817 | APP/B9506/W/15/3006387 |  |  |  |  | 2014-10-03 |  | 2014-12-17 | 2015-05-15 |  | 2016-03-30
C3429 | 4716 | 2015-05-28 | Redpath Energy | Hesledon East Farm | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 1.5 | 1 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | Hesleden East House, Cold Hesledon, Seaham | County Durham | North East | England | SR7 8SP | 442771 | 546955 | Durham County Council | DM/14/02910/FPA | [5 empty] | 2014-10-02 | 2015-05-12
C3436 | 4718 | 2016-02-16 | UK Solar Assets (Alcor LS-SPV) | Fambridge Road/Canewdon Road | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North East of Fambridge Road, Ulverston Road, Rochford | Essex | Eastern | England | SS4 3LD | 586831 | 194705 | Rochford District Council | 14/00649/FUL | [5 empty] | 2014-10-09 | [6 empty] | 2015-04-02 |  |  |  | 2018-04-02 | 2015-09-01 | 2015-11-23
C3446 | 4719 | 2015-11-05 | Iggesund Paperboard | Iggesund Wind Farm | Wind Onshore |  |  | 9 | n/a | 0.9 | n/a |  | 3 | 3 | 110 | n/a | Planning Permission Refused | Application Refused | Iggesund Paperboard (Workington) Ltd, Siddick, Workington | Cumbria | North West | England | CA14 1JX | 300407 | 530861 | Allerdale Borough Council | 2/2014/0737 | [5 empty] | 2014-10-08 |  | 2015-10-08
C3417 | 4720 | 2016-05-27 | Kinetica Energy | Land Adjacent to Taw Valley Creamery | Solar Photovoltaics |  |  | 22 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Adjacent to Taw Valley Creamery, North Tawton | Devon | South West | England | EX20 2AA | 265099 | 100526 | West Devon Borough Council | 01132/2014 | [5 empty] | 2014-10-06 |  | 2016-01-08
C3416 | 4721 | 2015-04-14 | Roskrow Solar | Roskrow Farm | Solar Photovoltaics |  |  | 8.9 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Roskrow Farm, Roskrow, Penryn | Cornwall | South West | England | TR10 9AP | 176446 | 35897 | Cornwall Council | PA14/08288 | [5 empty] | 2014-10-01 | [6 empty] | 2014-11-24 |  |  |  | 2017-11-24 | 2015-01-07 | 2015-03-31
| 4722 | 2014-12-05 | Private Developer | Blackburnhall Self Contained Hydro Generator | Small Hydro |  |  | 2 | n/a | 0.7 | 10.96 |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | 7 Blackburn Hall Holdings, Blackburn, Bathgate | West Lothian | Scotland | Scotland | EH47 7AB | 299316 | 664779 | West Lothian Council | 0697/FUL/14 | [5 empty] | 2014-10-07 | 2014-11-13
C3414 | 4723 | 2015-03-09 | Solar Park Developments | Land off Moss Side Lane | Solar Photovoltaics |  |  | 18 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land of Moss Side Lane, Wrea Green, Preston | Lancashire | North West | England | PR4 2WP | 338818 | 430575 | Fylde Borough Council | 14/0696 | [5 empty] | 2014-10-01 |  | 2015-02-04
| 4724 | 2017-04-18 | Island Green Power | Ballyboley Solar (Carrowdore) | Solar Photovoltaics |  |  | 6 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands 88m West of 2a Ballyblack Road East, Carrowdore, Newtownards | Co. Down | Northern Ireland | Northern Ireland | BT22 2HH | 169400 | 525454 | Northern Ireland Planning Service | X/2014/0538/F | [5 empty] | 2014-10-03 | [6 empty] | 2015-06-03 |  |  |  | 2020-06-03 | 2016-10-01 | 2017-02-28
| 4725 | 2020-06-04 | Scottish and Southern Energy (SSE) | Bessy Bell 2 Extension | Wind Onshore |  |  | 9 | n/a | 0.9 | n/a |  | 2.3 | 4 | 115 | n/a | Appeal Granted | Awaiting Construction | Drumlegagh Roadd crossing, South of Baronscourt Road junction, Omagh | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 5R | 52695 | 544591 | Northern Ireland Planning Service | K/2013/0145/F | 2013/A0219 |  |  |  |  | 2013-04-15 |  |  | 2014-10-06 |  |  | 2016-01-18 | 2016-01-18
| 4726 | 2016-01-04 | Renewable Developments | Gwenlais Uchaf Farm | Solar Photovoltaics |  |  | 4 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Gwenlais Uchaf Farm, Pontlliw | Swansea | Wales | Wales | SA4 9HB | 261848 | 201556 | City and County Council of Swansea | 2014/1620 | APP/B6855/A/15/3124709 |  |  |  |  | 2014-10-29 |  | 2015-05-15 | 2015-08-10 |  | 2015-11-30
| 4727 | 2016-03-04 | Hale Solar Limited | Hale Farm | Solar Photovoltaics |  |  | 8 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Hale Farm, Parley Green Lane, Christchurch | Dorset | South West | England | BH23 6BB | 409688 | 97654 | Christchurch Borough Council | 8/14/0520 | [5 empty] | 2014-10-28 | [6 empty] | 2015-09-23 |  |  |  | 2018-09-23 |  | 2016-02-26
| 4728 | 2018-10-03 | Pennant Walters | Esgair Cwmowen | Wind Onshore |  |  | 47.5 | n/a | 0.9 | n/a |  | 2.5 | 19 |  | n/a | Planning Application Submitted | Application Submitted | Land at Esgair Cwmowen Nr Carno | Powys | Wales | Wales |  | 306701.05 | 303409.4 | Powys County Council | P/2010/0890 | [5 empty] | 2010-05-21
| 4729 | 2016-03-17 | Pylle Solar/ John Laing Environmental | Pylle Southern solar park (Lower Easton Farm) | Solar Photovoltaics |  |  | 4.99 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off Easton Lane, Pylle, Somerset | Somerset | South West | England | BA4 6SY | 362355 | 138696 | Mendip District Council | 2014/2237/FUL | [5 empty] | 2014-10-25 | [6 empty] | 2015-01-26 |  |  |  | 2018-01-26 | 2015-10-20 | 2015-12-20
| 4730 | 2016-12-21 | University of St Andrews | Sustainable Power and Research Campus | Biomass (dedicated) |  |  | 6.5 | Yes | 2 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Main Street, Curtis Fine Paper Mill, Guardbridge, St. Andrews | Fife | Scotland | Scotland | KY16 0UU |  |  | Fife Council | 14/00189/PAN | [5 empty] | 2014-01-21 | [6 empty] | 2014-02-10 |  |  |  |  | 2015-07-14 | 2016-12-07
| 4734 | 2017-10-04 | SRE (Darran) | Land at Darran Farm | Solar Photovoltaics |  |  | 2.6 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Darran Farm, Argoed, Blackwood | Caerphilly | Wales | Wales | NP12 0HX | 318499 | 199490 | Caerphilly County Borough Council | 14/0455/FULL | [5 empty] | 2014-10-29 | [6 empty] | 2016-03-10 |  |  |  | 2021-03-10 | 2017-01-30 | 2017-03-30
| 4735 | 2015-02-20 | Cassidy & Ashton Group Ltd | Land off Tithe Barn lane | Solar Photovoltaics |  |  | 4.99 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Tithebarn Farm, Tithe Barn Lane, Heapey, Chorley | Lancashire | North West | England | PR6 8TE | 360436 | 419966 | Chorley Borough Council | 14/01132/FULMAJ | [5 empty] | 2014-10-30 |  | 2015-02-11
| 4736 | 2016-03-16 | British Solar Renewables | Wisbech Solar Farm | Solar Photovoltaics |  |  | 3.5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Begdale Road, Elm, Wisbech | Cambridgeshire | Eastern | England | PE14 0BE | 546405 | 306650 | Fenland District Council | F/YR14/0856/F | [5 empty] | 2014-10-24 | [6 empty] | 2015-01-21 |  |  |  | 2018-01-21 | 2015-10-01 | 2015-12-15
| 4737 | 2018-09-20 | Freewatt Renewable Energy | Stow Solar Farm | Solar Photovoltaics |  |  | 10.24 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Stow Park Road, Stow, Lincoln | Lincolnshire | East Midlands | England | LN1 2AJ | 487057 | 381428 | West Lindsey District Council | 131968 | [5 empty] | 2014-10-23 | [6 empty] | 2014-12-04 |  |  |  | 2017-12-04 | 2016-01-11 | 2016-03-11
| 4738 | 2016-07-25 | Rhug Estate | Rhug Estate | Solar Photovoltaics |  |  | 1.2 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Rhug Estate, Corwen | Denbighshire | Wales | Wales | LL21 0EH | 303123 | 344332 | Denbighshire County Council | 05/2014/1178 | [5 empty] | 2014-10-17 | [6 empty] | 2015-01-14 |  |  |  | 2020-01-14 | 2016-01-15 | 2016-03-15
| 4739 | 2017-06-27 | Solar Associates | Snettisham Solar Farm | Solar Photovoltaics |  |  | 2.7 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Bircham Road, Snettisham, King's Lynn | Norfolk | Eastern | England | PE31 7NF | 596653 | 334057 | King's Lynn and West Norfolk Borough Council | 14/01497/FM | APP/V2635/W/15/3130599 |  |  |  |  | 2014-10-20 |  | 2015-04-01 | 2015-08-24 |  |  | 2016-03-24 | 2016-03-24 |  |  |  | 2019-03-24 | 2017-01-01 | 2017-03-28
C3459 | 4740 | 2016-05-10 | Hazel Capital LLP | West Hill Farm | Solar Photovoltaics |  |  | 2.4 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | West Hill Farm, West Down, Ilfracombe | Devon | South West | England | EX34 8NF | 251037 | 141180 | North Devon District Council | 58320 | [5 empty] | 2014-10-22 | [6 empty] | 2015-03-05 |  |  |  | 2018-03-05 | 2015-03-06 | 2015-03-31
| 4741 | 2019-04-25 | Solar Power South | Land at New Orchard Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land at New Orchard Farm, Puxton Lane, Hewish, Weston-Super-Mare | Somerset | South West | England | BS24 6TA | 340817 | 163929 | North Somerset Council | 14/P/2283/F | [5 empty] | 2014-10-20 | [6 empty] | 2015-06-30 |  |  |  | 2018-06-30
| 4742 | 2014-11-14 | Gretton Brook Estates | Brookfield Plantation | Advanced Conversion Technologies |  |  |  | Yes | 2 | n/a |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Brookfield Plantation, Gretton Brook Road, Earlstrees Industrial Estate, Corby, Northamptonshire | Northamptonshire | East Midlands | England |  | 489725 | 291691 | Corby Borough Council | 13/00027/OUT | [5 empty] | 2013-01-24
| 4743 | 2014-11-14 | Gretton Brook Estates | Brookfield Plantation | EfW Incineration |  |  |  | Yes | 1 | n/a |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Brookfield Plantation, Gretton Brook Road, Earlstrees Industrial Estate, Corby, Northamptonshire | Northamptonshire | East Midlands | England |  | 489725 | 291691 | Corby Borough Council | 13/00027/OUT | [5 empty] | 2013-01-24
| 4744 | 2020-01-21 | B.X.C Development Partners | Brent Cross Cricklewood | Advanced Conversion Technologies |  |  |  | Yes | 2 | n/a |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Brent Cross Cricklewood Regeneration Area | Greater London | London | England |  |  |  | Barnet London Borough Council | C/17559/08 | [5 empty] | 2008-03-26 | [6 empty] | 2010-07-29 |  |  |  | 2017-07-29
| 4745 | 2015-12-22 | Lightsource Renewable Energy | Cold Harbour Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Cold Harbour Farm, Blind Piece Lane, Dalton | North Yorkshire | Yorkshire and Humber | England | YO7 3JG | 444776 | 475104 | Hambleton District Council | 14/02236/FUL | [5 empty] | 2014-11-03 | [6 empty] | 2015-02-18 |  |  |  | 2018-02-18 | 2015-10-16 | 2015-12-18
C3431 | 4746 | 2014-11-17 | Epsilon Solar | Land South of Melton Rd | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land South of Melton Road, Burton On The Wolds, Leicestershire | Leicestershire | East Midlands | England | LE12 5TQ | 461532 | 321015 | Charnwood Borough Council | P/14/2030/2 | [5 empty] | 2014-11-04 |  | 2015-01-09
| 4747 | 2017-04-24 | Southrigg WT | Southrigg | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 1.5 | 1 | 125 | n/a | Operational | Operational | Southrigg Farm, Bathgate | North Lanarkshire | Scotland | Scotland | EH48 3AW | 291875 | 665563 | North Lanarkshire Council | 14/02112/FUL | PPA-320-2086 |  |  |  |  | 2014-11-04 |  | 2015-05-18 | 2015-06-01 |  |  | 2015-08-12 | 2015-08-12 |  |  |  | 2018-08-12 | 2016-08-01 | 2016-10-01
| 4748 | 2016-07-18 | Push Energy | Land at Whatton Road | Solar Photovoltaics |  |  | 1.53 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Site East of Whatton Road, Kegworth, Derby | Leicestershire | East Midlands | England | DE74 2DU | 448140 | 325845 | North West Leicestershire District Council | 14/00847/FULM | [5 empty] | 2014-10-13 | [6 empty] | 2015-05-06 |  |  |  | 2018-05-06 | 2015-09-07 | 2015-10-23
| 4749 | 2017-01-24 | Culham Renewables | Land adjacent to Culham Science Centre | Solar Photovoltaics |  |  | 7 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Fullamoor Farm House, Clifton Hampden, Abingdon | Oxfordshire | South East | England | OX14 3DD | 453359 | 195096 | South Oxfordshire District Council | P14/S3192/FUL | [5 empty] | 2014-11-11 | [6 empty] | 2015-11-18 |  |  |  | 2018-11-18
| 4751 | 2020-04-21 | Upper Wick Solar Farm | Upper Wick Solar Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Parcel To East of Wick Bridge, Upper Wick, Dursley | Gloucestershire | South West | England | GL11 6DE | 371868 | 196522 | Stroud District Council | S.14/2460/FUL | [5 empty] | 2014-11-07 | [6 empty] | 2015-01-14 |  |  |  | 2020-10-10 | 2015-09-16 | 2016-01-18
| 4752 | 2015-08-19 | KWTN Solar | Marshwood Farm | Solar Photovoltaics |  |  | 1.755 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Station Road, Chard Junction, Chard, Somerset | Somerset | South West | England | TA20 4QN | 334116 | 104847 | South Somerset District Council | 14/04957/FUL | [5 empty] | 2014-11-05 | [6 empty] | 2015-01-12 |  |  |  | 2018-01-12 | 2015-05-28 | 2015-06-26
| 4753 | 2016-08-17 | House O'Hill Wind Energy | House O’Hill Solar Farm | Solar Photovoltaics |  |  | 1.6 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | House O'Hill, Memsie, Fraserburgh | Aberdeen | Scotland | Scotland | AB43 7AU | 397540 | 859050 | Aberdeenshire Council | APP/2014/3833 | [5 empty] | 2014-11-06 | [6 empty] | 2015-01-28 |  |  |  | 2018-01-28 | 2015-09-01 | 2015-12-01
| 4755 | 2019-01-28 | Millennium Park (Grimsby) Ltd | West Marsh (Phase 1) | Solar Photovoltaics |  |  | 2 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | West Marsh, Cromwell Road, Grimsby | Humberside | Yorkshire and Humber | England | DN31 2B | 525383 | 410022 | North East Lincolnshire Council | DM/1120/14/FUL | [5 empty] | 2014-10-31 | [6 empty] | 2015-02-13 |  |  |  | 2018-02-13
| 4756 | 2015-01-08 | London Southend Airport Ltd | London Southend Airport | Solar Photovoltaics |  |  | 3 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | London Southend Airport, Southend Airport, Southend-On-Sea | Essex | Eastern | England | SS2 6YF | 586759 | 189730 | Rochford District Council | 14/00779/FUL | [5 empty] | 2014-10-28 |  | 2014-12-22
| 4757 | 2015-04-16 | Greenfields (A) | Hawkers Farm (resubmission) | Solar Photovoltaics |  |  | 9.5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Hawkers Farm, Yeo Moor Drove, Theale, Wedmore | Somerset | South West | England | BS28 4SN | 346752 | 147518 | Sedgemoor District Council | 50/14/00095 | [5 empty] | 2014-11-05 | [6 empty] | 2015-02-17 |  |  |  | 2018-02-17 | 2015-02-18 | 2015-03-23
| 4759 | 2015-02-09 | Green Switch Solutions | Land at Rectory Farm | Solar Photovoltaics |  |  | 8.94 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Rectory Farm, Rectory Lane, Upton Warren, Bromsgrove | Hereford and Worcester | West Midlands | England | B61 7EL | 393414 | 268147 | Wychavon District Council | 14/02267 | [5 empty] | 2014-09-08 | 2015-01-26
| 4760 | 2019-01-28 | Millennium Park (Grimsby) Ltd | West Marsh (Phase 2) | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | West Marsh, Cromwell Road, Grimsby | Humberside | Yorkshire and Humber | England | DN31 2B | 525432 | 410064 | North East Lincolnshire Council | DM/1124/14/FUL | [5 empty] | 2014-10-31 | [6 empty] | 2015-02-13 |  |  |  | 2018-02-13
| 4761 | 2016-03-31 | Woodtown Solar Limited | Woodtown Farm | Solar Photovoltaics |  |  | 3.82 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Woodtown Farm, Christchurch Road, West Parley | Dorset | South West | England | BH22 8SW | 409137 | 97413 | East Dorset District Council | 3/14/0956/FUL | [5 empty] | 2014-10-24 | [6 empty] | 2015-10-14 |  |  |  | 2018-10-14 | 2015-10-23 | 2015-12-23
| 4764 | 2017-10-04 | Pennant Walters Ltd | Foel Trawsnant | Wind Onshore |  |  | 39 | n/a | 0.9 | n/a |  | 3 | 13 |  | n/a | Planning Application Submitted | Application Submitted | Foel Trawsnant, Bryn, Port Talbot | Neath Port Talbot | Wales | Wales |  | 283447 | 193081 | Neath Port Talbot County Borough Council | P2014/0825 | [5 empty] | 2014-10-20
| 4765 | 2015-05-28 | HP Sleigh & Son Ltd | Buckies Hill Wind Farm | Wind Onshore |  |  | 4.5 | n/a | 0.9 | 3.07 |  | 0.9 | 5 | 67 | n/a | Planning Permission Refused | Application Refused | Land 790m South of Farm House, Buckies, Halkirk | Highland | Scotland | Scotland | KW14 7XH | 311020 | 962427 | Highland Council | 14/03913/FUL | [5 empty] | 2014-11-06 |  | 2015-04-24
| 4766 | 2016-01-11 | West Sussex County Council | Land at Tangmere Airfield | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Tangmere Airfield Nurseries, The Old Airfield, Tangmere Road, Tangmere, Chichester | West Sussex | South East | England | PO20 2GP | 491485 | 106199 | Chichester District Council | 14/03894/CPO | [5 empty] | 2014-11-13 | [6 empty] | 2015-01-01 |  |  |  |  | 2015-08-01 | 2015-10-07
| 4767 | 2018-07-05 | NESF (formerly Green Energy Networks) | Land at Coton Park Colliery | Solar Photovoltaics |  |  | 2.5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Coton Park Colliery, Coton Park, Linton, Swadlincote | Derbyshire | East Midlands | England | DE12 6R | 427248 | 317953 | South Derbyshire District Council | 9/2014/1015 | [5 empty] | 2014-11-10 | [6 empty] | 2015-03-09 |  |  |  | 2018-03-09 | 2015-12-01 | 2015-12-21
| 4768 | 2015-08-14 | Airvolution Energy | Carr Ban Wind Farm | Wind Onshore |  |  | 23.8 | n/a | 0.9 | n/a |  | 3.4 | 7 | 114 | n/a | Planning Application Withdrawn | Application Withdrawn | Land 475M NW Of Cloughmor Farr, Inverarnie Park, Inverarnie, Inverness, Highlands | Highland | Scotland | Scotland | IV3 | 266696 | 836053 | Highland Council | 14/04805/FUL | [5 empty] | 2015-01-19 | 2015-05-12
| 4769 | 2017-08-24 | Public Power Solutions/ Swindon Borough Council | Chapel Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Chapel Farm, Lower Widhill Farm Lane, Blunsdon | Wiltshire | South West | England | SN26 8DD | 412790 | 190480 | Swindon Borough Council | S/LDO/15/1182 | [5 empty] | 2015-07-06 | [6 empty] | 2015-08-10 |  |  |  |  | 2017-01-18 | 2017-03-31
| 4770 | 2016-11-30 | Kilrubie Wind Farm | Kilrubie Wind Farm | Wind Onshore |  |  | 21 | n/a | 0.9 | n/a |  | 3 | 7 | 115 | n/a | Appeal Withdrawn | Application Withdrawn | Land North of Upper Stewarton, Eddleston, Peebles | Scottish Borders | Scotland | Scotland |  | 322102 | 648257 | Scottish Borders Council | 15/00818/FUL | PPA-140-2056 |  |  |  |  | 2015-07-14 |  |  | 2016-01-15 | 2016-11-01
| 4774 | 2015-10-06 | Amec Foster Wheeler | Auld Clay | Wind Onshore |  |  | 9.2 | n/a | 0.9 | n/a |  | 2.3 | 4 | 100 | n/a | Planning Permission Refused | Application Refused | Site to North West of Bankend Farm, Saltcoats | North Ayrshire | Scotland | Scotland |  | 227557 | 646379 | North Ayrshire Council | 15/00221/PP | [5 empty] | 2015-04-23 |  | 2015-09-03
| 4775 | 2020-02-24 | Lightsource BP | Bryn Henllys | Solar Photovoltaics |  |  | 20 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Bryn Henllys Open Cast, Upper Cwmtwch, Cwmllynfell | Powys | Wales | Wales | SA9 2XX | 276490 | 212410 | Powys County Council | P/2015/0176 | [5 empty] | 2015-02-06 | [6 empty] | 2018-06-11 |  |  |  | 2021-06-11
| 4776 | 2019-06-24 | Whirlwind Renewables | Achlachan Wind Farm - Phase 2 | Wind Onshore |  |  | 6.9 | n/a | 0.9 | n/a |  | 2.3 | 3 | 110 | n/a | Abandoned | Abandoned | Achlachan Windfarm, Watten | Highland | Scotland | Scotland |  | 315293 | 951239 | Highland Council | 15/01831/FUL | PPA-270-2142 |  |  |  |  | 2015-05-21 |  | 2015-09-24 | 2015-11-06 |  |  | 2016-03-29 | 2016-03-29
| 4780 | 2016-03-14 | GPV Rhynie | Cairnmore Solar Park | Solar Photovoltaics |  |  | 3.75 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Cairnmore, Rhynie, Huntly | Aberdeen | Scotland | Scotland | AB54 4NA | 350267 | 824528 | Aberdeenshire Council | APP/2014/3956 | [5 empty] | 2014-11-13 | [6 empty] | 2015-02-05 |  |  |  | 2018-01-05 | 2015-05-01 | 2016-02-17
| 4782 | 2015-09-27 | Community Wind Power | Spango Community Wind Farm | Wind Onshore |  |  | 49 | n/a | 0.9 | n/a |  | 3.5 | 12 | 145 | n/a | Planning Permission Refused | Application Refused | Spango (Mid Rig/Black Hill), northeast of Kirkconnel, Kirkconnel, Sanquhar | Dumfries and Galloway | Scotland | Scotland | DG4 6AA | 275900 | 614386 | Dumfries and Galloway Council | 14/P/3/0560 | [5 empty] | 2014-11-10 |  | 2015-09-24
| 4783 | 2017-06-23 | British Solar Renewables | Bake Farm Solar Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Bake Farm House, Salisbury Road, Coombe Bissett, Salisbury | Wiltshire | South West | England | SP5 4JT | 411771 | 127679 | Wiltshire Council | 14/10548/FUL | [5 empty] | 2014-11-14 | [6 empty] | 2015-03-05 |  |  |  | 2018-03-05 | 2015-12-30 | 2016-03-15
| 4784 | 2015-02-09 | Lark Energy | Land adjacent to A422 | Solar Photovoltaics |  |  | 1.6 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land adjacent to A422, Buckingham road near Brackley | Buckinghamshire | South East | England | NN13 5JB | 460128 | 236071 | Aylesbury Vale District Council | 14/03309/APP | [5 empty] | 2014-11-12 | 2015-02-05
| 4785 | 2016-11-28 | Emotion Solar One | Thompson House Equestrian farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Thompson House Equestrain Centre, Pepper Lane, Standish | Greater Manchester | North West | England | WN6 0PP | 354830 | 411442 | Wigan Council | A/14/79904/MAJOR | [5 empty] | 2014-10-13 | [6 empty] | 2015-02-06 |  |  |  | 2018-02-06 | 2016-01-05 | 2016-03-31
| 4786 | 2018-10-03 | Severn Trent (formerly Agrivert) | Stormy Down (Waste AD) | Anaerobic Digestion |  |  | 3 | No | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Operational | Operational | Parc Stormy, Stormy Down, Airfield Stormy, Pyle, Bridgend | Bridgend | Wales | Wales | CF33 4RS | 284103 | 180025 | Bridgend County Borough Council | P/14/700/FUL | [5 empty] | 2014-10-23 | [6 empty] | 2015-04-19 |  |  |  | 2018-04-19 | 2015-08-25 | 2016-10-03
| 4787 | 2018-03-02 | Biogen (formerly Tamar Energy) | Knowsley AD Facility | Anaerobic Digestion |  |  | 3 | Yes | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land off North Perimeter Road, Knowsley Industrial Park, Knowsley | Merseyside | North West | England |  | 343358 | 399823 | Knowsley Metropolitan Borough Council | 14/00657/FUL | [5 empty] | 2014-10-01 | [6 empty] | 2015-07-15
| 4790 | 2019-01-22 | Kingspan | Kingspan | Wind Onshore |  |  | 1.8 | n/a | 0.9 | 3.07 |  | 0.9 | 2 | 78 | n/a | Operational | Operational | Kingspan Ltd, 2-4 Bagillt Road, Greenfield, Holywell | Flintshire | Wales | Wales | CH8 7GJ | 320053 | 377640 | Flintshire County Council | 052922 | [5 empty] | 2014-11-19 | [6 empty] | 2015-04-14 |  |  |  | 2018-04-14 | 2018-03-19 | 2019-01-11
| 4791 | 2016-03-03 | JG Pears Power | Spicer Hill Wind Farm Extension | Wind Onshore |  |  | 6.9 | n/a | 0.9 | n/a |  | 2.3 | 3 | 93 | n/a | Appeal Refused | Application Refused | Land at Spicer Hill, Whitley Road, Whitley Common, Ingbirchworth, Sheffield | South Yorkshire | Yorkshire and Humber | England | S36 9PA | 420310 | 404845 | Barnsley Council | 2014/1442 | APP/R4408/W/15/3089664 |  |  |  |  | 2014-11-25 |  | 2015-02-23 | 2015-07-31 |  | 2016-02-24
| 4792 | 2016-02-22 | Lightsource Renewable Energy | Red Hill Farm | Solar Photovoltaics |  |  | 4.8 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Redhill Farm, Burlescombe, Tiverton | Devon | South West | England | EX16 7JT | 308588 | 118087 | Mid Devon District Council | 14/01984/MFUL | [5 empty] | 2014-11-25 | [6 empty] | 2015-02-13 |  |  |  | 2018-02-13 | 2015-09-22 | 2015-12-09
| 4793 | 2016-10-04 | Hive Energy | School Farm | Solar Photovoltaics |  |  | 12 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Fields South Of Black Spinney, Kilsby, Churchover, Rugby | Warwickshire | West Midlands | England |  | 452136 | 281061 | Rugby Borough Council | R13/1401 | [5 empty] | 2014-11-04 |  | 2016-09-28
| 4794 | 2017-11-02 | Green Energy UK Direct | Stoneshill Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Stoneshill Farm, Willand Road, Cullompton | Devon | South West | England |  | 302687 | 109668 | Mid Devon District Council | 14/01949/MFUL | APP/Y1138/W/15/3135271 |  |  |  |  | 2014-11-21 |  | 2015-04-28 | 2015-11-03 |  |  | 2016-02-05 | 2016-02-05 |  |  |  |  | 2016-12-17 | 2017-03-17
| 4795 | 2016-06-29 | ABO Wind NI | Carnalbanagh Wind Farm | Wind Onshore |  |  | 28.5 | n/a | 0.9 | n/a |  | 2.85 | 10 | 75 | n/a | Appeal Refused | Application Refused | 560 metres east of 87 Carnalbanagh Road to 670 metres west of 21 Carnalbanagh Road in townlands of Carnalbanagh, Kilnacolpagh and Buckna, 11 kilometres east of Broughshane | Co. Down | Northern Ireland | Northern Ireland |  | 140150 | 563786 | Northern Ireland Planning Service | G/2014/0182/F | 2014/A0168 |  |  |  |  | 2014-05-30 |  |  | 2014-11-24 |  | 2016-06-06
| 4796 | 2019-12-04 | TGC Renewables | Redmoor Farm | Solar Photovoltaics |  |  | 25.52 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Redmoor Farm, Skipwith Common Road, North Duffield, Selby | North Yorkshire | Yorkshire and Humber | England | YO8 5DE | 467529 | 438614 | Selby District Council | 2014/1150/FUL | APP/N2739/W/15/3129522 |  |  |  |  | 2014-11-18 |  | 2015-06-15 | 2015-08-13 |  |  | 2016-07-25 | 2016-07-25 |  |  |  | 2019-07-25
| 4797 | 2018-04-25 | Broadland Renewable Construction | Bruach Caorainn Hydro Scheme | Small Hydro |  |  | 1.1 | n/a | 0.7 | 10.96 |  | n/a | n/a | n/a | n/a | Operational | Operational | Bruach Caorainn, Aberfoyle, Queen Elizabeth Forest Park, Stirling | Loch Lomond and The Trossachs | Scotland | Scotland | FK8 3SX | 241957 | 700895 | Loch Lomond and The Trossachs National Park Authority | 2014/0294/DET | [5 empty] | 2014-11-25 | [6 empty] | 2015-05-14 |  |  |  | 2018-05-14 | 2016-06-15 | 2017-05-15
| 4798 | 2020-01-15 | European Energy Photovoltaics | Home Farm | Solar Photovoltaics |  |  | 13 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Home Farm, Worset Lane, Elwick, Hartlepool | Cleveland | North East | England | TS27 3BL | 445762 | 534187 | Hartlepool Borough Council | H/2014/0513 | APP/H0724/W/15/3131584 |  |  |  |  | 2014-10-31 |  | 2015-04-21 | 2015-08-26 |  |  | 2016-03-24 | 2016-03-24
| 4803 | 2016-05-30 | Lightsource Renewable Energy | Land at Havering Grove Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Havering Grove Farm, 552A Rayleigh Road, Hutton | Essex | Eastern | England | CM13 1SG | 564855 | 194830 | Brentwood Borough Council | 15/00161/FUL | APP/H1515/W/15/3134301 |  |  |  |  | 2015-02-16 |  | 2015-06-26 | 2015-10-28 |  | 2016-05-23
| 4804 | 2017-09-29 | Greencoat (formerly Renesola) | Carlam Hill Education CIC | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Carlam Hill Farm, East of Cumbrian Way, Kingston Upon Hull | Humberside | Yorkshire and Humber | England | HU7 5YX | 511000 | 436000 | Kingston upon Hull City Council | 15/00511/FULL | [5 empty] | 2015-04-23 | [6 empty] | 2015-06-12 |  |  |  | 2018-06-12 | 2016-01-18 | 2016-06-24
| 4807 | 2017-06-29 | Force 9 Energy | Cnoc an Eas Wind Farm | Wind Onshore |  |  | 44.2 | n/a | 0.9 | n/a |  | 3.4 | 13 | 136.5 | n/a | Appeal Refused | Application Refused | Land 2265m North West of Achratagan Balnain Drumnadrochit | Highland | Scotland | Scotland |  | 242650 | 832965 | Highland Council | 15/02758/FUL | PPA-270-2155 |  |  |  |  | 2015-07-15 |  | 2016-05-09 | 2016-07-06 |  | 2017-06-02
| 4809 | 2018-07-19 | Martifer Solar (Voltalia) | Stud Solar Farm | Solar Photovoltaics |  |  | 25 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Stud Farm, Ossington Road, Carlton On Trent | Nottinghamshire | East Midlands | England | NG23 6NX | 478100 | 364600 | Newark and Sherwood District Council | 15/00324/FULM | [5 empty] | 2015-02-19 | [6 empty] | 2015-06-15 |  |  |  | 2018-06-15
| 4810 | 2017-03-31 | Scottish Power Renewables | Green knowes Windfarm Ext. (resubmission) | Wind Onshore |  |  | 10 | n/a | 0.9 | n/a |  | 2 | 5 | 111 | n/a | Planning Application Withdrawn | Application Withdrawn | Greenknowes Windfarm, Glendevon, Dollar | Perth and Kinross | Scotland | Scotland | FK14 7JY | 297990 | 706550 | Perth and Kinross Council | 15/02197/FLL | [5 empty] | 2015-12-21 | 2017-03-30
| 4812 | 2015-10-30 | Private Developer | 490m north East of no 64 Backglen Road | Wind Onshore |  |  | 2 | n/a | 0.9 | 3.07 |  | 2 | 1 | 100 | n/a | Appeal Withdrawn | Application Withdrawn | 490m North East of 64 Backglen Road, Omagh | Co. Tyrone | Northern Ireland | Northern Ireland |  |  |  | Northern Ireland Planning Service | K/2014/0477/F | 2014/A0198 |  |  |  |  | 2014-10-23 |  |  | 2014-12-23 | 2015-10-01
| 4813 | 2019-11-26 | Hill Power | 690 Metres east of no 4 Vestry Road | Wind Onshore |  |  | 2 | n/a | 0.9 | 3.07 |  | 2 | 1 | 100 | n/a | Appeal Granted | Awaiting Construction | 690m East of 4 Vestry Road, Cladymore | Co. Armagh | Northern Ireland | Northern Ireland |  | 100706 | 493441 | Northern Ireland Planning Service | O/2014/0529/F | 2014/A0275 |  |  |  |  | 2014-10-23 |  |  | 2015-03-26 |  |  | 2015-11-02 | 2015-11-02 |  |  |  | 2020-11-02
| 4814 | 2016-08-17 | P & L Turbines | Tomfat | Wind Onshore |  |  | 1.6 | n/a | 0.9 | 3.07 |  | 0.8 | 2 | 79 | n/a | Planning Permission Refused | Application Refused | Land 2500m North West of Balnafoich Bridge, Farr, Inverness | Highland | Scotland | Scotland |  | 267969 | 832089 | Highland Council | 14/04452/FUL | [5 empty] | 2014-11-10 |  | 2015-06-22
| 4815 | 2016-08-17 | Primrose Solar/Camborne Energy | Wiseburrow Farm | Solar Photovoltaics |  |  | 6 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Wiseburrow Farm, Greenham, Tiverton | Devon | South West | England | TA21 0JT | 307946 | 118283 | Mid Devon District Council | 14/01932/MFUL | [5 empty] | 2014-11-28 |  | 2015-02-12
| 4817 | 2018-07-05 | Binn Eco Park | Binn Eco park Wind Farm | Wind Onshore |  |  | 10 | n/a | 0.9 | n/a |  | 2.3 | 4 | 115 | n/a | Planning Permission Expired | Planning Permission Expired | Binn Eco Park Wind Farm, Glenfarg, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 9PX | 317830 | 713430 | Perth and Kinross Council | 14/01970/FLL | [5 empty] | 2014-11-25 | [6 empty] | 2015-08-20 |  |  |  | 2018-06-19
C3412 | 4818 | 2016-05-04 | Glen Lyn Generations | Glen Lyn Gorge | Small Hydro |  |  | 1.3 | n/a | 0.7 | 10.96 |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Glen Lyn Gorge, Lynmouth, Devon | Devon | South West | England |  | 271454 | 147626 | Exmoor National Park | 62/41/14/036 | [5 empty] | 2014-09-30 | 2016-04-05
B1537 | 4819 | 2016-10-31 | Panda Green | Easter Langlee EfW (ATT) | Advanced Conversion Technologies |  |  | 2.9 | Yes | 2 | n/a |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land South Of Easter Langlee Recycling Centre, Galashiels, Scottish Borders | Borders | Scotland | Scotland |  | 352029 | 636142 | Scottish Borders Council | 13/00445/FUL | [5 empty] | 2013-04-16 | [6 empty] | 2013-09-05 |  |  |  | 2016-09-05
C3402 | 4820 | 2016-02-05 | TGC Renewables | Aller Farm (resubmission) | Solar Photovoltaics |  |  | 4.65 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Aller Farm, East of Woodford and North of Monnksilver, Williton | Somerset | South West | England | TA4 4HH | 307238 | 138547 | West Somerset District Council | 3/28/14/005 | APP/H3320/W/15/3025089 |  |  |  |  | 2014-09-24 |  | 2015-04-02 | 2015-07-07 |  | 2016-01-22
C3397 | 4824 | 2016-04-04 | Push Energy | Butlers Farm (resubmission) | Solar Photovoltaics |  |  | 7.7 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Butlers Farm, Butlers Lane, Saffron, Walden, Essex | Essex | Eastern | England | CB10 2ND | 556052 | 240692 | Uttlesford District Council | UTT/14/2755/FUL | APP/C1570/W/15/3132170 |  |  |  |  | 2014-09-19 |  | 2015-03-16 | 2015-11-04 |  | 2016-03-22
C3410 | 4825 | 2016-03-16 | Sustain Energy Solutions | Caldecote Manor Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South West Of Caldecote Manor Farm St Neots Road Abbotsley - resubmission | Cambridgeshire | Eastern | England |  | 522603 | 258420 | Huntingdonshire District Council | 1401623FUL | [5 empty] | 2014-09-17 | [6 empty] | 2015-01-07 |  |  |  | 2018-01-07 | 2015-05-14 | 2016-02-24
C3442 | 4827 | 2016-02-17 | European Energy Photovoltaics | Claydon Farm | Solar Photovoltaics |  |  | 18.2 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land To The South Of Claydon Farm, Claydon, Pamington | Gloucestershire | South West | England | GL20 7BH | 393688 | 230697 | Tewkesbury Borough Council | 14/00785/FUL | [5 empty] | 2014-09-25 | [6 empty] | 2015-02-05 |  |  |  | 2018-01-05
C3413 | 4830 | 2015-04-20 | Vogt Solar | Crundale / Fenton Home Farm (extension) | Solar Photovoltaics |  |  | 5.9 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Fenton Home Farm, Crundale, Haverfordwest | Dyfed | Wales | Wales | SA62 4PY | 198289 | 217945 | Pembrokeshire County Council | 14/0511/PA | [5 empty] | 2014-09-03 | [6 empty] | 2014-11-12 |  |  |  | 2019-11-12 | 2015-01-01 | 2015-03-31
C3395 | 4833 | 2016-07-28 | SBC Renewables | Fieldscale | Solar Photovoltaics |  |  | 10.62 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Hale Manor Farm, Hale Common, Newport, Isle of Wight | Isle of Wight | South East | England | PO30 3AR | 453412 | 86665 | Isle of Wight Council | P/00979/14 | [5 empty] | 2014-08-07 | [6 empty] | 2014-10-22 |  |  |  | 2017-10-22 | 2016-02-01 | 2016-04-15
C3406 | 4834 | 2019-11-29 | Green Switch Solutions - Liquidated | Hatherton Lodge | Solar Photovoltaics |  |  | 8.28 | n/a | 1.4 | n/a |  | n/a | n/a | n/a |  | Appeal Granted | Awaiting Construction | Agricultural Land at Hatherton Lodge Farm, Hunterson Road, Hatherton, Nantwich | Cheshire | North West | England | CW5 7RA | 369090 | 346762 | Cheshire East Council | 14/4296N | APP/R0660/W/15/3033298 |  |  |  |  | 2014-09-11 |  | 2015-03-05 | 2015-06-04 |  |  | 2016-02-12 | 2016-02-12 |  |  |  | 2019-02-12
C3423 | 4835 | 2016-03-03 | Green Switch Solutions | Hurst Hall | Solar Photovoltaics |  |  | 13.28 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Hurst Hall, Wrenbury Road, Marbury, Cheshire | Cheshire | North West | England | SY13 4LU | 357027 | 346326 | Cheshire East Council | 14/4380N | APP/R0660/W/15/3011357 |  |  |  |  | 2014-09-22 |  | 2014-12-11 | 2015-06-04 |  | 2016-02-12
B1542 | 4836 | 2016-11-24 | FH Dean Ltd | Iwade Solar Farm | Solar Photovoltaics |  |  | 1.68 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | New Kane Farm, Holywell Lane, Sittingbourne | Kent | South East | England | ME9 7HP | 584858 | 166460 | Swale Borough Council | SW/12/1019 | [5 empty] | 2013-01-17 | [6 empty] | 2013-07-11 |  |  |  | 2016-07-11 | 2014-11-15 | 2015-03-19
AA363 | 4838 | 2014-12-19 | Padero Solar | Kingsland Barton Solar Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Near South Molton, Devon | Devon | South West | England |  | 269279 | 125959 | North Devon District Council | 55742 | [5 empty] | 2013-06-13 | [6 empty] | 2013-10-29 | [5 empty] | 2014-02-22
C3430 | 4839 | 2016-10-20 | Wanageeska | Lee Moor China Clay Works | Solar Photovoltaics |  |  | 9.5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a |  | Operational | Operational | Portworthy Dams 2 and 3, Lee Moor China Clay Works, Lee Moor | Devon | South West | England | PL7 5JP | 257167 | 62751 | Devon County Council | DCC/3689/2014 | [5 empty] | 2014-08-06 | [6 empty] | 2014-10-27 |  |  |  | 2017-10-27 | 2015-08-15 | 2015-12-15
C3404 | 4840 | 2015-05-14 | Lightsource Renewable Energy | Littleton | Solar Photovoltaics |  |  | 12.14 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Blandford Forum Bypass, Blandford, St Mary, Dorset | Dorset | South West | England |  | 388332 | 105051 | North Dorset District Council | 2/2014/1066/FUL | [5 empty] | 2014-09-23 | [6 empty] | 2014-12-09 |  |  |  | 2017-12-09 | 2014-12-30 | 2015-03-23
C3438 | 4841 | 2016-02-01 | Hadstone Energy | Lount solar farm | Solar Photovoltaics |  |  | 2.8 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Site Opposite Ashby Rugby Club, Nottingham Road, Ashby, De La Zouch, Leicestershire | Leicestershire | East Midlands | England |  | 437859 | 317762 | North West Leicestershire District Council | 14/00862/FULM | [5 empty] | 2014-09-26 | [6 empty] | 2014-12-17 |  |  |  | 2017-12-17 | 2015-08-30 | 2015-11-30
C3407 | 4842 | 2016-04-04 | New Energy for the World | Lower Blakemore Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Lower Blakemore Farm, Totnes | Devon | South West | England |  | 276931 | 59621 | South Hams District Council | 23/2373/14/F | APP/K1128/W/15/3135465 |  |  |  |  | 2014-09-24 |  | 2015-06-18 | 2015-11-05 |  | 2016-03-23
C3408 | 4844 | 2017-03-22 | BWE Partnership | New Mains Of Guynd Farm | Solar Photovoltaics |  |  | 10 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Field 325M North Of New Mains Of Guynd Farm Guynd Arbroath | Tayside | Scotland | Scotland |  | 356528 | 742680 | Angus Council | 14/00526/FULL | [5 empty] | 2014-06-23 | [6 empty] | 2014-10-06 |  |  |  | 2017-10-06 | 2015-12-17 | 2016-06-15
C3437 | 4846 | 2016-03-16 | Omega Solar / OPDE | Orchard Farm | Solar Photovoltaics |  |  | 10 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | W/O Orchard Farm, School Lane, Iwade, Sittingbourne, Kent | Kent | South East | England | ME9 8QG | 587958 | 166869 | Swale Borough Council | 14/502072/FULL | [5 empty] | 2014-08-07 | [6 empty] | 2014-10-22 |  |  |  | 2017-10-22 | 2015-10-05 | 2016-02-02
C3452 | 4849 | 2015-12-16 | Renewable Energy Systems (RES) | Rufford Solar Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Rufford Colliery Lane, Rainworth, Mansfield | Nottinghamshire | East Midlands | England |  | 459863 | 359392 | Newark and Sherwood District Council | 15/01008/FULM | [5 empty] | 2015-09-16 |  | 2015-12-10
C3400 | 4850 | 2016-06-15 | AR Partners | Salford Lodge | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a |  | Operational | Operational | Salford Lodge Pitchill Evesham | Warwickshire | West Midlands | England | WR11 8SN | 404789 | 250939 | Stratford on Avon District Council | 14/02463/FUL | [5 empty] | 2014-09-11 | [6 empty] | 2014-12-11 |  |  |  | 2017-12-11 | 2015-06-01 | 2015-08-01
C3415 | 4856 | 2017-01-30 | Elgin Energy EsCo | The Grange | Solar Photovoltaics |  |  | 8 | n/a | 1.4 | n/a |  | n/a | n/a | n/a |  | Operational | Operational | The Grange, Wick Lane, West Hewish, Banwell | Avon | South West | England | BS24 6RR | 339100 | 164030 | North Somerset Council | 14/P/1938/F | [5 empty] | 2014-09-08 | [6 empty] | 2015-02-03 |  |  |  | 2018-01-03 | 2015-12-02 | 2016-03-30
C3411 | 4857 | 2015-12-15 | Conergy | Thorne Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Thorne Colliery, Grange Road, Moorends, Doncaster | South Yorkshire | Yorkshire and Humber | England | DN8 4NA | 470602 | 416004 | Doncaster Metropolitan Borough Council | 14/01554/FULM | [5 empty] | 2014-09-12 | [6 empty] | 2015-04-16 |  |  |  | 2018-04-16 | 2015-06-01 | 2015-12-18
C3398 | 4858 | 2016-05-10 | Vogt Solar | Tiddiecross Solar Farm | Solar Photovoltaics |  |  | 10.5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent to Tiddiecross, Charlton, Telford | Shropshire | West Midlands | England | TF6 5EY | 361262 | 311911 | Telford and Wrekin Council | TWC/2014/0810 | [5 empty] | 2014-09-10 | [6 empty] | 2015-01-07 |  |  |  | 2018-01-07 | 2015-01-08 | 2015-03-31
C3403 | 4859 | 2016-01-05 | Lightsource Renewable Energy | Tooleys Farm | Solar Photovoltaics |  |  | 5.32 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Site At Tooleys Farm, Brookend Road, Stebbing, Dunmow, Essex | Essex | Eastern | England | CM6 3AA | 564888 | 223424 | Uttlesford District Council | UTT/14/2739/FUL | [5 empty] | 2014-09-16 | [6 empty] | 2014-12-16 |  |  |  | 2017-12-16 | 2015-07-20 | 2015-10-08
C3401 | 4860 | 2015-08-11 | Anesco | Trickey Warren | Solar Photovoltaics |  |  | 4.75 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a |  | Operational | Operational | N/O Trickey Warren Lane, Churchstanton, Taunton, Somerset | Somerset | South West | England | TA3 | 320109 | 114779 | Taunton Deane Borough Council | 10/14/0031 | [5 empty] | 2014-09-01 | [6 empty] | 2014-11-25 |  |  |  | 2017-11-25 | 2015-01-31 | 2015-04-15
C3399 | 4861 | 2016-02-01 | Sunsave 27 (Twemlows)/ Vogt solar | Twemlows | Solar Photovoltaics |  |  | 10 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land On Runway At Twemlows Hall, Higher Heath, Whitchurch, Shropshire | Shropshire | West Midlands | England |  | 356843 | 338029 | Shropshire Council | 14/03957/FUL | [5 empty] | 2014-09-08 | [6 empty] | 2015-02-20 |  |  |  | 2018-02-20 | 2015-08-15 | 2015-11-15
C3396 | 4862 | 2015-12-22 | Lightsource Renewable Energy | Tyddyn Cae (Nefyn) | Solar Photovoltaics |  |  | 4.9 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Tyddyn Cae, Boduan, Pwllheli | Gwynedd | Wales | Wales | LL53 6DS | 233416 | 338035 | Gwynedd Council | C14/0885/33/LL | [5 empty] | 2014-09-08 | [6 empty] | 2015-02-02 |  |  |  | 2020-02-02 | 2015-07-27 | 2015-12-15
B1534 | 4866 | 2017-04-27 | Energiekontor UK | Fulbeck Airfield Wind Farm | Wind Onshore |  |  | 25 | n/a | 0.9 | n/a |  | 2.5 | 10 | 110 | n/a | Planning Permission Refused | Application Refused | Fulbeck Airfield, Fulbeck | Lincolnshire | East Midlands | England | NG32 3JE | 489748 | 350976 | South Kesteven District Council | S15/1764 | [5 empty] | 2015-08-19 |  | 2017-03-31
B1530 | 4873 | 2016-01-06 | Airvolution Energy | West Scales Wind Farm | Wind Onshore |  |  | 16.5 | n/a | 0.9 | n/a |  | 3.3 | 5 | 131 | n/a | Planning Application Withdrawn | Application Withdrawn | West Scales Farm, 1.5km north east of Eastriggs, between Annan and Gretna | Dumfries and Galloway | Scotland | Scotland | DG16 5JH | 326710 | 567763 | Dumfries and Galloway Council | 14/P/4/0538 | [5 empty] | 2014-12-24 | 2015-11-16
B1370 | 4874 | 2015-05-13 | British Solar Renewables | Abbots Ann | Solar Photovoltaics |  |  | 7 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Dipden Bottom Lane, Goodworth, Clatford, Hampshire | Hampshire | South East | England |  | 434200 | 140600 | Test Valley Borough Council | 14/02110/FULLN | [5 empty] | 2014-09-04 | [6 empty] | 2015-01-23 |  |  |  | 2018-01-23 | 2015-02-01 | 2015-03-30
| 4875 | 2017-02-28 | Kronos Solar | Land at Woodhall Farm | Solar Photovoltaics |  |  | 45 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Woodhall Farm, Wichenford, Worcester | Hereford and Worcester | West Midlands | England | WR6 6YE | 378242 | 258004 | Malvern Hills District Council | 14/01658/FUL | APP/J1860/W/16/3142020 |  |  |  |  | 2014-12-10 |  | 2015-08-12 | 2016-02-17 |  | 2017-02-23
C3448 | 4876 | 2020-03-16 | Zebec Energy | Bonby Lane (resubmission) | Anaerobic Digestion |  |  | 1.5 | Yes | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Bonby, North Lincolnshire | Humberside | Yorkshire and Humber | England | DN20 0QN | 501535 | 416439 | North Lincolnshire Council | WD/2014/0908 | APP/Y2003/W/15/3006726 |  |  |  |  | 2014-10-06 |  | 2015-02-11 | 2015-05-07 |  |  | 2015-11-18 | 2015-11-18
C3445 | 4877 | 2017-02-16 | British Sugar | British Sugar - Bury | Anaerobic Digestion |  |  | 5 | Yes | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Operational | Operational | Hollow Road, Bury, St Edmunds, Suffolk | Suffolk | Eastern | England | IP32 7BB | 586229 | 265294 | St Edmundsbury Borough Council | DC/14/1840/FUL | [5 empty] | 2014-10-09 | [6 empty] | 2014-12-11 |  |  |  | 2017-12-11 | 2015-08-15 | 2016-09-15
C3441 | 4878 | 2016-04-26 | Lanhydrock Estate Company | Margate Solar Farm | Solar Photovoltaics |  |  | 3 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Higher Margate, Bodmin, Cornwall | Cornwall | South West | England | PL31 1HE | 208657 | 66512 | Cornwall Council | PA14/08958 | [5 empty] | 2014-10-09 | [6 empty] | 2014-12-22 |  |  |  | 2017-12-22 | 2015-03-17 | 2015-09-01
C3454 | 4879 | 2018-08-29 | Solar Choice | Belle Eau Park | Solar Photovoltaics |  |  | 1.9 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Yearsley Group, Belle Eau Park, Bilsthorpe, Newark | Nottinghamshire | East Midlands | England | NG22 8TX | 466202 | 359338 | Newark and Sherwood District Council | 14/01782/FULM | [5 empty] | 2014-10-07 | [6 empty] | 2015-01-13 |  |  |  | 2018-01-13
B1394 | 4880 | 2016-07-14 | Conergy | Laceby Solar Farm | Solar Photovoltaics |  |  | 27.14 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Manor Top Farm Manor Top Farm Access Road To Laceby | Humberside | Yorkshire and Humber | England | DN37 7EA | 522997 | 404760 | North East Lincolnshire Council | DM/0174/15/FUL | [5 empty] | 2015-03-05 | [6 empty] | 2015-06-19 |  |  |  | 2018-06-19 | 2016-04-15 | 2016-06-22
| 4881 | 2018-10-03 | RWE | Dolgarrog | Large Hydro |  |  | 32 | n/a | 0.7 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Dolgarrog, Conwy | Conwy | Wales | Wales | LL32 8QE | 276988 | 367594 | Snowdonia National Park Authority | [19 empty] | 1938-01-01
| 4882 | 2014-12-19 | RWE | Cwm Dyli | Large Hydro |  |  | 9.9 | n/a | 0.7 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Nant Gwynant, Beddgelert | Gwynedd | Wales | Wales | LL55 4NW |  |  | Snowdonia National Park Authority | [19 empty] | 1906-01-01
| 4883 | 2014-12-19 | RWE | Kielder | Large Hydro |  |  | 6.1 | n/a | 0.7 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Kielder Water, Hexham | Northumberland | North East | England | NE48 1ND |  |  | Northumberland National Park Authority | [19 empty] | 1982-06-01
| 4884 | 2017-12-18 | Lightsource Renewable Energy | Finvoy Road | Solar Photovoltaics |  |  | 5.88 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands to the West of 289 Finvoy Road, Rasharkin, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland | BT44 8SD | 112523 | 572478 | Northern Ireland Planning Service | D/2014/0234/F | [5 empty] | 2014-12-04 | [6 empty] | 2015-08-10 |  |  |  | 2020-08-10 | 2017-05-17 | 2017-12-15
| 4885 | 2016-08-31 | Island Green Power | Land East of White Horse Lane | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of White Horse Lane, Norwich | Norfolk | Eastern | England |  | 623981 | 305949 | South Norfolk Council | 2014/2380 | [5 empty] | 2014-12-09 | [6 empty] | 2015-08-11 |  |  |  | 2018-08-11 | 2015-12-16 | 2016-03-30
| 4886 | 2016-11-30 | Be Renewables | The Place Solar Farm | Solar Photovoltaics |  |  | 23.2 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | The Gateway Academy, Marshfoot Road, Grays | Essex | Eastern | England | RM16 4LU | 564236 | 177845 | Thurrock Council | 14/01278/FUL | [5 empty] | 2014-12-09 |  | 2016-11-25
| 4887 | 2016-02-01 | Hive Energy/ Vogt Solar | Westfield Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Westfield Farm, Catterall | Lancashire | North West | England | PR3 0PU | 349769 | 442088 | Wyre Borough Council | 14/00909/LMAJ | [5 empty] | 2014-11-12 | [6 empty] | 2015-05-06 |  |  |  |  | 2015-11-01 | 2016-01-15
| 4888 | 2015-03-23 | Green Switch Developments | Land off the A5199, Brampton Valley Way | Solar Photovoltaics |  |  | 4.2 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Brampton Valley Way, Wellford Road, Kingthorpe | Northamptonshire | East Midlands | England | NN6 8AB | 473525 | 265114 | Daventry District Council | DA/2014/1026 | [5 empty] | 2014-11-19 |  | 2015-03-13
| 4889 | 2016-04-22 | Sunsave 24/ Vogt solar | West Woodlands | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Court Farm, West Woodlands, Frome | Somerset | South West | England | BA11 5EN | 377846 | 144006 | Mendip District Council | 2014/2326/FUL | APP/Q3305/W/15/3006749 |  |  |  |  | 2014-11-20 |  | 2015-02-24 | 2015-04-01 |  |  | 2015-08-24 | 2015-08-24 |  |  |  | 2018-08-24 | 2015-11-25 | 2016-03-23
| 4890 | 2015-02-09 | Cranham Golf Course | Cranham Golf Course (resubmission) | Solar Photovoltaics |  |  | 2.642 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Cranham Golf Course, St. Marys Lane, Upminster | Greater London | London | England | RM14 3NU | 558338 | 186896 | Havering London Borough Council | P1609.14 | [5 empty] | 2014-11-18 |  | 2015-01-29
| 4891 | 2017-07-21 | REG Solarpower | Mendennick Farm (resubmission) | Solar Photovoltaics |  |  | 2.8 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Mendennick Hill, Mendennick | Cornwall | South West | England | PL11 3AU | 240703 | 52965 | Cornwall Council | PA14/11090 | [5 empty] | 2014-11-25 | [6 empty] | 2015-02-13 |  |  |  | 2018-02-13 | 2015-04-15 | 2015-10-15
| 4892 | 2017-03-27 | Farm Energy Consulting | Gawnsmoss Cluster | Wind Onshore |  |  | 2.4 | n/a | 0.9 | 3.07 |  | 0.8 | 3 | 79 | n/a | Operational | Operational | Site at Cairnhill Banff | Aberdeen | Scotland | Scotland | AB45 3BS | 363483 | 859316 | Aberdeenshire Council | APP/2012/2406 | PPA-110-2248 |  |  |  |  | 2012-10-10 |  | 2014-10-02 | 2014-12-02 |  |  | 2015-03-11 | 2015-03-11 |  |  |  | 2018-03-11 | 2016-10-15 | 2017-03-27
| 4893 | 2020-03-11 | Muirhall Energy (formerly Infinis) | Melin Court | Wind Onshore |  |  | 18 | n/a | 0.9 | n/a |  | 3 | 5 |  | n/a | Planning Permission Granted | Awaiting Construction | Land to the East of Merlin Court, Resolven | Neath Port Talbot | Wales | Wales |  | 284900 | 200600 | Neath Port Talbot County Borough Council | P2014/0883 | [5 empty] | 2014-10-15 | [6 empty] | 2016-08-26
| 4894 | 2016-01-06 | Stewart Energy Ltd | Halls Burn | Wind Onshore |  |  | 2.5 | n/a | 0.9 | 3.07 |  | 2 | 1 |  | n/a | Planning Application Withdrawn | Application Withdrawn | Halls Burn, Strathaven | South Lanarkshire | Scotland | Scotland | ML10 6RF | 226452 | 636804 | South Lanarkshire Council | EK/14/0360 | [5 empty] | 2014-12-03 | 2015-04-22
| 4895 | 2016-10-04 | Solstice Renewables | Orchard Park (resubmission) | Solar Photovoltaics |  |  | 5.06 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Shepherds farm, Oil Mill Lane, Clyst St Mary | Devon | South West | England | EX5 1 AG | 298824 | 90072 | East Devon District Council | 14/2952/MFUL | APP/U1105/W/16/3144419 |  |  |  |  | 2014-12-15 |  | 2015-12-04 | 2016-03-16 |  | 2016-09-21
| 4896 | 2017-10-04 | Renewable Developments Wales | Cockett Valley | Solar Photovoltaics |  |  | 4 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Cockett Valley, Waunarlywydd Road, Swansea | Swansea | Wales | Wales | SA5 4RQ | 260794 | 195054 | City and County Council of Swansea | 2014/1837 | [5 empty] | 2014-12-05 | [6 empty] | 2015-08-18 |  |  |  | 2020-08-18 | 2017-01-26 | 2017-03-29
| 4897 | 2017-05-03 | British Solar Renewables | Rampisham North | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Rampisham, Dorchester | Dorset | South West | England | DT2 0HS | 355089 | 101344 | West Dorset District Council | WD/D/14/002974 | [5 empty] | 2014-11-19 | [6 empty] | 2016-12-22 |  |  |  | 2019-12-22 | 2017-01-20 | 2017-03-01
| 4899 | 2016-02-15 | Bristol City Council | Severn Road Solar Park | Solar Photovoltaics |  |  | 1.836 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Severn Road, Avonmouth | Avon | South West | England | BS11 0YL | 353695 | 181718 | Bristol City Council | 14/05915/FB | [5 empty] | 2014-12-11 | [6 empty] | 2015-05-14 |  |  |  | 2018-05-14 | 2016-01-05 | 2016-02-05
| 4900 | 2016-05-04 | MTS Exbury Solar | Exbury Solar Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land off Lepe Road, Exbury, Hampshire | Hampshire | South East | England | SO45 1AJ | 444079 | 99352 | New Forest National Park Authority | 14/01004 | APP/B9506/W/15/3132171 |  |  |  |  | 2014-12-11 |  | 2015-02-17 | 2015-10-07 |  | 2016-04-07
| 4901 | 2016-03-03 | Ecotricity / Next Generation | Shilton Downs Solar Park | Solar Photovoltaics |  |  | 10.8 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Shilton Downs Farm, Ladburn Lane, Shilton, Glouctershire | Oxfordshire | South East | England | OX18 4AL | 425747 | 208983 | West Oxfordshire District Council | 14/02156/FUL | APP/D3125/W/15/3133492 |  |  |  |  | 2014-12-06 |  | 2015-03-23 | 2015-09-23 |  | 2016-02-02
| 4902 | 2019-11-21 | TCI Renewables | Ballyutoag Wind Farm | Wind Onshore |  |  | 11.5 | n/a | 0.9 | n/a |  | 2.3 | 5 | 92.5 | n/a | Planning Permission Granted | Awaiting Construction | Land approximately 1km north of No. 71 Ballyutoag Road, Belfast, Co. Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT14 8SS | 140369 | 535388 | Northern Ireland Planning Service | T/2014/0478/F | [5 empty] | 2014-12-08 | [6 empty] | 2015-12-23 |  |  |  | 2020-12-21
| 4903 | 2017-02-27 | Solar Park Developments | Moorhouse Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Moor House Farm, Winscales, Workington | Cumbria | North West | England | CA14 4JZ | 301291 | 525388 | Allerdale Borough Council | 2/2014/0899 | APP/G0908/W/15/3130516 |  |  |  |  | 2014-12-17 |  | 2015-05-06 | 2015-08-05 |  |  | 2016-03-21 | 2016-03-21 |  |  |  |  | 2016-08-30 | 2016-11-30
| 4904 | 2015-07-01 | JFS Biogas | Church Farm AD | Anaerobic Digestion |  |  | 1 | No | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land at Church Farm, Kilburn, North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 450704 | 479574 | Hambleton District Council | 14/02534/FUL | [5 empty] | 2014-12-15 |  | 2015-06-30
| 4905 | 2015-08-05 | Lantanier UK | Bagletts Wind Farm | Wind Onshore |  |  | 6.9 | n/a | 0.9 | n/a |  | 2.3 | 3 | 121 | n/a | Planning Application Withdrawn | Application Withdrawn | Land off Ings Lane, Ellerker, East Yorkshire | Humberside | Yorkshire and Humber | England |  | 490700 | 428925 | East Riding of Yorkshire Council | 14/03106/STPLFE | [5 empty] | 2014-12-08 | 2015-07-15
| 4906 | 2017-11-02 | Olleco and Arla Foods | Arla Dairy Site | Anaerobic Digestion |  |  | 5 | Yes | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Operational | Operational | Land at College Road North, Aston Clinton, Buckinghamshire | Buckinghamshire | South East | England | HP22 5EZ | 487065 | 214308 | Buckinghamshire County Council | CM/78/14 | [5 empty] | 2014-12-11 | [6 empty] | 2015-07-15 |  |  |  | 2020-07-15 | 2015-10-15 | 2017-08-01
| 4907 | 2020-03-23 | Clay Cross Biomass | Clay Cross ERF | Advanced Conversion Technologies |  |  | 12 | Yes | 1 | n/a |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land off Bridge Street, Clay Cross | Derbyshire | East Midlands | England | S45 9NY | 439493 | 364077 | Derbyshire County Council | CW4/1114/98 | [5 empty] | 2014-12-10 | [6 empty] | 2017-03-29 |  |  |  | 2020-03-29
| 4908 | 2015-01-05 | AWE Renewables | Quarrendon Fields | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 1.5 | 1 | 143.5 | n/a | Operational | Operational | Quarrendon Fields, Aylesbury | Buckinghamshire | South East | England | HP18 0PT | 480288 | 216618 | Aylesbury Vale District Council | 10/00136/APP | APP/J0405/A/11/2155043 |  |  |  |  | 2010-02-15 |  |  | 2011-07-11 |  |  | 2012-03-19 | 2012-03-19 | [5 empty] | 2014-12-18
| 4909 | 2015-01-05 | Dwr Cymru Welsh Water | Llyn Celyn | Small Hydro |  |  | 4.507 | n/a | 0.7 | 2.99 |  | n/a | n/a | n/a | n/a | Operational | Operational | Celyn Reservoir near Bala | Gwynedd | Wales | Wales | LL23 7NU | 287800 | 339800 | Gwynedd Council | [19 empty] | 1994-01-01
| 4910 | 2015-01-05 | Dwr Cymru Welsh Water | Caban Coch | Small Hydro |  |  | 1.05 | n/a | 0.7 | 10.96 |  | n/a | n/a | n/a | n/a | Operational | Operational | Elan & Claerwen Rivers, Rhayader | Powys | Wales | Wales | LD6 5HL |  |  | Powys County Council | [19 empty] | 1997-05-01
| 4911 | 2020-03-11 | Muirhall Energy (formerly Infinis) | Drumelzie | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 1.5 | 1 | 126.5 | n/a | Planning Permission Granted | Awaiting Construction | Drumelzie, Blackridge | West Lothian | Scotland | Scotland | EH48 3AW | 288864 | 669037 | West Lothian Council | LIVE/0154/FUL/15 | [5 empty] | 2015-03-09 | [6 empty] | 2016-12-02 |  |  |  | 2019-12-02
| 4916 | 2016-06-21 | Elgin Energy EsCo | Land at Sutor Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Sutor Farm, Wincanton | Somerset | South West | England | BA9 9RA | 372634 | 126331 | South Somerset District Council | 14/05472/FUL | [5 empty] | 2014-10-16 | [6 empty] | 2015-03-19 |  |  |  | 2018-03-19 | 2016-01-20 | 2016-03-31
| 4917 | 2017-04-18 | Redpath Energy | Newstead and Annesley Wind Turbine | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 1.5 | 1 | 126 | n/a | Operational | Operational | Newstead and Annesley Country Park, Tilford Road, Newstead | Nottinghamshire | East Midlands | England | NG15 0BT | 452500 | 353400 | Gedling Borough Council | 2014/1168 | [5 empty] | 2014-10-04 | [6 empty] | 2015-10-20 |  |  |  | 2018-10-20 | 2016-08-01 | 2016-12-01
| 4918 | 2015-01-06 | ClearWinds | East Redhill Farms | Wind Onshore |  |  | 1.5 | n/a | 0.9 | 7.24 |  | 0.5 | 3 | 50 | n/a | Planning Application Withdrawn | Application Withdrawn | Land southeast of East Redhill, Rothienorman, Inverurie | Aberdeen | Scotland | Scotland |  | 368253 | 836288 | Aberdeenshire Council | APP/2014/4259 | [5 empty] | 2014-12-15 | 2015-01-05
| 4919 | 2016-09-22 | JFS Biogas | Gravel Pit Farm (Resubmission) | Anaerobic Digestion |  |  | 1 | Yes | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Operational | Operational | Gravel Pit Farm, Sand, Hutton, York | North Yorkshire | Yorkshire and Humber | England | YO41 1LN | 468377 | 458725 | Ryedale District Council | 14/01073/MFUL | [5 empty] | 2014-09-30 | [6 empty] | 2015-02-17 |  |  |  | 2018-02-17 | 2015-07-15 | 2016-01-15
| 4920 | 2015-10-30 | Private Developer |  | Wind Onshore |  |  | 2 | n/a | 0.9 | 3.07 |  | 2 | 1 | 100 | n/a | Appeal Withdrawn | Application Withdrawn | 775mts N/North East of no 64 Backglen Road, Omagh | Co. Tyrone | Northern Ireland | Northern Ireland |  | 63013 | 540306 | Northern Ireland Planning Service | K/2014/0440/F | 2014/A0197 |  |  |  |  | 2014-09-29 |  |  | 2014-12-23 | 2015-10-01
| 4922 | 2018-08-30 | Seneca Global Energy | Brenda Road Wind Turbine | Wind Onshore |  |  | 7.54 | n/a | 1.4 | n/a |  | 7.5 | 1 | 206.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Brenda Road, Hartlepool | Cleveland | North East | England |  | 451030 | 528464 | Hartlepool Borough Council | H/2014/0253 | APP/H0724/V/15/3136465 | APP/H0724/V/15/3136465 |  |  |  | 2014-06-20 | 2018-08-30
| 4923 | 2019-10-31 | North London Waste Authority (NLWA) | North London Heat and Power (Edmonton EcoPark Replacement) | EfW Incineration |  |  | 70 | Yes | 1 | n/a |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | London Waste EcoPark, Edmonton | London | London | England | N18 3AF |  |  | The Planning Inspectorate - National Infrastructure | EN010071 | [5 empty] | 2015-11-11 | [6 empty] | 2017-02-24
| 4924 | 2015-01-08 | Londonwaste | Edmonton EcoPark EfW | EfW Incineration |  |  | 55 | Yes | 1 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | London Waste EcoPark, Edmonton | London | London | England |  | 535767 | 192649 | The Planning Inspectorate - National Infrastructure | [19 empty] | 1974-01-01
| 4925 | 2015-01-08 | SITA UK | Teesside EfW | EfW Incineration |  |  | 19.2 | No | n/a | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Haverton Hill Road, Billingham | County Durham | North East | England | TS23 1PY | 448016 | 522664 | Stockton on Tees Borough Council | [19 empty] | 1998-01-01
| 4926 | 2015-01-08 | SITA UK | Teesside EfW (extension) | EfW Incineration |  |  | 10 | No | n/a | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Haverton Hill Road, Billingham | County Durham | North East | England | TS23 1PY | 448016 | 522664 | Stockton on Tees Borough Council | [19 empty] | 2009-01-01
| 4927 | 2017-09-27 | Suez (formerly SITA) | Bristol Resource Recovery Park | Advanced Conversion Technologies |  |  | 7.5 | No | 2 |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Plot M2, Merebank Estate, Kings Weston Lane, Avonmouth, Bristol | Avon | South West | England | BS11 9FG | 352547 | 179879 | Bristol City Council | 11/01773/F | [5 empty] | 2011-05-09 | [6 empty] | 2012-03-09 |  |  |  | 2015-03-09
| 4928 | 2015-01-08 | Veolia (SELCHP) | SELCHP ERF | EfW Incineration |  |  | 35 | Yes | 1 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Landmann Way, New Cross, Lewisham | London | London | England | SE14 5RS | 535817 | 177991 | [20 empty] | 1993-12-01
| 4929 | 2015-12-15 | Clean Earth Energy | Land North East Of Penrose Far | Solar Photovoltaics |  |  | 1.5 | n/a | 0 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North East Of Penrose Far, Penhale, Summercourt, Newquay | Cornwall | South West | England | TR8 5EE | 189849 | 57162 | Cornwall Council | PA14/12025 | [5 empty] | 2015-01-19 | [6 empty] | 2015-05-15 |  |  |  | 2018-05-15 |  | 2015-09-25
| 4931 | 2017-02-16 | BNRG (sold to another developer) | Land At Ferry Farm | Solar Photovoltaics |  |  | 10 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Ferry Farm, Chichester Road, Selsey, Chichester, West Sussex | West Sussex | South East | England | PO20 9ED | 485830 | 96047 | Chichester District Council | 14/03944/FULEIA | [5 empty] | 2014-12-10 | [6 empty] | 2015-04-07 |  |  |  | 2018-04-07 | 2015-11-01 | 2015-12-15
| 4933 | 2016-03-15 | Anesco | Land at Brookbarn Farm | Solar Photovoltaics |  |  | 3 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Brookbarn Farm, Courtwick Lane, Wick, Littlehampton, West Sussex | West Sussex | South East | England | BN17 7LD | 502595 | 103242 | Arun District Council | LU/385/14/PL | [5 empty] | 2015-01-16 | [6 empty] | 2015-04-23 |  |  |  |  | 2015-08-15 | 2015-10-15
| 4934 | 2015-05-28 | Earthworm | Land North East Of Heath Farm | Solar Photovoltaics |  |  | 2.8 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Heath Farm, Newbold Road, Osbaston, Nuneaton, Warwickshire | Leicestershire | East Midlands | England | CV13 0DS | 443427 | 304430 | Hinckley and Bosworth Borough Council | 15/00013/FUL | [5 empty] | 2015-01-13 | 2015-03-24
| 4935 | 2015-12-22 | Lightsource Renewable Energy | Field at School Aycliffe Lane | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | School Aycliffe Lane, School Aycliffe, Newton Aycliffe, County Durham | County Durham | North East | England | DL5 6QE | 426142 | 523694 | Darlington Borough Council | 14/01305/FUL | [5 empty] | 2015-01-09 | [6 empty] | 2015-06-30 |  |  |  | 2018-06-30 | 2015-10-23 | 2015-12-16
| 4936 | 2016-06-20 | West Coast Energy | Capel Grange Solar Park | Solar Photovoltaics |  |  | 6.6 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | OS Plot 8200, Badsell Road, Five Oak Green, Tonbridge | Kent | South East | England |  | 565032 | 144747 | Tunbridge Wells Borough Council | 14/506168/FULL | [5 empty] | 2014-12-12 | [6 empty] | 2015-04-10 |  |  |  |  | 2015-11-01 | 2016-03-31
| 4937 | 2020-03-11 | Muirhall Energy (formerly Infinis) | A'Chruach (Phase 2) | Wind Onshore |  |  | 4 | n/a | 0.9 | n/a |  | 2 | 2 | 135 | n/a | Planning Permission Granted | Awaiting Construction | Land 1.5km north of Blackmill Loch adjacent to consented A'Chruach Windfarm, West Of Minard | Argyll and Bute | Scotland | Scotland |  | 194350 | 697350 | Argyll and Bute Council | 14/02829/PP | [5 empty] | 2014-12-12 | [6 empty] | 2015-08-28 |  |  |  | 2018-08-28
| 4938 | 2015-01-19 | Kinetica Solar | Pentre farm | Solar Photovoltaics |  |  | 5.5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Pentre Farm, Llannon, Llanelli | Carmarthenshire | Wales | Wales | SA14 6AP | 253611 | 208800 | Carmarthenshire County Council | S/27526 | [5 empty] | 2012-12-18 | [6 empty] | 2013-03-11 | [5 empty] | 2014-09-25
| 4939 | 2016-07-28 | TGC Renewables | Land At Rymes Farm (Phase 1) | Solar Photovoltaics |  |  | 6.88 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Rymes Farm, Malswick, Newent, Gloucestershire | Gloucestershire | South West | England | GL18 1HF | 374545 | 224494 | Forest of Dean District Council | P1977/14/FUL | [5 empty] | 2014-12-23 | [6 empty] | 2015-06-12 |  |  |  | 2018-06-12 | 2016-01-05 | 2016-03-31
| 4940 | 2020-05-26 | Llancadle Solar Farm Ltd | Llancadle Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Llancadle Farm, Llancadle, Barry, South Glamorgan | Vale of Glamorgan | Wales | Wales | CF62 3AQ | 303679 | 168416 | Vale of Glamorgan Council | 2014/01490/FUL | [5 empty] | 2014-12-07 | [6 empty] | 2015-05-15 |  |  |  | 2020-05-15 | 2015-09-15 | 2015-12-15
| 4942 | 2020-03-31 | Turley Associates | Proposed Himley Village NW Bic | Solar Photovoltaics |  |  | 6.871 | n/a | 1.6 |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Proposed Himley Village NW Bic, Middleton Stoney Road, Bicester, Oxfordshire | Oxfordshire | South East | England | OX25 3TH | 456979 | 224554 | Cherwell District Council | 14/02121/OUT | [5 empty] | 2014-12-31 | [6 empty] | 2020-01-30 |  |  |  | 2023-01-30
| 4943 | 2016-09-20 | Solar Century (TGC Renewables) | Land At Rymes Farm (Phase 2)/Grange Solar Farm | Solar Photovoltaics |  |  | 6.78 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Rymes Farm, Malswick, Newent, Gloucestershire | Gloucestershire | South West | England | GL18 1HF | 374394 | 224673 | Forest of Dean District Council | P1976/14/FUL | [5 empty] | 2014-12-23 | [6 empty] | 2015-06-12 |  |  |  | 2018-06-12 | 2015-08-15 | 2015-11-15
| 4947 | 2018-11-27 | Coriolis Energy | Land East Of Shieldhill Farm | Wind Onshore |  |  | 18 | n/a | 0.9 | n/a |  | 3 | 6 | 115 | n/a | Appeal Refused | Application Refused | Land East Of Shieldhill Farm, Moor Road, Newton Mearns, Glasgow, Strathclyde | East Renfrewshire | Scotland | Scotland | G77 6SQ | 252010 | 649306 | East Renfrewshire Council | 2014/0820/TP | PPA-220-2048 |  |  |  |  | 2015-01-08 |  | 2018-03-14 | 2018-06-13 |  | 2018-10-25
| 4948 | 2016-04-28 | Low Carbon | Trowle Common | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Trowle Common, Trowbridge, Wiltshire | Wiltshire | South West | England | BA14 9B | 383857 | 158625 | Wiltshire Council | 14/11649/FUL | [5 empty] | 2015-01-06 | [6 empty] | 2015-06-15 |  |  |  | 2018-06-15 | 2015-10-01 | 2016-02-02
| 4950 | 2019-10-17 | Archiception | Shire-End Farm | Solar Photovoltaics |  |  | 17 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Shire-End Farm, Forgandenny, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 9DR | 309606 | 709502 | Perth and Kinross Council | 14/02077/FLL | [5 empty] | 2014-12-11 | [6 empty] | 2016-02-18 |  |  |  | 2019-02-18
| 4951 | 2017-08-14 | Countryside Renewables | Canopus Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Associates With Canopus F, Frith Bank, Boston, Lincolnshire | Lincolnshire | East Midlands | England | PE22 7BD | 530597 | 347613 | East Lindsey District Council | S/054/02433/14 | [5 empty] | 2015-01-05 | [6 empty] | 2015-03-26 |  |  |  | 2018-03-26 | 2015-08-26 | 2015-12-10
| 4952 | 2016-02-16 | Conergy West Sussex | Land At Guston Court Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Guston Court Farm, Han, Guston, East Langdon Road, Dover, Kent | Kent | South East | England | CT15 5EX | 632877 | 144096 | Dover District Council | 14/01133 | [5 empty] | 2014-12-16 | [6 empty] | 2015-03-19 |  |  |  | 2018-03-19 | 2015-11-12 | 2015-12-20
| 4953 | 2019-11-26 | Hill Power | 320mts South East of 43 Flush Road | Wind Onshore |  |  | 2 | n/a | 0.9 | 3.07 |  | 2 | 1 | 100 | n/a | Appeal Granted | Awaiting Construction | 320mts South East of, 43 Flush Road, Ballysillan, Belfast, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT14 8SJ | 142189 | 534705 | Northern Ireland Planning Service | Z/2014/1553/F | 2014/A0277 |  |  |  |  | 2014-11-20 |  |  | 2015-03-26 |  |  | 2015-11-04 | 2015-11-04
| 4954 | 2018-04-30 | Lightsource Renewable Energy | Former Maghaberry Airfield | Solar Photovoltaics |  |  | 25.7 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Maghaberry Airfield, Antrim, Craigavon, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT67 0JF | 129097 | 520344 | Northern Ireland Planning Service | S/2014/0913/F | [5 empty] | 2015-01-14 | [6 empty] | 2016-04-26 |  |  |  | 2021-04-25 | 2017-09-21 | 2018-01-30
| 4955 | 2018-09-25 | Solstice Renewables | Kenniford Farm | Solar Photovoltaics |  |  | 4 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Kenniford Farm, Clyst St Mary, Exeter | Devon | South West | England | EX5 1AQ | 299011 | 89265 | East Devon District Council | 15/0123/MFUL | [5 empty] | 2015-01-20 | [6 empty] | 2015-10-27 |  |  |  | 2018-10-27
| 4956 | 2020-04-24 | Lark Energy | Land at Wittering Ford Road | Solar Photovoltaics |  | 7631 | 3.9 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land to the South of Wittering Ford Road, Barnack, Stamford | Cambridgeshire | Eastern | England | PE9 3HX | 506193 | 302988 | Peterborough City Council | 14/02183/FUL | [5 empty] | 2015-01-02 | [6 empty] | 2016-01-29 |  |  |  | 2019-01-29
| 4957 | 2020-05-26 | Gaelectric Developments | Ballyhanedin Wind Farm | Wind Onshore |  |  | 24 | n/a | 0.9 | n/a |  | 3 | 8 | 126 | n/a | Planning Permission Granted | Awaiting Construction | Lands 650 metres east of 57A Ballyhanedin Road Ballyhanedin 1.5 kilometres north west of Feeny | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 76884 | 568273 | Northern Ireland Planning Service | A/2014/0630/F | [5 empty] | 2015-01-15 | [6 empty] | 2017-04-27 |  |  |  | 2022-04-27
| 4958 | 2015-11-05 | Airvolution Energy | Lancarr | Wind Onshore |  |  | 6.9 | n/a | 0.9 | n/a |  | 2.3 | 3 | 110 | n/a | Planning Application Withdrawn | Application Withdrawn | Land at Whitelees Farm, Aiglegill Farm and West Farm, Nr. Aspatria | Cumbria | North West | England | CA7 3PF | 312620 | 542564 | Allerdale Borough Council | 2/2015/0030 | [5 empty] | 2015-01-15 | 2015-10-07
| 4959 | 2020-01-14 | 4Evergreen Technologies | Garden of England Energy | Advanced Conversion Technologies |  |  | 10.4 | No | 2 |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Kemsley Fields Business Park, Barge Way, Sittingbourne | Kent | South East | England | ME10 2FE | 591217 | 166709 | Kent County Council | KCC/SW/0010/2015 | [5 empty] | 2015-01-08 | [6 empty] | 2016-01-29 |  |  |  | 2019-01-29
| 4960 | 2015-03-23 | Bee Green Solar | Vantage Point Business Park (resubmission) | Solar Photovoltaics |  |  | 3.57 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land to the east of Vantage Point Business Village, Mitcheldean | Gloucestershire | South West | England | GL17 0AF | 366936 | 219263 | Forest of Dean District Council | P1957/14/FUL | [5 empty] | 2015-01-15 |  | 2015-03-16
| 4961 | 2018-08-24 | Stoerhouse Highlands | Georgemas | Biomass (dedicated) |  |  | 15 | Yes | 2 |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Georgmass Junction, Georgemas, Halkirk | Highland | Scotland | Scotland | KW12 6XA | 291110 | 955562 | Highland Council | 14/04545/FUL | PPA-270-2134 |  |  |  |  | 2014-12-04 |  | 2015-08-18 | 2015-08-20 |  |  | 2015-10-29 | 2015-10-29 |  |  |  | 2018-10-29
| 4962 | 2020-05-26 | Sun Farming | Apple Tree Close (resubmission) | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Bovey Road, Chudleigh, Newton Abbot, Devon, South West | Devon | South West | England | TQ13 0EY | 283747 | 77576 | Teignbridge District Council | 15/02092/MAJ | [5 empty] | 2015-10-28 | [6 empty] | 2016-05-31
| 4964 | 2020-07-09 | EDF Energy Renewables | Fallago Rig 2 (extension) | Wind Onshore |  |  | 41 | n/a | 0.9 | n/a |  | 3.45 | 12 | 126.5 | n/a | Appeal Refused | Application Refused | Fallago Rig 2, Longformacus, Duns | Borders | Scotland | Scotland | TD11 3PB | 369234 | 657296 | Scottish Government (S36) | EC00003102 | WIN-140-5 |  |  |  |  | 2016-01-29 |  | 2020-06-25 | 2016-12-21 |  | 2020-06-25
| 4968 | 2020-02-04 | RAF Desb | RAF Desborough | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Desborough Airfield, Desborough Road, Stoke Albany, Market Harborough, Leicestershire | Northamptonshire | East Midlands | England | LE16 8PT | 481920 | 286320 | Kettering Borough Council | KET/2015/0297 | [5 empty] | 2015-04-09 | [6 empty] | 2015-08-26 |  |  |  | 2018-08-26
| 4969 | 2017-10-04 | Green Power Consultants | Pressock Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field 225m North East of Pressock Farm, Pressock, Guthrie | Angus | Scotland | Scotland | DD8 2SN | 356893 | 749462 | Angus Council | 15/00330/FULL | [5 empty] | 2015-04-20 | [6 empty] | 2015-10-08 |  |  |  | 2018-10-08 | 2017-01-15 | 2017-03-28
| 4970 | 2017-03-22 | Agri-Gen/Downing | Bentwaters Park (extension) | Anaerobic Digestion |  |  | 1.8 | Yes | 2 | 9.02 |  | n/a | n/a | n/a | n/a | Operational | Operational | Land north of building 568 Bentwaters Parks, Rendlesham, Woodbridge | Suffolk | Eastern | England | IP12 2TW | 635759 | 253035 | Suffolk County Council | PL\0162\15 (C15/2358) | [5 empty] | 2015-06-04 | [6 empty] | 2015-12-03 |  |  |  |  | 2015-12-03 | 2016-03-15
| 4975 | 2016-09-02 | Intervate Renewable Energy | Cradley Heath | Advanced Conversion Technologies |  |  | 1.1 | Yes | 1.5 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Intervate Limited Portersfield Road Cradley Heath | West Midlands | West Midlands | England | B64 7BN | 394528 | 285627 | Sandwell Metropolitan Borough Council | [19 empty] | 2014-10-04
| 4976 | 2015-02-10 | Thames Water Utilities | Beckton Sewage Treatment Works | Wind Onshore |  |  | 2.2 | n/a | 0.9 | 3.07 |  | 1 | 2.2 | 64 | n/a | Operational | Operational | Beckton Sewage Works, Jenkins Lane, Barking | Greater London | London | England | IG11 0AD | 544385 | 182797 | Newham London Borough Council | [19 empty] | 2014-11-12
| 4978 | 2016-01-06 | Airvolution Energy | Land At Hartwood Hill | Wind Onshore |  |  | 21 | n/a | 0.9 | n/a |  | 3 | 7 | 126.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Hartwood Hill, Hightae, Lockerbie, Dumfries & Galloway | Dumfries and Galloway | Scotland | Scotland | DG11 1J | 307069 | 577164 | Dumfries and Galloway Council | 14/P/4/0542 | [5 empty] | 2015-01-21 | 2015-11-16
| 4979 | 2017-10-02 | REG Windpower | Scarcewater Tip | Wind Onshore |  |  | 6.9 | n/a | 0.9 | n/a |  | 2.3 | 3 | 92.5 | n/a | Appeal Refused | Application Refused | Scarcewater Tip, The Square, Grampound Road, Truro, Cornwall | Cornwall | South West | England | TR2 4 | 192800 | 54100 | Cornwall Council | PA15/00511 | APP/D0840/W/16/3158674 |  |  |  |  | 2015-01-21 |  | 2016-03-17 | 2016-12-30 |  | 2017-09-11
| 4980 | 2019-12-09 | Atlantis Resources | Inner Sound Phase 1B/1C (MeyGen) | Tidal Barrage and Tidal Stream |  |  | 86 | n/a | 2 | n/a |  | n/a | n/a |  | n/a | Planning Permission Granted | Awaiting Construction | Pentland Firth and Orkney waters strategic area, between Caithness on the Scottish mainland and the island of Stroma | Orkney Islands | Offshore | Scotland |  | 335503 | 984335 | Scottish Government (S36) | [6 empty] | 2012-07-19 | [6 empty] | 2013-09-16
| 4982 | 2015-05-07 | SBC Renewables | South of Johnsons Lane | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | South of Johnsons Lane, Widnes, Cheshire | Cheshire | North West | England | WA8 0SJ | 345000 | 385731 | Warrington Borough Council | 2014/24931 | [5 empty] | 2015-01-27 |  | 2015-04-22
| 4983 | 2016-06-17 | Anesco | Rufford Lane | Solar Photovoltaics |  |  | 2.62 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Field Reference Number 3753, Rufford Lane, Wellow, Newark | Nottinghamshire | East Midlands | England | NG22 0EQ | 466439 | 366123 | Newark and Sherwood District Council | 5/00083/FULM | [5 empty] | 2015-01-29 | [6 empty] | 2015-05-11 |  |  |  | 2018-05-11 | 2016-01-17 | 2016-06-17
| 4986 | 2017-05-26 | Canadian Solar | Land to the north and south of Cakers Lane (Wilsom) | Solar Photovoltaics |  |  | 11 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Cakers Lane, East Worldham, Alton, Hampshire | Hampshire | South East | England | GU34 3AB | 473543 | 138648 | East Hampshire District Council | 55465/001 | [5 empty] | 2015-01-20 | [6 empty] | 2015-11-02 |  |  |  | 2018-11-02 | 2017-01-20 | 2017-03-20
| 4987 | 2018-10-25 | Green Cat Renewables | Land to the north west of Hill of Petty | Wind Onshore |  |  | 3.6 | n/a | 0.9 | 3.07 |  | 0.9 | 4 | 67 | n/a | Planning Permission Granted | Awaiting Construction | Hill of Petty, Fyvie, Turriff, Grampian | Aberdeen | Scotland | Scotland | AB53 8QR | 375052 | 835922 | Aberdeenshire Council | APP/2015/0112 | [5 empty] | 2015-01-26 | [6 empty] | 2016-02-18 |  |  |  | 2019-02-18
| 4988 | 2019-07-02 | ESB | Kirk Hill Wind Farm | Wind Onshore |  |  | 24 | n/a | 0.9 | n/a |  | 3 | 8 | 110 | n/a | Appeal Granted | Awaiting Construction | Wallacetown-North West To, Hallowshean Cottage, Maybole, Strathclyde | South Ayrshire | Scotland | Scotland |  | 226190 | 604790 | South Ayrshire Council | 14/01646/APPM | PPA-370-2052 |  |  |  |  | 2015-01-29 |  | 2016-03-02 | 2016-05-31 |  |  | 2017-02-16 | 2017-02-16
| 4990 | 2016-04-19 | Cooper Energy Engineering | Collacott Farm | Solar Photovoltaics |  |  | 4.5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Collacott Farm, Newton Tracey, Barnstaple, Devon | Devon | South West | England | EX31 3QT | 251139 | 130383 | North Devon District Council | 58715 | [5 empty] | 2015-01-16 | [6 empty] | 2015-06-15 |  |  |  | 2018-06-15 | 2015-12-01 | 2016-03-22
| 4991 | 2016-11-29 | BE Renewables/Little Eau Solar | Fendyke Solar Farm - Extension | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | New Fendyke House, Fen Dyke, Sutton St. James, Spalding, Lincolnshire | Lincolnshire | East Midlands | England | PE12 0LQ | 537500 | 315900 | South Holland District Council | H20-0128-15 | APP/A2525/W/15/3138266 |  |  |  |  | 2015-02-12 |  | 2015-09-11 | 2015-12-01 |  | 2016-11-01
| 4992 | 2017-10-02 | REG Windpower | Land At Pines Tip | Wind Onshore |  |  | 2.7 | n/a | 0.9 | 3.07 |  | 0.9 | 3 | 70 | n/a | Appeal Refused | Application Refused | Land At Pines Tip, Summercourt, Newquay, Cornwall | Cornwall | South West | England | TR8 5 | 191800 | 56900 | Cornwall Council | PA15/00955 | APP/D0840/W/16/3158450 |  |  |  |  | 2015-02-02 |  | 2016-03-15 | 2016-12-29 |  | 2017-09-11
| 4993 | 2016-01-04 | Solar Power South | Land to the South West of Horsey Lane | Solar Photovoltaics |  |  | 25 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land to the South West of Horsey Lane, Puriton Hill and East of the Bridgwater | Somerset | South West | England | TA7 8 | 333645 | 141571 | Sedgemoor District Council | 09/15/00005 | APP/V3310/W/15/3049326 |  |  |  |  | 2015-01-22 |  | 2015-04-22 | 2015-09-03 |  | 2015-12-10
| 4994 | 2016-08-17 | Capital Estate Tonedale | Tonedale Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Tonedale Farm, Linden Hill, Wellington, Somerset | Somerset | South West | England | TA21 0DW | 312488 | 120781 | Taunton Deane Borough Council | 43/15/0008 | [5 empty] | 2015-02-03 | [6 empty] | 2015-06-11 |  |  |  | 2018-06-11 | 2015-09-10 | 2015-12-10
| 4995 | 2017-06-21 | Seneca Global Energy | Melton Waste Park (resubmission) | Wind Onshore |  |  | 5 | n/a | 0.9 | 3.07 |  | 2.5 | 2 | 117 | n/a | Operational | Operational | Land South West Of Melton Waste, Gibson Lane, Melton, North Ferriby, Humberside | Humberside | Yorkshire and Humber | England | HU14 3HH | 496867 | 425532 | East Riding of Yorkshire Council | 14/03951/STPLFE | [5 empty] | 2015-02-03 | [6 empty] | 2015-04-20 |  |  |  | 2018-04-20 | 2016-06-15 | 2017-03-01
| 4996 | 2015-12-21 | Sun Farming | Lindridge Farm | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Lindridge Farm, Lindridge Lane, Desford, Leicester | Leicestershire | East Midlands | England | LE9 9FD | 446680 | 305219 | Hinckley and Bosworth Borough Council | 14/01270/FUL | [5 empty] | 2015-02-03 | [6 empty] | 2015-04-23 |  |  |  | 2018-04-23 |  | 2015-12-21
| 4997 | 2016-09-30 | Rectory Lane Renewables | Abbots Ripton Solar Farm (ext.) | Solar Photovoltaics |  |  | 3.9 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Railway Line & South Of Brooklands Farm, Abbots Ripton, Huntingdon, Cambridgeshire | Cambridgeshire | Eastern | England | PE28 2PB | 523027 | 276480 | Huntingdonshire District Council | 1402200FUL | [5 empty] | 2014-12-23 | [6 empty] | 2015-07-15 |  |  |  | 2018-07-15 | 2015-09-01 | 2015-12-01
| 4998 | 2018-08-30 | Island Renewable Energy | Beltonanean Wind Farm (revised) | Wind Onshore |  |  | 12 | n/a | 0.9 | n/a |  | 2 | 6 | 126.5 | n/a | Appeal Withdrawn | Application Refused | Beltonanean Ballynasollus, Ballynasollus, Beleevna-More and Ballynagill, Cookstown, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT80 | 85741 | 543706 | Northern Ireland Planning Service | I/2014/0413/F | 2017/A0257 |  |  |  |  | 2015-01-19 |  | 2017-11-24 | 2018-03-22 | 2018-08-20
| 5000 | 2015-03-09 | Kingspan Energy | Gilford Road | Solar Photovoltaics |  |  | 1.3 | n/a | 1.6 | 6.38 |  | n/a | n/a | n/a | Roof | Operational | Operational | 180 Gilford Road, Portadown, Craigavon | Co. Armagh | Northern Ireland | Northern Ireland | BT63 5LF | 113760 | 510643 | Northern Ireland Planning Service | N/2013/0454/F | [5 empty] | 2013-11-26 | [6 empty] | 2014-01-22 |  |  |  | 2019-01-22 | 2014-12-01 | 2015-02-06
| 5001 | 2016-06-16 | United Utilities | Fleetwood Water Treatment Works | Solar Photovoltaics |  |  | 1.32 | n/a | 1.6 | 6.38 |  | n/a | n/a | n/a | Roof | Operational | Operational | Fleetwood Waste Water Treatment Works, Jameson Road, Fleetwood | Lancashire | North West | England |  | 333178 | 446368 | Lancashire County Council | LCC/2014/0121 | [5 empty] | 2014-07-16 | [6 empty] | 2014-02-02 |  |  |  | 2019-07-16 | 2015-11-30 | 2015-03-15
| 5002 | 2017-02-02 | Cambridge County Council | Triangle Solar Farm Park | Solar Photovoltaics |  |  | 10 | n/a | 1.4 | n/a | 12 | n/a | n/a | n/a | Ground | Operational | Operational | Triangle Farm, Soham, Cambridgeshire | Cambridgeshire | Eastern | England | CB7 5HX | 558007 | 272569 | East Cambridgeshire District Council | 14/00779/FUM | [5 empty] | 2014-07-09 | [6 empty] | 2014-10-08 |  |  |  | 2017-10-08 | 2016-11-04 | 2017-01-04
| 5003 | 2015-03-09 | REG Bio-Power | Whitemoor | Biomass (dedicated) |  |  | 18 | No | 1.5 | n/a |  | n/a | n/a | n/a | n/a | Operational | Operational | Whitemoor Business Park, Cliffe Rd, Cliffe Common, Selby | North Yorkshire | Yorkshire and Humber | England | YO8 6EG | 466450 | 435843 | Selby District Council | 2012/0914/FUL | [5 empty] | 2012-09-27 | [6 empty] | 2012-11-29 |  |  |  | 2015-11-29 |  | 2014-10-01
| 5006 | 2016-05-27 | 3C Energy | Land at Lower House Farm | Solar Photovoltaics |  |  | 8.1 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Lower House Farm, Kemeys Commander, Usk | Monmouthshire | Wales | Wales | NP15 1JJ | 334772 | 204371 | Monmouthshire County Council | DC/2012/00666 | [5 empty] | 2012-08-08 | [6 empty] | 2012-12-10 |  |  |  |  | 2016-02-01 | 2016-03-21
| 5011 | 2016-06-28 | Renewable Energy Systems (RES) | Former Woolfox Lodge Airfield | Wind Onshore |  |  | 27 | n/a | 0.9 | n/a |  | 3 | 9 | 130 | n/a | Planning Permission Refused | Application Refused | Former Woolfox Lodge Airfield, Woolfox Wind Farm, Stretton, Oakham, Leicestershire | Leicestershire | East Midlands | England |  | 496071 | 313008 | Rutland County Council | 2014/1003/MAJ | [5 empty] | 2015-02-09 |  | 2015-12-16
| 5012 | 2015-12-21 | Aldi | Aldi Distribution Centre | Solar Photovoltaics |  |  | 1.28 | n/a | 1.6 | 6.38 |  | n/a | n/a | n/a | Roof | Operational | Operational | Aldi Distribution Centre, Pottishaw Road, Bathgate, Lothian | West Lothian | Scotland | Scotland | EH48 2FB | 296982 | 666291 | West Lothian Council | LIVE/0087/FUL/15 | [5 empty] | 2015-02-10 | [6 empty] | 2015-03-04 |  |  |  | 2018-03-04 |  | 2015-10-22
| 5013 | 2020-01-24 | Wirsol / Elgar Middleton | Raventhorpe Lodge (Sweeting Thorns) | Solar Photovoltaics |  |  | 25 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Raventhorpe Lodge, Storage Lan, Brigg Road, Access Road In Raventhorpe Lod, Scunthorpe, Humberside | Humberside | Yorkshire and Humber | England | DN16 3RJ | 492685 | 407666 | North Lincolnshire Council | PA/2015/0114 | APP/Y2003/W/16/3145863 |  |  |  |  | 2015-02-12 |  | 2015-11-18 | 2016-05-11 |  |  | 2016-12-05 | 2016-12-05
| 5014 | 2019-10-17 | Sovereign Partners | Bromfield Sand and Gravel | Solar Photovoltaics |  |  | 0.5 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Bromfield Sand And Gravel Co L, Bromfield Pit, Bromfield, Ludlow, Shropshire | Shropshire | West Midlands | England | SY8 2JT | 348216 | 277082 | Shropshire Council | 15/00284/FUL | [5 empty] | 2015-02-09 | [6 empty] | 2015-06-25 |  |  |  | 2018-06-25 | 2015-07-20 | 2017-08-25
| 5015 | 2016-12-23 | Sovereign Partners | Land at Heywood Grange | Solar Photovoltaics |  |  | 8.36 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Heywood Grange, Tickhill Lane, Dilhorne, Stoke-On-Trent, Staffordshire | Staffordshire | West Midlands | England | ST10 2PL | 396046 | 344411 | Staffordshire Moorlands District Council | SMD/2015/0088 | [5 empty] | 2015-02-18 | [6 empty] | 2015-09-03 |  |  |  | 2018-09-03 |  | 2016-10-19
| 5016 | 2020-06-25 | Renewable Energy Systems (RES) | Woolfox Quarry | Solar Photovoltaics |  |  | 36.74 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Woolfox Quarry, Great North Ro, Stretton, Empingham, Oakham, Leicestershire | Leicestershire | East Midlands | England | LE15 7Q | 496740 | 313180 | Rutland County Council | 2014/1004/MAJ | [5 empty] | 2015-02-13 | [6 empty] | 2016-03-18 |  |  |  | 2019-03-18
| 5017 | 2018-03-02 | NESF (formerly Tau Solar) | Ravens Close | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Solar PV Farm Grazing Land, Ravens Close, Lower Bentham, Lancaster, Lancashire | North Yorkshire | Yorkshire and Humber | England | LA2 7EU | 364025 | 470692 | Craven District Council | 08/2015/15473 | APP/C2708/W/15/3129664 |  |  |  |  | 2015-02-02 |  | 2015-06-10 | 2015-07-30 |  |  | 2016-03-21 | 2016-03-21 |  |  |  |  | 2016-10-24 | 2017-03-14
| 5018 | 2017-05-03 | NESF (formerly Earthworm/Waltham Solar) | Forest Farm | Solar Photovoltaics |  |  | 3 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Forest Farm, Winchester Road, Waltham Chase, Southampton | Hampshire | South East | England | SO32 2LL | 456113 | 116238 | Winchester City Council | 15/00082/FUL | [5 empty] | 2015-02-04 | [6 empty] | 2015-12-11 |  |  |  | 2018-12-11 | 2017-02-01 | 2017-03-01
| 5019 | 2016-03-24 | Navitas Project | Land West of Roberts Wall Far | Solar Photovoltaics |  |  | 2.5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West of, Roberts Wall Far, Trefloyne Lane, Penally, Tenby, Dyfed | Pembrokeshire | Wales | Wales | SA70 8NF | 210186 | 200504 | Pembrokeshire County Council | 14/1055/PA | [5 empty] | 2015-02-17 | [6 empty] | 2015-06-26 |  |  |  | 2020-06-26 | 2016-02-01 | 2016-03-23
| 5020 | 2017-08-23 | Anesco | Drayton Manor Farm | Solar Photovoltaics |  |  | 25 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Drayton Manor Farm, Alcester Road, Stratford-On-Avon, Warwickshire | Warwickshire | West Midlands | England | CV37 9RG | 415469 | 255805 | Stratford on Avon District Council | 15/00326/FUL | [5 empty] | 2015-01-30 | [6 empty] | 2015-06-08 |  |  |  | 2018-06-08 | 2015-12-15 | 2016-03-23
| 5021 | 2018-12-14 | The Crown Estate and Albion Stone | Independent Quarries | Solar Photovoltaics |  |  | 3 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Independent Quarries, Easton Lane, Portland, Dorset | Dorset | South West | England | DT5 1BW | 369087 | 72568 | Weymouth and Portland Borough Council | WP/15/00039/FUL | [5 empty] | 2015-02-16 | [6 empty] | 2015-09-30
| 5022 | 2016-03-24 | Navitas Project | Somersal Mill Farm | Solar Photovoltaics |  |  | 2.6 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Somersal Mill Farm, Somersal Herbert, Ashbourne | Derbyshire | East Midlands | England | DE6 5PD | 413907 | 335414 | Derbyshire Dales District Council | 15/00059/FUL | [5 empty] | 2015-02-11 | [6 empty] | 2015-05-13 |  |  |  | 2018-05-13 | 2016-02-01 | 2016-03-23
| 5023 | 2018-10-29 | Marriages Specialist Foods | Bluestone Heath Road | Solar Photovoltaics |  |  | 1.5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Marriages Specialist Foods, Bluestone Heath Road, Driby Top, Alford, Lincolnshire | Lincolnshire | East Midlands | England | LN13 0BT | 540273 | 374815 | East Lindsey District Council | N/163/00245/15 | [5 empty] | 2015-02-19 | [6 empty] | 2015-03-31
| 5024 | 2020-05-27 | First Renewable Developments | Burton Wold Solar Farm | Solar Photovoltaics |  |  | 8.4 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Burton Wold Farm, Wold Road, Burton Latimer, Kettering, Northamptonshire | Northamptonshire | East Midlands | England | NN15 5PJ | 491204 | 274882 | Kettering Borough Council | KET/2014/0863 | [5 empty] | 2015-02-09 | [6 empty] | 2015-04-10
| 5025 | 2016-08-02 | Renewable Energy Systems (RES) | Rhos Garn Whirlgarn (resubmission) | Wind Onshore |  |  | 6 | n/a | 0.9 | n/a |  | 2 | 3 | 126.5 | n/a | Appeal Refused | Application Refused | Rhosgarn Whirlgarn, Talgarreg, Llandysul, Dyfed | Ceredigion | Wales | Wales | SA44 4EP | 245013 | 252013 | Ceredigion County Council | A150038 | APP/D6820/A/15/3139282 |  |  |  |  | 2015-02-12 |  | 2015-05-28 | 2016-03-16 |  | 2016-07-06
| 5026 | 2016-08-24 | Lightsource Renewable Energy | Land Opposite Tyn Y Pistyll | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Opposite Tyn Y Pistyll, West of Delph Road, Penycae, Wrexham, Clwyd | Wrexham | Wales | Wales | LL14 1TU | 328238 | 343877 | Wrexham County Borough Council | P/2015/0092 | [5 empty] | 2015-02-10 | [6 empty] | 2015-05-12 |  |  |  | 2020-05-12 | 2015-10-16 | 2015-12-22
| 5028 | 2015-08-05 | Dulas Hydrogeneration | Land East of Allt Airdeasaidh | Small Hydro |  |  | 2 | n/a | 0.7 | 10.96 |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land East Of Allt Airdeasaidh,, Dundonnell, Ardessie, Garve, Highlands | Highland | Scotland | Scotland | IV23 2QU | 205563 | 889593 | Highland Council | 15/00258/FUL | [5 empty] | 2015-02-09 |  | 2015-07-20
| 5030 | 2019-10-24 | Kew Technologies (formerly JCB Broadcrown) | Wednesbury (resubmission) | EfW Incineration |  |  | 2 | Yes | n/a | n/a |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Former Spread Eagle Works, Portway Road, Wednesbury, West Midlands | West Midlands | West Midlands | England | WS10 7DZ | 398082 | 294992 | Sandwell Metropolitan Borough Council | DC/14/57758 | [5 empty] | 2014-12-31 | [6 empty] | 2015-03-25 |  |  |  | 2018-03-25 | 2017-04-26
| 5031 | 2015-04-07 | South West Solar Parks (Brook Hall Farm SPV) | Brook Hall Farm | Solar Photovoltaics |  |  | 10 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Brook Hall Farm, North Bradley, Trowbridge, Wiltshire | Wiltshire | South West | England | BA14 9PT | 385062 | 153433 | Wiltshire Council | 15/01199/FUL | [5 empty] | 2015-02-09 | 2015-05-11
| 5033 | 2016-08-24 | Lightsource Renewable Energy | Land South of Highfield House | Solar Photovoltaics |  |  | 5 | n/a | 1.4 | 6.38 |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South East Of Highfield House, Husthwaite, York, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO61 4PN | 450236 | 472744 | Hambleton District Council | 15/00318/FUL | [5 empty] | 2015-02-20 | [6 empty] | 2015-06-29 |  |  |  | 2018-06-29 | 2016-01-14 | 2016-03-15
| 5051 | 2018-04-27 | EDF Energy Renewables | Dorenell Wind Farm (extension/redesign) | Wind Onshore |  |  | 174.9 | n/a | 0.9 | n/a |  | 3.3 | 53 | 150 | n/a | Abandoned | Abandoned | Glenlivet Estate, Dufftown, Speyside, Moray | Grampian | Scotland | Scotland |  | 332000 | 829500 | Scottish Government (S36) | EC00003111 | WIN-300-2 |  |  |  |  | 2014-12-12 |  | 2016-06-02 | 2016-09-22
| 5052 | 2015-08-04 | Private Developer | Pen yr Heol Las Farm | Wind Onshore |  |  | 1 | n/a | 0.9 | 7.24 |  | 0.5 | 2 | 64 | n/a | Appeal Refused | Application Refused | Pen yr Heol Las Farm | Caerphilly | Wales | Wales | CF83 2TT | 314089 | 189685 | Caerphilly County Borough Council | 14/0622/FULL | APP/K6920/A/15/2230059 |  |  |  |  | 2014-09-23 |  | 2014-11-25 | 2015-03-04 |  | 2015-07-28
| 5053 | 2016-07-25 | Renesola | Rhewl Farm | Solar Photovoltaics |  |  | 6 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Rhewl Farm, Shirenewton | Monmouthshire | Wales | Wales | NP16 6AG | 349490 | 193050 | Monmouthshire County Council | DC/2014/00939 | APP/E6840/A/14/2229840 |  |  |  |  | 2014-08-06 |  | 2014-12-05 | 2015-02-24 |  |  | 2015-06-25 | 2015-06-25 |  |  |  | 2020-06-25 | 2016-04-04 | 2016-06-26
| 5054 | 2018-08-28 | PerPetum Sun | Robert McBride Ltd | Solar Photovoltaics |  |  | 1.269 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Expired | Planning Permission Expired | Robert McBride Ltd, Middleton , Middleton, Rochdale, Manchester | Greater Manchester | North West | England | M24 4DP | 386694 | 405586 | Rochdale Borough Council | 15/00165/FUL | [5 empty] | 2015-03-05 | [6 empty] | 2015-04-29 |  |  |  | 2018-04-29
| 5055 | 2018-07-19 | Wykes Engineering | Chelveston Renewable Energy Park | Solar Photovoltaics |  |  | 21 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Chelveston Renewable Energy Park, Caldecott, Wellingborough, Northamptonshire | Northamptonshire | East Midlands | England | NN9 6AR | 499887 | 267620 | East Northamptonshire Council | 15/00489/FUL | [5 empty] | 2015-03-11 | [6 empty] | 2015-06-30 |  |  |  | 2018-06-30
| 5056 | 2016-03-03 | Iota Solar (OPDE) | Catsfield Solar Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Catsfield Road, Catsfield, Battle | East Sussex | South East | England | TN33 9BB | 571962 | 113200 | Rother District Council | RR/2015/142/P | APP/U1430/W/15/3033695 |  |  |  |  | 2015-01-23 |  | 2015-04-09 | 2015-07-13 |  | 2016-02-17
| 5057 | 2015-08-05 | Town Farm Solar Farm | Land at Wood Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Wood Road, Harrold, Bedford, Bedfordshire, | Norfolk | Eastern | England | MK43 7BS | 494575 | 258345 | Bedford Borough Council | 15/00444/MAF | [5 empty] | 2015-03-10 |  | 2015-07-27
| 5058 | 2015-04-07 | Dowsett Mayhew Planning Partnership | Land at Barrow Green Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Barrow Green Farm, Haxted Road, Lingfield, Surrey | Surrey | South East | England | RH7 6DE | 540136 | 144342 | Tandridge District Council | 2015/57 | [5 empty] | 2015-01-13 |  | 2015-02-25
| 5061 | 2015-07-01 | Still Wind | Land East of Mount Pleasant Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | Mount Pleasant Farm, Land East Of, Bedlington, Northumberland | Northumberland | North East | England | NE22 7BP | 429510 | 582636 | Northumberland County Council | 15/00454/RENEIA | [5 empty] | 2015-03-05 | 2015-06-03
| 5062 | 2015-03-23 | 1 Stop Renewables | Land South East Of Auchterhead | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 99.5 | n/a | Planning Application Submitted | Application Submitted | Land South East Of Auchterhead, Dura Road, Wishaw, Strathclyde | North Lanarkshire | Scotland | Scotland | ML2 9PJ | 287876 | 654682 | North Lanarkshire Council | 15/00395/FUL | [5 empty] | 2015-03-03
| 5063 | 2017-04-20 | TGC Renewables | Land at Dayfields Farm | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Dayfields Farm, Atlow, Ashbourne, Derbyshire | Derbyshire | East Midlands | England | DE6 1NU | 423086 | 347786 | Derbyshire Dales District Council | 15/00089/FUL | APP/P1045/W/15/3131502 |  |  |  |  | 2015-03-03 |  | 2015-07-23 | 2015-08-20 |  |  | 2016-03-09 | 2016-03-09 |  |  |  |  | 2016-11-01 | 2016-12-30
| 5064 | 2016-05-04 | Clearwinds | Land At Knightacott Cross | Solar Photovoltaics |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land At Knightacott Cross, Bratton Fleming, Barnstaple, Devon | Devon | South West | England | EX31 4 | 265750 | 139450 | North Devon District Council | 58895 | APP/X1118/W/15/3135317 |  |  |  |  | 2015-02-18 |  | 2015-08-06 | 2015-12-23 |  | 2016-04-15
| 5066 | 2018-08-28 | Raw Energy | Prospect Farm | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Prospect Farm, The Highway, Drayton Parslow, Milton Keynes, Buckinghamshire | Buckinghamshire | South East | England | MK17 0JW | 484285 | 228984 | Aylesbury Vale District Council | 15/00557/APP | [5 empty] | 2015-03-09 | [6 empty] | 2015-06-08 |  |  |  | 2018-06-08
| 5071 | 2015-03-23 | EvoEnergy | MMD Shipping Services | Solar Photovoltaics |  |  | 1.16 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Portsmouth Harbour | Hampshire | South East | England | PO2 8HB | 464214 | 101577 | Portsmouth City Council | 14/00830/FUL | [5 empty] | 2014-07-04 | [6 empty] | 2014-09-12 |  |  |  |  | 2015-01-01 | 2015-03-09
| 5077 | 2016-10-03 | Partnerships for Renewables | Haverigg Prison (resubmission) | Wind Onshore |  |  | 9 | n/a |  |  |  | 1.8 | 5 | 100 | n/a | Abandoned | Abandoned | Land to west & south of HMP Prison, Off North Lane, Haverigg, Millom, Cumbria | Cumbria | North West | England | LA18 4NA | 313860 | 478710 | Copeland Borough Council | 4/15/2022/0F1 | [5 empty] | 2015-01-23 | [6 empty] | 2015-06-10 |  |  |  | 2020-06-10
| 5078 | 2020-06-09 | Peel Environmental | Houghton Main | EfW Incineration |  |  | 20 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land off Houghton Main Collier, Spring Road, Roundabout Park, Barnsley, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | S71 5EX | 441743 | 406376 | Barnsley Council | 2015/0137 | [5 empty] | 2015-02-17 | [6 empty] | 2015-06-29
| 5079 | 2017-02-21 | Tulip Meats | Newton Margate | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Tulip Ltd, Newtons Margate, Bodmin | Cornwall | South West | England | PL31 1HF | 208517 | 66931 | Cornwall Council | PA14/11690 | [5 empty] | 2015-03-19 | [6 empty] | 2015-05-22 |  |  |  | 2018-05-22 | 2015-08-01 | 2015-10-01
| 5080 | 2016-03-23 | PS Renewables | Eveley Farm (resubmission) | Solar Photovoltaics |  |  | 49 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Eveley Farm Stevens Drove Houghton Stockbridge | Hampshire | South East | England | SO20 6SA | 432987 | 134363 | Test Valley Borough Council | 15/00094/FULLS | [5 empty] | 2015-02-16 | [6 empty] | 2015-07-27 |  |  |  | 2018-07-27 | 2016-03-01 | 2016-03-17
| 5081 | 2017-08-31 | Kelda Organic Energy | Cardiff Organic Waste Treatment Project (resubmission) | Anaerobic Digestion |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cardiff Waste Water Treatment Works, Tide Fields Road, East Moors | Cardiff | Wales | Wales | CF14 2RX | 321166 | 175969 | Cardiff Council | 15/00591/MJR | [5 empty] | 2015-03-12 | [6 empty] | 2015-05-13 |  |  |  | 2020-05-13 | 2016-01-23 | 2017-01-23
| 5082 | 2019-09-16 | Energiekontor UK | Mynydd Pencarreg | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 | 99.5 | n/a | Planning Permission Granted | Awaiting Construction | Land North of Esgairliving, Rhydcwmerau, Llandeilo | Carmarthenshire | Wales | Wales | SA19 7RG | 256960 | 241000 | Carmarthenshire County Council | W/31728 | [5 empty] | 2015-03-18 | [6 empty] | 2016-03-08 |  |  |  | 2019-03-08
| 5084 | 2017-10-04 | BE Renewables | Court Farm (Resubmission) | Solar Photovoltaics |  |  | 8.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Forming Part Of Court Farm, Magor Road | Newport | Wales | Wales | NP18 2EB | 339241 | 189511 | Newport City Council | 14/1275 | APP/G6935/A/15/3034087 |  |  |  |  | 2015-03-05 |  | 2015-04-07 | 2015-07-10 |  |  | 2015-10-09 | 2015-10-09 |  |  |  |  | 2017-01-30 | 2017-03-30
| 5085 | 2017-04-04 | Lightsource Renewable Energy | Millar Farm | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands 90m west of lands to the South of 72 Milltown Road | Co. Antrim | Northern Ireland | Northern Ireland | BT41 2JJ | 127283 | 546753 | Northern Ireland Planning Service | T/2015/0094/F | [5 empty] | 2015-03-03 | [6 empty] | 2015-07-22 |  |  |  | 2020-07-22 | 2016-11-28 | 2017-03-27
| 5087 | 2018-03-28 | Beltonanean Renewable Energy | Beltonanean Wind Turbine 2 | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 92.5 | n/a | Appeal Refused | Application Refused | Beltonanean Mountain, Beltonanean TD, Cookstown | Co. Tyrone | Northern Ireland | Northern Ireland |  | 85122 | 543266 | Northern Ireland Planning Service | I/2014/0399/F | 2016/A0221 |  |  |  |  | 2014-12-17 |  | 2017-02-08 | 2017-02-20 |  | 2018-03-05
| 5088 | 2018-07-18 | Sunrise Renewables | Barry Docks (new project) | Advanced Conversion Technologies |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | David Davies Road, Woodham Road, Barry | Vale of Glamorgan | Wales | Wales | CF634JE | 312610 | 167683 | Vale of Glamorgan Council | 2015/00031/OUT | [5 empty] | 2015-02-12 | [6 empty] | 2015-07-31 |  |  |  | 2018-07-31 | 2016-04-15 | 2018-04-15
| 5089 | 2016-02-16 | Hive Energy | Green Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Green Farm, Oakley Road, Wix | Essex | Eastern | England | CO11 2SE | 616994 | 228407 | Tendring District Council | 15/00147/FUL | [5 empty] | 2015-02-04 | [6 empty] | 2015-05-06 |  |  |  |  | 2015-11-01 | 2015-12-01
| 5090 | 2017-06-30 | Wirsol Energy | Home Farm | Solar Photovoltaics |  |  | 6.68 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Home Farm, Brockhampton Lane, Brockhampton | Gloucestershire | South West | England | GL51 9RS | 393922 | 226330 | Tewkesbury Borough Council | 15/00238/FUL | [5 empty] | 2015-03-03 | [6 empty] | 2015-10-22 |  |  |  | 2018-10-22 | 2016-11-15 | 2017-03-31
| 5091 | 2020-03-18 | Gazelle Properties | Fosseway Environment Park | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Fosseway Environment Park, Fosseway, Englishcombe, Bath | Somerset | South West | England | BA2 8PD | 372395 | 161189 | Bath and North East Somerset Council | 14/00839/EMINW | [5 empty] | 2015-02-21 | [6 empty] | 2014-08-04 |  |  |  |  | 2018-09-15
| 5092 | 2018-07-05 | NESF (formerly Lark Energy) | Land at Thornborough Grounds | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Thornborough Grounds, Bletchley Road, Thornborough | Buckinghamshire | South East | England | MK18 2AB | 473734 | 234922 | Aylesbury Vale District Council | 15/00723/APP | [5 empty] | 2015-03-11 | [6 empty] | 2015-06-10 |  |  |  | 2018-06-10 | 2016-01-11 | 2016-03-31
| 5093 | 2015-08-28 | Associated British Ports (ABP) | Port of Barry (Resubmission) - Site 1 | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Atlantic Way, Port of Barry, Barry | Vale of Glamorgan | Wales | Wales | CF63 3RA | 312836 | 167102 | Vale of Glamorgan Council | 2015/00173/FUL | [5 empty] | 2013-02-18 | [6 empty] | 2015-04-15 |  |  |  | 2020-04-15 | 2015-06-01 | 2015-08-18
| 5094 | 2019-04-01 | Drummond Estate | Allt an Dubh Choirein | Small Hydro |  |  | 1.6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Dubh Choirein Hydro Scheme Comrie | Perth and Kinross | Scotland | Scotland |  | 269463 | 715260 | Perth and Kinross Council | 14/02056/FLL | [5 empty] | 2014-11-26 | 2018-03-08
| 5095 | 2018-10-26 | British Solar Renewables | Coombe Solar Farm | Solar Photovoltaics |  |  | 15.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Bob Lane and Chapel Road, Twineham | West Sussex | South East | England | BN6 9JE | 525093 | 121274 | Mid Sussex District Council | DM/15/0644 |  |  |  | 41711 |  | 2015-02-16 | [6 empty] | 2015-08-10 |  |  |  | 2018-08-10
| 5096 | 2017-03-31 | British Solar Renewables / NextEenrgy Solar Fund (NESF) | Southern Counties Shooting Ground Phase 1 (resubmission) | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Long Ash Lane, Wardon Hill | Dorset | South West | England | DT2 9PW | 360954 | 102553 | West Dorset District Council | WD/D/14/003367 | [5 empty] | 2014-12-24 | [6 empty] | 2015-09-08 |  |  |  | 2018-09-08 | 2016-09-15 | 2017-01-06
| 5098 | 2016-05-30 | W.H. Malcolm Ltd | Energy Recovery Facility South Street | Advanced Conversion Technologies |  |  | 12 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Lodged | Application Refused | 865 South Street | Glasgow | Scotland | Scotland | G14 0BX | 253217 | 667154 | Glasgow City Council | 15/00549/DC | PPA-260-2055 |  |  |  |  | 2015-03-06 |  | 2016-02-29 | 2016-05-06
| 5099 | 2015-12-22 | Primrose Solar | Fanny House Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fanny House Farm, Heysham | Lancashire | North West | England | LA3 3EF | 342598 | 462146 | Lancaster City Council | 15/00243/FUL | [5 empty] | 2015-03-04 | [6 empty] | 2015-06-30 |  |  |  | 2018-06-30 | 2015-11-01 | 2015-12-21
| 5102 | 2016-04-01 | Conergy | Chard Solar Park | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Os 5600, Chaffcombe Road, Chard, Somerset | Somerset | South West | England | TA20 1RR | 333733 | 110028 | South Somerset District Council | 15/03187/FUL | [5 empty] | 2015-07-15 | [6 empty] | 2015-10-28 |  |  |  | 2018-10-28 | 2015-12-07 | 2016-03-23
| 5104 | 2017-06-16 | Cenin Renewables | Home Farm | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Home Farm, land West of Drope Road, St. George's-super-Ely, Cardiff, South Glamorgan, Wales | Vale of Glamorgan | Wales | Wales | CF5 6EP | 310310 | 175854 | Vale of Glamorgan Council | 2015/00852/FUL | [5 empty] | 2015-07-30 | [6 empty] | 2016-01-14 |  |  |  | 2021-01-14 | 2017-01-09 | 2017-04-15
| 5116 | 2019-05-31 | Brookfield Renewable Energy Group (PNE Wind UK) | Larbrax Wind Farm (resubmission) | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 | 100 | n/a | Appeal Granted | Awaiting Construction | Larbrax, Leswalt, Stranraer | Dumfries and Galloway | Scotland | Scotland | DG9 0RR | 197120 | 561850 | Dumfries and Galloway Council | 15/P/1/0044 | PPA-170-2105 |  |  |  |  | 2015-02-25 |  | 2015-08-26 | 2015-11-27 |  |  | 2016-10-21 | 2016-10-21
| 5117 | 2016-02-01 | Vogt Solar | Marshborough Farm solar park (resubmission) | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Marshborough Farm, Marshborough, Sandwich | Kent | South East | England | CT3 2BZ | 630755 | 158334 | Dover District Council | 15/00115 | [5 empty] | 2015-02-14 | [6 empty] | 2015-05-29 |  |  |  | 2018-05-29 | 2015-09-15 | 2015-11-15
| 5118 | 2018-09-17 | Lark Energy | Fiskerton Airfield (Phase 2) | Solar Photovoltaics |  |  | 22 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Reepham Road, Fiskerton, Lincoln | Lincolnshire | East Midlands | England | LN3 4EZ | 504955 | 373023 | West Lindsey District Council | 130671 | [5 empty] | 2013-11-07 | [6 empty] | 2014-01-30 |  |  |  |  | 2014-10-01 | 2015-03-01
| 5119 | 2018-09-17 | Lark Energy | Langley Priory, Walnut Yard (Phase 2) | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The West Of Gelscoe House Farm Outbuildings Gelscoe Lane Diseworth | Leicestershire | East Midlands | England |  | 442964 | 322649 | North West Leicestershire District Council | 14/00408/FULM | [5 empty] | 2014-05-06 | [6 empty] | 2014-10-07 |  |  |  | 2017-10-07 | 2014-12-01 | 2016-06-01
| 5120 | 2020-03-18 | Thames Gateway Waste to Energy (Chinook Urban Mining) | Thames Gateway EfW (Resubmission) | Advanced Conversion Technologies |  |  | 19 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | London Sustainable Industries Park, Choats Road, Dagenham, Essex | Greater London | London | England |  | 548402 | 182606 | Barking and Dagenham London Borough Council | 13/01134/FUL | [5 empty] | 2013-12-24 | [6 empty] | 2014-11-05 |  |  |  | 2017-11-05 | 2017-03-01
| 5122 | 2019-06-25 | Ecotricity | Upper Sonachan Wind Farm | Wind Onshore |  |  | 64.6 | n/a |  |  |  | 3.4 | 19 | 136.5 | n/a | Appeal Refused | Application Refused | Upper Sonachan Forest, between the B840 and A819 | Argyll and Bute | Scotland | Scotland |  | 206490 | 720032 | Scottish Government (S36) | EC00002081 | WIN-130-2 |  |  |  |  | 2015-10-29 |  |  | 2017-04-24 |  | 2019-05-24
| 5123 | 2020-05-26 | Infinergy (formerly PI Renewables) | Eascairt Wind Farm | Wind Onshore |  |  | 26 | n/a |  |  |  | 2 | 13 | 100 | n/a | Appeal Granted | Awaiting Construction | Escairt Farm by Skipness | Argyll and Bute | Scotland | Scotland |  | 183500 | 655000 | Argyll and Bute Council | 15/00205/PP | PPA-130-2059 |  |  |  |  | 2015-02-19 |  | 2016-09-21 | 2016-12-20 |  |  | 2018-09-28 | 2018-09-28
| 5125 | 2015-05-07 | Edgar Middleton | Bluegates Solar Park | Solar Photovoltaics |  |  | 10.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Blue Gates Farm Colchester Main Road Alresford | Essex | Eastern | England | CO7 8DE | 607018 | 222279 | Colchester Borough Council | 14/00352/FUL | [5 empty] | 2014-04-04 | [6 empty] | 2014-07-04 |  |  |  | 2017-07-04 | 2014-10-01 | 2015-01-30
| 5127 | 2016-07-01 | EBS Energy LLP | Whitton Solar Farm (resubmission) | Solar Photovoltaics |  |  | 8.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Whitton Solar Farm, Caynham, Ludlow, Shropshire | Shropshire | West Midlands | England | SY3 8BW | 356451 | 273394 | Shropshire Council | 15/01238/FUL | APP/L3245/W/15/3141378 |  |  |  |  | 2015-03-19 |  | 2015-07-01 | 2016-02-02 |  | 2016-06-07
| 5128 | 2016-03-15 | Anesco | Land To The East Of Back Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The East Of Back Lane, Bole Hill, Calow, Chesterfield, Derbyshire | Derbyshire | East Midlands | England | S44 5 | 441867 | 370139 | North East Derbyshire District Council | 15/00218/FL | [5 empty] | 2015-03-10 | [6 empty] | 2015-06-25 |  |  |  | 2018-06-25 | 2015-06-30 | 2015-09-30
| 5129 | 2020-03-18 | Pencloe Wind Energy (PWEL) / North British Wind | Pencloe Wind Farm | Wind Onshore |  |  | 62.7 | n/a |  |  |  | 3.2857 | 19 | 125 | n/a | Appeal Granted | Awaiting Construction | Pencloe Wind Farm, Carsphairn Forest, North Of New Cumnock, Cumnock | Strathclyde | Scotland | Scotland | KA18 4A | 257641 | 610606 | Scottish Government (S36) | EC00003106 | WIN-190-4 |  |  |  |  | 2015-02-26 |  |  | 2016-12-06 |  |  | 2018-12-06 | 2018-12-06 |  |  |  | 2021-12-06
| 5130 | 2018-09-27 | Gamma Solar Limited | Allsetts Farm | Solar Photovoltaics |  |  | 6.81 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Allcett Farm, Broadwas, Worcester, Hereford & Worcester | Hereford and Worcester | West Midlands | England | WR6 5NS | 378481 | 256989 | Malvern Hills District Council | 15/00386/FUL | [5 empty] | 2015-03-20 | [6 empty] | 2015-08-14 |  |  |  | 2018-08-14
| 5131 | 2018-03-02 | NESF (formerly INRG Solar) | Land East Of Wadbrook Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of Wadbrook Farm, Wadbrook, Axminster, Devon | Devon | South West | England | EX13 7AS | 332531 | 101790 | East Devon District Council | 15/0645/MFUL | APP/U1105/W/16/3141816 |  |  |  |  | 2015-03-24 |  | 2015-11-05 | 2016-01-19 |  |  | 2016-04-15 | 2016-04-15 |  |  |  |  | 2017-01-15 | 2017-03-15
| 5132 | 2017-03-21 | Anesco | Land at Fell View Farm (Phase 1) | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Fell View Farm, Preston Road, Grimsargh, Preston, Lancashire | Lancashire | North West | England | PR2 5SD | 359231 | 433013 | Preston City Council | 06/2015/0218 | [5 empty] | 2015-03-16 | [6 empty] | 2015-07-16 |  |  |  | 2018-07-16 | 2016-01-15 | 2016-03-28
| 5135 | 2016-10-04 | Iceni Projects | Weylands Treatment Works | Anaerobic Digestion |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Weylands Treatment Works, Lyon Road, Walton-On-Thames, Surrey | Surrey | South East | England | KT12 3PB | 512940 | 165672 | Surrey County Council | EL/2015/0235 | [5 empty] | 2015-01-20 | 2016-07-06
| 5136 | 2018-03-02 | NESF (formerly Kronos Solar (KS SPV39)) | South of Henley Hall | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Henley Hall, Ludlow Road, Clee Hill | Shropshire | West Midlands | England | SY8 3HD | 354130 | 276090 | Shropshire Council | 15/01472/FUL | APP/L3245/W/15/3132946 |  |  |  |  | 2015-04-02 |  | 2015-08-12 | 2015-11-04 |  |  | 2016-06-08 | 2016-06-08 |  |  |  | 2019-06-08 | 2016-12-15 | 2017-03-17
| 5137 | 2017-06-23 | British Solar Renewables | Place Barton Farm | Solar Photovoltaics |  |  | 4.94 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Solar Array at, Place Barton Farm, Moreleigh, Totnes, Devon | Devon | South West | England | TQ9 7JN | 275813 | 52590 | South Hams District Council | 22/0848/15/F | [5 empty] | 2015-04-15 | [6 empty] | 2015-09-21 |  |  |  | 2018-09-21 | 2017-01-20 | 2017-03-31
| 5139 | 2017-02-02 | Green Hedge (BayWa r.e.) | Lower Stanley Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lower Stanley Farm, Gretton Fields, Gretton, Cheltenham, Gloucestershire | Gloucestershire | South West | England | GL54 5HQ | 400243 | 231268 | Tewkesbury Borough Council | 15/00350/FUL | [5 empty] | 2015-04-13 | [6 empty] | 2015-09-17 |  |  |  | 2018-09-17 | 2015-12-07 | 2016-03-23
| 5140 | 2016-03-22 | INRG Solar | Land Parcel North of Goddards | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Parcel North Of Goddards, Cuckfield Road, Ansty, Haywards Heath, West Sussex | West Sussex | South East | England | RH17 5AL | 528684 | 121331 | Mid Sussex District Council | DM/15/1518 | [5 empty] | 2015-04-07 | [6 empty] | 2015-08-07 |  |  |  | 2018-08-07 | 2016-02-05 | 2016-03-30
| 5142 | 2016-02-22 | Lightsource Renewable Energy | Ld At Lawrence End Park &, Dane Street | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Lawrence End Park &, Dane Street, To The E Of Birch Spring, Luton, Bedfordshire | Hertfordshire | Eastern | England | LU2 8PE | 513149 | 220690 | North Hertfordshire District Council | 15/00845/1 | [5 empty] | 2015-03-30 | [6 empty] | 2015-06-26 |  |  |  | 2018-06-26 | 2015-10-13 | 2015-12-19
| 5143 | 2017-05-03 | NESF (formerly INRG Solar) | Gravel Works, Wasing Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Gravel Works, Station Road, Woolhampton, Reading, Berkshire | Berkshire | South East | England | RG7 5S | 456246 | 164821 | West Berkshire Council | 15/00557/COMIND | APP/W0340/W/16/3141813 |  |  |  |  | 2015-03-20 |  | 2015-09-18 | 2016-02-04 |  |  | 2016-06-09 | 2016-06-09 |  |  |  |  | 2017-02-01 | 2017-03-01
| 5144 | 2015-09-02 | Earthworm | Long Lane Solar Farm | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Off, Long Lane, Watnall, Nottingham, Nottinghamshire | Nottinghamshire | East Midlands | England | NG16 1HY | 451522 | 346871 | Broxtowe Borough Council | 15/00174/FUL | [5 empty] | 2015-03-14 |  | 2015-06-17
| 5145 | 2017-03-01 | BlackRock | Drakelow Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At, Walton Road, Drakelow, Burton-On-Trent, Staffordshire | Derbyshire | East Midlands | England | DE15 9TY | 423474 | 319685 | South Derbyshire District Council | 9/2015/0256 | [5 empty] | 2015-04-08 | [6 empty] | 2015-06-24 |  |  |  | 2018-06-24 | 2016-01-12 | 2016-03-15
| 5146 | 2016-04-28 | Low Carbon | Land at Five Oaks Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Five Oaks Farm, Stane Street, Five Oaks, Billingshurst, West Sussex | West Sussex | South East | England | RH14 9AZ | 509860 | 128603 | Horsham District Council | DC/15/0501 | [5 empty] | 2015-03-27 | [6 empty] | 2015-08-19 |  |  |  | 2018-08-19 | 2015-10-01 | 2016-03-31
| 5147 | 2016-09-26 | Pegasus Group | Knolton Farmhouse Cheese Solar Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Knolton Farmhouse Cheese Ltd, Oswestry Road, Overton, Wrexham, Clwyd | Wrexham | Wales | Wales | LL13 0LG | 335887 | 340585 | Wrexham County Borough Council | P/2015/0249 | [5 empty] | 2015-04-02 | [6 empty] | 2015-06-01 |  |  |  | 2020-06-01 | 2015-12-01 | 2016-03-01
| 5148 | 2016-03-14 | Mercer Farming | Blakenhall Park Solar Farm | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Blakenhall Park, Bar Lane, Barton Under Needwood, Burton-On-Trent, Staffordshire | Staffordshire | West Midlands | England | DE13 8AJ | 417353 | 318116 | East Staffordshire Borough Council | P/2015/00401 | [5 empty] | 2015-04-01 | [6 empty] | 2015-06-06 |  |  |  | 2018-06-06 | 2015-08-10 | 2015-09-15
| 5149 | 2016-03-16 | British Solar Renewables | Grantham Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land south-east of Pasture Far, Allington Lane, Foston, Grantham | Lincolnshire | East Midlands | England | NG32 2JR | 485891 | 342307 | South Kesteven District Council | S15/0383 | [5 empty] | 2015-04-02 | [6 empty] | 2015-06-24 |  |  |  | 2018-06-24 | 2015-10-01 | 2015-12-15
| 5150 | 2016-01-11 | Suncredit UK/ Vogt solar | Agricultural Land at Trecastle | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Agricultural Land at Trecastel, Four Fields Centered on, Llanharry, Pontyclun, Mid Glamorgan | Rhondda Cynon Taff | Wales | Wales | CF72 9LY | 301218 | 181507 | Rhondda Cynon Taff County Borough Council | 15/0411/10 | [5 empty] | 2015-03-26 | [6 empty] | 2015-10-15 |  |  |  | 2020-10-15 | 2015-11-15 | 2015-12-15
| 5151 | 2015-08-05 | SRL | Parks of Kellour Wind Farm | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 | 125 | n/a | Planning Permission Refused | Application Refused | Parks of Kellour Farm, Methven, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH1 3RB | 297896 | 726020 | Perth and Kinross Council | 15/00445/FLL | [5 empty] | 2015-03-25 |  | 2015-07-15
| 5152 | 2017-05-26 | Lightsource Renewable Energy | Sharland Solar Farm | Solar Photovoltaics |  |  | 2.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at (Sharland Farm), Morchard Bishop, Crediton, Devon | Devon | South West | England | EX17 6SJ | 276119 | 106179 | Mid Devon District Council | 15/00537/MFUL | [5 empty] | 2015-03-31 | [6 empty] | 2015-07-08 |  |  |  | 2018-07-08 | 2016-12-19 | 2017-03-04
| 5153 | 2019-07-24 | Cornwall Council | Land near Ventonteague | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 98.5 | n/a | Planning Permission Expired | Planning Permission Expired | Land Off Ventonteague, St. Allen, Truro, Cornwall | Cornwall | South West | England | TR4 9QX | 182586 | 51229 | Cornwall Council | PA15/02972 | [5 empty] | 2015-03-27 | [6 empty] | 2015-10-26 |  |  |  | 2018-10-26
| 5156 | 2016-07-28 | Pearmat Solar | Short Hazel Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Short Hazel Farm Land At SK322, Manchester Lane, Hartshorne, Swadlincote, Derbyshire | Derbyshire | East Midlands | England | DE11 7BD | 433077 | 319883 | South Derbyshire District Council | 9/2015/0257 | [5 empty] | 2015-03-23 | [6 empty] | 2015-08-05 |  |  |  | 2018-08-05 | 2016-01-05 | 2016-03-02
| 5157 | 2015-12-22 | Lightsource Renewable Energy | Mill Hill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mill Hill Farm, Cornborough Road, Sheriff Hutton, York, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO60 6QL | 463388 | 467066 | Ryedale District Council | 15/00377/MFUL | [5 empty] | 2015-04-01 | [6 empty] | 2015-07-28 |  |  |  | 2018-07-28 | 2015-11-02 | 2015-12-17
| 5158 | 2018-07-05 | NESF (formerly Lark Energy) | Little Irchester, Higham Road Solar Farm | Solar Photovoltaics |  |  | 4.59 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Opposite, 7-11 Higham Road, Irchester, Wellingborough, Northamptonshire | Northamptonshire | East Midlands | England | NN29 7EZ | 491853 | 266543 | Wellingborough Borough Council | WP/15/00200/FUL | [5 empty] | 2015-04-01 | [6 empty] | 2015-07-08 |  |  |  | 2018-07-08 | 2016-02-01 | 2016-03-31
| 5160 | 2017-10-20 | Green Power Consultants | Field 279M North East of 15 Tealing | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Field 270M North East Of, 15, Tealing, Dundee, Tayside | Angus | Scotland | Scotland | DD4 0QZ | 341126 | 738331 | Angus Council | 15/00331/FULL | [5 empty] | 2015-04-20 | [6 empty] | 2015-11-03 |  |  |  | 2018-11-05
| 5161 | 2016-07-01 | Pegasus Group | Manton Manor Solar Farm | Solar Photovoltaics |  |  | 27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Manor Farm, Access Roads In Ma, Manton, Gainsborough, Lincolnshire | Humberside | Yorkshire and Humber | England | DN21 4JT | 492461 | 403284 | North Lincolnshire Council | PA/2015/0387 | APP/Y2003/W/16/3144447 |  |  |  |  | 2015-04-17 |  | 2015-11-18 | 2016-03-02 |  | 2016-06-28
| 5162 | 2016-05-20 | Lightsource Renewable Energy | Land North of Chiltern Greeen | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Chiltern Green F, Lawrence End Park North Herts, Chiltern Green, Luton, Bedfordshire | Bedfordshire | Eastern | England | LU2 9PN | 513581 | 219407 | Central Bedfordshire Council | CB/15/01204/FULL | [5 empty] | 2015-03-27 | [6 empty] | 2015-06-26 |  |  |  | 2018-06-26 | 2016-01-10 | 2016-03-10
| 5163 | 2017-12-04 | Greencoat Capital | Land off Moss Land (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off, Moss Lane, Bilsborrow, Preston, Lancashire | Lancashire | North West | England | PR3 0RU | 350124 | 439100 | Wyre Borough Council | 15/00260/LMAJ | [5 empty] | 2015-03-23 | [6 empty] | 2015-06-15 |  |  |  | 2018-06-15 | 2016-12-12 | 2017-03-30
| 5164 | 2017-05-03 | NESF (formerly Earthworm) | Hill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hill Farm, Hill Farm Lane, Duns Tew, Bicester, Oxfordshire | Oxfordshire | South East | England | OX25 6JJ | 445909 | 229497 | Cherwell District Council | 15/00570/F | [5 empty] | 2015-03-31 | [6 empty] | 2015-10-16 |  |  |  | 2018-10-16 | 2017-02-01 | 2017-03-01
| 5165 | 2016-08-31 | OST Energy | Padleywood Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Padleywood Farm, Evershill Lane, Morton, Alfreton, Derbyshire | Derbyshire | East Midlands | England | DE55 6HB | 441094 | 361390 | North East Derbyshire District Council | 15/00224/FL | [5 empty] | 2015-03-05 | [6 empty] | 2015-08-19 |  |  |  | 2018-08-19 | 2015-12-01 | 2016-03-29
| 5166 | 2020-03-18 | Gresham House | Pant y Maen | Wind Onshore |  |  | 14 | n/a |  |  |  | 2.5 | 8 | 102 | n/a | Appeal Granted | Awaiting Construction | Land Adjacent To Llyn Bran, Bylchau, Denbigh, Clwyd | Denbighshire | Wales | Wales | LL16 5 | 296775 | 358953 | Denbighshire County Council | 25/2015/0321 | APP/R6830/A/17/3171058 |  |  |  |  | 2015-03-27 |  | 2016-09-14 | 2017-04-20 |  |  | 2018-01-11 | 2018-01-11
| 5167 | 2016-07-18 | Pfalz Solar | Tiln Farm Retford (extension) | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of, Tiln Lane, Retford, Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 9JL | 471452 | 384014 | Bassetlaw District Council | 15/00228/FUL | [5 empty] | 2015-03-24 | [6 empty] | 2015-06-23 |  |  |  | 2018-06-23 | 2015-01-15 | 2015-04-01
| 5168 | 2016-08-31 | Elgar Middleton | Tower Hayes Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Tower Hayes Farm, Ellistown Lane, Stanton Under Bardon, Markfield, Leicestershire | Leicestershire | East Midlands | England | LE67 9TJ | 446236 | 309944 | Hinckley and Bosworth Borough Council | 15/00343/FUL | [5 empty] | 2015-03-20 | [6 empty] | 2015-07-10 |  |  |  | 2018-07-10 | 2016-01-17 | 2016-05-17
| 5169 | 2016-08-18 | Lightsource Renewable Energy | Land West of Sheriffhales (resubmission) | Solar Photovoltaics |  |  | 8.17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land west of Sheriffhales, 16 Sandy Lane, Sheriffhales, Shifnal, Shropshire | Shropshire | West Midlands | England | TF11 8QZ | 375171 | 312179 | Shropshire Council | 15/01366/FUL | [5 empty] | 2015-03-27 | [6 empty] | 2015-07-01 |  |  |  | 2018-07-01 | 2015-10-01 | 2015-12-16
| 5170 | 2016-04-04 | Lightsource Renewable Energy | Land At Hornacott (resubmission) | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land At Hornacott, West Ditchin, North Tamerton, Launceston, Cornwall | Cornwall | South West | England | PL15 9RN | 229817 | 94674 | Cornwall Council | PA15/03083 | APP/D0840/W/15/3134592 |  |  |  |  | 2015-04-01 |  | 2015-06-05 | 2015-10-07 |  | 2016-03-21
| 5173 | 2020-06-25 | Renewable Energy Systems (RES) | Jack's Lane Solar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | land west of the B1454 | Norfolk | Eastern | England |  | 580210 | 333880 | King's Lynn and West Norfolk Borough Council | 15/01701/FM | [5 empty] | 2015-10-22 | [6 empty] | 2016-02-11 |  |  |  | 2019-02-11
| 5174 | 2015-07-20 | Wilson Renewables | Bankend Wind Farm (extension) | Wind Onshore |  |  | 10.2 | n/a |  |  |  |  | 3 | 136 | n/a | Planning Application Submitted | Application Submitted | Bankend Rig II Wind Farm Drumclog | Strathclyde | Scotland | Scotland |  | 264000 | 633700 | South Lanarkshire Council | EK/15/0217 | [5 empty] | 2015-06-11
| 5181 | 2020-01-02 | Forsa (formerly 2020 Renewables/ Buccleuch) | Lowther Hills (North Lowther Energy Initiative) | Wind Onshore |  |  | 147 | n/a |  |  |  | 4.2 | 30 | 149 | n/a | Appeal Lodged | Application Submitted | near Wanlockhead and the Muirkirk and North Lowther Uplands special protection area | Dumfries and Galloway | Scotland | Scotland |  | 283464 | 615138 | Scottish Government (S36) | ECU00000426 | WIN-170-2004 |  |  |  |  | 2017-06-12 |  |  | 2018-12-07
| 5182 | 2016-08-24 | Lightsource Renewable Energy | Land Adjacent Claypits Farm (a) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent Claypits Farm, Maldon Road, Birch, Colchester, Essex | Essex | Eastern | England | CO2 0NU | 593319 | 219800 | Colchester Borough Council | 150614 | [5 empty] | 2015-03-27 | [6 empty] | 2015-06-30 |  |  |  | 2018-06-30 | 2015-10-22 | 2015-12-23
| 5183 | 2016-03-04 | Lightsource SPV 186 (community owned) | Land Adjacent Claypits Farm (b) (Birch Estate) | Solar Photovoltaics |  |  | 2.26 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent Claypits Farm, Maldon Road, Birch, Colchester, Essex | Essex | Eastern | England | CO2 0NU | 593289 | 219984 | Colchester Borough Council | 150614 | [5 empty] | 2015-03-27 | [6 empty] | 2015-06-30 |  |  |  | 2018-06-30 |  | 2016-02-26
| 5184 | 2018-04-30 | Lightsource Renewable Energy | Land at Dobbs Estate | Solar Photovoltaics |  |  | 21.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land at Dobbs Estate, Tongue Loanen Road, Carrickfergus | Co. Antrim | Northern Ireland | Northern Ireland | BT38 9BU | 157541 | 545333 | Northern Ireland Planning Service | V/2015/0038/F | [5 empty] | 2015-03-25 | [6 empty] | 2016-03-14 |  |  |  | 2021-03-13
| 5186 | 2017-12-21 | Awre Peninsula Farmers' Community Solar Scheme | Awre Penisular Farmer's Community Solar Scheme | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Guy Hall Farm, Northington Lane, Awre, Newnham | Gloucestershire | South West | England | GL14 1EL | 371017 | 208537 | Forest of Dean District Council | P0664/15/FUL | [5 empty] | 2015-06-04 |  | 2016-01-19
| 5187 | 2018-10-02 | The Energy Workshop | Hill of Lybster (Wind Turbine - Extension) | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 99.5 | n/a | Planning Permission Refused | Application Refused | Land 200M N Of, 3 Lybster Road, Forss, Thurso, Highlands | Highland | Scotland | Scotland | KW14 7YA | 302481 | 969366 | Highland Council | 17/04934/FUL | [5 empty] | 2017-10-20 |  | 2018-08-16
| 5188 | 2020-05-28 | Hoolan Energy | Costa Head Wind Farm | Wind Onshore |  |  | 16.32 | n/a |  |  | 16.3 | 4.08 | 5 | 125 | n/a | Appeal Granted | Awaiting Construction | Costa Head, on the north coast of Orkney Mainland | Orkney Islands | Scotland | Scotland | KW17 2NP | 329920 | 1029790 | Orkney Islands Council | 16/580/TPPMAJ | PPA-330-2022 |  |  |  |  | 2016-12-09 |  | 2018-09-21 | 2018-10-08 |  |  | 2019-04-18 | 2019-04-18 |  |  |  | 2022-04-18
| 5190 | 2017-12-21 | BNRG Renewables | Fferm Bryn Bachau | Solar Photovoltaics |  |  | 4.42 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fferm Bryn Bachau, Chwilog, Pwllheli | Gwynedd | Wales | Wales | LL53 6RQ | 243136 | 336998 | Gwynedd Council | C15/0751/41/LL | [5 empty] | 2015-07-23 | [6 empty] | 2015-09-30 |  |  |  | 2020-09-30 | 2016-01-12 | 2016-03-29
| 5198 | 2019-11-01 | Hoolan Energy/ Hesta Head Wind Farm | Hesta Head Wind Farm | Wind Onshore |  |  | 20.4 | n/a |  |  | 20.4 | 4 | 5 | 125 | n/a | Appeal Granted | Awaiting Construction | Hesta Head (Land Near), South Ronaldsay Windwick, Kirkwall, Orkney Isles | Orkney Islands | Scotland | Scotland | KW15 1HQ | 346223 | 988155 | Orkney Islands Council | 17/083/TPPMAJ | PPA-330-2023 |  |  |  |  | 2017-03-06 |  | 2018-09-21 | 2018-10-08 |  |  | 2019-04-18 | 2019-04-18 |  |  |  | 2022-04-18
| 5199 | 2017-04-04 | Greencoat Capital | Scottow Moor - RAF Coltishall Solar Farm (Phase 2) | Solar Photovoltaics |  |  | 17.9 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Operational | Operational | Former RAF Coltishall, Coltishall Airfield, Filby Road, Norwich, Norfolk | Norfolk | Eastern | England |  | 626626 | 322780 | North Norfolk District Council | PF/14/1334 | [5 empty] | 2014-10-09 | [6 empty] | 2014-12-23 |  |  |  |  | 2016-01-25 | 2016-03-29
| 5200 | 2018-04-19 | Levenseat | Levenseat EfW | Advanced Conversion Technologies |  |  | 12.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | By Forth, Lanark, Lanarkshire | West Lothian | Scotland | Scotland |  | 294854 | 655234 | West Lothian Council | 0528/FUL/10 | [5 empty] | 2010-08-03 | [6 empty] | 2010-12-01 |  |  |  |  | 2015-07-01 | 2017-12-15
| 5201 | 2016-05-27 | Lightsource Renewable Energy | Land north of 20 Knockcairn Road | Solar Photovoltaics |  |  | 4.12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land north of 20 Knockcairn Road, Crumlin | Co. Antrim | Northern Ireland | Northern Ireland |  | 131047 | 531970 | Northern Ireland Planning Service | LA03/2015/0021/F | [5 empty] | 2015-03-30 |  | 2016-05-23
| 5202 | 2018-05-30 | Canadian Solar | West Carclaze Solar Farm | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At West Carclaze, Carluddon, St Austell | Cornwall | South West | England |  | 201930 | 55161 | Cornwall Council | PA15/03922 | [5 empty] | 2015-05-28 | [6 empty] | 2015-08-28 |  |  |  | 2018-08-28 | 2017-12-29 | 2017-03-29
| 5203 | 2016-06-29 | Power Capital | Doagh Road Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Lands west of Doagh Road, Newtownabbey | Co. Antrim | Northern Ireland | Northern Ireland |  | 146074 | 540877 | Northern Ireland Planning Service | LA03/2015/0025/F | 2015/A0223 |  |  |  |  | 2015-03-30 |  | 2015-10-22 | 2016-02-18 | 2016-06-01
| 5204 | 2017-05-03 | NESF (formerly INRG Solar) | Flixborough Industrial Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent to Flixborough Industrial Estate, Stather Road, Flixborough | Humberside | Yorkshire and Humber | England |  | 486438 | 414521 | North Lincolnshire Council | PA/2015/0434 | APP/Y2003/W/16/3142032 |  |  |  |  | 2015-04-08 |  | 2015-11-18 | 2016-01-20 |  |  | 2016-10-11 | 2016-10-11 |  |  |  |  | 2017-03-01 | 2017-03-01
| 5205 | 2019-06-11 | Power Capital | Red Brae | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Lands east and south of no. 51 Red Brae Road, Carrickfergus | Co. Antrim | Northern Ireland | Northern Ireland |  | 155136 | 546044 | Northern Ireland Planning Service | LA02/2015/0017/F | [5 empty] | 2015-03-30 | [6 empty] | 2015-10-13 |  |  |  | 2020-10-13
| 5206 | 2016-06-17 | Durham County Council | Comeleon House Solar PV Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land to South of Comeleon House, Tanfield Lea Industrial Estate, North Stanley | County Durham | North East | England | DH9 9NX | 419112 | 554227 | Durham County Council | DM/15/01366/FPA | [5 empty] | 2015-05-01 | [6 empty] | 2015-06-03 |  |  |  | 2018-06-03
| 5207 | 2016-06-17 | Canadian Solar | Land adjacent to Church Road | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent to Church Road and the M49, Severn Beach, Bristol | Gloucestershire | South West | England | BS35 4NL | 354510 | 184911 | South Gloucestershire Council | PT15/1586/F | [5 empty] | 2015-04-13 | [6 empty] | 2015-09-01 |  |  |  | 2018-09-01 | 2015-02-28 | 2016-03-31
| 5208 | 2016-10-26 | Clean Earth Energy | Lower Ninestones Solar Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Lower Ninestones Mica Dam, Carbean, St Austell | Cornwall | South West | England | PL26 8XG | 200846 | 56100 | Cornwall Council | PA15/03935 | [5 empty] | 2015-05-28 | [6 empty] | 2015-08-28 |  |  |  | 2018-08-28
| 5210 | 2019-06-20 | D2Smart Projects | Smart Systems | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Smart Systems Ltd, Arnolds Way, Yatton | Somerset | South West | England | BS49 4QN | 341752 | 166241 | North Somerset Council | 15/P/0957/F | [5 empty] | 2015-04-27 | [6 empty] | 2015-09-28 |  |  |  | 2018-09-28
| 5211 | 2020-03-18 | D2Smart Projects | Smart Systems | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 | 77 | n/a | Planning Permission Granted | Awaiting Construction | Smart Systems Ltd, Arnolds Way, Yatton | Somerset | South West | England | BS49 4QN | 341752 | 166241 | North Somerset Council | 15/P/0957/F | [5 empty] | 2015-04-27 | [6 empty] | 2015-09-28 |  |  |  | 2018-09-28
| 5212 | 2016-05-20 | Solarig | Lady Hole Farm | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lady Hole Farm, Lady Hole Lane, Yeldersley | Derbyshire | East Midlands | England | DE6 1LR | 420840 | 345776 | Derbyshire Dales District Council | 15/00279/FUL | [5 empty] | 2015-04-22 | [6 empty] | 2015-07-23 |  |  |  | 2018-07-23 | 2016-01-08 | 2016-03-30
| 5214 | 2016-07-25 | Renesola (community owned) | Bransholme Solar CIC | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Carlam Hill Farm, East of Cumbrian Way, Kingston Upon Hull | Humberside | Yorkshire and Humber | England | HU7 5YX | 511000 | 436000 | Kingston upon Hull City Council | 15/00511/FULL | [5 empty] | 2015-04-23 | [6 empty] | 2015-06-12 |  |  |  | 2018-06-12 | 2016-01-18 | 2016-06-24
| 5215 | 2015-08-05 | Rochester 003 /Elgar Middleton | Preston Deanery | Solar Photovoltaics |  |  | 4.54 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Preston Lodge Farm, Houghton Road, Preston Deanery | Northamptonshire | East Midlands | England | NN7 2DS | 479687 | 256709 | South Northamptonshire Council | S/2015/0880/MAF | [5 empty] | 2015-04-14 |  | 2015-07-02
| 5218 | 2016-12-15 | Photon Energy | Land at Christ’s Hospital School | Solar Photovoltaics |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the south of Christ's Hospital School, Two Mile Ash, Horsham | West Sussex | South East | England | RH13 0YP | 514678 | 127626 | Horsham District Council | DC/15/0667 | [5 empty] | 2015-04-14 | [6 empty] | 2015-09-09 |  |  |  | 2018-09-09 | 2016-02-26 | 2015-12-15
| 5219 | 2017-02-01 | Hill Power | Land North East And North West Of Shanmaghry | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 | 77 | n/a | Planning Application Withdrawn | Application Withdrawn | Lds North East And North W Of,, Shanmaghry, Pomeroy, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 2PA | 82555 | 547553 | Northern Ireland Planning Service | M/2015/0092/F | [5 empty] | 2015-02-20 | 2016-12-15
| 5221 | 2016-03-14 | Renewable Energy Systems (RES) | Swift Wind Farm | Wind Onshore |  |  | 8 | n/a |  |  |  | 2 | 4 | 126.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Cestersover Farm, Lutterworth Road, Churchover, Pailton, Rugby, Warwickshire | Warwickshire | West Midlands | England | CV23 0QP | 451914 | 282104 | Rugby Borough Council | R15/0908 | [5 empty] | 2015-04-22 | 2016-03-14
| 5222 | 2015-05-29 | ABO Wind | Gruggandoo Wind Farm | Wind Onshore |  |  | 39.6 | n/a |  |  |  | 3.3 | 12 | 125 | n/a | Planning Application Submitted | Application Submitted | Lands approximately 650m south, 40 Mullaghgariff Road, Hilltown, Newry | Co. Down | Northern Ireland | Northern Ireland | BT34 5LT | 129125 | 483679 | Northern Ireland Planning Service | P/2015/0218/F | [5 empty] | 2015-03-31
| 5223 | 2020-03-31 | St. Modwen Developments | Baglan Bay Solar Farm - Phase 2 | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land adjacent to, Central Aven, Baglan Energy Park, Baglan, Phase 1, Port Talbot, West Glamorgan | Neath Port Talbot | Wales | Wales | SA12 7AX | 273890 | 192702 | Neath Port Talbot County Borough Council | P2015/0304 | [5 empty] | 2015-05-06 | 2020-03-11
| 5224 | 2017-01-16 | Sovereign Energy Partners | Creswell Solar Park (resubmission) | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The North And, Frithwo, Elmton, South Of Sewage Treatment Plan, Worksop, Nottinghamshire | Derbyshire | East Midlands | England | S80 4LT | 452973 | 373493 | Bolsover District Council | 15/00173/FUL | [5 empty] | 2015-04-20 | [6 empty] | 2015-07-03 |  |  |  | 2018-07-03 | 2016-02-19 | 2016-03-23
| 5225 | 2017-10-04 | Pollington Solar | Pollington Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North East Of Quarryside, Heck & Pollington Lane, Great Heck, Goole, Humberside | Humberside | Yorkshire and Humber | England | DN14 0DA | 460418 | 421013 | East Riding of Yorkshire Council | 15/01315/STPLF | [5 empty] | 2015-04-27 | [6 empty] | 2015-07-17 |  |  |  | 2018-07-17 | 2017-01-23 | 2017-03-23
| 5226 | 2017-12-20 | NextEnergy Solar Fund | Land NW Of Pickhill Bridge Farm | Solar Photovoltaics |  |  | 3.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land NW Of Pickhill Bridge Far, Holt Road, Cross Lanes, Wrexham, Clwyd | Wrexham | Wales | Wales | LL13 0UA | 338023 | 347831 | Wrexham County Borough Council | P/2015/0287 | [5 empty] | 2015-04-13 | [6 empty] | 2015-07-31 |  |  |  | 2020-07-31 | 2016-12-19 | 2017-03-24
| 5227 | 2020-02-04 | Community Windpower | Sanquhar 'Six' Community Wind Farm | Wind Onshore |  |  | 19.8 | n/a |  |  |  | 3.3 | 6 | 130 | n/a | Planning Permission Granted | Awaiting Construction | Magheughan Rig, Dalmet Hill & , Tynron, Sanquhar, Thornhill, Dumfries & Galloway | Dumfries and Galloway | Scotland | Scotland | DG3 4JY | 268285 | 606841 | Dumfries and Galloway Council | 15/P/3/0166 | [5 empty] | 2015-04-27 | [6 empty] | 2017-11-15 |  |  |  | 2020-11-15
| 5228 | 2015-08-05 | BE Renewables | Back Lane Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The West Of, Back Lane, Aughton, Ormskirk, Lancashire | Lancashire | North West | England | L39 6SX | 333519 | 417158 | West Lancashire Borough Council | 2015/0424/FUL | [5 empty] | 2015-04-29 | 2015-07-09
| 5229 | 2016-11-23 | SBC Renewables | Moneystone Quarry Solar Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Moneystone Quarry, Cheadle Road, Oakamoor, Stoke-On-Trent, Staffordshire | Staffordshire | West Midlands | England | ST10 2DZ | 404572 | 346224 | Staffordshire Moorlands District Council | SMD/2015/0220 | [5 empty] | 2015-04-15 | [6 empty] | 2015-07-22 |  |  |  | 2018-07-22 | 2016-07-01 | 2016-11-21
| 5230 | 2015-05-28 | Coleford Energy | Pingry Farm - Phase 2 | Solar Photovoltaics |  |  | 3.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Pingry Farm, Pingry Lane, Milkwall, Coleford | Gloucestershire | South West | England | GL16 8QD | 357121 | 209434 | Forest of Dean District Council | P1418/12/FUL | [5 empty] | 2013-03-06 | [6 empty] | 2013-04-11 |  |  |  |  | 2015-01-01 | 2015-03-25
| 5231 | 2015-05-28 | Norfolk Renewables | Kenninghall Solar / Hazeldick Solar | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the west of Kenninghall | Norfolk | Eastern | England | NR16 2EH | 603420 | 285869 | Breckland Council | 3PL/2012/1088/F | APP/F2605/W/13/2211560 |  |  |  |  | 2012-10-17 |  | 2013-10-03 | 2014-01-10 |  |  | 2014-09-24 | 2014-09-24 |  |  |  |  | 2015-01-01 | 2015-03-31
| 5232 | 2015-05-28 | Elgin Energy EsCo | Wogaston Solar Farm | Solar Photovoltaics |  |  | 5.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Wogaston Farm | Pembrokeshire | Wales | Wales | SA71 5AA | 191197 | 200960 | Pembrokeshire County Council | 12/0906/PA | APP/N6845/A/13/2203220 |  |  |  |  | 2012-12-21 |  | 2013-06-27 | 2013-11-27 |  |  | 2014-04-16 | 2014-04-16 |  |  |  |  | 2015-01-01 | 2015-03-17
| 5233 | 2017-07-03 | John Laing Environmental Assets Group | Crugmore Farm | Solar Photovoltaics |  |  | 6.375 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Crugmore Farm, Penparc, Cardigan | Dyfed | Wales | Wales | SA43 1RD | 220569 | 246960 | Ceredigion County Council | A130807 | [5 empty] | 2013-10-25 | [6 empty] | 2014-02-24 |  |  |  | 2017-02-24 | 2015-01-01 | 2015-03-25
| 5234 | 2015-05-29 | MTS Rydon Solar | Rydon Farm | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Rydon Farm, Ogwell, Teignbridge | Devon | South West | England | TQ12 6DB | 284136 | 68721 | Teignbridge District Council | 13/02129/MAJ | [5 empty] | 2013-07-31 | [6 empty] | 2014-01-20 |  |  |  |  | 2014-12-01 | 2015-03-31
| 5241 | 2017-04-20 | TGC Renewables | Solar farm at land at The Willows, Uttoxeter | Solar Photovoltaics |  |  | 6.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South East Of The Willows, Dove Walk, Uttoxeter, Staffordshire | Staffordshire | West Midlands | England | ST14 8EJ | 410840 | 333181 | East Staffordshire Borough Council | P/2015/00434 | [5 empty] | 2015-04-15 | [6 empty] | 2015-07-24 |  |  |  | 2018-07-24 | 2016-12-12 | 2017-03-31
| 5242 | 2016-10-31 | Solstice Renewables | Highwood Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Highwood Lane, North Baddesley, Romsey, Hampshire | Hampshire | South East | England | SO51 9AF | 434775 | 121294 | Test Valley Borough Council | 15/01001/FULLS | [5 empty] | 2015-05-05 | [6 empty] | 2015-07-22 |  |  |  | 2018-07-22 | 2016-06-30 | 2016-08-31
| 5243 | 2016-01-18 | Bee Green Solar | Yorkley Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Yorkley Court, Yorkley Wood Road, Yorkley, Lydney, Gloucestershire | Gloucestershire | South West | England | GL15 4TY | 363118 | 205377 | Forest of Dean District Council | P0278/15/FUL | [5 empty] | 2015-05-11 | [6 empty] | 2015-06-30 |  |  |  | 2018-06-30 | 2015-11-12 | 2015-12-18
| 5244 | 2016-09-20 | Foresight Group (TGC Renewables) | Solar Farm at Fields Farm (Phase 1) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Fields Farm, Southam | Warwickshire | West Midlands | England | CV47 2HD | 440365 | 260913 | Stratford on Avon District Council | 15/00767/FUL | [5 empty] | 2015-03-16 | [6 empty] | 2015-06-29 |  |  |  | 2018-06-29 | 2016-01-04 | 2016-03-23
| 5247 | 2019-05-31 | FCC Environment | Millerhill EfW (resubmission) | EfW Incineration |  |  | 12.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Former Millerhill Marshalling, Millerhill, Whitehill Mains Road, Dalkeith, Lothian | Midlothian | Scotland | Scotland | EH22 1RZ | 332352 | 670580 | Midlothian Council | 15/00285/DPP | [5 empty] | 2015-03-31 | [6 empty] | 2015-09-17 |  |  |  |  | 2016-10-06 | 2019-05-01
| 5248 | 2019-11-26 | Hill Power | Development SE of Flush Road | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 | 100 | n/a | Appeal Granted | Awaiting Construction | 630 mts east/south east of, 43 Flush Road, Ballysillan Upper, Belfast, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT14 8SJ | 142929 | 534790 | Northern Ireland Planning Service | Z/2015/0010/F | 2014/A0278 |  |  |  |  | 2015-01-15 |  |  | 2015-03-26 |  |  | 2015-11-04 | 2015-11-04 |  |  |  | 2020-11-04
| 5253 | 2017-02-02 | Vortex (formerly SunEdison) | Land at Beech Farm | Solar Photovoltaics |  |  | 4.55 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Beech Farm, Stanton, Fitzwarren, Swindon | Wiltshire | South West | England |  | 418335 | 189653 | Swindon Borough Council | S/LDO/15/1133 | [5 empty] | 2015-07-06 | [6 empty] | 2015-08-28 |  |  |  | 2018-08-28 | 2016-05-01 | 2016-02-17
| 5255 | 2020-01-31 | Wessex Solar Energy | West Holcombe | Solar Photovoltaics |  |  | 5.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at NGR 299298 125070 (East Of Bowdens Lane) Shillingford Devon | Devon | South West | England |  | 298519 | 125428 | Mid Devon District Council | 14/01452/MFUL | APP/Y1138/W/14/3001908 |  |  |  |  | 2014-08-28 |  |  | 2015-01-20 |  |  | 2015-06-24 | 2015-06-24 |  |  |  | 2018-06-24
| 5256 | 2015-06-29 | JBM Solutions | Aberporth Solar Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Aberporth Solar Farm B4333 Aberporth, Cardigan | Ceredigion | Wales | Wales |  | 224624 | 250331 | Ceredigion County Council | A140417 | [5 empty] | 2014-06-12 | [6 empty] | 2014-12-24 |  |  |  | 2017-12-24 | 2015-01-15 | 2015-03-24
| 5257 | 2015-09-30 | Kronos Solar | Hoplass Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Hoplass Farm, Roscrowther | Pembrokeshire | Wales | Wales | SA71 5TG | 191770 | 201076 | Pembrokeshire County Council | 12/1000/PA | [5 empty] | 2013-02-06 | [6 empty] | 2014-04-16 |  |  |  | 2017-04-16 | 2015-01-01 | 2015-03-13
| 5258 | 2015-06-29 | FEL Solar | Chelveston Renewable Energy Park - Solar Extension | Solar Photovoltaics |  |  | 19.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Chelveston Renewable Energy Park, Chelveston Airfield, Chelveston | Northamptonshire | East Midlands | England | NN9 6AR | 500422 | 268346 | East Northamptonshire Council | 14/01777/FUL | [5 empty] | 2014-06-23 | [6 empty] | 2014-10-17 |  |  |  | 2017-10-17 | 2014-11-15 | 2015-03-20
| 5259 | 2016-07-01 | Solar Century | Grove Solar Park (Phase 1) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Grove Solar Park, Land west of A3057 (Romsey Road), Romsey | Hampshire | South East | England | SO51 9LH | 436685 | 118373 | Test Valley Borough Council | 14/01826/FULLS | APP/C1760/W/15/3010697 |  |  |  |  | 2014-07-31 |  | 2014-12-24 | 2015-04-23 |  |  | 2015-09-04 | 2015-09-04 |  |  |  | 2018-09-04 | 2016-05-01 | 2016-03-30
| 5260 | 2018-09-17 | Lark Energy | Habertoft, Solar Farm South of Low Lane | Solar Photovoltaics |  |  | 10.39 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land south of, Habertoft Lane, Habertoft, Alford | Lincolnshire | East Midlands | England | LN13 9NU | 550968 | 368562 | East Lindsey District Council | S/208/01064/15 | [5 empty] | 2015-06-09 | [6 empty] | 2015-09-03 |  |  |  | 2018-09-03
| 5261 | 2017-03-21 | Anesco | Fell View Farm (Phase 2) | Solar Photovoltaics |  |  | 2.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Fell View Farm, Preston Road, Grimsargh, Preston | Lancashire | North West | England | PR2 5SD | 359015 | 432981 | Preston City Council | 06/2015/0288 | [5 empty] | 2015-04-13 | [6 empty] | 2015-08-04 |  |  |  | 2018-08-04 | 2016-01-15 | 2016-03-15
| 5263 | 2017-02-27 | REPOWER Balcombe & Chiddinglye Solar Park | Land At Chiddinglye Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Chiddinglye Farm, Selsfield Road, West Hoathly, East Grinstead | West Sussex | South East | England | RH19 4QS | 535734 | 123903 | Mid Sussex District Council | DM/15/2460 | [5 empty] | 2015-06-17 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30 | 2015-12-30 | 2016-03-30
| 5264 | 2016-04-13 | Wirsol Energy/Island Green Power | Land of coal pit lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off, Coal Pit Lane, Gisburn, Clitheroe | Lancashire | North West | England | BB7 4JH | 383048 | 447960 | Ribble Valley Borough Council | 3/2015/0459 | [5 empty] | 2015-05-22 | [6 empty] | 2015-08-21 |  |  |  | 2018-08-21 | 2016-01-11 | 2016-03-31
| 5265 | 2018-09-26 | Raker Farms | Huntingfield Solar Farm | Solar Photovoltaics |  |  | 4.35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Huntingfield Farm, Mill Street, Bradenham, Thetford | Norfolk | Eastern | England | IP25 7QN | 592794 | 308739 | Breckland Council | 3PL/2015/0699/F | [5 empty] | 2015-06-18 | [6 empty] | 2015-09-22 |  |  |  | 2018-09-22 | 2018-06-15 | 2018-07-15
| 5266 | 2017-05-02 | Rockfire Capital | Astley Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Astley Farm, Six Ashes, Alveley, Bridgnorth | Shropshire | West Midlands | England | WV15 6ER | 378096 | 285524 | Shropshire Council | 15/02095/FUL | [5 empty] | 2015-05-14 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30 | 2015-12-09 | 2016-03-15
| 5267 | 2016-06-15 | Haymaker Energy | Majors Hill/Turners Hill Solar Farm | Solar Photovoltaics |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Parcel At 532484 136274 M, Turners Hill Road, Crawley Down, Crawley | West Sussex | South East | England | RH10 4 | 532485 | 136270 | Mid Sussex District Council | DM/15/1949 | [5 empty] | 2015-06-15 | [6 empty] | 2015-10-02 |  |  |  | 2018-10-02 | 2016-01-08 | 2016-03-15
| 5269 | 2020-05-27 | First Renewable Developments | Wold Cottage Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Wold Cottage Farm, Wold Road, Burton Latimer, Kettering | Northamptonshire | East Midlands | England | NN15 5PJ | 491293 | 275006 | Kettering Borough Council | KET/2015/0446 | [5 empty] | 2015-06-01 | [6 empty] | 2015-07-31 |  |  |  | 2020-07-31
| 5270 | 2019-12-04 | TGC Renewables | Land north of Bryn Lane | Solar Photovoltaics |  |  | 6.37 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land North Of, Bryn Lane, Ridley Wood, Holt, Wrexham | Wrexham | Wales | Wales | LL13 9YB | 338726 | 351130 | Wrexham County Borough Council | P/2015/0397 | APP/H6955/A/16/3147773 |  |  |  |  | 2015-05-27 |  | 2015-12-07 | 2016-06-06 |  |  | 2016-09-13 | 2016-09-13
| 5271 | 2018-02-01 | Green Switch Solutions - Liquidated | Land South Of Bryn Cyrnau Isaf (resubmission) | Solar Photovoltaics |  |  | 5.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of, Bryn Cyrnau Isaf, Cwmffrwd, Carmarthen | Carmarthenshire | Wales | Wales | SA31 2LS | 242953 | 217478 | Carmarthenshire County Council | W/31690 | [5 empty] | 2015-03-09 | [6 empty] | 2015-06-09 |  |  |  |  | 2017-01-31 | 2017-03-31
| 5272 | 2020-05-27 | First Renewable Developments | Welby Road Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Fields 7329, 8218 And Top Fiel, 4900, 7900 Welby Road, Asfordby Hill, Melton Mowbray | Leicestershire | East Midlands | England | LE14 3R | 471883 | 321022 | Melton Borough Council | 15/00430/FUL | [5 empty] | 2015-06-11 | [6 empty] | 2015-09-10 |  |  |  | 2018-09-10
| 5273 | 2016-06-16 | Primrose Solar | Ashby Solar Farm (a) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The East Side B4116, M, Ashby De La Zouch And, North Of Measham Rd,Packington, Ashby-De-La-Zouch | Leicestershire | East Midlands | England | LE65 1W | 434859 | 314016 | North West Leicestershire District Council | 15/00499/FULM | [5 empty] | 2015-05-26 | [6 empty] | 2015-09-09 |  |  |  | 2018-09-09 | 2015-12-12 | 2016-03-12
| 5274 | 2020-05-27 | First Renewable Developments | Latimer Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Latimer Solar Park, Wold Road, Burton Latimer, Kettering | Northamptonshire | East Midlands | England | NN15 5PJ | 491204 | 274822 | Kettering Borough Council | KET/2015/0445 | [5 empty] | 2015-06-01 | [6 empty] | 2015-08-03 |  |  |  | 2020-08-03
| 5275 | 2018-09-25 | Solstice Renewables | Ashby Solar Farm (b) | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land To The East Of B41, Meash, Packington, Ashby De La Zouch And North Of, Ashby-De-La-Zouch | Leicestershire | East Midlands | England | LE65 1W | 434859 | 314016 | North West Leicestershire District Council | 15/00500/FULM | [5 empty] | 2015-05-26 | [6 empty] | 2015-09-09 |  |  |  | 2018-09-09
| 5276 | 2020-01-24 | Rock Fire Energy | Cirencester Solar Farm | Solar Photovoltaics |  |  | 26.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land Parcel East Of, Wilpit Lane, Preston, Cirencester | Gloucestershire | South West | England | GL7 5 | 405507 | 201350 | Cotswold District Council | 15/01923/FUL | [5 empty] | 2015-05-08 | [6 empty] | 2015-09-17 |  |  |  | 2018-09-17
| 5277 | 2017-04-24 | Infinergy/ Muirhall Energy | Burton Wold Wind Farm South | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.75 | 3 | 136.5 | n/a | Operational | Operational | Land at Glendon Farm, Burton Latimer, Kettering | Northamptonshire | East Midlands | England | NN15 5 | 491602 | 273681 | Kettering Borough Council | KET/2014/0861 | [5 empty] | 2015-02-18 | [6 empty] | 2015-03-27 |  |  |  |  | 2016-09-15 | 2017-04-24
| 5278 | 2015-08-05 | Kronos Solar | Chadwicks Farm (resubmission) | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land Near Chadwick''s Farm, Garford, Abingdon | Oxfordshire | South East | England | OX13 5PH | 441332 | 194892 | Vale of White Horse District Council | P15/V0169/FUL | APP/V3120/W/15/3029775 |  |  |  |  | 2015-01-28 |  | 2015-04-29 | 2015-06-18 |  | 2015-11-23
| 5279 | 2019-03-29 | Whittington Hill Solar | Land North Of, Whittington Hil | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land North Of, Whittington Hil, Whittington, Oxborough Lane, King's Lynn | Norfolk | Eastern | England | PE33 9TE | 573519 | 299217 | King's Lynn and West Norfolk Borough Council | 15/00866/FM | [5 empty] | 2015-06-08 | [6 empty] | 2015-10-09 |  |  |  | 2018-10-09
| 5280 | 2020-05-27 | First Renewable Developments | Windmill Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Windmill Farm, Wold Road, Burton Latimer, Kettering, Northamptonshire | Northamptonshire | East Midlands | England | NN15 5PJ | 491204 | 274882 | Kettering Borough Council | KET/2015/0438 | [5 empty] | 2015-06-01 | [6 empty] | 2015-07-30 |  |  |  | 2020-07-30
| 5281 | 2019-12-04 | TGC Renewables/NESF | Land south of Francis Land | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land South Of, Francis Lane, Holt, Wrexham, Clwyd | Wrexham | Wales | Wales | LL13 9Y | 338997 | 351449 | Wrexham County Borough Council | P/2015/0396 | APP/H6955/A/16/3147767 |  |  |  |  | 2015-05-27 |  | 2015-12-07 | 2016-06-06 |  |  | 2016-09-13 | 2016-09-13
| 5282 | 2016-12-22 | Solar Power Inc UK Services/SPI China (HK) | Land South of Knock Lane | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The South of, Knock Lane, Blisworth, Northampton, Northamptonshire | Northamptonshire | East Midlands | England | NN7 3DA | 473801 | 252253 | South Northamptonshire Council | S/2015/1233/MAF | APP/Z2830/W/15/3138458 |  |  |  |  | 2015-06-05 |  | 2015-09-24 | 2015-11-23 |  |  | 2016-04-21 | 2016-04-21 |  |  |  |  | 2016-07-01 | 2016-10-01
| 5283 | 2015-12-02 | Solar Planning | Land South of Shothanger Works | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Near Shothanger Works, Shothanger Lane, Wootton St Lawrence, Basingstoke, Hampshire | Hampshire | South East | England | RG23 8TH | 460061 | 154352 | Basingstoke and Deane Borough Council | 15/01378/FUL | [5 empty] | 2015-06-11 |  | 2015-11-19
| 5284 | 2019-06-12 | Rochdale Metropolitan Borough Council | Chamber House | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Chamber House Farm Off, Rochdale Road East, Heywood, Greater Manchester | Greater Manchester | North West | England | OL10 1R | 385998 | 410423 | Rochdale Borough Council | 15/00595/FUL | [5 empty] | 2015-06-04 | [6 empty] | 2015-07-28 |  |  |  | 2018-07-28
| 5285 | 2016-08-18 | Lightsource Renewable Energy | Land south of Brick Kiln Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of, Brick Kiln Road, Mulbarton, Norwich, Norfolk | Norfolk | Eastern | England | NR14 8AJ | 620403 | 299936 | South Norfolk Council | 2015/1221 | [5 empty] | 2015-06-04 | [6 empty] | 2015-09-03 |  |  |  | 2018-09-03 | 2016-01-18 | 2016-03-17
| 5286 | 2016-01-06 | Pfalzsolar GmbH | Land off Paradise Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Off Paradise Farm, Headley Lane, Bramham, Wetherby, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | LS23 6LN | 443014 | 441687 | Leeds City Council | 15/02188/FU | [5 empty] | 2015-05-19 |  | 2015-12-07
| 5287 | 2016-02-22 | Lightsource Renewable Energy | Averhill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Averill Farm, Evershill Lane, Morton, Alfreton | Derbyshire | East Midlands | England | DE55 6HB | 441094 | 361390 | North East Derbyshire District Council | 15/00307/FL | [5 empty] | 2015-04-28 | [6 empty] | 2015-09-29 |  |  |  | 2018-09-29 | 2015-11-04 | 2015-12-16
| 5288 | 2016-09-20 | Foresight Group (TGC Renewables) | Morton House (Marchington) | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Morton House, Moreton Lane, Draycott-in-the-Clay, Ashbourne, Derbyshire | Staffordshire | West Midlands | England | DE6 5BZ | 415144 | 330728 | East Staffordshire Borough Council | P/2015/00405 | [5 empty] | 2015-04-15 | [6 empty] | 2015-07-08 |  |  |  | 2018-07-08 | 2016-01-04 | 2016-03-24
| 5289 | 2016-07-14 | Conergy West Sussex | Biglis Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Biglis Farm, Argae Lane, Barry, South Glamorgan | Vale of Glamorgan | Wales | Wales | CF63 1BL | 313916 | 170097 | Vale of Glamorgan Council | 2015/00573/FUL | [5 empty] | 2015-05-28 | [6 empty] | 2015-10-02 |  |  |  | 2018-10-02 | 2016-01-15 | 2016-03-31
| 5290 | 2018-06-25 | Big 60 Million | Milborne Port Solar Farm | Solar Photovoltaics |  |  | 4.18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land OS 2269, Old Bowden Way, Milborne Port, Sherborne | Somerset | South West | England | DT9 | 368218 | 119662 | South Somerset District Council | 15/02187/FUL | APP/R3325/W/16/3142550 |  |  |  |  | 2015-05-18 |  | 2015-10-14 | 2016-02-05 |  |  | 2016-08-18 | 2016-08-18 |  |  |  | 2019-06-18 | 2018-02-15 | 2018-06-25
| 5291 | 2015-08-05 | TGC Renewables | Land to the south of Hill Farm | Solar Photovoltaics |  |  | 6.84 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land to the south of Hill Farm, Blisworth, Kislingbury, Northampton | Northamptonshire | East Midlands | England | NN7 3BP | 469990 | 256921 | South Northamptonshire Council | S/2015/1190/MAF | [5 empty] | 2015-05-27 | 2015-07-16
| 5292 | 2017-03-24 | Kronos Solar/ Vogt Solar | Land At Cwm Bargoed | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Cwm Bargoed, West of, Fochriw Road, Cwmbargoed, Merthyr Tydfil, Mid Glamorgan | Merthyr Tydfil | Wales | Wales | CF48 4AE | 309161 | 206091 | Merthyr Tydfil County Borough Council | P/15/0169 | [5 empty] | 2015-06-01 | [6 empty] | 2015-09-17 |  |  |  | 2020-09-17 | 2015-11-25 | 2016-01-20
| 5293 | 2017-03-21 | Anesco | Land South Off Ollerton Road | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Off, Ollerton Road, Edwinstowe, Mansfield | Nottinghamshire | East Midlands | England | NG21 9Q | 463220 | 366009 | Newark and Sherwood District Council | 15/00875/FULM | APP/B3030/W/15/3141404 |  |  |  |  | 2015-05-22 |  | 2015-09-09 | 2016-03-10 |  |  | 2016-06-07 | 2016-06-07 |  |  |  |  | 2016-10-15 | 2017-01-15
| 5294 | 2015-08-05 | Clenergy | Land At Pen Y Fan | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 123.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Pen Y Fan, Industrial Estate Pen Y Fan, Newport, Gwent | Caerphilly | Wales | Wales | NP11 3AA | 319869 | 200296 | Caerphilly County Borough Council | 15/0388/FULL | [5 empty] | 2015-06-05 | 2015-07-28
| 5295 | 2017-07-19 | Gascoyne Holdings | Land At Swanland Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At, Swanland Road, South Mimms, Potters Bar | Hertfordshire | Eastern | England | EN6 3NE | 522972 | 201255 | Hertsmere Borough Council | 15/0784/FUL | [5 empty] | 2015-05-28 | [6 empty] | 2016-01-07 |  |  |  | 2019-01-07 | 2017-01-03 | 2017-03-23
| 5296 | 2016-08-31 | Solar Century/ Bluefield Solar | Rookery Business Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land adjacent to Rookery Busin, Silver Street, Besthorpe | Norfolk | Eastern | England | NR17 2LD | 608047 | 297464 | South Norfolk Council | 2015/1215 | [5 empty] | 2015-05-29 | [6 empty] | 2015-09-03 |  |  |  | 2018-09-03 | 2015-12-11 | 2016-02-11
| 5297 | 2017-12-04 | Greencoat Capital | Land North of Sandhutton Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of, Sandhutton Lane, Carlton Miniott, Thirsk | North Yorkshire | Yorkshire and Humber | England | YO7 4NH | 439302 | 482532 | Hambleton District Council | 15/01074/FUL | [5 empty] | 2015-05-25 | [6 empty] | 2015-09-25 |  |  |  | 2018-09-25 | 2016-12-12 | 2017-02-15
| 5298 | 2019-10-31 | Private Developer | Land Off Mill Lane | Solar Photovoltaics |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land Off Mill Lane Long Manor, Asher Lane, Ruddington, Nottingham | Nottinghamshire | East Midlands | England | NG11 6JX | 456829 | 331794 | Rushcliffe Borough Council | 15/00972/FUL | [5 empty] | 2015-04-28 | [6 empty] | 2015-09-18 |  |  |  | 2018-09-18
| 5299 | 2019-10-17 | JCB Broadcrown | Bloomfield | Advanced Conversion Technologies |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Bloomfield Recycling Depot, Bloomfield Road, Tipton | West Midlands | West Midlands | England | DY4 9BS | 395058 | 293032 | Dudley Metropolitan Borough Council | P15/0685 | [5 empty] | 2015-05-12 | [6 empty] | 2015-08-11 |  |  |  | 2018-08-11
| 5300 | 2015-07-06 | SEP Elton | Land At Elton Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land At Elton Farm, Hapsford Lane, Ince, Chester | Cheshire | North West | England | CH2 4LB | 346957 | 376301 | Cheshire West and Chester Council | 15/01909/FUL | [5 empty] | 2015-05-11
| 5301 | 2017-12-04 | Greencoat Capital | Land West Of Hunger Hill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Hunger Hill Farm,, Middleton St George, Brass Castle, Darlington | County Durham | North East | England | DL2 1DW | 433439 | 512522 | Darlington Borough Council | 15/00484/FUL | [5 empty] | 2015-05-19 | [6 empty] | 2015-08-13 |  |  |  | 2018-08-13 | 2016-12-12 | 2017-02-15
| 5302 | 2016-04-25 | Honeysome Road Solar | Land East Of Honeysome Road | Solar Photovoltaics |  |  | 4.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of, Honeysome Road, Honeysome Farm Bungalow, Chatteris | Cambridgeshire | Eastern | England | PE16 6SB | 538665 | 286282 | Fenland District Council | F/YR15/0429/F | [5 empty] | 2015-05-20 | [6 empty] | 2015-12-14 |  |  |  | 2018-12-14 |  | 2016-03-15
| 5303 | 2016-01-04 | Greater Manchester Waste Disposal Authority | Salford Road Solar Farm (resubmission) | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former CMP/GMB Batteries Ltd, Salford Road, Bolton | Greater Manchester | North West | England | BL5 1BL | 405774 | 369100 | Bolton Metropolitan Borough Council | 94267/15 | [5 empty] | 2015-05-26 | [6 empty] | 2015-06-29 |  |  |  | 2018-06-29 | 2015-07-01 | 2015-08-09
| 5304 | 2015-09-02 | SEP Burtonwood | Land South Of Joy Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land South Of, Joy Lane, And West Of Wrights Lane, Burtonwood, Warrington | Cheshire | North West | England | WA5 4AH | 356338 | 391258 | Warrington Borough Council | 2015/25803 | [5 empty] | 2015-05-20 |  | 2015-08-17
| 5305 | 2016-02-22 | Lightsource Renewable Energy | Ld NW Of Ratcliffe House Farm | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ld NW Of Ratcliffe House Farm, Ratcliffe House Lane, Ratcliffe Culey, Atherstone | Leicestershire | East Midlands | England | CV9 3LZ | 433432 | 299754 | Hinckley and Bosworth Borough Council | 15/00560/FUL | [5 empty] | 2015-05-19 | [6 empty] | 2015-08-17 |  |  |  | 2018-08-17 | 2015-10-19 | 2015-12-21
| 5306 | 2020-03-11 | Muirhall Energy (Southrigg WT) | South Priorhill Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 130 | n/a | Planning Permission Granted | Awaiting Construction | South Priorhill Farm, Lesmahagow, Lanark, Strathclyde | South Lanarkshire | Scotland | Scotland | ML11 0JL | 275280 | 639176 | South Lanarkshire Council | CL/15/0219 | [5 empty] | 2015-06-04 | [6 empty] | 2016-08-16 |  |  |  | 2019-08-16
| 5309 | 2016-08-24 | Lightsource Renewable Energy | Land at Woodhouse Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Woodhouse Farm, Middlesbrough Road, Guisborough | Cleveland | North East | England | TS14 6QU | 459902 | 515917 | Redcar and Cleveland Borough Council | R/2015/0328/FFM | [5 empty] | 2015-05-21 | [6 empty] | 2015-11-24 |  |  |  | 2018-11-24 | 2016-01-20 | 2016-03-24
| 5310 | 2016-03-15 | Anesco | Parklands | Solar Photovoltaics |  |  | 4.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Parklands, Almondsbury, Oakham Farm Land At, Bristol | Gloucestershire | South West | England | BS32 4B | 361833 | 184427 | South Gloucestershire Council | PT15/2164/F | [5 empty] | 2015-05-22 | [6 empty] | 2015-10-22 |  |  |  | 2018-10-22 | 2015-12-15 | 2016-02-15
| 5311 | 2016-03-03 | Private Developer | Land To West Of Cefn Llogell Farm | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land To West Of Cefn Llogell Farm, Cardiff Road, Newport, Gwent | Newport | Wales | Wales | NP10 8UD | 331275 | 187470 | Newport City Council | 15/0393 | APP/G6935/A/15/3138411 |  |  |  |  | 2015-05-19 |  | 2015-11-04 | 2015-11-27 |  | 2016-02-29
| 5312 | 2016-04-26 | Langley Eco | Amcor Flexibles | Solar Photovoltaics |  |  | 1.69 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Amcor Flexibles, Winterbourne Road, Bradley Stoke, Bristol | Gloucestershire | South West | England | BS34 6PT | 363561 | 180524 | South Gloucestershire Council | PT15/2341/F | [5 empty] | 2015-06-02 | [6 empty] | 2015-07-09 |  |  |  | 2018-07-09 | 2015-09-01 | 2015-11-01
| 5313 | 2015-10-06 | Flanchford Solar Park | Land At Flanchford Farm | Solar Photovoltaics |  |  | 3.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Flanchford Farm, Flanchford Road, Heath, Reigate | Surrey | South East | England | RH2 8RB | 523605 | 148197 | Reigate and Banstead Borough Council | 15/01151/F | [5 empty] | 2015-05-22 |  | 2015-09-04
| 5314 | 2019-07-31 | Balfour Beatty Capital | Thurrock Biomass CHP Facility | Biomass (dedicated) |  |  | 9 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Land part of Fiddlers Reach, Wouldham Road, (Eastern Side), Grays | Essex | Eastern | England | RM20 4XQ | 560297 | 177779 | Thurrock Council | 15/00510/FUL | APP/M1595/W/15/3140789 |  |  |  |  | 2015-05-13 |  | 2015-11-03 | 2016-02-05 |  |  | 2016-08-23 | 2016-08-23
| 5315 | 2016-03-16 | New Forest Energy | Waterditch Solar Farm | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | East Close Farm, Waterditch, Christchurch | Dorset | South West | England | BH23 | 417600 | 95536 | Christchurch Borough Council | 8/15/0284 | [5 empty] | 2015-05-21 | [6 empty] | 2015-06-24 |  |  |  | 2018-06-24 | 2016-01-01 | 2016-03-31
| 5316 | 2016-08-31 | T J Coates Ltd | Land Off Ingarsby Lane | Solar Photovoltaics |  |  | 2.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off, Ingarsby Lane, Ingarsby, Houghton On The Hill, Leicester | Leicestershire | East Midlands | England | LE7 9JL | 467878 | 304470 | Harborough District Council | 15/00676/FUL | [5 empty] | 2015-05-14 | [6 empty] | 2015-07-30 |  |  |  | 2018-07-30 | 2016-04-05 | 2016-06-05
| 5317 | 2015-07-06 | SEP Puddington | Land West Of Vicarage Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land West Of, Vicarage Lane, Shotwick, Chester, Cheshire | Cheshire | North West | England | CH1 6HZ | 333272 | 371926 | Cheshire West and Chester Council | 15/01910/FUL | [5 empty] | 2015-05-11
| 5318 | 2016-05-04 | The Energy Workshop | Achlachan 2 Windfarm | Wind Onshore |  |  | 7.5 | n/a |  |  |  | 2.5 | 3 | 110 | n/a | Planning Permission Refused | Application Refused | Achlachan 2 Windfarm, Watten, Wick, Highlands | Highland | Scotland | Scotland | KW1 5U | 315293 | 951239 | Highland Council | 15/01831/FUL | [5 empty] | 2015-05-11 |  | 2015-09-18
| 5319 | 2015-09-02 | SEP Chester | Land south of 50 Station Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land south of, 50 Station Road, Penketh, Warrington | Cheshire | North West | England | WA5 2NZ | 356800 | 387184 | Warrington Borough Council | 2015/25801 | [5 empty] | 2015-05-20 |  | 2015-08-14
| 5320 | 2016-06-17 | Nissan / On-Site Land Solutions | Nissan Test Track | Solar Photovoltaics |  |  | 4.77 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Nissan Test Track, Washington Road, Nissan Motor Manufacturing (UK, Sunderland, Tyne and Wear | Tyne and Wear | North East | England | SR5 3NS | 434270 | 558567 | Sunderland City Council | 15/00942/FUL | [5 empty] | 2015-05-03 | [6 empty] | 2015-07-22 |  |  |  | 2018-07-22 | 2016-01-30 | 2016-03-30
| 5321 | 2016-05-16 | Suncredit UK/ Vogt solar | Cooper House Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cooper House Farm, Kirkham Road, Freckleton, Preston, Lancashire | Lancashire | North West | England | PR4 1HX | 342344 | 430364 | Fylde Borough Council | 15/0329 | [5 empty] | 2015-05-13 | [6 empty] | 2015-11-06 |  |  |  | 2018-11-06 | 2016-01-15 | 2016-03-15
| 5322 | 2016-02-22 | Lightsource Renewable Energy | Land at Pollington Airfield | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Pollington Airfield, Gowdall Lane, Pollington, Goole, Humberside | Humberside | Yorkshire and Humber | England | DN14 0AU | 461763 | 420079 | East Riding of Yorkshire Council | 15/01403/STPLF | [5 empty] | 2015-05-15 | [6 empty] | 2015-07-24 |  |  |  | 2018-07-24 | 2015-11-02 | 2015-12-21
| 5323 | 2016-12-15 | Swancote Energy | Swancote Farm | Anaerobic Digestion |  |  | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Swancote Energy Ltd, , Anaerobic Digestion Plant At, Swancote Farm, Swancote, Bridgnorth, Shropshire | Shropshire | West Midlands | England | WV15 5HB | 374234 | 293942 | Shropshire Council | 15/01864/FUL | [5 empty] | 2015-05-20 | [6 empty] | 2015-08-17 |  |  |  | 2018-08-17 | 2015-09-01 | 2016-08-01
| 5324 | 2018-07-27 | Sunsave 13 (Southwick) | Land at Poles Hole Farm | Solar Photovoltaics |  |  | 6.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Poles Hole Farm, Southwick, Trowbridge, Wiltshire | Wiltshire | South West | England | BA14 9PP | 383960 | 154595 | Wiltshire Council | 15/04583/FUL | [5 empty] | 2015-05-20 | [6 empty] | 2015-10-29 |  |  |  | 2018-10-29 | 2016-07-15 | 2017-03-01
| 5325 | 2015-09-27 | Community Windpower | Hill Rig Community Wind Farm (resubmission) | Wind Onshore |  |  | 28 | n/a |  |  |  | 3.5 | 8 | 130 | n/a | Planning Permission Refused | Application Refused | Land on Greenbank Farm, Carluke | South Lanarkshire | Scotland | Scotland | ML8 4QR | 289999 | 648659 | South Lanarkshire Council | CL/15/0175 | [5 empty] | 2015-05-11 |  | 2015-09-24
| 5326 | 2018-09-27 | Green Power Consultants | Land To The West Of Kirkton Barns Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land To The West Of, Kirkton Barns Farm, Tayport | Fife | Scotland | Scotland | DD6 9PD | 344749 | 726196 | Fife Council | 15/00545/FULL | [5 empty] | 2015-04-17 | [6 empty] | 2015-10-09 |  |  |  | 2018-10-09
| 5327 | 2017-08-16 | Lightsource Renewable Energy | Ringtail Airfield | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The North Of, Pippin Street, Burscough, Ormskirk | Lancashire | North West | England | L40 7SP | 342700 | 411160 | West Lancashire Borough Council | 2015/0447/FUL | [5 empty] | 2015-05-21 | 2015-11-09
| 5328 | 2016-08-18 | Lightsource Renewable Energy | Staining Wood Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Staining Wood Farm, Preston New Road, Westby, Preston | Lancashire | North West | England | PR4 3PH | 336844 | 432004 | Fylde Borough Council | 15/0337 | [5 empty] | 2015-05-18 | [6 empty] | 2015-09-30 |  |  |  | 2015-09-29 | 2016-01-04 | 2016-03-30
| 5329 | 2019-12-04 | TGC Renewables/NESF | Land at Moss Farm (South) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Moss Farm, Moss Lane, Warmingham, Crewe | Cheshire | North West | England | CW1 4PW | 369924 | 358982 | Cheshire East Council | 15/2126N | [5 empty] | 2015-05-08 | [6 empty] | 2016-05-31
| 5330 | 2016-03-22 | INRG Solar | Land between Orton Park Farm | Solar Photovoltaics |  |  | 6.35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land between Orton Park Farm, Newby West, Carlisle | Cumbria | North West | England | CA2 6QY | 336729 | 553838 | Carlisle City Council | 15/0405 | [5 empty] | 2015-05-11 | [6 empty] | 2015-09-23 |  |  |  | 2018-09-23 | 2016-01-22 | 2016-03-29
| 5331 | 2017-04-18 | RAD Energy One/ Island Green Power | Ballinderry Road Solar Phase 2 (Lisburn) | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands immediately north east o, Moneybroom Road, the junction of Ballinderry Rd, Lisburn | Co. Antrim | Northern Ireland | Northern Ireland | BT28 2QP | 135485 | 520798 | Lisburn and Castlereagh City Council | LA05/2015/0157/F | [5 empty] | 2015-05-19 | [6 empty] | 2015-10-14 |  |  |  |  | 2016-07-01 | 2017-02-20
| 5332 | 2016-11-23 | SBC Renewables | Site To North East Of, Lochcraigs Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Site To North East Of, Lochcraigs Farm, Stevenston, Strathclyde | North Ayrshire | Scotland | Scotland | KA20 4LB | 227518 | 643857 | North Ayrshire Council | 15/00252/PP | [5 empty] | 2015-05-12 | [6 empty] | 2015-08-13 |  |  |  | 2018-08-13 | 2016-10-15 | 2017-03-31
| 5333 | 2016-04-18 | BWE Partnership | West Mains of Kinblethmont | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | West Mains of Kinblethmont, Kinblethmont, Arbroath, Tayside | Angus | Scotland | Scotland | DD11 4RW | 363182 | 746857 | Angus Council | 15/00468/FULL | [5 empty] | 2015-05-18 | [6 empty] | 2015-09-04 |  |  |  | 2018-09-04 | 2016-02-15 | 2016-03-31
| 5334 | 2016-01-06 | Ethical Power | Land at Sunnyside Court | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at SK2821 3837, Sunnyside Court, Newhall, Swadlincote, Derbyshire | Derbyshire | East Midlands | England | DE11 0GY | 428625 | 321161 | South Derbyshire District Council | 9/2015/0124 | [5 empty] | 2015-05-06 |  | 2015-12-16
| 5335 | 2015-08-05 | Formby Lane Solar | Fromby Lane Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The Rear Of Old Waggoners Cottage, Formby Lane, Aughton, Ormskirk, Lancashire | Lancashire | North West | England | L39 7HQ | 337362 | 406972 | West Lancashire Borough Council | 2015/0425/FUL | [5 empty] | 2015-04-29 | 2015-07-09
| 5336 | 2016-05-18 | Wessex Solar Energy | Land West Side of Axe and Cleaver Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Side of, Axe and Cleaver Lane, Southwick, Trowbridge | Wiltshire | South West | England | BA14 | 385331 | 154796 | Wiltshire Council | 15/04570/FUL | [5 empty] | 2015-05-14 | [6 empty] | 2015-08-20 |  |  |  | 2018-08-20 | 2015-12-18 | 2016-03-31
| 5337 | 2016-05-30 | Peel Energy | Land off, Common Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land off, Common Lane, Hapsford, Frodsham | Cheshire | North West | England | WA6 0JS | 346842 | 374107 | Cheshire West and Chester Council | 15/01724/FUL | APP/A0665/W/15/3140162 |  |  |  |  | 2015-04-27 |  | 2015-10-21 | 2015-12-21 |  | 2016-05-25
| 5338 | 2018-09-27 | Green Power Consultants | Cameron Reservoir | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Cameron Reservoir, Cameron Drive, Kirkcaldy | Fife | Scotland | Scotland | KY16 8PF | 347689 | 710386 | Fife Council | 15/00538/FULL | [5 empty] | 2015-04-20 | [6 empty] | 2015-10-13 |  |  |  | 2018-10-13
| 5339 | 2015-07-06 | Kislingbury Solar | Kislingbury Road Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land west of, Banbury Lane, Rothersthorpe, Northampton | Northamptonshire | East Midlands | England | NN7 3 | 471320 | 256973 | South Northamptonshire Council | S/2015/1065/MAF | [5 empty] | 2015-05-13 |  | 2015-07-30
| 5340 | 2017-09-04 | Navitas Project | Land To The North Of Moor Farm | Solar Photovoltaics |  |  | 3.75 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The North Of Moor Farm, Ruyton Road, Baschurch, Shrewsbury | Shropshire | West Midlands | England | SY4 2 | 341738 | 323343 | Shropshire Council | 15/01805/FUL | [5 empty] | 2015-05-14 | [6 empty] | 2016-01-06 |  |  |  | 2019-01-06 | 2016-06-01 | 2017-03-11
| 5342 | 2017-12-01 | Greencoat/ Renesola | Henley Solar Farm | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Henley Common Henley Lane Acton Scott | Shropshire | West Midlands | England | SY6 6RS | 345538 | 287874 | Shropshire Council | 14/04930/FUL | APP/L3245/W/15/3022913 |  |  |  |  | 2014-11-03 |  | 2015-02-16 | 2015-06-25 |  |  | 2016-01-04 | 2016-01-04 |  |  |  |  | 2016-12-29 | 2017-03-29
| 5343 | 2016-04-25 | Greenfields (A) | Hawkers Farm | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hawkers Farm Yeo Moor Drove Theale Wedmore | Somerset | South West | England | BS28 4SN | 346740 | 147660 | Mendip District Council | 2014/1598/FUL | APP/Q3305/W/14/3000543 |  |  |  |  | 2014-07-04 |  | 2014-11-24 | 2015-01-20 |  |  | 2015-09-08 | 2015-09-08 |  |  |  | 2018-09-08 | 2016-01-20 | 2016-03-20
| 5346 | 2015-07-06 | Singleton Birch / Energos | Melton Ross (resubmission) | Advanced Conversion Technologies |  |  | 5.75 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Melton Ross Quaries, Melton Ross, Barnetby, North Lincolnshire | Humberside | Yorkshire and Humber | England | DN38 6AE | 508390 | 411142 | North Lincolnshire Council | WD/2010/0704 | [5 empty] | 2010-06-25 | [6 empty] | 2010-09-14
| 5347 | 2015-07-06 | Singleton Birch / Energos | Melton Ross (resubmission no. 2) | Advanced Conversion Technologies |  |  | 5.75 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Singleton Birch, Brigg Road, Melton Ross, Croxton | Humberside | Yorkshire and Humber | England | DN38 6AE | 508390 | 411142 | North Lincolnshire Council | WD/2013/0471 | [5 empty] | 2013-03-25 | [6 empty] | 2013-07-04 |  |  |  | 2016-07-04
| 5351 | 2018-06-28 | European Forest Resource Group | Druim Ba Windfarm (resubmission) | Wind Onshore |  |  | 30 | n/a |  |  |  | 3 | 10 | 126.5 | n/a | Appeal Refused | Application Refused | near Kiltarlity of Loch Ness | Highland | Scotland | Scotland | IV4 7HT | 252358 | 838656 | Highland Council | 15/03998/FUL | PPA-270-2147 |  |  |  |  | 2015-10-23 |  | 2018-06-28 | 2016-02-24 |  | 2018-06-28
| 5352 | 2019-03-28 | Earls Gate Energy Centre | CalaChem Fine Chemicals (Grangemouth) | EfW Incineration |  |  | 21.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Calachem Ltd, Earls Road, Grangemouth, Central | Falkirk | Scotland | Scotland | FK3 8XG | 291830 | 681210 | Falkirk Council | P/16/0321/FUL | [5 empty] | 2016-05-20 | [6 empty] | 2017-01-18 |  |  |  | 2020-01-18 | 2019-01-01
| 5357 | 2018-01-25 | Suncredit UK (Sunventures 7) | Crown Farm | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Crown Farm, Bagworth Road, Nailstone, Nuneaton, Warwickshire, West Midlands | Leicestershire | East Midlands | England | CV13 0QL | 442775 | 307520 | Hinckley and Bosworth Borough Council | 15/00823/FUL | [5 empty] | 2015-07-28 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30 | 2016-02-15 | 2017-03-01
| 5358 | 2015-10-06 | Lark Energy | Waye Barton | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land At Waye Barton, Littlehempston, Totnes | Devon | South West | England | TQ9 6NQ | 283382 | 64197 | Teignbridge District Council | 15/02090/MAJ | [5 empty] | 2015-08-21 | 2016-01-14
| 5359 | 2017-05-23 | UK Sustainable Energy | Eaglescliffe Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Durham Lane, Eaglescliffe, Stockton-On-Tees, Cleveland | County Durham | North East | England | TS16 0AA | 441817 | 516371 | Stockton on Tees Borough Council | 15/1842/FUL | [5 empty] | 2015-09-18 | [6 empty] | 2015-12-18 |  |  |  | 2018-12-18 | 2017-01-01 | 2017-03-28
| 5360 | 2017-05-26 | Lightsource Renewable Energy | Tyddyn Gwyn (Gelli Gron Farm) | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Tyddyn Gwyn, Llangybi, Pwllheli, Gwynedd, Wales | Gwynedd | Wales | Wales | LL53 6DQ | 241889 | 340088 | Gwynedd Council | C15/0755/41/LL | [5 empty] | 2015-07-23 | [6 empty] | 2015-11-09 |  |  |  | 2020-11-09 | 2016-09-01 | 2016-11-30
| 5368 | 2017-02-02 | Green Hedge (BayWa r.e.) | Thornton Lane | Solar Photovoltaics |  |  | 2.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of, Thornton Lane, Stanton Under Bardon, Markfield, Leicestershire | Leicestershire | East Midlands | England | LE67 9TU | 446458 | 309845 | Hinckley and Bosworth Borough Council | 15/00645/FUL | [5 empty] | 2015-06-09 | [6 empty] | 2015-09-08 |  |  |  | 2018-09-08 | 2016-01-15 | 2016-03-23
| 5371 | 2020-06-30 | Wessex Solar Energy | Aborfield Solar Park | Solar Photovoltaics |  |  | 14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Bartletts Farm, Swallowfield Road, Arborfield, Reading | Berkshire | South East | England | RG2 9JX | 475150 | 165755 | Wokingham Borough Council | 200711 | [5 empty] | 2020-03-23
| 5373 | 2019-09-17 | Vento Ludens | Lurg Hill Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 | 130 | n/a | Appeal Granted | Awaiting Construction | Lurg Hill, Grange, Deskford, Keith, Grampian | Moray | Scotland | Scotland | AB55 6TA | 351190 | 858727 | Moray Council | 17/01198/EIA | PPA-300-2052 |  |  |  |  | 2017-09-28 |  | 2018-06-20 | 2018-09-19 |  |  | 2019-02-25 | 2019-02-25 |  |  |  | 2022-02-25
| 5374 | 2020-01-16 | Caledon Partners (Solar Power Parks) | Knights End Road Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | North Of Bradney Farm, Knights End Road, March | Cambridgeshire | Eastern | England | PE15 0YW | 537109 | 294716 | Fenland District Council | F/YR15/0900/F | [5 empty] | 2015-10-08 | [6 empty] | 2015-12-15 |  |  |  | 2018-12-15
| 5375 | 2016-05-26 | SBC Renewables | Castlehill Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Site To North East Of Castlehill Farm, Stevenston, Ayrshire | North Ayrshire | Scotland | Scotland | KA13 6TT | 228423 | 643496 | North Ayrshire Council | 15/00469/PP | [5 empty] | 2015-08-26 | [6 empty] | 2015-10-16 |  |  |  | 2018-10-16
| 5376 | 2016-05-26 | SBC Renewables | Penycae Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To East And West Of, Benn, The Grange Plas, Penycae, Wrexham, Clwyd | Wrexham | Wales | Wales | LL14 1 | 328970 | 344020 | Wrexham County Borough Council | P/2015/0546 | [5 empty] | 2015-07-15 | [6 empty] | 2015-10-05 |  |  |  | 2020-10-05 | 2016-01-28 | 2016-03-28
| 5377 | 2016-06-14 | Sunventures (Suncredit UK) | Land at Ingles Hill Farm | Solar Photovoltaics |  |  | 3.04 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Ingles Hill Farm, Burton Road, Ashby-De-La-Zouch, Leicestershire | Leicestershire | East Midlands | England | LE65 2TE | 434525 | 317774 | North West Leicestershire District Council | 15/00714/FULM | [5 empty] | 2015-07-23 | [6 empty] | 2015-09-29 |  |  |  | 2018-09-29 | 2016-02-15 | 2016-04-15
| 5378 | 2019-07-18 | Derbyshire County Council | Land at Mansfield Road | Solar Photovoltaics |  |  | 3.72 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land at Mansfield Road, Temple Normanton | Derbyshire | East Midlands | England | S42 5DQ | 442612 | 367282 | Derbyshire County Council | CD4/0615/36 | [5 empty] | 2015-07-29 | [6 empty] | 2016-01-11 |  |  |  | 2019-01-11
| 5379 | 2016-06-14 | Sunventures (Suncredit UK) | Southbrook Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Southbrook Farm, Sudbrook Road, Sudbrook, Portskewett, Caldicot, Gwent | Monmouthshire | Wales | Wales | NP26 5SR | 350024 | 187852 | Monmouthshire County Council | DC/2015/00855 | [5 empty] | 2015-07-13 | [6 empty] | 2015-12-03 |  |  |  |  | 2016-02-15 | 2016-05-15
| 5380 | 2017-02-01 | Anesco | Green Croft Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Between Greencroft Indust, Tower Road/Lanchester Road, Greencroft, Stanley, County Durham | County Durham | North East | England | DH9 7XR | 417005 | 550340 | Durham County Council | DM/15/02279/FPA | [5 empty] | 2015-07-23 | [6 empty] | 2015-11-04 |  |  |  |  | 2016-10-07 | 2016-12-07
| 5381 | 2017-04-26 | Suncredit UK | Upper Pant-Ysgawen Farm/Crumlin | Solar Photovoltaics |  |  | 4.92 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pant-Ysgawen Farm, Pant Ysgawen Farm Lane, Newbridge, Newport, Gwent | Caerphilly | Wales | Wales | NP11 4RJ | 320409 | 197637 | Caerphilly County Borough Council | 15/0512/FULL | [5 empty] | 2015-07-22 | [6 empty] | 2015-09-10 |  |  |  | 2020-09-10 | 2016-02-15 | 2016-12-07
| 5382 | 2020-03-24 | Kronos Solar | Land at Lltty Morphil Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Llettyr Morfil Farm, , U/S-Y878, Felindre, Swansea, West Glamorgan | Swansea | Wales | Wales | SA5 7LU | 264741 | 201094 | City and County Council of Swansea | 2015/1529 | APP/B6855/A/15/3139869 |  |  |  |  | 2015-07-22 |  | 2015-11-19 | 2016-01-04 |  |  | 2016-05-10 | 2016-05-10
| 5383 | 2016-04-25 | Anesco | Land at Oxcroft Stocking Ground | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Former Oxcroft Stockin, East Of Woodthorpe Road, Mastin Moor, Chesterfield, Derbyshire | Derbyshire | East Midlands | England | S43 3AZ | 446492 | 374323 | Chesterfield Borough Council | CHE/15/00477/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-12-08 |  |  |  | 2018-12-08 | 2016-01-15 | 2016-03-25
| 5384 | 2017-07-17 | West Strathore Solar | West Strathore Solar Limited | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | West Strathore House, Strathore Road, Thornton, Kirkcaldy, Fife | Fife | Scotland | Scotland | KY1 4DY | 328619 | 697504 | Fife Council | 15/02351/FULL | [5 empty] | 2015-07-23 | [6 empty] | 2015-11-26 |  |  |  | 2018-11-26 | 2016-11-01 | 2017-03-30
| 5385 | 2017-05-26 | Lightsource Renewable Energy | Land at Meadow Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Meadow Farm, Main Street, Thorpe Langton, Market Harborough, Leicestershire | Leicestershire | East Midlands | England | LE16 7TS | 473392 | 291590 | Harborough District Council | 15/01116/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-10-08 |  |  |  | 2018-10-08 | 2017-01-09 | 2017-03-10
| 5386 | 2018-10-02 | XSCH | Ferneylea Farm | Wind Onshore |  |  | 18 | n/a |  |  |  | 3 | 6 | 115 | n/a | Planning Application Withdrawn | Application Withdrawn | Ferneylea Farm, High Street, Ferneylea, Aberlady, Longniddry, Lothian | East Lothian | Scotland | Scotland | EH32 9 | 373273 | 668433 | East Lothian Council | 15/00363/P | [5 empty] | 2015-07-21 | 2018-08-13
| 5387 | 2016-10-03 | Solstice Renewables | Hungerford Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hungerford Farm, Pale Lane, Winchfield, Hook, Hampshire | Hampshire | South East | England | RG27 8SW | 478178 | 153997 | Hart District Council | 15/01777/FUL | [5 empty] | 2015-07-24 | [6 empty] | 2015-10-13 |  |  |  | 2018-10-13 | 2016-06-22 | 2016-08-22
| 5388 | 2020-05-27 | First Renewable Developments | Top Lodge Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Top Lodge, Burton Wold Farm, Wold Road, Burton Latimer, Kettering, Northamptonshire | Northamptonshire | East Midlands | England | NN15 5PJ. <br> | 491204 | 274882 | Kettering Borough Council | KET/2015/0422 | [5 empty] | 2015-06-03 | [6 empty] | 2015-07-29
| 5389 | 2016-08-19 | Novus Solar Developments | Land at Morfa Camp | Solar Photovoltaics |  |  | 2.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Morfa Camp, Sandilands, Tywyn, Gwynedd | Gwynedd | Wales | Wales | LL36 9BH | 258062 | 301195 | Gwynedd Council | C15/0662/09/LL | [5 empty] | 2015-07-01 | [6 empty] | 2015-10-19 |  |  |  |  | 2016-01-05 | 2016-03-20
| 5391 | 2017-05-16 | Murex Energy | Land South of Pogmore Spinney | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South of Pogmore Spinney, Merevale Lane, Atherstone, Warwickshire | Warwickshire | West Midlands | England | CV9 2LA | 427328 | 289035 | North Warwickshire Borough Council | PAP/2015/0459 | [5 empty] | 2015-07-24 | [6 empty] | 2016-02-29 |  |  |  | 2019-03-01 | 2017-01-23 | 2017-03-30
| 5392 | 2018-10-29 | Burcote Wind | Sandy Knowe Wind Farm (resubmission) | Wind Onshore |  |  | 49.4 | n/a |  |  |  | 2 | 24 | 125 | n/a | Planning Permission Granted | Awaiting Construction | Site Art Libry Moor, Locharbriggs, By Kirkconnel and Kelloholm, Dumfries | Dumfries and Galloway | Scotland | Scotland | DG1 1QF | 270100 | 610600 | Dumfries and Galloway Council | 15/P/3/0279 | [5 empty] | 2015-07-09 | [6 empty] | 2016-11-24 |  |  |  | 2019-11-23
| 5393 | 2020-01-24 | Greencoat (formerly 3R Energy/Blue Energy) | Douglas West and Dalquhandy Renewable Energy Project | Wind Onshore |  |  | 49 | n/a |  |  |  | 3 | 15 | 127 | n/a | Planning Permission Granted | Awaiting Construction | Douglas West and Dalquhandy, F, Lesmahagow, Site West of Junction 11 of M7, Lanark, Strathclyde | South Lanarkshire | Scotland | Scotland | ML11 0 | 280968 | 634257 | South Lanarkshire Council | CL/15/0273 | [5 empty] | 2015-07-16 | [6 empty] | 2016-02-02 |  |  |  | 2021-02-02
| 5394 | 2016-10-03 | FR Solar Kent PV | Abbey Fields Farm | Solar Photovoltaics |  |  | 5.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Abbey Fields Farm, Abbey Fields, Faversham, Kent | Kent | South East | England | ME13 8HX | 602383 | 161735 | Maidstone Borough Council | 15/505437/FULL | [5 empty] | 2015-07-08 | [6 empty] | 2015-10-30 |  |  |  | 2018-10-30 | 2016-01-30 | 2016-03-30
| 5395 | 2016-05-27 | PEC Renewables | Ernesettle Solar Farm | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Site to the west of, Ernesettle Crescent, Plymouth, Devon | Devon | South West | England | PL5 2ET | 245039 | 59158 | Plymouth City Council | 15/01377/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-09-25 |  |  |  | 2018-09-25 | 2016-01-11 | 2016-03-23
| 5396 | 2016-07-28 | Navitas Project | SPF Thirty Acres Farm | Solar Photovoltaics |  |  | 3.76 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Associated with, Carter L, Warsop Vale, Thiry Acres Farm, Mansfield, Nottinghamshire | Nottinghamshire | East Midlands | England | NG20 8XT | 453745 | 367983 | Mansfield District Council | 2015/0451/NT | [5 empty] | 2015-07-22 | [6 empty] | 2015-11-18 |  |  |  | 2018-11-18 | 2016-06-01 | 2016-03-31
| 5398 | 2018-01-29 | Y Felin Ddwr Charitable Trust | Killan Farm Solar Array Extens | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Killan Fach Farm, Killan Road, Dunvant, Swansea, West Glamorgan | Swansea | Wales | Wales | SA2 7US | 258483 | 193944 | City and County Council of Swansea | 2015/1209 | [5 empty] | 2015-07-17 | [6 empty] | 2015-12-14 |  |  |  | 2020-12-14 | 2017-05-15 | 2017-05-20
| 5400 | 2018-06-04 | Gresham House | Land East of Appleton Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ld N Of East Appleton Hall Far, East Appleton, Richmond, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | DL10 7QE | 423660 | 495768 | Richmondshire District Council | 15/00448/FULL | [5 empty] | 2015-06-16 | [6 empty] | 2015-09-14 |  |  |  | 2018-09-14 | 2016-01-15 | 2016-03-27
| 5401 | 2016-08-01 | Equitix Fund IV | Land At Debdale Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Debdale Lane, Burlington Drive, Mansfield, Nottinghamshire | Nottinghamshire | East Midlands | England | NG19 7HS | 452509 | 362845 | Mansfield District Council | 2015/0449/NT | [5 empty] | 2015-07-22 | [6 empty] | 2015-10-21 |  |  |  | 2018-10-21 | 2016-01-15 | 2016-03-25
| 5402 | 2016-02-22 | Lightsource Renewable Energy | Land at Ash Row Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ash Row Farm, Bishopdyke Road, Sherburn in Elmet, Leeds, West Yorkshire | North Yorkshire | Yorkshire and Humber | England | LS25 6JJ. <br | 451649 | 433677 | Selby District Council | 2015/0777/FUL | [5 empty] | 2015-07-13 | [6 empty] | 2015-09-29 |  |  |  | 2018-09-29 | 2015-10-26 | 2015-12-21
| 5403 | 2018-06-04 | Gresham House | Land at Stripe Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of East Appleton Hal, East Appleton, Richmond, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | DL10 7QE | 419640 | 502487 | Richmondshire District Council | 15/00449/FULL | [5 empty] | 2015-06-16 | [6 empty] | 2015-09-14 |  |  |  | 2018-09-14 | 2016-01-15 | 2016-03-28
| 5404 | 2017-05-26 | Lightsource Renewable Energy | Land at Bolsover Moor Quarry | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The North And East Of, The Works, Whaley Road, Bolsover, Chesterfield, Derbyshire | Derbyshire | East Midlands | England | S44 6XE | 449860 | 371682 | Bolsover District Council | 15/00334/FUL | [5 empty] | 2015-07-15 | [6 empty] | 2015-09-29 |  |  |  | 2018-09-29 | 2017-01-04 | 2017-03-01
| 5405 | 2018-06-21 | Northumberland County Council | New Moor Shaft | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land s/New Moor Shaft Cottages, Ellington Road, Ashington, Northumberland | Northumberland | North East | England | NE63 9XS | 426539 | 589584 | Northumberland County Council | 15/02357/CCD | [5 empty] | 2015-07-20 | [6 empty] | 2015-09-02 |  |  |  | 2020-09-02
| 5406 | 2016-07-28 | Lightsource Renewable Energy | Land To The North Of Dairy House Farm | Solar Photovoltaics |  |  | 3.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ld To The N Of Dairy House Far, Main Road, Worleston, Nantwich, Cheshire | Cheshire | North West | England | CW5 6DN | 365834 | 356455 | Cheshire East Council | 15/2779N | [5 empty] | 2015-06-19 | [6 empty] | 2015-09-30 |  |  |  |  | 2016-01-05 | 2016-02-27
| 5407 | 2016-08-19 | Novus Solar Developments | Pennington Recycling Centre | Solar Photovoltaics |  |  | 1.18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pennington Recycling Centre, Milford Road, Pennington, Lymington, Hampshire | Hampshire | South East | England | SO41 8QZ | 430922 | 93325 | New Forest District Council | 15/11012 | [5 empty] | 2015-07-08 | [6 empty] | 2015-09-29 |  |  |  | 2018-09-29 | 2016-01-05 | 2016-03-20
| 5408 | 2016-01-06 | Solstice Renewables | The Fields Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | The Fields Farm, Draycott Cross, Cheadle, Stoke-On-Trent, Staffordshire | Staffordshire | West Midlands | England | ST10 2NT | 398666 | 341842 | Staffordshire Moorlands District Council | SMD/2015/0394 | [5 empty] | 2015-07-13 |  | 2015-12-21
| 5409 | 2020-03-18 | McGuckian Milling Company | Drumbare Road | Biomass (dedicated) |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 29 Drumbare Road, Cloughmills, Ballymena, Co Antrim | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT44 9LA | 123016 | 574959 | Magherafelt District Council | LA01/2015/0377/F | [5 empty] | 2015-07-03 | [6 empty] | 2016-03-24 |  |  |  | 2021-03-23
| 5410 | 2016-01-06 | Herefordshire New Leaf Cooperative | Stretton Sugwas Solar Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Stretton Sugwas Closed Landfil, Land south of New Barnfields, tretton Sugwas, Hereford, Hereford and Worcester | Hereford and Worcester | West Midlands | England | HR4 7AZ | 345864 | 242228 | Herefordshire Council | P151697/CD4 | [5 empty] | 2015-07-07 | 2015-12-01
| 5411 | 2020-02-24 | Lightsource Renewable Energy | Goosehall Solar Farm | Solar Photovoltaics |  |  | 39.48 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | New Fen Farm, Factory Road, Burwell, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB25 0BN | 557620 | 268622 | East Cambridgeshire District Council | 15/00723/ESF | [5 empty] | 2015-07-03 | [6 empty] | 2015-11-10 |  |  |  | 2018-11-10
| 5412 | 2016-08-24 | Lightsource Renewable Energy | Land west of Welton Road | Solar Photovoltaics |  |  | 4.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land west of, Welton Road, Dalston, Carlisle, Cumbria | Cumbria | North West | England | CA5 7EL | 335683 | 546464 | Carlisle City Council | 15/0630 | [5 empty] | 2015-07-03 | [6 empty] | 2015-10-23 |  |  |  | 2018-10-23 | 2016-02-03 | 2016-03-29
| 5413 | 2015-11-30 | Navitas Project | Land on Park Farm | Solar Photovoltaics |  |  | 2.38 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Parc Pengroeslon, Carmel, Caernarfon, Gwynedd | Gwynedd | Wales | Wales | LL54 7SH | 248859 | 353969 | Gwynedd Council | C15/0700/22/LL | [5 empty] | 2015-07-10 |  | 2015-11-09
| 5414 | 2015-08-06 | Wilson Renewables II | Bankend Rig II Wind Farm | Wind Onshore |  |  | 10.2 | n/a |  |  |  | 3.4 | 3 | 136 | n/a | Planning Application Submitted | Application Submitted | Bankend Rig II Wind Farm, Drumclog, Strathaven, Strathclyde | South Lanarkshire | Scotland | Scotland | ML10 6QG | 264000 | 633700 | South Lanarkshire Council | EK/15/0217 | [5 empty] | 2015-07-09
| 5415 | 2017-10-31 | Global Renewable Construction | Twin Yards Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The South East Of, The Hideaway, Pasture Lane, Hilcote, Alfreton, Derbyshire | Derbyshire | East Midlands | England | DE55 5HQ. <br> | 445514 | 358173 | Bolsover District Council | 15/00327/FUL | [5 empty] | 2015-07-09 | [6 empty] | 2015-09-25 |  |  |  | 2018-09-25 | 2017-01-20 | 2017-03-20
| 5416 | 2015-09-02 | Mulbrick Cleans Energy | Stud Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Stud Farm, Sulhamstead Road, Ufton Nervet, Reading, Berkshire | Berkshire | South East | England | RG7 4 | 465298 | 167987 | West Berkshire Council | 15/01649/COMIND | [5 empty] | 2015-07-06 |  | 2015-08-13
| 5418 | 2018-08-21 | Green Highland Renewables | River Coiltie Hydro Scheme | Small Hydro |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Corbay Wood Glen, Coiltie, Drumnadrochit, Inverness | Highland | Scotland | Scotland | IV63 | 249251 | 827905 | Highland Council | 15/02595/FUL | [5 empty] | 2015-07-07 | [6 empty] | 2015-09-18 |  |  |  | 2018-09-18 | 2016-08-15 | 2017-07-01
| 5420 | 2020-01-20 | Gridserve | Hull Solar Farm | Solar Photovoltaics |  |  | 25.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land South Of, Main Road, Bilton, Hull | Humberside | Yorkshire and Humber | England | HU11 4 | 516098 | 432170 | East Riding of Yorkshire Council | 15/01752/STPLF | [5 empty] | 2015-06-05 | [6 empty] | 2015-10-15 |  |  |  | 2018-10-15 | 2019-07-01
| 5421 | 2019-12-04 | TGC Renewables/NESF | Land at Radbrook Pastures | Solar Photovoltaics |  |  | 20.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land To The West Of, Admington, Adjacent To Preston Bushes, Preston on Stour, Stratford-On-Avon | Warwickshire | West Midlands | England | CV37 8 | 419590 | 247785 | Stratford on Avon District Council | 15/00588/FUL | APP/J3720/W/16/3164711 |  |  |  |  | 2015-04-27 |  | 2016-06-30 | 2017-03-16 |  |  | 2017-08-10 | 2017-08-10
| 5422 | 2016-09-01 | Blackstock Farms | Pixford Fruit Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Pixford Fruit Farm, Raleighs C, Bishops Lydeard, Combe Florey, Taunton | Somerset | South West | England | TA4 3HS | 315713 | 130570 | Taunton Deane Borough Council | 02/15/0006 | APP/D3315/W/16/3142598 |  |  |  |  | 2015-06-29 |  | 2015-11-26 | 2016-02-09 |  | 2016-08-30
| 5423 | 2020-01-16 | Future Earth Energy | Drakelow Renewable Energy Centre | Advanced Conversion Technologies |  |  | 15 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Drakelow Renewable Energy Centre, Drakelow Park, Burton on Trent | Derbyshire | East Midlands | England | DE!5 9TY | 423377 | 319802 | Derbyshire County Council | CW9/0615/48 | [5 empty] | 2015-06-30 | [6 empty] | 2015-11-24 |  |  |  |  | 2019-09-01
| 5424 | 2017-04-20 | TGC Renewables | Land of Green Lane | Solar Photovoltaics |  |  | 5.77 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At, Green Lane, Marchington, Uttoxeter | Staffordshire | West Midlands | England | ST14 8LQ | 414839 | 330919 | East Staffordshire Borough Council | P/2015/00791 | [5 empty] | 2015-07-03 | [6 empty] | 2015-09-23 |  |  |  | 2018-09-23 | 2016-12-12 | 2017-03-31
| 5425 | 2016-03-04 | Actrees Solar Power/ Vogt Solar | Land At Actrees Farm | Solar Photovoltaics |  | 7230 | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Actrees Farm, Heathfield, Alkington, Berkeley | Gloucestershire | South West | England | GL13 9PP | 371098 | 198169 | Stroud District Council | S.15/1523/FUL | [5 empty] | 2015-06-26 | [6 empty] | 2015-10-29 |  |  |  | 2018-10-29 | 2015-11-25 | 2016-01-28
| 5427 | 2017-09-01 | Novus Solar Developments | Land At Pullen Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land At Pullen Farm, Staplehurst Road, Frittenden, Cranbrook | Kent | South East | England | TN17 2EE | 581204 | 142397 | Maidstone Borough Council | 15/503884/FULL | APP/U2235/W/16/3155702 |  |  |  |  | 2015-06-30 |  | 2016-03-24 | 2016-12-16 |  | 2017-08-25
| 5428 | 2017-06-23 | British Solar Renewables / NextEnergy Solar Fund (NESF) | Land at Bowden Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Bowden Lane, Henstridge, Templecombe | Somerset | South West | England | BA8 0PB | 370004 | 120357 | South Somerset District Council | 15/02718/FUL | [5 empty] | 2015-06-16 | [6 empty] | 2015-10-19 |  |  |  | 2018-10-19 | 2017-01-04 | 2017-03-31
| 5429 | 2017-06-23 | British Solar Renewables / NextEnergy Solar Fund (NESF) | Land at Stalbridge Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Stalbridge Park, Landshire Lane, Henstridge, Templecombe, Somerset | Dorset | South West | England | BA8 0SD | 373303 | 119285 | North Dorset District Council | 2/2015/0898/FUL | [5 empty] | 2015-07-03 | [6 empty] | 2015-10-13 |  |  |  | 2018-10-13 | 2017-01-04 | 2017-03-31
| 5430 | 2016-07-28 | Frogs Loke Solar | Frog's Loke Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Frog''s Loke, North Walsham Road, Norwich, Norfolk | Norfolk | Eastern | England | NR28 9LZ | 629164 | 327731 | North Norfolk District Council | PF/15/0938 | [5 empty] | 2015-06-26 | [6 empty] | 2015-10-16 |  |  |  | 2018-10-16 | 2015-11-16 | 2016-01-12
| 5431 | 2020-03-18 | GreenHedge (BayWa r.e.) / Next Energy Capital | Staughton Airfield Solar Farm | Solar Photovoltaics |  |  | 40 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land At Top Farm and Little Stau, Airfield Industrial Estate, Little Staughton, Bedford, Bedfordshire | Cambridgeshire | Eastern | England | MK44 2BN | 512106 | 261675 | Huntingdonshire District Council | 15/00940/FUL | [5 empty] | 2015-06-18 | [6 empty] | 2015-09-28 |  |  |  | 2018-09-28 | 2019-03-01
| 5432 | 2019-11-14 | Over Farm Solar | Over Farm | Solar Photovoltaics |  |  | 9.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Over Farm, Over Bridge, Over, Gloucester, Gloucestershire | Gloucestershire | South West | England | GL2 8DB | 381282 | 381282 | Tewkesbury Borough Council | 15/00409/FUL | APP/G1630/W/16/3141824 |  |  |  |  | 2015-05-28 |  | 2015-11-24 | 2016-01-22 |  |  | 2016-06-06 | 2016-06-06 |  |  |  | 2019-06-06
| 5433 | 2015-12-02 | Global Renewable Construction | Land Off Penniment Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Off, Penniment Lane, Mansfield, Nottinghamshire | Nottinghamshire | East Midlands | England | NG19 6PH | 450868 | 362069 | Mansfield District Council | 2015/0400/ST | [5 empty] | 2015-07-02 |  | 2015-11-20
| 5434 | 2019-12-04 | TGC Renewables | Land at Mill Farm | Solar Photovoltaics |  |  | 7.05 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Mill Farm, Nottingham Road, Loughborough, Leicestershire | Leicestershire | East Midlands | England | LE11 1AE | 455644 | 315958 | Charnwood Borough Council | P/15/1054/2 | [5 empty] | 2015-06-23 | [6 empty] | 2017-08-15 |  |  |  | 2020-08-15
| 5435 | 2017-05-03 | Lightsource Renewable Energy | Lands West of Belfast Road | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands Approximately 140m West, 66 Belfast Road, Nutts Corner, Crumlin, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT29 4TH | 134568 | 534503 | Northern Ireland Planning Service | LA03/2015/0257/F | [5 empty] | 2015-06-29 | [6 empty] | 2015-12-23 |  |  |  | 2020-12-21 | 2017-02-15 | 2017-03-15
| 5436 | 2015-12-02 | Solar Century | Lane South-East from Cowbridge | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | The Farm, , St. Hilary, The Farm, lane South-East from, Cowbridge, South Glamorgan | Vale of Glamorgan | Wales | Wales | CF71 7DP | 301815 | 173282 | Vale of Glamorgan Council | 2015/00649/FUL | [5 empty] | 2015-06-29 |  | 2015-11-20
| 5437 | 2017-12-01 | Pearmat Solar | Manmoel Road Solar Park | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Pen-y-Fan Farm, Pen-y-Fan Farm Lane, Manmoel, Blackwood, Gwent | Caerphilly | Wales | Wales | NP12 0HZ | 318604 | 201211 | Caerphilly County Borough Council | 15/0433/FULL | [5 empty] | 2015-06-30 | [6 empty] | 2015-11-05 |  |  |  | 2020-11-05 | 2017-01-30 | 2017-03-30
| 5439 | 2016-10-04 | Hadstone Energy | Clandeboye Estate Solar Farm | Solar Photovoltaics |  |  | 10.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Lands located south-west of junction of A2 Belfast Road and B170 Ballysallagh Road, Bangor | Co. Down | Northern Ireland | Northern Ireland | BT19 | 159262 | 532839 | Northern Ireland Planning Service | LA06/2015/0389/F | [5 empty] | 2015-07-06 | 2016-09-15
| 5440 | 2017-01-25 | Wessex Solar Energy | Huntspill Level Solar Park | Solar Photovoltaics |  |  | 5.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bangor (bounded by Belfast Road | Somerset | South West | England | TA9 3NP | 332877 | 144342 | Sedgemoor District Council | 25/15/00014 | [5 empty] | 2015-06-19 | [6 empty] | 2015-09-11 |  |  |  | 2018-09-11 | 2016-01-15 | 2016-03-15
| 5441 | 2019-12-04 | TGC Renewables | Bascote Road Solar Farm | Solar Photovoltaics |  |  | 4.64 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Ballysallagh Road and Clandeboye Avenue, Bascote | Warwickshire | West Midlands | England | CV47 9NN | 441057 | 265143 | Stratford on Avon District Council | 15/01740/FUL | APP/J3720/W/16/3146833 |  |  |  |  | 2015-06-03 |  | 2016-03-03 | 2016-04-06 |  |  | 2016-09-05 | 2016-09-05 |  |  |  | 2019-09-05
| 5442 | 2016-06-14 | Suncredit UK | Land at Box Road | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land N/O Cam and Coaley Railway, Box Road, Cam, Dursley, Gloucestershire | Gloucestershire | South West | England | GL11 5DJ | 375183 | 202249 | Stroud District Council | S.15/1477/FUL | [5 empty] | 2015-06-30 | [6 empty] | 2015-09-29 |  |  |  | 2018-09-29 | 2016-02-15 | 2016-03-24
| 5443 | 2017-07-28 | Lightsource Renewable Energy | Hillside Solar Farm | Solar Photovoltaics |  |  | 25.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lds Approximately 180m S Of, 7a Lough Road, Ballinderry Upper, Lisburn, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT28 2PQ | 129820 | 526363 | Northern Ireland Planning Service | LA05/2015/0305/F | [5 empty] | 2015-06-30 | [6 empty] | 2016-05-19 |  |  |  | 2021-05-18 | 2017-02-15 | 2017-03-15
| 5444 | 2018-07-23 | Wirsol / Island Green Power | Low Farm Solar Array | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Low Farm, Bradley Road, Bradley, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN37 0AL | 523802 | 405691 | North East Lincolnshire Council | DM/0483/15/FUL | [5 empty] | 2015-06-25 | [6 empty] | 2015-10-09 |  |  |  | 2018-10-09
| 5446 | 2017-02-28 | Wessex Solar Energy | Cowles Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Cowles Farm, Elton Road, Elton, Newnham, Gloucestershire | Gloucestershire | South West | England | GL14 1JQ | 369885 | 214260 | Forest of Dean District Council | P0856/15/FUL | APP/P1615/W/16/3148113 |  |  |  |  | 2015-07-01 |  | 2015-10-15 | 2016-04-29 |  | 2017-02-07
| 5447 | 2017-05-26 | Lightsource Renewable Energy | Land south of Wood Lane (Safeguard Bradwell) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land south of, Wood Lane, Bradwall, Sandbach, Cheshire | Cheshire | North West | England | CW11 1PA | 374525 | 362487 | Cheshire East Council | 15/1541C | [5 empty] | 2015-03-31 | [6 empty] | 2015-09-04 |  |  |  |  | 2016-09-22 | 2017-01-15
| 5448 | 2015-08-06 | West Cost Energy | Forrestfield Wind Farm | Wind Onshore |  |  | 13.2 | n/a |  |  |  | 3.3 | 4 | 125 | n/a | Planning Application Submitted | Application Submitted | Site South Of, Airdrie Road, Caldercruix, Airdrie, Strathclyde | North Lanarkshire | Scotland | Scotland | ML6 8NX | 286350 | 666350 | North Lanarkshire Council | 15/01411/FUL | [5 empty] | 2015-07-02
| 5449 | 2018-11-19 | Vale Green Energy | Rotherdale Farm (3rd Phase) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Rotherdale Farm, Long Lane, Tilesford, Pershore, Hereford and Worcester | Hereford and Worcester | West Midlands | England | WR10 2LA | 397764 | 250587 | Wychavon District Council | 15/00835 | [5 empty] | 2015-03-27 | [6 empty] | 2015-07-07
| 5450 | 2019-01-02 | Hadstone Energy | South Antrim Solar Park - Phase 1 | Solar Photovoltaics |  |  | 6.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands approx 550m South of, 99 Dublin Road, Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT41 4PN | 127265 | 541491 | Northern Ireland Planning Service | LA03/2015/0262/F | [5 empty] | 2015-06-30 | [6 empty] | 2016-04-26 |  |  |  | 2021-04-25 | 2018-03-10 | 2018-05-10
| 5451 | 2018-03-02 | Core Aries (Renewable Energy) | Newton Downs Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Newton Downs Farm, Newton Ferrers, Plymouth, Devon | Devon | South West | England | PL8 1JA | 255576 | 49352 | South Hams District Council | 37/1426/15/F | [5 empty] | 2015-06-26 | [6 empty] | 2016-07-15 |  |  |  |  | 2016-10-31 | 2017-02-15
| 5452 | 2019-11-14 | Pike Solar | Highnam Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land At Highnam Farm, Two Mile Lane, Highnam, Gloucester, Gloucestershire | Gloucestershire | South West | England | GL2 8DW | 378972 | 219963 | Tewkesbury Borough Council | 15/00410/FUL | APP/G1630/W/16/3141634 |  |  | 42636 |  | 2015-06-16 |  | 2015-11-24 | 2016-01-22 |  |  | 2016-06-06 | 2016-06-06 |  |  |  | 2019-06-06
| 5453 | 2016-08-31 | Solar Century/ Bluefield Solar | Bunn's Hill Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Bunn's Hill, North Walsham Road, Norwich, Norfolk | Norfolk | Eastern | England | NR6 7JG | 629164 | 327731 | North Norfolk District Council | PF/15/0936 | [5 empty] | 2015-06-26 | [6 empty] | 2015-10-16 |  |  |  | 2018-10-16 | 2015-12-03 | 2016-02-03
| 5454 | 2015-03-04 | Ventus Renewables | Land North West Of Lower Lybster (Resubmission) | Wind Onshore |  |  | 1 | n/a |  |  |  | 1 | 1 | 80 | n/a | Planning Permission Refused | Application Refused | Land 700M North West Of Lower, Lybster, Highlands | Highland | Scotland | Scotland | KW3 | 321192 | 936449 | Highland Council | 15/02386/FUL | [5 empty] | 2015-06-24 |  | 2016-01-26
| 5455 | 2018-04-05 | Cumberhead Wind Energy | Cumberhead Wind Farm | Wind Onshore |  |  | 48 | n/a |  |  |  | 3 | 16 | 125 | n/a | Planning Application Submitted | Application Submitted | Cumberhead, Lanark, Strathclyde | South Lanarkshire | Scotland | Scotland | ML11 0HN | 276581 | 632651 | South Lanarkshire Council | CL/15/0231 | [5 empty] | 2015-06-19
| 5459 | 2015-11-05 | 1 Stop Renewables | Land South West Of Backfield Farm (Resubmission) | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 99.5 | n/a | Planning Permission Refused | Application Refused | Land South West Of, Backfield Farm, Drumlithie, Stonehaven, Grampian | Aberdeen | Scotland | Scotland | AB39 3YN | 375706 | 782283 | Aberdeenshire Council | APP/2015/2092 | [5 empty] | 2015-06-29 |  | 2015-10-29
| 5460 | 2020-03-18 | Green Switch Solutions/Belvedere Energy Developments | Partridge Hill Solar Farm | Solar Photovoltaics |  |  | 33 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Partridge Hill Farm, High Common Lane, Austerfield, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | DN10 6HA | 465403 | 396507 | Doncaster Metropolitan Borough Council | 15/01268/FULM | [5 empty] | 2015-05-20 | [6 empty] | 2016-07-29 |  |  |  | 2019-07-29
| 5461 | 2018-06-25 | Big 60 Million | Northallerton | Solar Photovoltaics |  |  | 28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | White House Farm, Great Smeaton, Northallerton, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | DL6 2NF | 436402 | 495097 | Hambleton District Council | 15/01335/FUL | [5 empty] | 2015-06-12 | [6 empty] | 2015-10-15 |  |  |  | 2018-10-15
| 5462 | 2019-10-21 | Green Energy UK Direct | Bryncoch Solar Farm | Solar Photovoltaics |  |  | 19 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Bryncoch, Ferryside, Dyfed | Carmarthenshire | Wales | Wales | SA17 5YD | 238277 | 210810 | Carmarthenshire County Council | W/32171 | [5 empty] | 2015-06-15 | [6 empty] | 2015-09-11 |  |  |  | 2020-09-11
| 5463 | 2018-04-30 | Lightsource Renewable Energy | Sealstown Road Solar Farm | Solar Photovoltaics |  |  | 6.66 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Sealstown Road, Newtownabbey, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT36 0BQ | 145202 | 540405 | Northern Ireland Planning Service | LA03/2015/0250/F | [5 empty] | 2015-06-25 | [6 empty] | 2015-11-17 |  |  |  | 2020-11-16
| 5464 | 2020-05-27 | Selettra Holding | Land East of Sandyford | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Field 775M East Of, Sandyford Farm, Sandyford, Kirriemuir, Tayside | Angus | Scotland | Scotland | DD8 5QH | 342302 | 754319 | Angus Council | 15/00603/FULL | [5 empty] | 2015-06-26 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30
| 5465 | 2016-02-05 | Sunsave 38/ Vogt Solar | Rushmoor Lane Farm (Cheshire Coppice) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of, Rushmoor Lane, Bratton, Telford | Shropshire | West Midlands | England | TF5 0DA | 362767 | 314537 | Telford and Wrekin Council | TWC/2015/0560 | [5 empty] | 2015-06-17 | [6 empty] | 2015-10-13 |  |  |  | 2018-10-13 | 2015-11-25 | 2016-01-28
| 5466 | 2015-11-05 | Solar Power South | Eashing Farm (Resubmission) | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Eashing Farm, Eashing Lane, Godalming, Surrey | Surrey | South East | England | GU7 2QA | 495056 | 143760 | Guildford Borough Council | 15/P/01126 | [5 empty] | 2015-06-08 |  | 2015-10-14
| 5467 | 2019-03-22 | Barr Environmental | Killoch Depot | EfW Incineration |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Killoch Depot Killoch Colliery, Ochiltree, Cumnock, Strathclyde | East Ayrshire | Scotland | Scotland | KA18 2RL | 248650 | 620732 | East Ayrshire Council | 15/0413/PP | [5 empty] | 2015-06-09 | [6 empty] | 2017-06-22 |  |  |  | 2020-06-22
| 5470 | 2016-12-23 | INRG Solar | Redeham Hall Solar Farm | Solar Photovoltaics |  |  | 5.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Redeham Hall, Smallfield, Horley, Surrey | Surrey | South East | England | RH6 9SA | 532177 | 141979 | Tandridge District Council | 2015/1056 | APP/M3645/W/16/3146389 |  |  |  |  | 2015-06-10 |  | 2016-01-15 | 2016-03-19 |  | 2016-12-05
| 5471 | 2018-09-27 | Green Power Consultants | Jamesfield Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land 200M South E Of The Bothy, Jamesfield, Newburgh, Cupar, Fife | Perth and Kinross | Scotland | Scotland | KY14 6EW | 320043 | 717986 | Perth and Kinross Council | 15/00833/FLL | [5 empty] | 2015-06-17 | [6 empty] | 2015-08-14 |  |  |  | 2018-08-14
| 5472 | 2017-06-27 | Tealing Solar Parks | Fullenton Solar Farm | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Fullerton Farm, Fullerton Road, Cottonworth, Andover, Hampshire | Hampshire | South East | England | SP11 7JX | 437992 | 139758 | Test Valley Borough Council | 15/01401/FULLN | [5 empty] | 2015-06-25 | [6 empty] | 2015-12-11 |  |  |  | 2018-12-11 | 2016-10-15 | 2016-12-15
| 5474 | 2019-03-26 | Island Renewable Energy | Ballynagilly Renewable Energy Project | Wind Onshore |  |  | 18.4 | n/a |  |  |  | 2.3 | 8 | 126.5 | n/a | Appeal Withdrawn | Application Refused | Stanley Bell and Sons Ltd Quar, Ballynagilly Townland, Lissan, Cookstown, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT80 9SX | 90358 | 543567 | Northern Ireland Planning Service | LA09/2015/0459/F | 2018/A0083 |  |  |  |  | 2015-06-26 |  | 2018-05-11 | 2018-09-07 | 2019-02-06
| 5475 | 2018-10-26 | British Solar Renewables | Churchers Common Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Churchers Common Land Off P, Pound Lane, Ampfield, Romsey, Hampshire | Hampshire | South East | England | SO51 9BL | 440177 | 121880 | Test Valley Borough Council | 15/01399/FULLS | [5 empty] | 2015-06-19 | [6 empty] | 2015-12-01 |  |  |  | 2018-12-01
| 5476 | 2016-12-15 | INRG Solar | Land North West of Magor Service Station | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land North West of, Magor Service Station/Area INR, Magor, Caldicot, Gwent | Monmouthshire | Wales | Wales | NP26 3YL | 342162 | 187978 | Monmouthshire County Council | DC/2015/00573 | [5 empty] | 2015-05-11 | [6 empty] | 2015-12-14
| 5477 | 2017-03-24 | Kronos Solar | Cwm Derwyn Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cwm Derwyn Farm, Waycock Road, Barry, South Glamorgan | Vale of Glamorgan | Wales | Wales | CF62 3AA | 308691 | 169396 | Vale of Glamorgan Council | 2015/00632/FUL | [5 empty] | 2015-06-01 | [6 empty] | 2015-09-04 |  |  |  |  | 2017-01-15 | 2017-03-17
| 5478 | 2017-02-01 | First Renewable Developments | Land to the west of Ashfordby Business Park | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field 0051 and 7540, Welby Road, Asfordby Hill, Melton Mowbray, Leicestershire | Leicestershire | East Midlands | England | LE14 3RE | 471735 | 320630 | Melton Borough Council | 15/00424/FUL | [5 empty] | 2015-06-11 | [6 empty] | 2015-09-10 |  |  |  | 2018-09-10 | 2016-02-26 | 2016-04-26
| 5479 | 2018-10-25 | Green Cat Renewables | Hill of Blairfowl Solar Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land To The North Of St Johns, Fyvie, Turriff, Grampian | Aberdeen | Scotland | Scotland | AB53 8PX | 379540 | 837700 | Aberdeenshire Council | APP/2015/1819 | [5 empty] | 2015-06-16 | [6 empty] | 2015-08-07 |  |  |  | 2018-08-07
| 5480 | 2020-05-28 | TGC Renewables/NESF | Bourne Road | Solar Photovoltaics |  |  | 19.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Glebe Farm, Bourne Road, Defford, Worcester, Hereford and Worcester | Hereford and Worcester | West Midlands | England | WR8 9BT | 389827 | 241212 | Wychavon District Council | 15/01323 | [5 empty] | 2015-05-21 | [6 empty] | 2015-10-21
| 5481 | 2016-09-01 | Ventient (formerly Infinis) | Mynydd Pen-y-Graig Wind Farm | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 | 115 | n/a | Planning Application Withdrawn | Application Withdrawn | Mynydd Penygraig, Pen-y-Graig, Cardiff, South Glamorgan | Rhondda Cynon Taff | Wales | Wales | CF24 | 298670 | 190740 | Rhondda Cynon Taff County Borough Council | 15/0831/10 | [5 empty] | 2015-06-18 | 2016-08-17
| 5482 | 2020-05-28 | Gridserve | York Solar Farm | Solar Photovoltaics |  |  | 34.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Boscar Grange Farm, Thirsk Road, Easingwold, York, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO61 3NQ | 450521 | 472345 | Hambleton District Council | 15/01268/FUL | [5 empty] | 2015-06-05 | [6 empty] | 2015-09-21 |  |  |  |  | 2019-05-23 | 2019-12-18
| 5483 | 2016-07-28 | Solar Century/ Bluefield Solar | Land Off Folly Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Off, Folly Lane, Stickney, Boston, Lincolnshire | Lincolnshire | East Midlands | England | PE22 8BN | 532650 | 358372 | East Lindsey District Council | S/203/01106/15 | [5 empty] | 2015-06-18 | [6 empty] | 2015-09-17 |  |  |  | 2018-09-17 | 2016-01-05 | 2016-03-07
| 5484 | 2015-11-05 | Lightsource Renewable Energy | Cask Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Cask Farm, Mythop Road, Weeton With Preese, Preston, Blackpool, Lancashire | Lancashire | North West | England | FY4 4XF | 336684 | 434830 | Fylde Borough Council | 15/0406 | [5 empty] | 2015-06-17 |  | 2015-10-12
| 5485 | 2016-06-17 | Murex Energy | Land At Bake Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Bake Farm, Bake Lane, Trerulefoot, Saltash, Cornwall | Cornwall | South West | England | PL12 5 | 232647 | 58419 | Cornwall Council | PA15/04793 | [5 empty] | 2015-06-19 | [6 empty] | 2015-09-01 |  |  |  | 2018-09-01 | 2016-01-21 | 2016-03-31
| 5486 | 2017-07-20 | Solar Power Inc UK Services/SPI China (HK) | Land To The South Of Todderstaffe | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ld To The S Of Todderstaffe Ha, Singleton, Weeton With Preese, Poulton-Le-Fylde, Lancashire | Lancashire | North West | England | FY6 8LF | 336767 | 436761 | Fylde Borough Council | 15/0380 | [5 empty] | 2015-06-18 | [6 empty] | 2015-11-17 |  |  |  | 2018-11-16 | 2016-01-04 | 2017-03-28
| 5487 | 2016-04-22 | Sunsave 30 (Strettington)/ Vogt solar | Strettington Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field South East Of Temple Bar, Strettington, Boxgrove, Chichester, West Sussex | West Sussex | South East | England | PO18 0LB | 489500 | 107164 | Chichester District Council | 15/01497/FUL | [5 empty] | 2015-05-15 | [6 empty] | 2015-10-21 |  |  |  | 2018-10-21 | 2015-11-25 | 2016-03-23
| 5497 | 2017-04-26 | Octopus Investments | Cressing Solar Farm (Phase 1) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South Of Sheepcote Wood B, Witham Road, Cressing, Braintree, Essex | Essex | Eastern | England | CM77 8NZ | 579287 | 219000 | Braintree District Council | 15/00949/FUL | [5 empty] | 2015-07-24 | [6 empty] | 2015-11-12 |  |  |  | 2018-11-12 | 2016-05-01 | 2016-03-16
| 5498 | 2017-04-26 | Conergy | Land north of Ashton Road | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north of, Ashton Road, Ashton Common, Steeple Ashton, Trowbridge, Wiltshire | Wiltshire | South West | England | BA14 6DY | 389300 | 158100 | Wiltshire Council | 15/07413/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-12-22 |  |  |  | 2018-12-22 | 2016-12-24 | 2017-03-24
| 5499 | 2016-04-01 | Vattenfall | Parc Cynog | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Parc Cynog, Pendine, Carms | Carmarthenshire | Wales | Wales | SA33 4PT | 225230 | 209760 | Carmarthenshire County Council | W/32580 | [5 empty] | 2015-08-10 | [6 empty] | 2015-11-10 |  |  |  | 2018-11-10 | 2016-01-18 | 2016-03-24
| 5506 | 2017-05-31 | Big 60 Million | Albrighton Solar farm | Solar Photovoltaics |  |  | 15.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The North of Harriotts Hayes Lane, Codsall Wood, Wolverhampton | Shropshire | West Midlands | England | WV8 1RQ | 383131 | 304665 | Shropshire Council | 15/02787/FUL | [5 empty] | 2015-07-24 | [6 empty] | 2015-12-14 |  |  |  | 2018-12-14 | 2016-11-28 | 2017-02-28
| 5507 | 2015-12-02 | Williams House Energy | Fawkes 2 Solar Farm | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | (Site 2) To The West Of, Stanley Downton Sewage Works, Leonard Stanley, Stonehouse | Gloucestershire | South West | England | GL10 3 | 378821 | 204696 | Stroud District Council | S.15/1781/FUL | [5 empty] | 2015-07-28 |  | 2015-11-26
| 5508 | 2017-06-23 | British Solar Renewables | Clapton Farm Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Tinkers Lane, Southeast Of B3081, Cucklington, Wincanton | Somerset | South West | England | BA9 | 375763 | 128657 | South Somerset District Council | 15/03373/FUL | [5 empty] | 2015-07-23 | [6 empty] | 2015-11-17 |  |  |  | 2018-11-17 | 2017-01-20 | 2017-03-31
| 5509 | 2019-08-13 | Delta Solar | Land North of Saddler Nook Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land North Of, Saddler Nook Lane, Whittington, Carnforth | Lancashire | North West | England | LA6 2QF | 359086 | 477074 | Lancaster City Council | 15/00876/FUL | [5 empty] | 2015-08-10 | [6 empty] | 2015-10-22 |  |  |  | 2018-10-22
| 5510 | 2020-02-04 | Good Energy | Land to the North of Cursey Lane | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land Off Cursey Lane, Elmstone Hardwicke, Cheltenham | Gloucestershire | South West | England | GL51 9TF | 391064 | 228110 | Tewkesbury Borough Council | 15/00801/FUL | APP/G1630/W/16/3146600 |  |  |  |  | 2015-07-22 |  | 2015-11-24 | 2016-03-30 |  |  | 2016-11-22 | 2016-11-22
| 5512 | 2017-06-23 | British Solar Renewables | Galton Manor Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to North East of Galton Road, Galton, Dorchester | Dorset | South West | England | DT2 8BY | 378440 | 85628 | West Dorset District Council | WD/D/15/001708 | [5 empty] | 2015-07-14 | [6 empty] | 2016-09-07 |  |  |  | 2019-09-07 | 2017-01-20 | 2017-03-31
| 5513 | 2017-02-27 | Green Hedge (BayWa r.e.) | Wormit Solar Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North East of Kilmany Road, Wormit, Newport-On-Tay | Fife | Scotland | Scotland | DD6 8P | 340703 | 725248 | Fife Council | 15/02521/FULL | [5 empty] | 2015-07-20 | [6 empty] | 2015-10-09 |  |  |  | 2018-10-09 | 2016-01-15 | 2017-03-31
| 5514 | 2015-11-04 | CSI FS Home Farm Limited | Home Farm (resubmission) | Solar Photovoltaics |  |  | 1.94 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Home Farm, Street Lane, Denby, Ripley | Derbyshire | North East | England | DE5 8NE | 438458 | 348482 | Amber Valley Borough Council | AVA/2015/0628 | [5 empty] | 2015-07-23 |  | 2015-10-13
| 5515 | 2015-11-05 | Omicron Solar | Land at Lane Head | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Lane Head, Northwest o, Beckside, Cartmel, Grange Over Sands | Cumbria | North West | England | LA11 | 336800 | 480900 | South Lakeland District Council | SL/2015/0693 | [5 empty] | 2015-07-27 |  | 2015-10-29
| 5516 | 2016-05-10 | First Milk Cheese Company | Aspatria Creamery | Anaerobic Digestion |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Aspatria Creamery, Station Road, Aspatria, Wigton | Cumbria | North West | England | CA7 2AR | 314453 | 541167 | Allerdale Borough Council | 2/2015/0401 | [5 empty] | 2015-06-29 | [6 empty] | 2015-08-10 |  |  |  |  | 2015-08-11 | 2016-04-05
| 5517 | 2019-08-27 | Power for Wales Inc | Rhas Fach Farm | Solar Photovoltaics |  |  | 1.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Rhas Fach Farm, Heol Mansant, Pontyates, Llanelli, Dyfed | Carmarthenshire | Wales | Wales | SA15 5SB | 246273 | 208842 | Carmarthenshire County Council | W/32377 | [5 empty] | 2015-07-22 | [6 empty] | 2015-09-30 |  |  |  | 2020-09-30
| 5518 | 2020-05-21 | Fulwood Grange Solar Farm Limited | Fulwood Grange Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Fulwood Grange Farm, Pinxton Lane, Sutton-In-Ashfield | Nottinghamshire | East Midlands | England | NG17 1JF | 447248 | 357200 | Ashfield District Council | V/2015/0455 | [5 empty] | 2015-07-30 | [6 empty] | 2015-11-25 |  |  |  | 2018-11-25
| 5519 | 2016-12-23 | Sirius SBC Renewables | Poyle Park Solar Farm | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Former Poyle Park Manor Landfi, Old Bath Road, Colnbrook, Slough | Berkshire | South East | England | SL3 0HY | 502959 | 176586 | Slough Borough Council | P/10012/005 | APP/J0350/W/16/3144685 |  |  |  |  | 2015-07-29 |  | 2015-10-13 | 2016-03-02 |  | 2016-12-19
| 5520 | 2016-08-18 | Lightsource Renewable Energy | The Breck | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | The Breck, Breck Lane, Barrow Hill, Chesterfield | Derbyshire | East Midlands | England | S43 2NP | 442646 | 376222 | Chesterfield Borough Council | CHE/15/00460/FUL | [5 empty] | 2015-07-31 | [6 empty] | 2015-10-27 |  |  |  | 2018-10-27 | 2016-02-01 | 2016-03-17
| 5521 | 2019-06-10 | Big 60 Million | Cambridge Solar Farm | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land east of Battle Gate Road, St. Neots Road, Dry Drayton, Cambridge | Cambridgeshire | Eastern | England | CB23 8BA | 535442 | 261838 | South Cambridgeshire District Council | S/1714/15/FL | [5 empty] | 2015-07-03 |  | 2016-02-11
| 5522 | 2017-02-28 | Blue Planet Solar | College Farm | Solar Photovoltaics |  |  | 4.76 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land Lying to the West of, Bosty Lane, College Farm, Aldridge, Walsall | West Midlands | West Midlands | England | WS9 0LF | 403610 | 300176 | Walsall Council | 15/0628/FL | APP/V4630/W/16/3148504 |  |  |  |  | 2015-05-28 |  | 2015-11-06 | 2016-04-21 |  | 2017-02-01
| 5523 | 2017-10-24 | North Tenement Solar Farm Limited | North Tenement | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | North Tenement, Dredgeman Hill, Haverfordwest, Dyfed | Pembrokeshire | Wales | Wales | SA61 1XL | 193951 | 212945 | Pembrokeshire County Council | 15/0443/PA | [5 empty] | 2015-07-22 | [6 empty] | 2016-05-18 |  |  |  | 2019-05-18 | 2017-02-10 | 2017-03-28
| 5524 | 2017-06-30 | Lightsource Renewable Energy | Cwrt Henllys Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Church Farm, Cwm Lane, Henllys, Cwmbran, Gwent | Torfaen | Wales | Wales | NP44 7AS | 325372 | 191949 | Torfaen County Borough Council | 15/P/00434 | [5 empty] | 2015-07-22 | [6 empty] | 2016-06-16 |  |  |  |  | 2016-10-29 | 2016-12-29
| 5525 | 2017-05-31 | Anesco | Land at Wreay | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Wreay, Calthwaite, Penrith, Carlisle | Cumbria | North West | England | CA4 0PY | 342451 | 547548 | Eden District Council | 15/0653 | APP/H0928/W/15/3140750 |  |  |  |  | 2015-07-31 |  | 2015-10-29 | 2016-01-12 |  |  | 2016-08-04 | 2016-08-04 |  |  |  |  | 2016-12-15 | 2017-03-29
| 5526 | 2016-05-04 | Blue Planet Solar | Two Dales Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Two Dales Farm, Salmon Lane, Kirkby-in-Ashfield, Nottingham | Nottinghamshire | East Midlands | England | NG17 9LA | 449214 | 353084 | Ashfield District Council | V/2015/0459 | [5 empty] | 2015-07-29 |  | 2016-03-30
| 5527 | 2016-07-18 | Public Power Solutions/ Swindon Borough Council | Common Farm | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Common Farm, Wharf Road, Wroughton, Swindon | Wiltshire | South West | England | SN4 9QJ | 413720 | 181837 | Swindon Borough Council | S/LDO/15/1247 | [5 empty] | 2015-07-29 | [6 empty] | 2015-10-13 |  |  |  | 2018-10-13 | 2016-05-02 | 2016-06-29
| 5529 | 2017-05-26 | Lightsource Renewable Energy | Fields Farm (Agden) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fields Farm, Agden Near Whitchurch | Cheshire | North West | England | SY13 4RB | 351447 | 344514 | Cheshire West and Chester Council | 15/03109/FUL | [5 empty] | 2015-07-23 | [6 empty] | 2016-02-10 |  |  |  | 2019-02-10 | 2016-12-09 | 2017-02-09
| 5530 | 2017-05-19 | Hill Farm | Land at Hill Farm | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hill Farm, Spring Lane, Packington, Ashby-De-La-Zouch | Leicestershire | East Midlands | England | LE65 1WU | 437532 | 314290 | North West Leicestershire District Council | 15/00719/FULM | [5 empty] | 2015-07-23 | [6 empty] | 2015-10-12 |  |  |  | 2018-10-12 | 2016-08-15 | 2016-11-01
| 5531 | 2017-05-26 | Lightsource Renewable Energy | Land to North West of Lodge Farm (Park Farm) | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To North West Of Lodge Fa, Lodge Hill, Caerleon | Newport | Wales | Wales | NP18 3BX | 331406 | 191683 | Newport City Council | 15/0902 | [5 empty] | 2015-07-23 | [6 empty] | 2016-02-08 |  |  |  | 2021-02-08 | 2016-12-05 | 2017-03-03
| 5532 | 2016-11-23 | SBC Renewables | Seaton Road Solar Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north of, Seaton Road, Uppingham, Oakham | Leicestershire | East Midlands | England | LE15 9HH | 487565 | 299395 | Rutland County Council | 2015/0662/MAJ | [5 empty] | 2015-07-23 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30 | 2016-10-15 | 2017-03-31
| 5533 | 2019-07-18 | Derbyshire County Council | Williamthorpe Colliery | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Williamthorpe Colliery, Mansfield Road, Heath | Derbyshire | East Midlands | England | DE4 3AG | 430072 | 360717 | Derbyshire County Council | CD4/0615/37 | [5 empty] | 2015-07-24 | [6 empty] | 2015-12-07 |  |  |  | 2018-12-07
| 5534 | 2020-03-18 | BE Renewables | Land at Tip Field | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land At Tip Field South Of, North Moss Lane, Formby, Liverpool | Merseyside | North West | England | L37 0A | 332212 | 409033 | Sefton Council | DC/2015/01265 | [5 empty] | 2015-07-29 | [6 empty] | 2016-09-23 |  |  |  | 2019-09-23 | 2019-09-01
| 5536 | 2017-04-25 | Navitas Project | Wick Lane Solar Ltd | Solar Photovoltaics |  |  | 2.79 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Wick Lane, Brent Knoll, Highbridge | Somerset | South West | England | TA9 4BU | 332955 | 152735 | Sedgemoor District Council | 07/15/00016 | [5 empty] | 2015-07-14 | [6 empty] | 2015-12-17 |  |  |  | 2018-12-17 | 2017-01-15 | 2017-03-20
| 5538 | 2017-08-31 | Wirisol (Sun & Soil) | Otherton Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Otherton Farm, Otherton Lane, Cotheridge, Worcester | Hereford and Worcester | West Midlands | England | WR6 5LS | 380529 | 254163 | Malvern Hills District Council | 15/00957/FUL | [5 empty] | 2015-07-29 | [6 empty] | 2015-12-18 |  |  |  | 2018-12-18 | 2017-01-21 | 2017-03-21
| 5539 | 2016-09-01 | Derbyshire County Council | Swanwick Colliery | Solar Photovoltaics |  |  | 1.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land Adjacent To Thornton Park, Old Swanwick Colliery Road, Swanwick, Alfreton | Derbyshire | East Midlands | England | DE55 1BH | 440671 | 351384 | Amber Valley Borough Council | AVA/2015/0715 | [5 empty] | 2015-07-30
| 5540 | 2017-03-21 | Anesco | Nanthenfoel Farms | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Nanthenfoel Farm, Creuddyn Bridge, Lampeter | Ceredigion | Wales | Wales | SA48 8AZ | 254014 | 252465 | Ceredigion County Council | A150516 | [5 empty] | 2015-07-27 | [6 empty] | 2015-11-18 |  |  |  | 2020-11-18 | 2016-11-30 | 2017-03-15
| 5541 | 2016-01-06 | Elgar Middleton | Land at Winshenford | Solar Photovoltaics |  |  | 6.97 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Green Farm and Bush Farm, Monkwood Green, Hallow, Worcester | Hereford and Worcester | West Midlands | England | WR2 6NX | 379934 | 260586 | Malvern Hills District Council | 15/01033/FUL | [5 empty] | 2015-07-31 |  | 2015-12-09
| 5543 | 2019-11-22 | Solar Century/ Bluefield Solar | New Road Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land Adj A47 And North Of, New Road, Bawburgh, Norwich | Norfolk | Eastern | England | NR9 3LZ | 616451 | 309303 | South Norfolk Council | 2015/1678 | [5 empty] | 2015-07-23 | [6 empty] | 2015-11-02 |  |  |  | 2018-11-02 | 2016-12-01
| 5544 | 2016-05-04 | Global Renewable Construction | Tir Nyth Soalr Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land To The South West (0.1 Km) Of Bryn Rhedyn And To The North (0.15 Km) Of Nant Y Fedw Farm Bedlinog | Merthyr Tydfil | Wales | Wales | CF46 6UF | 308906 | 200688 | Merthyr Tydfil County Borough Council | P/15/0254 | [5 empty] | 2015-07-30 |  | 2016-03-31
| 5545 | 2016-06-21 | Private Developer | Land at Green Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Green Farm, Allensmore, Hereford | Hereford and Worcester | West Midlands | England | HR2 9AH | 347256 | 235800 | Herefordshire Council | P152200/F | [5 empty] | 2015-07-29 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30 | 2016-05-21 | 2016-06-21
| 5546 | 2015-03-04 | Lightsource Renewable Energy | Eastern Site | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land to NW of Lodge Farm, Lodge Hill, Caerleon | Newport | Wales | Wales | NP18 3DL | 332172 | 192076 | Newport City Council | 15/0903 | [5 empty] | 2015-07-22 |  | 2016-02-08
| 5547 | 2017-05-31 | Solar Securities Group | West Venn Solar Farm (resubmission) | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At West Venn Farm, Ashwater, Beaworthy | Devon | South West | England | EX21 5DF | 237900 | 97500 | Torridge District Council | 1/0566/2015/FULM | [5 empty] | 2015-06-03 | [6 empty] | 2015-10-01 |  |  |  | 2018-10-01 | 2016-06-15 | 2017-03-13
| 5548 | 2016-11-23 | SBC Renewables | Corntown Farm | Solar Photovoltaics |  |  | 3.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Corntown Farm, Corntown, Bridgend, Mid Glamorgan | Vale of Glamorgan | Wales | Wales | CF35 5BB | 293814 | 176736 | Vale of Glamorgan Council | 2015/00859/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-11-20 |  |  |  | 2020-11-20 | 2016-10-15 | 2017-03-15
| 5549 | 2017-02-02 | Vortex (formerly SunEdison) | Brizlincote Hall Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at SK2721 4055 South East, Swadlincote | Derbyshire | East Midlands | England | DE11 | 427420 | 321550 | South Derbyshire District Council | 9/2015/0564 | [5 empty] | 2015-07-20 |  | 2015-11-09
| 5550 | 2018-09-25 | Solstice Renewables | Parchfields Farm | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Parchfields Farm, Blithbury Road, Colton, Rugeley | Staffordshire | West Midlands | England | WS15 3HB | 405132 | 319272 | Lichfield District Council | 15/00834/FULM | [5 empty] | 2015-07-21 | [6 empty] | 2015-10-19 |  |  |  | 2018-10-19
| 5551 | 2016-11-23 | SBC Renewables | Wally Corner Landfill Site | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off, Burcot Lane, Dorchester-on-Thames, Berinsfield, Wallingford | Oxfordshire | South East | England | OX10 7 | 458069 | 195731 | South Oxfordshire District Council | P15/S2486/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-09-29 |  |  |  | 2018-09-29 | 2016-10-15 | 2017-03-15
| 5552 | 2017-03-31 | Iceni Energy 2 | Link Park Industrial Estate | Biomass (dedicated) |  |  | 45 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Plots 50, 60, 70, Otterpool Lane, Link Park Industrial Estate, Lympne, Hythe | Kent | South East | England | CT21 4LR | 611184 | 136005 | Shepway District Council | Y15/0751/SH | [5 empty] | 2015-07-29 | 2017-03-23
| 5553 | 2017-02-01 | Mulbrick Clean Energy | Little Snodworth Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Little Snodworth Farm, Snodworth Road, Langho, Blackburn | Lancashire | North West | England | BB6 8DS | 370476 | 432960 | Ribble Valley Borough Council | 3/2015/0605 | APP/T2350/W/16/3147854 |  |  |  |  | 2015-07-29 |  | 2015-10-16 | 2016-05-03 |  | 2016-12-22
| 5554 | 2016-06-14 | Stretton Solar | Land North of the Wood at Averill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Averill Farm, Evershill Lane, Morton, Alfreton | Derbyshire | East Midlands | England | DE55 6HB | 440527 | 361250 | North East Derbyshire District Council | 15/00751/FL | [5 empty] | 2015-07-22 | [6 empty] | 2015-10-21 |  |  |  | 2018-10-21 | 2016-01-15 | 2016-03-15
| 5555 | 2016-10-24 | Associated British Ports | ANP Newport Wind Turbine | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 2 | 126 | n/a | Operational | Operational | Land To South Of South Dock, Alexandra Docks, And Adjacent to River Usk, East Way Road | Newport | Wales | Wales | NP20 2UW | 332583 | 184564 | Newport City Council | 15/0839 | [5 empty] | 2015-07-24 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30 | 2016-03-31 | 2016-08-15
| 5556 | 2016-09-01 | Colintraive and Glendarual Development Trust | Stronafian Community Forest Wind Turbines | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 | 86.5 | n/a | Planning Permission Refused | Application Refused | Land At Cruach Nam Mult Strona, Glendaruel | Argyll and Bute | Scotland | Scotland | PA25 | 201797 | 684359 | Argyll and Bute Council | 15/02060/PP | [5 empty] | 2015-07-30 |  | 2016-08-24
| 5558 | 2017-02-01 | Far West Solar | Land at Boslandew Hill | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land At Boslandew Hill, Paul, Penzance | Cornwall | South West | England | TR19 6UD | 146058 | 26681 | Cornwall Council | PA15/05386 | APP/D0840/W/16/3146032 |  |  |  |  | 2015-07-03 |  | 2015-12-23 | 2016-03-15 |  | 2017-01-05
| 5559 | 2017-10-31 | First Renewable Developments/ Harworth Group | Sudforth Lane (Kellingley Solar Farm) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Sudforth Lane, Beal, Goole, Humberside | North Yorkshire | Yorkshire and Humber | England | DN14 0SZ | 452849 | 423224 | Selby District Council | 2015/0415/FUL | [5 empty] | 2015-04-22 | [6 empty] | 2015-08-07 |  |  |  |  | 2017-01-15 | 2017-03-30
| 5560 | 2017-12-04 | Greencoat Capital | Berthlwyd Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Berthlwyd Farm, Maendy Road, Penycoedcae, Pontypridd | Rhondda Cynon Taff | Wales | Wales | CF37 1PS | 307796 | 188016 | Rhondda Cynon Taff County Borough Council | 15/0777/10 | [5 empty] | 2015-06-01 | [6 empty] | 2016-03-17 |  |  |  | 2021-03-17 | 2016-12-12 | 2017-02-15
| 5561 | 2020-06-16 | Fridays & Rika Biofuels | Knoxbridge Farm | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land to the north of existing farm buildings, Knoxbridge Farm, Cranbrook Road, Frittenden | Kent | South East | England | TN17 2BT | 579452 | 141169 | Kent County Council | KCC/TW/0170/2015 | [5 empty] | 2015-06-04 | [6 empty] | 2015-09-03 |  |  |  |  | 2019-03-15
| 5562 | 2016-07-28 | Pinguin Foods Ltd | Pinguin Foods | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Pinguin Foods, Marsh Lane, Boston | Lincolnshire | East Midlands | England | PE21 7RY | 533111 | 342691 | Boston Borough Council | B/15/0113 | [5 empty] | 2015-02-24 | [6 empty] | 2015-06-11 |  |  |  |  | 2016-02-03 | 2016-03-23
| 5563 | 2016-05-04 | BE Renewables | Little Frome Farm | Solar Photovoltaics |  |  | 16.14 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Little Frome, Linton Lane, Herefordshire, Bromyard | Hereford and Worcester | West Midlands | England | HR7 4RX | 365245 | 253561 | Herefordshire Council | P151506/F | APP/W1850/W/15/3140783 |  |  |  |  | 2015-06-02 |  | 2015-09-22 | 2016-01-11 |  | 2016-04-13
| 5564 | 2016-12-23 | SEP Solar | Wood Farm Solar Park (linked site) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Opp. Kingston Lane, Manor Farm, Deeside Lane, Sealand, Chester | Flintshire | Wales | Wales | CH1 6BP | 335816 | 367450 | Flintshire County Council | 053687 | APP/A6835/A/16/3151112 |  |  |  |  | 2015-05-11 |  | 2016-04-04 | 2016-07-13 |  | 2016-12-14
| 5565 | 2016-12-23 | SEP Solar | Banks Farm Solar Park (linked site) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Deeside Lane, Sealand, Chester | Flintshire | Wales | Wales | CH1 6BQ | 367788 | 334867 | Flintshire County Council | 053686 | APP/A6835/A/16/3151110 |  |  |  |  | 2015-05-11 |  | 2016-04-04 | 2016-07-13 |  | 2016-12-14
| 5567 | 2019-05-23 | BNRG Renewables UK | Snowdown Colliery | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Former Snowdown Colliery, Dorman Avenue South, Snowdown, Aylesham, Canterbury | Kent | South East | England | CT3 3AD | 624875 | 150964 | Dover District Council | 15/00777 | [5 empty] | 2015-08-20 | [6 empty] | 2016-01-28 |  |  |  | 2019-01-28
| 5568 | 2016-08-18 | Lightsource Renewable Energy | Land East of Lawn Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East Of, Lawn Lane, Coven, Wolverhampton | Staffordshire | West Midlands | England | WV9 5AX | 390500 | 304757 | South Staffordshire Council | 15/00648/FUL | [5 empty] | 2015-08-13 | [6 empty] | 2015-11-12 |  |  |  | 2018-11-12 | 2016-02-15 | 2016-03-30
| 5569 | 2020-06-11 | Elgin Energy EsCo | Carey Solar Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Carey Solar Farm, Abernethy, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 9LN | 317354 | 716778 | Perth and Kinross Council | 15/01327/FLL | [5 empty] | 2015-08-12 | [6 empty] | 2015-11-11 |  |  |  | 2018-11-10
| 5570 | 2018-08-29 | RF Logan & Co | Land to the North West of Sypsies Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land To The North West Of Farm, Sypsies, Crail, Anstruther | Fife | Scotland | Scotland | KY10 3XA | 359901 | 707818 | Fife Council | 15/00525/FULL | [5 empty] | 2015-05-28 | [6 empty] | 2015-09-09 |  |  |  | 2018-09-09
| 5571 | 2019-08-27 | Power for Wales Inc | Pistyllgwyn Farm | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Pistyllgwyn, Bronwydd Arms, Carmarthen | Carmarthenshire | Wales | Wales | SA33 6JD | 241250 | 224375 | Carmarthenshire County Council | W/32460 | [5 empty] | 2015-08-06 | [6 empty] | 2015-12-21 |  |  |  | 2020-12-21
| 5572 | 2017-02-01 | Trina Solar | Land off Ford Lane | Solar Photovoltaics |  |  | 4.65 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Between M20 And M26 West, Ford Lane, Wrotham Heath, Sevenoaks | Kent | South East | England | TN15 7 | 563507 | 158908 | Tonbridge and Malling Borough Council | 15/02431/FL | [5 empty] | 2015-07-23 | [6 empty] | 2015-11-30 |  |  |  | 2020-11-30 | 2016-04-01 | 2016-11-17
| 5573 | 2016-09-01 | Elgin Energy | Dunscombe Solar | Solar Photovoltaics |  |  | 4.96 | n/a | 1.4 | n/a |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land a Dunscombe, Cheriton Fitzpaine, Crediton, Newton St Cyres | Devon | South West | England | EX17 4JU | 282739 | 99967 | Mid Devon District Council | 15/01194/MFUL | APP/Y1138/W/16/3147127 |  |  |  |  | 2015-08-07 |  | 2015-12-11 | 2016-04-26 |  | 2016-08-02
| 5574 | 2019-08-27 | Mulbrick Clean Energy | Sulhamstead Solar Field (Stud Farm resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land North and S/O Stud Farm, Sulhamstead, Reading | Berkshire | South East | England | RG7 4E | 465345 | 168022 | West Berkshire Council | 15/02148/COMIND | APP/W0340/W/16/3154590 |  |  |  |  | 2015-08-18 |  | 2016-03-29 | 2016-08-01 |  |  | 2017-04-12 | 2017-04-12 |  |  |  | 2020-04-12
| 5575 | 2020-03-18 | Luminous Energy | Llwyndyrys Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Llwyndyrys Farm, Y Ffor, Pwllheli | Gwynedd | Wales | Wales | LL53 6RH | 238824 | 340269 | Gwynedd Council | C15/0810/40/LL | [5 empty] | 2015-08-10 | [6 empty] | 2015-11-09 |  |  |  | 2020-11-09
| 5576 | 2017-04-24 | BNRG (BL Solar 1) | Land at Lyons Way | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at, Lyons Way, Broadwater, Worthing | West Sussex | South East | England | BN14 9 | 515204 | 105739 | Worthing Borough Council | SDNP/15/03672/FUL | [5 empty] | 2015-08-11 |  | 2015-11-12
| 5577 | 2018-07-19 | Wirsol | Woodhouse Fields Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To East Of, Nab Lane, Rocester, Uttoxeter | Staffordshire | West Midlands | England | ST14 5JB | 408847 | 339083 | East Staffordshire Borough Council | P/2015/01032 | [5 empty] | 2015-08-07 | [6 empty] | 2015-11-20 |  |  |  | 2020-11-20 | 2016-12-10 | 2017-02-10
| 5578 | 2016-04-01 | Conergy UK | Land off Hooklands Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off Hooklands Lane, Spear Hill, Ashington, Pulborough | West Sussex | South East | England | RH20 3BA | 513504 | 118234 | Horsham District Council | DC/15/1651 | [5 empty] | 2015-08-13 | [6 empty] | 2015-11-20 |  |  |  | 2018-11-20 | 2016-01-10 | 2016-03-26
| 5579 | 2019-03-01 | Lightsource Renewable Energy | Corporation Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Corporation Farm, Hackmans Lane, Purleigh, Chelmsford | Essex | Eastern | England | CM3 6RH | 581642 | 202180 | Maldon District Council | 15/00779/FUL | APP/X1545/W/16/3150701 |  |  |  |  | 2015-08-05 |  | 2015-11-30 | 2016-06-30 |  |  | 2017-04-25 | 2017-04-25
| 5580 | 2019-11-26 | Tealing Solar Parks | Land Hill Farm | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land Hill Farm, Ghants Lane, Hambleton, Poulton-Le-Fylde | Lancashire | North West | England | FY6 9DG | 338251 | 442587 | Wyre Borough Council | 15/00652/LMAJ | [5 empty] | 2015-08-04 | [6 empty] | 2015-11-27 |  |  |  | 2018-11-27
| 5581 | 2017-01-26 | Island Green Power | High Dyke (Mill Farm) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land west of Boothby Great Woo, High Dyke, Woodnook, Grantham | Lincolnshire | East Midlands | England | NG33 5AA | 494348 | 332600 | South Kesteven District Council | S15/2137 | [5 empty] | 2015-08-11 | [6 empty] | 2015-11-10 |  |  |  | 2018-11-10 | 2016-02-29 | 2016-03-30
| 5582 | 2017-05-26 | Lightsource Renewable Energy | Land West of Parsonage Wood | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Parsonage Wood, Pyworthy, Holsworthy | Devon | South West | England | EX22 6LJ | 230985 | 101685 | Torridge District Council | 1/0754/2015/FULM | [5 empty] | 2015-08-05 | [6 empty] | 2015-09-30 |  |  |  | 2018-09-30 | 2016-12-06 | 2016-01-31
| 5583 | 2019-01-25 | Epsilon Solar | Melton Road (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land South of Melton Road, Burton On The Wolds, Leicestershire | Leicestershire | East Midlands | England | LE12 5AG | 461161 | 321320 | Charnwood Borough Council | P/15/1510/2 | [5 empty] | 2015-08-07 | [6 empty] | 2015-11-13 |  |  |  | 2018-11-13
| 5584 | 2020-03-11 | Murex Energy | Land at Martin Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Martin Farm, Whiddon Down, Okehampton | Devon | South West | England | EX20 2QL | 268697 | 93061 | West Devon Borough Council | 00715/2015 | [5 empty] | 2015-06-26 | [6 empty] | 2015-11-16 |  |  |  | 2018-11-16
| 5585 | 2017-04-26 | Earthworm Energy | Park Grounds Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Park Grounds, Brinkworth Road, Royal Wootton Bassett, Swindon | Wiltshire | South West | England | SN4 8DW | 405117 | 183986 | Wiltshire Council | 15/07373/FUL | [5 empty] | 2015-08-11 | [6 empty] | 2015-12-10 |  |  |  | 2018-12-10
| 5586 | 2016-01-06 | Sovereign Partners | West Orielton Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Orielton Home Farm, Orielton, Pembroke, Dyfed | Pembrokeshire | Wales | Wales | SA71 5EZ | 195561 | 199340 | Pembrokeshire County Council | 15/0442/PA | [5 empty] | 2015-08-05 | 2015-11-04
| 5587 | 2015-03-04 | GLID Wind Farms | Glens of Foudland Wind Farm (Extension) | Wind Onshore |  |  | 14 | n/a |  |  |  | 2 | 7 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | Glens Of Foudland Wind Farm, Hill Of Bainshole, Bainshole, Huntly, Grampian | Aberdeen | Scotland | Scotland | AB54 6AS | 360862 | 835604 | Aberdeenshire Council | APP/2015/2391 | [5 empty] | 2015-08-06 | 2016-02-17
| 5588 | 2017-06-23 | British Solar Renewables | Land at Oldstone Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Oldstone Farm, Blackawton, Totnes | Devon | South West | England | TQ9 7DG | 281849 | 51493 | South Hams District Council | 06/1725/15/F | [5 empty] | 2015-08-06 | [6 empty] | 2016-04-14 |  |  |  | 2019-04-14 | 2017-01-16 | 2017-03-31
| 5589 | 2017-10-04 | Longcliffe Quarries | Curzon Lodge Depot | Solar Photovoltaics |  |  | 3.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Curzon Lodge Depot, Longcliffe, Brassington, Matlock | Derbyshire | East Midlands | England | DE4 4 | 423243 | 356281 | Derbyshire Dales District Council | 15/00561/FUL | [5 empty] | 2015-08-03 | 2017-09-13
| 5590 | 2017-05-23 | Trina Solar | Shortheath Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Shortheath Farm, Shortheath, Overseal, Swadlincote | Derbyshire | East Midlands | England | DE12 6BN | 430324 | 314853 | South Derbyshire District Council | 9/2015/0680 | [5 empty] | 2015-08-05 | [6 empty] | 2015-12-16 |  |  |  | 2018-12-16 | 2017-01-15 | 2017-03-31
| 5591 | 2016-04-25 | Anesco | Land at Oxcroft Stocking Ground | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Oxcroft Stocking Ground Land A, Woodthorpe Road and Mill Lane, Stanfree, Chesterfield | Derbyshire | East Midlands | England | S44 6AG | 447301 | 373737 | Bolsover District Council | 15/00361/FUL | [5 empty] | 2015-08-03 | [6 empty] | 2015-12-09 |  |  |  | 2018-12-09 | 2016-01-15 | 2016-03-20
| 5592 | 2016-05-20 | Lightsource Renewable Energy | Holtwood Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Holtwood Farm, Yelt Lane, Doveridge, Ashbourne | Derbyshire | East Midlands | England | DE6 5JW | 413033 | 332318 | Derbyshire Dales District Council | 15/00525/FUL | [5 empty] | 2015-08-03 | [6 empty] | 2015-10-14 |  |  |  | 2018-10-14 | 2016-01-11 | 2016-03-10
| 5593 | 2019-09-16 | Suncredit UK | Carn Nicholas Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land At Carn Nicholas Farm, Bonymaen, Swansea | Swansea | Wales | Wales | SA1 7BL | 267843 | 194294 | City and County Council of Swansea | 2015/1546 | [5 empty] | 2015-08-10 | [6 empty] | 2015-12-14 |  |  |  | 2020-12-14 | 2018-12-28
| 5594 | 2020-02-24 | Lightsource Renewable Energy | Montreathmont Moor Forest | Solar Photovoltaics |  |  | 42 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Montreathmont Moor Forest, Montreathmont, Forfar, Tayside | Angus | Scotland | Scotland | DD8 2TU | 357573 | 753072 | Angus Council | 15/00747/FULM | [5 empty] | 2015-08-03 | [6 empty] | 2015-11-27 |  |  |  | 2018-11-27
| 5595 | 2019-12-09 | Ashland Solar Farm Ltd | Ashland Solar Farm | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Ashland Cottage Farm, Beck Lane, Sutton-In-Ashfield | Nottinghamshire | East Midlands | England | NG17 3AH | 451092 | 360983 | Mansfield District Council | 2015/0480/ST | [5 empty] | 2015-08-05 | [6 empty] | 2015-11-18 |  |  |  | 2018-11-18
| 5596 | 2015-09-02 | Sainsbury's | Nectar Way Regional Distribution Centre | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Nectar Way, Pineham, Northampton | Northamptonshire | East Midlands | England | NN4 9BX | 471028 | 258480 | Northampton Borough Council | [19 empty] | 2015-06-12
| 5598 | 2018-11-21 | CGNEE | Brenig Wind Farm (Resubmission) | Wind Onshore |  |  | 37.6 | n/a |  |  | 45 | 3 | 16 | 110 | n/a | Operational | Operational | Land east of Llyn Brenig, Nantglyn, Denbigh, Clwyd | Denbighshire | Wales | Wales |  | 299481 | 357920 | Denbighshire County Council | 25/2015/0636 | APP/R6830/A/15/3141249 |  |  |  |  | 2015-06-18 |  | 2015-11-19 | 2016-01-27 |  |  | 2016-05-18 | 2016-05-18 |  |  |  |  | 2017-08-24 | 2018-10-15
| 5599 | 2016-06-15 | Haymaker Energy | Gib Lane Solar farm (Extension) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to East of Gib Lane, Bierton | Buckinghamshire | South East | England |  | 487183 | 215067 | Aylesbury Vale District Council | 15/02533/APP | [5 empty] | 2015-07-22 | [6 empty] | 2015-10-21 |  |  |  | 2018-10-21 | 2016-01-08 | 2016-03-22
| 5600 | 2016-08-24 | Lightsource Renewable Energy | Land east of Littledown Business Park | Solar Photovoltaics |  |  | 6.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land east of Littledown Business Park, Shaftesbury | Wiltshire | South West | England |  | 386895 | 124480 | Wiltshire Council | 14/06350/FUL | [5 empty] | 2014-07-01 | [6 empty] | 2014-12-09 |  |  |  | 2017-12-09 | 2016-01-26 | 2016-03-30
| 5601 | 2019-01-04 | INRG Solar | Royals Wood Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land South Of Royals Wood Farm, Whitchurch, Aston | Cheshire | North West | England | CW5 8DN | 360075 | 345340 | Cheshire East Council | 15/3380N | [5 empty] | 2015-08-11
| 5602 | 2016-01-26 | Addison Energy | Lyreco - Telford Distribution Centre | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Deer Park Court, Telford | Shropshire | West Midlands | England |  | 371576 | 312126 | Telford and Wrekin Council | [18 empty] | 2015-08-30 | 2016-01-26
| 5603 | 2019-12-02 | Earthworm/ EW Capital | Long Lane Solar Farm (resubmission) / Nottingham Brick Works | Solar Photovoltaics |  |  | 17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land Off, Long Lane, Watnall, Nottingham | Nottinghamshire | East Midlands | England | NG16 1HY | 451522 | 346871 | Broxtowe Borough Council | 15/00525/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-11-11 |  |  |  |  | 2016-07-15
| 5605 | 2016-10-24 | Associated British Ports (ABP) | Port of Barry (Resubmission) - Site 2 | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Atlantic Way, Port of Barry, Barry | Vale of Glamorgan | Wales | Wales | CF63 3RA | 312836 | 167102 | Vale of Glamorgan Council | 2015/00173/FUL | [5 empty] | 2013-02-18 | [6 empty] | 2015-04-15 |  |  |  | 2020-04-15 | 2015-01-15 | 2015-04-16
| 5611 | 2019-02-19 | North Ayrshire Council | Shewalton Landfill Site | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Landfill Site Shewalton Road, Riverside Business Park, Irvine, Strathclyde | North Ayrshire | Scotland | Scotland | KA11 5AN | 233455 | 636406 | North Ayrshire Council | 15/00569/PP | [5 empty] | 2015-10-13 | [6 empty] | 2015-11-24 |  |  |  | 2018-11-24
| 5614 | 2016-04-05 | Lightsource Renewable Energy | South of Ballysculty | Solar Photovoltaics |  |  | 6.24 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land 130m South of no 28 Ballysculty Road, Muckamore | Co. Antrim | Northern Ireland | Northern Ireland | BT41 4QU | 133086 | 538546 | Northern Ireland Planning Service | T/2014/0460/F | 2015/A0135 |  |  |  |  | 2014-11-06 |  | 2015-08-27 | 2015-09-29 |  | 2016-03-31
| 5615 | 2019-12-16 | Aberdeen / Aberdeenshire / Moray Councils | East Tullos | EfW Incineration |  |  | 11.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Scottish Gas Network, Greenbank Crescent, Aberdeen | Aberdeen | Scotland | Scotland | AB12 3BS | 395448 | 803990 | Aberdeen City Council | 160276 | [5 empty] | 2016-03-08 | [6 empty] | 2016-10-11 |  |  |  | 2019-10-11 | 2019-10-01
| 5616 | 2017-07-04 | 2020 Renewables | Loch Hill Wind Farm (resubmission) | Wind Onshore |  |  | 28.8 | n/a |  |  |  | 3.6 | 8 | 126.5 | n/a | Appeal Refused | Application Refused | South east of Lochinvar, appoximately 4km north east of St. John's Town of Dalry | Dumfries and Galloway | Scotland | Scotland |  | 266794 | 584308 | Dumfries and Galloway Council | 16/P/2/0122 | PPA-170-2119 |  |  |  |  | 2016-04-19 |  |  | 2016-10-31 |  | 2017-06-13
| 5618 | 2019-06-25 | Muirden Energy | Drum Hollistan Wind Farm | Wind Onshore |  |  | 51 | n/a |  |  |  | 3 | 17 | 140 | n/a | Appeal Refused | Application Refused | the Sandside Estate, Land 2215M SW Of Under Keepers, Sandside, Reay, Thurso | Highland | Scotland | Scotland | KW14 7RN | 293078 | 963740 | Scottish Government (S36) | ECU00000243 | WIN-270-9 |  |  |  |  | 2016-10-20 |  |  | 2017-08-31 |  | 2019-06-21
| 5623 | 2015-10-06 | Fresh Growers | Farnsfield AD | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land south of Baulker Lane, Farnsfield | Nottinghamshire | East Midlands | England |  | 462248 | 356530 | Nottinghamshire County Council | F/3308 | [5 empty] | 2015-06-19 | 2015-08-19
| 5624 | 2015-10-06 | Awel Aman Tawe Community Energy | Mynydd Y Gwrhyd Windfarm | Wind Onshore |  |  | 4.7 | n/a |  |  |  | 2.35 | 2 | 100 | n/a | Abandoned | Abandoned | Mynydd Gwrhyd, (OS 727 107) north of Pontardawe and east of Cwmgors | Neath Port Talbot | Wales | Wales |  | 273119 | 210852 | Neath Port Talbot County Borough Council | P2007/1413 | APP/Y6930/A/08/2092727 |  |  |  |  | 2007-09-20 |  | 2008-06-17 | 2008-12-15 |  |  | 2009-05-07 | 2009-05-07 |  |  |  | 2014-05-07
| 5626 | 2017-07-05 | Mickram | Cross Bank Road (AD) | Anaerobic Digestion |  |  | 3 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Cross Bank Road | Norfolk | Eastern | England | PE30 2JB | 561301 | 321012 | King's Lynn and West Norfolk Borough Council | 15/02144/CM | [5 empty] | 2015-12-24 | 2016-01-27
| 5627 | 2020-01-14 | Clean Power Properties & Network Rail Infrastructure | Washwood Heath (resubmission) | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Washwood Heath Freight Yard No, Common Lane, Washwood Heath, Birmingham | West Midlands | West Midlands | England | B8 2U | 410868 | 289561 | Birmingham City Council | 2015/06588/PA | [5 empty] | 2015-09-02 | [6 empty] | 2015-11-26 |  |  |  | 2018-11-26
| 5628 | 2020-01-14 | Clean Power Properties & Network Rail Infrastructure | Washwood Heath (resubmission) | Advanced Conversion Technologies |  |  | 8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Washwood Heath Freight Yard No, Common Lane, Washwood Heath, Birmingham | West Midlands | West Midlands | England | B8 2U | 410868 | 289561 | Birmingham City Council | 2015/06588/PA | [5 empty] | 2015-09-02 | [6 empty] | 2015-11-26 |  |  |  | 2018-11-26
| 5629 | 2018-10-26 | British Solar Renewables | The Down House | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land At E 385926 104812, Down House Estate, Blandford St. Mary, Blandford Forum | Dorset | South West | England | DT11 9AD | 386677 | 104604 | North Dorset District Council | 2/2015/1129/PAEIA | APP/N1215/W/16/3154739 |  |  |  |  | 2015-09-16 |  | 2016-01-19 | 2016-10-07 |  |  | 2017-03-31 | 2017-03-31
| 5630 | 2019-03-01 | Lightsource Renewable Energy | Burton Top Farm | Solar Photovoltaics |  |  | 3.64 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Burton Top Farm, Station Lane, South Stainley, Harrogate | North Yorkshire | Yorkshire and Humber | England | HG3 3RX | 431195 | 463991 | Harrogate Borough Council | 15/03314/FULMAJ | [5 empty] | 2015-09-07 | [6 empty] | 2015-11-27 |  |  |  | 2018-11-27
| 5631 | 2019-12-03 | Carsebank Solar | Carsebank Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land 950M North East Of Carsebank Farm, Carsebank, Forfar, Tayside | Angus | Scotland | Scotland | DD8 3NP | 348194 | 754403 | Angus Council | 15/00863/FULL | [5 empty] | 2015-09-14 | [6 empty] | 2015-12-04 |  |  |  | 2018-12-04 | 2018-10-01
| 5632 | 2017-06-23 | British Solar Renewables | Holly Farm Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Holly Farm, Moreton Road, Owermoigne, Dorchester, | Dorset | South West | England | DT2 8HZ | 377699 | 87644 | West Dorset District Council | WD/D/15/001856 | [5 empty] | 2015-07-29 | [6 empty] | 2015-12-18 |  |  |  | 2018-12-18 | 2017-01-20 | 2017-03-31
| 5633 | 2019-04-18 | S4N Worsted/ | Worsted Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Worsted Farm, Worsted Lane, East Grinstead, West Sussex | West Sussex | South East | England | RH19 3UF | 541144 | 138070 | Mid Sussex District Council | DM/15/3056 | APP/D3830/W/16/3151730 |  |  |  |  | 2015-09-15 |  | 2015-12-24 | 2016-06-27 |  |  | 2016-11-21 | 2016-11-21 |  |  |  |  | 2019-01-01 | 2019-04-16
| 5634 | 2018-04-30 | Lightsource Renewable Energy | Land South of Bury Road | Solar Photovoltaics |  |  | 3.95 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land South of Bury Road, Marchwood, Southampton | Hampshire | South East | England | SO40 4UD | 437726 | 111385 | New Forest District Council | 15/11153 | [5 empty] | 2015-08-04 | [6 empty] | 2015-09-30
| 5635 | 2016-12-22 | First Renewable | Gascoigne Wood Colliery - Peak Power | Biomass (dedicated) |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land at the Former Gascoigne Wood Colliery, Hagg Lane, Leeds | North Yorkshire | Yorkshire and Humber | England | LS25 6LH | 452821 | 431905 | Selby District Council | 2015/1034/FUL | [5 empty] | 2015-09-14 | 2016-12-01
| 5636 | 2018-10-25 | REG Biopower | Gascoigne Wood Colliery - STOR | Biomass (dedicated) |  |  | 19.8 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Gascoigne Wood Mine, Lennerton lane, South Milford | North Yorkshire | Yorkshire and Humber | England | LS25 6LH | 452604 | 431914 | Selby District Council | 2015/0674/FUL | [5 empty] | 2015-06-30 | [6 empty] | 2016-02-11 |  |  |  | 2019-02-11
| 5637 | 2019-12-02 | Mongoose (formerly Energy Law Unlimited/ Pogbie Windfarm) | Pogbie Wind Farm 2 | Wind Onshore |  |  | 4.8 | n/a |  |  |  | 0.8 | 6 | 74 | n/a | Operational | Operational | Humbie, Lothian | East Lothian | Scotland | Scotland | EH36 5PN | 347360 | 661013 | East Lothian Council | 15/00536/P | [5 empty] | 2015-08-03 | [6 empty] | 2016-05-06 |  |  |  | 2019-05-06 | 2017-06-01 | 2019-03-01
| 5639 | 2018-06-20 | Earthworm Energy | Daventry | Biomass (dedicated) |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Earthworm PLC, Browns Road, Daventry | Northamptonshire | East Midlands | England | NN11 4NS | 455592 | 262323 | Daventry District Council | DA/2015/0798 | [5 empty] | 2015-08-20 | [6 empty] | 2015-09-28 |  |  |  |  | 2016-10-17 | 2018-04-15
| 5641 | 2020-01-29 | Perpetum Sun | Vauxhall Motors | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | Vauxhall Motors, Luton Road, Chalton, Luton | Bedfordshire | Eastern | England | LU4 9TT | 504568 | 225084 | Central Bedfordshire Council | CB/15/03550/FULL | [5 empty] | 2015-09-21 | [6 empty] | 2015-11-05 |  |  |  | 2018-11-05
| 5643 | 2016-12-15 | Sun Farming UK | Basin Bridge Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Basin Bridge Farm, Basin Bridge Lane, Stoke Golding, Nuneaton | Leicestershire | East Midlands | England | CV13 6JJ | 439522 | 296115 | Hinckley and Bosworth Borough Council | 15/00828/FUL | [5 empty] | 2015-09-24 | [6 empty] | 2016-02-18 |  |  |  | 2019-02-18 | 2016-02-18 | 2016-03-31
| 5644 | 2020-05-21 | Northacre Renewable Energy (Hills Group) | Northacre RRC | Advanced Conversion Technologies |  |  | 22 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Northgate Industrial Park, Stephenson Road, Westbury | Wiltshire | South West | England | BA13 4WD | 385453 | 152475 | Wiltshire Council | 14/12003/WCM | [5 empty] | 2014-12-22 | [6 empty] | 2015-09-23 |  |  |  | 2020-09-23
| 5645 | 2019-02-19 | Mssrs R Miller Ltd | Arkleby Mill | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Arkleby Mill, Ellen Bank, Arkleby, Wigton | Cumbria | North West | England | CA7 2BG | 314330 | 540378 | Allerdale Borough Council | 2/2015/0484 | [5 empty] | 2015-07-29 | [6 empty] | 2015-09-23 |  |  |  |  | 2016-05-15 | 2017-02-01
| 5646 | 2018-06-22 | BWE Partnership | Drummygar Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Field 275M South of Carmyllie, Arbroath | Angus | Scotland | Scotland | DD11 2QS | 355381 | 743777 | Angus Council | 15/00873/FULL | [5 empty] | 2015-09-21 | [6 empty] | 2015-12-01 |  |  |  | 2018-12-01
| 5647 | 2019-08-27 | Mulbrick Clean Energy | Broxbournebury Solar Field | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land Adjacent to Cock Lane, Hoddesdon | Hertfordshire | Eastern | England | EN11 8LS | 535695 | 207603 | Broxbourne Borough Council | 07/15/0866/F | [5 empty] | 2015-09-15 | [6 empty] | 2016-02-15 |  |  |  | 2019-02-15
| 5648 | 2015-11-05 | Global Renewable Construction | Ladywood Farm | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Ladywood Farm, Ladywood Road, Dale Abbey, Ilkeston | Derbyshire | East Midlands | England | DE7 4PT | 444697 | 339719 | Erewash Borough Council | 0915/0023 | [5 empty] | 2015-09-10 |  | 2015-10-28
| 5649 | 2015-10-06 | Private Developer | Welton of Creuchies (resubmission) | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 | 115 | n/a | Planning Application Withdrawn | Application Withdrawn | Welton of Creuchies Farmhouse, Alyth, Blairgowrie, Tayside | Perth and Kinross | Scotland | Scotland | PH11 8LB | 321924 | 750200 | Perth and Kinross Council | 15/01425/FLL | [5 empty] | 2015-09-10 | 2015-12-15
| 5650 | 2017-06-23 | East Farm Solar Park Ltd | Land at East Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To East of Moreton Road, Owermoigne, Dorchester | Dorset | South West | England | DT2 8HT | 377293 | 86144 | West Dorset District Council | WD/D/15/001858 | [5 empty] | 2015-07-29 | [6 empty] | 2016-09-06 |  |  |  | 2019-09-06 | 2017-01-20 | 2017-03-31
| 5651 | 2019-12-10 | Sowerby Solar Solar Ltd | Sowerby Lodge | Solar Photovoltaics |  |  | 4.17 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Sowerby Lodge (Land north of), Bank Lane, Barrow-In-Furness | Cumbria | North West | England | LA14 4QY | 319156 | 472510 | Barrow in Furness Borough Council | B03/2015/0614 | [5 empty] | 2015-03-09 | [6 empty] | 2016-02-08 |  |  |  | 2019-02-08
| 5652 | 2019-12-06 | A J Butler & Sons Ltd | Bromham House Farm | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bromham House Farm, 40 Devizes Road, Bromham, Chippenham | Wiltshire | South West | England | SN15 2DX | 397499 | 165857 | Wiltshire Council | 15/07127/WCM | [5 empty] | 2015-05-08 | [6 empty] | 2015-09-24 |  |  |  |  | 2017-02-14 | 2018-05-15
| 5653 | 2016-09-22 | Kingfisher Scottish Limited Partnership | B&Q Swindon DC | Solar Photovoltaics |  |  | 2.462 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | BandQ Swindon DC, Unit A, G Park, Highworth Road South Marston, Swindon | Wiltshire | South West | England | SN3 4TZ | 417904 | 189004 | Swindon Borough Council | S/15/1492 | [5 empty] | 2015-09-16 | [6 empty] | 2015-10-26 |  |  |  | 2018-10-26 | 2015-11-02 | 2016-01-30
| 5654 | 2016-08-18 | Lightsource Renewable Energy | Stragglethorpe Road farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Opposite Entrance To, Main Road, Cotgrave Place Golf Clu, Nottingham | Nottinghamshire | East Midlands | England | NG12 2JZ | 463908 | 336973 | Rushcliffe Borough Council | 15/01776/FUL | [5 empty] | 2015-01-09 | [6 empty] | 2015-12-01 |  |  |  | 2018-12-01 | 2016-02-05 | 2016-03-29
| 5655 | 2019-01-29 | Howmuir Solar | Field 730M West Of Queen Street | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Field 730M West of Queen Street, Carsegownie, Forfar, Tayside | Angus | Scotland | Scotland | DD8 3A | 349552 | 754769 | Angus Council | 15/00864/FULL | [5 empty] | 2015-09-14 | [6 empty] | 2015-12-03 |  |  |  | 2018-12-04
| 5656 | 2016-12-22 | Anesco | Land at Bluehouse Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Bluehouse Farm, Stockton Road, Newton Bewley, Billingham | Cleveland | North East | England | TS22 5PH | 447326 | 526636 | Hartlepool Borough Council | H/2015/0316 | [5 empty] | 2015-09-09 | [6 empty] | 2015-11-30 |  |  |  | 2018-11-30 | 2016-06-15 | 2016-08-31
| 5659 | 2020-03-11 | Alaska (The Holme Estate) | Stokeford Farm (resubmission) | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Stokeford Farm (Land at), East Stoke, Wareham | Dorset | South West | England | BH20 6AN | 387473 | 87484 | Purbeck District Council | 6/2015/0516 | [5 empty] | 2015-08-19 | [6 empty] | 2015-10-28 |  |  |  | 2018-10-28
| 5660 | 2017-05-23 | UK Sustainable Energy | Potters Bar Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Rear of Cranborne Road, Household Waste Recycling Cent, Potters Bar | Hertfordshire | Eastern | England | EN6 3JN | 524112 | 202677 | Hertsmere Borough Council | 15/1289/FUL | [5 empty] | 2015-09-03 | [6 empty] | 2015-12-18 |  |  |  | 2018-12-18 | 2016-12-01 | 2017-03-28
| 5661 | 2016-11-01 | North Wharf Solar Farm | North Wharf Solar Farm | Solar Photovoltaics |  |  | 5.96 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Fields north of Ferry Road West, Flixborough, Scunthorpe | Humberside | Yorkshire and Humber | England | DN15 8DY | 486438 | 414521 | North Lincolnshire Council | PA/2015/0942 | APP/Y2003/W/16/3146209 |  |  |  |  | 2015-09-10 |  | 2015-11-18 | 2016-03-18 |  | 2016-10-17
| 5662 | 2020-01-15 | Brilliant Harvest Installations | Alton Mead Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At, Alton Mead Lane, Yetminster, Sherborne | Dorset | South West | England | DT9 6BN | 360850 | 109150 | West Dorset District Council | WD/D/15/001841 | [5 empty] | 2015-09-05 | [6 empty] | 2016-01-18 |  |  |  | 2019-01-18
| 5663 | 2019-12-10 | Susenco Management | Cuckmere Solar Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Wick Street Berwick, Berwick, Polegate | East Sussex | South East | England | BN26 6TH | 553304 | 108759 | Wealden District Council | WD/2015/1635/MEA | [5 empty] | 2015-09-10 | [6 empty] | 2017-02-06 |  |  |  | 2020-02-06
| 5664 | 2016-12-22 | Anesco | Stob House Farm | Solar Photovoltaics |  |  | 4.879 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North of Wolviston, Newton Bewley, Billingham | Cleveland | North East | England | TS22 5 | 445555 | 526689 | Hartlepool Borough Council | H/2015/0315 | [5 empty] | 2015-09-10 | [6 empty] | 2016-01-22 |  |  |  | 2019-01-22 | 2016-07-01 | 2016-09-01
| 5665 | 2018-10-23 | Mulbrick Clean Energy | Brailsford Farm | Solar Photovoltaics |  |  | 1.21 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Brailsford Farm, North Lane, Brailsford, Ashbourne | Derbyshire | East Midlands | England | DE6 3BE | 426290 | 344014 | Derbyshire Dales District Council | 15/00526/FUL | [5 empty] | 2015-09-04 | [6 empty] | 2015-12-02 |  |  |  | 2018-12-02
| 5666 | 2016-02-04 | New Energy for the World | Hill Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Proposed Solar Farm, Broughton Road, Dalton-In-Furness | Cumbria | North West | England | LA15 8JP | 323190 | 476408 | Barrow in Furness Borough Council | B06/2015/0532 | [5 empty] | 2015-08-27 | 2016-01-21
| 5668 | 2017-05-19 | William Corbett Farms | Austrey House Farm | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Austrey House Farm, Orton Lane, Austrey, Atherstone | Warwickshire | West Midlands | England | CV9 3EA | 430006 | 305205 | North Warwickshire Borough Council | PAP/2015/0259 | [5 empty] | 2015-05-01 | [6 empty] | 2015-09-17 |  |  |  |  | 2015-05-15 | 2016-06-01
| 5670 | 2017-02-01 | Solstice Renewables | Granville Road Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West and South West of Granville Road, Muxton Grange Cottages, Donnington, Telford | Shropshire | West Midlands | England | TF2 7QG | 372241 | 312458 | Telford and Wrekin Council | TWC/2015/0804 | [5 empty] | 2015-09-07 | [6 empty] | 2015-12-11 |  |  |  | 2018-12-11 | 2016-08-24 | 2016-10-24
| 5671 | 2016-06-29 | Temporis Capital | Land West Of Sookholme Road | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land West of Sookholme Road, Sookholme, Mansfield | Nottinghamshire | East Midlands | England | NG19 8LP | 454515 | 366602 | Mansfield District Council | 2015/0563/NT | [5 empty] | 2015-09-09 |  | 2016-06-01
| 5672 | 2017-01-23 | JBM Solutions | Holme Farm Solar Park | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land South of Radcliffe Road, Holme Pierrepont, Nottingham | Nottinghamshire | East Midlands | England | NG12 2LT | 463065 | 338203 | Rushcliffe Borough Council | 15/01971/FUL | [5 empty] | 2015-08-11 | [6 empty] | 2016-01-04 |  |  |  | 2019-01-04
| 5673 | 2017-02-16 | PAR Renewables | Tullywiggan Road | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 14 Tullywiggan Road, Tullywiggan, Cookstown | Co. Tyrone | Northern Ireland | Northern Ireland | BT80 8SD | 94165 | 535547 | Mid Ulster | LA09/2015/0696/F | [5 empty] | 2015-08-19 | [6 empty] | 2015-12-10 |  |  |  |  | 2013-08-15 | 2014-08-15
| 5674 | 2019-07-19 | East Yorkshire Power | Gameslack Farm (resubmission) | Biomass (dedicated) |  |  | 17.5 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Beverley Road, Wetwang, Fimber, Driffield | Humberside | Yorkshire and Humber | England | YO25 9LT | 491342 | 459844 | East Riding of Yorkshire Council | 15/02132/STREM | [5 empty] | 2015-07-27 | [6 empty] | 2015-10-26 |  |  |  | 2020-10-26 | 2016-05-01
| 5675 | 2020-03-18 | Caledon Partners (Solar Power Parks) | Castell Ddu Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land associated with Castell D, Castell Ddu Road, Pontarddulais | Swansea | Wales | Wales | SA4 8DH | 259871 | 201517 | City and County Council of Swansea | 2015/1786 | [5 empty] | 2015-09-09 | [6 empty] | 2016-01-14 |  |  |  | 2019-01-14
| 5676 | 2019-10-23 | Green Energy UK Direct | Yeorton Hall Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Yeorton Hall Farm, Oaklands, Egremont | Cumbria | North West | England | CA22 2NX | 301922 | 507805 | Copeland Borough Council | 4/15/2377/0F1 | [5 empty] | 2015-09-02 | [6 empty] | 2016-05-24 |  |  |  | 2019-05-24
| 5677 | 2019-08-27 | Global Renewable Construction | Knotwood Fields Farm | Solar Photovoltaics |  |  | 2.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Knotwood Fields Farm, Cosgrove Road, Old Stratford, Milton Keynes | Northamptonshire | East Midlands | England | MK19 6AG | 477564 | 242061 | South Northamptonshire Council | S/2015/2141/MAF | [5 empty] | 2015-09-03 | [6 empty] | 2015-12-17 |  |  |  | 2018-12-17
| 5678 | 2016-05-04 | Anesco | Mazelands Farm | Solar Photovoltaics |  |  | 2.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Mazelands Farm, Burnt Hill Road, Stanford Dingley, Reading | Berkshire | South East | England | RG7 6DU | 456974 | 172845 | West Berkshire Council | 15/02076/COMIND | [5 empty] | 2015-09-10 |  | 2016-04-22
| 5679 | 2019-02-26 | Inazin (Veiges Farm Solar Park Ltd) | Veiges Farm Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Veiges Farm House, St. Johns Road, Exmouth | Devon | South West | England | EX8 5EG | 303114 | 83972 | East Devon District Council | 15/2017/MFUL | [5 empty] | 2015-09-07 | [6 empty] | 2016-02-03 |  |  |  | 2019-02-03
| 5680 | 2016-07-21 | RenPlan Consulting | Potbridge Farm (resubmission) | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Potbridge Farm, Potbridge, Odiham, Hook | Hampshire | South East | England | RG29 1JN | 474827 | 153523 | Hart District Council | 15/01579/FUL | APP/N1730/W/16/3142031 |  |  |  |  | 2015-07-08 |  | 2015-10-07 | 2016-01-19 | 2016-03-22
| 5681 | 2018-11-21 | Green Switch Solutions/Belvedere Energy Developments - Liquidated | Hawthorn Farm Solar Park | Solar Photovoltaics |  |  | 4.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land At SK1930 5342, Scropton Road, Scropton, Derby | Derbyshire | East Midlands | England | DE65 5DS | 419549 | 330468 | South Derbyshire District Council | 9/2015/0688 | [5 empty] | 2015-01-09 | [6 empty] | 2015-12-16 |  |  |  | 2018-12-16
| 5683 | 2020-02-12 | Active Renewables | Mamhilad Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land South of Little Mill Brickworks, Little Mill, Pontypool, Gwent | Torfaen | Wales | Wales | NP4 0HD | 331456 | 202012 | Torfaen County Borough Council | 15/P/00436 | [5 empty] | 2015-08-24 | [6 empty] | 2015-12-22 |  |  |  |  | 2020-01-12 | 2020-02-12
| 5684 | 2015-03-04 | Anesco | Land North of Marlow Landfill Site | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Ld N Of Marlow Landfill Site, Marlow Road, Little Marlow, Marlow | Buckinghamshire | South East | England | SL7 3RW | 486956 | 187880 | Wycombe District Council | 15/07001/FULEA | [5 empty] | 2015-09-07 |  | 2016-02-26
| 5685 | 2017-04-26 | Conergy | Hyde Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Hyde Farm, Warrington Road, Olney | Buckinghamshire | South East | England | MK46 4DU | 488765 | 253909 | Milton Keynes Council | 15/01791/FUL | [5 empty] | 2015-08-07 | [6 empty] | 2016-01-12 |  |  |  | 2019-01-12 | 2016-12-16 | 2017-03-16
| 5686 | 2016-08-31 | New Energy for the World | Lower Venn Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land associated with, Lower Venn Farm, Sutton St. Nicholas, Hereford | Hereford and Worcester | West Midlands | England | HR1 3 | 354281 | 249138 | Herefordshire Council | P152189/F | [5 empty] | 2015-08-28 | [6 empty] | 2015-11-27 |  |  |  | 2018-11-27 | 2016-01-30 | 2016-03-30
| 5687 | 2017-05-16 | Littlewood Renewables | Littlewood Lane Solar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mansfield Woodhouse, Littlewood Lane, Pleasley Vale, Mansfield | Nottinghamshire | East Midlands | England | NG19 8RR | 453307 | 365197 | Mansfield District Council | 2015/0527/NT | [5 empty] | 2015-08-18 | [6 empty] | 2015-11-18 |  |  |  | 2018-11-18 | 2017-01-18 | 2017-03-30
| 5690 | 2015-12-02 | British Solar Renewables | Sunnydale Solar Farm | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land North Of Sunnydale, Smeeton Road, Saddington, Leicester | Leicestershire | East Midlands | England | LE8 0QT | 466650 | 292748 | Harborough District Council | 15/01120/FUL | [5 empty] | 2015-08-17 |  | 2015-11-16
| 5691 | 2020-01-15 | Catfoss | Derwenthaugh Ecoparc (resubmission) | Advanced Conversion Technologies |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Derwenthaugh Ecoparc, Derwenthaugh Road, Swalwell, Newcastle-Upon-Tyne | Tyne and Wear | North East | England | NE16 3BJ | 420075 | 563270 | Gateshead Metropolitan Borough Council | DC/15/00644/FUL | [5 empty] | 2015-07-17 | [6 empty] | 2015-09-10 |  |  |  | 2018-09-10
| 5692 | 2015-10-06 | Graphite Resources | Derwenthaugh Ecoparc | Advanced Conversion Technologies |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Derwenthaugh Ecoparc, Derwenthaugh Road, Swalwell, Newcastle-Upon-Tyne | Tyne and Wear | North East | England | NE16 3BJ | 420075 | 563270 | Gateshead Metropolitan Borough Council | DC/14/00034/FUL | [5 empty] | 2014-01-19 | [6 empty] | 2014-07-22
| 5693 | 2018-11-08 | Gamesa Energy Uk | Glenouther Renewable Energy Park | Wind Onshore |  |  | 30 | n/a |  |  |  | 2.5 | 12 | 126.5 | n/a | Appeal Refused | Application Refused | Glenouther Renewable Energy Park, Clunch Road, Fenwick, Kilmarnock | East Ayrshire | Scotland | Scotland | KA3 6EW | 247942 | 648393 | East Ayrshire Council | 15/0584/PP | PPA-190-2059 |  |  |  |  | 2015-08-10 |  | 2016-05-13 | 2016-08-12 |  | 2017-05-25
| 5694 | 2016-06-16 | Zaravolt Development | Peterlee Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land North Of Mill Hill, North West Industrial Estate, Peterlee | County Durham | North East | England | SR8 2H | 440912 | 542443 | Durham County Council | DM/15/02290/FPA | [5 empty] | 2015-07-23 | [11 empty] | 2016-01-15 | 2016-03-30
| 5695 | 2019-03-01 | Lightsource Renewable Energy | Graham Wood | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land to the South of Graham Wood, Great Strickland, Penrith | Cumbria | North West | England | CA10 3DU | 357214 | 522254 | Eden District Council | 15/0666 | APP/H0928/W/16/3147860 |  |  |  |  | 2015-08-14 |  | 2015-10-29 | 2016-04-26 |  |  | 2017-01-25 | 2017-01-25
| 5696 | 2019-06-11 | Psi Solar | Bowscar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land North of Bowscar Road, Bowscar, Penrith | Cumbria | North West | England | CA11 8RR | 352103 | 534715 | Eden District Council | 15/0657 | APP/H0928/W/16/3143418 |  |  |  |  | 2015-08-07 |  | 2015-10-29 | 2016-02-05 |  |  | 2016-06-07 | 2016-06-07 |  |  |  | 2019-06-07
| 5697 | 2019-03-01 | Lightsource Renewable Energy | Land To The South Of Dallan Bank Wood | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land To The South Of Dallan Bank Wood, Newby, Penrith | Cumbria | North West | England | CA10 3ED | 357214 | 522254 | Eden District Council | 15/0663 | APP/H0928/W/16/3147861 |  |  |  |  | 2015-08-14 |  | 2015-10-29 | 2016-04-26 |  |  | 2017-01-25 | 2017-01-25
| 5698 | 2019-11-20 | Muirmealing Solar Ltd (The Abbey Group) | Muirmealing Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Muirmealing Shaw, Saline, Dunfermline | Fife | Scotland | Scotland | KY12 9UB | 299830 | 692727 | Fife Council | 15/02993/FULL | [5 empty] | 2015-08-21 | [6 empty] | 2016-11-11 |  |  |  | 2019-11-11
| 5699 | 2020-05-21 | RALOS New Energy | Town End Farm | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land At Town End Farm, Skelton, Penrith | Cumbria | North West | England | CA11 9TZ | 342764 | 536649 | Eden District Council | 15/0658 | APP/H0928/W/16/3146738 |  |  |  |  | 2015-08-14 |  | 2015-10-29 | 2016-04-08 |  |  | 2016-10-11 | 2016-10-11
| 5700 | 2017-08-16 | Lightsource Renewable Energy | Land West Of Erlas Hall | Solar Photovoltaics |  |  | 3.95 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land West Of Erlas Hall, Erlas Lane | Wrexham | Wales | Wales | LL13 0PE | 337282 | 350765 | Wrexham County Borough Council | P/2015/0640 | [5 empty] | 2015-08-24 | 2015-11-11
| 5701 | 2019-03-01 | Lightsource Renewable Energy | Land At Southland Farm (NOR) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land At Southland Farm, Bridgerule, Holsworthy | Devon | South West | England | EX22 6LL | 228572 | 102299 | Torridge District Council | 1/0756/2015/FULM | APP/W1145/W/15/3140778 |  |  |  |  | 2015-08-20 |  | 2015-12-04 | 2016-01-08 |  |  | 2016-04-13 | 2016-04-13
| 5702 | 2019-03-01 | Lightsource Renewable Energy | Heathlands | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Heathlands, Harker Road Ends, Carlisle | Cumbria | North West | England | CA6 4HN | 337320 | 561525 | Carlisle City Council | 15/0687 | [5 empty] | 2015-09-03 | [6 empty] | 2015-11-27 |  |  |  | 2018-11-27
| 5703 | 2020-05-27 | Morayhill | Morayhill AD | Anaerobic Digestion |  |  | 2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ld 320M SW Of Norbord Europe, Dalcross, Inverness | Highland | Scotland | Scotland | IV2 7JQ | 274982 | 849481 | Highland Council | 15/03273/FUL | [5 empty] | 2015-08-26 | [6 empty] | 2015-10-27 |  |  |  | 2018-10-27 | 2016-03-01 | 2017-10-01
| 5704 | 2016-11-29 | Livos Energy | Weltree Brow | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land To The South of Willow Tree Brow, Morland, Penrith | Cumbria | North West | England | CA10 1TW | 360869 | 521013 | Eden District Council | 15/0668 | APP/H0928/W/16/3147136 |  |  |  |  | 2015-08-17 |  | 2015-12-17 | 2016-04-08 |  | 2016-11-22
| 5705 | 2018-03-20 | Levantera Developments | NEC, Birmingham | Solar Photovoltaics |  |  | 3.863 | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | National Exhibition Centre, Birmingham | West Midlands | West Midlands | England | B40 1NT | 419151 | 283814 | Solihull Metropolitan Borough Council | PL/2015/51905/PPFL | [5 empty] | 2015-08-28 | [6 empty] | 2015-10-05 |  |  |  | 2018-10-05
| 5706 | 2016-05-04 | Trimmers Solar Farm | Trimmers Solar Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Trimmers Farm, Totters Lane, Hartley Wintney, Hook | Hampshire | South East | England | RG27 8HX | 474944 | 154180 | Hart District Council | 15/01614/FUL | APP/N1730/W/15/3139981 |  |  |  |  | 2015-08-17 |  | 2015-11-16 | 2015-12-15 |  | 2016-04-26
| 5707 | 2019-06-12 | Raw Energy | Whiteborough Farm | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Whiteborough Farm, Chesterfield Road, Huthwaite, Sutton-In-Ashfield | Nottinghamshire | East Midlands | England | NG17 2QJ | 445889 | 360472 | Ashfield District Council | V/2015/0518 | [5 empty] | 2015-08-26 | [6 empty] | 2016-02-09 |  |  |  | 2021-02-09
| 5708 | 2016-01-06 | New Energy for the World | Whitestone Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land To The S Of Morland and, E Of Newby, Newby, Penrith | Cumbria | North West | England | CA10 3HB | 360546 | 520213 | Eden District Council | 15/0665 | [5 empty] | 2015-08-17 |  | 2015-12-17
| 5709 | 2016-06-29 | New Energy for the World | Orton Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Between M6 Carriageways, Orton, Penrith | Cumbria | North West | England | CA10 3SB | 360474 | 506237 | Eden District Council | 15/0667 | [5 empty] | 2015-08-12 |  | 2016-06-09
| 5710 | 2020-06-19 | Banks Renewables | Land At Penny Hill Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At, Penny Hill Lane, Ulley, Sheffield | South Yorkshire | Yorkshire and Humber | England | S26 3YA | 447691 | 386919 | Rotherham Metropolitan Borough Council | RB2015/1084 | [5 empty] | 2015-08-11 | [6 empty] | 2015-11-20 |  |  |  | 2020-11-20
| 5712 | 2017-04-24 | Anesco | Land On The East Side Of Fosse Way | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land On The East Side Of Fosse Way, Radford Semele, Leamington Spa | Warwickshire | West Midlands | England | CV31 1XJ | 435534 | 261856 | Stratford on Avon District Council | 15/02716/FUL | [5 empty] | 2015-07-23 | [6 empty] | 2015-11-27 |  |  |  | 2018-11-27 | 2016-11-28 | 2017-03-31
| 5713 | 2019-09-17 | Renewable Power Exchange | Stockton Court farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land Off, Stockton Road, Stockton-on-Teme, Worcester | Hereford and Worcester | West Midlands | England | WR6 6UT | 371893 | 267915 | Malvern Hills District Council | 15/01017/FUL | APP/J1860/W/16/3149836 |  |  |  |  | 2015-08-11 |  | 2016-04-13 | 2016-06-24 |  |  | 2017-04-05 | 2017-04-05 |  |  |  | 2020-04-05
| 5714 | 2015-12-02 | Mulbrick Cleans Energy | Bell Lane Solar Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Bell Lane And Opposite, Bell Lane, Shenley, Radlett | Hertfordshire | Eastern | England | WD7 9AD | 518387 | 201964 | Hertsmere Borough Council | 15/1287/FUL | [5 empty] | 2015-08-27 |  | 2015-11-26
| 5715 | 2018-06-21 | New Energy for the World | Blackdyke Farm | Solar Photovoltaics |  |  | 7.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Blackdyke Farm and Riding Cent, Blackford, Carlisle | Cumbria | North West | England | CA6 4EY | 337921 | 562235 | Carlisle City Council | 15/0688 | [5 empty] | 2015-08-25 | [6 empty] | 2016-01-08 |  |  |  | 2019-01-08
| 5716 | 2019-03-01 | Lightsource Renewable Energy | Towcett Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land To The East of Towcett Farm, Towcett, Little Strickland, Penrith | Cumbria | North West | England | CA10 3EQ | 358453 | 519283 | Eden District Council | 15/0644 | APP/H0928/W/16/3147740 |  |  |  |  | 2015-08-05 |  | 2015-10-29 | 2016-04-26 |  |  | 2017-01-25 | 2017-01-25
| 5717 | 2018-10-24 | New Energy for the World | Newfold Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Newfold Farm, Brown Lane, Wrea Green, Preston | Lancashire | North West | England | PR4 3PQ | 341449 | 430687 | Fylde Borough Council | 15/0501 | [5 empty] | 2015-08-27 | [6 empty] | 2015-12-15 |  |  |  | 2018-12-14
| 5718 | 2015-11-05 | Singleton Birch | Kingfisher Court | Anaerobic Digestion |  |  | 2.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land South Of Petunia Nurserie, Plaxton Bridge Road, Woodmansey, Beverley | Humberside | Yorkshire and Humber | England | HU17 0RT | 506337 | 436538 | East Riding of Yorkshire Council | 15/02417/STPLF | [5 empty] | 2015-08-06 |  | 2015-10-12
| 5720 | 2017-08-15 | NR16/ RenEnergy | Briar Solar Farm | Solar Photovoltaics |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Briar Chemicals Ltd, Sweet Briar Road, Norwich | Norfolk | Eastern | England | NR6 5AP | 620521 | 310256 | Norwich City Council | 15/01091/F | [5 empty] | 2015-07-24 | [6 empty] | 2016-06-16 |  |  |  | 2019-06-16 | 2017-02-16 | 2017-03-20
| 5721 | 2016-01-06 | Kelda Energy | Naburn Sewage Treatment Works | Solar Photovoltaics |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Sewage Works, Naburn Lane, Naburn, York | North Yorkshire | Yorkshire and Humber | England | YO19 4RN | 460178 | 446809 | York City Council | 15/01845/FULM | [5 empty] | 2015-08-26 |  | 2015-12-11
| 5722 | 2017-04-20 | BioConstruct | Brocklesby - Crosslands Lane | Anaerobic Digestion |  |  | 3.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | J Brocklesby and Son, Crosslands Lane, Brocklesby House, North Cave, Brough | Humberside | Yorkshire and Humber | England | HU15 2PG | 488146 | 432144 | East Riding of Yorkshire Council | 15/01433/STPLF | [5 empty] | 2015-06-05 | [6 empty] | 2015-07-06 |  |  |  | 2018-07-06 | 2016-07-01 | 2017-01-09
| 5723 | 2016-04-13 | Active Renewables | Bent Spur Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bent Spur Farm, Bent Spur Road, Kearsley, Bolton | Greater Manchester | North West | England | BL4 8SJ | 375173 | 404114 | Bolton Metropolitan Borough Council | 94654/15 | [5 empty] | 2015-08-24 | [6 empty] | 2015-11-20 |  |  |  | 2018-11-20 | 2016-02-20 | 2016-03-31
| 5724 | 2017-04-24 | Muirden Energy | Logie Newton Wind Farm | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 | 80 | n/a | Appeal Refused | Application Refused | Land At Hassiewells, Rothienorman, Inverurie, Grampian | Aberdeen | Scotland | Scotland | AB51 8XX | 366076 | 840845 | Aberdeenshire Council | APP/2015/2658 | APPEAL/2016/0005 |  |  |  |  | 2015-08-27 |  | 2016-03-09 | 2016-04-18 |  | 2016-12-29
| 5725 | 2015-12-17 | Severn Trent Water | Melton Mowbray Sewage Treatment Works (Solar) | Solar Photovoltaics |  |  | 2.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Severn Trent Water Authority, Sysonby Grange Lane, Melton Mowbray | Leicestershire | East Midlands | England | LE13 0JG | 473720 | 318555 | Melton Borough Council | 15/00667/CM | [5 empty] | 2015-08-21 | [6 empty] | 2015-10-08 |  |  |  | 2020-10-08
| 5727 | 2016-09-01 | West Grange Solar | West Grange Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The North Of West Grange, West Grange Farm, Brankstone , Blairhall, Dunfermline | Fife | Scotland | Scotland | KY12 | 298368 | 689777 | Fife Council | 15/02928/FULL | [5 empty] | 2015-08-20 | 2016-08-15
| 5728 | 2015-12-02 | Solstice Renewables | Malthouse Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Malthouse Farm, South Of Station Road, Barlaston, Stoke-On-Trent | Staffordshire | West Midlands | England | ST12 9AQ | 388581 | 337923 | Stafford Borough Council | 15/22672/FUL | [5 empty] | 2015-07-25 |  | 2015-11-24
| 5729 | 2018-08-30 | Solar Securities | Great Tong Solar Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Great Tong Farm, Great Tong, Headcorn, Ashford | Kent | South East | England | TN27 9PP | 583313 | 146559 | Maidstone Borough Council | 15/505974/FULL | APP/U2235/W/16/3157476 |  |  |  |  | 2015-08-24 |  | 2016-02-29 | 2016-12-21 | 2017-01-10
| 5730 | 2018-11-20 | Earthworm/ EW Capital | Maesygarn | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Maesygarn, Gorsgoch, Llanybydder, Dyfed | Ceredigion | Wales | Wales | SA40 9TR | 247811 | 249371 | Ceredigion County Council | A150539 | [5 empty] | 2015-08-12 | [6 empty] | 2016-08-16 |  |  |  | 2021-08-16
| 5731 | 2016-09-01 | Earthworm Energy | Brookhouse Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land opposite Aylus Cottages, Wellington, Hereford | Hereford and Worcester | West Midlands | England | HR4 8AZ | 349401 | 248192 | Herefordshire Council | P152188/F | APP/W1850/W/16/3150195 |  |  |  |  | 2015-08-21 |  | 2015-11-20 | 2016-05-31 |  | 2016-08-23
| 5732 | 2016-01-06 | TGC Renewables | Sandwath Farm | Solar Photovoltaics |  |  | 5.53 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Fields Nr. Sandwath Farm, Kirkby Stephen | Cumbria | North West | England | CA17 4HE | 376507 | 508723 | Eden District Council | 15/0461 | [5 empty] | 2015-08-17 | 2015-12-10
| 5733 | 2018-04-30 | Lightsource Renewable Energy | Bumpstead Hill | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Bumpstead Hill Land West Of A1, Chelmsford Road, Dunmow | Essex | Eastern | England | CM6 1LL | 564356 | 221015 | Uttlesford District Council | UTT/15/2318/FUL | [5 empty] | 2015-08-14 | [6 empty] | 2015-11-19 |  |  |  | 2018-11-19
| 5734 | 2016-09-01 | Elgar Middleton | Land At Moor Lane Farm | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Moor Lane Farm, Moor Lane, Minety, Malmesbury | Wiltshire | South West | England | SN16 9DR | 402518 | 191739 | Wiltshire Council | 15/07244/FUL | [5 empty] | 2015-08-25 |  | 2016-08-19
| 5735 | 2016-07-28 | Blaby Solar Farm | Blaby Solar Farm | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of Wigston Sewage Wo, Leicester Road, Countesthorpe, Leicester | Leicestershire | East Midlands | England | LE8 5QU | 459069 | 296752 | Oadby and Wigston Borough Council | 15/00327/FUL | [5 empty] | 2015-08-07 | [6 empty] | 2015-11-13 |  |  |  | 2018-11-13 | 2016-02-01 | 2016-03-29
| 5736 | 2015-12-02 | Lightsource Renewable Energy | Land West Of Flambirds Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land West Of Flambirds Farm, Hackmans Lane, Flambirds Chase, Purleigh, Chelmsford | Essex | Eastern | England | CM3 6RN | 581968 | 200694 | Maldon District Council | 15/00780/FUL | [5 empty] | 2015-08-12 |  | 2015-11-30
| 5737 | 2016-01-06 | British Solar Renewables | Land south of Holloway Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land south of Holloway Lane, North Harmondsworth Lane, Harmondsworth | Greater London | London | England | UB7 0AE | 506489 | 177979 | Hillingdon London Borough Council | 1354/APP/2015/2752 | [5 empty] | 2015-07-22 | 2015-12-17
| 5739 | 2019-12-02 | Solar Securities | Tuckey Farm | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | East Claydon Road Winslow, East Claydon Road, Winslow, Buckingham | Buckinghamshire | South East | England | MK18 3ND | 475396 | 226763 | Aylesbury Vale District Council | 15/02543/APP | [5 empty] | 2015-08-21 | [6 empty] | 2015-12-11 |  |  |  | 2018-12-11
| 5740 | 2015-10-06 | Active Renewables | Walton Cardiff Manor | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Walton Cardiff Manor, Walton Cardiff Lane, Walton Cardiff, Tewkesbury | Gloucestershire | South West | England | GL20 7BL | 390878 | 232236 | Tewkesbury Borough Council | 15/00763/FUL | [5 empty] | 2015-08-03 |  | 2015-12-02
| 5741 | 2015-12-02 | Tulip Renewables | FAWKES 1 | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Solar Farm (Site 1), Leonard Stanley, Stanley Downton, Stonehouse | Gloucestershire | South West | England | GL10 3QX | 379052 | 204390 | Stroud District Council | S.15/1856/FUL | [5 empty] | 2015-08-05 |  | 2015-11-26
| 5742 | 2017-07-04 | NESF (formerly Lark Energy) | Bilsthorpe (Land off Forest Lane) | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field Reference Number 2694, Forest Lane, Bilsthorpe, Newark | Nottinghamshire | East Midlands | England | NG22 8TR | 464198 | 359310 | Newark and Sherwood District Council | 15/01206/FULM | [5 empty] | 2015-08-17 | [6 empty] | 2016-01-13 |  |  |  | 2019-01-12 | 2017-02-15 | 2017-03-15
| 5744 | 2019-09-17 | West Coast Wind | Kittymuir Farm | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 | 77 | n/a | Planning Permission Expired | Planning Permission Expired | Kittymuir Farm, Millheugh Road, Hamilton, Strathclyde | South Lanarkshire | Scotland | Scotland | ML3 7XN | 275342 | 648327 | South Lanarkshire Council | HM/15/0336 | PPA-380-2068 |  |  |  |  | 2015-08-25 |  | 2015-12-15 | 2016-03-02 |  |  | 2016-06-27 | 2016-06-27 |  |  |  | 2019-06-27
| 5745 | 2015-11-05 | Arbour Hill Biogas | Arbour Hill | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Field at, Patrick Brompton, Bedale | North Yorkshire | Yorkshire and Humber | England | DL8 1JX | 422281 | 492570 | Richmondshire District Council | 15/00523/FULL | [5 empty] | 2015-07-06 |  | 2015-10-05
| 5746 | 2020-01-23 | Oaklands Farm Eggs | RAF Shawbury | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Storage Hangar, Wem Road, Shawbury, Shrewsbury | Shropshire | West Midlands | England | SY4 4RH | 356173 | 322726 | Shropshire Council | 15/02839/FUL | [5 empty] | 2015-07-30 | [6 empty] | 2017-05-30 |  |  |  | 2020-05-30
| 5747 | 2019-12-10 | Langdon Enterprises | Langdon Mill | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Langdon Mill, Begelly, Kilgetty, Dyfed | Pembrokeshire | Wales | Wales | SA68 0NJ | 208580 | 207612 | Pembrokeshire County Council | 15/0421/PA | [5 empty] | 2015-08-03 | [6 empty] | 2015-12-11 |  |  |  | 2020-12-11 | 2017-03-01
| 5748 | 2019-12-05 | Greener for Life Energy | Willand AD | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lloyd Maunder Road, Willand, Cullompton | Devon | South West | England | EX15 2PJ | 303030 | 111217 | Mid Devon District Council | DCC/3725/2014 | [5 empty] | 2015-01-12 | [6 empty] | 2015-05-26 |  |  |  |  | 2017-06-15 | 2015-08-15
| 5749 | 2017-03-01 | Neilson Biogas | Park Farm AD | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Park Farm, Hurlawcrook Road, East Kilbride, Glasgow, Strathclyde | South Lanarkshire | Scotland | Scotland | G75 0QL | 263684 | 649872 | South Lanarkshire Council | EK/15/0233 | [5 empty] | 2015-07-24 | 2015-10-02
| 5750 | 2016-09-27 | R Gough & Son Ltd | Wigley Farm | Anaerobic Digestion |  |  | 1.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Wigley Farm, Wigley Drive, Wigley, Ludlow | Shropshire | West Midlands | England | SY8 3DR | 352544 | 276744 | Shropshire Council | 15/00790/MAW | [5 empty] | 2015-02-24 | [6 empty] | 2015-06-24 |  |  |  |  | 2015-07-24 | 2016-06-24
| 5751 | 2018-04-20 | Marston St Lawrence Estate | Stuchbury Manor Farm | Anaerobic Digestion |  |  | 1.25 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Stuchbury Manor Farm, Greatworth | Northamptonshire | East Midlands | England | OX17 2DQ | 455740 | 243658 | South Northamptonshire Council | S/2015/0075/FUL | [5 empty] | 2015-01-15 | [6 empty] | 2015-03-12
| 5752 | 2018-02-01 | Veolia Energy Services | The Sawmill | Biomass (dedicated) |  |  | 6.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | The Sawmill, Fosse Way, Upper Broughton | Nottinghamshire | East Midlands | England | NG12 5PS | 465176 | 327428 | Nottinghamshire County Council | ES/2872 | [5 empty] | 2015-10-09 | [6 empty] | 2015-02-05 |  |  |  | 2018-02-05 | 2015-09-24 | 2017-03-24
| 5753 | 2015-10-15 | John Brooke Sawmills | The Sawmill | Biomass (dedicated) |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | The Sawmill, Fosse Way, Upper Broughton | Nottinghamshire | East Midlands | England | NG12 5PS | 465176 | 327428 | Nottinghamshire County Council | F/1908 | [5 empty] | 2010-04-30 | [6 empty] | 2011-01-07 |  |  |  | 2014-01-07
| 5754 | 2015-10-15 | John Brooke Sawmills | The Sawmill | Biomass (dedicated) |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | The Sawmill, Fosse Way, Upper Broughton | Nottinghamshire | East Midlands | England | NG12 5PS | 465176 | 327428 | Nottinghamshire County Council | F/1390 | [5 empty] | 2008-09-22 | [6 empty] | 2009-05-29 |  |  |  | 2012-05-29
| 5755 | 2015-11-05 | Agri-Gen | Bentwaters Park | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bentwaters Park, Rendlesham, Woodbridge | Suffolk | Eastern | England | IP12 2TW | 634881 | 253511 | Suffolk Coastal District Council | C/08/2152 | [5 empty] | 2008-12-03 | [6 empty] | 2010-04-08 |  |  |  |  | 2011-11-01 | 2012-11-21
| 5756 | 2016-06-16 | United Utilities | Godley Water Treatment Works | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Floating | Operational | Operational | Godley Water Treatment Works, Barmhouse Lane, Hyde, Tameside | Greater Manchester | North West | England |  | 396214 | 395374 | Tameside Metropolitan Borough Council | [18 empty] | 2015-10-26 | 2016-04-22
| 5757 | 2020-01-22 | Ecotricity | Bulkworthy Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Bulkworthy, Newton St. Petrock, Torrington | Devon | South West | England | EX38 8LY | 240512 | 114816 | Torridge District Council | 1/1177/2015/FULM | [5 empty] | 2015-12-21 | [6 empty] | 2016-05-19 |  |  |  | 2019-05-19
| 5758 | 2020-01-22 | Ecotricity | Fen Farm Solar Park (extension) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Fen Farm Solar Park, Fen Lane, Conisholme, Louth | Lincolnshire | East Midlands | England | LN11 7LU | 538602 | 393366 | East Lindsey District Council | N/036/02486/15 | [5 empty] | 2015-12-31 | [6 empty] | 2016-03-02 |  |  |  | 2019-03-02
| 5759 | 2020-01-22 | Ecotricity | Old Dalby Lodge Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Field No 0006, Paddys Lane, Old Dalby, Melton Mowbray | Leicestershire | East Midlands | England | LE14 3LY | 464846 | 323140 | Melton Borough Council | 16/00078/FUL | [5 empty] | 2016-02-05 | [6 empty] | 2016-05-12 |  |  |  | 2019-05-12
| 5780 | 2015-11-05 | FCC Environment | Eastcroft EfW (Lines 1 & 2) | EfW Incineration |  |  | 9 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Cattle Market Road, Nottingham, Nottinghamshire | Nottinghamshire | East Midlands | England |  | 458200 | 339100 | Nottingham City Council | [19 empty] | 1975-01-01
| 5781 | 2017-01-16 | FCC Environment | Eastcroft EfW (3rd Line) | EfW Incineration |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Cattle Market Road, Nottingham, Nottinghamshire | Nottinghamshire | East Midlands | England |  | 458200 | 339100 | Nottingham City Council | 07/01502/PMFUL3 | [5 empty] | 2007-08-06 | [6 empty] | 2009-02-12 | 2008-09-30 |  | 2009-02-12 | 2012-02-12
| 5782 | 2015-03-04 | New Energy for the World | Long Marton | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at Long Marton, Appleby | Cumbria | North West | England | CA16 6DS | 366400 | 526525 | Eden District Council | 15/0908 | [5 empty] | 2015-10-07 |  | 2016-02-24
| 5784 | 2018-10-31 | Ramboll Environ UK/Comsol Energy | Ballochmartin | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Site To The North East Of, Wee Minnemoer, Millport, Strathclyde | Strathclyde | Scotland | Scotland | KA28 0 | 216964 | 656725 | North Ayrshire Council | 16/00124/PP | [5 empty] | 2016-02-15 | [6 empty] | 2017-03-29 |  |  |  | 2020-03-29
| 5785 | 2019-01-29 | Greenside Wind Energy | South of Greenwellheads | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land To The S/Of Greenwellhead, St. Fergus, Peterhead, Grampian | Aberdeen | Scotland | Scotland | AB42 3HG | 406370 | 854550 | Aberdeenshire Council | APP/2015/2949 | [5 empty] | 2015-09-24 | [6 empty] | 2015-10-30 |  |  |  | 2018-10-30
| 5786 | 2016-04-19 | BNRG (BL Solar) | Park Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north west of Park Farm, Pagham, Lagness, Chichester | West Sussex | South East | England | PO20 1LL | 490501 | 101487 | Arun District Council | P/81/15/PL | [5 empty] | 2015-07-23 | [6 empty] | 2015-10-29 |  |  |  | 2018-10-29 | 2015-12-15 | 2016-03-24
| 5788 | 2017-12-05 | Engie | Varteg Hill | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 | 115 | n/a | Planning Permission Refused | Application Refused | Varteg Wind Farm, Land South Of, Ystalyfera, Swansea | Neath Port Talbot | Wales | Wales | CH7 | 277400 | 207500 | Neath Port Talbot County Borough Council | P2015/0859 | [5 empty] | 2015-09-17 |  | 2017-10-24
| 5789 | 2016-08-18 | Lightsource Renewable Energy | United Biscuits Distribution Warehouse | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | United Biscuits Distribution, Nottingham Road, Ashby-De-La-Zouch | Leicestershire | East Midlands | England | LE65 1DS | 436743 | 317567 | North West Leicestershire District Council | 15/00758/PDNALO | [5 empty] | 2015-07-30 | [6 empty] | 2015-09-17 |  |  |  | 2020-09-17
| 5790 | 2017-07-21 | British Solar Renewables | Country Lane Solar Development | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land To The West Of, County Lane, Albrighton, Wolverhampton | Shropshire | West Midlands | England | WV7 3AH | 383307 | 303996 | Shropshire Council | 15/04345/FUL | [5 empty] | 2015-10-13 | 2017-03-01
| 5793 | 2016-06-29 | New Energy for the World | Greaves Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Greaves Farm, Popplemire Lane, Old Hutton, Kendal | Cumbria | North West | England | LA8 0NA | 355498 | 488023 | South Lakeland District Council | SL/2015/0694 | [5 empty] | 2015-08-24 | [6 empty] | 2015-11-03 |  |  |  | 2018-11-03 |  | 2016-03-31
| 5795 | 2018-07-05 | NESF (formerly Lark Energy) | Balhearty Solar | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Balhearty, Coalsnaughton, Tillicoultry | Clackmannanshire | Scotland | Scotland | FK13 6NA | 293723 | 695800 | Clackmannanshire Council | 15/00188/FULL | [5 empty] | 2015-10-20 | [6 empty] | 2015-12-23 |  |  |  | 2020-12-23 | 2016-02-01 | 2016-03-31
| 5796 | 2019-11-29 | Green Switch Solutions/Belvedere Energy Developments - Liquidated | Weddington Farm | Solar Photovoltaics |  |  | 2.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Weddington Farm, Hambridge Road, Bishops Itchington, Southam | Warwickshire | West Midlands | England | CV47 2SA | 440523 | 257880 | Stratford on Avon District Council | 15/02717/FUL | [5 empty] | 2015-09-16 | [6 empty] | 2016-09-05 |  |  |  | 2019-09-05 | 2016-08-24 | 2016-10-28
| 5797 | 2018-04-04 | Lightsource Renewable Energy | Middle Balbeggie | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ld To N Of Redhouse Grid Subst, Thornton Road, Kirkcaldy | Fife | Scotland | Scotland | KY1 3NN | 328855 | 695619 | Fife Council | 15/02687/FULL | [5 empty] | 2015-09-16 | [6 empty] | 2015-12-17 |  |  |  | 2018-12-17 | 2016-10-17 | 2017-01-27
| 5798 | 2017-12-20 | Nissan | Nissan Wind Farm Extension | Wind Onshore |  |  | 4.25 | n/a |  |  |  | 0.85 | 5 | 76 | n/a | Planning Application Withdrawn | Application Withdrawn | Nissan Motor Manufacturing, Washington Road, Usworth, Sunderland | Tyne and Wear | North East | England | SR5 3NS | 433864 | 557695 | Sunderland City Council | 15/02550/FUL | [5 empty] | 2015-12-23 | 2017-11-07
| 5800 | 2020-01-20 | North Gisborne | Land North of Balbeggie Avenue | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land To North Of, Balbeggie Avenue, Balbeggie Thornton, Kirkcaldy | Fife | Scotland | Scotland | KY1 3NS | 328587 | 696532 | Fife Council | 15/03472/FULL | [5 empty] | 2015-10-13 | [6 empty] | 2016-03-29
| 5801 | 2016-05-04 | Sadborow Solar Parks | Gashay Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land East Of, Sadborow Lane, Thorncombe, Hawkchurch, Axminster | Dorset | South West | England | EX13 5UT | 337439 | 101761 | West Dorset District Council | WD/D/15/001863 | [5 empty] | 2015-10-15 |  | 2016-04-28
| 5802 | 2018-09-27 | Vortex (formerly SunEdison) | Cefn Cae For | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Cefn Caer For, Gwalchmai, Holyhead | Isle of Anglesey | Wales | Wales | LL65 4SF | 239589 | 374868 | Isle of Anglesey County Council | 48C160C/RE | [5 empty] | 2015-09-27 | [6 empty] | 2016-02-11 |  |  |  | 2021-02-11
| 5803 | 2018-12-14 | RALOS New Energy | Mill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land At Mill Farm, Downall Green Road, Ashton-in-Makerfield, Wigan | Greater Manchester | North West | England | WN4 0NA | 356311 | 400120 | Wigan Council | A/15/81185/MAJOR | [5 empty] | 2015-07-22 | [6 empty] | 2015-12-16 |  |  |  | 2018-12-16
| 5804 | 2018-09-17 | Lark Energy | Rollston on Dove, Marston Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land East Of, Marston Lane, Rolleston-on-Dove, Burton-On-Trent | Staffordshire | West Midlands | England | DE13 9B | 424064 | 328579 | East Staffordshire Borough Council | P/2015/01064 | [5 empty] | 2015-09-08 | [6 empty] | 2015-12-11 |  |  |  | 2018-12-11
| 5805 | 2020-01-29 | Perpetum Sun | Magor Brewery | Solar Photovoltaics |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | Magor Brewery, Newport Road, Magor, Caldicot | Monmouthshire | Wales | Wales | NP26 3RA | 341574 | 187703 | Monmouthshire County Council | DC/2015/01158 | [5 empty] | 2015-09-28 | [6 empty] | 2015-10-30 |  |  |  | 2020-10-30
| 5806 | 2016-05-04 | Earthworm Energy | Park Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | LAND AT SK2720, 3150 Park Road, Newhall, Swadlincote | Derbyshire | East Midlands | England | DE11 0TT | 427622 | 320179 | South Derbyshire District Council | 9/2015/0689 | [5 empty] | 2015-09-01 |  | 2016-04-21
| 5807 | 2018-09-27 | Solar Sense | Unit DC1 Prologis | Solar Photovoltaics |  |  | 1.09 | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | Unit DC1 Prologis, Boscombe Road, Dunstable | Bedfordshire | Eastern | England | LU5 4FA | 502294 | 222563 | Central Bedfordshire Council | CB/15/03890/LDON | [5 empty] | 2015-07-10 | [6 empty] | 2015-10-15 |  |  |  | 2018-10-15
| 5808 | 2018-09-25 | Solstice Renewables | Cleworth Hall Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Cleworth Hall Farm, Cleworth Hall Lane, Tyldesley, Agricultural Land North Of, Manchester | Greater Manchester | North West | England | M29 8WS | 370395 | 403132 | Wigan Council | A/15/81522/MAJOR | [5 empty] | 2015-10-13 | [6 empty] | 2016-02-09 |  |  |  | 2019-02-09
| 5809 | 2020-01-29 | Perpetum Sun | AB Inbev UK | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | AB Inbev UK Limited, Cuerdale Lane, Samlesbury, Preston | Lancashire | North West | England | PR5 0XD | 359421 | 429656 | South Ribble Borough Council | 07/2015/1627/FUL | [5 empty] | 2015-10-13 | [6 empty] | 2015-11-11 |  |  |  | 2020-11-12
| 5810 | 2019-08-27 | Roborough Solar | Tamerton Road | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land Off, Tamerton Road, Woolwell, Plymouth | Devon | South West | England | PL6 7BQ | 249374 | 61874 | South Hams District Council | 04/2253/15/F | [5 empty] | 2015-10-14 | [6 empty] | 2016-03-10 |  |  |  | 2019-03-10
| 5811 | 2015-11-05 | OST Energy | Warren House | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Warren Avenue, Annesley, Nottingham | Nottinghamshire | East Midlands | England | NG15 0AF | 451488 | 354409 | Ashfield District Council | V/2015/0618 | [5 empty] | 2015-10-12 |  | 2016-01-29
| 5812 | 2019-02-19 | North Ayrshire Council | Nethermains | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Nethermains Landfill, Irvine, Strathclyde | North Ayrshire | Scotland | Scotland | KA12 8EE | 231611 | 604614 | North Ayrshire Council | 15/00568/PP | [5 empty] | 2015-10-13 | [6 empty] | 2015-12-01 |  |  |  | 2018-12-01
| 5814 | 2016-01-06 | New Energy for the World | Tunstall Hall Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Tunstall Hall Farm, Park Lane, High Offley, Woodseaves, Stafford | Staffordshire | West Midlands | England | ST20 0NB | 379045 | 327412 | Stafford Borough Council | 15/23038/FUL | [5 empty] | 2015-09-30 |  | 2015-12-16
| 5815 | 2015-11-05 | New Energy for the World | West Newton | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at, Westnewton, Wigton | Cumbria | North West | England | CA7 3PE | 311677 | 544058 | Allerdale Borough Council | 2/2015/0620 | [5 empty] | 2015-10-09 |  | 2016-03-22
| 5816 | 2017-11-20 | Orsted (formerly Dong Energy) | Land at Lostock Works (Northwich Facility) | Anaerobic Digestion |  |  | 5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land At Lostock Works, Works Lane, Northwich | Cheshire | North West | England |  | 367920 | 374201 | Cheshire West and Chester Council | 15/04133/FUL | [5 empty] | 2015-10-08 | [6 empty] | 2016-02-11 |  |  |  | 2019-02-11 | 2016-05-07 | 2016-10-20
| 5817 | 2017-12-20 | West Coast Energy | Land South of Ystalyfera | Wind Onshore |  |  | 12 | n/a |  |  |  | 3 | 4 | 115 | n/a | Planning Permission Refused | Application Refused | Varteg Hill Land South of, Neath | Powys | Wales | Wales | SA9 | 277400 | 207500 | Powys County Council | P/2015/0803 | [5 empty] | 2015-09-17 |  | 2017-12-08
| 5818 | 2016-08-03 | TW Solar | Land South East of Low Common Farm | Solar Photovoltaics |  |  | 8.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land North Of Westfield Farm, Westfield Lane, Barlborough, Chesterfield | Derbyshire | East Midlands | England | S43 4TP | 446486 | 376935 | Bolsover District Council | 15/00493/FUL | [5 empty] | 2015-10-07 |  | 2016-06-29
| 5819 | 2017-05-02 | TGC Renewables | Moor Lane | Solar Photovoltaics |  |  | 5.82 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at, Moor Lane, Loughborough | Leicestershire | East Midlands | England | LE11 | 455722 | 319028 | Charnwood Borough Council | P/15/1056/2 | [5 empty] | 2015-06-23 | 2017-04-11
| 5820 | 2016-01-06 | Blue Planet Solar | Lower House Lane | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land North Of Stone Cottage, Lower House Lane, Baddesley Ensor, Atherstone | Warwickshire | West Midlands | England | CV9 2QB | 425671 | 298669 | North Warwickshire Borough Council | PAP/2015/0614 | [5 empty] | 2015-10-07 |  | 2015-12-15
| 5821 | 2016-05-04 | Gascorp | Pitwherry Bridge | Anaerobic Digestion |  |  | 3.25 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land South West Of West Farm, Foston Road, Beeford, Driffield | Humberside | Yorkshire and Humber | England |  | 511449 | 454539 | East Riding of Yorkshire Council | 15/02870/STPLF | [5 empty] | 2015-09-30 |  | 2016-04-20
| 5822 | 2018-10-26 | British Solar Renewables | Broadfield Farmhouse | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land At Broadfield Farm, Broadfield Farm Lane, Eastington, Cheltenham | Gloucestershire | South West | England | GL54 3PX | 412833 | 211197 | Cotswold District Council | 15/03186/FUL | [5 empty] | 2015-10-01 | [6 empty] | 2016-02-24 |  |  |  | 2019-02-24
| 5823 | 2016-04-13 | Active Renewables | Land East of Panteg Way | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land East of, Panteg Way, Pontypool | Torfaen | Wales | Wales | NP4 0LS | 329979 | 198509 | Torfaen County Borough Council | 15/P/00437 | [5 empty] | 2015-09-25 | [6 empty] | 2015-12-22
| 5824 | 2017-07-18 | Wirsol (formerly Susenco) | Widehurst Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Widehurst Farm, Thorn Road, Marden, Tonbridge | Kent | South East | England | TN12 9LN | 575536 | 142994 | Tunbridge Wells Borough Council | 15/505971/FULL | [5 empty] | 2015-10-01 | [6 empty] | 2016-03-03 |  |  |  | 2019-03-03 | 2016-11-07 | 2017-03-15
| 5825 | 2018-09-25 | Solstice Renewables | Hollamoor Farm | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Hollamoor Farm, Eastacombe, Barnstaple | Devon | South West | England | EX31 3NT | 254699 | 129962 | North Devon District Council | 60026 | [5 empty] | 2015-09-29 | [6 empty] | 2016-03-10 |  |  |  | 2019-03-10
| 5826 | 2016-05-04 | Blue Planet Solar | Hayden Hill Fruit Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Hayden Hill Fruit Farm, Old Gloucester Road, Hayden, Cheltenham | Gloucestershire | South West | England |  | 390575 | 224139 | Tewkesbury Borough Council | 15/00982/FUL | [5 empty] | 2015-09-11 |  | 2016-04-12
| 5828 | 2016-09-22 | Kingfisher Scottish Limited Partnership | Screwfix Direct | Solar Photovoltaics |  |  | 2.483 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Screwfix Direct, Trentham Lakes South, Stanley Matthews Way, Stoke-On-Trent | Staffordshire | West Midlands | England |  | 388612 | 341995 | Stoke on Trent City Council | 58866/FUL | [5 empty] | 2015-10-08 | [6 empty] | 2015-11-03 |  |  |  | 2018-11-03 | 2015-11-12 | 2016-01-12
| 5829 | 2015-11-30 | Ramsey Solar | Land at Biggin Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Ld SE Of Bury Green Farm and, Biggin Lane, South Of, Ramsey, Huntingdon | Cambridgeshire | Eastern | England |  | 527020 | 284650 | Huntingdonshire District Council | 15/00768/FUL | [5 empty] | 2015-05-13 | [6 empty] | 2015-09-23 |  |  |  | 2018-09-23 | 2015-10-15 | 2016-03-15
| 5830 | 2018-08-30 | Gascorp | Park Farm | Anaerobic Digestion |  |  | 3 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Park Farm, Market Weighton Road, Holme-on-spalding-Moor, York | Humberside | Yorkshire and Humber | England |  | 481592 | 439471 | East Riding of Yorkshire Council | 15/02993/STPLF | APP/E2001/W/16/3154080 |  |  |  |  | 2015-10-01 |  | 2016-02-09 | 2016-08-30 | 2017-06-20
| 5832 | 2017-09-21 | Wirsol | Land at Barnham | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At Barnham Court, Barnham, Bognor Regis | West Sussex | South East | England |  | 495086 | 103423 | Arun District Council | BN/29/15/PL | [5 empty] | 2015-08-10 | [6 empty] | 2016-02-24 |  |  |  | 2019-02-24 | 2017-01-16 | 2017-02-20
| 5834 | 2017-12-04 | Greencoat Capital | Ebnal Lodge (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land At, Rhosygadfa, Gobowen, Oswestry | Shropshire | West Midlands | England |  | 331810 | 334117 | Shropshire Council | 15/03975/FUL | [5 empty] | 2015-09-23 | [6 empty] | 2015-12-23 |  |  |  | 2018-12-23 | 2016-12-12 | 2017-02-15
| 5835 | 2016-11-30 | Sustainable Charlbury (Community) | Southill Solar (resubmission) | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land West Of, Fawler Road, Charlbury, Chipping Norton | Oxfordshire | South East | England |  | 436251 | 217933 | West Oxfordshire District Council | 15/01523/FUL | [5 empty] | 2015-04-28 | [6 empty] | 2015-09-07 |  |  |  | 2018-09-07 | 2016-08-15 | 2016-11-14
| 5836 | 2015-12-02 | Kingfisher Scottish Limited Partnership | Unit DC 1 - Screwfix Direct | Solar Photovoltaics |  |  | 1.848 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Application Withdrawn | Application Withdrawn | Unit DC 1 Screwfix Direct, 1 Shackleton Way, Stafford | Staffordshire | West Midlands | England |  | 390605 | 326193 | Stafford Borough Council | 15/23005/FUL | [5 empty] | 2015-09-23 | 2015-11-05
| 5837 | 2020-01-16 | FCC Environment | Eastcroft EfW (3rd Line) (resubmission) | EfW Incineration |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Eastcroft Energy From Waste Fa, Incinerator Road, Nottingham | Nottinghamshire | East Midlands | England |  | 458211 | 339082 | Nottingham City Council | 15/02548/PMFUL3 | [5 empty] | 2015-10-02 | [6 empty] | 2016-01-22 |  |  |  | 2019-01-22
| 5838 | 2017-04-25 | Navitas Project | Carver Hay, moss lane | Solar Photovoltaics |  |  | 2.54 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Carver Hey Farm, Moss Lane, Little Hoole, Preston | Lancashire | North West | England |  | 348519 | 423631 | South Ribble Borough Council | 07/2015/1494/FUL | [5 empty] | 2015-10-01 | [6 empty] | 2015-12-15 |  |  |  | 2018-12-15 | 2017-01-15 | 2017-03-20
| 5839 | 2015-03-04 | Stockley Hill Solar Farm | Stockley Hill Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land to south and e/o Rylah Farm, Rylah, Palterton, Chesterfield | Derbyshire | East Midlands | England |  | 446886 | 367711 | Bolsover District Council | 15/00366/FUL | [5 empty] | 2015-10-02 |  | 2016-02-11
| 5840 | 2020-04-21 | Mansfield Sand | Two Oaks Quarry | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Two Oaks Quarry, Derby Road, Coxmoor Road, Kirkby in Ashfield, Mansfield | Nottinghamshire | East Midlands | England |  | 453720 | 357006 | Ashfield District Council | V/2015/0589 | [5 empty] | 2015-09-30 | [6 empty] | 2015-10-15 |  |  |  | 2018-10-15
| 5841 | 2016-01-06 | Sun E Greenfield | Kenyon Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at, Kenyon Lane, Croft, Warrington | Cheshire | North West | England |  | 363137 | 396103 | Warrington Borough Council | 2015/26259 | [5 empty] | 2015-09-28 |  | 2015-12-24
| 5842 | 2015-11-05 | TW Solar | Lane East of Drakelow Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at SK2218 4377, Drakelow Road, Walton-on-Trent, Swadlincote | Derbyshire | East Midlands | England |  | 442602 | 318698 | South Derbyshire District Council | 9/2015/0858 | [5 empty] | 2015-09-22 |  | 2016-03-04
| 5843 | 2017-03-29 | Earthworm Energy | Broad Lane | Solar Photovoltaics |  |  | 8.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Hawkshurst Moor Farm, Broad Lane, Coventry | West Midlands | West Midlands | England |  | 426577 | 279803 | Solihull Metropolitan Borough Council | PL/2015/51636/PPFL | APP/Q4625/W/16/3155025 |  |  |  |  | 2015-09-14 |  | 2016-02-08 | 2016-09-13 |  | 2017-03-01
| 5844 | 2020-01-20 | Project Genesis | Hownsgill Industrial Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | E/o Hownsgill Industrial Park, Knitsley Lane, Consett | County Durham | North East | England |  | 410254 | 549392 | Durham County Council | DM/15/02364/FPA | [5 empty] | 2015-08-28 | [6 empty] | 2016-03-01 |  |  |  | 2019-03-02 | 2019-02-15
| 5845 | 2019-01-24 | Bruxiehill Wind Energy | Bruxiehall Farm | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land To The South Of Bruxiehil, St. Fergus, Peterhead | Aberdeen | Scotland | Scotland |  | 408820 | 851140 | Aberdeenshire Council | APP/2015/3060 | [5 empty] | 2015-09-29 | [6 empty] | 2015-11-25 |  |  |  | 2018-11-24 | 2018-09-15
| 5846 | 2019-01-29 | Livos Energy | Cinderbarrow Lane | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land South Of, Cinderbarrow Lane, Priest Hutton, Carnforth | Lancashire | North West | England |  | 352071 | 474910 | Lancaster City Council | 15/00949/FUL | [5 empty] | 2015-07-23 | [6 empty] | 2016-01-21 |  |  |  | 2019-01-21
| 5847 | 2015-11-05 | Haymaker Energy / Trina Solar | Heath Lane (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land at, Heath Lane, Honington, Grantham | Lincolnshire | East Midlands | England |  | 495586 | 343012 | South Kesteven District Council | S15/2136 | [5 empty] | 2015-09-18 |  | 2016-03-09
| 5848 | 2017-05-23 | UK Sustainable Energy | St Helen's Lane | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent To, St Helens Lane, Flimby, Maryport | Cumbria | North West | England |  | 301675 | 532077 | Allerdale Borough Council | 2/2015/0593 | [5 empty] | 2015-09-22 | [6 empty] | 2015-12-21 |  |  |  | 2018-12-21 | 2017-01-01 | 2017-03-28
| 5849 | 2017-03-29 | Townsend Solar Farm | Townsend Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land to the S/o Townsend Farm, Townsend, Axbridge | Somerset | South West | England |  | 342489 | 154692 | Sedgemoor District Council | 02/15/00019 | APP/V3310/W/16/3141866 |  |  |  |  | 2015-09-18 |  | 2015-12-17 | 2016-05-04 |  | 2017-03-22
| 5851 | 2018-01-30 | Viridor | Broadpath Landfill | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Viridor Waste Management Ltd, Broad Path Landfill Site, Uffculme, Burlescombe, Cullompton | Devon | South West | England |  | 306486 | 113940 | Mid Devon District Council | 15/01511/MFUL | [5 empty] | 2015-09-29 | [6 empty] | 2015-12-18 |  |  |  | 2018-12-18
| 5852 | 2018-08-29 | Solar Farm DFD | Dale Farm | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Approx. 350m south of the Dale, 139 Moneymore Road, Cookstown | Co. Tyrone | Northern Ireland | Northern Ireland |  | 94437 | 539069 | Northern Ireland Planning Service | LA09/2015/0885/F | [5 empty] | 2015-09-28 | [6 empty] | 2016-01-21 |  |  |  | 2021-01-20 | 2017-09-15 | 2018-08-01
| 5853 | 2016-01-06 | Active Renewables | Gatehouse Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Gate House Farm, High Cross Lane, Rowington, Warwick | Warwickshire | West Midlands | England | CV35 7BA | 420995 | 267251 | Warwick District Council | W/15/1173 | [5 empty] | 2015-09-18 |  | 2015-12-11
| 5858 | 2020-02-04 | Good Energy | Delabole | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land North Of Deli Farm, Delabole | Cornwall | South West | England |  | 208543 | 84039 | Cornwall Council | PA15/08617 | [5 empty] | 2015-09-29 | [6 empty] | 2016-02-26 |  |  |  | 2019-02-26
| 5859 | 2020-06-26 | Mountwest 838 | Mountwest Wind Cluster (resubmission) | Wind Onshore |  |  | 2.4 | n/a |  |  |  | 2.4 | 3 | 76.5 | n/a | Planning Permission Granted | Awaiting Construction | Land At Mains Of Cairnbrogie, Oldmeldrum, Inverurie | Aberdeen | Scotland | Scotland |  | 384500 | 828500 | Aberdeenshire Council | APP/2015/2965 | [5 empty] | 2015-09-21 | [6 empty] | 2016-08-24 |  |  |  | 2019-08-23
| 5861 | 2019-07-19 | Energia Renewables | Eshmore Wind Farm Extension | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 102.5 | n/a | Planning Permission Granted | Awaiting Construction | 641metres North of, 28 Altaglushan Road, Galbally, Dungannon | Co. Tyrone | Northern Ireland | Northern Ireland |  | 77440 | 527096 | Northern Ireland Planning Service | LA09/2015/0488/F | [5 empty] | 2015-07-02 | [6 empty] | 2016-07-08 |  |  |  | 2021-07-07
| 5863 | 2019-08-22 | Cierco | Forth of Firth (Methil) | Wind Offshore |  |  | 29.9 | n/a |  |  |  | 6 | 2 | 121 | n/a | Planning Permission Granted | Awaiting Construction | Forth of Firth | Offshore | Offshore | Scotland |  | 338141 | 696278 | Marine Scotland | [6 empty] | 2015-07-06 | [6 empty] | 2016-12-21
| 5864 | 2018-09-04 | Bristol Energy Co-Op | Avonmouth | Solar Photovoltaics |  |  | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Avonmouth | Avon | South West | England |  | 353021 | 179008 | Bristol City Council | 16/01640/COND | [5 empty] | 2016-03-30 | [6 empty] | 2016-04-08 |  |  |  |  | 2016-04-21 | 2016-06-28
| 5866 | 2017-02-27 | Eco Energy World | Newport (Began Road) | Solar Photovoltaics |  |  | 4.85 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Fairwater Farm, Michaelston-y-Fedw | Newport | Wales | Wales | CF3 6XS | 323807 | 184116 | Newport City Council | 14/0337 | [5 empty] | 2014-04-03 | [6 empty] | 2015-10-22 |  |  |  | 2020-10-22 | 2015-12-14 | 2016-02-14
| 5868 | 2018-09-17 | Lark Energy | Ellough Airfield (biodiesel) | Biomass (dedicated) |  |  | 19 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Beccles Heliport, Benacre Road, Ellough | Suffolk | Eastern | England | NR34 7XD | 646125 | 287835 | Waveney District Council | DC/15/2823/FUL | [5 empty] | 2015-07-14 | [6 empty] | 2015-12-18 |  |  |  | 2018-12-18
| 5871 | 2019-10-23 | Belectric (Big 60 Million) | Nanhoron Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Nanhoron Estate, Botwnnog, Pwllheli, Gwynedd, Wales | Gwynedd | Wales | Wales | LL53 8DP | 226439 | 330997 | Gwynedd Council | C15/0793/32/LL | [5 empty] | 2015-11-23 | [6 empty] | 2016-11-30 |  |  |  | 2021-11-30
| 5872 | 2016-05-04 | AR Partners | Stocks House Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land west of The Row, Upper Wellington, Wellington | Hereford and Worcester | West Midlands | England | HR4 8AZ | 348869 | 247693 | Herefordshire Council | P150929/F | APP/W1850/W/15/3137273 |  |  |  |  | 2015-03-31 |  | 2015-06-30 | 2015-11-05 |  | 2016-04-14
| 5874 | 2019-01-29 | Hunterston Estates | Land at Hunterston Estate | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Campbelton Bungalow, Hunterston Estate, (Site To South East Of), West Kilbride, Strathclyde, Scotland | North Ayrshire | Scotland | Scotland | KA23 9QF | 219397 | 650592 | North Ayrshire Council | 15/00487/PP | [5 empty] | 2015-11-24 | [6 empty] | 2016-01-15 |  |  |  | 2019-01-15
| 5876 | 2019-11-21 | Private Developer | Stoney Hill Farm | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 | 100 | n/a | Planning Permission Granted | Awaiting Construction | Stoneyhill Farm, Drumclog, Strathaven, Strathclyde, Scotland | South Lanarkshire | Scotland | Scotland | ML10 6RG | 266542 | 636804 | South Lanarkshire Council | EK/15/0375 | [5 empty] | 2015-11-23 | [6 empty] | 2016-07-05 |  |  |  | 2019-07-05
| 5877 | 2016-05-04 | Push Energy | Abbey Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at Abbey Farm, Grange Road, Ickleton, Saffron Walden, Essex, East of England | Cambridgeshire | Eastern | England | CB10 1TA | 547410 | 243820 | South Cambridgeshire District Council | S/2617/15/FL | [5 empty] | 2015-10-15 | 2016-04-01
| 5878 | 2019-12-10 | Yge Warren House | Wayside Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Wayside Farm, Skeyton Road, North Walsham, Norfolk, East of England | Norfolk | Eastern | England | NR28 0JG | 626665 | 329004 | North Norfolk District Council | PF/15/1536 | [5 empty] | 2015-11-10 | [6 empty] | 2016-02-17 |  |  |  | 2019-02-17
| 5879 | 2016-12-22 | Solar Power Inc UK Services | Land South of Knock Lane (resubmission) | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land to the South of Knock Lane, Blisworth | Northamptonshire | East Midlands | England | NN7 3DA | 473235 | 252464 | South Northamptonshire Council | S/2015/2492/MAF | [5 empty] | 2015-10-26 | [6 empty] | 2015-12-17 |  |  |  | 2018-12-17
| 5880 | 2017-04-20 | TGC Renewables | Land to the south of Hill Farm (resubmission) | Solar Photovoltaics |  |  | 6.84 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land to the south of Hill Farm, Gayton Road, Kislingbury | Northamptonshire | East Midlands | England |  | 469990 | 256921 | South Northamptonshire Council | S/2015/2469/MAF | [5 empty] | 2015-10-22 | [6 empty] | 2016-01-14 |  |  |  | 2019-01-14 | 2016-12-12 | 2017-03-31
| 5881 | 2016-05-04 | Push Energy | Rectory Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Rectory Farm, Grange Road, Ickleton, Saffron Walden, Essex, East of England | Cambridgeshire | Eastern | England | CB10 1TA | 547097 | 243728 | South Cambridgeshire District Council | S/2642/15/FL | [5 empty] | 2015-10-15 | 2016-04-01
| 5882 | 2017-09-01 | Ecotricity | Shilton Downs Solar Park (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Shilton Downs Farm, Shilton | Oxfordshire | South East | England | OX18 4AL | 425850 | 209028 | West Oxfordshire District Council | 15/04003/FUL | APP/D3125/W/16/3158494 |  |  |  |  | 2015-11-13 |  | 2016-03-23 | 2017-01-10 |  | 2017-08-16
| 5883 | 2020-06-30 | Hive Energy | Woodington Farm | Solar Photovoltaics |  |  | 40 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Woodington Farm, Woodington Road, East Wellow, Romsey, Hampshire, South East | Hampshire | South East | England | SO51 6DQ | 430472 | 121002 | Test Valley Borough Council | 15/02591/FULLS | [5 empty] | 2015-11-17 | [6 empty] | 2017-07-04 |  |  |  | 2020-07-04
| 5884 | 2017-01-31 | Environmental Energy Investments | Weels Farm Solar Array | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Weels Farm, Kaim Road, Lochwinnoch, Strathclyde, Scotland | Renfrewshire | Scotland | Scotland | PA12 4LD | 235358 | 661528 | Renfrewshire Council | 15/0821/PP | PPA-110-2298 |  |  |  |  | 2015-11-12 |  | 2016-02-03 | 2016-04-21 |  | 2016-12-29
| 5885 | 2016-05-04 | Hadstone Energy | Tomkins Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Tomkins Farm, Cinder Hill, North Chailey | East Sussex | South East | England | BN8 4HP | 540592 | 118937 | Lewes District Council | LW/15/0292 | APP/P1425/W/15/3135238 |  |  |  |  | 2015-04-21 |  | 2015-07-30 | 2015-11-05 |  | 2016-04-18
| 5886 | 2020-01-15 | Material Change (formerly Strutt & Parker Farms Ltd) | Manor Farm | Anaerobic Digestion |  |  | 5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Manor Farm, 122 The Street, Bridgham, Norwich, Norfolk, East of England | Norfolk | Eastern | England | NR16 2RX | 596926 | 286007 | Breckland Council | 3PL/2015/1262/F | [5 empty] | 2015-11-09 | [6 empty] | 2016-03-31 |  |  |  | 2019-03-31
| 5887 | 2017-04-18 | Push Energy/ NextEnergy Solar Fund (NESF) | Mill Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Mill Farm, Mentley Lane, Great Munden, Ware, Hertfordshire, East of England | Hertfordshire | Eastern | England | SG11 1JR | 534472 | 225009 | East Hertfordshire District Council | 3/15/2254/FUL | [5 empty] | 2015-11-09 | [6 empty] | 2016-07-20 |  |  |  | 2019-07-20 | 2017-01-04 | 2016-12-15
| 5888 | 2015-03-04 | Big 60 Million | Land At Penstruthal Farm | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land At Penstruthal Farm Lanne, Wheal Buller, Redruth, Cornwall, South West | Cornwall | South West | England | TR16 6ST | 170862 | 40261 | Cornwall Council | PA15/06838 | [5 empty] | 2015-08-28 |  | 2015-12-18
| 5890 | 2019-11-20 | Essential Supply Products | Blackmore Park Industrial Estate | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Bank Farm, Blackmore Park Road, Welland, Malvern, Hereford and Worcester, West Midlands | Hereford and Worcester | West Midlands | England | WR13 6NL | 379939 | 243542 | Malvern Hills District Council | 15/01510/FUL | [5 empty] | 2015-10-26 | [6 empty] | 2016-09-21 |  |  |  | 2019-09-21
| 5891 | 2017-06-23 | British Solar Renewables | Southern Counties Shooting Ground Phase 2 (resubmission) | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Southern Counties Leisure, Long Ash Lane, Wardon Hill | Dorset | South West | England |  | 360917 | 102647 | West Dorset District Council | WD/D/15/001862 | [5 empty] | 2015-09-08 | [6 empty] | 2016-01-08 |  |  |  | 2019-01-08 | 2016-09-20 | 2017-02-02
| 5893 | 2016-11-30 | Environmental Energy Investments | West Mitchelton Farm Solar Array | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | West Mitchelton, Bridesmill Road, Lochwinnoch, Strathclyde, Scotland | Renfrewshire | Scotland | Scotland | PA12 4HR | 236152 | 661252 | Renfrewshire Council | 15/0802/PP | PPA-350-2017 |  |  |  |  | 2015-11-12 |  | 2016-02-03 | 2016-04-21 |  | 2016-11-28
| 5895 | 2016-05-30 | Green Switch Developments | Rectory Farm | Solar Photovoltaics |  |  | 8.94 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land at Rectory Farm, Upton Warren | Hereford and Worcester | West Midlands | England | B61 7EL | 393375 | 268559 | Wychavon District Council | 15/01035 | APP/H1840/W/15/3136031 |  |  |  |  | 2015-04-22 |  | 2015-08-26 | 2015-11-03 |  | 2016-05-23
| 5896 | 2019-11-18 | Bulrush Horticulture | Craigs Wind Turbine II | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 | 126.5 | n/a | Planning Permission Granted | Awaiting Construction | On the site of existing commer, Peat extraction site in the t, Craigs Road, Rasharkin, Ballymena, Co Antrim, Northern Ireland | Co. Antrim | Northern Ireland | Northern Ireland | BT44 8RD | 116494 | 568756 | Northern Ireland Planning Service | LA02/2015/0657/F | [5 empty] | 2015-11-09 | [6 empty] | 2017-01-31 |  |  |  | 2020-01-31
| 5897 | 2019-10-23 | Energi Generation (formerly Solar Park Developments) | Morfa Ynys Farmlands | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Morfa Ynys Farmlands, Morfa, Llanelli, Dyfed, Wales | Carmarthenshire | Wales | Wales | SA15 2 | 252332 | 198930 | Carmarthenshire County Council | S/32892 | [5 empty] | 2015-10-30 | [6 empty] | 2016-05-03 |  |  |  | 2021-05-03
| 5898 | 2017-09-01 | PS Renewables | Flamsteadbury Farm | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land north of, Hemel Hempstead Road, Gaddesden Lane, Redbourn, St. Albans, Hertfordshire, East of England | Hertfordshire | Eastern | England | AL3 7AF | 509282 | 211574 | Dacorum Borough Council | 4/02486/15/MFA | APP/A1910/W/17/3168760 |  |  |  |  | 2015-10-26 |  | 2016-11-30 | 2017-05-26 |  | 2017-08-08
| 5899 | 2019-10-17 | RM Brown & Son Ltd | Inchdairnie | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Inchdairnie, Kinglassie Road, Glenrothes, Fife, Scotland | Fife | Scotland | Scotland | KY5 0UL | 324885 | 699061 | Fife Council | 15/03461/FULL | [5 empty] | 2015-10-28 | [6 empty] | 2016-07-15 |  |  |  | 2019-07-15 | 2017-01-01 | 2018-06-01
| 5900 | 2017-10-16 | Earthworm/ EW Capital | Celyn Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Celyn Farm Stryt-Cae-Rhedyn, Leeswood, Mold, Clwyd, Wales | Flintshire | Wales | Wales | CH7 4AG | 325713 | 360456 | Flintshire County Council | 054041 | [5 empty] | 2015-10-29 | [6 empty] | 2016-08-02
| 5902 | 2020-05-21 | Environmental Energy Investments | Berryhill Farm Solar Array | Solar Photovoltaics |  |  | 4.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Site To South Of Berryhill Far, Tak-ma-Doon Road, Kilsyth, Glasgow, Strathclyde, Scotland | North Lanarkshire | Scotland | Scotland | G65 0RY | 273164 | 679927 | North Lanarkshire Council | 15/02243/FUL | [5 empty] | 2015-10-21 | [6 empty] | 2016-07-13 |  |  |  | 2021-07-13
| 5903 | 2020-05-21 | Environmental Energy Investments | Glenhead Farm Lower Solar Array | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Glenhead Farm, High Banton Road, Kilsyth, Banton, Glasgow, Strathclyde, Scotland | North Lanarkshire | Scotland | Scotland | G65 0RB | 274229 | 678358 | North Lanarkshire Council | 15/02232/FUL | [5 empty] | 2015-10-21 | [6 empty] | 2016-07-06 |  |  |  | 2021-07-06
| 5904 | 2018-09-17 | Lark Energy | Solar Farm on land east of the A38, Willington | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land AT SK2828 6687, Burton Road, Egginton, Derby, Derbyshire, East Midlands | Derbyshire | East Midlands | England | DE65 6 | 428673 | 328890 | South Derbyshire District Council | 9/2015/0986 | [5 empty] | 2015-10-19 | [6 empty] | 2016-02-10 |  |  |  | 2019-02-10
| 5905 | 2017-05-02 | New Energy for the World | Land at Skelton Radio Transmitter Site | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at, Skelton Radio Transmitter Site, Skelton, Penrith, Cumbria, North West | Cumbria | North West | England | CA11 9SY | 343541 | 537078 | Eden District Council | 15/0907 | [5 empty] | 2015-10-23 | 2017-04-12
| 5906 | 2015-12-01 | New Energy for the World | Fountain Lot Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Fountain Lot Land At, Bentham, Bentham, Lancaster, Lancashire, North West | North Yorkshire | Yorkshire and Humber | England | LA2 7EY | 366904 | 471171 | Craven District Council | 08/2015/16260 | [5 empty] | 2015-10-21 |  | 2016-01-12
| 5909 | 2020-05-21 | Environmental Energy Investments | Glenhead Farm (Upper) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Glenhead Farm, High Banton Road, Kilsyth, Glasgow, Strathclyde, Scotland | North Lanarkshire | Scotland | Scotland | G65 0RB | 273746 | 680043 | North Lanarkshire Council | 15/02233/FUL | [5 empty] | 2015-10-21 | [6 empty] | 2016-07-06 |  |  |  | 2021-07-06
| 5910 | 2018-11-20 | Earthworm/ EW Capital | Land south of Ramsdale Park Golf Course | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land To The N/O Lime Lane and, Calverton Road, South Of Ramsdale Park Gol, Arnold, Nottingham, Nottinghamshire, East Midlands | Nottinghamshire | East Midlands | England | NG5 8FQ | 459055 | 348508 | Gedling Borough Council | 2015/0862 | [5 empty] | 2015-10-15 | [6 empty] | 2016-08-25 |  |  |  | 2019-08-25
| 5911 | 2019-10-23 | Stirling Council | Farm at Lower Polmaise | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | 485M South East of, Lower Polmaise Refuse Handling, Fallin, Stirling, Central, Scotland | Stirling | Scotland | Scotland | FK7 7LU | 283438 | 693163 | Stirling Council | 15/00492/FUL | [5 empty] | 2015-09-03 | [6 empty] | 2015-10-08 |  |  |  | 2018-10-08
| 5912 | 2017-06-01 | Renewable Energy Systems (RES) | Highlee Hill Wind Farm | Wind Onshore |  |  | 44.85 | n/a |  |  |  | 3.45 | 13 | 176 | n/a | Planning Application Withdrawn | Application Withdrawn | Land S/o Lustruther Farmhouse, (Highlee Hill), Hawick, Borders, Scotland | Scottish Borders | Scotland | Scotland | TD9 8TN | 361972 | 618210 | Scottish Borders Council | 16/00810/FUL | [5 empty] | 2016-07-01 | 2017-05-11
| 5913 | 2018-11-20 | Earthworm/ EW Capital | Lights Oaks Moss | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land At Light Oaks Moss Farm, Old Moss Lane, Glazebury, Warrington, Cheshire, North West | Greater Manchester | North West | England | WA3 5PY | 368359 | 396696 | Wigan Council | A/15/81182/MAJOR | [5 empty] | 2015-10-23 | [6 empty] | 2016-01-22 |  |  |  | 2019-01-22
| 5914 | 2020-04-24 | Innova / Lark Energy | Parkhill Solar Farm | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field 540M W Of Parkhill Farm, Letham Grange, Arbroath, Tayside, Scotland | Angus | Scotland | Scotland | DD11 5RG | 364125 | 745917 | Angus Council | 15/00973/FULL | [5 empty] | 2015-11-02 | [6 empty] | 2016-02-03 |  |  |  | 2019-02-03 | 2017-01-01 | 2018-11-01
| 5915 | 2016-01-06 | West Solent Solar Cooperative | Land South Of Carlton House | Solar Photovoltaics |  |  | 2.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land South Of Carlton House, Ringwood Road, Woodlands, Southampton | Hampshire | South East | England | SO40 7HT | 432494 | 112832 | New Forest National Park Authority | 15/00787 | [5 empty] | 2015-10-29 |  | 2015-12-23
| 5916 | 2018-10-02 | Gaelectric Developments | Monnaboy Wind Farm Ext. | Wind Onshore |  |  | 6 | n/a |  |  |  | 3 | 2 | 121.2 | n/a | Planning Application Withdrawn | Application Withdrawn | Monnaboy Wind Farm on land loc, 62 Monnaboy Road, Eglinton, Derry, Co Londonderry, Northern Ireland | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 3HP | 72948 | 577075 | Northern Ireland Planning Service | LA11/2015/0651/F | [5 empty] | 2015-10-23 | 2018-09-20
| 5917 | 2016-06-14 | Short Bros Homes | Dura Park Bynea Industrial Site | Solar Photovoltaics |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Former Bowdens Site, Yspitty Road, Dura Industrial Park, Llanelli, Dyfed, Wales | Carmarthenshire | Wales | Wales | SA14 9TD | 255583 | 198601 | Carmarthenshire County Council | S/32873 | [5 empty] | 2015-10-22 | [6 empty] | 2015-12-15 |  |  |  | 2018-12-15 | 2015-09-01 | 2015-12-21
| 5918 | 2016-01-06 | Mulbrick Cleans Energy | Lower House Farm | Solar Photovoltaics |  |  | 1.86 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land To The WeLower House Farm, Renacres Lane, Halsall, Ormskirk, Lancashire, North West | Lancashire | North West | England | L39 8S | 336341 | 412480 | West Lancashire Borough Council | 2015/0731/FUL | [5 empty] | 2015-07-13 |  | 2015-12-11
| 5922 | 2017-11-24 | S4N Worsted/Gamma Energy Exeter | Land adjacent to the former Coryton Refinery | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Petroplus Land Part Of Area, 418 Coryton Refinery, The Manorway, Stanford-Le-Hope, Essex, East of England | Essex | Eastern | England | SS17 9LG | 574132 | 183511 | Thurrock Council | 15/00877/FUL | [5 empty] | 2015-09-22 | [6 empty] | 2016-02-12 |  |  |  | 2019-02-12
| 5923 | 2018-11-20 | Earthworm/ EW Capital | Land at Borras Hall | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land T The West And North Of, Borras Hall Lane, Llan-y-Pwll, Wrexham, Clwyd, Wales | Wrexham | Wales | Wales | LL13 9 | 336822 | 353033 | Wrexham County Borough Council | P/2015/0777 | [5 empty] | 2015-10-28 | [6 empty] | 2016-03-11 |  |  |  | 2021-03-11
| 5925 | 2015-12-01 | WRS West Torrance | West Torrance Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 130 | n/a | Planning Application Withdrawn | Application Withdrawn | West Torrance Farm, Harthill | North Lanarkshire | Scotland | Scotland | ML7 5TT | 290738 | 665842 | North Lanarkshire Council | 11/00575/FUL | [5 empty] | 2011-05-20 | 2011-06-28
| 5926 | 2016-05-23 | South West Solar Parks (Brook Hall Farm SPV) | Brook Hall Farm (resubmission) | Solar Photovoltaics |  |  | 4.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | North Bradley, Trowbridge, Wiltshire | Wiltshire | South West | England | BA14 9PT | 385169 | 153475 | Wiltshire Council | 15/05656/FUL | [5 empty] | 2015-06-12 | [6 empty] | 2015-11-26 |  |  |  | 2018-11-26 | 2016-01-05 | 2016-03-21
| 5927 | 2020-03-26 | Fromby Lane Solar | Fromby Lane Solar Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Land To The Rear Of Old Waggoners Cottage, Formby Lane, Aughton | Lancashire | North West | England |  | 337973 | 406656 | West Lancashire Borough Council | 2015/0760/FUL | APP/P2365/W/16/3146746 |  |  |  |  | 2015-07-28 |  | 2015-10-09 | 2016-04-05 | 2016-04-22
| 5928 | 2017-12-01 | WEL Solar Park 11 | Land off Moss Side Lane (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land north of Moss Side Lane and south of the Railway, Ribby with Wrea, Preston | Lancashire | North West | England | PR4 2WP | 338818 | 431362 | Fylde Borough Council | 15/0530 | [5 empty] | 2015-08-06 | [6 empty] | 2015-11-17 |  |  |  | 2018-11-17 | 2017-01-31 | 2017-03-31
| 5929 | 2019-12-04 | TGC Renewables | Redmoor Farm (resubmission) | Solar Photovoltaics |  |  | 25.52 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Redmoor Farm, Skipwith Common Road, North Duffield, Selby | North Yorkshire | Yorkshire and Humber | England | YO8 5DE | 467529 | 438614 | Selby District Council | 2015/0967/FUL |  |  |  | 42350 |  | 2015-08-21 | [6 empty] | 2017-01-27 |  |  |  | 2020-01-27
| 5930 | 2017-03-24 | Solar Associates | Snettisham Solar Farm (resubmission) | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land North of Bircham Road, Snettisham | Norfolk | Eastern | England |  | 569953 | 334057 | King's Lynn and West Norfolk Borough Council | 15/01146/FM | [5 empty] | 2015-08-11 | [6 empty] | 2015-11-03 |  |  |  | 2018-11-03
| 5931 | 2015-12-01 | Tau Solar | Ravens Close (resubmission) | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land south of Ravens Close Brow, Low Bentham | North Yorkshire | Yorkshire and Humber | England |  | 364507 | 470846 | Craven District Council | 08/2015/15982 | [5 empty] | 2015-07-23 |  | 2015-10-28
| 5932 | 2015-12-01 | SBC Renewables | Johnson's Lane (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Johnson's Lane, Widnes | Cheshire | North West | England |  | 353580 | 385790 | Halton Borough Council | 15/00060/FUL | [5 empty] | 2015-01-29 | 2015-04-29
| 5933 | 2019-06-12 | SBC Renewables | Johnson's Lane (resubmission) - Halton | Solar Photovoltaics |  |  | 3.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Johnson's Lane, Widnes | Cheshire | North West | England |  | 353580 | 385790 | Halton Borough Council | 15/00332/FUL | [5 empty] | 2015-06-30 | [6 empty] | 2015-10-21 |  |  |  | 2018-10-21
| 5934 | 2019-06-12 | SBC Renewables | Johnson's Lane (resubmission) - Warrington | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Johnson's Lane, Widnes | Cheshire | North West | England |  | 353997 | 385705 | Warrington Borough Council | 2015/26105 | [5 empty] | 2015-06-30 | [6 empty] | 2016-02-05 |  |  |  | 2019-02-05
| 5935 | 2018-09-27 | Global Renewable Construction | Twin Oaks Farm | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Twin Oaks Yelt Lane, Doveridge | Derbyshire | East Midlands | England | DE6 5JW | 412616 | 333407 | Derbyshire Dales District Council | 15/00527/FUL | [5 empty] | 2015-07-23 | [6 empty] | 2015-10-14 |  |  |  | 2018-10-14
| 5936 | 2018-08-30 | BE Renewables | Back Lane Solar Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Withdrawn | Application Refused | Land To The West Of, Back Lane, Aughton, Ormskirk, Lancashire | Lancashire | North West | England | L39 6SX | 337955 | 405412 | West Lancashire Borough Council | 2015/0759/FUL | APP/P2365/W/16/3146719 |  |  |  |  | 2015-07-28 |  | 2015-10-09 | 2016-04-05 | 2016-05-24
| 5937 | 2015-12-01 | Mably Solar | Bunkers Hill (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Bunkers Hill, Townshend | Cornwall | South West | England |  | 158786 | 33384 | Cornwall Council | PA15/05327 | [5 empty] | 2015-06-10 |  | 2015-09-28
| 5938 | 2019-10-23 | Beacons Cross Solar (formerly Jemmys Carr Solar) | Jemmys Carr | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land At Jemmy Carr, Field North Of Downholland Brook, Moss Lane, Formby | Merseyside | North West | England | L37 0AL | 331997 | 408674 | Sefton Council | DC/2015/01266 | [5 empty] | 2015-08-03 | [6 empty] | 2016-09-23 |  |  |  | 2019-09-23 | 2019-09-23
| 5939 | 2019-12-04 | TGC Renewables/NESF | Land at Moss Farm (North) | Solar Photovoltaics |  |  | 6.02 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Moss Farm, Warmingham | Cheshire | North West | England | CW1 4PW | 369888 | 359234 | Cheshire East Council | 15/2113N | [5 empty] | 2015-05-08 | [6 empty] | 2016-05-20
| 5940 | 2016-07-01 | Sum Farming UK | Wiseburrow Farm (resubmission) | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Wiseburrow Farm, Greenham | Devon | South West | England | TA21 0JT | 307946 | 118283 | Mid Devon District Council | 15/01108/MFUL | APP/Y1138/W/15/3141503 |  |  |  |  | 2015-07-16 |  | 2015-12-04 | 2016-01-19 |  | 2016-06-09
| 5941 | 2015-12-01 | Suncredit UK | Carn Nicholas Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land At Carn Nicholas Farm, Bonymaen, Swansea | Swansea | Wales | Wales | SA1 7BL | 267843 | 194294 | City and County Council of Swansea | 2015/1646 | [5 empty] | 2015-08-07 | 2015-08-11
| 5942 | 2017-10-04 | BE Renewables/Barvills Solar Limited | Barvills Solar Farm (resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Barvills Farm, Princess Margaret Road, East Tilbury, Thurrock | Essex | Eastern | England | RM18 8PA | 568411 | 177573 | Thurrock Council | 15/00288/FUL | [5 empty] | 2015-03-19 | [6 empty] | 2015-08-07 |  |  |  | 2018-08-07 | 2017-01-29 | 2017-03-29
| 5943 | 2015-12-01 | Dow Corning | Barry Docks | Biomass (dedicated) |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land off Woodham Road, Barry | South Glamorgan | Wales | Wales |  | 312625 | 167514 | Vale of Glamorgan Council | 2010/00240/FUL | [5 empty] | 2010-03-10 | 2010-04-20
| 5944 | 2020-05-27 | First Renewable Developments | Bryant Field Solar Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Burton Wold | Northamptonshire | East Midlands | England |  | 491302 | 275499 | Kettering Borough Council | KET/2015/0440 | [5 empty] | 2015-06-01 | [6 empty] | 2015-07-30 |  |  |  | 2020-07-30
| 5945 | 2016-03-14 | GPV Rhynie | Cairnmore Solar Park (extension) | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cairnmore, Rhynie | Aberdeen | Scotland | Scotland | AB54 4NA | 350467 | 824466 | Aberdeenshire Council | APP/2015/1303 | [5 empty] | 2015-05-05 | [6 empty] | 2015-06-23 |  |  |  | 2018-06-22 | 2015-07-01 | 2015-09-15
| 5946 | 2017-12-15 | London Southend Airport Co. | London Southend Airport (resubmission) | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | London Southend Airport, Southend Airport, Southend-On-Sea | Essex | Eastern | England | SS2 6YF | 586759 | 189730 | Rochford District Council | 15/00190/FUL | [5 empty] | 2015-03-27 | [6 empty] | 2015-05-29 |  |  |  | 2018-05-29 | 2015-11-15 | 2016-01-12
| 5947 | 2015-12-17 | Gilkes Energy | Eas a Ghaill | Small Hydro |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Eas A Ghaill, Inverlochy, By Dalmally | Argyll and Bute | Scotland | Scotland |  | 219607 | 727417 | Argyll and Bute Council | 14/01709/PP | [5 empty] | 2014-07-24 | [6 empty] | 2014-09-19 |  |  |  | 2017-09-19 | 2014-11-01 | 2015-12-01
| 5948 | 2015-12-17 | Gilkes Energy | Eas a Ghaill | Small Hydro |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Eas A Ghaill, Inverlochy, By Dalmally | Argyll and Bute | Scotland | Scotland |  | 219607 | 727417 | Argyll and Bute Council | 13/01955/PP | [5 empty] | 2013-10-17 | [6 empty] | 2013-12-20 |  |  |  | 2013-12-20
| 5951 | 2018-08-20 | Earnside Energy | Binn Farm AD (extension) | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Teg Environmental, Binn Farm, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 9PX | 317439 | 713725 | Perth and Kinross Council | 15/02102/FLL | [5 empty] | 2015-12-07 | [6 empty] | 2016-01-27 |  |  |  | 2019-01-27 | 2016-02-15 | 2018-04-20
| 5952 | 2018-05-22 | BNRG Northern Power | Laurelhill | Solar Photovoltaics |  |  | 8.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands approx. 110m south east, 56 Moygannon Road, 31 Laurelhill Road, Donaghcloney, Craigavon | Co. Armagh | Northern Ireland | Northern Ireland | BT66 7PN | 123488 | 509151 | Northern Ireland Planning Service | LA08/2015/0381/F | [5 empty] | 2015-06-22 | [6 empty] | 2016-05-24 |  |  |  | 2021-05-23 | 2017-06-15 | 2018-03-01
| 5954 | 2018-10-30 | Powerquinn | Lower Tregeen Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Lower Tregeen Farm, Davidstow, Camelford | Cornwall | South West | England | PL32 9XU | 216459 | 88643 | Cornwall Council | PA15/11004 | [5 empty] | 2015-12-16 | [6 empty] | 2016-04-15 |  |  |  | 2019-04-15
| 5955 | 2017-12-04 | Greencoat Capital | Bann Road (Tullaghans Road) | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands surrounding 25 and 25(a), Tullaghans Road, Mullans 360m Southeast of 190, 430m South of 27 Tullaghans Ro, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland | BT44 9EA | 116129 | 576128 | Northern Ireland Planning Service | LA01/2015/1045/F | [5 empty] | 2015-12-14 | [6 empty] | 2016-08-04 |  |  |  | 2021-08-02 | 2016-12-12 | 2017-02-15
| 5956 | 2020-04-27 | J and LC Beattie Ltd | Brackenhills Farm (resubmission) | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 99.5 | n/a | Appeal Granted | Awaiting Construction | Land at Brackenhills Farm, Cornhill, Banff, Grampian | Aberdeen | Scotland | Scotland | AB45 2BD | 358303 | 859511 | Aberdeenshire Council | APP/2015/3800 | PPA-110-2313 |  |  |  |  | 2015-12-16 |  | 2016-06-16 | 2016-09-08 |  |  | 2016-12-06 | 2016-12-06
| 5957 | 2019-12-02 | Kelda Energy Services | Elvington Water Treatment Works | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Elvington Water Treatment Work, Kexby Lane, Elvington, York | North Yorkshire | Yorkshire and Humber | England | YO41 4BA | 470183 | 448177 | York City Council | 15/02639/FULM | [5 empty] | 2015-12-18 | [6 empty] | 2016-05-13 |  |  |  | 2019-05-13
| 5959 | 2020-04-22 | Industrial Property Investment Fund | Fort Industrial Park (Castle Bromwich) | Advanced Conversion Technologies |  |  | 10.2 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Fort Industrial Park, Dunlop Way, Castle Bromwich, Birmingham | West Midlands | West Midlands | England | B35 7R | 413581 | 290456 | Birmingham City Council | 2015/09679/PA | [5 empty] | 2015-12-10 | [6 empty] | 2016-06-24 |  |  |  | 2019-06-24
| 5960 | 2019-06-19 | Freelight (Shetland) | Culterfield Windfarm (resubmission) | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 | 67 | n/a | Planning Permission Granted | Awaiting Construction | Shelora, Cunningsburgh, Shetland | Shetland | Scotland | Scotland | ZE2 9HB | 442000 | 1129500 | Shetland Islands Council | 2015/425/PPF | [5 empty] | 2015-12-01 | [6 empty] | 2016-03-31 |  |  |  | 2021-03-30
| 5962 | 2019-12-11 | RWE Npower Renewables / Innogy | Glen Noe River | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Glen Noe Estate, Loch Etive, Taynuilt, Strathclyde | Argyll and Bute | Scotland | Scotland | PA35 1HU | 204878 | 734104 | Argyll and Bute Council | 15/03129/PP | [5 empty] | 2015-12-14 | [6 empty] | 2016-09-09 |  |  |  | 2019-09-09 | 2019-06-01
| 5963 | 2019-09-27 | E.ON UK | Land between Lorg Hill, Ewe Hill and Brown Hill | Wind Onshore |  |  | 32.4 | n/a |  |  |  | 3.3 | 9 | 149 | n/a | Planning Permission Granted | Awaiting Construction | Land between Ewe Hill, Brown Hill and Lorg Hill, Dumfries | Dumfries and Galloway | Scotland | Scotland | DG2 | 266135 | 600844 | Dumfries and Galloway Council | 15/P/2/0337 | [5 empty] | 2015-12-07 | [6 empty] | 2019-07-18 |  |  |  | 2024-07-18
| 5964 | 2016-01-04 | Storas Uibhist | Lochdar Hill Wind Farm | Wind Onshore |  |  | 6.9 | n/a |  |  |  | 2.3 | 3 | 99.5 | n/a | Planning Application Submitted | Application Submitted | Iochdar Hill Wind Farm, Lochcarnan, Lochboisdale | Comhairle nan Eilean Siar | Scotland | Scotland | HS8 5 | 81028 | 842424 | Comhairle nan Eilean Siar Council | 15/00515/PPW | [5 empty] | 2015-12-11
| 5965 | 2017-12-19 | Gilkes Energy | River Pattack (resubmission) | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Powerhouse Building On The, Shore Of Loch Laggan, Kinloch Laggan, Newtonmore | Highland | Scotland | Scotland | PH20 1B | 254876 | 783125 | Highland Council | 15/03858/FUL | [5 empty] | 2015-10-13 | [6 empty] | 2015-11-19 |  |  |  |  | 2016-01-15 | 2017-12-07
| 5967 | 2020-06-11 | Elgin Energy EsCo | Kells Solar Farm | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Lands Located Immediately NE, 11 at Bushtown Road, Extending Eastwards, 38 Kilmaconnell Road, Coleraine | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 3QP | 101980 | 586096 | Northern Ireland Planning Service | LA01/2015/0980/F | [5 empty] | 2015-11-27 | [6 empty] | 2016-05-31 |  |  |  | 2021-05-31
| 5968 | 2016-05-04 | GAG404 | Snetterton Heath AD | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land South-East of the A11, Chalk Lane, Former Airfield, Snetterton, Norwich | Norfolk | Eastern | England | NR16 2J | 600294 | 289735 | Breckland Council | 3PL/2015/1378/F | [5 empty] | 2015-12-04 | 2016-04-22
| 5969 | 2017-02-02 | Barclays Bank / Innogy (previously BELECTRIC Solar) | Galvin Road | Solar Photovoltaics |  |  | 1.6 | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | 672 Galvin Road, Slough | Berkshire | South East | England | SL1 4AN | 496075 | 180599 | Slough Borough Council | P/00348/008 | [5 empty] | 2015-04-24 | [6 empty] | 2015-07-06 |  |  |  | 2018-07-06
| 5971 | 2019-03-22 | AmeyCespa | Isle of Wight Waste Recovery Park | Advanced Conversion Technologies |  |  | 3.3 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Waste Fuels Plant, Forest Road, Newport | Isle of Wight | South East | England | PO30 5YS | 447130 | 89692 | Isle of Wight Council | P/01376/15 | [5 empty] | 2015-11-20 | [6 empty] | 2016-04-22 |  |  |  | 2019-04-22 | 2017-05-15
| 5974 | 2016-01-06 | Barley Brigg Biogas | Barley Brigg Farm | Anaerobic Digestion |  |  | 1.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Barley Brigg Farm, Laxfield Road, Stradbroke, Eye | Suffolk | Eastern | England | IP21 5NQ | 625353 | 273685 | Mid Suffolk District Council | PL\0279\15 | [5 empty] | 2015-10-29 |  | 2015-11-24
| 5977 | 2018-09-04 | Lightsource Renewable Energy | Gibson Farm | Solar Photovoltaics |  |  | 6.42 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Gibson Farm, Sealstown Road, Newtownabbey | Co. Antrim | Northern Ireland | Northern Ireland | BT36 4QU | 141191 | 538562 | Northern Ireland Planning Service | LA03/2015/0655/F | [5 empty] | 2015-12-04 | [6 empty] | 2016-07-26 |  |  |  | 2021-07-21 | 2017-12-11 | 2018-02-28
| 5980 | 2016-12-23 | Fordmouth Renewables | Fordmouth | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Hydrogen Plant, Carnwath Road, Carluke, Strathclyde | South Lanarkshire | Scotland | Scotland | ML8 4D | 298158 | 650900 | South Lanarkshire Council | CL/15/0455 | PPA-380-2072 |  |  |  |  | 2015-11-30 |  | 2016-06-21 | 2016-09-19 |  | 2016-12-23
| 5981 | 2016-07-01 | Cleator Solar Park | Cleator Solar Park | Solar Photovoltaics |  |  | 4.99 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Land between Woodend and Moor Row, Egremont | Cumbria | North West | England | CA22 2TA | 300923 | 512867 | Copeland Borough Council | 4/14/2336/0F1 | APP/Z0923/W/15/3138554 |  |  |  |  | 2014-08-01 |  | 2015-10-01 | 2015-12-14 |  | 2016-06-15
| 5982 | 2019-12-03 | Chinook Sciences | Bulwell Energy | Advanced Conversion Technologies |  |  | 29.5 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Former Blenheim Gardens Allotments, Blenheim Lane, Nottingham | Nottinghamshire | East Midlands | England | NG6 8UR | 452824 | 346221 | Nottingham City Council | 13/03051/PMFUL3 | [5 empty] | 2014-04-11 | [6 empty] | 2014-07-02 |  |  |  | 2017-07-02 | 2017-05-29
| 5983 | 2016-01-04 | Chinook Sciences | Bulwell Energy | Advanced Conversion Technologies |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Former Blenheim Gardens Allotments, Blenheim Lane, Nottingham | Nottinghamshire | East Midlands | England | NG6 8UR | 452824 | 346221 | Nottingham City Council | 13/00757/PMFUL3 | [5 empty] | 2013-05-14 | [6 empty] | 2013-06-25 |  |  |  | 2016-06-25
| 5984 | 2019-09-27 | Veolia | Fieldes Lock EfW (resubmission) | EfW Incineration |  |  | 33.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Secretary of State - Refusal | Application Refused | Rye House, Hoddesdon, Broxbourne | Hertfordshire | Eastern | England | EN11 0RF | 538944 | 209199 | Hertfordshire County Council | 7/0067-17 |  | APP/M1900/V/18/3195373 |  |  |  | 2017-01-18 |  | 2019-07-19 | [5 empty] | 2018-02-01 | 2019-07-19
| 5985 | 2016-02-05 | Sainsbury's | Thameside DC | Solar Photovoltaics |  |  | 1.028 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Depot 50, 50 Lombard Wall, Charlton, London |  | London | England | SE7 7SW | 540820 | 178999 | [20 empty] | 2016-01-15
| 5987 | 2020-02-04 | Good Energy | Warren Park Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Warren Park Farm, Ringwood Road, Alderholt | Dorset | South West | England | SP6 3DE | 411560 | 111172 | East Dorset District Council | 3/15/1020/FUL | [5 empty] | 2015-09-21 | [6 empty] | 2015-12-17 |  |  |  | 2018-12-17
| 5988 | 2017-11-23 | Canadian Solar | Royston Solar Farm (Phase 1) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land between Railway and Sewage Disposal Works, Royston Road, Melbourn, Cambridgeshire | Cambridgeshire | Eastern | England |  | 535667 | 242584 | South Cambridgeshire District Council | S/1427/14/FL | [5 empty] | 2014-07-01 | [6 empty] | 2014-10-29 |  |  |  | 2017-10-29
| 5989 | 2017-11-23 | Canadian Solar | Royston Solar Farm (Phase 2) | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land between Railway and Sewage Disposal Works, Royston Road, Melbourn, Cambridgeshire | Cambridgeshire | Eastern | England |  | 535667 | 242584 | South Cambridgeshire District Council | S/1427/14/FL | [5 empty] | 2014-07-01 | [6 empty] | 2014-10-29 |  |  |  | 2017-10-29
| 5992 | 2016-07-01 | Private Developer | Orton Park - Extension | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 | 86.5 | n/a | Appeal Refused | Application Refused | Road Leading From Sceughmire to Junction South of Orton Park, Great Orton | Cumbria | North West | England | CA5 6JU | 335742 | 552824 | Carlisle City Council | 15/0141 | APP/E0915/W/16/3141833 |  |  |  |  | 2015-03-04 |  | 2015-08-14 | 2016-01-26 |  | 2016-06-03
| 5995 | 2018-07-27 | Belfast Harbour Commissioners | Airport Road West | Anaerobic Digestion |  |  | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lands approximately 100 meters, 101b Airport Road West, Belfast | Co. Antrim | Northern Ireland | Northern Ireland | BT3 9ED | 150113 | 532543 | Antrim and Newtownabbey | LA04/2016/0057/F | [5 empty] | 2015-12-18 | [6 empty] | 2016-04-22 |  |  |  | 2021-04-21 | 2016-12-30 | 2017-03-30
| 5998 | 2020-04-22 | Sibor | Walworth Industrial Estate | Advanced Conversion Technologies |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Plot 37, Central Way, Walworth Business Park, Andover | Hampshire | South East | England | SP10 5AN | 438323 | 146697 | Hampshire County Council | 16/00058/CMAN | [5 empty] | 2016-01-05 | [6 empty] | 2016-06-16 |  |  |  | 2019-06-16
| 5999 | 2020-06-09 | Peel Environmental | North Clyde Recycling Centre (resubmission) | Anaerobic Digestion |  |  | 1.6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Rothesay Dock, Dock Street, Clydebank | Strathclyde | Scotland | Scotland | G81 1LX | 250389 | 669199 | West Dunbartonshire Council | DC15/251 | [5 empty] | 2015-11-18 | [6 empty] | 2016-10-27
| 6000 | 2017-04-20 | BioConstruct | Dean Group Business Park - Hartlepool | Anaerobic Digestion |  |  | 5.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land adjacent to Dean Group Business Park, Brenda Road, Frederick House, Hartlepool | Cleveland | North East | England | TS25 2BW | 451345 | 528361 | Hartlepool Borough Council | H/2015/0552 | [5 empty] | 2016-01-11 | [6 empty] | 2016-04-11 |  |  |  | 2019-04-11 | 2016-07-01 | 2017-01-09
| 6002 | 2017-10-04 | Gaelectric Renewable Energy | Monnaboy Road | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Lands South of, 62 Monnaboy Road, Eglinton, Derry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 3HP | 72992 | 577180 | Northern Ireland Planning Service | LA11/2016/0048/F | [5 empty] | 2016-01-04 | 2017-08-15
| 6004 | 2017-03-24 | WTE Developments | Massey Feeds | Biomass (dedicated) |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Mill Lane, Walton-le-Dale, Preston | Lancashire | North West | England | PR5 4JJ | 355843 | 427912 | South Ribble Borough Council | 07/2015/1855/FUL | [5 empty] | 2016-01-04 | [6 empty] | 2016-02-05 |  |  |  | 2019-02-05
| 6005 | 2020-05-28 | Boralex/Infinergy | Limekiln Wind Farm (resubmission) | Wind Onshore |  |  | 63 | n/a |  |  |  | 3 | 21 | 139 | n/a | Appeal Granted | Awaiting Construction | Limekilns Estate, Reay, Thurso | Highland | Scotland | Scotland |  | 298654 | 961356 | Scottish Government (S36) | EC00005269 | WIN-270-8 |  |  |  |  | 2016-06-15 |  |  | 2017-04-07 |  |  | 2019-06-21 | 2019-06-21
| 6007 | 2018-06-27 | Elgin Energy EsCo | Ballygarvey Road | Solar Photovoltaics |  |  | 13 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands at the N/o begin appro 3, 65 Ballygarvey Road, S/E 29 Ballygarvey Rd, S/o 42, 120m northeast of the M2 motor, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland | BT43 7HB | 127292 | 562641 | Antrim and Newtownabbey | LA02/2015/0756/F | [5 empty] | 2015-12-21 | [6 empty] | 2016-09-08 |  |  |  | 2021-09-08 | 2018-01-15 | 2018-04-25
| 6012 | 2016-02-05 | Elgin Energy EsCo | Kells Solar Farm (resubmission) | Solar Photovoltaics |  |  | 50 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Lands Extending NW And SE Of, Whappstown Road, Moorfields, Castlegore, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland | BT42 3DA | 133637 | 553991 | Northern Ireland Planning Service | LA03/2015/0234/F | [5 empty] | 2015-06-26
| 6013 | 2019-12-03 | Cenin Renewables | Parc Stormy, Stormy Down | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 | 125 | n/a | Under Construction | Under Construction | Land At Parc Stormy, Stormy Down, Pyle, Bridgend | Mid Glamorgan | Wales | Wales | CF33 4RS | 284119 | 180079 | Bridgend County Borough Council | P/15/868/FUL | [5 empty] | 2016-01-04 | [6 empty] | 2016-08-18 |  |  |  | 2021-08-18 | 2019-11-01
| 6015 | 2016-07-25 | Haymaker Energy | Kinmel 2 CIC | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land immediately north of A547, Rhuddlan Road, Towyn, Conwy | Gwynedd | Wales | Wales |  | 298420 | 377733 | Conwy County Borough Council | 0/40999 | [5 empty] | 2014-08-27 | [6 empty] | 2015-03-11 |  |  |  | 2020-03-11 | 2016-03-21 | 2016-06-27
| 6016 | 2016-06-21 | Volac | Felinfach | Biomass (dedicated) |  |  | 3.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Volac International Ltd, Felinfach, Lampeter | Ceredigion | Wales | Wales | SA48 8AF | 251860 | 257661 | Ceredigion County Council | A131001 | [5 empty] | 2014-01-22 | [6 empty] | 2014-05-29 |  |  |  | 2017-05-29 | 2015-03-15 | 2016-03-15
| 6017 | 2018-08-24 | UK Solar Assets (Pobail LS-SPV) | Fambridge Road/Canewdon Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land North East of Fambridge Road, Ulverston Road, Rochford | Essex | Eastern | England | SS4 3LD | 586831 | 194705 | Rochford District Council | 14/00649/FUL | [5 empty] | 2014-10-09 | [6 empty] | 2015-04-02 |  |  |  | 2018-04-02
| 6019 | 2017-04-20 | TGC Renewables | Moss Thorn Farm | Solar Photovoltaics |  |  | 5.76 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land near Moss Thorn Farm, Pallet Hill, Penrith | Cumbria | North West | England |  | 348608 | 530601 | Eden District Council | 15/0459 | APP/H0928/W/16/3143476 |  |  |  |  | 2015-05-29 |  | 2015-12-04 | 2016-02-25 |  |  | 2016-10-11 | 2016-10-11 |  |  |  |  | 2016-11-14 | 2017-02-27
| 6021 | 2016-05-06 | Private Developer | Govals Farm (Resubmission) | Wind Onshore |  |  | 4.8 | n/a |  |  |  | 0.8 | 6 | 86.5 | n/a | Planning Permission Refused | Application Refused | Land North West Of Govals Farm, Kincaldrum, Forfar, Tayside | Angus | Scotland | Scotland | DD8 1TX | 342944 | 743328 | Angus Council | 16/00055/EIAL | [5 empty] | 2016-02-01 |  | 2016-03-31
| 6022 | 2018-12-18 | Private Developer | Alton Muirhouse Farm | Wind Onshore |  |  | 6.8 | n/a |  |  |  | 3.4 | 2 | 130 | n/a | Appeal Refused | Application Refused | Land Turbines Alton Muirhouse, Newmilns | Strathclyde | Scotland | Scotland | KA16 9LJ | 250877 | 640340 | East Ayrshire Council | 15/0985/PP | PPA-190-2069 |  |  |  |  | 2015-12-22 |  | 2018-06-22 | 2018-09-21 |  | 2018-12-11
| 6023 | 2016-05-27 | Global Renewable Construction | Penniment House Farm/Water Lane Farm (Resubmission) | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land Off, Penniment Lane, Mansfield | Nottinghamshire | East Midlands | England | NG19 6PH | 451025 | 362333 | Mansfield District Council | 2016/0063/ST | [5 empty] | 2016-02-08 |  | 2016-05-09
| 6024 | 2020-06-11 | Elgin Energy Esco | Steeple Road | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Lands extending north and south, 58 Niblock Road, Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT41 2JQ | 129200 | 547323 | Northern Ireland Planning Service | LA03/2016/0135/F | 2016/A0240 |  |  |  |  | 2016-02-10 |  | 2016-12-15 | 2017-03-22 |  |  | 2018-05-24 | 2018-05-24 |  |  |  | 2021-05-24
| 6025 | 2017-06-29 | Plutus Energy | St Philips Marsh | Biomass (dedicated) |  |  | 20 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Avonbank, Feeder Road, Bristol, Avon, South West, | Bristol | South West | England | BS2 0TH | 360840 | 172197 | Bristol City Council | 16/00719/F | APP/Z0116/W/17/3167991 |  |  |  |  | 2016-02-10 |  | 2016-10-04 | 2017-03-24 |  | 2017-06-28
| 6028 | 2020-01-29 | Rolton Group | Keypoint Industrial Estate | Advanced Conversion Technologies |  |  | 14.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Land At Keypoint, Thornhill Road, South Marston, Swindon, Wiltshire | Wiltshire | South West | England | SN3 4RY | 418568 | 186806 | Swindon Borough Council | S/16/1055 | APP/U3935/W/18/3197964 |  |  |  |  | 2016-06-16 |  | 2017-09-15 | 2018-03-28 |  |  | 2019-06-06 | 2019-06-06
| 6033 | 2018-01-15 | Clean Earth Energy | Bodtegir | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 100 | n/a | Operational | Operational | Land at Bodtegir, part of the, Mwdwl Eithin, Nant Bach Wind Farm On Land At, Corwen | Clwyd | Wales | Wales | LL21 9AB | 299554 | 347741 | Conwy County Borough Council | 0/42466 | [5 empty] | 2016-02-12 | [6 empty] | 2016-04-20 |  |  |  | 2021-04-20 | 2017-06-21 | 2017-11-01
| 6034 | 2017-01-30 | United Utilities | Clifton Marsh Wwtw | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Clifton Marsh Wwtw, Preston New Road, Freckleton, Preston | Lancashire | North West | England | PR4 1HN | 345631 | 428457 | Lancashire County Council | LCC/2016/0007 | [5 empty] | 2016-01-22 |  | 2017-01-20
| 6035 | 2017-07-18 | Suncredit UK (Sunventures 7) | Caergarw Farm | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Caegarw Farm, Margam, Pyle, Bridgend | Mid Glamorgan | Wales | Wales | CF33 6PT | 282219 | 183728 | Neath Port Talbot County Borough Council | P2015/0692 | [5 empty] | 2015-11-23 | [6 empty] | 2016-05-17 |  |  |  | 2019-05-17 | 2016-12-20 | 2017-03-20
| 6036 | 2016-03-04 | E.ON Climate and Renewables UK | Lorg Windfarm | Wind Onshore |  |  | 49.5 | n/a |  |  |  | 3.3 | 15 | 130 | n/a | Planning Application Submitted | Application Submitted | Lorg Windfarm, Ayr | Strathclyde | Scotland | Scotland | KA6 | 263239 | 601647 | East Ayrshire Council | 15/0935/PP | [5 empty] | 2016-01-05
| 6040 | 2017-02-28 | J Haig Hamilton & Sons Ltd | Standalane near Ballencrieff | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land At Standalane, Near Ballencrieff, Longniddry | East Lothian | Scotland | Scotland | EH32 0PH | 348081 | 677289 | East Lothian Council | 16/00068/P | PPA-210-2057 |  |  |  |  | 2016-02-01 |  |  | 2016-06-27 |  | 2017-02-27
| 6042 | 2017-02-02 | Innogy (previously BELECTRIC Solar) | Rolls Royce Filton Campus Building 184 | Solar Photovoltaics |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Rolls Royce Filton Campus Buil, 184 Gloucester Road, Patchway, Bristol | Bristol | South West | England | BS34 6QA | 360460 | 180792 | South Gloucestershire Council | PT16/0435/F | [5 empty] | 2016-01-29 | [6 empty] | 2016-03-23 |  |  |  | 2019-03-23 | 2016-05-25 | 2016-08-15
| 6043 | 2017-02-02 | Innogy (previously BELECTRIC Solar) | Rolls Royce Filton Campus Building 185 | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Rolls Royce Filton Campus Buil, 184 Gloucester Road, Patchway, Bristol | Bristol | South West | England | BS34 6QA | 360460 | 180792 | South Gloucestershire Council | PT16/0447/F | [5 empty] | 2016-01-29 | [6 empty] | 2016-03-23 |  |  |  | 2019-03-23 | 2016-05-25 | 2016-08-15
| 6044 | 2016-11-01 | Lower Thura Renewables | Lower Thura | Wind Onshore |  |  | 4.6 | n/a |  |  |  | 2.3 | 2 | 92.5 | n/a | Planning Permission Refused | Application Refused | Lower Thura, Bower, Wick, Highlands, Scotland | Highland | Scotland | Scotland | KW1 4TP | 325234 | 962304 | Highland Council | 16/00268/FUL | [5 empty] | 2016-01-19 |  | 2016-10-06
| 6046 | 2016-05-27 | Ecotricity | Sparsholt College | Anaerobic Digestion |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Sparsholt College, Westley Lane, Sparsholt, Winchester | Hampshire | South East | England | SO21 2NF | 443094 | 132424 | Winchester City Council | 16/00116/FUL | [5 empty] | 2016-01-22 |  | 2016-05-06
| 6052 | 2016-03-04 | Honingham Thorpe Farm | Land to the west of Blind Lane | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Honingham Thorpe Farm, Norwich Road, Colton, Norwich | Norfolk | Eastern | England | NR9 5BZ | 611607 | 310520 | Broadland District Council | 20151560 | [5 empty] | 2015-09-30 |  | 2015-10-20
| 6053 | 2018-11-21 | Belvedere Energy Developments | Pant Cefn Farm | Solar Photovoltaics |  |  | 2.94 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Pantcefn Farm, Llanarth, Dyfed | Ceredigion | Wales | Wales | SA47 0RH | 243298 | 257835 | Ceredigion County Council | A150537 | [5 empty] | 2015-10-09 | [6 empty] | 2016-07-01 |  |  |  | 2021-07-01
| 6054 | 2017-10-31 | Thames Water Utilities | Basingstoke Sewage Treatment Works | Anaerobic Digestion |  |  | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Thames Water Utilities Ltd, Whitmarsh Lane, Sewage Disposal Works, Chineham, Basingstoke | Hampshire | South East | England | RG24 8LL | 467434 | 155168 | Basingstoke and Deane Borough Council | 15/03425/CMA | [5 empty] | 2015-09-29 | [6 empty] | 2015-12-21 |  |  |  | 2018-12-21 | 2016-02-16 | 2017-02-16
| 6055 | 2016-03-04 | Larimin | ParkerSteel Shoreham Plant | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Parker Steel Ltd, Fishgate Terminal, Basin Road South, Portslade | West Sussex | South East | England | BN41 1WF | 525794 | 104689 | Adur and Worthing Councils | [19 empty] | 2015-09-02
| 6057 | 2019-01-03 | Coriolis Energy/ ESB | Glendye Estate | Wind Onshore |  |  | 104 | n/a |  |  |  | 4 | 26 | 150 | n/a | Planning Application Submitted | Application Submitted | Glendye Estate, near Fettercairn, Aberdeenshire | Aberdeen | Scotland | Scotland |  | 364878 | 786267 | Scottish Government (S36) | ECU00000676 | [5 empty] | 2018-10-02
| 6059 | 2018-11-28 | Egnedol | Milford Haven/Blackbridge Biomass | Advanced Conversion Technologies |  |  | 49.9 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | The White House, Former Royal Navy Armaments Depot, Newton Road, Blackbridge, Milford Haven | Pembrokeshire | Wales | Wales | SA73 1DR | 191575 | 205212 | Welsh Government (NSIP) | DNS/3214296 | [5 empty] | 2016-12-22 |  | 2018-06-27
| 6061 | 2019-03-20 | Northern Energy Developments | Acharn Forest Killin Biomass Plant | Biomass (dedicated) |  |  | 5.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Acharn Forest, Killin, Stirling | Stirling | Scotland | Scotland | FK21 8RA | 256236 | 731409 | Loch Lomond and The Trossachs National Park Authority | 2014/0258/DET | [5 empty] | 2014-10-22 | [6 empty] | 2015-02-02 |  |  |  |  | 2017-01-15 | 2017-07-15
| 6062 | 2016-05-24 | Farm Power Apollo | Bourne Farm | Solar Photovoltaics |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Field B8 at Bourne Farm, adjacent to the Bourne Park Industrial Estates | Dorset | South West | England |  | 372234 | 97408 | West Dorset District Council | 1/D/13/001044 | [5 empty] | 2013-08-01 | [6 empty] | 2013-10-14 |  |  |  | 2016-10-14 | 2014-11-30 | 2015-03-15
| 6063 | 2016-07-28 | Lightsource Renewable Energy | London’s Queen Elizabeth II reservoir | Solar Photovoltaics |  |  | 6.3 | n/a |  |  |  | n/a | n/a | n/a | Floating | Operational | Operational | London’s Queen Elizabeth II reservoir, Walton-on Thames, Surrey | Surrey | South East | England | KT12 2YE | 517717 | 166986 | Elmbridge Borough Council | [18 empty] | 2016-02-15 | 2016-03-23
| 6064 | 2019-03-28 | Green Plan Energy/ Equitix | Land at Bryn Lane | Biomass (dedicated) |  |  | 5.4 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Bryn Lane, Wrexham Industrial Estate, Wreham | Wrexham | Wales | Wales | LL13 9UT | 338821 | 350498 | Wrexham County Borough Council | P/2010/0642 | [5 empty] | 2010-09-02 | [6 empty] | 2015-07-09 |  |  |  | 2020-07-09
| 6067 | 2016-09-01 | Elgar Middleton | Preston Lodge - Resubmission | Solar Photovoltaics |  |  | 4.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Land north east of Preston Deanery, Northamptonshire | Northamptonshire | East Midlands | England | NN7 2DS | 479687 | 256709 | South Northamptonshire Council | S/2016/0713/MAF | [5 empty] | 2016-03-09 |  | 2016-06-30
| 6069 | 2019-01-02 | Public Power Solutions | Barnfield Solar Park | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Landfill Site Galton Way Kendrick Industrial Estate Swindon | Wiltshire | South West | England | SN2 2YW | 413014 | 186119 | Swindon Borough Council | [6 empty] | 2016-08-26 | [6 empty] | 2016-10-25 |  |  |  |  | 2017-02-07 | 2018-12-10
| 6071 | 2020-05-21 | Countryside Renewables | Rhyd y Groes | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Llanbadrig, Cemaes Bay, Gwynedd | Isle of Anglesey | Wales | Wales | LL67 | 239215 | 392601 | Isle of Anglesey County Council | 20C310B/EIA/RE | [5 empty] | 2016-03-01 | [6 empty] | 2018-03-09 |  |  |  | 2023-03-09
| 6076 | 2019-09-24 | Van Elle | Former Langton Colliery Site | Solar Photovoltaics |  |  | 5.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Kirkby Lane, Pinxton, Nottingham | Nottinghamshire | East Midlands | England | NG16 6JA | 446935 | 355163 | Ashfield District Council | V/2016/0137 | [5 empty] | 2016-03-03 | [6 empty] | 2016-06-30 |  |  |  | 2019-06-30
| 6078 | 2017-03-31 | Billingham Valley Developments | Norton Bottoms | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land at Norton Bottoms, Fleet Bridge Road, Portrack Interchange Business, Stockton-On-Tees | County Durham | North East | England | TS18 2AD | 446152 | 521200 | Stockton on Tees Borough Council | 16/0431/OUT | [5 empty] | 2016-02-18 | 2017-02-28
| 6079 | 2018-09-20 | Infinite Renewables | West of Rhiwfelin Fach Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 116 | n/a | Operational | Operational | Land to the West of, Rhiwfelin Fach Farm, Llantrisant, Heol Sticil-Y-Beddau, Pontyclun | Mid Glamorgan | Wales | Wales | CF72 8LQ | 303640 | 185362 | Rhondda Cynon Taff County Borough Council | 16/0124/10 | [5 empty] | 2016-02-08 | [6 empty] | 2016-07-19 |  |  |  | 2019-07-19 | 2018-06-01 | 2018-08-31
| 6080 | 2016-09-01 | Scottish Enterprise/SSE | Hunterston Test Centre (Phase 2) | Wind Onshore |  |  | 8 | n/a |  |  |  | 8 | 1 | 220 | n/a | Planning Application Withdrawn | Application Withdrawn | Hunterston Construction Yard, Fairlie Largs, Largs | Strathclyde | Scotland | Scotland | KA30 9AG | 219008 | 652726 | North Ayrshire Council | 16/00060/PP | [5 empty] | 2016-01-28 | 2016-08-04
| 6081 | 2017-12-19 | AMP Holdings pic | Kingsnorth Industrial Estate | Anaerobic Digestion |  |  | 1.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Kingsnorth Industrial Estate, Kingsnorth Works, Hoo, St Werbrugh, Rochester | Kent | South East |  |  | 580868 | 172818 | Medway Council | MC/15/4424 | [5 empty] | 2015-12-18 | [6 empty] | 2016-04-04 |  |  |  | 2019-04-04
| 6082 | 2020-04-01 | University of St Andrews | Kenly Wind Farm (Resubmission) | Wind Onshore |  |  | 12.3 | n/a |  |  |  | 2.05 | 6 | 100 | n/a | Planning Permission Granted | Awaiting Construction | Kenly Farm, Boarhills, St. Andrews, Fife | Fife | Scotland | Scotland | KY16 8PW | 355244 | 713277 | Fife Council | 16/01425/EIA | [5 empty] | 2016-04-22 | [6 empty] | 2016-08-25 |  |  |  | 2019-08-25
| 6084 | 2016-04-13 | Active Renewables | Arail Farm Road | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land North of, Arail Farm Road, Abertillery | Blaenau Gwent | Wales | England | NP13 2ED | 321403 | 203178 | Blaenau Gwent County Borough Council | C/2015/0337 | [5 empty] | 2015-09-16 | 2015-12-17
| 6085 | 2016-05-04 | P-Fuel | Appley Bridge | Advanced Conversion Technologies |  |  | 4.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Appley Biomass To Energy Ltd D, Appley Lane North, Appley Bridge, West Quarry Railway Pad, Wigan, Greater Manchester | West Lancashire | North West | England | WN6 9AE | 351909 | 409621 | West Lancashire Borough Council | LCC/2015/0088 | [5 empty] | 2015-10-09 | 2016-01-18
| 6087 | 2018-07-19 | Solar 21 | Hull Biomass Plant (Tansterne power station) | Biomass (dedicated) |  |  | 22 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land at Tansterne Grange, Tansterne Lane, East Riding Of Yorkshire | Humberside | North East | England | HU11 4 RD | 522119 | 437456 | East Riding of Yorkshire Council | 15/03102/STREM | [5 empty] | 2015-10-08 | [6 empty] | 2016-02-05 |  |  |  |  | 2016-08-10 | 2018-02-15
| 6089 | 2016-08-25 | SIMEC Group | Uskmouth Power Station | Biomass (co-firing) |  |  | 18 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | West Nash Road, Nash, Newport, Gwent | Newport | Wales | Wales | NP18 2 BZ | 334280 | 183720 | DECC (S36) | [18 empty] | 2015-01-01 | 2015-03-01
| 6091 | 2016-04-06 | GIB and Equitix | Pulteney Distillery | Biomass (dedicated) |  |  | 3.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pultneytown Distillery, Huddart St, Wick, Highlands and Islands | Highland | Scotland | Scotland | KW1 5BA | 336714 | 950114 | Highland Council | 11/00235/FUL | [5 empty] | 2011-01-21 | [6 empty] | 2011-02-25 |  |  |  |  | 2011-04-25 | 2012-01-01
| 6093 | 2016-05-16 | Wessex Water | Trowbridge Sewage Treatment Works | Sewage Sludge Digestion |  |  | 1.16 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bradford Road, Trowbridge | Wiltshire | South West | England | BA14 9AX | 384894 | 158775 | Wiltshire Council | W/12/01818/WCM | [5 empty] | 2012-09-28 | [6 empty] | 2013-02-27 |  |  |  |  | 2015-10-19 | 2016-04-19
| 6096 | 2020-06-25 | Renewable Energy Systems (RES) | Glengesh Lower Forest (Murley) | Wind Onshore |  |  | 20.7 | n/a |  |  |  | 2.3 | 9 | 126.5 | n/a | Planning Permission Granted | Awaiting Construction | Murley Wind Farm, Townlands of Glengesh Lower Fo, Moysnaght Killygordon Tattanaf, Fivemiletown | Co. Tyrone | Northern Ireland | Northern Ireland | BT75 | 52824 | 515310 | Northern Ireland Planning Service | LA09/2015/0460/F | [5 empty] | 2015-10-13 | [6 empty] | 2018-05-08 |  |  |  | 2021-05-08
| 6097 | 2020-01-29 | Highwood Farm | Highwood Farm | Solar Photovoltaics |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Highwood Farm, Coventry Road, Brinklow, Rugby | Warwickshire | West Midlands | England | CV23 0NJ | 442119 | 279445 | Rugby Borough Council | R16/0174 | [5 empty] | 2016-04-14 | [6 empty] | 2016-06-07 |  |  |  | 2019-06-07
| 6099 | 2019-12-04 | Buccleuch Estate/ 2020 Renewables | Hopsrig Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 3.5 | 12 | 140 | n/a | Appeal Granted | Awaiting Construction | 7.5Km NW of Langholm, Westerkirk, Langholm | Dumfries and Galloway | Scotland | Scotland | DG13 0A | 327484 | 588675 | Dumfries and Galloway Council | 17/0415/FUL | PPA-170-2135 |  |  |  |  | 2017-03-02 |  | 2018-08-17 | 2018-11-14 |  |  | 2019-01-28 | 2019-01-28 |  |  |  | 2024-01-28
| 6102 | 2018-09-17 | Grangemouth Generation Ltd | Avondale Quarry (Pilot) | Advanced Conversion Technologies |  |  | 2 | no |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Avondale Quarry, Polmont, Falkirk, Central | Falkirk | Scotland | Scotland | FK2 0YG | 295367 | 678750 | Falkirk Council | P/16/0223/FUL | [5 empty] | 2016-04-12 | [6 empty] | 2016-06-08 |  |  |  | 2019-06-08 | 2016-04-01 | 2017-04-01
| 6104 | 2019-11-18 | Citrus Durham | Bowburn | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land South Of, Bowburn, Durham | County Durham | North East | England | DH6 5PE | 430430 | 537494 | Durham County Council | DM/15/03912/OUT | [5 empty] | 2015-12-23 | [6 empty] | 2017-02-15 |  |  |  | 2019-02-15
| 6105 | 2019-10-23 | Private Developer | Drumcairn Road | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Lands adjacent to and SE of, 61 Drumcairn Road, Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT61 8DQ | 96685 | 507087 | Northern Ireland Planning Service | LA08/2016/0388/F | [5 empty] | 2016-04-12 | [6 empty] | 2017-02-01 |  |  |  | 2020-02-01
| 6106 | 2016-08-18 | Green Cat Renewables | Marshill Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 119 | n/a | Operational | Operational | Farmland to the West of, Draffan Road, Draffanmarshill Farm, Lanark, Strathclyde | South Lanarkshire | Scotland | Scotland | ML11 9PW | 278551 | 645431 | South Lanarkshire Council | CL/12/0300 | [5 empty] | 2012-07-09 | [6 empty] | 2013-12-18 |  |  |  | 2019-06-17 | 2014-12-01 | 2015-08-01
| 6107 | 2020-04-22 | Rolton Kilbride | Former Templeborough Steel Works | Advanced Conversion Technologies |  |  | 23 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Former Templeborough Steel Works, Station Road, Templeborough, Rotherham | South Yorkshire | Yorkshire and Humber | England |  | 440517 | 391533 | Rotherham Metropolitan Borough Council | RB2016/0891 | [5 empty] | 2016-07-06 | [6 empty] | 2016-10-11
| 6108 | 2017-08-11 | North Tenement Solar Limited | Popehill Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of A4076(T), Popehill, Johnston, Haverfordwest, Dyfed | Pembrokeshire | Wales | Wales | SA62 3NX | 193972 | 212565 | Pembrokeshire County Council | 15/0443/PA | [5 empty] | 2015-10-08 | [6 empty] | 2016-05-18 |  |  |  | 2021-05-18 | 2017-01-29 | 2017-03-29
| 6109 | 2019-09-04 | Gap Waste Management | GAP House, Nest Road | Anaerobic Digestion |  |  |  | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | GAP House, Nest Road, Gateshead | Tyne and Wear | North East | England | NE10 0ES | 227901 | 562277 | Gateshead Metropolitan Borough Council | DC/16/00220/FUL | [5 empty] | 2016-02-26 | [6 empty] | 2016-09-13 |  |  |  | 2019-09-13
| 6113 | 2019-11-18 | Northern Energy Developments | Achnabreck | Advanced Conversion Technologies |  |  | 5.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Lochgair, Lochgilphead | Argyll and Bute | Scotland | Scotland | PA31 8SD | 192406 | 690450 | Argyll and Bute Council | 16/00885/PP | [5 empty] | 2016-04-14 | [6 empty] | 2016-05-25 |  |  |  | 2019-05-25
| 6114 | 2016-05-16 | Sainsbury's | Waltham Point Distribution Centre | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Fleming Road, Waltham Point | Essex | Eastern | England | EN9 3BZ | 537765 | 199723 | Epping Forest District Council | [18 empty] | 2016-01-05 | 2016-02-05
| 6115 | 2020-01-16 | Fortum Carlisle Limited and Kingmoor Park Properties | Kingmoor Park | Advanced Conversion Technologies |  |  | 22 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land to north of Kings Drive, Kingmoor Park Central, Carlisle, Cumbria | Cumbria | North West | England | CA6 4SE | 338085 | 559225 | Cumbria County Council | PL\1572\05 | [5 empty] | 2016-06-17 | [6 empty] | 2016-10-24
| 6116 | 2016-11-01 | Iota Solar (OPDE) | Catsfield Solar Farm (resubmission) | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Catsfield Road, Catsfield, Battle | East Sussex | South East | England | TN33 9BB | 571962 | 113200 | Rother District Council | RR/2015/1745/P | APP/U1430/W/16/3146975 |  |  |  |  | 2015-07-10 |  |  | 2016-04-08 |  | 2016-10-10
| 6119 | 2020-03-26 | E.ON UK | Bridge House, Muasdale, Tarbert, Strathclyde | Wind Onshore |  |  | 47.6 | n/a |  |  |  | 3.4 | 14 | 126.5 | n/a | Appeal Granted | Awaiting Construction | Bridge House, Muasdale, Tarbert, Strathclyde | Argyll and Bute | Scotland | Scotland | PA29 6XD | 172190 | 641550 | Argyll and Bute Council | 16/01313/PP | PPA-130-2064 |  |  |  |  | 2016-05-18 |  | 2017-09-21 | 2017-12-20 |  |  | 2019-12-18 | 2019-12-18 |  |  |  | 2024-12-18
| 6120 | 2019-12-03 | Checkley Wood Energy | Checkley Wood Farm | Wind Onshore |  |  | 3 | n/a |  |  |  | 3 | 1 | 149.8 | n/a | Planning Permission Granted | Awaiting Construction | Land off A5 at Checkley Wood F, Watling Street, Hockliffe, Leighton Buzzard, Bedfordshire | Bedfordshire | Eastern | England | LU7 9LG | 494144 | 229371 | Central Bedfordshire Council | CB/16/01389/FULL | [5 empty] | 2016-04-20 | [6 empty] | 2017-09-13 |  |  |  | 2022-09-13
| 6121 | 2017-12-19 | Gaelectric Developments | Altmore Road | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Pomeroy, Dungannon | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 | 78992 | 530866 | Mid Ulster | LA09/2015/1096/F | [5 empty] | 2015-11-18 | [6 empty] | 2016-05-05
| 6123 | 2019-05-01 | Yorkshire Water | Knostrop Sewage Treatment Works | Anaerobic Digestion |  |  | 4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Knostrop Treatment Works, Knowsthorpe Lane, Cross Green, Leeds, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | LS9 0PJ | 433623 | 431801 | Leeds City Council | 16/01946/FU | [5 empty] | 2016-05-02 | [6 empty] | 2016-09-06 |  |  |  | 2019-09-06 | 2016-10-01 | 2018-12-03
| 6129 | 2016-05-26 | Envantage Renewables | Knottingley B | Solar Photovoltaics |  |  | 2.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Middle Lane, England Lane, Knottingley, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF11 0BZ | 450120 | 423193 | Wakefield Council | 15/02492/FUL | [5 empty] | 2015-10-20 | [6 empty] | 2016-01-29 |  |  |  |  | 2016-03-15 | 2016-03-29
| 6130 | 2017-02-28 | TGC Renewables | Higher Humber Farm | Solar Photovoltaics |  |  | 5.89 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Refused | Application Refused | Humber Lane, Bishopsteignton, Devon | Devon | South West | England | TQ14 9TD | 288728 | 74835 | Teignbridge District Council | 14/03725/MAJ | APP/P1133/W/16/3148497 |  |  |  |  | 2015-01-06 |  | 2016-04-05 | 2016-05-12 |  | 2017-02-09
| 6131 | 2020-06-09 | This is Protos (Peel Environmental) | Plot 8 Protos/Ince Marshes (resubmission) | EfW Incineration |  |  | 35 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Plot 8 Protos, Grinsome Road, Ince, Ellesmere Port, Chester, Cheshire | Cheshire | North West | England | CH2 | 344998 | 376536 | Cheshire West and Chester Council | 16/03074/FUL | [5 empty] | 2016-07-18 | [6 empty] | 2017-09-07 |  |  |  | 2020-09-07
| 6132 | 2016-05-31 | London Borough of Hounslow | Western International Market | Solar Photovoltaics |  |  | 1.73 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Western International Market, Hayes Road, Southall, London | Greater London | London | England | UB2 5XU | 510606 | 178655 | Hounslow London Borough Council | P/2015/3360 | [5 empty] | 2015-07-28 | [6 empty] | 2015-09-14 |  |  |  |  | 2016-04-19 | 2016-05-19
| 6133 | 2018-07-05 | NESF (formerly Lark Energy) | Land East of Horton Road | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of Horton Road Brafield on the Green | Northamptonshire | East Midlands | England | NN7 1DN | 482438 | 257043 | South Northamptonshire Council | S/2014/2075/MAF | [5 empty] | 2014-10-20 | [6 empty] | 2015-05-01 |  |  |  |  | 2016-01-31 | 2017-07-07
| 6134 | 2017-12-21 | Stream Bioenergy | Tully Quarry | Anaerobic Digestion |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Tully Quarry, 116 Moorfields Road, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland | BT42 3HJ | 130509 | 557223 | Northern Ireland Planning Service | G/2013/0282/F | [5 empty] | 2013-07-31 | [6 empty] | 2013-12-17 |  |  |  |  | 2016-06-21 | 2017-07-01
| 6135 | 2019-12-17 | RWE | Harryburn Wind Farm | Wind Onshore |  |  | 67 | n/a |  |  |  | 3.6 | 16 | 150 | n/a | Appeal Refused | Application Refused | 1.3km east of Leadhills, Leadhills Road, Elvanfoot, 1km south-west of Crawford, Biggar, Strathclyde | South Lanarkshire | Scotland | Scotland | ML12 6TE | 291570 | 618905 | Scottish Government (S36) | EC00005277 | WIN-380-1 |  |  |  |  | 2017-05-17 |  |  | 2018-04-23 |  | 2019-09-27
| 6136 | 2020-06-18 | Kincardine Offshore Wind | Kincardine Offshore Windfarm | Wind Offshore |  |  | 50 | n/a |  |  |  | 6 | 8 | 176 | n/a | Under Construction | Under Construction | Kincardine Offshore Windfarm, Laurencekirk, Grampian | Offshore | Offshore | Scotland |  | 407766 | 789575 | Marine Scotland | APP/2016/1726 |  |  |  |  | Demo | 2016-06-16 | [6 empty] | 2017-03-07 |  |  |  |  | 2018-10-01
| 6137 | 2020-01-15 | FAB Energy | Hameldon Hill Wind Farm (extension 2) | Wind Onshore |  |  | 7.05 | n/a |  |  |  | 2.35 | 3 | 100 | n/a | Planning Permission Granted | Awaiting Construction | Land South Of New Barn, Billington Road, Hapton, Burnley, Lancashire | Lancashire | North West | England | BB11 5QQ | 381207 | 429690 | Burnley Borough Council | APP/2016/0263 | [5 empty] | 2016-06-13 | [6 empty] | 2017-07-28
| 6138 | 2018-02-01 | Glennon Brothers Troon | Harbour Road | Biomass (dedicated) |  |  | 2.55 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Harbour Road, Troon, Strathclyde | South Ayrshire | Scotland | Scotland | KA10 6DX | 230930 | 631425 | South Ayrshire Council | 16/00584/APP | [5 empty] | 2016-06-13 | [6 empty] | 2016-07-05 |  |  |  | 2019-07-05 | 2016-08-15 | 2017-03-18
| 6143 | 2016-06-30 | Renewable Energy Systems (RES) | Corlacky Hill Wind Farm | Wind Onshore |  |  | 36.3 | n/a |  |  |  | 3.3 | 11 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Corlacky Hill Wind Farm in the, townlands of Corlacky Knockon, Half Gayne and Tirkane near, Maghera | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT46 5NJ | 97245 | 566181 | Northern Ireland Planning Service | LA09/2016/0232/F | [5 empty] | 2016-05-19
| 6147 | 2019-09-16 | EnergieKontor UK | Pines Burn Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 | 145 | n/a | Appeal Granted | Awaiting Construction | Land South West of Lurgiescleuch, Hawick, Borders | Scottish Borders | Scotland | Scotland | TD9 9TW | 353795 | 606879 | Scottish Borders Council | 17/00010/FUL | PPA-140-2069 |  |  |  |  | 2017-01-11 |  | 2017-11-06 | 2017-12-22 |  |  | 2018-08-17 | 2018-08-17
| 6148 | 2019-12-05 | Wicks Farm (Biogas) | Land at Wicks Farm | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Wicks Farm, Ford Lane, Ford, Arundel, West Sussex | West Sussex | South East | England | BN18 0DG | 498997 | 104022 | West Sussex County Council | WSCC/026/16/F | [5 empty] | 2016-05-12 | [6 empty] | 2016-11-22
| 6152 | 2018-10-29 | Iona Capital | Crowland Street | Anaerobic Digestion |  |  | 1.6 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Southport Skip Hire, 55 Crowland Street, Southport, Merseyside | Merseyside | North West | England | PR9 7RX | 336678 | 416725 | Sefton Council | DC/2016/00534 | [5 empty] | 2016-03-17 | [6 empty] | 2016-10-04 |  |  |  | 2019-10-04
| 6154 | 2020-04-29 | Sperrin Environmental | Lands at Ballyutoag Road | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 88 | n/a | Planning Permission Granted | Awaiting Construction | Approx 430m North East of no, 60 Ballyutoag Road, Belfast, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT14 8SR | 141422 | 534979 | Northern Ireland Planning Service | LA03/2016/0214/F | [5 empty] | 2016-06-15 | [6 empty] | 2018-08-20 |  |  |  | 2023-08-20
| 6156 | 2018-11-16 | McLaughlin and Harvey | Michelin Tyres | Solar Photovoltaics |  |  |  | n/a |  |  |  | n/a | n/a | n/a | Roof | Abandoned | Abandoned | Michelin Tyres Plc, Baldovie Road, Dundee, Tayside | Dundee | Scotland | Scotland | DD4 8UQ | 345154 | 732713 | Dundee City Council | 16/00190/FULL | [5 empty] | 2016-02-05 | [6 empty] | 2016-03-31
| 6158 | 2020-03-23 | EDPR | Moray Firth 2 (West) | Wind Offshore |  |  | 850 | n/a |  |  |  | 10 | 85 | 230 | n/a | Planning Permission Granted | Awaiting Construction | Smith Bank, Moray Firth - 22.5 km off Lybster | Highland | Scotland | Scotland |  | 322637 | 909733 | Scottish Government (S36) | 18/03309/S35 | [5 empty] | 2018-07-15 | [6 empty] | 2019-06-14 |  |  |  | 2044-06-13
| 6159 | 2018-07-20 | Windflow UK | Navidale Estate | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 | 46.3 | n/a | Planning Permission Granted | Awaiting Construction | Land 1530M NE Of Caen Cottage Thorpe Helmsdale | Highland | Scotland | Scotland |  | 303250 | 918542 | Highland Council | 16/01959/FUL | [5 empty] | 2016-05-06 | [6 empty] | 2016-07-04 |  |  |  | 2019-07-04
| 6160 | 2019-12-03 | Cenin Renewables | Llwyncelyn Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 | 125 | n/a | Planning Permission Granted | Awaiting Construction | Nythbran House, Hafod Lane, Llwyncelyn, Porth, Mid Glamorgan | Rhondda Cynon Taff | Wales | Wales | CF39 9U | 303254 | 191696 | Rhondda Cynon Taff County Borough Council | 15/1635/10 | [5 empty] | 2015-12-23 | [6 empty] | 2017-11-24 |  |  |  | 2022-11-24
| 6161 | 2016-06-30 | Thames Water Utilities | Crossness Sewage Works | Sewage Sludge Digestion |  |  | 5.7 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Belvedere Road, London | Greater London | London | England | SE2 9AR | 548777 | 180312 | Bexley London Borough Council | 12/01114/FULM | [5 empty] | 2012-07-23 | [6 empty] | 2012-10-19 |  |  |  | 2015-10-19 | 2015-06-01 | 2016-06-30
| 6162 | 2016-06-30 | Aldi | Salford Road | Solar Photovoltaics |  |  | 1.6 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Salford Road, Bolton | Greater Manchester | North West | England | BL1 1BT | 371832 | 409339 | Bolton Metropolitan Borough Council | [18 empty] | 2016-06-01 | 2016-06-30
| 6163 | 2017-01-16 | Solar Century | Grove Solar Park (Phase 2) | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Grove Solar Park, Land west of A3057 (Romsey Road), Romsey | Hampshire | South East | England | SO51 9LH | 436685 | 118373 | Test Valley Borough Council | 14/01826/FULLS | APP/C1760/W/15/3010697 |  |  |  |  | 2014-07-31 |  | 2014-12-24 | 2015-04-23 |  |  | 2015-09-04 | 2015-09-04 |  |  |  | 2018-09-04 | 2016-01-18 | 2016-03-30
| 6164 | 2016-08-23 | SPEP | Barnsley 1.5 | Biomass (dedicated) |  |  | 9 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Whaley Road , Barugh Green , Barnsley | South Yorkshire | Yorkshire and Humber | England | S75 1HT | 432245 | 408040 | Barnsley Council | [18 empty] | 2015-09-01 | 2015-03-06
| 6165 | 2016-08-23 | SPEP | Spalding | Biomass (dedicated) |  |  | 14.5 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Clay Lane , Spalding Drove , Spalding | Lincolnshire | East Midlands | England | PE12 6BL | 525296 | 321104 | South Holland District Council | [18 empty] | 2015-02-01 | 2015-07-08
| 6166 | 2016-08-23 | SPEP | Balderton | Biomass (dedicated) |  |  | 20.3 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Quarry Farm, Bowbridge Lane, Balderton , Newark | Nottinghamshire | East Midlands | England | NG24 3BZ | 479824 | 350738 | Newark and Sherwood District Council | [18 empty] | 2015-02-01 | 2015-07-08
| 6167 | 2016-06-30 | Guy & Wright Ltd | The Nurseries, Green Tye | Anaerobic Digestion |  |  | 1.2 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | The Vineries , GreenTye , Much Hadham | Hertfordshire | Eastern | England | SG10 6JJ | 544192 | 218430 | East Hertfordshire District Council | [18 empty] | 2016-05-15 | 2016-06-15
| 6168 | 2018-08-21 | Octopus Investments | Cressing Solar Farm (Phase 2) | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land South Of Sheepcote Wood B, Witham Road, Cressing, Braintree, Essex | Essex | Eastern | England | CM77 8NZ | 579287 | 219000 | Braintree District Council | 15/00949/FUL | [5 empty] | 2015-07-24 | [6 empty] | 2015-11-12 |  |  |  | 2018-11-12
| 6169 | 2016-11-25 | Foresight Group (TGC Renewables) | Solar Farm at Fields Farm (Phase 2) | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land at Fields Farm, Southam | Warwickshire | West Midlands | England | CV47 2HD | 440365 | 260913 | Stratford on Avon District Council | 15/00767/FUL | [5 empty] | 2015-03-16 | [6 empty] | 2015-06-29 |  |  |  | 2018-06-29
| 6170 | 2020-01-24 | Wirsol | Outwood Farm (Phase 2) | Solar Photovoltaics |  |  | 7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Outwood Farm Road Billericay, Essex | Essex | Eastern | England |  | 569468 | 194288 | Basildon Borough Council | 14/00948/FULL | [5 empty] | 2014-08-07 | [6 empty] | 2014-12-11 |  |  |  | 2017-12-11
| 6171 | 2020-04-29 | MVV Environment | Baldovie Industrial Estate (Forties Road) | EfW Incineration |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land At Forties Road Baldovie Industrial Estate Dundee | Dundee | Scotland | Scotland | DD4 0NS | 344564 | 732870 | Dundee City Council | 16/00916/FULM | [5 empty] | 2016-12-22 | [6 empty] | 2017-03-21 |  |  |  | 2020-03-21 | 2018-11-16
| 6172 | 2016-07-28 | Solar Ventures | Williams Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Williams Farm, Maelor Gas Works, Marchwiel, Wrexham | Wrexham | Wales | Wales | LL13 0UW | 338309 | 348363 | Wrexham County Borough Council | P/2015/0463 | [5 empty] | 2015-06-26 | [6 empty] | 2015-12-21 |  |  |  |  | 2016-02-01 | 2016-03-31
| 6173 | 2016-07-28 | WhiteRock Energy | Woodlands Wind Farm | Wind Onshore |  |  | 2.55 | n/a |  |  |  | 0.85 | 3 | 69.9 | n/a | Operational | Operational | Woodlands Farm, Lesmahagow, Lanark | South Lanarkshire | Scotland | Scotland | ML11 0HQ | 279826 | 639404 | South Lanarkshire Council | CL/12/0139 | [5 empty] | 2012-03-22 | [6 empty] | 2013-07-22 |  |  |  |  | 2016-03-01 | 2016-07-28
| 6174 | 2016-07-28 | Ethical Power | Kirton Solar PV Farm | Solar Photovoltaics |  |  | 3.167 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land off Meeres Lane and adjacent to Pick's Barn, Kirton, Boston | Lincolnshire | East Midlands | England | PE20 1PR | 528032 | 338903 | Boston Borough Council | B/15/0001 | [5 empty] | 2014-11-28 | [6 empty] | 2015-05-07 |  |  |  |  | 2016-02-02 | 2016-03-30
| 6175 | 2020-06-30 | EnergieKontor (EKUK) | Over Hill Wind Farm | Wind Onshore |  |  | 33 | n/a |  |  |  | 3 | 11 | 149.9 | n/a | Planning Permission Granted | Awaiting Construction | Over Hill, New Cumnock, Cumnock, Strathclyde | East Ayrshire | Scotland | Scotland | KA18 4AA | 251694 | 611197 | East Ayrshire Council | 17/0395/PP | [5 empty] | 2017-05-26 | [6 empty] | 2020-05-07 |  |  |  | 2023-05-07
| 6176 | 2019-06-27 | Burcote Wind | Longburn Wind Farm | Wind Onshore |  |  | 23 | n/a |  |  |  | 2.3 | 10 | 134 | n/a | Appeal Refused | Application Refused | Carsphairn, 7.2km East of, Castle Douglas | Dumfries and Galloway | Scotland | Scotland | DG7 3SN | 256642 | 590350 | Dumfries and Galloway Council | 16/P/2/0187 | PPA-170-2129 |  |  |  |  | 2016-06-21 |  | 2017-09-13 | 2017-10-25 |  | 2019-05-14
| 6177 | 2019-06-28 | Renewable Energy Systems (RES) | Cairnmore Hill | Wind Onshore |  |  | 35 | n/a |  |  |  | 3.5 | 10 | 125 | n/a | Planning Application Submitted | Application Submitted | Land 1360M NW Of Hill Of Foss, Hopefield, Janetstown, Thurso | Highland | Scotland | Scotland | KW14 7XQ | 307973 | 967408 | Highland Council | 19/01172/PAN | [5 empty] | 2019-03-11
| 6178 | 2019-12-06 | SgurrEnergy | Sandwick North St Community wind turbine | Wind Onshore |  |  | 5 | n/a |  |  |  | 5 | 1 | 145 | n/a | Planning Permission Granted | Awaiting Construction | Point And Sandwick Power Beinn, Pentland Drive, Carloway, Isle Of Lewis, Western Isles | Comhairle nan Eilean Siar | Scotland | Scotland | HS2 9AX | 121228 | 941735 | Comhairle nan Eilean Siar Council | [6 empty] | 2017-01-20 | [6 empty] | 2019-11-05
| 6179 | 2020-04-22 | Rolton Kilbride | Hams Hall National Distribution Park | Advanced Conversion Technologies |  |  | 14.5 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Hams, Hams Hall Distribution Park, Faraday Avenue Coleshill, Birmingham | Warwickshire | West Midlands | England | B46 1AL | 420382 | 291541 | Warwickshire County Council | NWB/16CM011 | [5 empty] | 2016-06-07 | [6 empty] | 2017-02-16 |  |  |  | 2020-02-16
| 6180 | 2016-07-29 | Bury Green Farm Solar (Caledon Partners) | Bury Green Farm Solar | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | New Fen Road Lane, Ramsey | Cambridgeshire | Eastern | England |  | 526700 | 285350 | Huntingdonshire District Council | 15/00790/FUL | [5 empty] | 2015-05-18 | [6 empty] | 2015-09-25 |  |  |  |  | 2016-01-18 | 2016-03-15
| 6181 | 2016-07-29 | Novus | Misson Solar Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Bawtry Road, Misson | Nottinghamshire | East Midlands | England | DN10 6BU | 467776 | 394781 | Bassetlaw District Council | 15/00215/FUL | [5 empty] | 2015-02-18 | [6 empty] | 2015-10-27 |  |  |  |  | 2016-01-25 | 2016-03-24
| 6182 | 2016-07-29 | Thames Water Utilities | Beckton STW Enhanced Sludge Digestion | Sewage Sludge Digestion |  |  | 5.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Beckton STW, Jenkins Lane, East Ham | Greater London | London | England | IG11 0AD | 544385 | 182797 | Newham London Borough Council | 12/01573/FUL | [5 empty] | 2012-09-10 | [6 empty] | 2013-01-11 |  |  |  |  | 2014-06-15 | 2014-12-15
| 6183 | 2017-06-01 | Renewable Power Exchange | Stockton Court Farm (Resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Court Farm, Stockton Court, Stockton, Worcestershire, WR6 6UT | Hereford and Worcester | West Midlands | England | WR6 6UT | 371591 | 267221 | Malvern Hills District Council | 16/00678/FUL | [5 empty] | 2016-04-21 | 2017-05-25
| 6184 | 2017-08-24 | SIMEC/ Liberty House | Liberty Steel Power Station | Biomass (dedicated) |  |  | 9 |  |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Liberty Steel, Corporation Road, Newport | Newport | Wales | Wales | NP19 4XE | 333374 | 185135 | Newport City Council | 16/0096 | [5 empty] | 2016-02-01 | [6 empty] | 2016-03-03 |  |  |  |  | 2016-03-04 | 2017-01-15
| 6185 | 2018-07-18 | SIMEC | Uskmouth Power Station (ACT Plant) | Advanced Conversion Technologies |  |  | 8 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Uskmouth Power Station, West Nash Road, Nash, Newport | Newport | Wales | Wales | NP18 2BZ | 333031 | 183925 | Newport City Council | 16/0257 | [5 empty] | 2016-03-21 | [6 empty] | 2016-04-20
| 6186 | 2018-11-27 | Island Renewable Energy | Barony | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 2.3 | 4 | 126.5 | n/a | Appeal Refused | Application Refused | 89 Barony Road and Northstone Quarry at Barong Road, Alddrumman, Townland, Drumnakilly, Mountfield, Omagh | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 7QG | 71324 | 541529 | Northern Ireland Planning Service | LA10/2015/0283/F | 2017/A0050 |  |  |  |  | 2015-06-26 |  | 2017-05-19 | 2017-06-13 |  | 2018-10-10
| 6187 | 2020-05-26 | Gaelectric | Dunbeg Extension | Wind Onshore |  |  | 9 | n/a |  |  |  | 3 | 3 | 84 | n/a | Planning Permission Granted | Awaiting Construction | On lands directly North of A37/ Broad Road to the East of 156 Broad Road and to the West of the operational Dunbeg Windfarm in the townland of Dunbeg Limavady. | Co. Derry / Londonderry | Northern Ireland | Northern Ireland |  | 88740 | 587124 | Northern Ireland Planning Service | LA01/2016/0061/F | [5 empty] | 2015-12-22 | [6 empty] | 2017-04-27 |  |  |  | 2022-04-27
| 6188 | 2019-09-27 | Gaelectric | Tullyneil | Wind Onshore |  |  | 13.8 | n/a |  |  |  | 2.3 | 6 | 85 | n/a | Planning Application Withdrawn | Application Withdrawn | Land 80m south of junction of Chalybeate Road and Keady Road (A29) in the townland of Dangary and Tullyneill Newtownhamilton Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland |  | 99175 | 489139 | Northern Ireland Planning Service | O/2013/0190/F | [5 empty] | 2013-05-03 | 2019-08-23
| 6189 | 2018-11-19 | United Utilities | Lancaster Wastewater Treatment Works | Solar Photovoltaics |  |  | 1.243 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stodday Lane, Stodday, Lancaster, Lancashire | Lancashire | North West | England | LA2 0AG | 346555 | 458609 | Lancashire County Council | LCC/2016/0065 | [5 empty] | 2016-08-12 | [6 empty] | 2017-01-20 |  |  |  | 2022-01-20 | 2016-03-07 | 2016-04-07
| 6190 | 2017-07-28 | Stirling Council | Manor Powis | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Land Some 350 Metres South Of, Manor Steps, Manor Powis Road, Stirling, Central | Stirling | Scotland | Scotland | FK9 5QJ | 282664 | 695071 | Stirling Council | 16/00503/FUL | [5 empty] | 2016-07-29 | 2017-07-03
| 6193 | 2020-03-20 | Engie | CF Fertilizer site | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | CF Fertilisers UK Ltd, Grinsome Road, Ellesmere Por, Chester, Cheshire | Cheshire | North West | England | CH2 4LB | 347540 | 376597 | Cheshire West and Chester Council | 16/03310/FUL | [5 empty] | 2016-08-01 | [6 empty] | 2016-10-13 |  |  |  | 2019-10-13
| 6194 | 2019-12-17 | Green Cat Renewables | Navidale | Wind Onshore |  |  | 15 | n/a |  |  |  | 3 | 5 | 125 | n/a | Appeal Refused | Application Refused | Land NE of Church of Scotland, West Helmsdale, Helmsdale, Highlands | Highland | Scotland | Scotland | KW8 6HH | 303089 | 915952 | Highland Council | 17/02436/FUL | PPA-270-2212 |  |  |  |  | 2017-05-22 |  | 2019-03-11 | 2019-06-09 |  | 2019-10-23
| 6195 | 2019-01-03 | Hydroplan/Three Lochs Hydro | Gaineamhach Hydro Scheme Powerhouse | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land 3160M SW Of, Kerry Falls House, Gairloch, Highlands | Highland | Scotland | Scotland | IV21 2AH | 183896 | 869117 | Highland Council | 16/03353/FUL | [5 empty] | 2016-07-28 | 2018-06-11
| 6196 | 2016-10-04 | RWE Innogy | Conwy Falls | Large Hydro |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Afon Conwy, Betws-Y-Coed, Gwynedd | Gwynedd | Wales | Wales | LL24 0SH | 279800 | 354500 | Snowdonia National Park Authority | NP4/26/323A | [5 empty] | 2016-08-05 | 2016-09-28
| 6197 | 2016-12-22 | Tudor Griffiths Ltd | Wood Lane Quarry | Biomass (dedicated) |  |  | 5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Wood Lane Quarry, Wood Lane, Ellesmere, Shropshire | Shropshire | West Midlands | England | SY12 0HY | 342205 | 332562 | Shropshire Council | 16/03239/MAW | [5 empty] | 2016-07-20 | 2016-12-14
| 6198 | 2017-10-18 | Whitman Laboratories | Whitman Laboratories | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Whitman Laboratories Ltd, Bedford Road, Petersfield | Hampshire | South East | England | GU32 3DD | 473661 | 123479 | South Downs National Park Authority | SDNP/16/03016/FUL | [5 empty] | 2016-06-28 | [6 empty] | 2016-08-23 |  |  |  | 2019-08-23 | 2017-06-05 | 2017-10-18
| 6199 | 2019-09-25 | Veolia | Wapseys Wood | Anaerobic Digestion |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Wapseys Wood, Oxford Road, Gerrard's Cross, Buckinghamshire | Buckinghamshire | South East | England | SL9 8TE | 497450 | 188596 | Buckinghamshire County Council | CM/17/16 | APP/P0430/W/18/3204545 |  |  |  |  | 2016-05-06 |  | 2017-12-15 | 2018-06-29 |  | 2019-09-16
| 6204 | 2018-04-25 | Dahlman Renewable Technology | Former Huntsman Tioxide Site | Advanced Conversion Technologies |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Huntsman Tioxide Uk Ltd, Moody Lane, Grimsby | Humberside | Yorkshire and Humber | England | DN31 2SY | 525704 | 411176 | North East Lincolnshire Council | DM/0099/14/FUL | [5 empty] | 2014-02-17 | [6 empty] | 2014-05-14
| 6205 | 2016-08-31 | Lightsource BP | Binsted Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of Yapton Lane, Walberton | West Sussex | South East | England | DN31 2SY | 498258 | 104734 | Arun District Council | WA/34/15/PL | [5 empty] | 2015-07-06 | [6 empty] | 2015-09-28 |  |  |  |  | 2016-01-31 | 2016-03-31
| 6207 | 2020-04-02 | 2020 Renewables/ Forsa Energy | Gilston Hill Wind Farm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 | 126.6 | n/a | Appeal Granted | Awaiting Construction | Land North West Of Gilston Farm Heriot Scottish Borders | Scottish Borders | Scotland | Scotland |  | 344140 | 657352 | Scottish Borders Council | 17/00226/FUL | PPA-140-2068 |  |  |  |  | 2017-02-15 |  | 2017-02-01 | 2017-12-20 |  |  | 2019-02-07 | 2019-02-07 |  |  |  | 2022-02-07
| 6208 | 2020-03-31 | Muirhall Energy | Tormywheel Wind Farm Extension | Wind Onshore |  |  | 5 | n/a |  |  |  | 2.5 | 2 | 126.5 | n/a | Planning Permission Granted | Awaiting Construction | Tormywheel Wind Farm, Levenseath, Forth | West Lothian | Scotland | Scotland | ML11 8EP | 294590 | 657692 | West Lothian Council | LIVE/0226/FUL/17 | [5 empty] | 2017-03-30 | [6 empty] | 2020-03-06 |  |  |  | 2025-03-06
| 6209 | 2019-11-19 | Advanced Plasma Power | Tyseley Urban Resource Centre | Advanced Conversion Technologies |  |  | 6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 2 Hay Hall Road , Land to the rear of , Tyseley, Birmingham | West Midlands | West Midlands | England | B11 2AA | 411105 | 284152 | Birmingham City Council | 2013/07277/PA | [5 empty] | 2013-09-26 | [6 empty] | 2013-12-04
| 6210 | 2020-01-22 | O2N Energy (Billingham) LLP | Billingham Chemical Works | EfW Incineration |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Billingham Chemical Works, Haverton Hill Road, Billingham, Teesside | County Durham | North East | England |  | 447000 | 522000 | Stockton on Tees Borough Council | 10/1464/EIS | [5 empty] | 2010-06-04 | [6 empty] | 2010-09-03 |  |  |  | 2016-09-11
| 6212 | 2018-04-24 | Pengelly Farms | Pengelly Barton Farm | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Pengelly Barton Farm, Pengelly Cross, Breage, Helston, Cornwall | Cornwall | South West | England | TR13 9RG | 161464 | 32249 | Cornwall Council | PA16/08346 | [5 empty] | 2016-09-07 | [6 empty] | 2016-12-07 |  |  |  | 2019-12-07 | 2017-02-15 | 2017-05-15
| 6214 | 2018-10-29 | LE20 | Howpark Farm | Wind Onshore |  |  | 20 | n/a |  |  |  | 2.5 | 8 | 100 | n/a | Appeal Granted | Awaiting Construction | Land North of Howpark Farm, Grantshouse, Duns, Borders | Scottish Borders | Scotland | Scotland | TD11 3RP | 382529 | 667205 | Scottish Borders Council | 16/00980/FUL | PPA-140-2060 |  |  |  |  | 2016-08-23 |  | 2017-04-24 | 2017-07-19 |  |  | 2018-04-24 | 2018-04-24
| 6215 | 2019-12-10 | Levenseat | Levenseat Waste Management Facility | Advanced Conversion Technologies |  |  | 17 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Phase two, Levenseat, Forth, Lanark, Strathclyde | West Lothian | Scotland | Scotland | ML11 8EP | 293881 | 657597 | West Lothian Council | LIVE/0795/FUL/16 | [5 empty] | 2016-12-01 | [6 empty] | 2017-04-18 |  |  |  | 2022-04-18
| 6216 | 2019-11-27 | West Strathore Solar | West Grange Solar Farm (Resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land To The North Of, West Grange, West Grange Farm, Brankstone , Blairhall, Dunfermline, Fife | Fife | Scotland | Scotland | KY12 | 298345 | 689835 | Fife Council | 16/02840/FULL | [5 empty] | 2016-08-19 | [6 empty] | 2016-12-19 |  |  |  | 2019-12-19
| 6217 | 2020-03-23 | Bloomfield Recycling | Bloomfield Recycling Site | Biomass (dedicated) |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | William Gabriel Limited Compos, Cock Sparrow Lane, Cannock, Staffordshire | Staffordshire | West Midlands | England | WS12 4PB | 396604 | 312804 | Staffordshire County Council | SS.16/02/613 W | [5 empty] | 2016-07-20 | [6 empty] | 2016-11-24
| 6218 | 2020-03-23 | Bloomfield Recycling | Bloomfield Recycling Site | Anaerobic Digestion |  |  | 1.5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | William Gabriel Limited Compos, Cock Sparrow Lane, Cannock, Staffordshire | Staffordshire | West Midlands | England | WS12 4PB | 396604 | 312804 | Staffordshire County Council | SS.16/02/613 W | [5 empty] | 2016-07-20 | [6 empty] | 2016-11-24
| 6219 | 2017-05-05 | Viridis Wind Turbines | Hoddlesdon Moss (Resubmission) | Wind Onshore |  |  | 2.7 | n/a |  |  |  | 0.9 | 3 | 76.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Hoddlesden Moss, Roman Road, Hoddlesden, Darwen, Lancashire | Lancashire | North West | England | BB3 3PP | 372873 | 420534 | Blackburn with Darwen Borough Council | 10/16/0704 | [5 empty] | 2016-06-29 | 2017-04-25
| 6221 | 2020-03-31 | Herefordshire New Leaf Cooperative | Stretton Sugwas Solar Farm (Resubmission) | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Stretton Sugwas Closed Landfil, Roman Road, Land south of New Barnfields, off Roman Road, Stretton Sugwas | Hereford and Worcester | West Midlands | England | HR4 7AZ | 345887 | 242090 | Herefordshire Council | P162023/CD4 | [5 empty] | 2016-07-04 | 2020-02-27
| 6225 | 2016-10-04 | Teesside Bio Power/CoGen | Teesside Bio Power | Advanced Conversion Technologies |  |  | 28 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | North Tees Access Road, Port Clarence, Stockton on Tees, Middlesbrough | County Durham | North East | England | TS2 1FB | 451948 | 524549 | Stockton on Tees Borough Council | 16/1998/EIS | [5 empty] | 2016-08-01
| 6227 | 2018-07-19 | JG Pears Power | JG Pears' animal rendering facility | Biomass (dedicated) |  |  | 12 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | JG Pears (Newark) Ltd, Marnham Road, Low Marnham, Nottinghamshire, | Nottinghamshire | East Midlands | England | NG23 6SP | 480358 | 369197 | Bassetlaw District Council | 30/11/00005 | 13/00034/S36 |  |  |  |  | 2011-12-23 |  | 2013-04-12 |  |  |  |  | 2014-10-22 |  |  | 2014-10-22 |  | 2015-12-15 | 2018-04-15
| 6228 | 2018-09-01 | Newbridge Energy | Blazer Fuels | Biomass (dedicated) |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Blazers Fuels, Brickfield Lane, Off Denbigh Road, Ruthin, Denbighshire | Denbighshire | Wales | Wales | LL15 2TN | 311558 | 359049 | Denbighshire County Council | 02/2015/1095 | [5 empty] | 2015-11-02 | [6 empty] | 2015-12-22 |  |  |  |  | 2016-01-01 | 2017-03-31
| 6230 | 2016-10-31 | Renewable Source | Oakfield Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Oakfield Farm, Preston | Lancashire | North West | England |  | 346695 | 430917 | Fylde Borough Council | 14/0811 | [5 empty] | 2015-01-20 | [6 empty] | 2015-04-01 |  |  |  | 2018-04-01 | 2016-01-31 | 2016-03-31
| 6231 | 2016-10-05 | Renewable Source | Oakfield Farm - extension | Solar Photovoltaics |  |  | 1.73 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land East of Clifton Lane, Clifton | Lancashire | North West | England | PR4 0YH | 346934 | 430956 | Fylde Borough Council | 15/0679 | [5 empty] | 2015-10-02 | [6 empty] | 2015-12-14 |  |  |  | 2018-12-13 | 2016-02-28 | 2016-03-31
| 6232 | 2016-10-05 | Severn Trent Water | Minsworth Sewage Treatment Works | Sewage Sludge Digestion |  |  | 9.7 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Kingsbury Road, Minworth, Sutton Coldfield | West Midlands | West Midlands | England | B76 9DP | 416788 | 292692 | Birmingham City Council | 2013/06555/PA | [5 empty] | 2013-08-29 | [6 empty] | 2013-11-06 |  |  |  | 2016-11-06 | 2015-10-01 | 2016-04-01
| 6233 | 2016-10-10 | Allied Renewables | Stour Row Solar Farm | Solar Photovoltaics |  |  | 11.976 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Expired | Planning Permission Expired | Land At St (E) 382383 (N) 120456 Stour Row Shaftesbury Dorset | Dorset | South West | England | SP7 0QD | 382383 | 120456 | North Dorset District Council | 2/2011/0713/PLNG | [5 empty] | 2011-06-07 | [6 empty] | 2011-08-24 |  |  |  | 2014-08-23
| 6235 | 2017-10-04 | Green Cat Renewables | Hoy Farm | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 100 | n/a | Planning Permission Refused | Application Refused | Hoy Farm House, Castletown, Thurso | Highland | Scotland | Scotland | KW14 8TD | 321236 | 963110 | Highland Council | 16/04678/FUL | [5 empty] | 2016-10-14 |  | 2017-09-20
| 6244 | 2018-11-08 | West Sussex County Council | Former Westhampnett Landfill | Solar Photovoltaics |  |  | 7.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Former Westhampnett Landfill S, Coach Road, Westhampnett, Chichester | West Sussex | South East | England | PO19 7RT | 488572 | 106074 | West Sussex County Council | WSCC/057/16/WH | [5 empty] | 2016-09-30 | [6 empty] | 2017-01-10 |  |  |  |  | 2017-07-15 | 2018-10-25
| 6246 | 2019-01-28 | Bentley Motors | Bentley Motors | Solar Photovoltaics |  |  | 2.9 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Bentley Motors Ltd, Pyms Lane, Crewe | Cheshire | North West | England | CW1 3PL | 368482 | 356627 | Cheshire East Council | 16/4268N | [5 empty] | 2016-08-31 | [6 empty] | 2016-11-24 |  |  |  |  | 2018-03-21 | 2018-08-01
| 6247 | 2016-12-23 | Energy Circle | South Beach Parade/South Denes Rd | Biomass (dedicated) |  |  | 5.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | South Beach Parade, And South Denes Rd Adj, Outer Harbour, Great Yarmouth | Norfolk | Eastern | England | NR30 3EH | 653136 | 306190 | Great Yarmouth Borough Council | 06/16/0379/LDO | [5 empty] | 2016-06-17 | 2016-12-22
| 6248 | 2019-11-18 | Solafields/Ingham Renewables | Ingham North Solar (Resubmission) | Solar Photovoltaics |  |  | 14.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land north west of Ingham, The Street, Ingham, Bury St. Edmunds | Suffolk | Eastern | England | IP31 1NR | 584861 | 272449 | St Edmundsbury Borough Council | DC/16/2140/FUL | [5 empty] | 2016-09-26 | [6 empty] | 2017-03-24 |  |  |  | 2020-03-24
| 6249 | 2016-11-30 | 1 Stop Renewables/King Edward Community Services | Cairnandrew Wind Farm (Resubmission) | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.5 | 3 | 77 | n/a | Planning Permission Refused | Application Refused | Land 500 meters East/South-East of Cairnandrew, Longmanhill, King Edward | Aberdeen | Scotland | Scotland | AB45 3SR | 375155 | 860228 | Aberdeenshire Council | APP/2016/1848 | PPA-110-2312 |  |  |  |  | 2016-06-27 |  | 2016-06-28 | 2016-09-03 | 2016-06-28
| 6257 | 2019-09-09 | Bridgwater Resource Recovery | Showground Road | EfW Incineration |  |  | 7.75 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land at Showground Road, Bridgwater | Somerset | South West | England | TA6 6AJ | 330970 | 135064 | Somerset County Council | 1/37/15/093 | [5 empty] | 2014-07-17 | [6 empty] | 2015-04-24 |  |  |  | 2017-12-31 | 2019-07-15
| 6258 | 2020-01-17 | Private Developer | Hangmans Lane | EfW Incineration |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Hangmans Lane, Hanley Castle | Hereford and Worcester | West Midlands | England | WR8 0AJ | 383167 | 244019 | Worcestershire County Council | 15/000025/CL | APP/E1855/X/16/3147848 |  |  |  |  | 2015-07-13 |  | 2015-12-22 | 2016-05-13 |  |  | 2016-10-11 | 2016-10-11 |  |  |  |  | 2019-02-01
| 6259 | 2018-07-05 | ESB Asset Development UK | Craigneil Hill | Wind Onshore |  |  | 37.95 | n/a |  |  |  | 3.45 | 11 | 135 | n/a | Planning Application Submitted | Application Submitted | Land To The North And North East Of Hillside, Rickarton, Stonehaven | Aberdeen | Scotland | Scotland | AB39 3TA | 380100 | 791000 | Aberdeenshire Council | APP/2018/0993 | [5 empty] | 2018-05-01
| 6260 | 2019-08-13 | Green Energy North East | Bowesfield Ind Est | EfW Incineration |  |  | 2.6 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 2/3, Bowesfield Crescent, Stockton-On-Tees, Cleveland | County Durham | North East | England | TS18 3BL | 444589 | 517257 | Stockton on Tees Borough Council | 16/2461/COU | [5 empty] | 2016-11-14 | [6 empty] | 2017-02-21 |  |  |  | 2020-02-21
| 6261 | 2017-02-01 | Dobies Cumbria | Dobies Business Park | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.4 | 4 | 48 | n/a | Planning Application Withdrawn | Application Withdrawn | Dobies Business Park, Lillyhall, Workington | Cumbria | North West | England | CA14 4HX | 301552 | 524811 | Allerdale Borough Council | 2/2016/0715 | [5 empty] | 2016-11-05 | 2017-01-24
| 6264 | 2019-12-06 | Hexicon AB/ Dounreay Tri | Dounreay Trì Floating Wind Demonstration | Wind Offshore |  |  | 10 | n/a |  |  |  | 5 | 2 | 201 | n/a | Under Construction | Under Construction | Development Site 9KM NW Of, Dounreay, Nuclear Research Establishment, Thurso | Highland | Scotland | Scotland | KW14 7TY | 291337 | 980477 | Marine Scotland | 16/04775/S36 | [5 empty] | 2016-10-17 | [6 empty] | 2017-03-16 |  |  |  |  | 2017-03-31
| 6266 | 2019-10-02 | E.ON UK | Golticlay Wind Farm | Wind Onshore |  |  | 64.6 | n/a |  |  |  | 3.4 | 19 | 130 | n/a | Appeal Lodged | Application Submitted | Land 2040M NE Of Bulreanrob, Lybster | Highland | Scotland | Scotland | KW3 6BY | 322334 | 940553 | Scottish Government (S36) | EC00003133 | WIN-270-10 |  |  |  |  | 2016-10-28 |  |  | 2017-10-30
| 6267 | 2019-12-10 | Sweco | Sutton Heath Road | EfW Incineration |  |  | 15 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Green Gate Works, Sherdley Road, Sutton Health Road, St. Helens | Merseyside | North West | England | WA9 5DZ | 350972 | 394247 | St Helens Council | P/2016/0804/FUL | [5 empty] | 2016-11-09 | [6 empty] | 2017-03-31 |  |  |  | 2020-03-31
| 6270 | 2017-02-01 | AT Plant & Contracting | Slip Inn Quarry | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Slip Inn Quarry, Leicester Road, Lutterworth | Leicestershire | East Midlands | England | LE17 4LT | 454313 | 287877 | Leicestershire County Council | 2016/CM/0234/LCC | [5 empty] | 2016-10-18 | 2017-01-09
| 6271 | 2018-04-25 | Endless Energy/Halton Homes | Former Gas Works site on Aire Valley Road | EfW Incineration |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Former Gas Works Site, Airedale Road, Keighley | West Yorkshire | Yorkshire and Humber | England | BD21 4LW | 407528 | 441612 | Bradford Metropolitan District Council | 13/04217/FUL | [5 empty] | 2013-10-13 | [6 empty] | 2014-04-16 |  |  |  | 2017-04-16
| 6274 | 2016-11-30 | Rocpower | Loicher Lane | Biomass (dedicated) |  |  | 8 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Loicher Lane, Ecclesfield, Sheffield | South Yorkshire | Yorkshire and Humber | England | S35 9XN | 436474 | 394306 | Sheffield City Council | 09/02979/FUL | [5 empty] | 2009-09-22 | [6 empty] | 2011-05-26 |  |  |  |  | 2014-05-26 | 2016-03-21
| 6275 | 2020-04-02 | Fred Olsen Renewables | Rothes Wind Farm III | Wind Onshore |  |  | 150 | n/a |  |  |  | 5 | 29 | 225 | n/a | Planning Application Submitted | Application Submitted | Land near Rothes village, Moray | Moray | Scotland | Scotland |  | 321000 | 848000 | Scottish Government (S36) | ECU00000474 | [5 empty] | 2019-02-01
| 6277 | 2020-04-29 | Kingspan Insulation | Kingspan Insulation | Advanced Conversion Technologies |  |  | 48 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Kingspan Insulation Ltd, Enterprise Way, Sherburn in Elmet, Leeds, West Yorkshire | North Yorkshire | Yorkshire and Humber | England | LS25 6NA | 451184 | 433466 | Selby District Council | 2016/1456/EIA | [5 empty] | 2016-12-09 | [6 empty] | 2017-06-23 |  |  |  | 2020-06-23
| 6279 | 2020-01-28 | Port of Tyne Authority | Howdon Green Energy Park | Advanced Conversion Technologies |  |  | 25 | No |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Howdon Yard, Tyne View Terrace, Willington Quay, Wallsend | Tyne and Wear | North East | England | NE28 6UL | 433241 | 566182 | North Tyneside Council | 16/01922/FUL | [5 empty] | 2016-12-01 | [6 empty] | 2017-04-21 |  |  |  | 2020-04-21
| 6280 | 2018-09-01 | Connective Energy Holdings | Gortahurk Road | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 11 Gortahurk Road, Derrylin, Tonymore, Enniskillen | Co. Fermanagh | Northern Ireland | Northern Ireland | BT92 9DD | 39019 | 494600 | Northern Ireland Planning Service | LA10/2016/1232/F | [5 empty] | 2016-12-01 | [6 empty] | 2017-03-16 |  |  |  | 2022-03-16 | 2017-03-30 | 2018-03-30
| 6282 | 2020-06-04 | Anesco | Bumpers Farm Phase 2 | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land North Of Bumpers Farm, Ilmer Lane, Ilmer, Buckinghamshire | Buckinghamshire | South East | England | HP17 8 | 476290 | 206089 | Aylesbury Vale District Council | 14/01926/APP | APP/K0425/W/14/3001711 |  |  |  |  | 2014-07-11 |  | 2014-09-05 | 2015-02-04 |  |  | 2015-10-26 | 2015-10-26
| 6284 | 2020-01-02 | Renewable Energy Systems (RES) | Killean | Wind Onshore |  |  | 56 | n/a |  |  |  | 3.29 | 17 | 149.9 | n/a | Appeal Refused | Application Refused | Killean Estate approximately 2.5 kilometres (km) east of Tayinloan | Argyll and Bute | Scotland | Scotland |  | 172668 | 644646 | Scottish Government (S36) | EC00005266 | WIN-130-3 |  |  |  |  | 2016-12-09 |  | 2019-12-18 | 2017-12-20 |  | 2019-12-18
| 6287 | 2020-01-29 | Clean Power Properties | Willowbrook Industrial Estate East (Resubmission) | Advanced Conversion Technologies |  |  | 16.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Willowbrook East Industrial Estate, Shelton Road, Corby, Northamptonshire | Northamptonshire | East Midlands | England | NN17 5XH | 490943 | 290854 | Northamptonshire County Council | 16/00028/WASFUL | [5 empty] | 2016-06-28 | [6 empty] | 2016-09-21
| 6290 | 2017-03-29 | Energy Circle/RWE | South Denes Road | Advanced Conversion Technologies |  |  | 6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | RWE Power Station (Land within, South Denes Road, Great Yarmouth, Norfolk | Norfolk | Eastern | England | NR30 3 | 652900 | 304947 | Great Yarmouth Borough Council | 06/17/0041/LDO | [5 empty] | 2017-01-24 | 2017-03-21
| 6291 | 2018-06-28 | Fauch Hill Sustainable Energy | Fauch Hill | Wind Onshore |  |  | 48 | n/a |  |  |  | 4 | 12 | 125 | n/a | Appeal Refused | Application Refused | Fauch Hill, West Colzium, Crosswoodburn, West Calder, Lothian | West Lothian | Scotland | Scotland | EH55 8LR | 306275 | 657586 | West Lothian Council | LIVE/0235/FUL/17 | PPA-400-2084 |  |  |  |  | 2017-04-03 |  | 2017-12-20 | 2018-03-16 |  | 2018-06-13
| 6292 | 2020-01-24 | ESB Solar NI | Curryfree Wind Farm (co-location) | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Townland of Curryfree Co Londo, Curryfree Road, Creevedonnell Co. Londonderry, Taboe Glebe Co Tyrone, Derry, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 3 | 59555 | 572350 | Northern Ireland Planning Service | LA11/2017/0086/F | [5 empty] | 2017-01-24 | [6 empty] | 2018-11-21 |  |  |  | 2023-11-21
| 6293 | 2019-05-23 | Clean Earth Energy | Accolade Wines | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 1.5 | 1 | 130 | n/a | Operational | Operational | Accolade Wines, Kings Weston Lane, Avonmouth, Bristol, Avon | Avon | South West | England | BS11 9FG | 352283 | 180011 | Bristol City Council | 17/02240/F | [5 empty] | 2017-04-21 | [6 empty] | 2017-09-01 |  |  |  | 2020-09-01 | 2019-02-01 | 2019-06-15
| 6294 | 2019-09-24 | K3 CHP/Wheelabrator | Kemsley Mill | EfW Incineration |  |  | 75 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Wheelabrator Kemsley Mill, Ridham Avenue, Kemsley, Sittingbourne | Kent | South East | England | ME10 2S | 592144 | 166704 | The Planning Inspectorate - National Infrastructure | EN010083 | [5 empty] | 2019-09-11
| 6299 | 2020-06-29 | Vattenfall | Thanet (extension) | Wind Offshore |  |  | 340 | n/a |  |  |  | 10 | 34 | 210 | n/a | Planning Permission Refused | Application Refused | Thanet offshore windfarm, Dover, Kent | Offshore | Offshore | England | CT15 | 649878 | 175192 | DECC (S36) | [6 empty] | 2018-06-27 |  | 2020-06-01
| 6301 | 2018-01-30 | Clean Earth | Cwmbargoed Disposal Point | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 126 | n/a | Appeal Refused | Application Refused | Cwmbargoed Disposal Point, Fochriw Road, Cwmbargoed, Merthyr Tydfil, Mid Glamorgan | Merthyr Tydfil | Wales | Wales | CF48 4AE | 308888 | 206171 | Merthyr Tydfil County Borough Council | P/17/0004 | APP/U6925/A/17/3176287 |  |  |  |  | 2017-01-09 |  | 2017-03-20 | 2017-09-27 |  | 2018-01-10
| 6304 | 2017-07-27 | Britania Crest Recycling | Former Wealden Brickworks Site | EfW Incineration |  |  | 21 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Former Wealden Brickworks (Site HB), Langhurstwood Road, Horsham, West Sussex | West Sussex | South East | England | RH12 4QD | 517058 | 134349 | West Sussex County Council | WSCC/062/16/NH | [5 empty] | 2016-12-15 | 2017-07-11
| 6310 | 2020-04-03 | Verus Energy Oak | Giffords Recycling/Kelvin Energy Recovery Facility | EfW Incineration |  |  | 35 | No |  |  |  | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Giffords Recycling, Kelvin Way, West Bromwich, West Midlands | West Midlands | West Midlands | England | B70 7JR | 400272 | 289946 | Sandwell Metropolitan Borough Council | DC/17/61177 | [5 empty] | 2017-10-20 |  | 2018-06-13 | 2019-06-10 |  |  | 2019-09-27 | 2019-09-27
| 6312 | 2020-04-22 | ABO Wind UK | Hartwood Windfarm | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 | 126.5 | n/a | Appeal Granted | Awaiting Construction | Land At Murdostoun Forrest & Home Farm, Hartwood, Shotts | North Lanarkshire | Scotland | Scotland | ML7 4JY | 284792 | 659236 | North Lanarkshire Council | 14/01699/FUL | PPA-320-2113 |  |  |  |  | 2014-08-25 |  | 2016-12-06 | 2017-01-31 |  |  | 2017-11-24 | 2017-11-24 |  |  |  | 2020-11-24
| 6314 | 2017-02-02 | DPD | DPD Distribution Centre | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | GeoPost Uk Limited Hub 3 Broadwell Road Oldbury B69 4DA | West Midlands | West Midlands | England | B69 4DA | 399486 | 289883 | Sandwell Metropolitan Borough Council | PD/15/00438 | [5 empty] | 2015-11-27 | [6 empty] | 2015-12-30 |  |  |  |  | 2016-12-10 | 2017-01-10
| 6318 | 2017-06-16 | Clean Earth Energy | Craigannet Farm Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Operational | Operational | Land Some 1600 Metres North West Of Craigannet Farm Fintry | Stirling | Scotland | Scotland |  | 271250 | 685550 | Stirling Council | 15/00211/FUL | [5 empty] | 2015-04-27 | [6 empty] | 2015-08-16 |  |  |  |  | 2016-12-15 | 2017-03-31
| 6320 | 2017-02-03 | Bywaters | Bywaters’ Materials Recovery Facility Solar Array | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Unit J Prologis Park Twelvetrees Crescent Bromley By Bow London E3 3JG | Greater London | London | England | E3 3JG | 538372 | 182235 | Newham London Borough Council | 15/02981/PREPV | [5 empty] | 2015-10-19 | [6 empty] | 2015-12-18 |  |  |  |  | 2016-12-24 | 2017-01-24
| 6321 | 2017-02-17 | Anesco | High Meadow Farm | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at high Meadow Farm, Letch Lane, Carlton, Stockton | County Durham | North East | England | TS21 1EE | 440320 | 521958 | Stockton on Tees Borough Council | 15/1826/FUL | [5 empty] | 2015-07-22 | [6 empty] | 2015-12-04 |  |  |  |  | 2016-08-18 | 2016-10-18
| 6322 | 2020-01-21 | Distributed Renewable Energy Networks (DRENL) | Eggborough (Former Abre Biomass Facility) | Advanced Conversion Technologies |  |  | 10 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Former ARBRE Power Station, Selby Road, Eggborough, Goole | North Yorkshire | Yorkshire and Humber | England | DN14 0BS | 456785 | 424198 | North Yorkshire County Council | NY/2014/0292/ENV | [5 empty] | 2014-09-11 | [6 empty] | 2015-05-15
| 6323 | 2020-06-30 | Sandwick Community Council | East of Beinn Ghrideag Wind Farm | Wind Onshore |  |  | 5 | n/a |  |  |  | 5 | 1 | 145 | n/a | Planning Permission Granted | Awaiting Construction | Sandwick North Street (Beinn B, Pentland Road To Achmore, Achmore, Isle Of Lewis, Western Isles | Comhairle nan Eilean Siar | Scotland | Scotland | HS2 | 136905 | 932771 | Comhairle nan Eilean Siar Council | 19/00209/PPW | [5 empty] | 2019-05-08 | [6 empty] | 2020-05-21 |  |  |  | 2025-05-21
| 6324 | 2020-05-28 | Wind Prospect Developments | Burnfoot East Wind Farm (further extension) | Wind Onshore |  |  | 10.8 | n/a |  |  |  | 3.6 | 3 | 135 | n/a | Under Construction | Under Construction | Site West Of Burnfoot Hill, High Street, Tillicoultry, Central | Clackmannanshire | Scotland | Scotland | FK13 6A | 290930 | 703230 | Clackmannanshire Council | 17/00026/FULL | [5 empty] | 2017-01-30 | [6 empty] | 2019-03-27 |  |  |  | 2022-03-27 | 2019-09-01
| 6325 | 2020-01-24 | ESB Solar NI | Carrickatane | Solar Photovoltaics |  |  | 4.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Killymallaght Road, Cullion, Limavady, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 3UT | 59092 | 569961 | Northern Ireland Planning Service | LA11/2017/0089/F | [5 empty] | 2017-02-09 | [6 empty] | 2018-11-21 |  |  |  | 2023-11-21
| 6327 | 2020-06-30 | EnergieKontor UK | Longhill Burn Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3.2 | 8 | 180 | n/a | Planning Permission Granted | Awaiting Construction | Longhill Burn (west of Pates H, West Calder, Lothian | West Lothian | Scotland | Scotland | EH55 | 298062 | 658993 | West Lothian Council | 0359/FUL/19 | [5 empty] | 2019-04-15 | [6 empty] | 2020-04-17 |  |  |  | 2025-04-17
| 6328 | 2018-06-26 | Coastal Recycling UK (formerly Devon Waste Management) | Deep Moor Landfill Site (Resubmission) | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Deep Moor Landfill Site, High Bullen, Devon Waste Management Ltd, Torrington | Devon | South West | England | EX38 7JA | 252989 | 120836 | Devon County Council | DCC/3848/2016 | [5 empty] | 2016-03-09 | [6 empty] | 2017-02-02 |  |  |  |  | 2018-03-15 | 2018-04-20
| 6329 | 2017-09-19 | Southern Water Services | Testwood Water Supply Works | Solar Photovoltaics |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Testwood Pumping Station, Nutsey Close, Totton, Southampton, Hampshire | Hampshire | South East | England | SO40 3QU | 435379 | 114903 | New Forest District Council | 16/11007 | [5 empty] | 2016-07-15 | [6 empty] | 2016-12-12 |  |  |  |  | 2017-03-23 | 2017-08-24
| 6335 | 2020-01-27 | Pennant Walters (MAESX) | Maesgwyn Wind Farm - extension (Phase 2) | Wind Onshore |  |  | 7 | n/a |  |  |  | 2.3 | 3 |  | n/a | Planning Permission Granted | Awaiting Construction | Maesgwyn Wind Farm Between Onllwyn & Glynneath | Neath Port Talbot | Wales | Wales |  | 286568 | 205930 | Neath Port Talbot County Borough Council | P2014/0733 | [5 empty] | 2014-08-15 | [6 empty] | 2015-12-17 |  |  |  | 2020-12-17
| 6336 | 2019-12-17 | Boralex/Infinergy | Ardtaraig Wind Farm | Wind Onshore |  |  | 29.4 | n/a |  |  |  | 4.2 | 7 | 136.5 | n/a | Appeal Refused | Application Refused | Located around 14.5km to the west of Dunoon, near Loch Striven, adjacent to the Stronafian Community Forest, Strathclyde | Argyll and Bute | Scotland | Scotland | PA23 8RG | 203695 | 685790 | Argyll and Bute Council | 18/01516/PP | PPA-130-2073 |  |  |  |  | 2018-08-03 |  | 2019-03-29 | 2019-06-26 |  | 2019-11-07
| 6339 | 2020-03-10 | Tilbury Green Power | Tilbury Docks - Phase 2 (EfW) | EfW Incineration |  |  | 30 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Tilbury Docks, Essex | Essex | Eastern | England | RM18 7HP | 563035 | 176557 | DECC (S36) | [6 empty] | 2008-02-07 | [6 empty] | 2009-08-27
| 6341 | 2020-06-11 | Elgin Energy | Milltown Airfield (Speyslaw) | Solar Photovoltaics |  |  | 50 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Milltown Airfield, Innes Estate, Elgin, Moray | Moray | Scotland | Scotland |  | 326418 | 865499 | Scottish Government (S36) | ECU00000452 | [5 empty] | 2017-07-26 | [6 empty] | 2018-05-25 |  |  |  | 2021-05-25
| 6343 | 2018-03-28 | Private Developer | Penyrheol Las Farm | Wind Onshore |  |  | 1 | n/a |  |  |  | 0.5 | 2 | 74 | n/a | Appeal Refused | Application Refused | Pen Yr Heol Las Farm, Heol Las, Caerphilly, Mid Glamorgan | Caerphilly | Wales | Wales | CF83 2TT | 313774 | 191119 | Caerphilly County Borough Council | 17/0218/FULL | APP/K6920/A/17/3189669 |  |  |  |  | 2017-03-23 |  | 2017-05-18 | 2017-11-30 |  | 2018-03-05
| 6347 | 2020-03-26 | Barrel Law Windfarm | Barrel Law Wind Farm | Wind Onshore |  |  | 24.5 | n/a |  |  |  | 3.5 | 7 | 132 | n/a | Appeal Refused | Application Refused | Land South West Of, Whitslade, Ashkirk, Selkirk, Borders | Scottish Borders | Scotland | Scotland | TD7 4PH | 341200 | 617800 | Scottish Borders Council | 17/01255/FUL | PPA-140-2072 |  |  |  |  | 2017-09-08 |  | 2018-09-03 | 2018-11-02 |  | 2019-12-23
| 6353 | 2019-05-16 | Private Developer | Beltonanean 2 (resubmission) | Wind Onshore |  |  | 2.3 | n/a |  |  |  | 2.3 | 1 | 92.5 | n/a | Appeal Granted | Awaiting Construction | Beltonanean Mountain, Beltonanean TD, Cookstown, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT80 0A | 85122 | 543266 | Northern Ireland Planning Service | LA09/2017/0272/F | 2017/A0176 |  |  |  |  | 2017-03-02 |  | 2017-10-04 | 2017-11-30 |  |  | 2018-04-18 | 2018-04-18
| 6355 | 2018-12-18 | Avocet Infinite | Neilson Biogas Park Farm AD (Resubmission) | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Park Farm, Hurlawcrook Road, East Kilbride, Glasgow, Strathclyde | South Lanarkshire | Scotland | Scotland | G75 0QL | 263684 | 649872 | South Lanarkshire Council | EK/17/0051 | [5 empty] | 2017-02-13 | 2018-11-27
| 6357 | 2020-04-29 | Kanes Foods | Cleeve Road | Solar Photovoltaics |  |  | 3.7 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land associated with Kanes Food, Cleeve Road, Middle Littleton, Evesham, Hereford and Worcester | Hereford and Worcester | West Midlands | England | WR11 8JR | 407454 | 246828 | Wychavon District Council | W/16/02929/PN | [5 empty] | 2016-12-21 | [6 empty] | 2017-12-15 |  |  |  | 2020-12-15
| 6358 | 2019-04-01 | Great Coates Energy | Moody Lane (Former Acordis site) | EfW Incineration |  |  | 18 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Former Acordis site, Energy Park Way, Moody Lane, Healing, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN31 2TT | 523376 | 412410 | North East Lincolnshire Council | DM/0195/17/FUL | [5 empty] | 2017-03-13 | [6 empty] | 2017-08-01 |  |  |  | 2020-08-01
| 6360 | 2020-01-24 | Wirsol | White Horse Lane (Trowse) - Phase 2 | Solar Photovoltaics |  |  | 9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land East of White Horse Lane, Norwich | Norfolk | Eastern | England |  | 623981 | 305949 | South Norfolk Council | 2014/2380 | [5 empty] | 2014-12-09 | [6 empty] | 2015-08-11 |  |  |  | 2018-08-11
| 6363 | 2020-03-11 | Muirhall Energy | Priestgill Wind Farm | Wind Onshore |  |  | 22.4 | n/a |  |  |  | 3.2 | 7 | 145 | n/a | Appeal Granted | Awaiting Construction | Priestgill Wind Farm, Little Gill Farm, Abington, Biggar, Strathclyde | South Lanarkshire | Scotland | Scotland | ML12 6RW | 295854 | 625399 | South Lanarkshire Council | CL/17/0009 | PPA-380-2075 |  |  |  |  | 2016-12-13 |  | 2017-08-16 | 2017-11-14 |  |  | 2018-12-07 | 2018-12-07 |  |  |  | 2021-12-07
| 6366 | 2019-06-28 | Hydro Electric Development | Ystradffin Hydropower Project | Small Hydro |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Ystradffin Hydropower Project, Rhandirmwyn, Llandovery, Dyfed | Carmarthenshire | Wales | Wales | SA20 | 277600 | 245890 | Carmarthenshire County Council | E/34887 | [5 empty] | 2016-12-21 | [6 empty] | 2017-10-09 |  |  |  | 2022-10-09 | 2018-11-25
| 6367 | 2019-08-22 | Safran Landing Systems UK/Technical Plant Services | Safran Landing Systems Service | Biomass (dedicated) |  |  | 3.6 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Safran Landing Systems Service, Cheltenham Road East, Meteor Business Park, Gloucester, Gloucestershire | Gloucestershire | South West | England | GL2 9QL | 388283 | 222154 | Tewkesbury Borough Council | 16/01398/FUL | [5 empty] | 2016-12-09 | [6 empty] | 2017-02-06 |  |  |  |  | 2019-02-07 | 2017-03-29
| 6368 | 2019-12-03 | CBRE | Former Croda site | Anaerobic Digestion |  |  |  | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Former Croda site, Wilton International, Redcar, Cleveland | Cleveland | North East | England | TS10 | 457525 | 522360 | Redcar and Cleveland Borough Council | R/2016/0484/FFM | [5 empty] | 2016-08-05 | [6 empty] | 2016-10-13
| 6369 | 2017-04-04 | INRG | Rosedew Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land at Rosedew Farm, Beach Road, Llantwit Major | Vale of Glamorgan | Wales | Wales | CF61 1PZ | 297779 | 167534 | Vale of Glamorgan Council | 2015/00218/FUL | [5 empty] | 2015-03-02 | [6 empty] | 2015-08-03 |  |  |  |  | 2016-01-29 | 2016-03-29
| 6372 | 2019-10-02 | EDF Energy Renewables/ Force 9 | Clash Gour | Wind Onshore |  |  | 256 | n/a |  |  |  | 5.33 | 48 | 175 | n/a | Planning Application Submitted | Application Submitted | located to the southwest, north and east of Berry Burn | Moray | Scotland | Scotland |  | 308050 | 844900 | Scottish Government (S36) | ECU00000738 | [5 empty] | 2018-12-03
| 6373 | 2020-03-31 | Vattenfall | Clashindarroch 2 (extension) | Wind Onshore |  |  | 70 | n/a |  |  |  | 5 | 14 | 180 | n/a | Planning Application Submitted | Application Submitted | Clashindarroch Forest, Huntly, Aberdeenshire | Grampian | Scotland | Scotland |  | 344000 | 833000 | Scottish Government (S36) | ECU00002002 | [5 empty] | 2019-12-23
| 6375 | 2017-04-05 | Merthyr Tydfil County Borough Council | Pengarnddu Industrial Estate - Biomass Recycling Plant | Advanced Conversion Technologies |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Plot 2 Pengarnddu estate, alongside the A465 Heads Of The Valleys Road at Dowlais Top. | Merthyr Tydfil | Wales | Wales |  | 307702 | 208951 | Merthyr Tydfil County Borough Council | P/12/0298 | [5 empty] | 2012-10-31 | [6 empty] | 2013-07-24 |  |  |  | 2014-01-01 | 2014-03-03
| 6376 | 2017-12-14 | Tudor Roof Tile Co | Dengemarsh Road | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Tudor Roof Tile Co, Dengemarsh Road, Lydd, Romney Marsh, Kent | Kent | South East | England | TN29 9JH | 604556 | 119110 | Shepway District Council | Y17/0005/PA | [5 empty] | 2017-02-21 | [6 empty] | 2017-04-13 |  |  |  |  | 2016-11-30 | 2016-12-14
| 6377 | 2019-06-28 | Boralex/Infinergy | Lochluichart Extention II | Wind Onshore |  |  | 24 | n/a |  |  |  | 3 | 8 | 125 | n/a | Planning Application Submitted | Application Submitted | Land Between, Lochluichart and Loch Glascarnoc, Garve, Highlands | Highland | Scotland | Scotland | IV23 2PZ | 232487 | 868453 | Highland Council | 19/01284/FUL | [5 empty] | 2019-04-11
| 6378 | 2020-01-29 | Sirius Group | Former Nant-y-Gwyddon Landfill Site | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 121.5 | n/a | Planning Permission Granted | Awaiting Construction | Land adj. to former Nant-Y-Gwy, Landfill site, Pentre, Mid Glamorgan | Rhondda Cynon Taff | Wales | Wales | CF41 | 297766 | 193866 | Rhondda Cynon Taff County Borough Council | 17/0321/10 | [5 empty] | 2017-03-17 | [6 empty] | 2017-08-22 |  |  |  | 2022-08-22
| 6384 | 2019-06-28 | Peel Wind Farms (Peel Energy) | Mossy Hill | Wind Onshore |  |  | 46.8 | N/A |  |  |  | 3.9 | 12 | 145 | n/a | Planning Permission Granted | Awaiting Construction | West of A970, includes Tagdale Hill, Hill of Dale, Mossy Hill and Bersa Hill, approx 2.4km from outskirts of Lerwick and approx 4.2km from Lerwick Harbour | Shetland | Scotland | Scotland | ZE2 9SB | 443900 | 1142000 | Shetland Islands Council | 2018/186/PPF | [5 empty] | 2018-06-27 | [6 empty] | 2019-05-27 |  |  |  | 2022-05-26
| 6388 | 2017-05-04 | CBK Galbraith | Ferneylea Farm | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 0.75 | 2 | 71 | n/a | Operational | Operational | Ferneylea Farm, Cockburnspath | East Lothian | Scotland | Scotland | TD13 5YN | 373982 | 669162 | East Lothian Council | 10/00769/P | PPA-210-2025 |  |  |  |  | 2010-09-21 |  | 2012-03-07 | 2012-05-01 |  |  | 2012-09-26 | 2012-09-26 |  |  |  |  | 2014-12-01 | 2015-01-01
| 6390 | 2017-07-20 | Greener For Life Energy | Enfield Farm | Anaerobic Digestion |  |  | 2 | yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Enfield Farm, Oil Mill Lane, Clyst St Mary, Exeter | Devon | South West | England | EX5 1AF | 298374 | 90778 | East Devon District Council | 14/0858/MFUL | [5 empty] | 2014-04-30 | [6 empty] | 2014-07-24 |  |  |  | 2017-07-24 | 2015-09-15 | 2016-09-15
| 6392 | 2019-11-20 | Jardin Smith International | Fontley House Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land Adjacent To Moorshill Far, Fontley Road, Titchfield, Fareham, Hampshire | Hampshire | South East | England | PO15 6QS | 455709 | 110976 | Winchester City Council | 16/00863/FUL | [5 empty] | 2016-04-21 | [6 empty] | 2017-05-03
| 6396 | 2020-04-21 | Crapper and Sons Landfill | Swindon Energy Plant (Park Grounds) | Advanced Conversion Technologies |  |  | 6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Crapper and Sons Landfill Ltd, Brinkworth Road, Royal Wootton Bassett, Park Grounds, Swindon, Wiltshire | Wiltshire | South West | England | SN4 8DW | 405117 | 183986 | Wiltshire Council | 17/03547/WCM | [5 empty] | 2017-04-07 | [6 empty] | 2017-08-02 |  |  |  | 2020-08-02 | 2018-06-15
| 6398 | 2018-10-25 | Green Cat Renewables | North Haddo | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 | 74 | n/a | Planning Permission Granted | Awaiting Construction | Land West Of North Haddo, Fyvie, Turriff, Grampian | Aberdeen | Scotland | Scotland | AB53 8LA | 374646 | 838972 | Aberdeenshire Council | APP/2017/0869 | [5 empty] | 2017-04-03 | [6 empty] | 2017-12-01 |  |  |  | 2020-11-30
| 6402 | 2017-06-01 | Athos Solar | Haigh Hall Solar Farm (Resubmission) | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Batley Road, Tingley, Wakefield | West Yorkshire | Yorkshire and Humber | England | WF3 1HA | 428383 | 424026 | Leeds City Council | 16/02663/FU | [5 empty] | 2016-05-04 | [6 empty] | 2016-07-27 |  |  |  |  | 2016-12-01 | 2017-02-01
| 6403 | 2017-06-01 | Next/ Eneco | Next Distribution Centre Doncaster | Solar Photovoltaics |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Lincolnshire Way, Armthorpe, Doncaster | South Yorkshire | Yorkshire and Humber | England | DN3 3FF | 464153 | 405024 | Doncaster Metropolitan Borough Council | [18 empty] | 2016-11-01 | 2016-12-01
| 6405 | 2018-07-05 | ESB | Blarghour | Wind Onshore |  |  | 60 | n/a |  |  |  | 3.75 | 16 | 136.5 | n/a | Planning Application Submitted | Application Submitted | 7km north west of Inveraray and 6km east of Dalavich | Argyll and Bute | Scotland | Scotland |  | 203718 | 713332 | Scottish Government (S36) | EC00005267 | [5 empty] | 2018-05-23
| 6407 | 2019-10-01 | Fred Olsen Renewables | Pauls Hill 2 | Wind Onshore |  |  | 28 | n/a |  |  |  | 4 | 7 | 149.9 | n/a | Appeal Lodged | Application Submitted | Paul's Hill, Bowlingalloch, Moray | Grampian | Scotland | Scotland |  | 311500 | 840500 | Scottish Government (S36) | ECU00000578 | WIN-300-3 |  |  |  |  | 2018-03-29 |  |  | 2018-12-20
| 6409 | 2019-06-27 | Clean Power Properties | Whistleberry Road, Hamilton | Advanced Conversion Technologies |  |  | 18 | yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Withdrawn | Application Refused | Site at, Whistleberry Road, Hamilton, Strathclyde | South Lanarkshire | Scotland | Scotland | ML3 0EG | 270740 | 657475 | South Lanarkshire Council | HM/17/0260 | PPA-380-2078 |  |  |  |  | 2017-06-09 |  | 2018-07-04 | 2018-10-01 | 2019-05-30
| 6411 | 2020-05-28 | Gwent Farmers' Community Solar Partnership | Llanwern | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | S/o Whitson Electricity Substa, Broad Street Common, Nash, Newport, Gwent | Newport | Wales | Wales | NP19 4QZ | 337488 | 185100 | Welsh Government (NSIP) | DNS/3213968 | [5 empty] | 2018-02-20 | [6 empty] | 2018-11-13 |  |  |  |  | 2020-05-27
| 6414 | 2018-11-30 | Innogy | Ashmark Hill Community Wind Farm | Wind Onshore |  |  | 21 | N/A |  |  |  | 3 | 7 | 135 | n/a | Planning Permission Refused | Application Refused | Land At Ashmark Hill C90, Afton Road, 5km south of New Cumnock, Mossmark, Strathclyde | East Ayrshire | Scotland | Scotland | KA18 4PR | 260000 | 608500 | East Ayrshire Council | 18/0354/PP | [5 empty] | 2018-05-01 |  | 2018-09-28
| 6416 | 2020-06-11 | Elgin Energy | Speyslaw Solar Farm | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Speyslaw Urquhart, Elgin, Highlands | Moray | Scotland | Scotland | IV30 8LX | 328565 | 866472 | Moray Council | 17/00808/APP | [5 empty] | 2017-05-26 | [6 empty] | 2017-07-21 |  |  |  | 2020-07-21
| 6420 | 2019-12-06 | Solar Energy Farm | Court Colman | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land south/west of Longacre, Court Colman, Bridgend, Mid Glamorgan | Bridgend | Wales | Wales | CF32 0HD | 288235 | 182822 | Bridgend County Borough Council | P/17/423/FUL | [5 empty] | 2017-05-16 | [6 empty] | 2017-08-31 |  |  |  | 2022-08-31
| 6422 | 2020-06-18 | Cleanearth | Graig Fatha Farm | Wind Onshore |  |  | 2.5 | n/a |  |  |  | 2.5 | 1 | 126 | n/a | Planning Permission Granted | Awaiting Construction | Land at Graig Fatha Farm, Tonyrefail, Porth, Mid Glamorgan | Rhondda Cynon Taff | Wales | Wales | CF39 8EX | 301279 | 185404 | Rhondda Cynon Taff County Borough Council | 17/0493/10 | [5 empty] | 2017-05-02 | [6 empty] | 2018-03-14 |  |  |  | 2023-03-14
| 6424 | 2019-10-21 | Rigg Wind | Southrigg 2 | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 128.5 | n/a | Abandoned | Abandoned | Southrigg Farm C1-Torrance Far, Bathgate, Lothian | North Lanarkshire | Scotland | Scotland | EH48 3AW | 292131 | 665673 | North Lanarkshire Council | 17/01478/FUL | [5 empty] | 2017-09-04 | [6 empty] | 2017-12-18 |  |  |  | 2022-12-18
| 6426 | 2020-07-02 | Mainstream Renewable Power | Neart na Gaoithe (Resubmission) | Wind Offshore |  |  | 450 | n/a |  |  |  | 8 | 54 | 208 | n/a | Planning Permission Granted | Awaiting Construction | Firth of Forth, 15.5km east of Fife Ness | Offshore | Offshore | Scotland |  | 384615 | 708641 | Marine Scotland | [6 empty] | 2018-03-16 | [6 empty] | 2018-12-03
| 6430 | 2018-01-31 | Mickram | Cross Banks Road | Anaerobic Digestion |  |  |  | yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land at Cross Bank Road, Kings Lynn | Norfolk | Eastern | England | PE30 2HD | 561216 | 321368 | Norfolk County Council | C/2/2017/2009 | [5 empty] | 2017-05-24 |  | 2017-10-13
| 6432 | 2019-03-26 | EDF Energy Renewables | Troston Loch | Wind Onshore |  |  | 67.2 | n/a |  |  |  | 4.8 | 14 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Troston Loch Wind Farm, New Abbey, West Of Moniaive, Dumfries, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG2 8EF | 268466 | 590107 | Scottish Government (S36) | ECU00001785 | [5 empty] | 2019-02-21
| 6433 | 2019-09-25 | EnergieKontor UK | Cornharrow Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3.3 | 11 | 149.9 | n/a | Appeal Refused | Application Refused | Proposed Cornharrow Wind Farm, Land At Cornharrow, Dalry, Castle Douglas, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG7 3UG | 266701 | 592862 | Dumfries and Galloway Council | 18/1127/FUL | PPA-170-2140 |  |  |  |  | 2017-07-20 |  |  | 2019-03-11 |  | 2019-09-11
| 6436 | 2017-10-04 | Tamani | Greenhill Farm | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 | 127 | n/a | Planning Application Withdrawn | Application Withdrawn | Wester Greenhill Farm, Avonbridge, Falkirk, Central | Falkirk | Scotland | Scotland | FK1 2JR | 283668 | 672320 | Falkirk Council | P/17/0411/FUL | [5 empty] | 2017-06-28 | 2017-09-01
| 6439 | 2017-08-30 | ABO Wind NI | Carnalbanagh Windfarm (Resubmission) | Wind Onshore |  |  | 21 | n/a |  |  |  | 3 | 7 | 125 | n/a | Planning Application Submitted | Application Submitted | 560 Metres East of, 87 Carnalbanagh Road To, 770 Metres West Of 43 Carnalba, Broughshane, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT42 4NS | 139634 | 563503 | Northern Ireland Planning Service | LA02/2017/0594/F | [5 empty] | 2017-06-29
| 6442 | 2017-07-28 | Dartmoor Bio Power 1 | Dartmoor Bio Power | Advanced Conversion Technologies |  |  | 3.9 | yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | 1 Belliver Way, Plymouth | Devon | South West | England | PL6 7BW | 250105 | 63417 | Plymouth City Council | 08/00117/FUL | [5 empty] | 2008-01-21 | [6 empty] | 2008-07-11 |  |  |  |  | 2012-05-06 | 2013-11-06
| 6443 | 2020-06-30 | EnergieKontor UK | Little Hartfell Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3 | 12 | 160 | n/a | Planning Permission Granted | Awaiting Construction | Little Hartfell Wind Farm, Langholm, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG13 0A | 320901 | 585871 | Dumfries and Galloway Council | 18/0188/FUL | [5 empty] | 2018-02-09 | [6 empty] | 2020-06-09 |  |  |  | 2023-06-09
| 6444 | 2020-04-30 | EnergieKontor UK | Glenshimmeroch Wind Farm | Wind Onshore |  |  | 36 | n/a |  |  |  | 3.6 | 10 | 149.9 | n/a | Appeal Granted | Awaiting Construction | Land At Glenshimmeroch Hill, St. John's Town of Dalry, Dalry, Castle Douglas | Dumfries and Galloway | Scotland | Scotland | DG7 3XL | 266021 | 587733 | Dumfries and Galloway Council | 18/0992/FUL | PPA-170-2138 |  |  |  |  | 2018-07-02 |  | 2019-03-05 | 2019-02-22 |  |  | 2019-09-04 | 2019-09-04 |  |  |  | 2022-09-04
| 6450 | 2017-08-16 | Bryn Group | Gelliargwellt Uchaf Farm AD | Anaerobic Digestion |  |  | 1.4 |  |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Gelliargwellt Uchaf Farm Gelligaer Road Gelligaer Hengoed CF82 8FY | Caerphilly | Wales | Wales | CF82 8FY | 312306 | 196957 | Caerphilly County Borough Council | 11/0224/FULL | 12/0020/REF |  |  |  |  | 2011-03-23 |  | 2011-12-08 | 2012-07-03 |  |  | 2013-03-28 | 2013-03-28 |  |  |  |  | 2015-10-01 | 2016-02-01
| 6451 | 2018-03-28 | Woodhouse Properties | Mossdown Road | EfW Incineration |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land at, Mossdown Road, Royton, Oldham, Greater Manchester | Greater Manchester | North West | England | OL2 6HS | 393642 | 407045 | Oldham Council | PA/339409/16 | [5 empty] | 2017-08-16 |  | 2018-03-22
| 6454 | 2018-11-27 | Improving New Cumnock and Young Brothers/ Green Cat Renewables | High Park Farm | Wind Onshore |  |  |  | n/a |  |  |  |  | 2 | 74 | n/a | Appeal Refused | Application Refused | High Park Farm, Afton Road, New Cumnock, Cumnock, Strathclyde | East Ayrshire | Scotland | Scotland | KA18 4BG | 262641 | 612007 | East Ayrshire Council | 17/0569/PP | PPA-190-2067 |  |  |  |  | 2017-07-20 |  | 2018-01-19 | 2018-04-17 |  | 2018-10-18
| 6456 | 2019-11-26 | Ethical Power | Branston Solar Park (extension) | Solar Photovoltaics |  |  | 40 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land Between, Mere Road and Sleaford Road, Branston, Lincoln, Lincolnshire | Lincolnshire | East Midlands | England | LN4 1NJ | 502619 | 366273 | North Kesteven District Council | 17/1546/FUL | [5 empty] | 2017-10-23 | [6 empty] | 2018-02-21 |  |  |  |  | 2019-09-30
| 6457 | 2019-03-01 | Lightsource Renewable Energy (Rashmika SPV 1) | Sutton Mawr Solar Farm (extension) | Solar Photovoltaics |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Land adj. to Sutton Mawr Farm, Waycock Road, BarrySouth Glamorgan | Vale of Glamorgan | Wales | Wales | CF62 3AA | 307867 | 169737 | Vale of Glamorgan Council | 2016/00979/FUL | [5 empty] | 2016-08-10 | [6 empty] | 2016-10-04 |  |  |  | 2021-10-04
| 6458 | 2017-09-04 | AR Partners | Sytchwythy Fields | Solar Photovoltaics |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Sytchwythy Fields, Sidings Lane, Aldington, Evesham | Hereford and Worcester | West Midlands | England | WR11 7ZN | 405947 | 244721 | Wychavon District Council | W/15/00104/PN | [5 empty] | 2015-01-15 | [6 empty] | 2015-03-12 |  |  |  | 2018-03-12 | 2017-02-28 | 2017-03-31
| 6459 | 2020-06-04 | Community Windpower | Faw Side Community Wind Farm | Wind Onshore |  |  | 315 | n/a |  |  |  | 7 | 45 | 200 | n/a | Planning Application Submitted | Application Submitted | Land 6.7km North of Langholm and 17.8 km south west of Hawick | Dumfries and Galloway | Scotland | Scotland | TD9 0 | 335000 | 596000 | Scottish Government (S36) | ECU00001833 | [5 empty] | 2019-05-22
| 6460 | 2020-06-25 | Amey | Waterbeach Waste Management Park | EfW Incineration |  |  | 27.4 |  |  |  |  | n/a | n/a | n/a | n/a | Secretary of State - Refusal | Application Refused | Levitt’s Field, Waterbeach Waste Management Park, Ely Road,, Waterbeach, Cambridge | Cambridgeshire | Eastern | England | CB25 9PQ | 548813 | 268542 | Cambridgeshire County Council | S/3372/17/CW | APP/E0535/W/19/3225123 |  |  |  |  | 2017-12-20 |  | 2018-09-21 | 2019-03-20 |  | 2020-06-15 |  |  |  | 2020-06-15
| 6463 | 2020-03-23 | Barn Energy | Cromwell Weir (Right Bank) | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Cromwell Weir (Right Bank), North Muskham, Newark, Nottinghamshire | Nottinghamshire | East Midlands | England | NG23 6HX | 480997 | 361123 | Newark and Sherwood District Council | 17/01447/FUL | [5 empty] | 2017-08-08 | [6 empty] | 2018-05-23 |  |  |  | 2021-05-23
| 6464 | 2020-03-25 | EDF Energy Renewables | Airigh Wind Farm | Wind Onshore |  |  | 58.8 | n/a |  |  |  | 4.2 | 14 | 149.5 | n/a | Planning Permission Granted | Awaiting Construction | Airigh Wind Farm SW of, Tarbert | Argyll and Bute | Scotland | Scotland | PA29 6 | 176171 | 666802 | Scottish Government (S36) | ECU00000471 | [5 empty] | 2017-09-01 | [6 empty] | 2020-03-20 |  |  |  | 2023-03-20
| 6466 | 2019-09-27 | United Utilities | Clifton Marsh Wastewater Treatment Works | Solar Photovoltaics |  |  | 1.28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Clifton Marsh Farm, Preston New Road, Clifton, Preston, Lancashire | Lancashire | North West | England | PR4 0 | 345637 | 428615 | Lancashire County Council | LCC/2017/0074 | [5 empty] | 2017-08-04 | [6 empty] | 2018-03-12 |  |  |  | 2021-03-12 | 2019-01-15 | 2019-08-22
| 6477 | 2018-11-28 | Elgin Energy | Wauntysswg Farm, near Tredagar | Solar Photovoltaics |  |  | 30 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Wauntysswg Farm, Abertysswg, Rhymney, Tredegar | Blaenau Gwent | Wales | Wales | NP22 5BQ | 314077 | 206445 | Welsh Government (NSIP) | DNS/3213639 | [5 empty] | 2018-07-28
| 6481 | 2018-12-14 | Think Greenenergy TOPCO (Think Environmental) | Blackbridge TGS 1 | Advanced Conversion Technologies |  |  | 5.6 | yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Blackbridge Farm, Cranford Road, Kettering, NN15 5JJ | Northamptonshire | East Midlands | England | NN15 5JJ | 490942 | 276374 | Northamptonshire County Council | 09/00014/WAS | [5 empty] | 2009-03-06 | [6 empty] | 2009-05-20
| 6483 | 2019-08-05 | Vattenfall/Scottish Power Renewables | The East Anglia Array - Norfolk Boreas | Wind Offshore |  |  | 1800 | n/a |  |  |  | 5 | 360 |  | n/a | Planning Application Submitted | Application Submitted | North Sea, off the East Anglia coast | Offshore | Offshore | England |  | 708047 | 312194 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2019-06-11
| 6484 | 2020-02-05 | REG Solarpower/Veolia | Ling Hall | Solar Photovoltaics |  |  | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Ling Hall Quarry, Coalpit Lane, Lawford Heath, Rugby | Warwickshire | West Midlands | England | CV23 9HH | 444322 | 273238 | Warwickshire County Council | RBC/14CM029 | [5 empty] | 2014-07-02 | [6 empty] | 2014-10-17
| 6485 | 2017-11-03 | Kingspan | Sherburn | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Widespan Works, Sherburn, Malton | North Yorkshire | Yorkshire and Humber | England | YO17 8PQ | 496365 | 476952 | Ryedale District Council | 14/00132/MFUL | [5 empty] | 2014-01-31 | [6 empty] | 2014-08-21 |  |  |  |  | 2016-11-30 | 2016-01-20
| 6486 | 2017-11-03 | Aldi | Aldi - Cardiff | Solar Photovoltaics |  |  | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Wentloog Ave, St. Mellons, Cardiff | Cardiff | Wales | Wales | CF3 2EX | 322487 | 178507 | Cardiff Council | [18 empty] | 2016-01-01 | 2016-04-01
| 6488 | 2017-10-31 | ABP Ellesmere | ABP Ellesmere Abbatoir | Biomass (dedicated) |  |  | 1.1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | ABP Ellesmere, The Abattoir, Hordley, Ellesmere | Shropshire | West Midlands | England | SY12 9BL | 339586 | 328910 | Shropshire Council | 10/01784/EIA | [5 empty] | 2010-05-20 | [6 empty] | 2013-09-25 |  |  |  | 2016-09-25 | 2014-03-14 | 2015-09-14
| 6489 | 2017-10-31 | Thames Water Utilities | Swindon Sewerage Treatment Works | Anaerobic Digestion |  |  | 1.2 |  |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Swindon STW, Barnfield Road, Swindon | Wiltshire | South West | England | SN2 2DJ | 413372 | 185464 | Swindon Borough Council | S/15/0530 | [5 empty] | 2015-04-01 | [6 empty] | 2015-06-09 |  |  |  | 2018-04-01 | 2015-12-15 | 2016-06-15
| 6490 | 2017-10-31 | Thames Water Utilities | Rye Meads Sewerage Treatment Works | Anaerobic Digestion |  |  | 2.3 |  |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Rye Meads STW, Stanstead Abbots, Nr Ware | Hertfordshire | Eastern | England | SG12 8JY | 539261 | 210391 | East Hertfordshire District Council | 3/14/0768/FP | [5 empty] | 2014-05-13 | [6 empty] | 2014-09-04 |  |  |  | 2017-09-04 | 2015-01-01 | 2015-07-01
| 6491 | 2017-10-31 | Thames Water Utilities | Deephams Sewerage Treatment Works | Anaerobic Digestion |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Picketts Lock Lane, Edmonton, London | Greater London | London | England | N9 0BA | 535666 | 193784 | Enfield London Borough Council | 14/02612/FUL | [5 empty] | 2014-07-07 | [6 empty] | 2015-02-20 |  |  |  | 2018-02-20 | 2016-04-18 | 2016-10-18
| 6492 | 2017-11-01 | RCMA Stratford | Alscot | Biomass (dedicated) |  |  | 1.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Atherstone Airfield, Atherstone-on-Stour, Stratford-upon-Avon | Warwickshire | West Midlands | England | CV37 8BE | 422048 | 253020 | Stratford on Avon District Council | 13/00952/FUL | [5 empty] | 2013-04-19 | [6 empty] | 2013-09-18 |  |  |  | 2016-09-18 | 2015-09-03 | 2017-03-03
| 6493 | 2017-11-01 | Monmouthshire County Council | Oak Grove Farm | Solar Photovoltaics |  |  | 5.67 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Oak Grove Farm, A48, Crick to Parkwall Roundabout, Crick | Monmouthshire | Wales | Wales | NP26 5UT | 350177 | 190450 | Monmouthshire County Council | DC/2015/00247 | [5 empty] | 2015-03-05 | [6 empty] | 2015-09-23 |  |  |  | 2018-09-23 | 2017-01-30 | 2017-03-30
| 6495 | 2019-04-01 | Keil Green Energy | Land at Keihill | Biomass (dedicated) |  |  | 3 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Site At Keilhill, King Edward, Banff, Grampian | Aberdeen | Scotland | Scotland | AB45 3LT | 371172 | 859784 | Aberdeenshire Council | APP/2017/1357 | [5 empty] | 2017-10-16 |  | 2019-02-26
| 6500 | 2019-12-18 | Rolton Kilbride | Sunderland Renewable Energy Centre (Hillthorn Farm) | Advanced Conversion Technologies |  |  | 27 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Lodged | Application Refused | Land At Hillthorn Farm, Washington, Tyne and Wear | Tyne and Wear | North East | England | NE37 3HZ | 432207 | 557282 | Sunderland City Council | 17/02085/MW4 | APP/J4525/W/19/3239523 |  |  |  |  | 2017-10-24 |  | 2019-08-02 | 2019-10-18
| 6501 | 2019-10-02 | Orsted (formerly Dong Energy)/ Macquarie Group | Race Bank (Phase 2) | Wind Offshore |  |  | 286.5 | n/a |  |  |  | 6 | 45 | 154 | n/a | Operational | Operational | Race Bank , Greater Wash | Offshore | Offshore | England |  | 573300 | 363000 | DECC (S36) | [6 empty] | 2009-01-23 | [6 empty] | 2012-07-06 |  |  |  |  | 2016-07-07 | 2018-02-01
| 6502 | 2020-06-24 | Cleve Hill Solar (Hive Energy/ Wirsol Energy) | Cleve Hill Solar Project | Solar Photovoltaics |  | 7856 | 350 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Graveney, Whitstable | Kent | South East | England | ME13 9EE | 603057 | 163995 | DECC (S36) | EN010085 | [5 empty] | 2018-11-16 | [6 empty] | 2020-05-28 |  |  |  | 2025-06-19
| 6505 | 2020-06-24 | Cory Riverside Energy | Riverside Energy Park (REP) | Anaerobic Digestion |  | 7036 | 19 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Norman Rd, Belvedere, Bexley | London | South East | England |  | 549545 | 180595 | The Planning Inspectorate - National Infrastructure | EN010093 | [5 empty] | 2018-11-16 | [6 empty] | 2020-04-09
| 6506 | 2017-11-27 | Elgin Energy | Bann Road (Rasharkin) | Solar Photovoltaics |  |  | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Lands located North of Bann Road East/S.East of Ballmaconnelly Road West/S.West of Finvoy Road and North/N.West of Moneyleck Road Rasharkin - approx 200m E of No 41 Ballymaconnelly Road Rasharkin | Co. Antrim | Northern Ireland | Northern Ireland | BT44 8SZ | 111100 | 572064 | Northern Ireland Planning Service | D/2014/0181/F | [5 empty] | 2014-09-19 | [6 empty] | 2015-06-12 |  |  |  | 2017-09-19 | 2017-02-06 | 2017-04-06
| 6507 | 2017-11-28 | Naturegen Energy Centre | Ipswich Hospital Energy Centre | Biomass (dedicated) |  |  | 2.6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Ipswich Hospital NHS Trust, Heath Road, Ipswich, Suffolk | Suffolk | Eastern | England | IP4 5PD | 619336 | 244656 | Ipswich Borough Council | 12/01006/FUL | [5 empty] | 2012-12-24 | [6 empty] | 2013-02-19 |  |  |  | 2016-02-19 | 2015-09-15 | 2017-03-15
| 6508 | 2017-11-29 | Thames Water Utilities | Slough Sewage Treatment Works | Sewage Sludge Digestion |  |  | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Thames Water Utilities Limited, Slough STW, Wood Lane, Slough | Berkshire | South East | England | SL1 9EB | 494651 | 179516 | Slough Borough Council | [18 empty] | 2015-04-17 | 2016-05-17
| 6509 | 2019-11-18 | Clean Earth (CE) | Longlands Farm, Rush Wall Lane | Wind Onshore |  |  | 3.5 | n/a |  |  |  | 3.5 | 1 | 130 | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent To And South Of, Rush Wall Lane, Magor, Caldicot, Gwent | Newport | Wales | Wales | NP26 3DX | 341283 | 186111 | Newport City Council | 18/0408 | [5 empty] | 2018-05-03 | [6 empty] | 2019-01-09 |  |  |  | 2024-01-09
| 6511 | 2020-02-04 | Parc Calon Gwyrdd | Rover Way | Biomass (dedicated) |  |  | 9.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At, Rover Way, Cardiff, South Glamorgan | Cardiff | Wales | Wales | CF24 2RX | 321114 | 176159 | Cardiff Council | 17/02130/MJR | [5 empty] | 2017-11-08 | [6 empty] | 2018-06-14 |  |  |  | 2021-06-14
| 6512 | 2020-01-28 | Larch Group and Woodford Recycling Services | Old Brick Works (Station Road, Warboys) | Biomass (dedicated) |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Warboys Landfill Site, Puddock Hill, Huntingdon, Cambridgeshire | Cambridgeshire | Eastern | England | PE28 2TX | 531139 | 281752 | Cambridgeshire County Council | H/5002/18/CW | [5 empty] | 2018-01-17 | [6 empty] | 2019-07-17 |  |  |  | 2024-07-17
| 6513 | 2019-05-22 | Lightsource BP | Lathom (Pilkington Technical Centre) | Solar Photovoltaics |  | 7037 | 2.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land To The E/O Lords Cottage, Hall Lane, Lathom, Ormskirk | Lancashire | North West | England | L40 6JB | 345479 | 408342 | West Lancashire Borough Council | 2018/0409/FUL | [5 empty] | 2018-04-17 | [6 empty] | 2018-07-31 |  |  |  |  | 2019-04-01 | 2019-05-20
| 6515 | 2020-06-11 | Elgin Energy EsCo | Desford Road, Thurlaston | Solar Photovoltaics |  |  | 40 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Field No 8236, Hinckley Road, Land To South And West Of, Desford Road, Thurlaston, Leicester | Leicestershire | East Midlands | England | LE9 7TD | 451267 | 300918 | Blaby District Council | 18/0242/FUL | [5 empty] | 2018-03-27 | [6 empty] | 2018-09-17 |  |  |  | 2021-09-17
| 6517 | 2019-11-22 | Highfield Environmental | ICI No2 (Teesport) Landfill | Landfill Gas |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | ICI No2 (Teesport) Landfill, 2 Teesport, Landfill Grange Town, South Bank, Middlesbrough, Cleveland | Cleveland | North East | England | TS6 6UG | 454600 | 522200 | Redcar and Cleveland Borough Council | R/2017/0709/FF | [5 empty] | 2017-10-09 | [6 empty] | 2017-12-07 |  |  |  | 2020-12-07
| 6518 | 2020-01-02 | RES/ SIMEC | Glenshero Wind Farm | Wind Onshore |  |  | 168 | n/a |  |  |  | 4.3 | 39 | 135 | n/a | Planning Application Submitted | Application Submitted | Land 3730M NW Of, 1 Garvamore, Laggan, Newtonmore, Highlands | Highland | Scotland | Scotland | PH20 1AJ | 255156 | 793734 | Scottish Government (S36) | ECU00000517 | [5 empty] | 2018-09-28
| 6519 | 2019-09-27 | Cardinghill Renewables | Cardinghill Wind Turbine | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 | 100 | n/a | Planning Permission Refused | Application Refused | Land At, Carding Hill, Ellon, Grampian | Aberdeen | Scotland | Scotland | AB41 8BG | 393896 | 836643 | Aberdeenshire Council | APP/2017/2857 | [5 empty] | 2017-11-21 |  | 2019-07-09
| 6520 | 2017-12-01 | Belisama Energy | Stormy Down Solar Farm | Solar Photovoltaics |  |  | 3.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Stormy Down Transfer Station, Stormy Down, Bridgend | Bridgend | Wales | Wales | CF33 4RS | 284154 | 180554 | Bridgend County Borough Council | P/15/312/FUL | [5 empty] | 2015-05-13 | [6 empty] | 2015-08-27 |  |  |  | 2017-08-27 | 2017-01-27 | 2017-03-27
| 6522 | 2019-02-27 | Innogy | Glasa Hydropower Cascade/Kildermorie Estate | Small Hydro |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Kildermorie Estate, Strathrusdale, Ardross, Alness | Highland | Scotland | Scotland | IV17 0YH | 252096 | 877941 | Highland Council | 18/02414/FUL | [5 empty] | 2018-05-25 | [6 empty] | 2018-11-06
| 6523 | 2019-09-27 | United Utilities Water/ Preston City Council | Clifton Marsh Wastewater Treatment Works | Solar Photovoltaics |  |  | 3.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Clifton Marsh Wastewater Treat, Lytham Road, Clifton, Preston | Lancashire | North West | England | PR4 0XE | 345240 | 428464 | Lancashire County Council | LCC/2017/0090 | [5 empty] | 2017-11-23 | [6 empty] | 2018-12-07 |  |  |  | 2021-12-07 | 2019-01-15 | 2019-08-22
| 6530 | 2019-12-20 | Intelligent Alternatives | White Cross Lane | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land To The North Of, White Cross Lane, Burton Gorse, Sleaford | Lincolnshire | East Midlands | England | NG34 0BN | 509849 | 343309 | North Kesteven District Council | 19/0863/FUL | [5 empty] | 2019-06-18 | [6 empty] | 2019-10-07 |  |  |  | 2022-10-07
| 6532 | 2019-09-27 | United Utilities | Huntington Water Treatment Works | Solar Photovoltaics |  |  | 7.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Huntington Water Treatment Wor, Chester Road, Huntington, Chester | Cheshire | North West | England | CH3 6EA | 342203 | 363955 | Cheshire West and Chester Council | 17/05078/FUL | [5 empty] | 2017-11-28 | [6 empty] | 2018-04-24 |  |  |  | 2021-04-24 | 2019-02-15 | 2019-07-24
| 6535 | 2020-06-24 | Cory Riverside Energy | Riverside Energy Park (REP) | EfW Incineration |  | 7036 | 76 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Norman Rd, Belvedere, Bexley | London | South East | England | DA17 6JY | 549545 | 180595 | DECC (S36) | EN010093 | [5 empty] | 2018-11-16 | [6 empty] | 2020-04-09
| 6538 | 2018-01-03 | Privilege Finance/ BioWatt | Station Works AD | Anaerobic Digestion |  |  | 1 | No |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Station Works Elsenham Road Thaxted CM6 2NG | Essex | Eastern | England | CM6 2NG | 560056 | 230336 | Uttlesford District Council | UTT/1709/10/FUL | [5 empty] | 2010-09-13 | [6 empty] | 2011-01-17 |  |  |  |  | 2011-02-01 | 2012-02-01
| 6539 | 2020-04-29 | Mickram | Cross Banks Road | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Land at Cross Bank Road, Kings Lynn | Norfolk | Eastern | England | PE30 2HD | 561216 | 321368 | Norfolk County Council | C/2/2016/2011 | APP/X2600/W/17/3174764 |  |  |  |  | 2016-08-25 |  | 2017-04-03 | 2017-12-22 |  |  | 2018-04-17 | 2018-04-17 |  |  |  | 2021-04-17
| 6545 | 2020-05-20 | Vento Ludens (formerly Hydroplan) | Allt Garaidh Ghualaich Hydro Scheme Powerhouse | Small Hydro |  |  | 1.08 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land 3520M SW Of, Bothy, Kingie, Invergarry, Highlands | Highland | Scotland | Scotland | PH35 | 215625 | 798782 | Highland Council | 17/05862/FUL | [5 empty] | 2017-12-20 | [6 empty] | 2018-05-23 |  |  |  | 2021-05-23 | 2020-02-01
| 6546 | 2020-03-27 | ABO Wind NI | Armoy Wind Farm | Wind Onshore |  | 7080 | 19.8 | n/a |  |  |  | 3.3 | 6 | 149.9 | n/a | Appeal Refused | Application Refused | Lands approx. 615m East of, 16 Coolkeeran Road, Armoy, 2.5km South East of Armoy, Ballymoney, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT53 8XL | 125543 | 588481 | Northern Ireland Planning Service | LA01/2017/1654/F | 2018/A0199 |  |  |  |  | 2017-12-22 |  | 2018-11-30 | 2019-01-24 |  | 2020-01-08
| 6555 | 2020-04-29 | North Beck Energy (NBE) | North Beck Energy Centre | EfW Incineration |  |  | 49.5 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South Of, Queens Road, Immingham, Humberside | Humberside | Yorkshire and Humber | England | DN40 1QR | 520686 | 414635 | North East Lincolnshire Council | DM/0026/18/FUL | [5 empty] | 2018-01-15 | [6 empty] | 2018-10-12 |  |  |  | 2023-10-12
| 6556 | 2020-07-02 | Innogy (formerly Forewind) | Sofia (Teesside B) | Wind Offshore |  |  | 1400 | n/a |  |  | 1400 | 14 | 100 |  | n/a | Planning Permission Granted | Awaiting Construction | 125km off coast of Yorkshire | Offshore | Offshore | England |  | 675550 | 599192 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2014-03-28 | [6 empty] | 2015-08-05
| 6558 | 2018-02-28 | Thames Water Utilities | Mogden STW | Sewage Sludge Digestion |  |  | 5.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Mogden Lane, Isleworth | Greater London | London | England | TW7 7LR | 515395 | 175228 | Hounslow London Borough Council | 00768/H/P24 | [5 empty] | 2013-07-02 | [6 empty] | 2013-10-14 |  |  |  | 2016-10-14 | 2016-02-21 | 2017-02-21
| 6560 | 2018-10-29 | Halton Borough Council | Former St Michaels Golf Course | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Former St Michaels Golf Course, Ditton Road, Widnes, Cheshire | Cheshire | North West | England | WA8 0NE | 359884 | 385001 | Halton Borough Council | 18/00087/FUL | [5 empty] | 2018-02-23 | [6 empty] | 2018-05-24 |  |  |  | 2021-05-24 | 2020-01-01
| 6561 | 2019-09-27 | Elgin Energy | Cayton Solar farm | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | High Cayton, Water Lane To Cayton, South Stainley, Harrogate, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | HG3 3NB | 429152 | 463684 | Harrogate Borough Council | 19/02259/FULMAJ | [5 empty] | 2019-06-14
| 6562 | 2018-03-01 | Renewable Energy Systems (RES) | Dunbeg South Wind Farm | Wind Onshore |  |  | 29.7 | n/a |  |  |  | 3.3 | 9 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Lands approx 6km N E of, Limavady Road, Derry, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 6 | 90156 | 585774 | Northern Ireland Planning Service | LA01/2018/0200/F | [5 empty] | 2018-02-19
| 6563 | 2020-06-30 | Intelligent Alternatives | Bindwell Lane | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land OS 1100 Bindwell Lane, Queen Camel, Yeovil, Somerset | Somerset | South West | England | BA22 7NB | 360058 | 124101 | South Somerset District Council | 20/00952/FUL | [5 empty] | 2020-03-31
| 6564 | 2019-11-22 | Balmoral Estates/Cairneyhill | Birkhall Estate | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Glen Muick, Birkhall Ballater, Balmoral Estates, Ballater, Grampian | Aberdeen | Scotland | Scotland | AB35 5TB | 334413 | 790888 | Cairngorms National Park Authority | 2018/0063/DET | [5 empty] | 2018-02-08 | [6 empty] | 2018-07-03 |  |  |  | 2021-07-03 | 2018-10-01
| 6569 | 2019-12-18 | Intelligent Alternatives | Higher Farm | Solar Photovoltaics |  |  | 11 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Lodged | Application Refused | Land At E 378449 N 121922, Fifehead Magdalen, Higher Farm Fifehead, Gillingham, Dorset | Dorset | South West | England | SP8 5RR | 378241 | 121816 | North Dorset District Council | 2/2019/0470/FUL | 3241953 |  |  |  |  | 2019-04-01 |  | 2019-10-14 | 2019-11-26
| 6571 | 2018-10-02 | Sirius Renewable Energy | Pen-Y-Fan Industrial Estate | Wind Onshore |  |  | 1.75 | n/a |  |  |  | 1.75 | 1 | 113 | n/a | Planning Permission Refused | Application Refused | Unit 4, Durisol UK, Parkway, Pen-Y-Fan Industrial Estate, Newport, Gwent | Caerphilly | Wales | Wales | NP11 3EF | 319930 | 200123 | Caerphilly County Borough Council | 17/0864/FULL | [5 empty] | 2017-10-09 |  | 2018-09-13
| 6572 | 2018-12-18 | Connaught Wind | Connaught Road | Wind Onshore |  |  | 1.6 | n/a |  |  |  | 0.8 | 2 | 76.5 | n/a | Appeal Refused | Application Refused | 36a Connaught Road, Randalstown, Antrim, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT41 2NX | 123206 | 549605 | Northern Ireland Planning Service | LA03/2017/0945/F | 2018/E0026 |  |  |  |  | 2018-01-12 |  | 2018-01-12 | 2018-08-03 |  | 2018-12-11
| 6577 | 2019-06-25 | Fred Olsen Renewables | Fetteresso Wind Farm (Mid Hill 3) | Wind Onshore |  |  | 40 | n/a |  |  |  | 4 | 10 | 200 | n/a | Planning Application Submitted | Application Submitted | Fetteresso, Stonehaven | Grampian | Scotland | Scotland |  | 378976 | 785963 | Scottish Government (S36) | ECU00001851 | [5 empty] | 2019-06-03
| 6578 | 2018-03-28 | Pretoria Energy Company | Mepal CHP | Anaerobic Digestion |  |  | 14.4 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Land Of Iretons Way, Mepal | Cambridgeshire | Eastern | England | CB6 2AZ | 542047 | 283203 | Fenland District Council | F/YR14/0163/F | [5 empty] | 2014-02-27 | [6 empty] | 2014-07-11 |  |  |  | 2017-07-11 | 2016-09-17 | 2017-03-17
| 6580 | 2020-06-11 | Elgin Energy | High Green | Solar Photovoltaics |  |  | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Appeal Granted | Awaiting Construction | Land To The East Of High Green, Longney, Gloucester, Gloucestershire | Gloucestershire | South West | England | GL2 3SH | 377569 | 212155 | Stroud District Council | S.18/0537/FUL | APP/C1625/W/19/3229860 |  |  |  |  | 2018-03-05 |  | 2018-11-30 | 2019-05-29 |  |  | 2019-09-26 | 2019-09-26
| 6581 | 2019-09-25 | Dwr Cymru Welsh Water | Llanasa Waste Treatment Works | Solar Photovoltaics |  |  | 0.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Llanasa Waste Treatment Works, Ffynnongroyw, Gwespyr, Holywell, Clwyd | Flintshire | Wales | Wales | CH8 9JP | 312268 | 384037 | Flintshire County Council | 59395 | [5 empty] | 2019-01-25 | 2019-04-23
| 6585 | 2019-05-23 | Cloffrickford Renewable Energy | Skelmonae Farm | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Skelmonae Farm, Methlick, Ellon, Grampian | Aberdeen | Scotland | Scotland | AB41 7 | 388690 | 839555 | Aberdeenshire Council | APP/2018/0362 | [5 empty] | 2018-02-28 | [6 empty] | 2018-04-27 |  |  |  | 2021-04-27
| 6588 | 2020-06-11 | Elgin Energy | High Parkfoot Farm | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at High Park Foot Farm, Roadhead, Carlisle, Cumbria | Cumbria | North West | England | CA6 6NH | 350872 | 573673 | Carlisle City Council | 18/0197 | [5 empty] | 2018-03-12 | [6 empty] | 2018-06-22 |  |  |  | 2021-06-22
| 6590 | 2020-06-04 | Element Power | Twentyshilling Hill Wind Farm (resubmission) | Wind Onshore |  |  | 36 | n/a |  |  |  | 4 | 9 | 140 | n/a | Planning Permission Granted | Awaiting Construction | Twentyshilling Hill Wind Farm, Greystone Avenue, Kelloholm, Sanquhar, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG4 6RY | 279500 | 604500 | Dumfries and Galloway Council | 18/0206/FUL | [5 empty] | 2018-02-22 | [6 empty] | 2019-12-23 |  |  |  | 2022-12-22
| 6591 | 2018-10-24 | Gnaton Farm | Creacombe Solar Farm | Solar Photovoltaics |  |  | 7.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Creacombe Farm, Yealmpton, Plymouth, Devon | Devon | South West | England | PL8 2JA | 259443 | 50013 | South Hams District Council | 1109/17/FUL | [5 empty] | 2017-04-24 | [6 empty] | 2018-03-30 |  |  |  | 2021-03-30 | 2019-09-05
| 6592 | 2019-12-06 | J Pointon & Sons Ltd | Cheddleton Industrial Estate | Biomass (dedicated) |  |  | 6.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | John Pointon and Sons, Felthouse Lane, Cheddleton, Leek, Staffordshire | Staffordshire | West Midlands | England | ST13 7BT | 397308 | 350565 | Staffordshire Moorlands District Council | SM.17/02/1138 W | [5 empty] | 2017-04-04 | [6 empty] | 2017-12-21 |  |  |  | 2021-12-21
| 6593 | 2019-09-13 | Dwr Cymru Welsh Water | Sluvad Road Water Treatment Works | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Abandoned | Abandoned | Trem Y Ffynnon, Sluvad Road, New Inn Pontypool, Torfaen, Pontypool, Gwent | Torfaen | Wales | Wales | NP4 0TA | 332013 | 199276 | Torfaen County Borough Council | 18/P/0707/FUL | [5 empty] | 2018-10-26 | [6 empty] | 2019-03-29 |  |  |  | 2024-03-29
| 6594 | 2020-06-11 | Elgin Energy | Cordon Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land 400 Metres North Of Cordon Farmhouse, Abernethy | Perth and Kinross | Scotland | Scotland | PH2 9LN | 318335 | 717885 | Perth and Kinross Council | 17/00487/FLL | [5 empty] | 2017-03-20 | [6 empty] | 2017-06-30
| 6595 | 2019-03-20 | Magallanes Renovables | Magallanes (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | EMEC, Fall of Warness, Eday, Orkney | Orkney Islands | Offshore | Scotland |  | 354000 | 1028400 | Scottish Government (S36) | [6 empty] | 2018-04-01 | [6 empty] | 2018-04-25 |  |  |  |  | 2018-09-15 | 2019-03-05
| 6600 | 2020-04-02 | EDF Energy | Stranoch 2 | Wind Onshore |  |  | 84 | n/a |  |  |  |  | 20 | 175 | n/a | Planning Application Submitted | Application Submitted | New Luce, Newton Stewart, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland |  | 215493 | 571022 | Scottish Government (S36) | ECU00000710 | [5 empty] | 2018-10-18
| 6601 | 2018-04-05 | GFG Alliance | Lochaber | Large Hydro |  |  | 65 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Fort William | Highland | Scotland | Scotland |  | 212621 | 775052 | Scottish Government (S36) | [18 empty] | 1924-01-01 | 1929-01-01
| 6603 | 2019-01-24 | Cranfield Univsersity | Cranfield Airfield | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Cranfield Airfield, College Road, Cranfield | Bedfordshire | Eastern | England | MK43 0DL | 495240 | 241889 | Central Bedfordshire Council | CB/17/04925/FULL | [5 empty] | 2017-10-12 | [6 empty] | 2018-01-05 |  |  |  |  | 2018-02-20 | 2018-09-01
| 6605 | 2019-12-03 | Endless Energy/Halton Homes | Former Gas Works, Aire Valley Road | EfW Incineration |  |  | 10 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Former Gas Works Site, Airedale Road, Keighley | West Yorkshire | Yorkshire and Humber | England | BD21 4LW | 407528 | 441612 | Bradford Metropolitan District Council | 16/06857/FUL | [5 empty] | 2016-08-11 | [6 empty] | 2017-04-11 |  |  |  | 2020-04-11
| 6606 | 2019-04-17 | OpenHydro | Open Centre Turbines (FoW - EMEC) | Tidal Barrage and Tidal Stream |  |  | 2.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Fall of Warness, Eday, Orkney | Orkney Islands | Offshore | Scotland |  | 314195 | 1009356 | Marine Scotland | [6 empty] | 2016-09-15 | [6 empty] | 2017-04-15
| 6607 | 2019-12-18 | Brockwell Energy | North Kyle Energy Project | Wind Onshore |  |  | 226.8 | n/a |  |  |  | 4.2 | 54 | 149.9 | n/a | Planning Application Submitted | Application Submitted | North Kyle Forest in East Ayrshire | Strathclyde | Scotland | Scotland |  | 250488 | 608948 | Scottish Government (S36) | ECU00001950 | [5 empty] | 2019-09-27
| 6611 | 2019-09-24 | Menter Mon Morlais | Morlais Demonstration Zone | Tidal Barrage and Tidal Stream |  |  | 240 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | West Anglesey Demonstration Zone, proximity of Holy Island | Isle of Anglesey | Wales | Wales |  | 218907 | 381977 | Welsh Government (NSIP) | TWA/3234121 | [5 empty] | 2019-09-19
| 6617 | 2019-04-01 | Solar 21 Renewable Energy | Melton Waste Park | EfW Incineration |  |  | 22 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South West Of Melton Wast, Gibson Lane, Melton, North Ferriby, Humberside | Humberside | Yorkshire and Humber | England | HU14 3HH | 497008 | 426253 | East Riding of Yorkshire Council | 18/00703/CM | [5 empty] | 2018-04-10 | [6 empty] | 2019-02-28 |  |  |  | 2022-02-28
| 6624 | 2020-06-30 | Leicestershire County Council | Pool Farm | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Pool Farm, Barrow Road, Quorn, Loughborough, Leicestershire | Leicestershire | East Midlands | England | LE12 8EN | 456147 | 317552 | Leicestershire County Council | 2020/REG3MA/0057/LCC | [5 empty] | 2020-05-05
| 6626 | 2018-05-30 | Broadley Energy | Broadley Copse | Anaerobic Digestion |  |  | 2.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Broadley Copse Farm, Downs Road, Funtington, Chichester | Hampshire | South East | England | PO18 9BT | 481091 | 108860 | South Downs National Park Authority | SDNP/15/04189/FUL | [5 empty] | 2015-08-18 | [6 empty] | 2016-04-06 |  |  |  | 2019-04-06 | 2017-03-24 | 2018-03-24
| 6629 | 2019-03-26 | Community Windpower | Sanquhar II Community Wind Farm | Wind Onshore |  |  | 350 | n/a |  |  |  | 7 | 50 | 220 | n/a | Planning Application Submitted | Application Submitted | Sanquhar II Wind Farm 7.5km So, New Cumnock, Kirkconnel, Sanquhar, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG4 6AA | 268554 | 603493 | Scottish Government (S36) | ECU00001801 | [5 empty] | 2019-03-21
| 6630 | 2019-04-01 | Great Coates Energy | Moody Lane (Former Acordis site) Resubmission | EfW Incineration |  |  | 18 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Former Acordis site, Energy Park Way, Moody Lane, Healing, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN31 2TT | 523376 | 412410 | North East Lincolnshire Council | DM/0329/18/FUL | [5 empty] | 2018-04-26 | [6 empty] | 2019-01-30 |  |  |  | 2022-01-30
| 6634 | 2019-07-02 | Coriolis Energy | Kirkan Wind Farm | Wind Onshore |  |  | 91.2 | n/a |  |  |  | 4.8 | 19 | 175 | n/a | Planning Application Submitted | Application Submitted | Land 3015M SE Of Aultguish Inn, Garve, Highlands | Highland | Scotland | Scotland | IV23 | 245959 | 865205 | Scottish Government (S36) | ECU00001800 | [5 empty] | 2019-03-14
| 6636 | 2018-06-04 | Renewable Energy Systems (RES) | Forss Wind Farm | Wind Onshore |  |  | 2.6 | n/a |  |  |  | 1.3 | 2 | 99 | n/a | Operational | Operational | Wind Turbine Ex Navy Base Forss Dounreay Thurso Caithness | Highland | Scotland | Scotland | KW14 7YB | 302000 | 969500 | Highland Council | 01/00030/FULCA | [5 empty] | 2001-01-12 | [6 empty] | 2001-06-22 |  |  |  |  | 2003-01-01 | 2003-07-01
| 6637 | 2019-07-02 | Nova Innovation | Shetland Tidal Array | Tidal Barrage and Tidal Stream |  |  | 0.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Bluemull Sound, Shetland, Scotland | Shetland | Offshore | Scotland |  | 440389 | 1183121 | Marine Scotland | [6 empty] | 2018-02-01 | [6 empty] | 2018-04-15 |  |  |  |  | 2017-06-24 | 2019-06-24
| 6638 | 2018-07-02 | Black Dog Biogas | Greenhill Anaerobic Digestion Plant | Anaerobic Digestion |  |  | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Stag Lane Anaerobic Digestion Plant, Stag Lane, Newport | Isle of Wight | South East | England | PO30 5TS | 450243 | 91601 | Isle of Wight Council | P/01378/12 | [5 empty] | 2012-09-17 | [6 empty] | 2013-05-02 |  |  |  | 2013-05-02 | 2015-10-10 | 2016-10-10
| 6645 | 2020-05-28 | BayWa r.e. (formerly Forsa) | Druim Leathann (resubmission) | Wind Onshore |  |  | 49.7 | n/a |  |  | 49.5 | 3.3 | 14 | 126.5 | n/a | Planning Permission Granted | Awaiting Construction | Druim Leathann Windfarm North, Lochside, North Tolsta, Isle Of Lewis, Western Isles | Comhairle nan Eilean Siar | Scotland | Scotland | HS2 0NF | 151403 | 947774 | Comhairle nan Eilean Siar Council | 17/00282/PPDM | [5 empty] | 2017-06-02 | [6 empty] | 2018-02-16 |  |  |  | 2023-02-16
| 6646 | 2020-05-20 | MPG Wind | Cloghfin Road | Wind Onshore |  |  | 4.8 | n/a |  |  |  | 1.6 | 3 | 100 | n/a | Planning Permission Granted | Awaiting Construction | Lands 487M NE 405M NE and 569M, 190 Cloghfin Road, Sixmilecross, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 9EQ | 76152 | 526561 | Northern Ireland Planning Service | LA10/2018/0763/F | [5 empty] | 2018-06-19 | [6 empty] | 2019-04-17 |  |  |  | 2024-04-15
| 6647 | 2019-12-06 | Sycamore Planning | Decoy Farm | Biomass (dedicated) |  |  | 1.5 | yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Decoy Farm, Spalding Road, Crowland, Peterborough, Cambridgeshire | Lincolnshire | East Midlands | England | PE6 0LX | 525601 | 312745 | Lincolnshire County Council | PL/0058/18 | [5 empty] | 2018-06-11 | [6 empty] | 2018-09-05 |  |  |  | 2021-09-05
| 6649 | 2019-10-31 | Morvern Community | Barr River, Loch Teacuis | Small Hydro |  |  | 1.65 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land 3370M West Of Ardantiobai, Morvern, Acharacle, Strathclyde | Highland | Scotland | Scotland | PH36 4JA | 161763 | 755977 | Highland Council | 18/04708/FUL | [5 empty] | 2018-09-10 | [6 empty] | 2019-02-12 |  |  |  | 2022-02-12
| 6655 | 2018-12-18 | J.M. Stratton and Co Ltd | East Farm (Clay Pit Hill) - Extension II | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Clay Pit Hill Codford Down Eas, Church Lane, Codford, Warminster, Wiltshire | Wiltshire | South West | England | BA12 0PJ | 397619 | 139793 | Wiltshire Council | 18/03167/FUL | [5 empty] | 2018-04-24 | 2018-12-01
| 6656 | 2019-02-19 | Knapton Green Energy (Tetragen and NCG Estates) | Land to the South of Knapton Quarry Landfill Site | EfW Incineration |  |  | 8 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Landfill Site Knapton Quarry, East Knapton, Malton, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO17 8JA | 488845 | 475039 | North Yorkshire County Council | NY/2016/0194/ENV | [5 empty] | 2016-11-14 | [6 empty] | 2018-08-01
| 6657 | 2020-01-15 | Dickins Hydro Resources | Allt Charnan | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Glen Etive Estate, Glenetive, Ballachulish, Strathclyde | Highland | Scotland | Scotland | PH49 4JA | 214370 | 748440 | Highland Council | 18/02738/FUL | [5 empty] | 2018-06-15 | [6 empty] | 2019-03-05 |  |  |  | 2022-03-05
| 6659 | 2018-09-03 | Drax Power | Drax Biomass Power Station - Unit 4 | Biomass (dedicated) |  |  | 645 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Near Selby in North Yorkshire | North Yorkshire | Yorkshire and Humber | England |  | 466650 | 427050 | The Planning Inspectorate - National Infrastructure | [18 empty] | 2018-06-06 | 2018-08-21
| 6660 | 2019-11-26 | Cardiff Council | Lamby Way Solar Farm | Solar Photovoltaics |  |  | 8.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Former Lamby Way landfill site, Lamby Way, Rumney, Cardiff, South Glamorgan | Cardiff | Wales | Wales | CF3 2HP | 321925 | 177854 | Cardiff Council | 19/00397/MJR | [5 empty] | 2019-02-22 | [6 empty] | 2019-05-16 |  |  |  | 2024-05-16 | 2019-11-26
| 6664 | 2019-12-06 | Green Cat Renewables | Binn Eco Park Wind Farm (resubmission) | Wind Onshore |  |  | 10 | n/a |  |  |  | 2.3 | 4 | 124 | n/a | Planning Permission Refused | Application Refused | Binn Eco Park Wind Farm, Glenfarg, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 9PX | 317830 | 713430 | Perth and Kinross Council | 18/00865/FLL | [5 empty] | 2018-05-21 |  | 2019-04-10
| 6665 | 2020-06-04 | Stornoway Wind Farm (SWL), Lewis Wind Power | Stornoway Wind Farm (second resubmission) | Wind Onshore |  |  | 196 | n/a |  |  |  | 5.6 | 35 | 180 | n/a | Planning Application Submitted | Application Submitted | North Lewis, Isle of Lewis | Western Isles | Scotland | Scotland |  | 142695 | 934003 | Scottish Government (S36) | ECU00001850 | [5 empty] | 2019-05-22
| 6670 | 2019-11-04 | Eggborough Power (EP SHB) | South Humber Bank Energy Centre | EfW Incineration |  |  | 49.9 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Rear Of Power Station, Hobson Way, Stallingborough, North East Lincolnshire | Humberside | Yorkshire and Humber | England | DN41 8BZ | 522769 | 413413 | North East Lincolnshire Council | DM/1070/18/FUL | [5 empty] | 2018-12-21 | [6 empty] | 2019-04-12 |  |  |  | 2022-04-12
| 6673 | 2019-06-28 | Aquatera | Sandwick East Community Wind Farm | Wind Onshore |  |  | 49.9 | n/a |  |  |  | 5 | 10 | 145 | n/a | Planning Application Submitted | Application Submitted | Sandwick East Street, Pentland Road To Achmore, Achmore, Isle Of Lewis, Western Isles | Comhairle nan Eilean Siar | Scotland | Scotland | HS2 9DU | 131345 | 929229 | Comhairle nan Eilean Siar Council | 9/00189/PPDM | [5 empty] | 2019-04-29
| 6675 | 2020-01-15 | Dickins Hydro Resources | Glen Etive Estate Phase I (Allt na Chaorainn) | Small Hydro |  |  | 1.36 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Dalness Estate, Glenetive, Ballachulish, Strathclyde | Highland | Scotland | Scotland | PH49 4JA | 219630 | 751060 | Highland Council | 18/02742/FUL | [5 empty] | 2018-06-16 | [6 empty] | 2019-03-22 |  |  |  | 2022-03-22
| 6676 | 2020-01-15 | Dickins Hydro Resources | Glen Etive Estate Phase II (Allt Mheuran & Allt na Meirleach) | Small Hydro |  |  | 0.885 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Allt Mheuran Glen Etive Estate, Glenetive, Ballachulish, Strathclyde | Highland | Scotland | Scotland | PH49 4JA | 213510 | 746040 | Highland Council | 18/05440/FUL | [5 empty] | 2018-11-28 | [6 empty] | 2019-03-22 |  |  |  | 2022-03-22
| 6683 | 2018-09-01 | Pinguin Foods UK | Chamber 16 (Cold Store) | Solar Photovoltaics |  |  | 1.2 | N/A |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Pinguin Foods, Scania Way, Kings Lynn | Norfolk | Eastern | England | PE30 4LR | 563499 | 318540 | Permitted Development | [18 empty] | 2016-01-07 | 2016-06-07
| 6684 | 2019-09-27 | Glen Hydro Development | Chailleach Hydro | Small Hydro |  |  | 1.7 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land 2100M East Of Murlaggan, Achnacarry, Spean Bridge, Highlands | Highland | Scotland | Scotland | PH34 4EL | 203172 | 792453 | Highland Council | 18/03860/FUL | [5 empty] | 2018-08-17 | 2019-02-11
| 6687 | 2020-04-29 | Simec/Green Highland Renewables | Glen Kinglass | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Allt Hallater Hydro Glen, Kinglass Argyll And Bute, Taynuilt, Strathclyde | Argyll and Bute | Scotland | Scotland | PA35 1JU | 215301 | 737604 | Argyll and Bute Council | 18/01258/PP | [5 empty] | 2018-08-01 | [6 empty] | 2019-03-28 |  |  |  | 2022-03-28 | 2019-12-01
| 6690 | 2020-06-30 | Green Highland Renewables/ SIMEC | Fort William Tail Race | Small Hydro |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land 110M SW Of Old Inverlochy, North Road, Fort William, Highlands | Highland | Scotland | Scotland | PH33 6TF | 211851 | 775367 | Highland Council | 19/00086/FUL | [5 empty] | 2019-01-10 |  | 2020-05-13
| 6696 | 2020-02-04 | Amazon UK Services / Push Energy | Amazon LBA2 (Principal Place) | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Unit 2a, Ontario Drive, New Rossington, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | DN11 0B | 459605 | 399059 | Doncaster Council | 18/01797/FULM | [5 empty] | 2018-07-18 | [6 empty] | 2018-08-31 |  |  |  | 2021-08-31
| 6700 | 2020-06-30 | Low Carbon | Terriers Farm | Solar Photovoltaics |  |  | 44 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Terriers Farm, Boyton End, Thaxted, Dunmow, Essex | Essex | Eastern | England | CM6 2RD | 562574 | 232044 | Uttlesford District Council | UTT/19/1864/FUL | [5 empty] | 2019-07-31 | [6 empty] | 2020-06-25 |  |  |  | 2023-06-25
| 6701 | 2020-06-11 | Elgin Energy Esco | Gorse Lane | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land South Of, Gorse Lane, Silk Willoughby, Sleaford, Lincolnshire | Lincolnshire | East Midlands | England | NG34 8PF | 506662 | 342377 | North Kesteven District Council | 19/0060/FUL | [5 empty] | 2019-01-15 | [6 empty] | 2019-04-11 |  |  |  | 2022-04-11
| 6703 | 2019-10-01 | ERG | Sandy Knowe Wind Farm (S.36 resubmission) | Wind Onshore |  |  | 81.6 | N/A |  |  |  | 3.4 | 24 | 125 | n/a | Planning Application Submitted | Application Submitted | Site Art Libry Moor, Locharbriggs, By Kirkconnel and Kelloholm, Dumfries | Dumfries and Galloway | Scotland | Scotland | DG1 1QF | 270100 | 610600 | Scottish Government (S36) | ECU00000660 | [5 empty] | 2018-08-16
| 6708 | 2019-12-20 | Brockwell Energy | Broken Cross (Former Surface Mine) | Wind Onshore |  |  | 40 | n/a |  |  |  | 4 | 10 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Former Surface Mine, Tower Road, Douglas, Broken Cross, Lanark, Strathclyde | South Lanarkshire | Scotland | Scotland | ML11 9PB | 285677 | 636040 | South Lanarkshire Council | P/19/1636 | [5 empty] | 2019-10-30
| 6711 | 2020-02-04 | Amazon UK Services / Push Energy | Boscombe Road (Unit DC1) | Solar Photovoltaics |  |  | 1.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Dc1, Boscombe Road, Dunstable, Bedfordshire | Bedfordshire | Eastern | England | LU5 4FE | 502851 | 222456 | Central Bedfordshire Council | CB/18/02801/FULL | [5 empty] | 2018-08-29 | [6 empty] | 2018-10-24 |  |  |  | 2021-10-24
| 6712 | 2020-02-04 | Amazon UK Services / Push Energy | Kingston Park | Solar Photovoltaics |  |  | 1.788 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Unit 2, Kingston Park, Peterborough, Cambridgeshire | Cambridgeshire | Eastern | England | PE2 9EN | 519579 | 295251 | Peterborough City Council | 18/01311/FUL | [5 empty] | 2018-07-19 | [6 empty] | 2018-11-13 |  |  |  | 2021-11-13
| 6715 | 2020-02-04 | Amazon UK Services / Push Energy | Amazon - BHX2 | Solar Photovoltaics |  |  | 3.7 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Amazon Services UK Ltd - BHX2, Beveridge Lane, Ellistown, Coalville, Leicestershire | Leicestershire | East Midlands | England | LE67 1FB | 443894 | 311290 | North West Leicestershire District Council | 18/01437/FULM | [5 empty] | 2018-08-29 | [6 empty] | 2018-10-16 |  |  |  | 2021-10-16
| 6716 | 2020-06-30 | Lightsource BP | Saputo Dairy UK | Solar Photovoltaics |  | 7950 | 4.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Dairy Crest Ltd, Blacka Lane, Davidstow, Camelford, Cornwall | Cornwall | South West | England | PL32 9XW | 213675 | 86266 | Cornwall Council | PA20/02612 | [5 empty] | 2020-04-29
| 6720 | 2020-06-30 | Vattenfall | Swinford Wind Farm | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Swinford Corner, Lutterworth Road, Swinford, Lutterworth, Leicestershire | Leicestershire | East Midlands | England | LE17 6AU | 456834 | 279582 | Harborough District Council | 19/01853/FUL | [5 empty] | 2019-12-16 | [6 empty] | 2020-05-04 |  |  |  | 2023-05-04
| 6722 | 2020-05-20 | Dacorar Southern | Goddard's Green | Solar Photovoltaics |  |  | 4.42 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land To The North Of The A2300, Cuckfield Road, Ansty, Haywards Heath, West Sussex | West Sussex | South East | England | RH17 5A | 528427 | 120656 | Mid Sussex District Council | DM/18/3617 | [5 empty] | 2018-08-30 | [6 empty] | 2018-12-19 |  |  |  | 2021-12-19
| 6723 | 2020-02-04 | Amazon UK Services/ Push Energy | Tilbury LCY2 | Solar Photovoltaics |  |  | 4 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | London Distribution Park, Windrush Road, Tilbury, Essex | Essex | Eastern | England | RM18 7AN | 563536 | 176914 | Thurrock Council | 18/01114/FUL | [5 empty] | 2018-08-07 | [6 empty] | 2018-10-29 |  |  |  | 2021-10-29
| 6724 | 2020-05-20 | Green Highland Renewables | Allt Easach Hydro | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land West Of Allt, Lochetive, Argyll And Bute, Taynuilt, Strathclyde | Argyll and Bute | Scotland | Scotland | PA35 1 | 206993 | 739515 | Argyll and Bute Council | 18/01257/PP | [5 empty] | 2018-06-08 | [6 empty] | 2019-03-15 |  |  |  | 2022-03-15
| 6725 | 2018-10-02 | Cenin Renewables | Llwyncelyn Wind Farm - Resubmission | Wind Onshore |  |  | 7.2 | n/a |  |  |  | 3.6 | 2 | 138.5 | n/a | Planning Application Submitted | Application Submitted | Llwyncelyn Farm, Hafod Lane, Porth, Mid Glamorgan | Rhondda Cynon Taff | Wales | Wales | CF39 9UE | 303627 | 192833 | Rhondda Cynon Taff County Borough Council | 18/0877/10 | [5 empty] | 2018-08-01
| 6726 | 2020-02-04 | Amazon UK Services/ Push Energy | Dunfermline EDI4 | Solar Photovoltaics |  |  | 1.9 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Amazon Management Office, Amazon Way, Dunfermline, Dunfermline, Fife | Fife | Scotland | Scotland | KY11 8XT | 313506 | 686540 | Fife Council | 18/02244/FULL | [5 empty] | 2018-08-06 | [6 empty] | 2018-10-26 |  |  |  | 2021-10-26
| 6728 | 2020-06-18 | EnergieKontor UK | Lairg Wind Farm Extension (Lairg 2) | Wind Onshore |  |  | 34.5 | n/a |  |  |  | 3.45 | 10 | 179 | n/a | Planning Permission Granted | Awaiting Construction | Land 100M SE Of 104 Torroble, Lairg, Highlands | Highland | Scotland | Scotland | IV27 | 259717 | 902222 | Highland Council | 19/01096/FUL | [5 empty] | 2019-03-18 | [6 empty] | 2020-06-19
| 6730 | 2020-04-29 | SIMEC Green Highland Renewables | Blackwater Dam | Small Hydro |  |  | 0.8 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Blackwater Dam East Of Kinloch, Glencoe, Ballachulish, Strathclyde | Highland | Scotland | Scotland | PH50 4QW | 224709 | 760249 | Highland Council | 18/05815/FUL | [5 empty] | 2019-01-08 | [6 empty] | 2019-03-29 |  |  |  | 2022-03-29
| 6731 | 2018-10-03 | SIMEC/ Liberty House | Liberty Steel Dalzell | Biomass (dedicated) |  |  | 17 |  |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Liberty Steel Dalzell, Park Street, Motherwell | North Lanarkshire | Scotland | Scotland | ML1 1PU | 275801 | 656790 | North Lanarkshire Council | [18 empty] | 2016-03-30 | 2017-03-30
| 6733 | 2020-06-24 | Scottish & Southern (SSE) | Cloiche Wind Farm | Wind Onshore |  |  | 150 | n/a |  |  |  | 4.17 | 36 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Glendoe and Garrogie Estates, Monadhliath Mountains, 11km south-east of Fort Augustus and 14km west of Newtonmore | Highland | Scotland | Scotland | IV2 6UP | 246861 | 813520 | Scottish Government (S36) | ECU00002054 | [5 empty] | 2020-04-28
| 6734 | 2020-05-28 | Scottish & Southern (SSE) | Tangy 4 Wind Farm | Wind Onshore |  |  | 80 | n/a |  |  |  | 5 | 16 | 149.9 | n/a | Planning Permission Granted | Awaiting Construction | Tangy, Kilkenzie, Campbeltown, Argyll And Bute | Argyll and Bute | Scotland | Scotland | PA28 6QD | 168500 | 628500 | Scottish Government (S36) | ECU00000673 | [5 empty] | 2018-09-06 | [6 empty] | 2019-12-20
| 6736 | 2020-04-29 | Green Energy International | Bilbo Solar Farm | Solar Photovoltaics |  |  | 36.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Bilbo Solar Farm, Moss-side, Crimond, Fraserburgh, Grampian | Aberdeen | Scotland | Scotland | AB43 8QJ | 405327 | 855492 | Aberdeenshire Council | APP/2019/0296 | [5 empty] | 2019-06-26 | [6 empty] | 2019-09-20
| 6737 | 2019-04-01 | Private Developer | Pont Yr River | Small Hydro |  |  | 0.6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land Near Pont Yr, Afon Gam, Blaenau Ffestiniog, Gwynedd | Conwy | Wales | Wales | LL41 4PT | 272444 | 341208 | Snowdonia National Park Authority | NP5/59/495A | [5 empty] | 2018-10-19 |  | 2018-11-26
| 6738 | 2019-06-28 | Hay Hall Bio Power | Hay Hall Road Energy Recovery Facility | Advanced Conversion Technologies |  |  | 25 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Off Hay Hall Road, Birmingham, West Midlands | West Midlands | West Midlands | England | B11 2AU | 411023 | 284169 | Birmingham City Council | 2018/09425/PA | [5 empty] | 2018-11-20 | [6 empty] | 2019-02-28 |  |  |  | 2022-02-28
| 6739 | 2019-06-28 | Private Developer | Crockanboy Road (resubmission) | Wind Onshore |  |  | 4.2 | n/a |  |  |  | 4.2 | 1 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | Land approx. 880m NE of, 128 Crockanboy Road, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 7RS | 69965 | 547528 | Fermanagh and Omagh | LA10/2018/1476/F | [5 empty] | 2018-11-20 | 2019-04-19
| 6741 | 2019-11-20 | H2O Power Generation | Duror 2 Hydro Scheme | Small Hydro |  |  | 0.35 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land 330M SE Of, Birch View, Auchindarroch Duror, Appin, Strathclyde | Highland | Scotland | Scotland | PA38 4BS | 200566 | 754831 | Highland Council | 18/05283/FUL | [5 empty] | 2018-11-16 | [6 empty] | 2019-03-06 |  |  |  | 2022-03-06
| 6742 | 2020-05-21 | Renishaw Group | Building F, Renishaw Factory | Solar Photovoltaics |  |  | 0.212 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Building F Renishaw PLC, New Mills, Wotton-Under-Edge, Gloucestershire | Gloucestershire | South West | England | GL12 8JR | 373718 | 193008 | Stroud District Council | S.18/2463/FUL | [5 empty] | 2018-11-13 | [6 empty] | 2018-12-21 |  |  |  | 2023-12-21 | 2019-10-01 | 2020-04-01
| 6744 | 2020-03-23 | Bristol Energy Cooperative | Netham Weir | Small Hydro |  |  | 0.36 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Rear Of, St Vincents Trading Estate, Feeder Road, Bristol, Avon | Avon | South West | England | BS2 0UY | 361519 | 172592 | Bristol City Council | 18/05891/F | [5 empty] | 2018-11-16 | [6 empty] | 2019-03-29 |  |  |  | 2022-03-29
| 6745 | 2020-05-20 | Scottish Water | Finmont Service Reservoir | Solar Photovoltaics |  |  | 0.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Finmont Reservoir, Kinglassie Road, Glenrothes, Lochgelly, Fife | Fife | Scotland | Scotland | KY5 0NL | 323203 | 699536 | Fife Council | 18/02956/FULL | [5 empty] | 2018-12-11 | [6 empty] | 2019-01-23 |  |  |  | 2022-01-23 | 2020-03-01
| 6746 | 2019-08-14 | Private Developer | Killail Farm | Small Hydro |  |  | 0.15 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South East Of Killail Far, Otter Ferry, Tighnabruaich, Strathclyde | Argyll and Bute | Scotland | Scotland | PA21 2DH | 193443 | 684327 | Argyll and Bute Council | 18/02445/PP | [5 empty] | 2018-11-14 | [6 empty] | 2019-03-04 |  |  |  | 2022-03-04
| 6747 | 2019-08-14 | Private Developer | Dingle Farm | Biomass (dedicated) |  |  | 0.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Dingle Farm Industrial Estate, Vicarage Lane, Newton, Preston, Lancashire | Lancashire | North West | England | PR4 3RX | 345386 | 431543 | Fylde Borough Council | 18/0664 | [5 empty] | 2018-09-19 | [6 empty] | 2018-11-16 |  |  |  | 2021-11-16
| 6748 | 2019-12-10 | Codemaster Software Co | Lower Farm | Solar Photovoltaics |  |  | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Lower Farm, Southam Road, Southam, Warwickshire | Warwickshire | West Midlands | England | CV47 2DL | 439656 | 261797 | Stratford on Avon District Council | 18/03187/FUL | [5 empty] | 2018-10-29 | [6 empty] | 2019-06-26 |  |  |  | 2022-06-26 | 2019-10-15
| 6750 | 2018-12-03 | Peel Energy | John Lennon Airport Scheme | Solar Photovoltaics |  |  | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | East Of Liverpool John Lennon, Hale Road, Baileys Lane, Dungeon Lane, Liverpool, Merseyside | Cheshire | North West | England | L24 7SD | 344958 | 382511 | Halton Borough Council | 18/00513/FUL | [5 empty] | 2018-10-16 | 2019-06-27
| 6752 | 2020-05-21 | Renishaw Group | Renishaw PLC Factory | Solar Photovoltaics |  |  | 0.804 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Renishaw PLC, Brunel Way, Stroudwater Business Park, Stonehouse, Gloucestershire | Gloucestershire | South West | England | GL10 3SX | 379562 | 206053 | Stroud District Council | S.18/2399/FUL | [5 empty] | 2018-06-11 | [6 empty] | 2018-12-21 |  |  |  | 2021-12-21 | 2019-10-01 | 2020-04-01
| 6753 | 2020-03-31 | Dover Yard | Oldhall Industrial Estate | EfW Incineration |  |  | 15 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 16 - 20 Murdoch Place, Oldhall West Industrial Estate, Irvine, Strathclyde | North Ayrshire | Scotland | Scotland | KA11 5DG | 233712 | 636561 | North Ayrshire Council | 19/00539/PPM | [5 empty] | 2019-07-29 | [6 empty] | 2020-01-22 |  |  |  | 2023-01-22
| 6755 | 2020-03-31 | Cleanearth | Land at Tacher | Wind Onshore |  |  | 4.3 | n/a |  |  |  | 4.3 | 1 | 145 | n/a | Planning Application Submitted | Application Submitted | Tacher, Caithness, Latheron, Highlands | Highland | Scotland | Scotland | KW5 6DX | 317285 | 947350 | Highland Council | 19/05479/FUL | [5 empty] | 2019-12-12
| 6757 | 2019-06-28 | SSE Renewables | Luichart Power Station | Small Hydro |  |  | 2.6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Luichart Power Station, Contin, Strathpeffer, Highlands | Highland | Scotland | Scotland | IV14 9EW | 239414 | 857013 | Highland Council | 18/05005/FUL | [5 empty] | 2018-10-31 | [6 empty] | 2019-03-21 |  |  |  | 2022-03-21
| 6759 | 2019-12-12 | Community Energy Cumbria | Burneside Mill | Solar Photovoltaics |  |  | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Burneside Mill, Burneside, Kendal, Cumbria | Cumbria | North West | England | LA9 6PZ | 350539 | 495939 | South Lakeland District Council | SL/2018/0855 | [17 empty] | 2019-02-01 | 2019-11-01
| 6761 | 2019-11-20 | Mypower Solar | Leeways | Solar Photovoltaics |  |  | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Land Adjacent To Lobstock Hous, Near Churcham, Gloucester, Gloucestershire | Gloucestershire | South West | England | GL2 8AN | 374703 | 218612 | Forest of Dean District Council | P1671/18/FUL | [5 empty] | 2018-10-22 | [6 empty] | 2018-12-21 |  |  |  | 2021-12-21 | 2019-04-01 | 2019-07-01
| 6762 | 2020-01-14 | Anglian Water Services | Field north of Water Treatment Works / Hoggs Drove | Solar Photovoltaics |  |  | 0.994 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Anglian Water Services Ltd, Hoggs Drove, Marham, King's Lynn, Norfolk | Norfolk | Eastern | England | PE33 9JW | 571684 | 310953 | King's Lynn and West Norfolk Borough Council | 18/01936/FM | [5 empty] | 2018-10-30 | [6 empty] | 2019-03-01 |  |  |  | 2022-03-01
| 6765 | 2019-03-26 | EON UK Renewables | Church and Dwight, Bowles Well Gardens | Solar Photovoltaics |  |  | 0.4225 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Church and Dwight Uk Ltd, Bowles Well Gardens, Folkestone, Kent | Kent | South East | England | CT19 6PQ | 623659 | 137267 | Folkstone and Hythe District Council | Y18/1224/FH | [5 empty] | 2018-10-18 | 2019-02-14
| 6766 | 2020-02-24 | Lightsource BP | Pretoria Road | Solar Photovoltaics |  |  | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land North Of, Pretoria Road, West Of Ellistown Terrace, Ellistown, Coalville, Leicestershire | Leicestershire | East Midlands | England | LE67 1ES | 443155 | 310530 | North West Leicestershire District Council | 18/01595/FULM | [5 empty] | 2018-09-26 | [6 empty] | 2018-12-21 |  |  |  | 2021-12-21
| 6767 | 2019-04-01 | Dwr Cymru Welsh Water | Llannerch Water Treatment Works | Solar Photovoltaics |  |  | 0.35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Llannerch Water Treatment Work, Llanerch Park, St. Asaph, Clwyd | Denbighshire | Wales | Wales | LL17 0BB | 306010 | 371532 | Denbighshire County Council | 30/2018/0732 | [5 empty] | 2018-10-18 | 2019-01-09
| 6768 | 2020-06-05 | Dwr Cymru Welsh Water | Bolton Hill WTW | Solar Photovoltaics |  |  | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Bolton Hill WTW, Tiers Cross, Haverfordwest, Dyfed | Pembrokeshire | Wales | Wales | SA62 3ER | 191754 | 211158 | Pembrokeshire County Council | 18/0386/PA | [5 empty] | 2018-07-30 | [6 empty] | 2018-09-20 |  |  |  | 2023-09-20
| 6772 | 2019-11-20 | H2O Power Generation | Winterburn Hydro | Small Hydro |  |  | 0.185 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Winterburn Hydro, Winterburn, Winterburn Reservoir, Skipton, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | BD23 3QU | 394431 | 460025 | Yorkshire Dales National Park | C/43/51B | [5 empty] | 2018-10-15 | [6 empty] | 2019-03-05 |  |  |  | 2022-03-05
| 6773 | 2019-09-25 | Infinite Renewables | Rassau Industrial Estate | Wind Onshore |  |  | 1.5 | n/a |  |  |  | 1.5 | 1 |  | n/a | Planning Permission Granted | Awaiting Construction | Unit 18, Rassau Industrial Estate, Rassau, Ebbw Vale, Gwent | Blaenau Gwent | Wales | Wales | NP23 5SD | 315099 | 212232 | Blaenau Gwent County Borough Council | C/2018/0293 | [5 empty] | 2018-10-05 | [6 empty] | 2019-07-19 |  |  |  | 2024-07-19
| 6774 | 2019-11-25 | J and J Energies | Islandranny Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 74 | n/a | Planning Permission Granted | Awaiting Construction | Approx 140m, 23 Islandranny Road, Bushmills, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT57 8YE | 117309 | 596785 | Causeway Coast and Glens | LA01/2018/1267/F | [5 empty] | 2018-12-10 | [6 empty] | 2019-06-18 |  |  |  | 2024-06-11
| 6778 | 2020-02-04 | National Trust/Ellergreen Hydro | Combe Gill Hydro Station | Small Hydro |  |  | 0.225 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Combe Gill Hydro Station, Borrowdale, Keswick, Cumbria | Cumbria | North West | England | CA12 5XQ | 325321 | 513428 | Lake District National Park | 7/2018/2266 | [5 empty] | 2018-04-10 | [6 empty] | 2019-01-31 |  |  |  | 2022-01-31 | 2019-07-24
| 6779 | 2020-04-29 | Simec Lochaber Hydropower 2 | Lochaber Hydro Development (Scheme 2) | Small Hydro |  |  | 1.1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land 2460M SE Of Aonach Mor Ho, 9 Forestry Houses, Torlundy, Fort William, Highlands | Highland | Scotland | Scotland | PH33 6SW | 216991 | 775784 | Highland Council | 18/04646/FUL | [5 empty] | 2018-10-10 | [6 empty] | 2019-03-27 |  |  |  | 2022-03-27
| 6780 | 2019-09-27 | Simec Lochaber Hydropower 2 | Lochaber Hydro Development (Scheme 5) | Small Hydro |  |  | 1.6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Leanachan Forest, Torlundy, Fort William, Highlands | Highland | Scotland | Scotland | PH33 6S | 219997 | 778186 | Highland Council | 18/04648/FUL | [5 empty] | 2018-08-10 | 2019-03-15
| 6781 | 2020-04-29 | Simec Lochaber Hydropower 2 | Lochaber Hydro Development (Scheme 3) | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Leanachan Forest, Torlundy, Fort William, Highlands | Highland | Scotland | Scotland | PH33 6SW | 222504 | 775903 | Highland Council | 18/04647/FUL | [5 empty] | 2018-10-10 | [6 empty] | 2019-03-26 |  |  |  | 2022-03-26
| 6783 | 2020-03-31 | Wilson's Country | Carn Industrial Estate | Anaerobic Digestion |  |  | 0.17 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Lands NE Of, 21 Carn Road, Carn Industrial Estate, Craigavon, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT63 5WG | 113992 | 516027 | Armagh, Banbridge and Craigavon | LA08/2018/1389/F | [5 empty] | 2018-09-27 | [6 empty] | 2020-01-06 |  |  |  | 2025-01-05
| 6784 | 2019-04-01 | Purple Renewables | Aviva Headquarters Perth | Wind Onshore |  |  | 0.85 | n/a |  |  |  | 0.85 | 1 |  | n/a | Planning Permission Refused | Application Refused | Aviva Headquarters Pitheavlis, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 0NH | 309884 | 722143 | Perth and Kinross Council | 18/01656/FLL | [5 empty] | 2018-09-17 |  | 2019-01-17
| 6785 | 2020-03-26 | Axis PED / Veolia | Lancaster West Business Park | EfW Incineration |  |  | 30 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Lancaster West Business Park, Imperial Road, Off Imperial Way, Heysham, Morecambe, Lancashire | Lancashire | North West | England | LA3 3RW | 342321 | 459311 | Lancashire County Council | LCC/2019/0021 | [5 empty] | 2019-05-02 | [6 empty] | 2020-02-07 |  |  |  | 2023-02-07
| 6790 | 2020-04-22 | ABO Wind NI | Whappstown Windfarm (Resubmission) (Castlegore) | Wind Onshore |  |  | 9.2 | n/a |  |  |  | 3.1 | 3 | 125 | n/a | Abandoned | Abandoned | 65 Whappstown Road, Moorfields, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT42 3DB | 135307 | 553534 | Ards and North Down | LA02/2018/0897/F | [5 empty] | 2018-10-04 | [6 empty] | 2019-08-16 |  |  |  | 2024-08-13
| 6793 | 2020-03-31 | Wind 2 | Coishletter | Wind Onshore |  |  | 36 | n/a |  |  |  | 4 | 9 | 135 | n/a | Planning Application Submitted | Application Submitted | Land 2800M SW Of, Edinbane, Portree, Highlands | Highland | Scotland | Scotland | IV51 9PW | 133545 | 847925 | Highland Council | 20/00013/FUL | [5 empty] | 2020-01-07
| 6796 | 2020-06-24 | REG Power Management/ Savills | Greenburn Wind Park | Wind Onshore |  | 7866 | 67.2 | n/a |  |  |  | 4.2 | 16 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Land Adj Former Opencast, Greenburn Wind Park, New Cumnock, Cumnock, Strathclyde | East Ayrshire | Scotland | Scotland | KA18 1AY | 256423 | 614614 | Scottish Government (S36) | ECU00002037 | [5 empty] | 2020-03-27
| 6798 | 2020-06-25 | Scottish Power Renewables | Arecleoch Wind Farm (extension) | Wind Onshore |  | 7882 | 73 | n/a |  |  |  | 5.6 | 13 | 200 | n/a | Planning Application Submitted | Application Submitted | Land 2km south west of Barrhill, South Ayrshire | South Ayrshire | Scotland | Scotland | KA26 0PP | 221500 | 578500 | Scottish Government (S36) | ECU00001864 | [5 empty] | 2019-06-12
| 6800 | 2019-06-27 | Private Developer | Lands 260m SW of 76 Strabane Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 40 | n/a | Appeal Refused | Application Refused | Lands 260m South West of 76 Strabane Road, Birnaghs, Newtownstewart, Co. Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 4JZ | 51087 | 551083 | Northern Ireland Planning Appeals Commission | LA11/2015/0518/F | 2018/A0129 |  |  |  |  | 2015-09-11 |  | 2018-09-13 | 2018-10-26 |  | 2019-03-27
| 6801 | 2020-01-23 | Glenview Green Energy | 402 metres NE of 45 Dickeystown Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 30 | n/a | Appeal Granted | Awaiting Construction | Approximately 402 metres north east of 45 Dickeystown Road, Glenarm, Ballymena | Co. Antrim | Northern Ireland | Northern Ireland | BT44 0AB | 147788 | 570314 | Northern Ireland Planning Appeals Commission | LA02/2017/0715/F | 2018/A0096 |  |  |  |  | 2017-08-04 |  | 2018-08-22 | 2018-09-26 |  |  | 2019-03-28 | 2019-03-28 |  |  |  | 2024-03-28
| 6807 | 2020-06-16 | Drax (formerly Scottish Power) | Loch Doon Dam Compensation Set | Small Hydro |  |  | 0.3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Loch Doon Dam U759 Loch Doon, Dalmellington, From A713 At Mossdale To, Ayr, Strathclyde | East Ayrshire | Scotland | Scotland | KA6 7SJ | 247750 | 601586 | East Ayrshire Council | 18/0922/LB | [5 empty] | 2018-12-11 | [6 empty] | 2019-05-16 |  |  |  | 2022-05-16
| 6808 | 2019-08-14 | Private Developer | Tregeen Farm | Anaerobic Digestion |  |  | 0.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Tregeen Farm, Davidstow, Camelford, Cornwall | Cornwall | South West | England | PL32 9SN | 215473 | 89507 | Cornwall Council | PA18/10836 | [5 empty] | 2018-12-04 | [6 empty] | 2019-03-05 |  |  |  | 2022-03-05
| 6810 | 2018-12-21 | Wave Hub | Wave Hub Floating Wind | Wind Offshore |  |  | 40 | n/a |  |  |  | 10 | 4 | 220 | n/a | Planning Application Submitted | Application Submitted | Wave Hub 16km North Of, St Ives Head, Hayle, Cornwall | Cornwall | South West | England | TR27 4DD | 143573 | 54771 | The Planning Inspectorate - National Infrastructure | PA18/10363 | [5 empty] | 2018-10-31
| 6812 | 2019-06-28 | Private Developer | Ballybrack Road | Wind Onshore |  |  | 0.15 | n/a |  |  |  | 0.15 | 1 | 40 | n/a | Planning Permission Granted | Awaiting Construction | Lands appr. 140m north of, 19 Ballybrack Road, Loughmacrory, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | D18 Y673 | 70143 | 537929 | Fermanagh and Omagh | LA10/2018/1548/F | [5 empty] | 2018-12-07 | [6 empty] | 2019-05-02 |  |  |  | 2024-04-30
| 6813 | 2018-12-21 | Randox AD | 47 Crosshill Road | Anaerobic Digestion |  |  | 0.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | 45 metres north of, 47 Crosshill Road, Aldergrove, Crumlin, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT29 4BL | 128784 | 536599 | Ards and North Down | LA03/2018/1093/F | [5 empty] | 2018-12-04
| 6816 | 2020-01-24 | Moog Controls | Moog Controls Factory | Solar Photovoltaics |  |  | 0.4 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Unit 5, Moog Control Ltd Industrial Gr, Ashchurch Parkway, Tewkesbury, Gloucestershire | Gloucestershire | South West | England | GL20 8TU | 392463 | 233374 | Tewkesbury Borough Council | 18/01175/PDSOL | [5 empty] | 2018-11-23 | [6 empty] | 2019-01-17 |  |  |  | 2024-01-17
| 6817 | 2019-11-20 | CR and GM Woollam | Bryn-Y-Plentyn Farm | Solar Photovoltaics |  |  | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Bryn-Y-Plentyn Farm, Bryn-Y-Plentyn, Middleton, Oswestry, Shropshire | Shropshire | West Midlands | England | SY11 4LP | 332784 | 329206 | Shropshire Council | 18/05499/FUL | [5 empty] | 2018-11-28 | [6 empty] | 2019-10-22 |  |  |  | 2022-10-22
| 6818 | 2019-09-27 | Private Developer | Lower Tregeen | Wind Onshore |  |  | 0.9 | n/a |  |  |  | 0.9 | 1 | 77 | n/a | Planning Permission Granted | Awaiting Construction | Land at Lower Tregeen, Davidstow, Camelford, Cornwall | Cornwall | South West | England | PL32 9XU | 216165 | 88033 | Cornwall Council | PA18/10990 | [5 empty] | 2018-11-20 | [6 empty] | 2019-09-13 |  |  |  | 2022-09-13
| 6819 | 2020-05-28 | Wind Estate | Brownhill Farm | Wind Onshore |  |  | 8.4 | n/a |  |  |  | 4.2 | 2 | 138.5 | n/a | Planning Permission Granted | Awaiting Construction | Brownhill Farm, West Benhar Road, Harthill, Shotts, Strathclyde | North Lanarkshire | Scotland | Scotland | ML7 5TG | 288880 | 662140 | North Lanarkshire Council | 18/01433/FUL | [5 empty] | 2018-11-05 | [6 empty] | 2019-08-07 |  |  |  | 2024-08-07
| 6821 | 2019-12-20 | Wind 2 | South Kilbraur Wind Farm | Wind Onshore |  |  | 28 | n/a |  |  |  | 4 | 7 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Land 1700M South Of, 43 Farlary, Rogart, Highlands | Highland | Scotland | Scotland | IV28 3YE | 278361 | 907028 | Highland Council | 19/04826/FUL | [5 empty] | 2019-11-23
| 6822 | 2019-12-11 | Barnstone Estate | Crewe Hill Farm | Anaerobic Digestion |  |  | 0.36 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Crewe Hall Farm, Crewe Hill Lane, Crewe By Farndon, Chester, Cheshire | Cheshire | North West | England | CH3 6PD | 342293 | 353022 | Cheshire West and Chester Council | 18/03880/FUL | [5 empty] | 2018-11-09 | [6 empty] | 2018-12-21 |  |  |  | 2021-12-21
| 6823 | 2019-09-27 | Simec Hydro Site | Land To West of Allt Na Lairig | Small Hydro |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land To West Of Allt Na Lairig, Corrour, Highlands | Highland | Scotland | Scotland | PH30 4AA | 241195 | 769762 | Highland Council | 18/04649/FUL | [5 empty] | 2018-10-04 | 2019-03-15
| 6824 | 2019-08-22 | Private Developer | Colony Farm | Anaerobic Digestion |  |  | 4 |  |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land South West Of Crane Farm, Fifties, Manea, March, Cambridgeshire | Cambridgeshire | Eastern | England | PE15 0HN | 550047 | 293013 | Fenland District Council | F/YR18/0908/F | [5 empty] | 2018-10-05 | [6 empty] | 2019-02-27 |  |  |  | 2022-02-27 | 2019-03-01
| 6826 | 2019-06-25 | Douglas West Extension / 3R Energy Solutions | Douglas West Wind Farm (extension) | Wind Onshore |  |  | 78 | n/a |  |  |  | 6 | 13 | 200 | n/a | Planning Application Submitted | Application Submitted | Douglas West and Dalquhandy, F, Lesmahagow, Site West of Junction 11 of M7, Lanark, Strathclyde | Strathclyde | Scotland | Scotland | ML11 0NN | 280968 | 634257 | Scottish Government (S36) | ECU00001836 | [5 empty] | 2019-04-12
| 6827 | 2020-06-24 | Banks Renewables | Lethans Wind Farm (resubmission) | Wind Onshore |  |  | 105.5 | n/a |  |  |  | 4.8 | 22 | 220 | n/a | Planning Permission Granted | Awaiting Construction | Land to the north east of New Cumnock, Lethans, East Ayrshire | Strathclyde | Scotland | Scotland |  | 268331 | 616048 | Scottish Government (S36) | ECU00001856 | [5 empty] | 2019-05-22 | [6 empty] | 2020-06-18 |  |  |  | 2023-06-18
| 6828 | 2020-06-18 | Viking Energy Wind Farm | Viking Wind Farm (resubmission) | Wind Onshore |  |  | 443 | n/a |  |  |  | 4.5 | 103 | 155 | n/a | Planning Permission Granted | Awaiting Construction | Lang Kame, Shetland Island | Shetland | Scotland | Scotland |  | 443800 | 1161960 | Scottish Government (S36) | ECU00000723 | [5 empty] | 2018-11-14 | [6 empty] | 2019-05-24
| 6829 | 2019-01-02 | Hadstone Energy | South Antrim Solar Park - Phase 2 | Solar Photovoltaics |  |  | 39.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Lands approx 550m South of, 99 Dublin Road, Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT41 4PN | 127265 | 541491 | Northern Ireland Planning Service | LA03/2015/0262/F | [5 empty] | 2015-06-30 | [6 empty] | 2016-04-26 |  |  |  | 2021-04-25
| 6835 | 2020-05-04 | Miller Turner Group / Savills | Red Scar Industrial Estate - EfW | EfW Incineration |  |  | 40 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Red Scar Industrial Estate, Longriddge Road, Preston | Lancashire | North West | England | PR2 5LX | 357957 | 431898 | Lancashire County Council | LCC/2019/0029 | [5 empty] | 2019-06-05 | [6 empty] | 2019-11-27 |  |  |  | 2022-11-27
| 6838 | 2020-01-29 | Hydroplan/Three Lochs Hydro | Gaineamhach Hydro Scheme Powerhouse (resubmission) | Small Hydro |  |  | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land 3160M SW Of, Kerry Falls House, Gairloch, Highlands | Highland | Scotland | Scotland | IV21 2AH | 181797 | 868972 | Highland Council | 18/05132/FUL | [5 empty] | 2018-11-05 | [6 empty] | 2019-03-29 |  |  |  | 2022-03-29
| 6839 | 2018-10-23 | First Hydro Company | Dinorwig | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 1728 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Snowdonia | Conwy | Wales | Wales | LL55 4TY | 258627 | 360025 | Snowdonia National Park Authority | [18 empty] | 1978-01-01 | 1983-01-01
| 6840 | 2018-10-23 | First Hydro Company | Ffestiniog | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 360 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Ffestiniog, Gwynedd, Snowdonia | Conwy | Wales | Wales | LL41 3TP | 267909 | 344424 | Snowdonia National Park Authority | [18 empty] | 1956-01-01 | 1961-01-01
| 6841 | 2018-10-23 | Scottish Power | Cruachan | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 440 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Argyll and Bute | Argyll and Bute | Scotland | Scotland | PA33 1AN | 208017 | 728674 | Argyll and Bute Council | [18 empty] | 1961-01-01 | 1966-01-01
| 6842 | 2018-10-23 | SSE Renewables | Foyers | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 300 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Highland | Highland | Scotland | Scotland | IV2 6YE | 249655 | 820941 | Highland Council | [18 empty] | 1969-01-01 | 1974-01-01
| 6843 | 2019-02-19 | Viridor/Highview Power Storage | Pilsworth Landfill Site | Liquid Air Energy Storage | Stand-alone Storage | n/a | 5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Bury | Lancashire | North West | England | BL9 8RS | 382227 | 408975 | Bury Metropolitan Borough Council | [18 empty] | 2015-10-23 | 2018-06-05
| 6844 | 2018-10-23 | ABB | ABB & UK Power Networks Energy Storage Installation | Battery | Stand-alone Storage | n/a | 0.2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Hemsby, Nolfolk | Norfolk | Eastern | England | NR29 4NH | 649060 | 317282 | Norfolk County Council | [18 empty] | 2010-11-01 | 2011-05-19
| 6845 | 2018-12-12 | AES Kilroot Power (AES KPL) | AES Kilroot Station Battery Storage Array | Battery | Co-located with fossil fuel plant | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Carrickfergus | Co. Antrim | Northern Ireland | Northern Ireland | BT38 7LX | 157517 | 543117 | Northern Ireland Planning Service | [18 empty] | 2015-11-18 | 2016-01-18
| 6846 | 2018-10-23 | University of Sheffield/ Eon/ Uniper | EPSRC Willenhall | Battery | Stand-alone Storage | n/a | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Willenhall, Wolverhampton | West Midlands | West Midlands | England | WV13 2NU | 396192 | 298580 | Coventry City Council | [18 empty] | 2014-08-01 | 2014-09-01
| 6847 | 2018-12-07 | Wind & Sun | Flat Holm Microgrid Project | Battery | Co-located with RE | n/a | 0.005 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Flat Holm Island | Cardiff | Wales | Wales |  | 321972 | 164932 | Cardiff Council | [18 empty] | 2006-06-01 | 2006-07-01
| 6848 | 2018-12-07 | Foula Community Electricity Trust | Foula Community Electricity Scheme | Battery | Co-located with RE | n/a | 0.016 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Foula, Shetland, Shetland Islands | Shetland | Scotland | Scotland | ZE2 9PN | 397081 | 1138943 | Shetland Islands Council | [18 empty] | 2008-08-01 | 2008-09-01
| 6849 | 2017-07-17 | Gigha Island community (Multiple Owners) | Gigha Wind Farm Battery Project | Battery | Stand-alone Storage | n/a | 0.1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Gigha | Argyll and Bute | Scotland | Scotland | PA41 7AB | 164429 | 649830 | Argyll and Bute Council | [18 empty] | 2015-11-15 | 2016-12-15
| 6850 | 2018-10-23 | Highview Power Storage | Highview Pilot Plant | Liquid Air Energy Storage | Stand-alone Storage | n/a | 0.35 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Slough, Berkshire | Berkshire | South East | England | SL1 4TT | 495219 | 181513 | Slough Borough Council | [18 empty] | 2011-01-15 | 2011-07-15
| 6851 | 2018-12-07 | Wind & Sun | Horse Island Microgrid Project | Battery | Co-located with RE | n/a | 0.012 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Horse Island, Highland Scotland | Highland | Scotland | Scotland |  | 202386 | 904706 | Highland Council | [18 empty] | 2009-09-01 | 2009-10-01
| 6852 | 2016-04-29 | Eigg Electric | Isle of Eigg Electrification Project | Battery | Co-located with RE | n/a | 0.06 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Isle of Eigg, Highland Scotland | Highland | Scotland | Scotland | PH42 4RL | 147908 | 786328 | Highland Council | [18 empty] | 2008-05-01 | 2008-06-01
| 6853 | 2018-10-23 | Wind & Sun | Isle of Muck Microgrid System | Battery | Co-located with RE | n/a | 0.045 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Isle of Muck, Highland Scotland | Highland | Scotland | Scotland | PH41 2RP | 141577 | 779605 | Highland Council | [18 empty] | 2013-10-12 | 2013-11-12
| 6854 | 2018-12-07 | Wind & Sun | Isle of Rum Microgrid Project | Battery | Co-located with RE | n/a | 0.045 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Isle of Rum, Highland Scotland | Highland | Scotland | Scotland | PH43 4RR | 137593 | 799241 | Highland Council | [18 empty] | 2015-10-12 | 2015-11-12
| 6855 | 2017-07-14 | Scottish Hydroelectric Power Distribution (SHEPD) | Northern Isles New Energy Solution (NINES) 1 | Battery | Stand-alone Storage | n/a | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Lerwick, Shetlands | Shetland | Scotland | Scotland | ZE1 0PS | 446456 | 1142794 | Shetland Islands Council | [18 empty] | 2014-01-15 | 2014-02-15
| 6856 | 2018-10-23 | Northern Powergrid | Rise Carr, Darlington / CLNR EES3-1 | Battery | Stand-alone Storage | n/a | 2.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Rise Carr, Darlington | County Durham | North East | England | DL3 0RX | 428615 | 516869 | Darlington Borough Council | [18 empty] | 2014-05-05 | 2014-06-05
| 6857 | 2016-10-01 | Northern Powergrid | Maltby / CLNR EES1 | Battery | Stand-alone Storage | n/a | 0.05 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Maltby, South Yorkshire | Northumberland | North East | England | S66 7PZ | 454253 | 391507 | Northumberland County Council | [18 empty] | 2013-08-15 | 2013-09-15
| 6858 | 2016-10-01 | Northern Powergrid | Wooler Ramsey / CLNR ESS2-1 | Battery | Stand-alone Storage | n/a | 0.1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Wooler, Northumberland | County Durham | North East | England | NE71 6NZ | 398767 | 627958 | Darlington Borough Council | [18 empty] | 2013-08-15 | 2013-09-15
| 6859 | 2016-10-01 | Northern Powergrid | Wooler St. Mary / CLNR ESS2-2 | Battery | Stand-alone Storage | n/a | 0.1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Wooler, Northumberland | Northumberland | North East | England | NE71 6NF | 399286 | 627979 | Northumberland County Council | [18 empty] | 2013-08-15 | 2013-09-15
| 6860 | 2016-10-01 | Northern Powergrid | Harrowgate Hill, Darlington / CLNR ESS3-2 | Battery | Stand-alone Storage | n/a | 0.05 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Harrowgate Hill, Darlington | County Durham | North East | England | DL1 3EL | 429494 | 517295 | Darlington Borough Council | [18 empty] | 2013-08-15 | 2013-09-15
| 6861 | 2016-10-01 | Northern Powergrid | High Northgate, Darlington / CLNR ESS3-3 | Battery | Stand-alone Storage | n/a | 0.1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | High Northgate, Darlington | County Durham | North East | England | DL3 0HJ | 428852 | 516827 | Darlington Borough Council | [18 empty] | 2013-08-15 | 2013-09-15
| 6862 | 2018-10-23 | Scottish Hydroelectric Power Distribution (SHEPD) | Orkney Storage Park Project | Battery | Stand-alone Storage | n/a | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Kirkwall, Orkney | Orkney Islands | Scotland | Scotland | KW15 1QX | 344780 | 1011192 | Orkney Islands Council | [18 empty] | 2013-05-01 | 2013-06-01
| 6863 | 2018-10-23 | UK Power Networks | Smarter Network Storage | Battery | Stand-alone Storage | n/a | 6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Decommissioned | Decommissioned | Leighton Buzzard, Bedfordshire | Bedfordshire | Eastern | England | LU7 3NU | 492757 | 225085 | Central Bedfordshire Council | [18 empty] | 2014-05-15 | 2014-12-12
| 6864 | 2018-10-23 | Western Power Distribution | Falcon Project | Battery | Stand-alone Storage | n/a | 0.25 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Milton Keynes, Buckinghamshire | Buckinghamshire | South East | England | MK9 3DX | 485187 | 238751 | Milton Keynes Council | [18 empty] | 2013-12-11 | 2013-12-11
| 6865 | 2018-10-23 | EFDA JET | EFDA JJET Fusion Flywheel | Flywheels | Stand-alone Storage | n/a | 400 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Abingdon, Oxfordshire | Oxfordshire | South East | England | OX14 3DB | 453453 | 195744 | South Oxfordshire District Council | [18 empty] | 2005-08-01 | 2006-01-01
| 6866 | 2016-11-03 | Farm Power Apollo/ Anesco | Slepe Farm | Battery | Co-located with RE | n/a | 0.25 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Slepe Farm, Dorset | Dorset | South West | England | BH16 6HT | 392955 | 93272 | Purbeck District Council | [18 empty] | 2014-09-10 | 2014-10-10
| 6868 | 2019-05-22 | Snowdonia Pumped Hydro (Quarry Battery Company) | Glyn Rhonwy (larger version) | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 99.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Llanberis, Caernarfon, Gwynedd | Gwynedd | Wales | Wales | LL55 4EL | 257240 | 360808 | The Planning Inspectorate - National Infrastructure | [6 empty] | 2015-10-21 | [6 empty] | 2017-03-08
| 6869 | 2019-02-04 | Belectric UK | Willersey solar farm | Battery | Co-located with RE | 1867 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land Parcel To The North Of The Byre Badsey Lane Willersey Gloucestershire | Gloucestershire | South West | England | WR12 7PJ | 410549 | 239577 | Cotswold District Council | 16/04853/FUL | [5 empty] | 2016-11-22 | [6 empty] | 2015-12-23 |  |  |  |  | 2019-01-01 | 2019-02-01
| 6870 | 2019-04-23 | SSE Renewables | Coire Glas - Phase I | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 600 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Loch a' Choire Ghlais, Balmaccan near, Invermoriston, Spean Bridge | Highland | Scotland | Scotland | PH34 | 222889 | 795160 | Scottish Government (S36) | EC00003164 | [5 empty] | 2012-02-10 | [6 empty] | 2013-12-13
| 6871 | 2019-03-22 | Buccleuch Estates | Glenmuckloch | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 210 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Glenmucklock, Kirckconnel | Dumfries and Galloway | Scotland | Scotland | DG4 6LS | 273301 | 612213 | Scottish Government (S36) | EC00005236 | [5 empty] | 2015-12-23 | [6 empty] | 2016-11-29
| 6872 | 2017-04-24 | Big60Million/Belectric | Redruth Solar Farm - Penstruthal Farm | Battery | Co-located with RE | 5888 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land At Penstruthal Farm Lanne, Wheal Buller, Redruth, Cornwall | Cornwall | South West | England | TR16 6ST | 170862 | 40261 | Cornwall Council | PA15/06838 | [5 empty] | 2015-08-28 |  | 2015-12-18
| 6873 | 2020-05-26 | Jaguar Land Rover | Jaguar Land Rover Kingsway Battery | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Kingsway, off Banbury Road (B4100), Gaydon | Warwickshire | West Midlands | England | CV35 0DB | 435149 | 255064 | Stratford on Avon District Council | 15/03646/FUL | [5 empty] | 2015-12-04 | [6 empty] | 2015-12-11 |  |  |  | 2018-12-11
| 6874 | 2019-02-26 | Veiges Farm Solar Park | Lower Veiges Plantation | Battery | Co-located with RE | 5679 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Veiges Farm House, St. Johns Road, Exmouth | Devon | South West | England | EX8 5EG | 303114 | 83972 | East Devon District Council | 15/2017/MFUL | [5 empty] | 2015-12-04 | [6 empty] | 2016-02-03
| 6875 | 2019-02-04 | Big60Million/Belectric | Albrighton Solar farm | Battery | Co-located with RE | 5506 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land To The North of Harriotts Hayes Lane, Codsall Wood, Wolverhampton | Shropshire | West Midlands | England | WV8 1RQ | 383131 | 304665 | Shropshire Council | 15/02787/FUL | [5 empty] | 2015-12-04 | [6 empty] | 2015-12-14 |  |  |  | 2018-12-14 | 2019-01-01 | 2019-02-01
| 6876 | 2019-05-22 | Snowdonia Pumped Hydro (Quarry Battery Company) | Glyn Rhonwy (smaller version) | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Llanberis, Caernarfon, Gwynedd | Gwynedd | Wales | Wales | LL55 4EL | 256968 | 361136 | Gwynedd Council | C12/1451/15/LL | [5 empty] | 2012-10-31 | [6 empty] | 2014-02-19
| 6877 | 2019-04-01 | Strathmore English Estates | Hield House | Battery | Co-located with RE | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Holwick, Middleton in Teesdale, Durham | County Durham | North East | England | DL12 0XJ | 389339 | 527923 | Durham County Council | DM/14/01299/FPA | [5 empty] | 2013-10-25 | 2014-12-23
| 6878 | 2018-11-23 | Fordmouth Renewables | Fordmouth, Carnwath | Fuel Cell (Hydrogen) | Co-located with RE | 5890 | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Fordmouth, Carnwath | South Lanarkshire | Scotland | Scotland | ML11 8LS | 298158 | 650900 | South Lanarkshire Council | CL/15/0455 | PPA-380-2072 |  |  |  |  | 2015-12-09 |  | 2016-06-21 | 2016-09-19 |  | 2016-12-23
| 6879 | 2016-11-03 | Anesco | Limberlost Solar Farm | Battery | Co-located with RE | 5678 | 0.25 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Landfill Site Crookham Common, Thatcham, Berkshire | Berkshire | South East | England | RG19 8DH | 453510 | 164953 | West Berkshire Council | [18 empty] | 2015-11-11 | 2015-12-11
| 6880 | 2019-03-21 | Anesco | Cotgrave Solar Farm Battery | Battery | Co-located with RE | 1843 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land North West of Gozen Lodge, Main Road, Cotgrave | Nottinghamshire | East Midlands | England | NG12 3GU | 464046 | 336291 | Rushcliffe Borough Council | 15/02835/FUL | [5 empty] | 2015-12-01 | [6 empty] | 2016-01-08 |  |  |  | 2019-01-08
| 6881 | 2017-03-28 | British Solar Renewables / Western Power Distribution / RES | Higher Hill Farm Energy Storage | Battery | Co-located with RE | 2174 | 0.3 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land At Higher Hill Farm, Butleigh Hill, Butleigh, Glastonbury, Somerset | Somerset | South West | England | BA6 8TW | 351373 | 131348 | Mendip District Council | [18 empty] | 2016-08-12 | 2016-09-12
| 6883 | 2016-11-03 | Connected Energy | The Everest System | Battery | Stand-alone Storage | n/a | 0.05 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Lotus Car Factory, Potash Ln, Hethel, Norwich NR14 8EZ | Norfolk | Eastern | England | NR14 8EZ | 615642 | 300729 | South Norfolk Council | [18 empty] | 2015-12-19 | 2016-01-19
| 6884 | 2018-11-30 | Statoil | Hywind 2 | Battery | Co-located with RE | 2479 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Buchan Deeps, 20km off Peterhead | Aberdeen | Scotland | Scotland |  | 411917 | 846754 | Aberdeenshire Council | APP/2017/0868 | [12 empty] | 2017-05-09 |  |  |  |  | 2018-10-20 | 2018-11-20
| 6885 | 2019-03-21 | Anesco | Oxcroft Solar Farm | Battery | Co-located with RE | 5591 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Oxcroft Stocking Ground Land A, Woodthorpe Road and Mill Lane, Stanfree, Chesterfield | Derbyshire | East Midlands | England | S44 6AG | 447301 | 373737 | Bolsover District Council | 16/00145/FUL | [5 empty] | 2016-03-30 | [6 empty] | 2016-07-01 |  |  |  | 2019-07-01 | 2017-09-01 | 2017-12-01
| 6886 | 2016-05-24 | London Borough of Hounslow | Western International Market (WIM) Site | Battery | Co-located with RE | 6132 | 0.24 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Western Int Market, Hayes Rd, Southall | Greater London | London | England | UB2 5XJ | 510599 | 178669 | Hounslow London Borough Council | P/2015/5475 | [5 empty] | 2015-12-14 | [6 empty] | 2016-02-19 |  |  |  |  | 2016-02-24 | 2016-05-24
| 6887 | 2020-06-25 | Renewable Energy Systems (RES) | Petre Street | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Expired | Planning Permission Expired | Site Of 350 Petre Street, Sheffield | South Yorkshire | Yorkshire and Humber | England | S4 8LU | 436979 | 389555 | Sheffield City Council | 16/03302/FUL | [5 empty] | 2016-09-05 | [6 empty] | 2016-11-04 |  |  |  | 2019-11-04
| 6888 | 2019-03-21 | Anesco | Salcey Solar Farm | Battery | Co-located with RE | 1878 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Bulls Head Farm, Eakley Lanes, Newport Pagnell | Buckinghamshire | South East | England | MK16 8LP | 481633 | 250599 | Milton Keynes Council | 16/00631/FUL | [5 empty] | 2016-03-17 | [6 empty] | 2016-05-12 | [5 empty] | 2017-12-01
| 6892 | 2019-05-16 | Kiwi Power | Cleveland Potash | Battery | Stand-alone Storage | n/a | 6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Boulby Mine, Loftus, Saltburn-by-the-Sea, Cleveland | North Yorkshire | North East | England | TS13 4UZ | 476307 | 518514 | North York Moors National Park Authority | NYM/2015/0922/FL | [5 empty] | 2016-01-07 | [6 empty] | 2016-03-02 |  |  |  |  | 2017-06-01 | 2017-10-01
| 6894 | 2019-05-16 | 2020 Renewables | Whitelaw Brae Wind farm | Battery | Co-located with RE | 3317 | 4 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Whitelaw Brae Wind Farm, Tweedsmuir, Biggar, Strathclyde | South Lanarkshire | Scotland | Scotland | ML12 6QS | 306039 | 621476 | Scottish Government (S36) | EC00002090 | WIN-140-4 |  |  |  |  | 2014-12-11 |  |  | 2015-11-25 |  |  | 2017-12-07 | 2017-12-07
| 6897 | 2016-08-08 | E.ON UK | JB Wheaton | Battery | Co-located with RE | 4752 | 0.005 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | JB Wheaton, Chard Junction, Chard, Somerset | Somerset | South West | England | TA20 4QN | 334232 | 105025 | South Somerset District Council | [18 empty] | 2016-07-08 | 2016-08-08
| 6898 | 2019-01-03 | Statera Energy/ InfraRed Capital | Pelham | Battery | Stand-alone Storage | n/a | 49 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | LAND NORTH OF PELHAM SUBSATION AND SOUTH OF BERDEN ROAD, BERDEN, BISHOP’S STORTFORD, | Essex | Eastern | England | CM23 1BA | 545779 | 228669 | Uttlesford District Council | UTT/16/2316/FUL | [5 empty] | 2016-08-16 | [6 empty] | 2016-10-18 |  |  |  | 2019-10-18 | 2017-01-15 | 2017-06-15
| 6900 | 2019-03-21 | Anesco | Berry Court Solar Farm - energy storage | Battery | Co-located with RE | 2150 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Bramley road, Little London | Hampshire | South East | England | RG26 5AT | 462119 | 158890 | Basingstoke and Deane Borough Council | 16/01901/FUL | [5 empty] | 2016-06-07 | [6 empty] | 2016-08-02 | [5 empty] | 2017-12-01
| 6902 | 2018-11-23 | Camborne Energy Storage | Chineham Battery Energy Storage Facility | Battery | Stand-alone Storage | n/a | 15 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land off Carpenters Down, Basingstoke | Hampshire | South East | England | RG24 9PJ | 464386 | 154816 | Basingstoke and Deane Borough Council | 16/02534/FUL | [5 empty] | 2016-07-26 | 2017-01-04
| 6903 | 2020-06-02 | CESL UK Atomic Energy Authority | Culham Science Centre | Battery | Stand-alone Storage | n/a | 250 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | UK A E A, Culham Science Centre, Abingdon | Oxfordshire | South East | England | OX14 3DB | 453452 | 195723 | South Oxfordshire District Council | P16/S2368/FUL | [5 empty] | 2016-07-18 | [6 empty] | 2016-11-15 |  |  |  | 2019-11-15
| 6906 | 2019-03-21 | E.ON UK | Blackburn Meadows | Battery | Co-located with RE | 166 | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Blackburn Meadows in Sheffield, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | S9 1HF | 440075 | 391650 | Sheffield City Council | [18 empty] | 2017-04-07 | 2017-10-09
| 6907 | 2019-03-21 | Anesco | Chittening Road | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Chittening Road, Bristol | Avon | South West | England | BS11 0YU | 353538 | 181753 | Bristol City Council | 16/04250/F | [5 empty] | 2016-08-05 | [6 empty] | 2016-11-04
| 6909 | 2020-03-20 | Grid Battery Storage (GBSL) | Dorking Battery Energy Storage System | Battery | Stand-alone Storage | n/a | 6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Milton Court Farm, Milton Court Lane, Dorking, Surrey, RH4 3LY | Surrey | South East | England | RH4 3LY | 514966 | 149202 | Mole Valley District Council | MO/2016/1168 | [5 empty] | 2016-07-20 | [6 empty] | 2016-10-12 |  |  |  |  | 2017-01-15
| 6910 | 2019-04-18 | Renewable Energy Systems (RES) | Broxburn | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land at Lookabootye, by Broxburn, adjacent to the Lookabootye substation. | West Lothian | Scotland | Scotland |  | 309143 | 670530 | West Lothian Council | LIVE/0502/FUL/16 | PPA-400-2073 |  |  |  |  | 2016-08-03 |  | 2016-11-25 | 2016-12-15 |  |  | 2017-03-06 | 2017-03-06 |  |  |  |  | 2017-08-15 | 2018-09-15
| 6911 | 2020-01-20 | Anesco (formerly owned by Energy Reservoirs) | Land to the west of Clay Hill Pit / Larport Farm | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land West of Clay Hill Pit Larport Farm Larport Lane Dormington Herefordshire | Hereford and Worcester | West Midlands | England | HR1 4EP | 357450 | 239700 | Herefordshire Council | P162400/F | [5 empty] | 2016-08-23 | [6 empty] | 2016-11-18 |  |  |  |  | 2019-01-01 | 2020-01-01
| 6912 | 2018-11-30 | Centrica | Roosecote | Battery | Stand-alone Storage | n/a | 49 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Roosecote coal and gas-fired power station, Barrow-in-Furness, Cumbria, UK, | Cumbria | North West | England | LA13 0PQ | 322288 | 468359 | Barrow in Furness Borough Council | [18 empty] | 2017-03-01 | 2018-11-30
| 6913 | 2018-11-16 | Anesco | Bumpers Lane Solar Farm | Battery | Co-located with RE | 6282 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land North Of Bumpers Farm, Ilmer Lane, Ilmer, Buckinghamshire | Buckinghamshire | South East | England | HP27 9RE | 476556 | 206578 | Aylesbury Vale District Council | 14/A1926/NON | [5 empty] | 2016-11-23 | 2016-12-21
| 6914 | 2020-03-23 | Anesco/ Green Hedge Energy UK | Breach Farm - Energy Barn | Battery | Stand-alone Storage | n/a | 40 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Breach Farm, Caldwell, Swadlincote, Derbyshire | Derbyshire | East Midlands | England | DE12 6RJ | 426427 | 318855 | South Derbyshire District Council | 9/2017/0541 | [5 empty] | 2017-05-18 | [6 empty] | 2017-08-15
| 6915 | 2019-03-15 | Anesco/ Green Hedge Energy UK | Hill Farm - Energy Barn | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Hill Farm, Spring Lane, Packington, Ashby de la Zouch, Leicestershire | Leicestershire | East Midlands | England | LE65 1WU | 436639 | 314607 | North West Leicestershire District Council | 16/00735/FUL | [5 empty] | 2016-06-22 | [6 empty] | 2016-08-17 |  |  |  |  | 2016-12-15 | 2017-03-31
| 6916 | 2019-03-15 | Anesco/ Green Hedge Energy UK | Kings Barn Farm - Energy Barn | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Kings Barn Farm, Steyning, West Sussex | West Sussex | South East | England | BN44 3YR | 518460 | 111380 | Horsham District Council | DC/16/1648 | [5 empty] | 2016-07-22 | [6 empty] | 2016-10-04 |  |  |  |  | 2016-12-15 | 2017-03-31
| 6917 | 2018-12-11 | Eelpower | Leverton Farm - Energy Barn | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Leverton Farm, Birch Holt Farm, Burton Lincoln, Lincoln | Lincolnshire | East Midlands | England | LN1 2RD | 495886 | 374623 | Lincoln City Council | [18 empty] | 2017-11-01 | 2018-01-01
| 6918 | 2019-05-09 | Hazel Capital/ Noriker Power | Noriker Power Staunch | Battery | Co-located with fossil fuel plant | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Holditch House, Holditch Road, Chesterton | Staffordshire | West Midlands | England | ST5 9JQ | 383781 | 348429 | Newcastle Under Lyme Borough Council | 16/00242/FUL | [5 empty] | 2016-03-24 | [6 empty] | 2016-05-19 |  |  |  |  | 2016-12-15 | 2017-03-15
| 6919 | 2020-02-26 | Cefn y Maes Community / REG Power Management | Cefn y Maes Community Renewable Energy Park | Battery | Co-located with RE | n/a | 0.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Cefn y Maes Rhydycroesau, Oswestry | Powys | Wales | Wales | SY10 7JB | 322812 | 332448 | Powys County Council | P/2017/0255 | [5 empty] | 2017-03-10 | [6 empty] | 2018-02-02
| 6920 | 2018-11-27 | EDF Energy Renewables | West Burton | Battery | Co-located with fossil fuel plant | n/a | 49 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | West Burton Power Station North Road West Burton Retford Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 9BL | 480060 | 385968 | Bassetlaw District Council | 16/00954/FUL | [5 empty] | 2016-07-11 | [6 empty] | 2016-09-30 |  |  |  |  | 2018-01-25 | 2018-06-25
102 | 6923 | 2020-03-12 | Statera Energy/ InfraRed Capital | Norton | Battery | Stand-alone Storage | n/a | 49 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land just north of the railway line, High Middlefield Farm, Durham Road, Thorpe Thewles, | County Durham | North East | England | TS21 3LS | 441440 | 522394 | Stockton on Tees Borough Council | 16/1978/FUL | [5 empty] | 2016-07-28 | [6 empty] | 2016-11-03
| 6924 | 2020-02-04 | Push Energy | Kentishes West, Essex | Battery | Co-located with RE | 1464 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Kentishes Farm, Stisted, Braintree, Essex | Essex | Eastern | England | CM77 8BX | 579269 | 226163 | Essex County Council | 16/01507/FUL | [5 empty] | 2016-09-02 | [6 empty] | 2016-10-28
| 6925 | 2018-08-03 | Enel (formerly Element Power) | Tynemouth Energy Storage System (TESS) | Battery | Stand-alone Storage | n/a | 25 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Newcastle | Tyne and Wear | North East | England | NE27 0NB | 431864 | 570273 | North Tyneside Council | 16/01451/FUL | [5 empty] | 2016-09-08 | [6 empty] | 2016-10-12 |  |  |  | 2019-10-12 | 2018-12-20 | 2018-05-25
| 6926 | 2017-03-28 | Belectric UK / Foresight | Nevendon | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Nevendon, Essex | Essex | Eastern | England | SS14 3JH | 572912 | 191225 | Essex County Council | [18 empty] | 2018-10-15 | 2018-03-15
| 6927 | 2019-01-03 | Vattenfall | Pen y Cymoedd Energy Storage | Battery | Co-located with RE | 4595 | 22 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Pen y Cymoedd, Neath Port Talbot | Neath Port Talbot | Wales | Wales | SA13 3HF | 282793 | 196557 | Neath Port Talbot County Borough Council | [18 empty] | 2017-11-01 | 2018-05-01
| 6929 | 2020-04-28 | UK Power Reserve | Traston Road | Battery | Co-located with fossil fuel plant | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land East Of Clarke Energy Production, Traston Road, Newport | Newport | Wales | Wales | NP19 4PW | 333094 | 185913 | Newport City Council | 16/0855 | [5 empty] | 2016-08-19 | [6 empty] | 2016-11-03 |  |  |  | 2021-11-03
| 6930 | 2020-04-28 | UK Power Reserve | Bristol Road | Battery | Co-located with fossil fuel plant | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | NGPlot 6 Bristol Road Gloucester | Gloucestershire | South West | England | GL2 5YA | 381828 | 215977 | Gloucester City Council | 16/01044/FUL | [5 empty] | 2016-08-30 | [6 empty] | 2016-10-26
| 6932 | 2020-04-28 | UK Power Reserve | Asfordby Business Park (1) | Battery | Co-located with fossil fuel plant | n/a | 23.4 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Zone P, Asfordby Business Park, Welby Road, Melton Mowbray, Leicestershire, | Leicestershire | East Midlands | England | LE14 3JL | 472654 | 320733 | Melton Borough Council | 16/00522/FUL | [5 empty] | 2016-08-01 | [6 empty] | 2016-09-30 |  |  |  | 2019-09-30
| 6936 | 2020-04-28 | UK Power Reserve | Oil Sites Road | Battery | Co-located with fossil fuel plant | n/a | 9.629 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At North Road Ellesmere Port | Cheshire | North West | England | CH65 4EQ | 342135 | 376238 | Cheshire West and Chester Council | 17/03414/FUL | [5 empty] | 2017-08-08 | [6 empty] | 2017-10-30 |  |  |  | 2020-10-30
| 6941 | 2020-05-27 | Federal Estates | Chelveston Renewable Energy Park | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Chelveston Renewable Energy Pa, The Airfield, Chelveston, Wellingborough, Northamptonshire | Northamptonshire | East Midlands | England | NN9 6AR | 500254 | 269084 | East Northamptonshire Council | 17/00784/FUL | [5 empty] | 2017-04-20 | [6 empty] | 2017-06-15 |  |  |  |  | 2019-07-01
| 6942 | 2020-05-27 | Enstor Power UK | Tofts Lane | Battery | Stand-alone Storage | n/a | 40 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Tofts Lane, Snowden Hill, Barnsley | South Yorkshire | Yorkshire and Humber | England | S36 8YR | 425805 | 400394 | Barnsley Council | 2017/0624 | [5 empty] | 2017-05-03 | [6 empty] | 2017-09-07
| 6943 | 2019-08-13 | Vattenfall Wind Power | Ray Battery Storage Facility | Battery | Co-located with RE | 4026 | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Ray Wind Farm, Kirkwhelpington, Newcastle Upon Tyne, Northumberland | Northumberland | North East | England | NE19 2RG | 395129 | 585703 | Northumberland County Council | 17/01923/RENE | [5 empty] | 2017-05-30 | [6 empty] | 2017-07-25 |  |  |  | 2022-07-25
| 6944 | 2019-09-16 | Green Hedge Energy UK | Pikelaw Place | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Pikelaw Place, Skelmersdale, Lancashire | Lancashire | North West | England | WN8 9PP | 349208 | 404425 | West Lancashire Borough Council | 2017/0563/FUL | [5 empty] | 2017-05-24 | [6 empty] | 2017-07-21
| 6945 | 2019-11-26 | Zenobe (formerly Energy Reservoir 15) | Claredown Farm | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land at Claredown Farm, Hickford Hill, Belchamp St Paul | Essex | Eastern | England | CO10 7DW | 578833 | 244577 | Braintree District Council | 17/00583/FUL | [5 empty] | 2017-04-04 | [6 empty] | 2017-06-05 |  |  |  |  | 2017-09-01 | 2018-02-27
| 6946 | 2020-02-26 | Spencer Farm Produce | The Hollies | Battery | Co-located with RE | 1622 | 24 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | The Hollies, High Lane, Croft | Lincolnshire | East Midlands | England | PE24 4SH | 549998 | 363104 | East Lindsey District Council | S/039/00841/17 | [5 empty] | 2017-05-12 | [6 empty] | 2017-07-17
| 6947 | 2018-11-27 | SSE Renewables | Coire Glas - Phase II | Pumped Storage Hydroelectricity |  | n/a | 1500 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land At Coire Glas, Laggan, Newtonmore, Highlands, | Highland | Scotland | Scotland | PH34 4EA | 226693 | 796765 | Scottish Government (S36) | ECU00000577 | [5 empty] | 2018-03-28
| 6948 | 2019-03-21 | Anesco | Manor Farm Energy Storage | Battery | Co-located with RE | 1694 | 9.6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Manor Farm, Wainfleet Road, Irby-in-the-Marsh, Skegness, Lincolnshire | Lincolnshire | East Midlands | England | PE24 5AY | 546683 | 363395 | East Lindsey District Council | S/051/00772/17 | [5 empty] | 2017-05-02 | [6 empty] | 2017-11-30
| 6949 | 2018-11-23 | RNA Energy | Tollgate Battery Storage Facil | Battery | Stand-alone Storage | n/a | 49.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Tollgate Farm, Tollgate Road, North Mymms | Hertfordshire | Eastern | England | AL4 0NY | 521828 | 205528 | Welwyn Hatfield Borough Council | 6/2017/0702/MAJ | [5 empty] | 2017-04-06 |  | 2017-07-06
| 6950 | 2018-11-23 | Camborne Energy Storage | Foxs Lane | Battery | Stand-alone Storage | n/a | 5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land Off Foxs Lane, Bixhead, Coleford | Gloucestershire | South West | England | GL16 7ED | 359262 | 210910 | Forest of Dean District Council | P0723/17/FUL | [5 empty] | 2017-05-15 | 2017-07-07
| 6951 | 2018-11-23 | Harmony Energy Storage | Station Road | Battery | Stand-alone Storage | n/a | 49.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land Off, Station Road, Nursling, Southampton, SO16 0AH | Hampshire | South East | England | SO16 0AH | 436242 | 115515 | Test Valley Borough Council | 17/01205/FULLS | [5 empty] | 2017-05-09 | 2017-06-22
132 | 6952 | 2020-06-30 | Statera Energy / Minety North Storage | Minety North | Battery | Stand-alone Storage | n/a | 49.99 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land North of Minety Substation Minety | Wiltshire | South West | England | SN16 9RP | 400916 | 189181 | Wiltshire Council | 17/03936/FUL | [5 empty] | 2017-05-09 | [6 empty] | 2017-07-20
| 6953 | 2020-03-12 | Statera Energy / Melksham East Storage | Melksham Substation East Storage | Battery | Stand-alone Storage | n/a | 49.99 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land to the south of Melksham Substation Westlands Farm Westlands Lane Whitley Melksham | Wiltshire | South West | England | SN12 7QG | 389389 | 166695 | Wiltshire Council | 17/04110/FUL | [5 empty] | 2017-05-10 | [6 empty] | 2017-09-28
| 6954 | 2018-11-23 | Anesco | Feckenham Energy Storage System | Battery | Stand-alone Storage | n/a | 18 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land South of Feckenham Energy, Salt Way, Feckenham, Redditch | Worcestershire | West Midlands | England | B96 6JR | 402461 | 261001 | Redditch Borough Council | 17/00453/FUL | [5 empty] | 2017-04-28 | 2017-11-13
| 6955 | 2020-03-12 | Statera Energy / Melksham West Storage | Melksham Substation West Storage | Battery | Stand-alone Storage | n/a | 49.99 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land to the south west of Melksham Substation, Westlands Farm, Westlands Lane, Whitley | Wiltshire | South West | England | SN12 7QG | 389389 | 166695 | Wiltshire Council | 17/04116/FUL | [5 empty] | 2017-05-10 | [6 empty] | 2017-09-28
| 6956 | 2019-05-16 | Anesco | Addison Road | Battery | Stand-alone Storage | n/a | 22 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land West Of Electricity Subst, Addison Road, Toronto | County Durham | North East | England | DL14 7RN | 419207 | 531034 | Durham County Council | DM/17/01439/FPA | [5 empty] | 2017-05-05 | [6 empty] | 2017-08-17 |  |  |  | 2020-08-17
| 6957 | 2018-11-23 | Greenmore Bank Storage | Greenmoor Bank | Battery | Stand-alone Storage | n/a | 49.99 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land to the north of Old Hutton Substation, Greenmoor Bank Old Hutton KENDAL | Cumbria | North West | England | LA8 0NT | 356455 | 489577 | South Lakeland District Council | SL/2017/0425 | [5 empty] | 2017-05-09 |  | 2018-01-05
| 6958 | 2020-01-27 | RNA Energy | Norwich Road Industrial Estate | Battery | Stand-alone Storage | n/a | 40 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Within Norwich Road Industrial Estate West Of Sub Station And North Of Halesworth Business Park Norwich Road Halesworth Suffolk | Suffolk | Eastern | England | IP19 8QJ | 639014 | 278928 | Suffolk Coastal District Council | DC/17/0161/FUL | [5 empty] | 2017-01-16 | [6 empty] | 2017-02-28 |  |  |  | 2020-02-28
| 6960 | 2019-07-18 | Reliable Generation | Land adjacent Bonnybridge Substation | Battery | Stand-alone Storage | n/a | 19.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land To The North Of Scottish Power Falkirk Road Bonnybridge | Falkirk | Scotland | Scotland | FK4 1BA | 284326 | 681187 | Falkirk Council | P/17/0109/FUL | [5 empty] | 2017-03-10 | [6 empty] | 2017-05-09 |  |  |  | 2020-05-08
| 6961 | 2019-01-31 | Aura Power | Lockleaze Energy Storage | Battery | Stand-alone Storage | n/a | 15 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land at the SWEB Estate, Romney Avenue, Lockleaze, Bristol | Avon | South West | England | BS7 9ST | 360403 | 176373 | Bristol City Council | 17/01147/F | [5 empty] | 2017-03-10 | [6 empty] | 2017-05-05 |  |  |  |  | 2017-06-01 | 2017-12-01
| 6962 | 2018-11-27 | Green Hedge Energy Barn | Breach Farm | Battery | Stand-alone Storage | n/a | 39.99 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Breach Farm, Cadley Lane, Caldwell, Swadlincote, Derbyshire | Derbyshire | East Midlands | England | DE12 6RJ | 426431 | 318856 | South Derbyshire District Council | 9/2017/0154 | [5 empty] | 2017-02-16 | 2017-05-05
| 6964 | 2019-09-16 | Green Hedge Energy UK | Watts Group Factory Site | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land at Watts Group Factory Site, Lydney | Gloucestershire | South West | England | GL15 5EL | 363116 | 201920 | Forest of Dean District Council | P0644/17/FUL | [5 empty] | 2017-04-21 | [6 empty] | 2017-07-26 |  |  |  | 2020-07-26
| 6965 | 2019-01-31 | Aura Power | Bransholme, Hull | Battery | Stand-alone Storage | n/a | 18 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land at Bransholme Road, Bransholme, Hull | Humberside | Yorkshire and Humber | England | HU7 4YP | 511541 | 435141 | Kingston upon Hull City Council | 17/00491/FULL | [5 empty] | 2017-04-11 | [6 empty] | 2017-07-14
| 6967 | 2020-05-27 | First Renewable Developments | Wold Road (land south of) Peak Power Generation Plant | Battery | Co-located with RE | 1979 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To The South Of Wold Road, Burton Latimer, Wellingborough, Northamptonshire, | Northamptonshire | East Midlands | England | NN9 5HW | 492344 | 274767 | Kettering Borough Council | KET/2015/0751 | [5 empty] | 2015-09-22 | [6 empty] | 2015-10-21
| 6969 | 2019-02-04 | Barn Energy | Thrybergh Hydroelectric Scheme | Battery | Co-located with RE | n/a | 0.26 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Thrybergh weir, Kilnhurst, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | S64 5TJ | 446375 | 396433 | Rotherham Metropolitan Borough Council | RB2016/1468 | [5 empty] | 2016-11-03 | [6 empty] | 2016-12-14 |  |  |  |  | 2015-01-01 | 2015-10-01
| 6970 | 2019-04-03 | Brockwell Energy | Westfield Restoration and Regeneration Project | Battery | Co-located with RE | 6263 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Westfield Opencast Coal Site, Cardenden, Lochgelly | Fife | Scotland | Scotland | KY5 0JD | 321764 | 695893 | Fife Council | 16/03661/EIA | [5 empty] | 2016-10-31 | [6 empty] | 2018-08-15
| 6972 | 2020-06-16 | Renewable Energy Systems (RES) | Oxford Road | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 33 Oxford Road, Pen Mill Trading Estate, Yeovil, Somerset | Somerset | South West | England | BA21 5HR | 357641 | 116971 | South Somerset District Council | 16/03791/FUL | [5 empty] | 2016-09-06 | [6 empty] | 2016-11-03
| 6976 | 2019-05-09 | Foresight | Port of Tyne | Battery | Stand-alone Storage | n/a | 35 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Port of Tyne, Tyne Dock, South Shields, Tyne & Wear | Tyne and Wear | North East | England | NE34 9PT | 434923 | 564875 | South Tyneside Council | ST/0867/16/FUL | [5 empty] | 2016-09-07 | [6 empty] | 2016-10-21 |  |  |  |  | 2018-04-01 | 2018-07-01
| 6977 | 2020-03-12 | Statera Energy | Wolverhampton West Sub Station | Battery | Stand-alone Storage | n/a | 49.99 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land East of West Wolverhampton West Sub Station, Langley Road, Wolverhampton | Staffordshire | West Midlands | England | WV3 8EA | 387595 | 297280 | South Staffordshire Council | 16/00747/FUL | [5 empty] | 2016-08-22 | [6 empty] | 2016-10-21
| 6979 | 2020-05-27 | Car Hill Power | J3 Business Park | Battery | Co-located with fossil fuel plant | n/a | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | J3 Business Park, Balby Carr Bank, Balby, Doncaster | South Yorkshire | Yorkshire and Humber | England | DN4 8DE | 458327 | 400980 | Doncaster Council | 16/02055/FUL | [5 empty] | 2016-08-12 | [6 empty] | 2016-09-23
| 6981 | 2019-08-15 | ENGIE Renewables | Former Rugeley Power Station | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Rugeley Power Station, Armitage Road, Rugeley, Staffordshire | Staffordshire | West Midlands | England | WS15 1PR | 405398 | 317702 | Cannock Chase Council | CH/17/214 | [5 empty] | 2017-05-25 | [6 empty] | 2017-08-31
| 6982 | 2018-11-23 | Astra Ventures | Batham Gate Battery Storage Development | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land off Batham Gate Road, North of Buxton, in close proximity to the primary substation off Waterswallows Lane. | Derbyshire | East Midlands | England | SK17 7HS | 407548 | 375903 | High Peak Borough Council | HPK/2017/0312 | APP/H1033/W/17/3186235 |  |  |  |  | 2017-06-08 |  | 2017-09-29 | 2017-11-29 |  | 2018-05-29
| 6983 | 2020-05-27 | Gwent Farmers' Community Solar Partnership | Whitson Electricity Substation | Battery | Co-located with RE | 6411 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Caldicot Levels To South Of Whitson Electricity Substation, Broad Street Common, Nash, Newport | Newport | Wales | Wales | NP18 2BE | 335210 | 184888 | Newport City Council | 18/0198 | [5 empty] | 2018-03-07 | [6 empty] | 2018-11-08 |  |  |  | 2021-11-08
| 6984 | 2020-03-23 | Aura Power / South East Grid Storage Two | Rayleigh Transforming Station | Battery | Stand-alone Storage | n/a | 10.8 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Rayleigh Transforming Station, High Mead, Rayleigh, Essex | Essex | Eastern | England | SS6 7AW | 579617 | 190593 | Rochford District Council | 17/00437/FUL | [5 empty] | 2017-05-02 | [6 empty] | 2017-11-08 |  |  |  | 2020-11-08
| 6989 | 2020-03-31 | Muirhall Energy | Tormywheel Wind Farm | Battery | Co-located with RE | 6208 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Tormywheel Wind Farm, Levenseath, Forth | West Lothian | Scotland | Scotland | ML11 8FE | 295290 | 658102 | West Lothian Council | LIVE/0226/FUL/17 | [5 empty] | 2017-03-30 | [6 empty] | 2020-03-06 |  |  |  | 2025-03-06
| 6992 | 2020-02-26 | Ørsted | Burbo Bank Energy Storage | Battery | Co-located with RE | 2487 | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Burbo Banks Electricity Sub Station, BRECK ROAD, POULTON | Merseyside | North West | England | CH44 3EQ | 329964 | 391134 | Wirral Council | APP/17/00463 | [5 empty] | 2017-04-14 | [6 empty] | 2017-06-14 |  |  |  |  | 2018-10-24 | 2018-12-24
| 6993 | 2019-05-09 | EvoEnergy | Trent Basin Community Battery | Battery | Co-located with RE | n/a | 0.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Depot East Of Trent Basin Trent Lane Nottingham | Nottinghamshire | East Midlands | England | NG2 4DF | 459034 | 338800 | Nottingham City Council | 16/02914/PFUL3 | [5 empty] | 2016-12-21 | [6 empty] | 2017-02-15 |  |  |  | 2020-02-15 | 2018-01-24 | 2018-07-15
| 6995 | 2020-03-20 | Camborne Energy Storage | Land at and adjacent to Leicester Forest Services | Battery | Stand-alone Storage | n/a | 1.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Leicester Forest East Services (Baines Lane), Adjoining Land And Land Adjacent To 61 Goodheart Way Leicestershire | Leicestershire | East Midlands | England | LE3 3GB | 453873 | 302669 | Blaby District Council | 17/0936/FUL | [5 empty] | 2017-06-16 | [6 empty] | 2017-09-15
| 6996 | 2019-03-21 | Anesco | Radford Solar Farm - energy storage | Battery | Co-located with RE | 5712 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land On The East Side Of Fosse Way Radford Semele | Warwickshire | West Midlands | England | CV31 1XJ | 435309 | 261924 | Stratford on Avon District Council | 17/01783/FUL | [5 empty] | 2017-06-14 | [6 empty] | 2017-08-09 |  |  |  | 2020-08-09
| 6999 | 2020-05-27 | Low Carbon Storage Investment Company | Blackdyke Farm Battery Storage Project | Battery | Co-located with RE | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Blackdyke Farmhouse Blackford, Road Leading From Tewthwaite Green North to Junction West of Justicetown | Cumbria | North West | England | CA6 4EY | 338273 | 561594 | Carlisle City Council | 17/0616 | [5 empty] | 2017-07-07 | [6 empty] | 2017-09-11
| 7000 | 2020-01-20 | Gridserve Energy Storage | Slamseys Energy Storage | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land North Of Slamseys Farm, Blackley Lane, Great Notley, Essex | Essex | Eastern | England | CM77 7QW | 573901 | 219919 | Braintree District Council | 17/01235/FUL | [5 empty] | 2017-07-06 | [6 empty] | 2017-10-26 |  |  |  |  | 2020-01-13
| 7001 | 2020-06-25 | Renewable Energy Systems (RES) | Stony Energy Storage Facility | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land to the south west of Stony Stratford Substation, south of Stratford Road, Milton Keynes | Buckinghamshire | South East | England | MK19 6DZ | 477740 | 236134 | Aylesbury Vale District Council | 17/02259/APP | [5 empty] | 2017-07-14 | [6 empty] | 2017-10-12
| 7002 | 2018-11-23 | Renewable Energy Systems (RES) | Roaring Hill Energy Storage Facility | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land To East Of Balsillie Avenue And To The South Of The Limekilns Glenrothes Fife | Fife | Scotland | Scotland | KY6 3QH | 325596 | 702254 | Fife Council | 17/01988/FULL | [5 empty] | 2017-06-23 | 2017-09-20
| 7003 | 2020-04-28 | UK Power Reserve | Land off Queenborough Road | Battery | Stand-alone Storage | n/a | 40 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent To 9 Neatscourt Cottages, Queenborough Road, Halfway, Kent | Kent | South East | England | ME12 3RJ | 592600 | 171381 | Swale Borough Council | 17/503032/FULL | [5 empty] | 2017-06-08 | [6 empty] | 2018-10-30 |  |  |  | 2021-10-30
| 7004 | 2020-02-04 | London Borough of Hounslow | Southall Lane Waste Depot | Battery | Co-located with RE | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Waste Depot, Southall Lane, Southhall, Hounslow | Greater London | London | England | UB2 5XG | 510749 | 178630 | Hounslow London Borough Council | P/2017/2665 | [5 empty] | 2017-06-22 | [6 empty] | 2017-10-06 |  |  |  | 2020-10-05
| 7005 | 2019-06-13 | Harmony Energy Storage | Creyke Substation | Battery | Stand-alone Storage | n/a | 49.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South East Of Lawns Farm, Park Lane, Cottingham, East Riding Of Yorkshire | Humberside | Yorkshire and Humber | England | HU16 5SB | 504478 | 435057 | East Riding of Yorkshire Council | 17/01993/STPLF | [5 empty] | 2017-04-06 | [6 empty] | 2017-11-17
| 7007 | 2020-06-04 | Max Design Consultancy | Aven Industrial Estate | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Aven Industrial Estate, Tickhill Road, Maltby | South Yorkshire | Yorkshire and Humber | England | S66 7QR | 455593 | 392111 | Rotherham Metropolitan Borough Council | RB2017/0910 | [5 empty] | 2017-06-16 | [6 empty] | 2018-06-19
| 7011 | 2020-04-29 | Hall Farm Energy | Litchlake Farm | Battery | Co-located with fossil fuel plant | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent To Henwood Farm Land At Litchlake Farm, Adjacent To Henwood Farm, Buckingham Road, Silverstone | Buckinghamshire | South East | England | NN12 8TJ | 466365 | 242159 | Aylesbury Vale District Council | 17/02081/APP | [5 empty] | 2017-05-31 | [6 empty] | 2017-12-07
| 7012 | 2019-11-27 | Flexible Grid Power | Land off Shilton Lane | Battery | Stand-alone Storage | n/a | 19 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land Bet Shilton Cottage & M89, Shilton Lane, Bishopton, Strathclyde | Renfrewshire | Scotland | Scotland | PA7 5PR | 245343 | 671600 | Renfrewshire Council | 17/0592/PP | [5 empty] | 2017-08-21 | [6 empty] | 2017-11-07
| 7014 | 2020-02-12 | Arlington Energy (formerly Enso Energy) | Ravensroost Farm | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent Ravensroost Farm, Minety, Malmesbury, Wiltshire | Wiltshire | South West | England | SN16 9RJ | 403012 | 188462 | Wiltshire Council | 18/04914/FUL | [5 empty] | 2018-06-15 | [6 empty] | 2018-10-10
| 7015 | 2020-01-21 | Community Wind Power | Aikengall II Community Wind Farm Battery | Battery | Co-located with RE | 4332 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Aikengall II Community Wind Fa, Innerwick, Dunbar, Lothian | East Lothian | Scotland | Scotland | EH42 1 | 367967 | 668389 | East Lothian Council | 18/00865/P | [5 empty] | 2018-01-10 | [6 empty] | 2019-07-04 |  |  |  | 2022-07-04
| 7016 | 2020-02-04 | Amazon UK Services / Push Energy | Dc1 Boscombe Road | Battery | Co-located with RE | 6711 | 1.7 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Dc1, Boscombe Road, Dunstable, Bedfordshire | Bedfordshire | Eastern | England | LU5 4RW | 502851 | 222456 | Central Bedfordshire Council | CB/18/02801/FULL | [5 empty] | 2018-08-29 | [6 empty] | 2018-10-24
| 7017 | 2020-01-02 | Drax Group | Drax Re-Power | Battery | Co-located with fossil fuel plant | n/a | 200 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | New Road, Drax, Selby, North Yorkshire | Cleveland | North East | England | YO8 8PH | 466381 | 426676 | The Planning Inspectorate - National Infrastructure | N/A | [5 empty] | 2018-06-27 | [6 empty] | 2019-10-04
| 7018 | 2020-05-18 | Capbal | STOR Field 9 | Battery | Stand-alone Storage | n/a | 37 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land East of North Road, Inverkeithing, Dunfermline, Fife | Fife | Scotland | Scotland | KY11 1HT | 313196 | 683767 | Fife Council | 18/01583/PPP | [5 empty] | 2018-06-09 | [6 empty] | 2018-12-06 |  |  |  | 2021-12-06
| 7019 | 2020-05-27 | Thurcroft Energy (Max Design Consultancy) | Nether Moor Field | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Nether Moor Field, Green Lane, Thurcroft, Rotherham, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | S66 | 448748 | 389630 | Rotherham Metropolitan Borough Council | RB2017/1426 | [5 empty] | 2017-09-29 | [6 empty] | 2019-11-22
| 7020 | 2020-04-29 | Green Energy International | Bilbo Solar Farm Energy Storage | Battery | Co-located with RE | 6736 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Bilbo Solar Farm, Moss-side, Crimond, Fraserburgh, Grampian | Aberdeen | Scotland | Scotland | AB43 8QJ | 405327 | 855492 | Aberdeenshire Council | APP/2019/0296 | [5 empty] | 2019-06-26 | [6 empty] | 2019-09-20
| 7021 | 2020-05-18 | Pivot Power | Norwich Substation Storage Facility | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Norwich Main Substation, Mangreen Hall Lane, Dunston, Norwich, Norfolk | Norfolk | Eastern | England | NR14 8PG | 622065 | 302336 | South Norfolk Council | 2018/2017 | [5 empty] | 2018-11-09 | [6 empty] | 2018-11-15 |  |  |  | 2021-11-15
| 7022 | 2020-02-03 | Conrad (Calne) | Land At Dunkeswell Airfield | Battery | Stand-alone Storage | n/a | 6.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At, Dunkeswell Airfield, Dunkeswell Industrial Estate, Honiton, Devon | Devon | South West | England | EX14 4LG | 313798 | 108122 | East Devon District Council | 18/1113/FUL | [5 empty] | 2018-07-06 | [6 empty] | 2018-09-17
| 7023 | 2020-02-04 | Amazon UK Services / Push Energy | Beveridge Lane Battery Storage | Battery | Co-located with RE | 6715 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Amazon Services UK Ltd - BHX2, Beveridge Lane, Ellistown, Coalville, Leicestershire | Leicestershire | East Midlands | England | LE67 1FB | 443165 | 311565 | North West Leicestershire District Council | 18/01437/FULM | [5 empty] | 2018-08-29 | [6 empty] | 2018-10-16 |  |  |  | 2021-10-16
| 7024 | 2020-05-27 | Public Power Solutions | Mannington Battery Storage Plant | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Mannington Depot Telford Way, Service Road, Mannington, Swindon, Wiltshire | Wiltshire | South West | England | SN5 8WA | 412926 | 183867 | Swindon Borough Council | S/17/1879 | [5 empty] | 2017-11-21 | [6 empty] | 2018-02-28
| 7026 | 2020-01-22 | Immersa / Kirkby Battery Storage 2 | Charleywood Road, Knowsley Industrial Park | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Eldapoint, Charleywood Road, Knowsley Industrial Park, Liverpool, Merseyside | Merseyside | North West | England | L33 7SG | 343170 | 398252 | Knowsley Metropolitan Borough Council | 17/00649/FUL | [5 empty] | 2017-10-26 | [6 empty] | 2017-12-21
| 7027 | 2020-02-04 | Amazon UK Services / Push Energy | London Distribution Park | Battery | Co-located with RE | 6723 | 3.77 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | London Distribution Park, Windrush Road, Tilbury, Essex | Essex | Eastern | England | RM18 7AN | 563536 | 176914 | Thurrock Council | 18/01114/FUL | [5 empty] | 2018-08-20 | [6 empty] | 2018-10-29 |  |  |  | 2021-10-29
| 7028 | 2018-11-02 | Harmony Energy | Rye Common Lane | Battery | Stand-alone Storage | n/a | 49.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Blue Bell Lodge, Rye Common Lane, Crondall, Farnham, Surrey | Hampshire | South East | England | GU10 5DE | 478578 | 150676 | Hart District Council | 18/01114/FUL | [5 empty] | 2018-05-23 | 2018-08-30
| 7029 | 2020-06-04 | Lancaster Power | Middleton Clean Energy Plant | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Middleton Clean Energy Plant, Middleton Road, Heysham, Morecambe, Lancashire, LA3 2 | Lancashire | North West | England | LA32 | 341454 | 460919 | Lancaster City Council | 18/01203/FUL | [5 empty] | 2018-10-01 | [6 empty] | 2020-01-17 |  |  |  | 2023-01-17
| 7030 | 2020-03-26 | Capbal | Hilfield Farm Tech | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Hilfield Farm Hilfield Lane Aldenham Watford Hertfordshire | Hertfordshire | Eastern | England | WD25 8DD | 514901 | 196616 | Hertsmere Borough Council | 18/1587/OUT | APP/N1920/W/19/3240825 |  |  |  |  | 2018-08-08 |  | 2019-05-28 | 2019-11-13 |  | 2020-03-24
| 7031 | 2020-02-12 | Arlington Energy (formerly Enso Energy) | Land Adjacent Davanden Kennels | Battery | Stand-alone Storage | n/a | 7.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land adj Davanden Kennels, Cotton Lane, Greenhithe, Kent | Kent | South East | England | DA9 9BB | 556768 | 174850 | Dartford Borough Council | 18/00418/FUL | [5 empty] | 2018-05-03 | [6 empty] | 2018-06-28
| 7032 | 2020-05-27 | Energy Demand and Response | Leighton Hall Farm | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Leighton Hall Farm, Middlewich Road, Leighton, Crewe, Cheshire | Cheshire | North West | England | CW1 4QH | 367911 | 357227 | Cheshire East Council | 17/4941N | [5 empty] | 2017-09-27 | [6 empty] | 2017-11-20
| 7033 | 2020-05-18 | Capbal | Berfern Farm | Battery | Stand-alone Storage | n/a | 5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Berfern Farm, Finnockbog Road, Inverkip, Greenock, Strathclyde | Inverclyde | Scotland | Scotland | PA16 0DA | 220467 | 671157 | Inverclyde Council | 18/0144/IC | [5 empty] | 2018-05-14 | [6 empty] | 2018-08-07
| 7034 | 2020-03-10 | Scottish Power | Carland Cross Wind Farm - Storage | Battery | Co-located with RE | 3976 | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Wind Farm Carland Cross Mitchell Newquay Cornwall | Cornwall | South West | England | TR8 5AY | 184107 | 54669 | Cornwall Council | PA18/09608 | [5 empty] | 2018-08-12 | [6 empty] | 2018-12-17 |  |  |  | 2021-12-17 | 2020-02-01
| 7035 | 2020-06-04 | Lark Gas Assets | Manton Wood | Battery | Co-located with fossil fuel plant | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Former Manton Colliery, Retford Road, Worksop, Nottinghamshire | Nottinghamshire | East Midlands | England | S80 2PU | 460758 | 378442 | Bassetlaw District Council | 17/01303/FUL | [5 empty] | 2017-10-09 | [6 empty] | 2017-12-04
| 7036 | 2020-06-24 | Cory Riverside Energy | Riverside Energy Park | Battery | Co-located with RE | 6535 | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Norman Road, Bexley, London | London | South East | England | DA17 6JY | 549545 | 180595 | The Planning Inspectorate - National Infrastructure | EN010093 | [5 empty] | 2018-11-16 | [6 empty] | 2020-04-09
| 7037 | 2020-02-24 | Lightsource BP | Lathom (Pilkington Technical Centre) Battery Storage | Battery | Co-located with RE | 6513 | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To The E/O Lords Cottage, Hall Lane, Lathom, Ormskirk, Lancashire | Lancashire | North West | England | L40 6JB | 345479 | 408342 | West Lancashire Borough Council | 2018/0409/FUL | [5 empty] | 2018-04-17 | [6 empty] | 2018-07-31
| 7039 | 2020-05-27 | AMPY Energy Services | Salt End Lane | Battery | Co-located with fossil fuel plant | n/a | 49 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Salt End Chemicals Par, Saltend Lane, Preston, Hull, Humberside | Humberside | Yorkshire and Humber | England | HU12 8PP | 516413 | 428413 | East Riding of Yorkshire Council | 17/03771/STPLF | [5 empty] | 2017-11-10 | [6 empty] | 2017-12-12
| 7040 | 2019-07-23 | EDF Energy Renewables | Lackenby | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at, Crow Lane, Old Lackenby, Middlesbrough, Cleveland | Cleveland | North East | England | TS6 8DN | 456654 | 519399 | Redcar and Cleveland Borough Council | R/2017/0564/FF | [5 empty] | 2017-08-17 | [6 empty] | 2017-11-10
| 7041 | 2020-01-22 | Immersa | Fraserburgh Development | Battery | Stand-alone Storage | n/a | 25 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To South East Of Hillcres, Fraserburgh, Grampian | Aberdeen | Scotland | Scotland | AB43 6 | 398525 | 864618 | Aberdeenshire Council | APP/2018/0488 | [5 empty] | 2018-03-16 | [6 empty] | 2018-05-31
| 7042 | 2020-04-20 | Suncredit | Peel Road Energy Centre | Battery | Co-located with fossil fuel plant | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Land opposite Sub Station, Peel Road, Blackpool, Lancashire | Lancashire | North West | England | FY4 5LN | 335774 | 398525 | Fylde Borough Council | 17/0822 | APP/M2325/W/18/3196360 |  |  |  |  | 2017-09-28 |  | 2018-01-02 | 2018-03-14 |  |  | 2018-06-04 | 2018-06-04
| 7043 | 2019-11-27 | CJ Energy | Land To The East Of Wholeflats Road (Grangemouth) | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Unit 2, Land To The East Of, Wholeflats Road, Grangemouth, Central | Falkirk | Scotland | Scotland | FK3 9UY | 293973 | 679925 | Falkirk Council | P/18/0201/FUL | [5 empty] | 2018-04-11 | [6 empty] | 2018-07-17
| 7044 | 2020-03-12 | Statera Energy / Enderby Storage | Enderby Storage, Redcomb Farm | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Opposite Redcomb Farm, Desford Road, Lubbesthorpe, Leicester, Leicestershire | Leicestershire | East Midlands | England | LE19 4AD | 452711 | 300246 | Blaby District Council | 17/1223/FUL | [5 empty] | 2017-10-13 | [6 empty] | 2017-12-20
| 7045 | 2018-10-19 | UK Battery Storage | Harrop Edge Farm | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Harrop Edge Farm, Stephenson Road, Allerton, Bradford, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | BD15 9AG | 408940 | 434920 | Bradford Metropolitan District Council | 18/01635/OUT | [5 empty] | 2018-04-20 | 2018-07-13
| 7046 | 2018-11-27 | Intelligent Land Investments | Red John Pumped Storage | Pumped Storage Hydroelectricity | Stand-alone Storage | n/a | 499 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land 120M NE of South Barn, Dores, Inverness, Highlands | Highland | Scotland | Scotland | IV2 6TU | 261478 | 833306 | Scottish Government (S36) | ECU00000728 | [5 empty] | 2018-11-15
| 7047 | 2020-06-23 | Low Carbon Storage Ireland | Portadown Road | Battery | Stand-alone Storage | n/a | 50 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land @ & 100m S/E of, 87 Portadown Road, Immediately adjacent to NIE, Craigavon, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT62 2BB | 112456 | 506231 | Northern Ireland Planning Service | LA08/2018/0851/F | [5 empty] | 2018-06-18 | [6 empty] | 2018-09-21 |  |  |  | 2023-09-20 | 2020-01-15
| 7048 | 2020-01-31 | RWE Generation | Tilbury Energy Centre | Battery | Co-located with fossil fuel plant | n/a | 100 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Civic Centre, Home Gardens, Dartford | Kent | South East | England | DA1 1DR | 568868 | 176498 | The Planning Inspectorate - National Infrastructure | N/A | [5 empty] | 2018-02-20 | [6 empty] | 2018-03-09
| 7050 | 2020-03-03 | Low Carbon Storage Ireland | Dungannon Energy Storage System | Battery | Stand-alone Storage | n/a | 50 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Under Construction | Under Construction | 77a Ballynakilly Road, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT71 6HG | 97523 | 523089 | Northern Ireland Planning Service | LA09/2018/0803/F | [5 empty] | 2018-06-05 | [6 empty] | 2018-10-08 |  |  |  | 2023-10-07 | 2019-12-01
| 7051 | 2020-05-18 | Pivot Power | Ellbridge Lane | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Sub Station, Ellbridge Lane, Hatt, Saltash, Cornwall | Cornwall | South West | England | PL12 6PU | 240358 | 63237 | Cornwall Council | PA19/03935 | [5 empty] | 2019-06-03 | [6 empty] | 2019-08-28 |  |  |  | 2022-08-28
| 7053 | 2019-11-14 | UK Battery Storage | Elland Storage Project | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To South Of, Lowfields Way, Lowfields Business Park, Elland, West Yorkshire | Greater Manchester | Yorkshire and Humber | England | HX5 9DA | 411689 | 421815 | Calderdale Metropolitan Borough Council | 18/00478/192 | [5 empty] | 2018-04-17 | [6 empty] | 2018-06-01
| 7054 | 2020-05-27 | Derwenthaugh | Land at Derwenthaugh Eco Park | Battery | Stand-alone Storage | n/a | 29 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Derwenthaugh Eco Park, Derwenthaugh Road, Blaydon, Derwenthaugh Indl Estate, Newcastle-Upon-Tyne, Tyne & Wear | Tyne and Wear | North East | England | NE16 3BJ | 420034 | 563262 | Gateshead Metropolitan Borough Council | DC/18/00243/FUL | [5 empty] | 2018-03-14 | [6 empty] | 2018-05-30
| 7055 | 2020-01-31 | Cambridgeshire CC / Bouygues Energies | Meadow Lane Park and Ride | Battery | Co-located with RE | 7330 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Park and Ride Site, The Meadow, Meadow Lane, St Ives | Cambridgeshire | Eastern | England | PE27 4LG | 531958 | 271112 | Cambridgeshire County Council | H/5016/16/CC | [5 empty] | 2017-04-07 | [6 empty] | 2017-07-06
| 7056 | 2020-01-22 | Immersa | Strichen South | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Site S/E of South Redbog Farm, Strichen, Fraserburgh, Grampian | Aberdeen | Scotland | Scotland | AB43 6RP | 398939 | 854433 | Aberdeenshire Council | APP/2018/0525 | [5 empty] | 2018-03-16 | [6 empty] | 2018-05-25
| 7057 | 2020-01-22 | Immersa | Strichen North | Battery | Stand-alone Storage | n/a | 25 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To The North Of, Strichen, Smiddyhill, Fraserburgh, Grampian | Aberdeen | Scotland | Scotland | AB43 6RS | 397549 | 855489 | Aberdeenshire Council | APP/2018/0526 | [5 empty] | 2018-03-16 | [6 empty] | 2018-05-25
| 7058 | 2019-06-13 | Harmony Energy | Chapel Farm | Battery | Stand-alone Storage | n/a | 49.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Chapel Farm, Luton Road, Chalton, Luton, Bedfordshire | Bedfordshire | Eastern | England | LU4 9UJ | 503243 | 226320 | Central Bedfordshire Council | CB/18/01795/FULL | [5 empty] | 2018-05-08 | [6 empty] | 2019-01-18 |  |  |  | 2022-01-18
| 7059 | 2019-10-01 | Farmcare Trading | Easter Parkhead Farm | Battery | Stand-alone Storage | n/a | 19.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land 100m N/E of, 3 Parkhead Road, Parkhead Farm Cottage, Blairgowrie, Tayside | Perth and Kinross | Scotland | Scotland | PH10 6LP | 321782 | 744174 | Perth and Kinross Council | 18/00687/FLL | [5 empty] | 2018-05-23 | [6 empty] | 2018-10-10 |  |  |  | 2021-10-09
| 7060 | 2019-03-21 | Green Hedge Energy | Magnolia Street | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land At Jnc Magnolia Street, Spark Street, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN34 4JJ | 525354 | 409302 | North East Lincolnshire Council | DM/0905/17/FUL | [5 empty] | 2017-09-22 | [6 empty] | 2017-11-15
| 7061 | 2020-01-31 | Noriker Power | Perseverance Road | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Perseverance Road, Perseverance Road, Hereford, Hereford & Worcester | Hereford and Worcester | West Midlands | England | HR4 9SN | 350791 | 241336 | Herefordshire Council | P181659/F | [5 empty] | 2018-05-04 | [6 empty] | 2018-12-21 |  |  |  | 2021-12-21
| 7062 | 2020-03-20 | AMDC Energy | Steyning Battery Energy Storage Facility | Battery | Stand-alone Storage | n/a | 18 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Steyning WWTW, Kings Barn Lane, Steyning, West Sussex | West Sussex | South East | England | BN44 3YR | 518598 | 111969 | Horsham District Council | DC/18/0298 | [5 empty] | 2018-03-07 | [6 empty] | 2018-05-02
| 7063 | 2018-11-23 | Highflat Energy Storage | Highflat Battery Energy Storage | Battery | Stand-alone Storage | n/a | 19.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land At, Cairnmuir Road, East Kilbride, Glasgow, Strathclyde | South Lanarkshire | Scotland | Scotland | G74 4GY | 262458 | 657551 | South Lanarkshire Council | P/18/0528 | [5 empty] | 2018-04-26 | 2018-10-22
| 7064 | 2019-05-16 | Anesco | Lovedean Energy Storage System | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land S/O Lovedean Electricity, Broadway Lane, Lovedean, Land west of, Waterlooville, Hampshire | Hampshire | South East | England | PO8 0SG | 467489 | 113279 | East Hampshire District Council | 57524/001 |  |  |  | 43350 |  | 2017-09-29 |  | 2018-10-02
| 7066 | 2020-05-26 | EDF Energy | Cottam Power Station | Battery | Co-located with fossil fuel plant | n/a | 49 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Cottam Power Station, Cottam, Retford, Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 0EU | 481450 | 378800 | Bassetlaw District Council | 18/00249/FUL | [5 empty] | 2018-02-22 | [6 empty] | 2018-04-17
| 7067 | 2020-01-22 | Ecotricity | Gloucestershire Science and Technology Park | Battery | Stand-alone Storage | n/a | 30 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Hamfield Lane, Berkeley, Gloucestershire | Gloucestershire | South West | England | GL13 9FB | 365607 | 199140 | Stroud District Council | S.18/0019/FUL | [5 empty] | 2018-01-03 | [6 empty] | 2018-04-03
| 7068 | 2019-08-16 | Private Developer | Hadham Road | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Wickham Hall Farm, Hadham Road, Bishops Stortford, Hertfordshire | Hertfordshire | Eastern | England | CM23 1JG | 547338 | 222879 | East Hertfordshire District Council | 3/17/2959/FUL | [5 empty] | 2017-12-22 | [6 empty] | 2018-03-29
| 7070 | 2020-06-04 | STOR Power | Aldon Road | Battery | Co-located with fossil fuel plant | n/a | 6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Off, Aldon Road, Poulton Industrial Estate, Poulton-Le-Fylde, Lancashire | Lancashire | North West | England | FY6 8JL | 335950 | 438956 | Wyre Borough Council | 17/00912/FUL | [5 empty] | 2017-09-29 | [6 empty] | 2018-01-12
| 7071 | 2020-04-28 | UK Power Reserve | Burnley Road | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At, Burnley Road, Simonstone, Burnley, Lancashire | Lancashire | North West | England | BB12 7ND | 377420 | 433312 | Ribble Valley Borough Council | 3/2018/0106 | [5 empty] | 2018-02-22 | [6 empty] | 2018-05-25
| 7072 | 2020-05-18 | Capbal | Kilshaw Street | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent To, 1 - 4 Kilshaw Street, Pemberton, Kilshaw Court, Wigan, Greater Manchester | Greater Manchester | North West | England | WN5 8 | 355265 | 404367 | Wigan Council | A/17/84749/FULL | [5 empty] | 2017-10-25 | [6 empty] | 2018-02-09
| 7073 | 2018-10-19 | Conrad (Calne) | Tiddlywink Barn | Battery | Stand-alone Storage | n/a | 5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Tiddlywink Barn, Tiddly Wink, Yatton Keynell, Chippenham, Wiltshire | Wiltshire | South West | England | SN14 7BY | 387213 | 175784 | Wiltshire Council | 17/10611/FUL | [5 empty] | 2017-11-09 |  | 2017-12-21
| 7074 | 2019-10-28 | British Solar Renewables | Ventura Park | Battery | Stand-alone Storage | n/a | 7 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Ventura Park, 10 Broadshires Way, Carterton, Oxfordshire | Oxfordshire | South East | England | OX18 1AD | 428373 | 207617 | West Oxfordshire District Council | 17/03531/FUL | [5 empty] | 2017-10-27 | [6 empty] | 2017-12-29
| 7075 | 2020-05-27 | Enstor Power | Jenny Field Drive | Battery | Stand-alone Storage | n/a | 5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | The Hydro, Jenny Field Drive, Harrogate, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | HG1 2RP | 429585 | 456441 | Harrogate Borough Council | 17/04644/FUL | [5 empty] | 2017-11-06 | [6 empty] | 2018-01-19
| 7077 | 2020-02-24 | Lightsource BP | Church Farm | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To South Of Church Farm, Church Road, Slapton, Leighton Buzzard, Bedfordshire | Buckinghamshire | South East | England | LU7 9BX | 494195 | 219978 | Aylesbury Vale District Council | 17/04036/APP | [5 empty] | 2017-10-20 | [6 empty] | 2018-01-08
| 7078 | 2020-01-27 | Abham Storage / Statera Energy | Riverford Farm | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Riverford Farm, Zc88 at A384 to Staverton Brid, Staverton, Totnes, Devon | Devon | South West | England | TQ9 6AF | 277179 | 63873 | South Hams District Council | 3360/17/FUL | [5 empty] | 2017-10-18 | [6 empty] | 2018-01-05
| 7079 | 2019-02-26 | Tiger Energy | Long Lands Lane | Battery | Stand-alone Storage | n/a | 12 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Electricity Sub Station, Long Lands Lane, Brodsworth, Doncaster, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | DN5 7XB | 452431 | 407886 | Doncaster Council | 17/02562/FUL | [5 empty] | 2017-10-16 | [6 empty] | 2018-01-08
| 7080 | 2020-03-27 | ABO Wind NI | Armoy Wind Farm | Battery | Co-located with RE | 6546 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Lands approx. 615m East of, 16 Coolkeeran Road, Armoy, 2.5km South East of Armoy, Ballymoney, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT53 8XL | 125543 | 589083 | Northern Ireland Planning Service | LA01/2017/1654/F | 2018/A0199 |  |  |  |  | 2017-12-22 |  | 2018-11-30 | 2019-01-24 |  | 2020-01-08
| 7081 | 2020-01-27 | RNA Energy | Sundridge Hill | Battery | Stand-alone Storage | n/a | 49.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To South Of A228, Sundridge Hill, Cuxton, Rochester, Kent | Kent | South East | England | ME2 1LB | 571652 | 167049 | Medway Council | MC/17/3770 | [5 empty] | 2017-11-14 | [6 empty] | 2017-12-29
| 7082 | 2018-11-27 | The Energy Workshop | Shelley Road | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land North of, Shelley Road, East of substation, Newcastle-Upon-Tyne, Tyne & Wear | Tyne and Wear | North East | England | NE15 9RT | 417371 | 564956 | Newcastle upon Tyne City Council | 2017/1567/01/DET | [5 empty] | 2017-10-09 |  | 2017-12-22
| 7083 | 2018-10-19 | Sterling Power Group | Stainland Road | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land adjacent to, Stainland Road, Elland, Halifax, West Yorkshire | Greater Manchester | Yorkshire and Humber | England | HX4 0AG | 406069 | 419935 | Calderdale Metropolitan Borough Council | 16/01216/FUL | [5 empty] | 2017-09-16 | 2018-02-08
| 7085 | 2020-05-26 | FPC Industry & Enterprise | Severn Road | Battery | Stand-alone Storage | n/a | 18 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At, Severn Road, Hallen, Bristol, Avon | Gloucestershire | South West | England | BS10 7RZ | 354274 | 180141 | South Gloucestershire Council | PT17/4664/F | [5 empty] | 2017-10-05 | [6 empty] | 2017-12-22
| 7086 | 2020-02-24 | Lightsource BP / LL Property Services | Hill Hall | Battery | Co-located with RE | 1292 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land to the West Of Hill Hall, Hawkspur Green, Little Bardfield, Little Sampford Road, Braintree, Essex | Essex | Eastern | England | CM7 4SH | 565295 | 232270 | Uttlesford District Council | UTT/17/3037/FUL | [5 empty] | 2017-10-20 | [6 empty] | 2017-12-22
| 7087 | 2020-04-20 | Volta Energy Storage | Callywhite Lane Commercial Estate | Battery | Stand-alone Storage | n/a | 18 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land On The West Side, Callywhite Lane, Kilner Vaccumation Co Ltd, Dronfield, South Yorkshire | Derbyshire | East Midlands | England | S18 2AA | 436764 | 378148 | North East Derbyshire District Council | 17/01072/FL | [5 empty] | 2017-10-12 | [6 empty] | 2017-12-22
| 7088 | 2020-03-12 | Statera Energy / Dollymans Storage | Dollymans Storage | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land North Of National Grid, Doublegate Lane, Rawreth, Wickford, Essex | Essex | Eastern | England | SS11 8UD | 577686 | 191429 | Rochford District Council | 17/00939/FUL | [5 empty] | 2017-09-25 | [6 empty] | 2017-12-20
| 7089 | 2020-03-12 | Statera Energy / Grendon Storage | Grendon Storage | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Field South East Of Sub Statio, Station Road, Grendon, Wellingborough, Northampton, Northamptonshire | Northamptonshire | East Midlands | England | NN7 1JW | 487933 | 260897 | Wellingborough Borough Council | WP/17/00602/FUL | [5 empty] | 2017-09-28 | [6 empty] | 2017-12-21
| 7090 | 2020-01-27 | Little Fair Energy | Kiln Lane Industrial Estate | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land West Of Netherlands Way, Kiln Lane Industrial Estate, Stallingborough, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN41 8DF | 520537 | 414107 | North East Lincolnshire Council | DM/1016/17/FUL | [5 empty] | 2017-11-02 | [6 empty] | 2017-12-21
| 7091 | 2019-06-27 | Renewable Energy Systems | Fair Oak Lane | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land opposite Chessington Subs, Fair Oak Lane, Kingston-On-Thames, London | Greater London | London | England | KT9 2NS | 517088 | 161611 | Royal Borough of Kingston upon Thames | 17/10404 | APP/Z5630/W/18/3205282 |  |  |  |  | 2017-10-31 |  | 2017-12-19 | 2019-02-14 |  | 2019-06-14
| 7092 | 2018-11-27 | Broadfield Farm Ess | All Alone Lane | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land At All Alone Lane, Northleach, Cheltenham, Gloucestershire | Gloucestershire | South West | England | GL54 3HJ | 410566 | 214278 | Cotswold District Council | 17/04160/FUL | [5 empty] | 2017-10-09 | 2017-12-19
| 7093 | 2019-09-16 | Green Hedge Energy | Rusholme Grange | Battery | Stand-alone Storage | n/a | 35 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Rusholme Grange, Rusholme Lane, Drax, Selby, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO8 8PW | 470197 | 426610 | Selby District Council | 2017/1018/FULM | [5 empty] | 2017-09-15 | [6 empty] | 2017-12-19
| 7094 | 2019-08-12 | Balance Power | Land at Calthwaite | Battery | Stand-alone Storage | n/a | 6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Low Dyke, Calthwaite, Penrith, Cumbria | Cumbria | North West | England | CA11 9PS | 345807 | 538814 | Eden District Council | 17/0925 | [5 empty] | 2017-10-27 | [6 empty] | 2017-12-19
| 7095 | 2020-05-18 | Capbal | Maldon Hall | Battery | Stand-alone Storage | n/a | 40 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Land North West Of Maldon Hall, Spital Road, Maldon, Essex | Essex | Eastern | England | CM9 6D | 584569 | 206779 | Maldon District Council | 17/01106/FUL | APP/X1545/W/18/3204562 |  |  |  |  | 2017-09-29 |  | 2017-12-15 | 2019-01-14 |  |  | 2019-05-13 | 2019-05-13
| 7096 | 2020-04-20 | Volta Energy Storage | Rubber and Allied Products | Battery | Stand-alone Storage | n/a | 40 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Rubber & Allied Products Ltd, Turner Crescent, Newcastle-Under-Lyme, Staffordshire | Staffordshire | West Midlands | England | ST5 7LU | 383353 | 348514 | Newcastle Under Lyme Borough Council | 17/00847/FUL | [5 empty] | 2017-10-20 | [6 empty] | 2017-12-15
| 7097 | 2020-02-25 | Winchester Power | Stockbridge Road | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Stockbridge Road Energy Storag, Land adjacent to B3049, Salters Lane, Winchester, Hampshire | Hampshire | South East | England | SO22 5FP | 445912 | 131325 | Winchester City Council | 17/02575/FUL | [5 empty] | 2017-10-06 | [6 empty] | 2017-12-14
| 7098 | 2019-02-26 | Tiger Energy | Burtonhead Road | Battery | Stand-alone Storage | n/a | 30 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land To South Of Dma Ltd, Burtonhead Road, St. Helens, Merseyside | Merseyside | North West | England | WA9 5DS | 351134 | 394333 | St Helens Council | P/2017/0822/FUL | [5 empty] | 2017-10-03 | [6 empty] | 2017-12-13
| 7099 | 2019-03-15 | Philip Dennis Food Service | Philip Dennis Food Service | Battery | Stand-alone Storage | n/a | 3.75 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land at Philip Dennis Food Ser, Brannam Crescent, Roundswell Business Park, Barnstaple, Devon | Devon | South West | England | EX31 3TD | 253804 | 131592 | North Devon District Council | 63981 | [5 empty] | 2017-10-20 | [6 empty] | 2017-12-12 |  |  |  |  | 2018-01-15 | 2018-05-01
| 7100 | 2020-01-22 | Ecotricity | Sparsholt college | Battery | Stand-alone Storage | 7180 | 2 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Sparsholt College, Stockbridge Road, Sparsholt, Winchester, Hampshire | Hampshire | South East | England | SO21 2NF | 442605 | 132252 | Winchester City Council | 17/02485/FUL | [5 empty] | 2017-09-27 | [6 empty] | 2017-12-08
| 7102 | 2019-02-26 | Tiger Energy | Bochum Parkway | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Battery Storage Site, Bochum Parkway, Sheffield, South Yorkshire | Derbyshire | East Midlands | England | S8 8JR | 435915 | 381617 | North East Derbyshire District Council | 17/00987/FL | [5 empty] | 2017-09-14 | [6 empty] | 2017-11-30
| 7103 | 2019-06-13 | Innogy | Dolgarrog Hydro Power Station | Battery | Co-located with RE | 4881 | 5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Dolgarrog Hydro Power Station, Conway Road, Dolgarrog, Conwy, Gwynedd | Conwy | Wales | Wales | LL32 8QE | 277022 | 367672 | Conwy County Borough Council | 0/44511 | [5 empty] | 2017-10-20 | [6 empty] | 2017-12-06
| 7108 | 2020-05-01 | Hampshire County Council (Southern Water/Enzygo) | Peel Common Waste Water Treatment Works | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Peel Common Wastewater Treatme, Land off Newgate Lane, Peel Common, Fareham, Hampshire | Hampshire | South East | England | PO14 2AH | 456220 | 102877 | Fareham Borough Council | P/17/0886/CC | [5 empty] | 2017-07-27 | [6 empty] | 2017-08-10
| 7109 | 2020-01-21 | Morris & co Handling | South Kirkby Business Park | Battery | Co-located with fossil fuel plant | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Plot 4 South Kirkby Business P, Brigantian Way, South Kirkby, Pontefract, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF9 3TH | 444487 | 411842 | Wakefield Council | 17/02798/FUL | [5 empty] | 2017-10-24 | [6 empty] | 2019-03-14 |  |  |  | 2022-03-14
| 7110 | 2019-10-28 | British Solar Renewables (Sunnydale Farm Energy Storage) | Sunnydale Farm | Battery | Stand-alone Storage | n/a | 4.23 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land North Of Sunnydale, Smeeton Road, Saddington, Leicester, Leicestershire | Leicestershire | East Midlands | England | LE8 0QT | 466650 | 292748 | Harborough District Council | 17/01528/FUL | [5 empty] | 2017-09-07 | [6 empty] | 2017-11-09
| 7111 | 2019-11-27 | CJ Energy | Land Adjacent to 4 Redcote Lane (Armley) | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent, 4 Redcote Lane, Armley, Leeds, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | LS4 2AL | 426967 | 434272 | Leeds City Council | 17/06830/FU | [5 empty] | 2017-10-24 | [6 empty] | 2019-06-07 |  |  |  | 2022-06-07
| 7113 | 2019-12-03 | AMDC Energy / Balanced Grid Solutions | Gaywood Farm | Battery | Stand-alone Storage | n/a | 7.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South Of Gaywood Farm, Hole Lane, Edenbridge, Kent | Kent | South East | England | TN8 6SL | 543533 | 148266 | Sevenoaks District Council | 17/02668/FUL | [5 empty] | 2017-08-18 | [6 empty] | 2017-10-27
| 7114 | 2020-02-21 | KWTN Solar | Coombe Farm | Battery | Co-located with RE | 4752 | 7.5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | J B Wheaton and Sons, Station Road Tatworth and Fort, Chard Junction, Chard, Somerset | Somerset | South West | England | TA20 4QN | 334148 | 104976 | South Somerset District Council | 17/03395/FUL | [5 empty] | 2017-08-18 | [6 empty] | 2017-10-13
| 7115 | 2020-06-04 | STOR Power | Balle Street | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land off, Balle Street, Darwen, Lancashire | Lancashire | North West | England | BB3 0AA | 368328 | 423789 | Blackburn with Darwen Borough Council | 10/17/1198 | [5 empty] | 2017-10-10 | [6 empty] | 2019-01-19 |  |  |  | 2022-01-19
| 7116 | 2020-05-27 | Private Developer | Mill Cottage | Battery | Co-located with RE | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Mill Cottage, 33 Winchcombe Road, Sedgeberrow, Evesham, Hereford & Worcester | Hereford and Worcester | West Midlands | England | WR11 7UA | 402504 | 238758 | Wychavon District Council | 17/01717/HP | [5 empty] | 2017-08-18 | [6 empty] | 2017-10-11
| 7119 | 2020-03-12 | Statera Energy | Penwortham Sub Station | Battery | Stand-alone Storage | n/a | 49.99 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Howick Hall Farm, Howick Cross Lane, Penwortham, Preston | Lancashire | North West | England | PR1 0NS | 350101 | 428155 | South Ribble Borough Council | 07/2017/2821/FUL | [5 empty] | 2017-09-18 | [6 empty] | 2017-11-16 |  |  |  | 2020-11-16
| 7120 | 2020-06-04 | Kiwi Power | Neatscourt | Battery | Stand-alone Storage | n/a | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land Adjacent To 9 Neatscourt, Queenborough Road, Minster on Sea, Sheerness, Kent | Kent | South East | England | ME12 3RJ | 556292 | 174354 | Swale Borough Council | 17/503032/FULL | [5 empty] | 2017-06-08 | [6 empty] | 2018-10-30
| 7121 | 2018-10-23 | Asta Ventures | Ditchers Farm | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land At Ditchers Farm, Slack Lane, Westhoughton, Bolton, Greater Manchester | Greater Manchester | North West | England | BL5 3 | 365223 | 405999 | Bolton Metropolitan Borough Council | 01119/17 | APP/N4205/W/17/3186248 |  |  |  |  | 2017-06-08 |  | 2017-10-05 | 2017-10-30 |  | 2018-01-09
| 7122 | 2019-01-28 | Statera Energy | Creyke Beck | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land to the south of, Park Lane, Cottingham, Humberside | Humberside | Yorkshire and Humber | England | HU16 5SB | 504098 | 434708 | East Riding of Yorkshire Council | 17/01372/STPLF | [5 empty] | 2017-04-20 | [6 empty] | 2017-06-15 |  |  |  |  | 2018-03-01 | 2018-11-01
| 7123 | 2020-04-20 | Volta Energy Storage | Land SE of, Spectrum Business Park | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South East Of, Spectrum Business Park, Wrexham Industrial Estate, Bridge Road, Wrexham, Clwyd | Wrexham | Wales | Wales | LL13 9QA | 337956 | 349414 | Wrexham County Borough Council | P/2017/0469 | [5 empty] | 2017-06-12 | [6 empty] | 2017-10-04
| 7125 | 2019-01-31 | Aura Power | Northway Lane Waste Transfer Station | Battery | Stand-alone Storage | n/a | 7 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Waste Transfer Station, Northway Lane, Tewkesbury, Gloucestershire | Gloucestershire | South West | England | GL20 8HG | 391073 | 233721 | Tewkesbury Borough Council | 17/00117/FUL | [5 empty] | 2017-01-31 | [6 empty] | 2017-05-05
| 7128 | 2020-04-28 | UK Power Reserve | Beaufort Road | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land north of, Beaufort Road, Birkenhead, Merseyside | Merseyside | North West | England | CH41 1HQ | 330370 | 390106 | Wirral Council | APP/16/01212 | [5 empty] | 2016-09-05 | [6 empty] | 2016-11-04
| 7129 | 2018-10-23 | Low Carbon | Huggin's Hall | Battery | Stand-alone Storage | n/a | 40 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Land at Huggin's Hall, Glassenbury Road, Cranbrook, Kent | Kent | South East | England | N17 2QE | 575739 | 135688 | Tunbridge Wells Borough Council | 16/06052/FULL | [5 empty] | 2016-08-01 | [6 empty] | 2016-10-21 |  |  |  |  | 2017-08-13 | 2018-02-13
| 7131 | 2020-04-29 | South Redhouse | Land North of Thornton Road | Battery | Co-located with RE | 5797 | 19.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land North of, Thornton Road, Redhouse Grid Substation, Kirkcaldy, Fife | Fife | Scotland | Scotland | KY1 | 329101 | 695410 | Fife Council | 15/04010/FULL | [5 empty] | 2015-11-03 | [6 empty] | 2016-02-10
| 7133 | 2020-01-21 | Private Developer | North West Of Jameston Farm | Battery | Stand-alone Storage | n/a | 19.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | North West Of Jameston Farm, Dalry, Strathclyde | North Ayrshire | Scotland | Scotland | KA24 4EY | 232189 | 647344 | North Ayrshire Council | 18/00948/PPP | [5 empty] | 2018-10-29 | [6 empty] | 2018-12-07
| 7134 | 2020-03-11 | Muirhall Energy | Land SW of Shilton Cottage | Battery | Stand-alone Storage | n/a | 29.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Site 300 metres South West of, Old Greenock Road, Bishopton, Strathclyde | Renfrewshire | Scotland | Scotland | PA7 5BB | 243794 | 671266 | Renfrewshire Council | 18/0286/PP | [5 empty] | 2018-04-19 | [6 empty] | 2018-10-25
| 7136 | 2019-01-03 | Enso Energy | Gipsy Lane Battery Energy Storage Facility | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land Off, Gipsy Lane, Rochdale, Greater Manchester | Greater Manchester | North West | England | OL11 3HA | 388270 | 411258 | Rochdale Borough Council | 18/01106/FUL | [5 empty] | 2018-10-15 | 2018-12-05
| 7140 | 2020-02-12 | Arlington Energy (formerly Enso Energy) | Calow Green Farm | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Calow Green Farm, Calow Green, Calow, Chesterfield, Derbyshire | Derbyshire | East Midlands | England | S44 5XQ | 441877 | 369573 | North East Derbyshire District Council | 18/01011/FL | [5 empty] | 2018-09-10 | [6 empty] | 2019-01-25 |  |  |  | 2022-01-25
| 7141 | 2019-12-03 | Forepower | Queen Margarets Industrial Estate | Battery | Stand-alone Storage | n/a | 18 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Land At, Queen Margarets Road, Queen Margarets Industrrial Es, Scarborough, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO11 2YH | 503434 | 486609 | Scarborough Borough Council | 18/01627/FL | [5 empty] | 2018-07-23 | [6 empty] | 2018-09-24
| 7143 | 2020-04-29 | New Forest Energy (formerly Somerley Estate) | Land Adj Harmer Warren Quarry | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adj Harmer Warren Quarry, Plumley, Harbridge Drove, Ellingham, Ringwood, Hampshire | Hampshire | South East | England | BH24 3PZ | 413310 | 109700 | New Forest District Council | 17/11630 | [5 empty] | 2017-11-30 | [6 empty] | 2018-02-13
| 7144 | 2019-11-27 | Flexible Grid Power | Unit 15, Borrowmeadow Road | Battery | Stand-alone Storage | n/a | 19 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Unit 15, Land adj and Rear Of Units @, Borrowmeadow Road, Stirling, Central | Stirling | Scotland | Scotland | FK7 7FB | 281090 | 693290 | Stirling Council | 17/00665/FUL | [5 empty] | 2017-08-22 | [6 empty] | 2017-10-25
| 7145 | 2020-06-04 | STOR Power | Holden Way | Battery | Stand-alone Storage | n/a | 6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Off Holden Way, Dukinfield, Greater Manchester | Greater Manchester | North West | England | SK16 5LP | 394931 | 398390 | Tameside Metropolitan Borough Council | 17/00846/FUL | [5 empty] | 2017-04-10 | [6 empty] | 2018-06-25
| 7146 | 2018-11-23 | Peel Land and Property | Eastham Balacing Services Plant | Battery | Stand-alone Storage | n/a | 27 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land adj to Eastham FC of ,, Bankfields Road, Wirral, Merseyside | Merseyside | North West | England | CH62 0BB | 336900 | 380467 | Wirral Council | APP/17/01243 | [5 empty] | 2017-10-04 | 2018-04-04
| 7148 | 2018-11-27 | Private Developer | Kirkhaw Lane | Battery | Co-located with fossil fuel plant | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Industrial Pallet And Transpor, Kirkhaw Lane, Knottingley, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF11 8RD | 447870 | 424886 | Wakefield Council | 17/01857/FUL | [5 empty] | 2017-07-17 |  | 2017-10-06
| 7149 | 2020-04-20 | Volta Energy Storage | Kirkhaw Lane - Resubmission | Battery | Co-located with fossil fuel plant | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Industrial Pallet And Transpor, Kirkhaw Lane, Knottingley, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF11 8RD | 447870 | 424886 | Wakefield Council | 17/02739/FUL | [5 empty] | 2017-10-18 | [6 empty] | 2017-12-22
| 7151 | 2019-09-19 | Grid Code Power | North-East of Spitfire Way - GCP | Battery | Co-located with fossil fuel plant | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To The North East Of, 1 Spitfire Way, Grangemouth | Falkirk | Scotland | Scotland | FK3 9UB | 293750 | 680150 | Falkirk Council | P/17/0563/FUL | [5 empty] | 2017-08-29 | [6 empty] | 2017-11-24
| 7152 | 2020-02-21 | Kiwi Power (formerly Taunton Battery Storage) | Fideoak Mills | Battery | Stand-alone Storage | n/a | 30 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Fideoak Mills, Upcott Road, Bishops Hull, Taunton, Somerset | Somerset | South West | England | TA4 1AF | 319099 | 125158 | Taunton Deane Borough Council | 05/16/0056 | [5 empty] | 2016-12-02 | [6 empty] | 2017-02-23 |  |  |  |  | 2019-09-01
| 7153 | 2020-05-18 | Pivot Power | Taunton Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Taunton Substation, Upcott Road, Bishops Hull, Taunton, Somerset | Somerset | South West | England | TA4 1AF | 319121 | 124936 | Taunton Deane Borough Council | 05/18/0040 | [5 empty] | 2018-09-13 | [6 empty] | 2018-11-26
| 7154 | 2018-11-29 | Century Power | Ferndale Park Newfields Industrial Estate | Battery | Co-located with fossil fuel plant | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Ferndale Park, Century Road, Newfields Industrial Estate, Hull | Humberside | Yorkshire and Humber | England | HU12 8FB | 516137 | 429429 | East Riding of Yorkshire Council | 17/03684/PLF | [5 empty] | 2017-10-27 |  | 2018-07-20
| 7155 | 2019-01-02 | Ørsted | Land at Carnegie Road | Battery | Stand-alone Storage | n/a | 20 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Carnegie Road, Liverpool, Merseyside | Merseyside | North West | England | L13 7HY | 338448 | 391860 | Liverpool City Council | 16F/2680 | [5 empty] | 2016-11-01 | [6 empty] | 2016-12-15 |  |  |  |  | 2018-10-24 | 2018-12-24
| 7156 | 2020-04-20 | Suncredit | Anchor Lane Energy Centre | Battery | Co-located with RE | 6796 | 4 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land adj to Birmingham Canal S, Anchor Lane, Anchor Bridge, Bilston, West Midlands | West Midlands | West Midlands | England | WV14 9NE | 393956 | 294923 | Wolverhampton City Council | 18/01234/FUL | [5 empty] | 2018-10-19 | [6 empty] | 2018-12-21 |  |  |  | 2021-12-21
| 7157 | 2020-01-23 | Coronation Power | Tarland Substation | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To South Of Bogfern Farm, Cushnie, Alford, Grampian | Aberdeen | Scotland | Scotland | AB33 8LP | 352561 | 807158 | Aberdeenshire Council | APP/2018/2702 | [5 empty] | 2018-09-11 | [6 empty] | 2019-01-08 |  |  |  | 2022-01-08
| 7158 | 2019-06-28 | Flexygen | Barnsdale Road | Battery | Co-located with fossil fuel plant | n/a | 3 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land To The West Of, Barnsdale Road, Allerton Bywater, Castleford, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF10 2AX | 442255 | 428407 | Leeds City Council | 18/06374/FU | [5 empty] | 2018-05-11 | 2019-06-13
| 7159 | 2020-06-24 | Energy Consents And Deployment Unit | Greenburn Wind Park | Battery | Co-located with RE | 7865 | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land Adj Former Opencast, Greenburn Wind Park, New Cumnock, Cumnock, Strathclyde | Strathclyde | Scotland | Scotland | KA18 | 256423 | 614614 | Scottish Government (S36) | ECU00002037 | [5 empty] | 2020-03-27
| 7160 | 2020-04-21 | Kells Bes (ABO Wind) | Kells Substation | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Lands at, Doagh Road, Approximately 137m North East, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT71 5BJ | 132477 | 553404 | Northern Ireland Planning Service | LA03/2018/0984/F | 2018/A0248 |  |  |  |  | 2018-10-25 |  | 2019-03-22 | 2019-03-27 |  |  | 2019-11-27 | 2019-11-27 |  |  |  | 2024-11-27
| 7161 | 2020-05-18 | Pivot Power | Braintree Road Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Electricity Sub Station, Braintree Road, 209m From Hoppit House Braintr, 65m From Unnamed Road Cressing, Braintree, Essex | Essex | Eastern | England | CM77 8DJ | 577617 | 221615 | Braintree District Council | 18/01927/FUL | [5 empty] | 2018-10-25 | [6 empty] | 2019-01-16 |  |  |  | 2022-01-16
| 7162 | 2018-12-06 | Greenock Hydro Power | Kip Water Hydro Scheme | Battery | Stand-alone Storage | n/a | 1 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Kip Water Hydro Scheme Powerho, Greenock, Strathclyde | Inverclyde | Scotland | Scotland | PA16 | 221610 | 673062 | Inverclyde Council | 18/0290/IC | [5 empty] | 2018-10-31
| 7163 | 2019-04-01 | Coronation Power / Persimmon Homes | East of Crudie Acre Cottage | Battery | Stand-alone Storage | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Land To East Of Crudie Acre Co, Arbroath, Tayside | Angus | Scotland | Scotland | DD11 3ET | 362057 | 741675 | Angus Council | 18/00810/FULL | [5 empty] | 2018-10-23 |  | 2019-02-01
| 7165 | 2020-05-18 | Capbal | Drumfad Wood | Battery | Stand-alone Storage | n/a | 29.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land North East Of Blackhill, Luss Road, Argyll And Bute, Helensburgh, Strathclyde | Argyll and Bute | Scotland | Scotland | G84 9EE | 231381 | 684279 | Argyll and Bute Council | 18/01749/PPP | [5 empty] | 2018-10-22 | [6 empty] | 2018-12-10
| 7166 | 2020-04-20 | Suncredit | Nottingham Road | Battery | Co-located with fossil fuel plant | n/a |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at, Nottingham Road, Loughborough, Leicestershire | Leicestershire | East Midlands | England | LE11 1EX | 454324 | 320464 | Charnwood Borough Council | P/18/2057/2 | [5 empty] | 2018-12-10 | [6 empty] | 2018-12-21 |  |  |  | 2021-12-21
| 7169 | 2019-09-13 | Dwr Cymru Welsh Water | Sluvad Road Water Treatment Works | Battery | Co-located with RE | 6593 |  | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Trem Y Ffynnon, Sluvad Road, New Inn Pontypool, Torfaen, Pontypool, Gwent | Torfaen | Wales | Wales | NP4 0TA | 332013 | 199276 | Torfaen County Borough Council | 18/P/0707/FUL | [5 empty] | 2018-10-26 | [6 empty] | 2019-03-29 |  |  |  | 2024-03-29
| 7171 | 2020-05-27 | Enstor Energy | Showfield Lane | Battery | Stand-alone Storage | n/a | 5 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land North Of Pyramid Systems, Showfield Lane, Malton, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO17 6BT | 478703 | 472716 | Ryedale District Council | 18/01288/FUL | [5 empty] | 2018-11-29 | [6 empty] | 2019-02-06 |  |  |  | 2022-02-06
| 7172 | 2019-11-14 | UK Battery Storage | Osbaldwick Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Os Field 5070, Hull Road, Dunnington, York, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO19 5L | 464442 | 451746 | York City Council | 18/02659/OUT | [5 empty] | 2018-11-21 | [6 empty] | 2019-02-22 |  |  |  | 2022-02-22
| 7174 | 2020-04-29 | Scottish Power Renewables (formerly Arcus Consultancy Services) | Whitelee Wind Farm Battery Storage Extension | Battery | Co-located with RE | 3489 | 50 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Eaglesham Moor, Whitelee Forest, Fenwick Moor, East Kilbride, South of Glasgow | Renfrewshire | Scotland | Scotland | G76 0PW | 263618 | 646810 | Scottish Government (S36) | ECU00000729 | [5 empty] | 2019-01-30 | [6 empty] | 2019-06-10
| 7177 | 2019-01-03 | Low Carbon Storage Investment Company/ VLC | Cleator | Battery | Stand-alone Storage | n/a | 10 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Operational | Operational | Cleator, Cumbria | Cumbria | North West | England | CA22 2TA | 301067 | 513081 | Copeland Borough Council | [18 empty] | 2017-08-08 | 2018-01-08
| 7179 | 2019-03-26 | Boralex/Infinergy | Shepherd's Rig Wind Farm | Battery | Co-located with RE | 3417 | 6 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Shepherds Rig Windfarm 5KM E/O, Carsphairn, Castle Douglas, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG7 | 262319 | 593591 | Scottish Government (S36) | ECU00000735 | [5 empty] | 2018-12-17
| 7180 | 2020-01-22 | Ecotricity | Sparsholt College (resubmission) | Anaerobic Digestion | n/a | 7100 | 6 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Sparsholt College, Stockbridge Road, Sparsholt, Winchester, Hampshire | Hampshire | South East | England | SO21 2NF | 442605 | 132252 | Winchester City Council | 16/01679/FUL | [5 empty] | 2016-07-19 | [6 empty] | 2016-11-01 |  |  |  | 2019-11-01
| 7181 | 2020-01-22 | Ecotricity | Gloucestershire Science and Technology Park (small) | Battery | Stand-alone Storage | 7067 | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Hamfield Lane, Berkeley, Gloucestershire | Gloucestershire | South West | England | GL13 9FB | 365607 | 199140 | Stroud District Council | S.17/2430/FUL | [5 empty] | 2017-10-25 | [6 empty] | 2017-12-19 |  |  |  | 2020-12-19
| 7182 | 2020-01-22 | Ecotricity | Old Green Farm, Alveston Battery Storage | Battery | Stand-alone Storage | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Agricultural Field Circa 600M South Of Earthcott Green And Circa 297M East Of The B4427 | Gloucestershire | South West | England | BS35 3TD | 364952 | 184630 | South Gloucestershire Council | PT17/1992/RVC | [5 empty] | 2017-04-27 | [6 empty] | 2017-11-17 |  |  |  | 2022-11-17
| 7183 | 2020-01-22 | Ecotricity | Leechpool Farm, Norrington Battery Storage | Battery | Stand-alone Storage | n/a | 13 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Leechpool Farm, Norrington Lane, Broughton Gifford, Melksham | Wiltshire | South West | England | SN12 8LS | 388544 | 164667 | Wiltshire Council | 18/04039/FUL | [5 empty] | 2018-05-10 | [6 empty] | 2018-08-24 |  |  |  | 2021-08-24
| 7184 | 2020-03-12 | Statera Energy | Minety South Battery Storage | Battery | Stand-alone Storage | n/a | 49.99 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land South of Minety Substation Minety | Wiltshire | South West | England | SN16 9RP | 400916 | 189181 | Wiltshire Council | 17/03941/FUL | [5 empty] | 2017-05-05 | [6 empty] | 2017-07-19 |  |  |  | 2020-07-19
| 7185 | 2020-03-12 | Statera Energy | West Didsbury Battery Storage | Battery | Stand-alone Storage | n/a | 49.99 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Sawfield Nurseries Fairy Lane, Sale | Greater Manchester | North West | England | M33 2JU | 381429 | 391372 | Trafford Council | 92459/FUL/17 | [5 empty] | 2017-09-25 | [6 empty] | 2017-12-20 |  |  |  | 2020-12-20
| 7187 | 2020-05-05 | Transition Bro Gwaun | Trecoed Farm | Solar Photovoltaics | n/a | n/a | 8.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Trecoed Farm, Letterston, Haverfordwest | Pembrokeshire | Wales | Wales | SA62 5UN | 192883 | 232451 | Pembrokeshire County Council | 18/0858/PA | [5 empty] | 2018-11-26 | [6 empty] | 2019-01-18 |  |  |  | 2023-04-10
| 7195 | 2019-06-27 | Harmony Energy Storage | Lye Green Energy Storage | Battery | Stand-alone Storage | n/a | 25 | n/a |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land Adjacent To Electricity Transform Station Lycrome Road Chesham Buckinghamshire | Buckinghamshire | South East | England |  | 497567 | 203435 | Chiltern District Council | PL/18/2421/FA | APP/X0415/W/18/3212793 |  |  |  |  | 2018-06-21 |  | 2018-08-24 | 2019-01-09 |  | 2019-04-02
| 7196 | 2020-03-26 | Britaniacrest Recycling | Former Wealden Brickworks Site EfW (resubmission) | EfW Incineration | n/a | n/a | 21 | Yes |  |  |  | n/a | n/a | n/a | n/a | Appeal Granted | Awaiting Construction | Former Wealden Brickworks (Site HB), Langhurstwood Road, Horsham, West Sussex | West Sussex | South East | England | RH12 4QD | 517058 | 134349 | West Sussex County Council | WSCC/015/18/NH | APP/P3800/W/18/3218965 |  |  |  |  | 2018-03-15 |  | 2018-07-11 | 2019-01-14 |  |  | 2020-02-27 | 2020-02-27
| 7197 | 2019-09-25 | Enso Energy | Land at Court Farm | Battery | Stand-alone Storage | n/a |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Land at Court Farm Court Farm LOWER WOODFORD | Wiltshire | South West | England | SP4 6NQ | 412555 | 135109 | Wiltshire Council | 18/00457/FUL | APP/Y3940/W/18/3213367 |  |  |  |  | 2018-01-17 |  | 2018-07-30 | 2019-02-27 |  | 2019-06-17
| 7204 | 2020-07-06 | Brookfield Renewable | Kennoxhead Wind Farm Extension | Wind Onshore | n/a | n/a | 40 | n/a |  |  |  | 2.78 | 18 | 180 | n/a | Planning Application Submitted | Application Submitted | Land north of Southern Upland hills, South Lanarkshire | South Lanarkshire | Scotland | Scotland |  | 276456 | 625384 | Scottish Government (S36) | ECU00002038 | [5 empty] | 2020-03-31
| 7206 | 2020-03-31 | ScottishPower Renewables | Clauchrie Windfarm | Wind Onshore | n/a | n/a | 100 | n/a |  |  |  | 5 | 18 | 200 | n/a | Planning Application Submitted | Application Submitted | Land 6km north east of Barhill, South Ayrshire and Dumfries and Galloway | South Ayrshire | Scotland | Scotland |  | 229552 | 588722 | Scottish Government (S36) | ECU00002001 | [5 empty] | 2019-12-18
| 7208 | 2020-04-16 | Engie Developments Ireland | Classic Marble Showers Site | Battery | Stand-alone Storage | n/a | 48 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | South of Classic Marble (Showe, 31 Garvaghy Bridge Road, Garvaghy, Dungannon, Co Tyrone | Co. Fermanagh | Northern Ireland | Northern Ireland | BT70 2EW | 68914 | 522080 | Fermanagh and Omagh | LA10/2018/1589/F | [5 empty] | 2018-12-18 | [6 empty] | 2019-09-03 |  |  |  | 2024-09-01
| 7209 | 2019-09-27 | Cawdor SDT | Clunas Reservoir | Small Hydro | n/a | n/a | 0.32 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Estate Office, Cawdor, Nairn, Highlands | Highland | Scotland | Scotland | IV12 5RE | 284725 | 850184 | Highland Council | 18/05681/FUL | [5 empty] | 2018-12-19 | 2019-03-25
| 7210 | 2020-05-04 | Regenerco | Unipres building | Solar Photovoltaics | n/a | n/a | 4.9 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Unipres Uk Ltd, Cherry Blossom Way, Washington, Sunderland, Tyne and Wear | Tyne and Wear | North East | England | SR5 3NT | 433100 | 558280 | Sunderland City Council | 18/02055/FUL | [5 empty] | 2018-12-12 | [6 empty] | 2019-03-05 |  |  |  | 2022-03-05
| 7211 | 2019-09-27 | The National Trust | Combe Park Lodge | Small Hydro | n/a | n/a | 0.25 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Combe Park Lodge, Lynton, Devon | Somerset | South West | England | EX35 6LE | 274019 | 147766 | Exmoor National Park | 62/11/18/013 | [5 empty] | 2018-12-12 |  | 2019-09-10
| 7213 | 2020-03-27 | Hill Power | Vestry Road | Wind Onshore | n/a | n/a | 1.5 | n/a |  |  |  | 1.5 | 1 | 100 | n/a | Appeal Granted | Awaiting Construction | 553 Metres South East Of No, 4 Vestry Cladymore, Mowhan, Armagh, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT60 | 100512 | 493306 | Armagh, Banbridge and Craigavon | LA08/2018/1648/F | 2019/A0033 |  |  |  |  | 2018-11-21 |  |  | 2019-05-17 |  |  | 2020-01-06 | 2020-01-06 |  |  |  | 2025-01-05
| 7217 | 2020-01-23 | Coronation Power | Pleasance Road | Battery | Stand-alone Storage | n/a | 45 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land 130M S/E of, Pleasance Road, Coupar Angus Substation, Blairgowrie, Tayside | Perth and Kinross | Scotland | Scotland | PH13 9JB | 321821 | 739152 | Perth and Kinross Council | 19/00513/FLM | [5 empty] | 2019-03-29 | [6 empty] | 2019-09-24 |  |  |  | 2022-09-23
| 7220 | 2020-04-23 | Tesco Stores | Tesco Store Cygnet View | Solar Photovoltaics | n/a | n/a | 0.6 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Cygnet View, Lakeside, Grays, Essex | Essex | Eastern | England | RM20 1TX | 557081 | 179109 | Thurrock Council | 19/00333/PASOND | [5 empty] | 2019-03-04 | [6 empty] | 2019-04-29
| 7221 | 2020-03-31 | ENGIE Renewables | Mauxhall Farm | Solar Photovoltaics | n/a | n/a | 18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Mauxhall Farm, Immingham Road, Stallingborough, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN41 8BS | 519206 | 413210 | North East Lincolnshire Council | DM/1145/19/FUL | [5 empty] | 2019-12-17
| 7222 | 2020-07-06 | University of Edinburgh (Estates Department) | Easter Bush | Solar Photovoltaics | n/a | n/a | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Land 175M NE Of Midlothian Inn, Bush Farm, Roslin, Lothian | Midlothian | Scotland | Scotland | EH25 | 325277 | 664574 | Midlothian Council | 19/00022/DPP | [5 empty] | 2019-01-11 | [6 empty] | 2019-03-15 |  |  |  |  | 2020-06-30
| 7223 | 2020-02-24 | Lightsource BP | Inkersall Grange Farm | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Inkersall Grange Farm, Inkersall Grange Road, Bilsthorpe, Newark, Nottinghamshire | Nottinghamshire | East Midlands | England | NG22 8TN | 462592 | 359434 | Newark and Sherwood District Council | 19/01165/FULM | [5 empty] | 2019-07-01 | [6 empty] | 2019-09-26 |  |  |  | 2022-09-25
| 7224 | 2020-05-04 | Corby | Shelton Road EfW | EfW Incineration | n/a | n/a | 23 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At, Shelton Road, Willowbrook East Industrial Es, Corby, Northamptonshire | Northamptonshire | East Midlands | England | NN17 5XH | 491039 | 291729 | East Northamptonshire Council | 19/00777/NCC | [5 empty] | 2019-04-26 | [6 empty] | 2019-10-04 |  |  |  | 2022-10-03
| 7225 | 2020-04-27 | Batchelor Electrical | Tesco Wombwell Lane | Solar Photovoltaics | n/a | n/a | 0.185 | n/a |  |  |  | n/a | n/a | n/a | Roof | Under Construction | Under Construction | Tesco Extra, Wombwell Lane, Barnsley, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | S70 3NS | 437710 | 404956 | Barnsley Council | 2019/0194 | [5 empty] | 2019-03-12 | [6 empty] | 2019-04-29 |  |  |  |  | 2020-01-20
| 7226 | 2019-08-22 | Shires Hamilton | Blackpark Farm | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Black Park Farm, Nairn, Highlands | Highland | Scotland | Scotland | IV12 5HY | 289712 | 814915 | Highland Council | 19/00702/FUL | [5 empty] | 2019-02-28 | [6 empty] | 2019-05-17 |  |  |  | 2022-05-17
| 7227 | 2020-05-05 | Betchworth Estate | Betchworth Weir | Small Hydro | n/a | n/a | 0.15 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Betchworth House, The Street, Betchworth, Surrey | Surrey | South East | England | RH3 7AE | 521120 | 149552 | Mole Valley District Council | MO/2019/0153 | [5 empty] | 2018-12-21 | [6 empty] | 2019-07-23 |  |  |  | 2022-07-23
| 7229 | 2020-04-27 | Batchelor Electrical | Tesco Superstore Shripney Road | Solar Photovoltaics | n/a | n/a | 0.154 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Superstore, Shripney Road, Bognor Regis, West Sussex | West Sussex | South East | England | PO22 9ND | 493839 | 100536 | Arun District Council | BR/60/19/PD | [5 empty] | 2019-03-11 | [6 empty] | 2019-05-02
| 7230 | 2020-01-22 | Immersa | Land North of Actrees Solar Farm | Battery | Co-located with RE | 5425 | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Actrees Solar Farm, Heathfield, Alkington, Berkeley, Gloucestershire | Gloucestershire | South West | England | GL13 9PP | 370951 | 198185 | Stroud District Council | S.19/0372/FUL | [5 empty] | 2019-03-07 | [6 empty] | 2019-10-10 |  |  |  | 2022-10-10
| 7231 | 2020-06-05 | Dwr Cymru Welsh Water | Ridgehill WPS | Solar Photovoltaics | n/a | n/a | 0.242 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Ridgehill WPS, Twyford, Hereford, Hereford and Worcester | Hereford and Worcester | West Midlands | England | HR2 8AD | 350816 | 235358 | Herefordshire Council | P190599/F | [5 empty] | 2019-02-18 | [6 empty] | 2019-07-09 |  |  |  | 2022-07-09
| 7232 | 2020-01-16 | Glaxosmithkline | Glaxosmithkline Shewalton Road | Solar Photovoltaics | n/a | n/a | 19.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Glaxosmithkline, Shewalton Road, Irvine, Strathclyde | North Ayrshire | Scotland | Scotland | KA11 5AP | 234491 | 636772 | North Ayrshire Council | 19/00163/PP | [5 empty] | 2019-03-14 | [6 empty] | 2019-06-19 |  |  |  | 2022-06-19
| 7233 | 2020-04-23 | Push Energy | Tesco Moatfield Meadow | Solar Photovoltaics | n/a | n/a | 0.275 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Stores Ltd, Moatfield Meadow, Kingsnorth, Ashford, Kent | Kent | South East | England | TN23 3LU | 600573 | 139883 | Ashford Borough Council | 18/01837/AS | [5 empty] | 2018-12-20 | [6 empty] | 2019-02-28
| 7234 | 2020-06-30 | Shires Hamilton | Fordtown Energy Storage | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Abandoned | Abandoned | Fordtown, Kintore, Inverurie, Grampian | Aberdeen | Scotland | Scotland | AB51 0XJ | 377990 | 814576 | Aberdeenshire Council | APP/2019/0373 | [5 empty] | 2019-03-06 | [6 empty] | 2019-08-20 |  |  |  | 2022-08-20
| 7235 | 2020-01-28 | Tesco Stores | Tesco Lottbridge Drove | Solar Photovoltaics | n/a | n/a | 0.16 | n/a |  |  |  | n/a | n/a | n/a |  | Operational | Operational | 21 Lottbridge Drove, Eastbourne, East Sussex | East Sussex | South East | England | BN23 6QD | 562475 | 101031 | Eastbourne Borough Council | 190187 | [5 empty] | 2019-03-08 | [6 empty] | 2019-04-26 |  |  |  |  | 2019-09-11 | 2019-11-15
| 7236 | 2019-06-28 | Radio City Association | Standingstone Hill | Wind Onshore | n/a | n/a | 2.5 | n/a |  |  |  | 2.5 | 1 | 110 | n/a | Planning Permission Refused | Application Refused | Site To North Of Standingstone, Kilbirnie, Strathclyde | North Ayrshire | Scotland | Scotland | KA25 7 | 229172 | 658616 | North Ayrshire Council | 18/01123/PP | [5 empty] | 2019-01-07 |  | 2019-03-06
| 7238 | 2020-04-27 | Push Energy | Tesco Super-Store (Bridge Road) | Solar Photovoltaics | n/a | n/a | 0.382 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Tesco, Bridge Road, Sheerness, Kent | Kent | South East | England | ME12 1RH | 591875 | 175127 | Swale Borough Council | 18/506645/PN14J | [5 empty] | 2019-01-02 | [6 empty] | 2019-02-06 |  |  |  |  | 2019-12-02 | 2020-01-24
| 7240 | 2020-05-11 | Torfaen CBC | Ty Coch Hollybush Way | Solar Photovoltaics | n/a | n/a | 3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Ty Coch, Hollybush Way, Ty Coch, Cwmbran, Gwent | Torfaen | Wales | Wales | NP44 7BA | 329445 | 193181 | Torfaen County Borough Council | 19/P/0464/FUL | [5 empty] | 2019-07-31 | [6 empty] | 2019-10-21 |  |  |  | 2024-10-21
| 7241 | 2020-06-05 | Dwr Cymru Welsh Water | Broomy Hill Water Treatment Works | Solar Photovoltaics | n/a | n/a | 0.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land At Welsh Water Treatment, Broomy Hill, Hereford, Hereford and Worcester | Hereford and Worcester | West Midlands | England | HR4 0LQ | 349676 | 239699 | Herefordshire Council | P190598/F | [5 empty] | 2019-02-18 | [6 empty] | 2019-07-09
| 7242 | 2020-02-21 | Safran Landing Systems | Meteor Business Park | Battery | Stand-alone Storage | n/a | 1.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Unit 4, Hangar Meteor Business Park, Cheltenham Road East, Gloucester, Gloucestershire | Gloucestershire | South West | England | GL2 9QL | 388317 | 222010 | Tewkesbury Borough Council | 19/00093/FUL | [5 empty] | 2019-02-21 | [6 empty] | 2019-04-18 |  |  |  | 2022-04-18 | 2019-04-19 | 2020-01-16
| 7244 | 2020-01-17 | Solar Options for Schools | The Hazeley Academy | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Emperor Drive, Hazeley, Milton Keynes, Buckinghamshire | Buckinghamshire | South East | England | MK8 0PT | 481628 | 236329 | Milton Keynes Council | 19/00475/PANSOL | [5 empty] | 2019-02-22 | [6 empty] | 2019-03-29 |  |  |  |  | 2019-09-23 | 2019-10-16
| 7245 | 2019-03-29 | North East Grains | North East Grains Site | Anaerobic Digestion | n/a | n/a | 0.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land At South Of North East Gr, Longhirst, Morpeth, Northumberland | Northumberland | North East | England | NE61 3HX | 423375 | 588667 | Northumberland County Council | 18/04533/FUL | [5 empty] | 2019-02-25
| 7247 | 2020-01-28 | Push Energy | Tesco Extra Hazelmere | Solar Photovoltaics | n/a | n/a | 0.364 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Pitsea, Basildon, Essex | Essex | Eastern | England | SS13 3JU | 573525 | 187839 | Basildon Borough Council | 18/01749/PVPA | [5 empty] | 2019-01-07 | [6 empty] | 2019-03-01 |  |  |  | 2024-03-01 | 2019-08-27 | 2019-10-04
| 7248 | 2020-02-04 | Amazon UK Services / Push Energy | Amazon Omega Business Park | Solar Photovoltaics | n/a | n/a | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 1Amazon UK Services Ltd - Warr, Orion Boulevard, Great Sankey, Omega South, Warrington, Cheshire | Cheshire | North West | England | WA5 3XA | 356255 | 390209 | Warrington Borough Council | 2018/33362 | [5 empty] | 2019-02-20 | [6 empty] | 2019-05-14 |  |  |  | 2022-05-14
| 7249 | 2020-05-04 | Iron Mountain | Iron Mountain Site | Solar Photovoltaics | n/a | n/a | 0.6 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Iron Mountain, Pennine Way, Hemel Hempstead, Hertfordshire | Hertfordshire | Eastern | England | HP2 5UD | 506854 | 208896 | Dacorum Borough Council | 4/00363/19/OTD | [5 empty] | 2019-02-25 | [6 empty] | 2019-04-17
| 7250 | 2020-02-04 | Amazon UK Services / Push Energy | Amazon Boundary Way | Solar Photovoltaics | n/a | n/a | 2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Amazon Co UK Ltd, Boundary Way, Hemel Hempstead, Hertfordshire | Hertfordshire | Eastern | England | HP2 7LF | 508622 | 208198 | Dacorum Borough Council | 4/00368/19/FUL | [5 empty] | 2019-02-25 | [6 empty] | 2019-06-07 |  |  |  | 2022-06-07
| 7251 | 2020-04-27 | Tesco Stores | Tesco Crab Tree Lane | Solar Photovoltaics | n/a | n/a | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Tesco, Crab Tree Lane, Atherton, Manchester, Greater Manchester | Greater Manchester | North West | England | M46 0AG | 367646 | 402986 | Wigan Council | A/18/86499/14PDJ | [5 empty] | 2018-12-20 | [6 empty] | 2019-02-14 |  |  |  |  | 2020-02-24 | 2020-03-27
| 7252 | 2020-05-26 | Science Museum Group | Building ONE | Solar Photovoltaics | n/a | n/a | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Under Construction | Under Construction | Building One Science Museum Gr, Red Barn, Wroughton, Swindon, Wiltshire | Wiltshire | South West | England | SN4 9LT | 413873 | 179060 | Swindon Borough Council | S/19/0229 | [5 empty] | 2019-02-19 | [6 empty] | 2019-04-18 |  |  |  | 2022-04-18 | 2019-08-01
| 7253 | 2020-05-04 | The City of Cardiff Council | Llanishen High School | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Heol Hir, Llanishen, Cardiff, South Glamorgan | Cardiff | Wales | Wales | CF14 5YL | 317736 | 182168 | Cardiff Council | 19/00333/MNR | [5 empty] | 2019-02-20 | [6 empty] | 2019-03-19 |  |  |  | 2024-03-19
| 7255 | 2019-09-25 | Ashrona Power Systems | River Calder Hydro Scheme | Small Hydro | n/a | n/a | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Appeal Refused | Application Refused | Clyde Muirshiel, Regional Park-Renfrewshire, Lochwinnoch, Strathclyde | Renfrewshire | Scotland | Scotland | PA12 | 231974 | 662325 | Renfrewshire Council | 18/0836/PP | PPA-350-2034 |  |  |  |  | 2018-12-13 |  | 2019-06-19 | 2019-09-19 |  | 2019-09-20
| 7256 | 2020-02-24 | Lightsource BP | The Grange | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | The Grange, Cotham Lane, Hawton, Newark, Nottinghamshire | Nottinghamshire | East Midlands | England | NG24 3RJ | 478920 | 351013 | Newark and Sherwood District Council | 19/01408/FULM | [5 empty] | 2019-08-09 | [6 empty] | 2019-11-29 |  |  |  | 2022-11-28
| 7257 | 2020-03-03 | Eurofoods UK | EFG Food And Technology Park | Solar Photovoltaics | n/a | n/a | 0.48 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | E F G Food Technology Park, Llantarnam Park Way, Llantarnam Industrial Park, Cwmbran, Gwent | Torfaen | Wales | Wales | NP44 3GA | 330147 | 193159 | Torfaen County Borough Council | 19/P/0084/FUL | [5 empty] | 2019-01-21 | [6 empty] | 2019-03-25 |  |  |  | 2024-03-25
| 7258 | 2020-02-24 | Lightsource BP | Streetfield Farm | Solar Photovoltaics | n/a | n/a | 18.32 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Streetfields Farm, Land West of Watling Street, South of Lutterworth Road, Lutterworth, Leicestershire | Warwickshire | West Midlands | England | LE17 4HU | 450726 | 282742 | Rugby Borough Council | R19/0259 | [5 empty] | 2019-02-07 | [6 empty] | 2019-07-18 |  |  |  | 2022-07-18
| 7259 | 2020-05-04 | Iron Mountain | Iron Mountain Building | Solar Photovoltaics | n/a | n/a | 0.25 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 4A Nettlehill Road, Houstoun Industrial Estate, Livingston, Lothian | West Lothian | Scotland | Scotland | EH54 5DL | 305189 | 670062 | West Lothian Council | 0153/FUL/19 | [5 empty] | 2019-02-21 | [6 empty] | 2019-03-29 |  |  |  | 2022-03-29
| 7260 | 2020-05-04 | Repowering London | Westway Sports and Fitness Centre | Solar Photovoltaics | n/a | n/a | 0.15 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 1 Crowthorne Road, Kensington and Chelsea, London | Greater London | London | England | W10 6RP | 523611 | 181199 | Royal Borough of Kensington and Chelsea | PP/19/00080 | [5 empty] | 2018-12-31 | [6 empty] | 2019-02-19 |  |  |  | 2022-02-19
| 7261 | 2020-04-01 | EnergieKontor UK | Hare Craig Windfarm | Wind Onshore | n/a | n/a | 36 | n/a |  |  |  | 4.5 | 8 | 230 | n/a | Planning Application Submitted | Application Submitted | Land At Hare Craig, Muirkirk, Cumnock, Strathclyde | East Ayrshire | Scotland | Scotland | KA18 | 274078 | 630954 | East Ayrshire Council | 20/0001/PP | [5 empty] | 2020-01-31
| 7262 | 2020-01-15 | Eurofoods Group | Eurofoods Building | Solar Photovoltaics | n/a | n/a | 0.6 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Blakemore Wholesale, Clarion Close, Swansea Enterprise Park, Swansea, West Glamorgan | Swansea | Wales | Wales | SA6 8QZ | 268173 | 198054 | City and County Council of Swansea | 2019/0331/FUL | [5 empty] | 2019-02-13 | [6 empty] | 2019-04-09 |  |  |  | 2024-04-09
| 7264 | 2020-06-30 | CleanEarth | Meikleton of Ardonald | Wind Onshore | n/a | n/a | 1 | n/a |  |  |  | 1 | 1 | 135 | n/a | Planning Permission Refused | Application Refused | Meikleton Of Ardonald, Cairnie, Huntly, Grampian | Aberdeen | Scotland | Scotland | AB54 4UB | 345225 | 843717 | Aberdeenshire Council | APP/2019/0351 | [5 empty] | 2019-02-15 |  | 2020-05-29
| 7266 | 2020-05-04 | North Fish | North Hoo Fields | Wind Onshore | n/a | n/a | 0.9 | n/a |  |  |  | 0.9 | 1 | 100 | n/a | Planning Permission Granted | Awaiting Construction | North Hoo Fields, Gremista, Lerwick, Shetland, Shetland Isles | Shetland | Scotland | Scotland | ZE1 | 445388 | 1142745 | Shetland Islands Council | 2019/024/PPF | [5 empty] | 2019-02-11 | [6 empty] | 2019-07-11 |  |  |  | 2022-07-10
| 7267 | 2020-06-16 | Scottish Water | St Margarets Bay | Solar Photovoltaics | n/a | n/a | 0.23 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Dunfermline W W T W, St Margarets Bay, North Queensferry, Rosyth, Inverkeithing, Fife | Fife | Scotland | Scotland | KY11 1HP | 312275 | 681623 | Fife Council | 19/00319/FULL | [5 empty] | 2019-02-08 | [6 empty] | 2019-04-02 |  |  |  | 2022-04-02 | 2019-10-14 | 2020-03-31
| 7269 | 2020-02-04 | National Trust | Lamp Hill Wimpole Estate | Solar Photovoltaics | n/a | n/a | 0.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Wimpole Estate, Arrington, Royston, Hertfordshire | Cambridgeshire | Eastern | England | SG8 0BW | 534250 | 250350 | South Cambridgeshire District Council | S/0449/19/FL | [5 empty] | 2019-02-07 | [6 empty] | 2019-04-26 |  |  |  | 2022-04-26 | 2019-08-01 | 2020-02-04
| 7270 | 2019-09-27 | South Seeds | Myres Hill Wind Turbine Test Centre | Wind Onshore | n/a | n/a | 1 | n/a |  |  |  | 0.5 | 2 | 37 | n/a | Planning Application Withdrawn | Application Withdrawn | Myres Hill Wind Turbine Test S, Enoch Road, Eaglesham, Glasgow, Strathclyde | East Renfrewshire | Scotland | Scotland | G76 | 256838 | 646558 | East Renfrewshire Council | 2019/0069/TP | [5 empty] | 2019-02-01 | 2019-09-24
| 7271 | 2020-05-19 | Private Developer | Tullyaran Road | Wind Onshore | n/a | n/a | 0.225 | n/a |  |  |  | 0.225 | 1 | 31.5 | n/a | Planning Permission Granted | Awaiting Construction | 250m SW of, Tullyaran Road, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 3HL | 86921 | 529738 | Mid Ulster | LA09/2019/0171/F | [5 empty] | 2019-02-07 | [6 empty] | 2019-09-03 |  |  |  | 2024-09-02
| 7272 | 2020-05-18 | Aura Power / Pivot Power | Burwell Main Sub-Station | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land adj to Burwell 400kV Subs, Weirs Drove, Burwell, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB25 0BP | 557976 | 267089 | East Cambridgeshire District Council | 19/00155/FUL | [5 empty] | 2019-01-24 | [6 empty] | 2019-04-29 |  |  |  | 2022-04-29
| 7273 | 2019-09-27 | MCM Renewables | Derrylin Rd and Marble Arch Rd Junction | Wind Onshore | n/a | n/a | 0.75 | n/a |  |  |  | 0.75 | 1 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | 565m S. West of junction of Ma, Derrylin Road, Bellanaleck, Drumnaskill Road Mackan Glebe, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT92 | 32695 | 499349 | Fermanagh and Omagh | LA10/2019/0173/F | [5 empty] | 2019-02-04 | 2019-06-28
| 7274 | 2020-05-04 | Highland Council | Alness Academy | Solar Photovoltaics | n/a | n/a | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Under Construction | Under Construction | Alness Academy, Alness, Highlands | Highland | Scotland | Scotland | IV17 0UY | 265884 | 869312 | Highland Council | 18/05963/FUL | [5 empty] | 2019-01-28 | [6 empty] | 2019-03-18 |  |  |  | 2022-03-18 | 2020-02-01
| 7275 | 2019-03-29 | Solar Options for Schools | St Bedes Inter-Church School | Solar Photovoltaics | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Application Submitted | Application Submitted | Birdwood Road, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB1 3TD | 547902 | 256922 | Cambridge City Council | 19/0136/C14P14 | [5 empty] | 2019-02-05
| 7277 | 2019-09-24 | Private Developer | Hill Street | Anaerobic Digestion | n/a | n/a | 0.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | 155 metres south west of, 61 Ballyards Road, Milford, Armagh, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT60 3NS | 95455 | 502756 | Armagh, Banbridge and Craigavon | LA08/2018/1737/F | [5 empty] | 2018-12-19
| 7278 | 2020-03-31 | River Ridge Holdings | River Ridge MRF | Anaerobic Digestion | n/a | n/a | 6 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 56 Craigmore Road, Garvagh, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 5HF | 97661 | 581585 | Ards and North Down | LA01/2018/1570/F | [5 empty] | 2018-12-20 | [6 empty] | 2020-01-29 |  |  |  | 2025-01-28
| 7279 | 2019-09-27 | United Utilities | Ainsdale Wastewater Treatment Works | Solar Photovoltaics | n/a | n/a | 0.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | NWWA Sewage Treatment Works, Meadow Lane, Halsall, Southport, Merseyside | Lancashire | North West | England | PR8 3RS | 331828 | 411186 | West Lancashire Borough Council | LCC/2018/0058 | [5 empty] | 2018-12-18 | [6 empty] | 2019-03-13 |  |  |  | 2022-03-13 | 2019-07-15 | 2019-09-06
| 7280 | 2019-03-29 | H2O Power Generation | Kegworth Deep Lock | Small Hydro | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land Record Containing Kegwort, Soar Lane, Sutton, Bonington, Derby, Derbyshire | Nottinghamshire | East Midlands | England | DE74 | 449154 | 326797 | Rushcliffe Borough Council | 19/00232/LBC | [5 empty] | 2019-01-29
| 7281 | 2020-05-04 | Highland Council | Lochaber High School (Resubmission) | Solar Photovoltaics | n/a | n/a | 0.27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Camaghael, Fort William, Highlands | Highland | Scotland | Scotland | PH33 7ND | 212357 | 775929 | Highland Council | 19/02587/FUL | [5 empty] | 2019-06-13 | [6 empty] | 2019-08-16 |  |  |  | 2022-08-16 | 2019-10-01 | 2019-12-01
| 7282 | 2020-03-23 | ATTIX CIC | Blackbarn Farm | Small Hydro | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Site To South East Of, Blackbarn Farm, Kilbirnie, Strathclyde | North Ayrshire | Scotland | Scotland | KA25 7JZ | 231548 | 656890 | North Ayrshire Council | 19/00059/PP | [5 empty] | 2019-01-30 | [6 empty] | 2019-02-27 |  |  |  | 2022-02-27
| 7283 | 2020-05-18 | Pivot Power | Sundon Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Sundon 400KV Substation, Waterend Lane, Chalton, Luton, Bedfordshire | Bedfordshire | Eastern | England | LU4 9UL | 503325 | 226795 | Central Bedfordshire Council | CB/19/00200/FULL | [5 empty] | 2019-01-23 | [6 empty] | 2019-04-30 |  |  |  | 2022-04-30
| 7285 | 2019-09-27 | Hallidays Hydropower | Castleford Weir | Small Hydro | n/a | n/a | 0.45 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Castleford Weir, Castleford, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF10 | 442794 | 426004 | Wakefield Council | 18/02889/FUL | [5 empty] | 2019-01-21 | 2019-03-25
| 7286 | 2020-06-05 | Dwr Cymru Welsh Water | Dolymynach | Small Hydro | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Llanerchcawr, Claerwen Valley, Dolymynach Reservoir Dam Nr., Rhayader, Powys | Powys | Wales | Wales | LD6 5HF | 290640 | 261823 | Powys County Council | 19/0112/FUL | [5 empty] | 2019-01-22 | [6 empty] | 2019-03-29 |  |  |  | 2022-03-29
| 7287 | 2020-06-16 | Scottish Water | Perth Wastewater Treatment Works | Solar Photovoltaics | n/a | n/a | 0.42 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Sleepless Inch Waste Water Tre, Rhynd, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 8QJ | 314552 | 722067 | Perth and Kinross Council | 19/00037/FLL | [5 empty] | 2019-02-01 | [6 empty] | 2019-03-22 |  |  |  | 2022-03-21
| 7288 | 2020-05-04 | TF and JH Braime | TF and JH Braime Holdings Factory | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | T F and J H Braime Holdings Plc, Hunslet Road, Hunslet, Leeds, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | LS10 1JZ | 430853 | 432470 | Leeds City Council | 19/00211/FU | [5 empty] | 2019-01-30 | [6 empty] | 2019-03-18 |  |  |  | 2022-03-18
| 7289 | 2020-03-31 | The Green Yard | Slaghtmanus Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 55 | n/a | Planning Permission Granted | Awaiting Construction | Lands 440m East of, 35 Slaghtmanus Road, Derry, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 3EX | 67866 | 576364 | Derry City and Strabane District | LA11/2019/0070/F | [5 empty] | 2019-01-25 | [6 empty] | 2020-03-19 |  |  |  | 2025-03-18
| 7290 | 2020-05-04 | Computacenter UK | Computacenter Warehouse | Solar Photovoltaics | n/a | n/a | 2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Under Construction | Under Construction | Computer centre UK Ltd, Hatfield Avenue, Hatfield, Hertfordshire | Hertfordshire | Eastern | England | AL10 9TW | 521126 | 209843 | Welwyn Hatfield Borough Council | 6/2019/0141/MAJ | [5 empty] | 2019-01-29 | [6 empty] | 2019-05-02 |  |  |  | 2022-05-02 | 2019-11-01
| 7292 | 2020-04-27 | Push Energy | Tesco Super-Store (Garratt Way, Gorton) | Solar Photovoltaics | n/a | n/a | 0.726 | n/a |  |  |  | n/a | n/a | n/a | Roof | Under Construction | Under Construction | Tesco Stores Ltd, Garratt Way/ Hyde Road, Manchester, Greater Manchester | Greater Manchester | North West | England | M18 8LD | 388542 | 396150 | Manchester City Council | 122212/P14J/2018 | [5 empty] | 2019-01-02 | [6 empty] | 2019-02-01 |  |  |  | 2024-02-01 | 2020-03-16
| 7296 | 2020-04-20 | Volta Energy Storage | Whelley Hill Farm | Battery | Stand-alone Storage | n/a | 25 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Whelley Hill Farm, Worset Lane, Hart, Hartlepool, Cleveland | Cleveland | North East | England | TS27 3BH | 445123 | 534084 | Hartlepool Borough Council | H/2018/0508 | [5 empty] | 2019-01-16 | 2019-05-14
| 7297 | 2019-06-28 | Hydro Energy Developments | Moss Moor Service Reservoir | Small Hydro | n/a | n/a | 0.235 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Moss Moor Service Reservoir, Pudding Hill Road, Barnforth, Richmond, North Yorkshire | County Durham | North East | England | DL11 7UG | 415469 | 515095 | Durham County Council | DM/19/00210/FPA | [5 empty] | 2019-01-24 | [6 empty] | 2019-02-21 |  |  |  | 2022-02-21
| 7298 | 2019-09-17 | Volmary | Volmary Site | Solar Photovoltaics | n/a | n/a | 0.18 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Volmary Limited, Station Road, Wisbech St. Mary, Wisbech, Cambridgeshire | Cambridgeshire | Eastern | England | PE13 4RY | 541944 | 309041 | Fenland District Council | F/YR19/0063/F | [5 empty] | 2019-01-24 | [6 empty] | 2019-03-20 |  |  |  | 2022-03-20 | 2019-03-31 | 2019-07-31
| 7299 | 2019-06-28 | Lancing College | Lancing College Campus | Solar Photovoltaics | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | College Drive, Lancing, West Sussex | Hampshire | South East | England | BN15 0RW | 519422 | 106480 | South Downs National Park Authority | SDNP/18/05306/FUL | [5 empty] | 2019-01-22 | 2019-03-11
| 7300 | 2019-06-28 | Tamani | Easter Drumclair Wood | Wind Onshore | n/a | n/a | 4 | n/a |  |  |  | 2 | 2 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | Land to North OfLochview House, Slamannan, Falkirk, Central | Falkirk | Scotland | Scotland | FK1 3BZ | 286869 | 671605 | Falkirk Council | P/19/0023/FUL | [5 empty] | 2019-01-18 | 2019-03-13
| 7301 | 2019-06-28 | Rhos Quarries Holdings | Pont Cyfyng | Small Hydro | n/a | n/a | 0.42 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Pont Cyfyng, Capel Curig, Betws-Y-Coed, Gwynedd | Conwy | Wales | Wales | LL24 0EA | 273364 | 357174 | Snowdonia National Park Authority | NP4/13/244 | [5 empty] | 2019-01-11 | 2019-02-26
| 7303 | 2020-05-04 | Renewables First | Naburn Weir Hydro | Small Hydro | n/a | n/a | 0.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Naburn Locks, York Road, Naburn, York, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO19 4RU | 459358 | 444555 | York City Council | 18/02552/FUL | [5 empty] | 2019-01-08 | [6 empty] | 2020-01-20 |  |  |  | 2023-01-20
| 7304 | 2019-12-20 | Green Cat Renewables | Deuchries Windfarm (extension) | Wind Onshore | n/a | n/a | 2 | n/a |  |  |  | 1 | 2 | 119 | n/a | Planning Permission Granted | Awaiting Construction | Land At Deuchries, Near Aberchirder, Huntly, Grampian | Aberdeen | Scotland | Scotland | AB54 7PY | 363721 | 853713 | Aberdeenshire Council | APP/2019/0017 | [5 empty] | 2019-01-17 | [6 empty] | 2019-10-08 |  |  |  | 2022-10-08
| 7305 | 2020-05-04 | Argyll Hydro Management | Garvie Burn | Small Hydro | n/a | n/a | 0.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land App 1776 Metres SE Of Gar, Glendaruel, Colintraive, Strathclyde | Argyll and Bute | Scotland | Scotland | PA22 3AE | 205457 | 690018 | Argyll and Bute Council | 18/02697/PP | [5 empty] | 2019-01-14 | [6 empty] | 2019-03-01 |  |  |  | 2022-03-01
| 7307 | 2020-03-23 | Eclipse Power Generation | Silver Spinney Farm | Battery | Stand-alone Storage | n/a | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Silver Spinney Farm, Deanshanger Road, Wicken, Milton Keynes, Buckinghamshire | Northamptonshire | East Midlands | England | MK19 6BS | 475259 | 239436 | South Northamptonshire Council | S/2019/0086/FUL | [5 empty] | 2019-01-14 | [6 empty] | 2019-03-08 |  |  |  | 2022-03-08
| 7310 | 2020-05-04 | Highland Council | Invergordon Academy | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Invergordon Sports Centre, Academy Road, Invergordon, Highlands | Highland | Scotland | Scotland | IV18 0LD | 270904 | 869074 | Highland Council | 18/05962/FUL | [5 empty] | 2019-01-11 | [6 empty] | 2019-02-27 |  |  |  | 2022-02-27 | 2019-08-01 | 2019-11-01
| 7311 | 2019-06-28 | Elgin Energy | Tuckey Farm (Resubmission) | Solar Photovoltaics | n/a | n/a | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Tuckey Farm, East Claydon Road, Winslow, Buckingham, Buckinghamshire | Buckinghamshire | South East | England | MK18 3ND | 475130 | 226669 | Aylesbury Vale District Council | 19/00983/APP | [5 empty] | 2019-03-25
| 7312 | 2020-01-30 | Keele University | The Low Carbon Energy Generation Project at Keele University | Wind Onshore | n/a | n/a | 1 | n/a |  |  |  | 0.5 | 2 | 77 | n/a | Planning Permission Granted | Awaiting Construction | Land Adj To Springpool Wood, Keele, Newcastle-Under-Lyme, Staffordshire | Staffordshire | West Midlands | England | ST5 5BW | 381909 | 344989 | Newcastle Under Lyme Borough Council | 18/00933/FUL | [5 empty] | 2018-12-20 | [6 empty] | 2019-08-30 |  |  |  | 2022-08-30
| 7313 | 2020-05-20 | Private Developer | Craig Farm | Small Hydro | n/a | n/a | 0.42 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land North Of, Edendonich, Dalmally, Strathclyde | Argyll and Bute | Scotland | Scotland | PA33 1AU | 216482 | 728103 | Argyll and Bute Council | 18/02654/PP | [5 empty] | 2019-01-04 | [6 empty] | 2019-03-27 |  |  |  | 2022-03-27 | 2020-05-20
| 7315 | 2020-04-29 | Harmony Energy Storage | Jamesfield Organic Centre | Battery | Stand-alone Storage | n/a | 19 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land 140 Metres North East Of, Jamesfield Organic Centre, Newburgh, Cupar, Fife | Perth and Kinross | Scotland | Scotland | KY14 6EW | 320261 | 717467 | Perth and Kinross Council | 18/02336/FLL | [5 empty] | 2019-01-09 | [6 empty] | 2019-03-07 |  |  |  | 2022-03-06
| 7316 | 2020-05-04 | Mann Power Hydro | The River Irwell | Small Hydro | n/a | n/a | 0.16 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Located South Of, The River Irwell, West Of Littleton Road, Centred On Whit Lane, Salford, Greater Manchester | Greater Manchester | North West | England | M6 6HP | 381448 | 400482 | Salford City Council | 18/72857/FUL | [5 empty] | 2018-12-23 | [6 empty] | 2019-03-29 |  |  |  | 2022-03-29
| 7318 | 2020-03-23 | Glen Creran Hydro | Allt Eilidh | Small Hydro | n/a | n/a | 0.6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land 6500M SE Of Birch View, Duror, Auchindarroch, Appin, Strathclyde | Highland | Scotland | Scotland | PA38 4BS | 206669 | 752800 | Highland Council | 18/05850/FUL | [5 empty] | 2018-12-18 | [6 empty] | 2019-03-31 |  |  |  | 2022-03-31 | 2019-11-01
| 7320 | 2019-05-09 | EvoEnergy | National Space Centre | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | National Space Centre, Exploration Drive, Leicester, Leicestershire | Leicestershire | East Midlands | England | LE4 5NS | 458801 | 306556 | Leicester City Council | 20190026 | [5 empty] | 2019-01-09 | [6 empty] | 2019-02-20 |  |  |  |  | 2019-03-01 | 2019-03-31
| 7321 | 2020-01-28 | Push Energy | Tesco Queensway Place | Solar Photovoltaics | n/a | n/a | 0.306 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Tesco Stores, Queensway Place, Yeovil, Somerset | Somerset | South West | England | BA20 1DL | 355332 | 116050 | South Somerset District Council | 19/00027/PAPV | [5 empty] | 2019-01-03 | [6 empty] | 2019-02-27 |  |  |  |  | 2019-11-18 | 2019-12-20
| 7327 | 2020-05-04 | Renewables First | Gunthorpe Weir | Small Hydro | n/a | n/a | 0.33 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Gunthorpe Weir, Trentside, Gunthorpe, Nottingham, Nottinghamshire | Nottinghamshire | East Midlands | England | NG14 7FB | 468837 | 343682 | Newark and Sherwood District Council | 18/02222/FUL | [5 empty] | 2018-12-17 | [6 empty] | 2019-03-29 |  |  |  | 2022-03-28
| 7328 | 2020-05-20 | Vento Ludens | Allt an t-Sidhein Hydro Scheme | Small Hydro | n/a | n/a | 0.45 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land 730M SE Of Rowan Bank, South Laggan, Spean Bridge, Highlands | Highland | Scotland | Scotland | PH34 4 | 229697 | 797369 | Highland Council | 18/05816/FUL | [5 empty] | 2018-12-18 | [6 empty] | 2019-03-15 |  |  |  | 2022-03-15 | 2020-03-01
| 7329 | 2019-03-29 | Cross Energies | Huntly Road | Wind Onshore | n/a | n/a | 0.5 | n/a |  |  |  | 0.5 | 1 | 53 | n/a | Planning Application Submitted | Application Submitted | Land At 258m West Of, 142 Huntly Road, Banbridge, Co Down | Co. Armagh | Northern Ireland | Northern Ireland | BT32 3UA | 121684 | 505535 | Armagh, Banbridge and Craigavon | LA08/2018/1765/F | [5 empty] | 2018-12-18
| 7330 | 2020-01-31 | Cambridgeshire CC / Bouygues Energies | Meadow Lane Park and Ride | Solar Photovoltaics | n/a | 7055 | 0.948 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Park and Ride Site, The Meadow, Meadow Lane, St Ives | Cambridgeshire | Eastern | England | PE27 4LG | 531958 | 271112 | Cambridgeshire County Council | H/5016/16/CC | [5 empty] | 2017-04-07 | [6 empty] | 2017-07-06 |  |  |  | 2020-07-06
| 7332 | 2020-01-02 | Gridserve | Boscar Grange Farm | Battery | Co-located with RE | 5482 | 27 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Boscar Grange Farm, Thirsk Road, Easingwold, York, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO61 3NQ | 450521 | 472345 | Hambleton District Council | 18/02314/NMC | [5 empty] | 2018-10-29 | [6 empty] | 2018-11-29 |  |  |  |  | 2019-05-23 | 2019-12-18
| 7333 | 2019-04-02 | EDF Renewables | Troston Loch Wind Farm | Battery | Co-located with RE | 6432 | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Troston Loch Wind Farm, New Abbey, West Of Moniaive, Dumfries, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG2 8EF | 268466 | 590107 | Scottish Government (S36) | ECU00001785 | [5 empty] | 2019-02-21
| 7334 | 2019-04-03 | Anesco | Clayhill | Battery | Co-located with RE | 2265 | 6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | North Clayhill Farm, Greenfield Road, Westoning, Bedford, Bedfordshire | Bedfordshire | Eastern | England | MK45 5JD | 504351 | 233195 | Central Bedfordshire Council | CB/14/03419/FULL | [5 empty] | 2014-09-01 | [6 empty] | 2015-01-29 |  |  |  |  | 2016-04-24 | 2016-06-24
| 7335 | 2020-01-27 | RNA Energy | Tollgate Farm Battery Storage (Resubmission) | Battery | Stand-alone Storage | n/a | 49.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Tollgate Farm, Tollgate Road, North Mymms | Hertfordshire | Eastern | England | AL4 0NY | 521828 | 205528 | Welwyn Hatfield Borough Council | 6/2017/2340/FULL | [5 empty] | 2017-10-12 | [6 empty] | 2018-01-05
| 7337 | 2019-12-18 | ScottishPower Renewables | Sheirdrim Renewable Energy Development - Wind | Wind Onshore | n/a | 7585 | 114 | n/a |  |  |  | 6 | 19 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Sheirdrim Windfarm East Of, Clachan, Tarbert, Strathclyde | Strathclyde | Scotland | Scotland | PA29 6 | 181450 | 657720 | Scottish Government (S36) | ECU00001957 | [5 empty] | 2019-10-10
| 7340 | 2020-03-31 | ScottishPower Renewables | Kilgallioch Windfarm (Extension) | Wind Onshore |  |  | 62 | n/a |  |  |  | 5.64 | 11 | 180 | n/a | Planning Application Submitted | Application Submitted | High Eldrig, land 12 km NW of Kirkcowan, SE of Kilgallioch Windfarm | Dumfries and Galloway | Scotland | Scotland |  | 225000 | 570000 | Scottish Government (S36) | ECU00001996 | [5 empty] | 2019-12-16
| 7345 | 2020-07-09 | Blue Energy | High Constellation Wind Farm | Wind Onshore |  |  | 65 | n/a |  |  |  | 6.5 | 10 | 149.9 | n/a | Planning Permission Granted | Awaiting Construction | Mull of Kintyre | Argyll and Bute | Scotland | Scotland |  | 181000 | 651000 | Scottish Government (S36) | ECU00001857 | [5 empty] | 2019-05-28 | [6 empty] | 2020-06-26
| 7346 | 2019-06-28 | Private Developer | Seagahan Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Lands 165 metres south east of, 20 Seagahan Road, Collone, Armagh, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT60 2BJ | 103359 | 499647 | Armagh, Banbridge and Craigavon | LA08/2019/0768/F | [5 empty] | 2019-05-30
| 7347 | 2020-05-04 | Aviva | Aviva Headquarters | Solar Photovoltaics |  |  | 1.8 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Aviva Headquarters Pitheavlis, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH2 0NH | 309819 | 722214 | Perth and Kinross Council | 19/00847/FLL | [5 empty] | 2019-06-07 | [6 empty] | 2019-07-19 |  |  |  | 2022-07-18
| 7350 | 2020-05-04 | Generale Du Solaire | Minnis Farm | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Photovoltaic Installation, Woodstock Road, Land South Of Minnis Farm, Yarnton, Kidlington, Oxfordshire | Oxfordshire | South East | England | OX5 1PQ | 448589 | 211729 | Cherwell District Council | 19/01046/F | [5 empty] | 2019-06-05 | [6 empty] | 2019-10-30 |  |  |  | 2022-10-30
| 7351 | 2019-06-28 | Pivot Power | Lovedean Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Old Mill Lane, Lovedean, Waterlooville, Hampshire | Hampshire | South East | England | PO8 0SN | 467674 | 113928 | South Downs National Park Authority | 19/01071/FUL | [5 empty] | 2019-05-28
| 7353 | 2019-09-27 | Shires Hamilton | Kerrow Farm | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land 690M SW Of Balnabruich, Cannich, Kerrow Farm, Beauly, Highlands | Highland | Scotland | Scotland | IV4 7NA | 232089 | 829779 | Highland Council | 19/00704/FUL | [5 empty] | 2019-03-01 | 2019-06-12
| 7354 | 2020-06-30 | URTV | Laurel Lane | Wind Onshore |  |  | 0.5 | n/a |  |  |  | 0.5 | 1 | 100 | n/a | Planning Permission Granted | Awaiting Construction | 12 Laurel Lane, Belfast, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT14 8SQ | 138301 | 532234 | Antrim and Newtownabbey | LA03/2019/0442/F | [5 empty] | 2019-05-24 | [6 empty] | 2020-04-20 |  |  |  | 2025-04-19
| 7357 | 2020-03-31 | Pivot Power | Fleet Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Land At Fleet Substation, Farnham Road, Crondall, Farnham, Surrey | Hampshire | South East | England | GU10 5 | 478248 | 150922 | Hart District Council | 19/01186/FUL | [5 empty] | 2019-06-04 | 2019-12-30
| 7358 | 2019-06-28 | Brice Aggregates | Colemans Farm | Solar Photovoltaics |  |  | 0.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Colemans Farm, Little Braxted Lane, Rivenhall, Witham, Essex | Essex | Eastern | England | CM8 3EX | 583455 | 215300 | Braintree District Council | 19/00886/FUL | [5 empty] | 2019-05-30
| 7360 | 2020-01-31 | Northern Powergrid | Creyke Beck Substation | Battery | Stand-alone Storage | n/a | 49.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Creyke Beck Substation 4875, Park Lane, Cottingham, Humberside | Humberside | Yorkshire and Humber | England | HU16 5SB | 504356 | 435160 | East Riding of Yorkshire Council | 19/01449/STPLF | [5 empty] | 2019-05-23 | [6 empty] | 2019-11-14 |  |  |  | 2022-11-14
| 7363 | 2020-06-30 | British Solar Renewables | Bracks Farm | Solar Photovoltaics |  |  | 28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Bracks Farm, Wicken, Ely, Cambridgeshire | Cambridgeshire | Eastern | England | CB7 | 558157 | 271520 | East Cambridgeshire District Council | 20/00522/FUM | [5 empty] | 2020-04-21
| 7365 | 2019-08-14 | Private Developer | Barnby Manor | Solar Photovoltaics |  |  | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Barnby Manor, Beckingham Road, Barnby, Newark, Nottinghamshire | Nottinghamshire | East Midlands | England | NG24 2SH | 486207 | 354256 | Newark and Sherwood District Council | 18/02319/FUL | [5 empty] | 2019-03-28 | [6 empty] | 2019-06-04 |  |  |  | 2022-06-04
| 7367 | 2019-06-28 | Private Developer | Tallbridge Road | Wind Onshore |  |  | 0.65 | n/a |  |  |  | 0.65 | 1 | 53 | n/a | Planning Application Submitted | Application Submitted | Lands 370M South East Of, 10 Tallbridge Road, Portadown, Craigavon, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT62 1SF | 103089 | 514872 | Armagh, Banbridge and Craigavon | LA08/2019/0718/F | [5 empty] | 2019-05-20
| 7368 | 2020-05-18 | Pivot Power | Kemsley Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land To The South Of Kemsley S, Ypres Drive, Kemsley, Sittingbourne, Kent | Kent | South East | England | ME10 2 | 591008 | 166650 | Swale Borough Council | 19/502514/FULL | [5 empty] | 2019-05-24 | [6 empty] | 2019-07-19 |  |  |  | 2022-07-19 | 2019-11-15
| 7370 | 2019-09-27 | SR Wind | Southrigg 2 (Resubmission) | Wind Onshore |  |  | 4.2 | n/a |  |  |  | 4.2 | 1 | 150 | n/a | Planning Permission Granted | Awaiting Construction | Southrigg Farm, C1-Torrance Farm To Southrigg, Bathgate, Lothian | North Lanarkshire | Scotland | Scotland | EH48 3AW | 292119 | 665711 | North Lanarkshire Council | 19/00644/FUL | [5 empty] | 2019-05-28 | [6 empty] | 2019-07-31 |  |  |  | 2024-07-31
| 7373 | 2020-01-23 | Good Energy | Eden Project | Battery | Stand-alone Storage | n/a | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Central Processing Unit The Ed, Bodelva Road, Bodelva, Par, Cornwall | Cornwall | South West | England | PL24 2SG | 205153 | 54944 | Cornwall Council | PA19/03137 | [5 empty] | 2019-04-10 | [6 empty] | 2019-05-26 |  |  |  | 2022-05-29
| 7374 | 2019-11-01 | M & G | Flamingo House | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Flamingo Produce, Cockerell Close, Stevenage, Hertfordshire | Hertfordshire | Eastern | England | SG1 2NB | 522853 | 224499 | Stevenage Borough Council | 19/00216/CPAS | [5 empty] | 2019-04-08 | [6 empty] | 2019-05-23
| 7375 | 2020-01-23 | Push Energy / Kingmoor Park | Kingmoor Park | Solar Photovoltaics |  |  | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land West Of, Dukes Drive, Kingmoor Park North, Carlisle, Cumbria | Cumbria | North West | England | CA6 4SH | 337812 | 559940 | Carlisle City Council | 19/0391 | [5 empty] | 2019-05-16 | [6 empty] | 2019-09-12 |  |  |  | 2022-09-12
| 7376 | 2020-01-16 | GlaxoSmithKline | Shewalton Road | Wind Onshore |  |  | 3 | n/a |  |  |  | 1.5 | 2 | 150 | n/a | Planning Permission Granted | Awaiting Construction | Glaxosmithkline, Shewalton Road, Irvine, Strathclyde | North Ayrshire | Scotland | Scotland | KA11 5AP | 234160 | 636667 | North Ayrshire Council | 19/00164/PP | [5 empty] | 2019-03-14 | [6 empty] | 2019-06-19 |  |  |  | 2022-06-19
| 7380 | 2020-01-22 | Immersa | Snarlton Farm | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at Snarlton Farm, Praters Lane Bridleway, Melksham, Wiltshire | Wiltshire | South West | England | SN12 7QP | 393100 | 164313 | Wiltshire Council | 19/02437/FUL | [5 empty] | 2019-03-22 | [6 empty] | 2019-05-16 |  |  |  | 2022-05-16
| 7381 | 2020-01-24 | The Oxfordshire Golf Club | The Oxfordshire Golf Club | Solar Photovoltaics |  |  | 0.25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | The Oxfordshire Golf Club, Rycote Lane, Milton Common, Thame, Oxfordshire | Oxfordshire | South East | England | OX9 2PU | 468108 | 203722 | South Oxfordshire District Council | P19/S1413/FUL | [5 empty] | 2019-05-10 | [6 empty] | 2019-08-05 |  |  |  | 2022-08-05
| 7382 | 2019-12-20 | Elgin Energy | Hangmans Hall Farm | Solar Photovoltaics |  |  | 35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Hangmans Hall Farm, Twenty Acre Lane, Sutton Cheney, Nuneaton, Warwickshire | Leicestershire | East Midlands | England | CV13 0AJ | 442474 | 299432 | Hinckley and Bosworth Borough Council | 19/01256/FUL | [5 empty] | 2019-11-07
| 7383 | 2020-01-31 | Trenport Investments | Plot 2B EurolinkV | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Plot 2B Eurolink V, Sittingbourne, Land orth of Swale Way, Sittingbourne, Kent | Kent | South East | England | ME9 9AR | 592954 | 164443 | Swale Borough Council | 19/502257/FULL | [5 empty] | 2019-05-03 | [6 empty] | 2019-10-25 |  |  |  | 2022-10-25
| 7384 | 2020-03-31 | Low Carbon UK Solar Investment Company | Aurora Solar Farm | Solar Photovoltaics | n/a | 7385 | 32 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Twelve Acre Farm, Chilbridge Road, Eynsham, Witney, Oxfordshire | Oxfordshire | South East | England | OX29 4BH | 441242 | 209314 | West Oxfordshire District Council | 19/02516/FUL | [5 empty] | 2019-09-24 | [6 empty] | 2020-03-23 |  |  |  | 2023-03-23
| 7385 | 2020-06-04 | Low Carbon UK Solar Investment Company | Aurora Solar Farm | Battery | Co-located with RE | 7384 | 18 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Twelve Acre Farm, Chilbridge Road, Eynsham, Witney, Oxfordshire | Oxfordshire | South East | England | OX29 4BH | 441242 | 209314 | West Oxfordshire District Council | 19/02516/FUL | [5 empty] | 2019-09-24 | [6 empty] | 2020-03-23 |  |  |  | 2023-03-23
| 7386 | 2020-04-27 | Batchelor Electrical | Buckingham Tesco Superstore | Solar Photovoltaics |  |  | 0.166 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Stores Ltd, London Road, Buckingham, Buckinghamshire | Buckinghamshire | South East | England | MK18 1AB | 470048 | 232803 | Aylesbury Vale District Council | 19/00589/PVN | [5 empty] | 2019-03-11 | [6 empty] | 2019-04-30
| 7387 | 2019-06-28 | Thompson Renewables | Coa Chapel Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Lands 330m South West Of, 60 Coa Chapel Road, Ballinamallard, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT94 2BE | 38504 | 515543 | Fermanagh and Omagh | LA10/2019/0564/F | [5 empty] | 2019-05-13
| 7391 | 2019-10-31 | Henry Colbeck | Henry Colbeck Office | Solar Photovoltaics |  |  | 0.15 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | 6 South Caldeen Road, Coatbridge, Strathclyde | North Lanarkshire | Scotland | Scotland | ML5 4EG | 274033 | 664118 | North Lanarkshire Council | 19/00331/FUL | [5 empty] | 2019-04-01 | [6 empty] | 2019-05-10 |  |  |  | 2024-05-10 | 2019-02-01 | 2019-03-01
| 7392 | 2019-06-28 | Private Developer | Loughan Road | Wind Onshore |  |  | 0.225 | n/a |  |  |  | 0.225 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Site Approx 552m North West Of, 22 Loughan Road, Dunamanagh, Strabane, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT82 0QE | 61461 | 566061 | Derry City and Strabane District | LA11/2019/0379/F | [5 empty] | 2019-05-01
| 7395 | 2020-06-25 | ScottishPower Renewables | Harestanes Windfarm | Battery | Co-located with RE | 4119 | 100 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Harestanes Windfarm, Forest Of Ae, Northwest Of Ae Village, Moffat, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG10 | 300958 | 597760 | Scottish Government (S36) | ECU00001870 | [5 empty] | 2019-06-20 | [6 empty] | 2019-12-20 |  |  |  | 2022-12-20
| 7397 | 2020-05-19 | Wood Energy | Kingspan | Biomass (dedicated) |  |  | 10 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Kingspan Ltd, St Hildas Street, Sherburn, Malton, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | YO17 8PQ | 496187 | 477052 | Ryedale District Council | 19/00432/MFUL | [5 empty] | 2019-05-07 | [6 empty] | 2019-07-17 |  |  |  | 2022-07-17
| 7398 | 2020-03-31 | EnergieKontor UK | Fell Wind Farm | Wind Onshore |  | 7757 | 49 | n/a |  |  |  | 5.5 | 9 | 200 | n/a | Planning Application Submitted | Application Submitted | Fell Wind Farm, Moniaive, Thornhill, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG3 | 272679 | 583776 | Dumfries and Galloway Council | 20/0148/FUL | [5 empty] | 2020-02-19
| 7400 | 2019-12-17 | Flintshire County Council | Flint Landfill Site Castle Park | Solar Photovoltaics |  |  | 2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Flint Landfill Site, Castle Park Industrial Estate, Flint, Clwyd | Flintshire | Wales | Wales | CH6 5XA | 324099 | 373832 | Flintshire County Council | 59862 | [5 empty] | 2019-04-29 | [6 empty] | 2019-10-07 |  |  |  | 2021-10-07
| 7401 | 2020-04-23 | Tesco Stores | Bellerophon Way Tesco | Solar Photovoltaics |  |  | 0.4 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 2 Bellerophon Way, Haydock, St. Helens, Merseyside | Merseyside | North West | England | WA11 0GT | 355915 | 396670 | St Helens Council | P/2019/0175/SOL | [5 empty] | 2019-03-11 | [6 empty] | 2019-05-03 |  |  |  | 2022-05-03
| 7402 | 2019-06-28 | Private Developer | Aghory Road | Wind Onshore |  |  | 0.85 | n/a |  |  |  | 0.85 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Lands approx. 70m South-West o, 111 Aghory Road, Portadown, Craigavon, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT62 3ST | 107501 | 505182 | Armagh, Banbridge and Craigavon | LA08/2019/0586/F | [5 empty] | 2019-04-18
| 7403 | 2019-06-28 | Shawton Engineering | Carnegie Road (Phase 2) | Battery | Stand-alone Storage | n/a | 40 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Carnegie Road, Liverpool, Merseyside | Merseyside | North West | England | L13 7HY | 338451 | 391858 | Liverpool City Council | 19F/0626 | [5 empty] | 2019-03-11 | [6 empty] | 2019-05-01 |  |  |  | 2022-05-01
| 7404 | 2020-01-23 | Londonwide Properties | Trevol Business Park | Battery | Stand-alone Storage | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At, Trevol Business Park, Torpoint, Cornwall | Cornwall | South West | England | PL11 2TB | 241778 | 55300 | Cornwall Council | PA19/03228 | [5 empty] | 2019-04-12 | [6 empty] | 2019-09-02 |  |  |  | 2022-09-02
| 7405 | 2020-01-29 | J M Stratton and Co | East Codford Solar Farm Extension Phase 3 (Resubmission) | Solar Photovoltaics |  |  | 6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Clay Pit Hill Codford Down Eas, Codford, Warminster, Wiltshire | Wiltshire | South West | England | BA12 0PJ | 399545 | 142177 | Wiltshire Council | 19/03576/FUL | [5 empty] | 2019-04-08 | [6 empty] | 2019-08-02 |  |  |  | 2022-08-02
| 7406 | 2020-02-28 | ERG UK Holding | Evishagaran Wind Farm (Resubmission) | Wind Onshore |  |  | 48 | n/a |  |  |  | 3.43 | 14 | 140 | n/a | Planning Permission Granted | Awaiting Construction | Lands 600 metres south of, 175 Gelvin Road, Dungiven, and east of the American Road, Limavady, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 4QY | 89802 | 570135 | Causeway Coast and Glens | LA01/2018/1151/F | [5 empty] | 2018-09-25 | [6 empty] | 2019-04-18 |  |  |  | 2024-04-17
| 7407 | 2019-06-28 | Private Developer | Camlough Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 78 | n/a | Planning Permission Granted | Awaiting Construction | Approx 800m SW of, 141 Camlough Road, Carrickmore, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 9BJ | 75964 | 536204 | Fermanagh and Omagh | LA10/2019/0320/F | [5 empty] | 2019-03-12 | [6 empty] | 2019-04-30 |  |  |  | 2024-04-28
| 7409 | 2020-01-30 | Keele University | Keele University | Solar Photovoltaics |  |  | 7.57 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Keele, Newcastle-Under-Lyme, Staffordshire | Staffordshire | West Midlands | England | ST5 5BG | 382738 | 344314 | Newcastle Under Lyme Borough Council | 18/00934/FUL | [5 empty] | 2018-12-20 | [6 empty] | 2019-08-30 |  |  |  | 2022-08-30
| 7410 | 2020-04-23 | Batchelor Electrical | Tesco Superstore Bicester | Solar Photovoltaics |  |  | 0.556 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Superstore 4480, Lakeview Drive, Bicester Business Park, Bicester, Oxfordshire | Oxfordshire | South East | England | OX26 1DE | 457956 | 221709 | Cherwell District Council | 19/00268/REN56 | [5 empty] | 2019-03-12 | [6 empty] | 2019-04-29
| 7415 | 2019-06-28 | Fiord Wind | Lisbarnet Road | Wind Onshore |  |  | 0.85 | n/a |  |  |  | 0.85 | 1 | 50 | n/a | Planning Application Submitted | Application Submitted | Land approximately 150m SE of, 32a Lisbarnet Road, Comber, Newtownards, Co Down | Co. Down | Northern Ireland | Northern Ireland | BT23 6AW | 159416 | 517971 | Ards and North Down | LA06/2019/0371/F | [5 empty] | 2019-04-05
| 7417 | 2019-06-28 | Private Developer | Ballindery Road | Wind Onshore |  |  | 0.85 | n/a |  |  |  | 0.85 | 1 | 50 | n/a | Planning Application Withdrawn | Application Withdrawn | Lands 244m north east of, 106 Ballinderry Road, Ballinderry Upper, Lisburn, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT28 2NW | 130990 | 523875 | Lisbury and Caseltreach City Council | LA05/2019/0400/F | [5 empty] | 2019-04-10 | 2019-06-27
| 7418 | 2019-06-28 | Private Developer | Corkley Road | Wind Onshore |  |  | 0.85 | n/a |  |  |  | 0.85 | 1 | 50 | n/a | Planning Application Submitted | Application Submitted | 450m north east of, 26 Corkley Road, Tassagh, Armagh, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT60 2NZ | 97675 | 491501 | Armagh, Banbridge and Craigavon | LA08/2019/0522/F | [5 empty] | 2019-04-09
| 7419 | 2019-12-20 | Hill Power | Boghill Road | Wind Onshore |  |  | 2 | n/a |  |  |  | 2 | 1 | 100 | n/a | Planning Application Withdrawn | Application Withdrawn | Approx. 240m south west of no, 72 Boghill Road, Newtownabbey, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT36 4QT | 140388 | 536939 | Antrim and Newtownabbey | LA03/2019/0272/F | [5 empty] | 2019-04-01 | 2019-11-07
| 7420 | 2020-01-31 | Balanced Grid Solutions | Hamble Lane Battery Energy Storage | Battery | Stand-alone Storage | n/a | 6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land off the B397, Netley Abbey, Hound, Southampton, Hampshire | Hampshire | South East | England | SO31 5FT | 447423 | 108944 | Eastleigh Borough Council | F/19/85302 | [5 empty] | 2019-04-05 | [6 empty] | 2019-11-22 |  |  |  | 2022-11-22
| 7422 | 2020-01-29 | Tamani | Easter Drumclair Wood (Resubmission) | Wind Onshore |  |  | 4 | n/a |  |  |  | 2 | 2 | 100 | n/a | Planning Permission Granted | Awaiting Construction | Land to North OfLochview House, Slamannan, Falkirk, Central | Falkirk | Scotland | Scotland | FK1 3BZ | 286869 | 671605 | Falkirk Council | P/19/0183/FUL | [5 empty] | 2019-03-25 | [6 empty] | 2019-06-24 |  |  |  | 2022-06-23
| 7423 | 2020-05-28 | Intelligent Alternatives | Bourne Road (Extension) | Solar Photovoltaics |  |  | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land North Of Strensham, Bourne Road, Defford, Worcester, Hereford and Worcester | Hereford and Worcester | West Midlands | England | WR8 9B | 390182 | 241597 | Wychavon District Council | 19/01680/FUL | [5 empty] | 2019-07-25 | [6 empty] | 2019-10-23 |  |  |  | 2022-10-23
| 7425 | 2020-03-31 | Intelligent Alternatives | Hatherden Farm | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Hatherden Farm, Hatherden Lane, Hatherden, Andover, Hampshire | Hampshire | South East | England | SP11 0HT | 434283 | 150014 | Test Valley Borough Council | 19/03043/FULLN | [5 empty] | 2019-12-20
| 7426 | 2020-06-08 | Bro Dyfi Community Renewables | Glandulas Mawr Farm | Solar Photovoltaics |  |  | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land On Mynydd Glandulas, Nr. Glan-Dulas Mawr, Mawr Farm Pantperthog, Machynlleth, Powys | Powys | Wales | Wales | SY20 9AX | 276382 | 303977 | Powys County Council | 19/0541/FUL | [5 empty] | 2019-03-29 | [6 empty] | 2019-06-28 |  |  |  | 2024-06-28
| 7428 | 2020-03-31 | Private Developer | Dullaghy Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 52 | n/a | Planning Application Withdrawn | Application Withdrawn | Lands approximately 190m North, 45 Dullaghy Road, Garvagh, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 5PB | 103073 | 572574 | Causeway Coast and Glens | LA01/2019/0268/F | [5 empty] | 2019-03-19 | 2020-02-10
| 7429 | 2020-06-26 | EnergieKontor UK | Wull Muir Wind Farm | Wind Onshore |  | 7430 | 33.6 | n/a |  |  |  | 4.2 | 8 | 130 | n/a | Appeal Lodged | Application Refused | Land North Of Carcant Lodge, Wull Muir Wind Farm, Heriot, Lothian | Scottish Borders | Scotland | Scotland | EH38 | 336253 | 654660 | Scottish Borders Council | 19/00191/FUL | PPA-140-2080 |  |  |  |  | 2019-04-02 |  | 2020-02-05 | 2020-04-14
| 7430 | 2020-06-26 | EnergieKontor UK | Wull Muir Wind Farm | Battery | Co-located with RE | 7429 | 4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Appeal Lodged | Application Refused | Land North Of Carcant Lodge, Wull Muir Wind Farm, Heriot, Lothian | Scottish Borders | Scotland | Scotland | EH38 | 336253 | 654660 | Scottish Borders Council | 19/00191/FUL | PPA-140-2080 |  |  |  |  | 2019-04-02 |  | 2020-02-05 | 2020-04-14
| 7436 | 2019-06-28 | Sperrin Environmental | Bangor Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 52 | n/a | Planning Application Submitted | Application Submitted | Lands app 300m North West of, 239 Bangor Road, Newtownards, Co Down | Co. Down | Northern Ireland | Northern Ireland | BT23 7PH | 162126 | 530795 | Ards and North Down | LA06/2019/0009/F | [5 empty] | 2019-03-07
| 7439 | 2020-01-24 | Liberty Tubes | Tafarnaubach Industrial Estate | Solar Photovoltaics |  |  | 0.85 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Liberty Tubes Tredegar, Tafarnaubach Industrial Estate, Tredegar, Gwent | Blaenau Gwent | Wales | Wales | NP22 3AA | 311422 | 210241 | Blaenau Gwent County Borough Council | C/2019/0052 | [5 empty] | 2019-03-11 | [6 empty] | 2019-04-08 |  |  |  | 2024-04-08
| 7445 | 2020-05-19 | Private Developer | Barony Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 100 | n/a | Planning Permission Granted | Awaiting Construction | 230 Barony Road, Creggan, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 9AQ | 76560 | 541048 | Fermanagh and Omagh | LA10/2019/0323/F | [5 empty] | 2019-03-11 | [6 empty] | 2019-06-24 |  |  |  | 2022-06-20
| 7448 | 2020-04-27 | Push Energy | Hewitts Avenue Tesco | Solar Photovoltaics |  |  | 0.458 | n/a |  |  |  | n/a | n/a | n/a | Roof | Operational | Operational | Tesco Extra, Hewitts Avenue, New Waltham, Cleethorpes, Humberside | Humberside | Yorkshire and Humber | England | DN35 9QR | 529603 | 406481 | North East Lincolnshire Council | DM/1109/18/PNSOL | [5 empty] | 2018-12-28 | [6 empty] | 2019-02-20 |  |  |  |  | 2020-01-06 | 2020-03-06
| 7450 | 2019-06-28 | PJT Power | Drumard Road (repowering) | Wind Onshore |  |  | 0.5 | n/a |  |  |  | 0.5 | 1 | 97 | n/a | Planning Application Submitted | Application Submitted | Approximately 750 m north west, Cullion Road, Draperstown, Drumard Road.junction Straw, Magherafelt, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT45 7 | 92612 | 550025 | Mid Ulster | LA09/2018/1694/F | [5 empty] | 2018-12-21
| 7451 | 2019-12-20 | JBM Solar Projects | Langford Solar Farm | Solar Photovoltaics | n/a | 7661 | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land at NGR 303437 103555 East, Langford Mill and Tye Farm, Cullompton, Devon | Devon | South West | England | EX15 1RE | 303437 | 103555 | Mid Devon District Council | 19/01679/MFUL | [5 empty] | 2019-10-10
| 7456 | 2020-05-28 | Scottish Power Renewables | Hagshaw Hill (Repowering) | Wind Onshore |  |  | 84 | n/a |  |  |  |  | 14 | 200 | n/a | Planning Permission Granted | Awaiting Construction | Hagshaw Hill Wind Farm, Douglas, Lanark | South Lanarkshire | Scotland | Scotland | ML11 0RR | 282089 | 631116 | Scottish Government (S36) | ECU00000737 | [5 empty] | 2018-12-03 | [6 empty] | 2020-02-26 |  |  |  | 2023-02-26
| 7458 | 2020-06-11 | Elgin Energy | High Green (Resubmission) | Solar Photovoltaics |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land To The East Of High Green Longney Gloucester Gloucestershire | Gloucestershire | South West | England |  | 377569 | 212155 | Stroud District Council | S.19/0760/FUL | [5 empty] | 2019-04-05 | [6 empty] | 2019-07-26 |  |  |  | 2022-07-26
| 7459 | 2020-04-03 | Muirden Energy | Creag Dhubh | Wind Onshore |  |  | 27 | n/a |  |  |  | 3 | 9 | 139 | n/a | Planning Application Submitted | Application Submitted | 3km north east of Strachur, Argyll and Bute | Argyll and Bute | Scotland | Scotland | PA27 8DW | 212821 | 703627 | Argyll and Bute Council | 19/02544/PP | [5 empty] | 2019-12-05
| 7460 | 2019-07-02 | Douglas West Extension / 3R Energy Solutions | Douglas West Wind Farm (extension) | Battery | Co-located with RE | 6826 | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Douglas West and Dalquhandy, F, Lesmahagow, Site West of Junction 11 of M7, Lanark, Strathclyde | Strathclyde | Scotland | Scotland | ML11 0NN | 280968 | 634257 | Scottish Government (S36) | ECU00001836 | [5 empty] | 2019-04-12
| 7462 | 2020-05-18 | Pivot Power | Harker Grid Sub Station | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land to the west of Harker Grid Sub Station, Low Harker, Harker, Carlisle | Cumbria | North West | England | CA6 4DQ | 338345 | 561274 | Carlisle City Council | 19/0371 | [5 empty] | 2019-05-08 | [6 empty] | 2019-07-10 |  |  |  | 2022-07-10
| 7463 | 2019-07-02 | Nova Innovation | Shetland Tidal Array (extension) | Tidal Barrage and Tidal Stream |  |  | 1.4 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Bluemull Sound, Shetland, Scotland | Shetland | Scotland | Scotland |  | 440389 | 1183121 | Marine Scotland | [6 empty] | 2018-02-01 | [6 empty] | 2018-04-15
| 7464 | 2019-07-03 | Anesco | Lascar Works | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Lascar Works, Tanpits Road, Bury, BL9 5BY | Lancashire | North West | England | BL9 5BY | 380570 | 411256 | Bury Metropolitan Borough Council | [18 empty] | 2019-03-26 | 2019-06-26
| 7467 | 2020-06-24 | Eggborough Power (EP SHB) | South Humber Bank Power Station (Resubmission) | EfW Incineration |  |  | 95 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land Rear Of Power Station Hobson Way Stallingborough North East Lincolnshire | Humberside | Yorkshire and Humber | England | DN41 8BZ | 522769 | 413413 | The Planning Inspectorate - National Infrastructure | EN010107 | [5 empty] | 2020-04-09
| 7472 | 2020-03-26 | Energiekontor UK | Narachan Wind Farm | Wind Onshore |  |  | 95.2 | n/a |  |  |  | 5.6 | 17 | 180 | n/a | Planning Application Submitted | Application Submitted | Land 1.6km east of Tayinloan | Argyll and Bute | Scotland | Scotland |  | 175585 | 647445 | Scottish Government (S36) | ECU00001884 | [5 empty] | 2020-01-17
| 7476 | 2020-06-30 | Energiekontor UK | Strathrory Wind Farm | Wind Onshore |  |  | 44.8 | n/a |  |  |  | 5.6 | 8 | 180 | n/a | Planning Application Submitted | Application Submitted | Land at Strathrory, 4km northeast of Ardross and 8km northwest of Alness | Highland | Scotland | Scotland |  | 264000 | 877500 | Highland Council | 20/00584/FUL | [5 empty] | 2020-03-06
| 7477 | 2019-09-26 | William Grant and Sons Distillers | Glenfiddich Distillery | Anaerobic Digestion |  |  | 1.5 | Yes |  |  |  | n/a | n/a | n/a | n/a | Operational | Operational | Grissan Riverside Ltd, Glenfiddich Distillery, Castle Road, Dufftown, Keith, Grampian | Moray | Scotland | Scotland | AB55 4DH | 332714 | 841065 | Moray Council | 13/01781/EIA | [5 empty] | 2013-09-28 | [6 empty] | 2014-02-05 |  |  |  |  | 2014-12-15 | 2015-12-15
| 7478 | 2020-06-05 | Ivy Link Partnership | Pall Europe Building | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Pall Europe Ltd, Station Road, Ilfracombe, Devon | Devon | South West | England | EX34 8BH | 251419 | 146768 | North Devon District Council | 66784 | [5 empty] | 2019-06-27 | [6 empty] | 2019-08-13 |  |  |  | 0
| 7479 | 2020-05-18 | Pivot Power | Bramford Substation | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent To, Bullen Lane, Bramford, Ipswich, Suffolk | Suffolk | Eastern | England | IP8 4JH | 610154 | 246043 | Mid Suffolk District Council | DC/19/03008 | [5 empty] | 2019-06-25 | [6 empty] | 2019-09-23 |  |  |  | 2022-09-23
| 7484 | 2019-12-17 | Exeter City Council | Council Green Waste Facility | Solar Photovoltaics |  |  | 1.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Exeter City Council, Canal Banks, Green Waste Facility, Exeter, Devon | Devon | South West | England | EX2 8DX | 292530 | 90885 | Exeter City Council | 19/0458/ECC | [5 empty] | 2019-09-10 | [6 empty] | 2019-10-29 |  |  |  | 2024-10-29
| 7485 | 2019-12-17 | Exeter City Council | Council Green Waste Facility | Battery | Co-located with RE | 7484 | 1 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Exeter City Council, Canal Banks, Green Waste Facility, Exeter, Devon | Devon | South West | England | EX2 8DX | 292530 | 90885 | Exeter City Council | 19/0458/ECC | [5 empty] | 2019-09-10 | [6 empty] | 2019-10-29 |  |  |  | 2024-10-29
| 7486 | 2020-02-24 | Lightsource BP | South Lowfields Farm | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | South Lowfields Farm, Lowfield Lane, Kirkby Fleetham, Northallerton, North Yorkshire | North Yorkshire | Yorkshire and Humber | England | DL7 0 | 428671 | 494437 | Hambleton District Council | 19/01882/FUL | [5 empty] | 2019-09-09 | [6 empty] | 2019-12-09 |  |  |  | 2022-12-09
| 7489 | 2019-09-27 | Scottish Power Renewables | Rigged Hill Wind Farm (Repowering) | Wind Onshore |  |  | 28 | n/a |  |  |  | 4 | 7 | 137 | n/a | Planning Application Submitted | Application Submitted | Existing Rigged Hill Windfarm, Market Street, Limavady, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT49 | 91903 | 580576 | Derry City and Strabane District | LA01/2019/0890/F | [5 empty] | 2019-08-13
| 7491 | 2019-09-27 | Renewable Energy Systems (RES) | Dungiven | Wind Onshore |  |  | 24 | n/a |  |  |  | 4 | 6 | 150 | n/a | Planning Application Submitted | Application Submitted | Lands Opp entrance to, 59 Magheramore Road, Dungiven, Derry, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT47 4SW | 83729 | 566312 | Derry City and Strabane District | LA01/2019/0922/F | [5 empty] | 2019-08-02
| 7494 | 2019-09-27 | Private Developer | Newtonstewart | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 55 | n/a | Planning Application Submitted | Application Submitted | Approximately 300m South East, River Road, Newtownstewart, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 4LY | 53382 | 548639 | Derry City and Strabane District | LA11/2019/0724/F | [5 empty] | 2019-08-21
| 7495 | 2019-12-19 | Private Developer | Ballinderry Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 52 | n/a | Planning Application Withdrawn | Application Withdrawn | Lands 217m east of, 106 Ballinderry Road, Aughacarnan, Lisburn, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT28 2NW | 130176 | 523732 | Lisbury and Caseltreach City Council | LA05/2019/0855/F | [5 empty] | 2019-08-19 | 2019-09-19
| 7497 | 2020-06-30 | Low Carbon | Brook Farm | Solar Photovoltaics |  | 7791 | 25 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Os Parcel 6086 Adjacent, Ploughley Road, Railway Line, Arncott, Bicester, Oxfordshire | Oxfordshire | South East | England | OX25 1AB | 460212 | 217404 | Cherwell District Council | 20/00285/F | [5 empty] | 2020-02-03 | [6 empty] | 2020-05-28 |  |  |  | 2023-05-28
| 7498 | 2020-06-30 | Low Carbon | Brook Farm | Battery | Co-located with RE | 7497 | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Os Parcel 6086 Adjacent, Ploughley Road, Railway Line, Arncott, Bicester, Oxfordshire | Oxfordshire | South East | England | OX25 1AB | 460212 | 217404 | Cherwell District Council | 20/00285/F | [5 empty] | 2020-02-03 | [6 empty] | 2020-05-28 |  |  |  | 2023-05-28
| 7504 | 2019-09-27 | Private Developer | Killymendon (Replacement Turbine) | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 50 | n/a | Planning Application Submitted | Application Submitted | 255m East Of, 27 Dorney Bridge Road, Ballinamallard, Killymendon, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT94 2EF | 38175 | 519240 | Fermanagh and Omagh | LA10/2019/0978/F | [5 empty] | 2019-08-15
| 7508 | 2019-09-27 | Private Developer | A J Lowther and Son Premise | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Street Record, A4137 From A40 Junction To Bur, Marstow, Ross-On-Wye, Hereford and Worcester | Hereford and Worcester | West Midlands | England | HR9 6EG | 355750 | 218454 | Herefordshire Council | P192795/F | [5 empty] | 2019-08-14
| 7509 | 2020-03-31 | Private Developer | Mullawinny Road (Replacement Turbine) | Wind Onshore |  |  | 0.15 | n/a |  |  |  | 0.15 | 1 | 31.5 | n/a | Planning Application Withdrawn | Application Withdrawn | Approximately 100M North East, 21 Mullawinny Road, Accessing Onto Glennan Road, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 2LX | 52061 | 528353 | Fermanagh and Omagh | LA10/2019/0947/F | [5 empty] | 2019-08-08 | 2020-02-06
| 7510 | 2020-04-29 | Harmony Energy Storage | Salisbury Substation | Battery | Stand-alone Storage | n/a | 49.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent To, Salisbury Substation, Wilton, Salisbury, Wiltshire | Wiltshire | South West | England | SP2 0BL | 410452 | 131423 | Wiltshire Council | 19/05443/FUL | [5 empty] | 2019-08-05 | [6 empty] | 2020-03-05 |  |  |  | 2023-03-05
| 7511 | 2020-06-30 | Burcote Wind | Rigghill Wind Farm | Wind Onshore |  |  | 42 | n/a |  |  |  | 4.2 | 10 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Site To East Of Fardens, Skelmorlie, Strathclyde | North Ayrshire | Scotland | Scotland | PA17 5EU | 221492 | 666156 | North Ayrshire Council | 20/00248/PPM | [5 empty] | 2020-04-27
| 7512 | 2019-12-20 | William Grant and Sons Distillers | Glenfiddich Distillery AD (Extension) | Anaerobic Digestion |  |  | 2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Grissan Riverside Ltd, Glenfiddich Distillery, Castle Road, Dufftown, Keith, Grampian | Moray | Scotland | Scotland | AB55 4DH | 332714 | 841065 | Moray Council | 19/00988/APP | [5 empty] | 2019-08-13 | [6 empty] | 2019-10-15 |  |  |  | 2022-10-15
| 7518 | 2020-02-27 | EDF Energy Renewables | Lackenby (Resubmission) | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land at, Crow Lane, Old Lackenby, Middlesbrough, Cleveland | Cleveland | North East | England | TS6 8DN | 456654 | 519399 | Redcar and Cleveland Borough Council | R/2019/0433/FF | [5 empty] | 2019-07-25 | [6 empty] | 2019-10-24 |  |  |  | 2022-10-24
| 7519 | 2020-06-30 | JBM Solar | Corner Copse Solar Farm | Solar Photovoltaics |  |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Corner Copse Solar Farm, Stanton Fitzwarren, Swindon, Wiltshire | Wiltshire | South West | England | SN6 | 418268 | 190691 | Swindon Borough Council | S/19/1097 | [5 empty] | 2019-07-31 | [6 empty] | 2020-06-25 |  |  |  | 2023-06-25
| 7520 | 2020-06-30 | JBM Solar | Corner Copse Solar Farm | Battery | Co-located with RE | 7519 |  | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Corner Copse Solar Farm, Stanton Fitzwarren, Swindon, Wiltshire | Wiltshire | South West | England | SN6 | 418268 | 190691 | Swindon Borough Council | S/19/1097 | [5 empty] | 2019-07-31 | [6 empty] | 2020-06-25 |  |  |  | 2023-06-25
| 7522 | 2019-09-27 | DBE | Rathfriland Road | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 76 | n/a | Planning Application Submitted | Application Submitted | Approx 555M East Of, 199 Rathfriland Road, Dromara, Dromore, Co Down | Co. Down | Northern Ireland | Northern Ireland | BT25 2EG | 137982 | 503675 | Armagh, Banbridge and Craigavon | LA07/2019/1124/F | [5 empty] | 2019-07-16
| 7524 | 2020-06-30 | Ambition Community Energy | Severn Road | Wind Onshore | n/a | n/a | 4.2 | n/a |  |  |  | 4.2 | 1 | 150 | n/a | Planning Application Submitted | Application Submitted | Land On The South East Side Of, Severn Road, Shirehampton, Bristol, Avon | Avon | South West | England | BS11 0YL | 353345 | 182337 | Bristol City Council | 20/01270/F | [5 empty] | 2020-03-17
| 7526 | 2020-05-04 | Iron Mountain | Iron Mountain Howe Moss Drive | Solar Photovoltaics | n/a |  | 0.25 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Iron Mountain, Howe Moss Drive, Aberdeen, Grampian | Aberdeen | Scotland | Scotland | AB21 0GF | 386724 | 812305 | Aberdeen City Council | 191026/DPP | [5 empty] | 2019-06-28 | [6 empty] | 2019-07-25 |  |  |  | 2022-07-25
| 7527 | 2019-12-20 | McBallester | Tiddlywink Barn | Battery | Stand-alone Storage | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | The Barn South East Of, 8 Tiddly Wink, Yatton Keynell, Chippenham, Wiltshire | Wiltshire | South West | England | SN14 7BY | 387318 | 175704 | Wiltshire Council | 19/06775/FUL | [5 empty] | 2019-07-15 | 2019-09-10
| 7530 | 2019-09-27 | ABO Wind | Cullion wind farm | Wind Onshore |  |  | 25 | n/a |  |  |  | 4.1 | 6 | 145 | n/a | Planning Application Submitted | Application Submitted | 29 Cullion Road, Desertmartin, Magherafelt, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT45 5NR | 95453 | 550727 | Mid Ulster | LA09/2019/0990/F | [5 empty] | 2019-07-19
| 7531 | 2020-06-30 | Eden Campus Consultancy | Eden Campus | Solar Photovoltaics |  |  | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Woodchipping Plant, Main Street, Guardbridge, St. Andrews, Fife | Fife | Scotland | Scotland | KY16 0UG | 345120 | 719601 | Fife Council | 19/03311/FULL | [5 empty] | 2019-11-18 | [6 empty] | 2020-06-05 |  |  |  | 2023-06-05
| 7533 | 2019-09-27 | Grundon Waste Management | Lakeside EfW Colnbrook (Replacement) | EfW Incineration |  |  | 40 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land West Of The Iver Sou, Old Slade Lane, Sludge Dewatering Centre, Iver, Buckinghamshire | Berkshire | South East | England | SL0 9DX | 503390 | 178063 | Slough Borough Council | P/17826/000 | [5 empty] | 2019-06-25
| 7535 | 2019-09-27 | Private Developer | Greenhall Highway (resubmission/variation) | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 50 | n/a | Planning Application Submitted | Application Submitted | Approx 370m NW of, 60 Greenhall Highway, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 3EW | 100828 | 591868 | Causeway Coast and Glens | LA01/2019/0751/F | [5 empty] | 2019-07-02
| 7538 | 2020-06-30 | Riverside Energy / Enzygo | Connect Waste (Chequers Lane) | EfW Incineration |  |  | 20 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | 75 - 77 Chequers Lane, Barking and Dagenham, London | Greater London | London | England | RM9 6QJ | 548899 | 182077 | Barking and Dagenham London Borough Council | 20/00331/CTY | [5 empty] | 2020-03-12
| 7539 | 2020-06-30 | Solar South West | Bowerhouse Farm (extension) | Solar Photovoltaics |  |  | 19.8 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Photovoltaic Installation At B, Riverside, Banwell, Somerset | Somerset | South West | England | BS24 6UA | 340277 | 161883 | North Somerset Council | 20/P/0620/FUL | [5 empty] | 2020-03-31
| 7540 | 2020-06-30 | Noriker Power | Albion Road | Battery | Stand-alone Storage | n/a | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Unit 4, Adjacent, Albion Road, Dartford, Kent | Kent | South East | England | DA1 5PZ | 556321 | 175748 | Dartford Borough Council | 19/00882/FUL | [5 empty] | 2019-07-15 | 2020-06-16
| 7541 | 2020-06-08 | East Kent Hospitals University NHS Foundation Trust | Queen Elizabeth The Queen Mothers Hospital | Solar Photovoltaics |  |  | 0.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Ramsgate Road, Margate, Kent | Kent | South East | England | CT9 4BG | 169601 | 635907 | Thanet District Council | F/TH/19/0959 | [5 empty] | 2019-07-09 | [6 empty] | 2019-10-18 |  |  |  | 2022-10-18
| 7542 | 2019-09-27 | East Kent Hospitals University NHS Foundation Trust | William Harvey Hospital | Solar Photovoltaics |  |  | 0.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Plot 3 and Plot 5, Land adj. to, Kennington Road, Willesborough, Ashford, Kent | Kent | South East | England | TN24 0LZ | 604090 | 142068 | Ashford Borough Council | 19/01008/AS | [5 empty] | 2019-07-11
| 7543 | 2019-09-27 | ScottishPower Renewables | Corkey Windfarm (repowering) | Wind Onshore |  |  | 20 | n/a |  |  |  | 4 | 5 | 137 | n/a | Planning Application Submitted | Application Submitted | Corkey Windfarm, Corkey Road, Approx 19km North of Ballymena, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT44 9JB | 127705 | 579206 | Mid and East Antrim | LA01/2019/0772/F | [5 empty] | 2019-07-09
| 7544 | 2019-09-27 | Private Developer | Dundrinne Road | Wind Onshore |  |  | 0.225 | n/a |  |  |  | 0.225 | 1 | 40 | n/a | Planning Application Submitted | Application Submitted | App 275m South West Of, 63 Dundrinne Road, Castlewellan, Co Down | Co. Down | Northern Ireland | Northern Ireland | BT31 9EX | 144149 | 490451 | Newry, Mourne and Down | LA07/2019/1096/F | [5 empty] | 2019-07-10
| 7545 | 2019-09-27 | Aikens Farms | Greenhall Highway (resubmission/variation) | Wind Onshore |  |  | 0.25 | n/a |  |  |  | 0.25 | 1 | 55 | n/a | Planning Application Submitted | Application Submitted | Approx 185m SW of, 60 Greenhall Highway, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 3EW | 144594 | 490451 | Causeway Coast and Glens | LA01/2019/0749/F | [5 empty] | 2019-07-02
| 7551 | 2020-01-31 | Carlton Power | Langage Solar Park | Battery | Co-located with RE | 1039 | 0.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Langage Solar Park, Lower Langage Farm, Plymouth, Devon | Devon | South West | England | PL7 5AQ | 257480 | 56426 | South Hams District Council | 1185/19/FUL | [5 empty] | 2019-06-06 | [6 empty] | 2019-10-04 |  |  |  | 2022-10-04
| 7556 | 2020-06-25 | Energia Group | Lisnabreeny Road | Battery | Stand-alone Storage | n/a | 36 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Lands to the southeast of, 1 Lisnabreeny Road East, Belfast, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT6 9SS | 150249 | 524705 | Belfast City Council | LA05/2019/0675/F | [5 empty] | 2019-06-21 | [6 empty] | 2020-04-29 |  |  |  | 2025-04-28
| 7559 | 2020-05-19 | East Riding of Yorkshire Council | South Shore Holiday Village | Solar Photovoltaics |  |  | 0.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land North of Hill Farm, Wilsthorpe, Bridlington, Humberside | Humberside | Yorkshire and Humber | England | YO15 3QJ | 516655 | 464450 | East Riding of Yorkshire Council | 19/01883/REG3 | [5 empty] | 2019-06-25 | [6 empty] | 2019-09-24 |  |  |  | 2022-09-24
| 7560 | 2019-12-20 | Private Developer | Aghnaglea Road (relplacement turbine) | Wind Onshore |  |  | 0.15 | n/a |  |  |  | 0.15 | 1 | 50 | n/a | Planning Permission Granted | Awaiting Construction | Approx. 30m East of, 17 Aghnaglea Road, Sixmilecross, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 9NP | 70230 | 530585 | Fermanagh and Omagh | LA10/2019/0720/F | [5 empty] | 2019-06-14 | [6 empty] | 2019-10-03 |  |  |  | 2024-10-02
| 7562 | 2020-01-28 | Statkraft UK | Windy Rig Wind Farm (resubmission) | Wind Onshore |  |  | 48 | n/a |  |  |  | 3 | 12 | 125 | n/a | Planning Permission Granted | Awaiting Construction | Carsphairn, Castle Douglas, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG7 3 | 261700 | 600000 | Dumfries and Galloway Council | 19/0938/FUL | [5 empty] | 2019-06-11 | [6 empty] | 2019-11-08 |  |  |  | 2022-11-07
| 7563 | 2019-09-27 | Private Developer | Lagangreen Road | Wind Onshore |  |  | 0.15 | n/a |  |  |  | 0.15 | 1 | 42 | n/a | Planning Application Submitted | Application Submitted | Approximately 90 Metres North, 22 Lagangreen Road, Dromore, Co Down | Co. Down | Northern Ireland | Northern Ireland | BT25 1EL | 135231 | 508451 | Armagh, Banbridge and Craigavon | LA08/2019/0801/F | [5 empty] | 2019-06-07
| 7567 | 2020-03-18 | Renewable Energy Waste Solution | Bloomfield Recycling Depot (Resubmission) | EfW Incineration |  |  | 5 | No |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Bloomfield Recycling Depot, Bloomfield Road, Tipton, West Midlands | West Midlands | West Midlands | England | DY4 9BS | 395058 | 293032 | Dudley Metropolitan Borough Council | P19/0720 | [5 empty] | 2019-05-21 | [6 empty] | 2019-11-07 |  |  |  | 2022-11-07
| 7568 | 2019-09-27 | European Marine Energy Centre | Billia Croo Wave Test Site (Extension) | Shoreline Wave |  |  | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Billa Croo Test Site, Fall of Warness, Off Eday, Orkney Islands | Orkney Islands | Scotland | Scotland |  | 323401 | 983560 | Marine Scotland | [6 empty] | 2019-06-21
| 7570 | 2020-01-20 | Arlington Energy | Greenfield Road | Battery | Co-located with RE | 2265 | 40 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land at Clayhill Farm, Greenfield Road, Westoning, Bedford | Bedfordshire | Eastern | England | MK45 5JD | 503744 | 232982 | Central Bedfordshire Council | CB/17/06006/FULL | [5 empty] | 2017-12-19 | [6 empty] | 2018-03-23 |  |  |  |  | 2019-06-19
| 7571 | 2020-05-18 | Pivot Power | Cowley electricity sub-station | Battery | Co-located with fossil fuel plant |  | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Cowley Main Sub Station, Lower Blackberry Lane, Garsington, Oxford | Oxfordshire | South East | England | OX44 9BD | 456332 | 202409 | South Oxfordshire District Council | P19/S0623/FUL | [5 empty] | 2019-02-25 | [6 empty] | 2019-07-19 |  |  |  |  | 2019-11-15
| 7572 | 2020-03-25 | Scottish Power Renewables | Hagshaw Hill | Battery | Co-located with RE | 7456 | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Hagshaw Hill Wind Farm, Douglas, Lanark | South Lanarkshire | Scotland | Scotland | ML11 0RR | 282089 | 631116 | Scottish Government (S36) | ECU00000737 | [5 empty] | 2018-12-03 | [6 empty] | 2020-02-26 |  |  |  | 2023-02-26
| 7573 | 2020-05-18 | Capbal | Shindour Feddal Hill Wood Braco | Battery | Stand-alone Storage | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land West of Braco, Dunblane | Perth and Kinross | Scotland | Scotland | FK15 9RD | 281015 | 709090 | Perth and Kinross Council | 17/01810/FLL | [5 empty] | 2017-10-14 | [6 empty] | 2017-11-24 |  |  |  | 2020-11-24
| 7574 | 2020-05-18 | Capbal | Orchardbank Industrial Estate | Battery | Stand-alone Storage | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Ground at Rear of Dean Park, Orchard Loan, Orchardbank Industrial Estate | Angus | Scotland | Scotland | DD8 1TD | 344086 | 750088 | Angus Council | 17/00848/FULL | [5 empty] | 2017-10-17 | [6 empty] | 2017-12-20 |  |  |  | 2020-12-20
| 7575 | 2020-05-18 | Capbal | Ardoch Farm | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Ardoch Farm, Kilwinning, Ayrshire | North Ayrshire | Scotland | Scotland | KA13 7QJ | 231148 | 644103 | North Ayrshire Council | 18/00445/PPP | [5 empty] | 2018-05-17 | [6 empty] | 2018-06-25 |  |  |  | 2021-06-25
| 7576 | 2020-05-18 | Capbal | Shaws Farm | Battery | Stand-alone Storage | n/a | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Shaws Farm, Shaws Road, Larkhall, South Lanarkshire | South Lanarkshire | Scotland | Scotland | ML9 2TY | 277378 | 649453 | South Lanarkshire Council | P/18/0548 | [5 empty] | 2018-04-19 | [6 empty] | 2018-07-23 |  |  |  | 2021-07-23
| 7577 | 2019-11-15 | UK Battery Storage | Bradford West Substation (Harrop Edge Farm Resubmission) | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At Grid Ref 409233 434810 Old Allen Road Wilsden Bradford West Yorkshire | West Yorkshire | Yorkshire and Humber | England |  | 409233 | 434810 | Bradford Metropolitan District Council | 18/03894/OUT | [5 empty] | 2018-09-19 | [6 empty] | 2019-03-18 |  |  |  | 2022-03-18
| 7584 | 2019-12-18 | ScottishPower Renewables | Sheirdrim Renewable Energy Development - Solar | Solar Photovoltaics | n/a | 7585 | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Sheirdrim Windfarm East Of, Clachan, Tarbert, Strathclyde | Strathclyde | Scotland | Scotland | PA29 6 | 181450 | 657720 | Scottish Government (S36) | ECU00001957 | [5 empty] | 2019-10-10
| 7585 | 2019-12-18 | ScottishPower Renewables | Sheirdrim Renewable Energy Development - Battery | Battery | Co-located with RE | 7583 | 38 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Sheirdrim Windfarm East Of, Clachan, Tarbert, Strathclyde | Strathclyde | Scotland | Scotland | PA29 6 | 181450 | 657720 | Scottish Government (S36) | ECU00001957 | [5 empty] | 2019-10-10
| 7588 | 2019-12-19 | Cornwall Council | Land near Ventonteague (Resubmission) | Wind Onshore | n/a | n/a | 2.3 | n/a |  |  |  | 2.3 | 1 | 98.5 | n/a | Planning Permission Granted | Awaiting Construction | Land Off Ventonteague, St. Allen, Truro, Cornwall | Cornwall | South West | England | TR4 9QX | 182586 | 51229 | Cornwall Council | PA18/08772 | [5 empty] | 2018-10-10 | [6 empty] | 2018-12-14 |  |  |  | 2021-12-14
| 7590 | 2019-12-20 | SS Agri Power | Ellingham Road | Anaerobic Digestion | n/a | n/a | 1 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | SS Agri Power Ltd, Ellingham Road, Attleborough, Norfolk | Norfolk | Eastern | England | NR17 1AE | 603299 | 295670 | Norfolk County Council | FUL/2019/0056 | [5 empty] | 2019-12-11
| 7591 | 2020-06-30 | Gigabox Developments | Dunsinane Industrial Estate | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To The W/O Kinnoull Stree, Dunsinane Avenue, Dunsinane Industrial Estate, Dundee, Tayside | Dundee | Scotland | Scotland | DD2 3QT | 337745 | 732482 | Dundee City Council | 19/00876/FULL | [5 empty] | 2019-12-02 | [6 empty] | 2020-03-27 |  |  |  | 2023-03-27
| 7592 | 2019-12-20 | Gibson Bros | Moy Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 65 | n/a | Planning Application Submitted | Application Submitted | Land 263m south west of, 60 Moy Road, Portadown, Craigavon, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT62 1QW | 108851 | 513606 | Armagh, Banbridge and Craigavon | LA08/2019/1597/F | [5 empty] | 2019-11-29
| 7593 | 2020-03-31 | Warter Priory Farms | The Gardens | Solar Photovoltaics | n/a | n/a | 0.26 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | The Gardens, Warter, York, North Yorkshire | Humberside | Yorkshire and Humber | England | YO42 1XA | 485397 | 450079 | East Riding of Yorkshire Council | 19/04018/PLF | [5 empty] | 2019-12-05 | [6 empty] | 2020-01-27 |  |  |  | 2023-01-27
| 7594 | 2020-03-31 | Ministry of Justice | HMP Bure | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Refused | Application Refused | H M Prison Bure, Jaguar Drive, Badersfield, Norwich, Norfolk | Norfolk | Eastern | England | NR10 5GB | 625884 | 323261 | North Norfolk District Council | NS/19/1931 | [5 empty] | 2019-11-20 |  | 2020-01-15
| 7595 | 2019-12-20 | Ednie Farms | St Fergus Renewable Energy Park | Wind Onshore | n/a | 7597 | 3 | n/a |  |  |  | 1.5 | 2 | 119 | n/a | Planning Application Submitted | Application Submitted | Land Adjacent To The St Fergus, St. Fergus, Peterhead, Grampian | Aberdeen | Scotland | Scotland | AB42 3BR | 409589 | 852842 | Aberdeenshire Council | APP/2019/2653 | [5 empty] | 2019-12-03
| 7596 | 2019-12-20 | Ednie Farms | St Fergus Renewable Energy Park | Solar Photovoltaics | n/a | 7597 | 5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land Adjacent To The St Fergus, St. Fergus, Peterhead, Grampian | Aberdeen | Scotland | Scotland | AB42 3BR | 409589 | 852842 | Aberdeenshire Council | APP/2019/2653 | [5 empty] | 2019-12-03
| 7597 | 2019-12-20 | Ednie Farms | St Fergus Renewable Energy Park | Battery | Co-located with RE | 7595 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land Adjacent To The St Fergus, St. Fergus, Peterhead, Grampian | Aberdeen | Scotland | Scotland | AB42 3BR | 409589 | 852842 | Aberdeenshire Council | APP/2019/2653 | [5 empty] | 2019-12-03
| 7599 | 2020-06-30 | Ministry of Defence | Duke Of Gloucester Barracks | Solar Photovoltaics | n/a | n/a | 1.4 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Duke Of Gloucester Barracks Ai, Cricklade Road, South Cerney, Cirencester, Gloucestershire | Gloucestershire | South West | England | GL7 5RD | 405555 | 198811 | Cotswold District Council | 19/04344/FUL | [5 empty] | 2019-11-26 | [6 empty] | 2020-04-27 |  |  |  | 2023-04-27
| 7600 | 2020-03-31 | Inicio Fresco | Cairnandrew | Wind Onshore | n/a | n/a | 6 | n/a |  |  |  | 3 | 2 | 150 | n/a | Planning Permission Refused | Application Refused | Cairnandrew, Longmanhill, Banff, Grampian | Aberdeen | Scotland | Scotland | AB45 3SR | 374610 | 860223 | Aberdeenshire Council | APP/2019/2280 | [5 empty] | 2019-10-30 |  | 2019-12-02
| 7601 | 2020-04-27 | Tesco Stores | Tesco Extra Dumfries | Solar Photovoltaics | n/a | n/a | 0.75 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Extra Cuckoo Bridge Reta, Glasgow Road, Dumfries, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG2 9BF | 296221 | 576844 | Dumfries and Galloway Council | 19/1747/FUL | [5 empty] | 2019-11-18 | [6 empty] | 2020-01-10 |  |  |  | 2023-01-09
| 7603 | 2019-12-20 | Private Developer | Ballinderry Road (Resubmission) | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 52 | n/a | Planning Application Submitted | Application Submitted | Lands 217m East Of, 106 Ballinderry Road, Aughacarnan, Lisburn, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT28 2NW | 130988 | 523731 | Lisburn and Castlereagh City Council | LA05/2019/1212/F | [5 empty] | 2019-11-27
| 7604 | 2019-12-20 | Alboro Developments | Ely Road Waste Management Park | Solar Photovoltaics | n/a | n/a | 1.1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Cambridge Waste Management Par, Ely Road, Chittering, Landbeach, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB25 9PH | 548755 | 268890 | South Cambridgeshire District Council | S/4028/19/FL | [5 empty] | 2019-11-21
| 7605 | 2020-03-31 | RPS Group | Mursley Road | Solar Photovoltaics | n/a | n/a | 36 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Home Farm, Mursley Road, Little Horwood, Milton Keynes, Buckinghamshire | Buckinghamshire | South East | England | MK17 0PG | 479451 | 230539 | Aylesbury Vale District Council | 19/04485/APP | [5 empty] | 2020-01-10
| 7606 | 2020-06-04 | Tribus Clean Energy | Crown Farm | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Crown Farm, Mill Road, West Walton, Wisbech, Cambridgeshire | Norfolk | Eastern | England | PE14 7EU | 546741 | 316174 | King's Lynn and West Norfolk Borough Council | 19/02002/FM | [5 empty] | 2019-11-25 | [6 empty] | 2020-03-05 |  |  |  | 2023-03-05
| 7608 | 2020-04-27 | Tesco Stores | Tesco Superstore Annan | Solar Photovoltaics | n/a | n/a | 0.23 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco, Scotts Street, Annan, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG12 6JH | 566340 | 320134 | Dumfries and Galloway Council | 19/1746/FUL | [5 empty] | 2019-11-18 | [6 empty] | 2020-01-10 |  |  |  | 2023-01-09
| 7609 | 2020-06-04 | Tribus Clean Energy | Model Farm | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Model Farm, Frenchs Road, Walpole St. Andrew, Wisbech, Cambridgeshire | Norfolk | Eastern | England | PE14 7JF | 548338 | 316760 | King's Lynn and West Norfolk Borough Council | 19/02003/F | [5 empty] | 2019-11-25 | [6 empty] | 2020-03-06 |  |  |  | 2023-03-06
| 7611 | 2020-06-30 | Standard Life Investments Property Holdings | Flamingo Flowers | Solar Photovoltaics | n/a | n/a | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Flamingo Flowers, Great North Road, Sandy, Bedfordshire | Bedfordshire | Eastern | England | SG19 2AJ | 516251 | 251961 | Central Bedfordshire Council | CB/19/03775/FULL | [5 empty] | 2019-11-21 | 2020-05-12
| 7612 | 2019-12-20 | Private Developer | Callagheen Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 90 | n/a | Planning Application Submitted | Application Submitted | 370m SE Of, 28 Callagheen Road, Belleek, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT93 3 | 10181 | 522887 | Fermanagh and Omagh | LA10/2019/1354/F | [5 empty] | 2019-11-25
| 7613 | 2019-12-20 | Private Developer | Afon Cynfal Hydro Scheme | Small Hydro | n/a | n/a | 0.6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land between Pont yr Afon Gam, Ffestiniog, Blaenau Ffestiniog, Gwynedd | Conwy | Wales | Wales | LL41 4PS | 274437 | 341780 | Snowdonia National Park Authority | NP5/59/495B | [5 empty] | 2019-11-20
| 7614 | 2020-06-04 | Tribus Clean Energy | Flower Farm | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Flower Farm, The Marsh, Walpole St. Andrew, Wisbech, Cambridgeshire | Norfolk | Eastern | England | PE14 7JG | 546780 | 316765 | King's Lynn and West Norfolk Borough Council | 19/02004/FM | [5 empty] | 2019-11-25 | [6 empty] | 2020-03-19 |  |  |  | 2023-03-19
| 7615 | 2019-12-20 | Private Developer | Larne Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 70 | n/a | Planning Application Submitted | Application Submitted | Lands 400m West Of, 110 Larne Road, Ballycarry, Carrickfergus, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT38 9JN | 159057 | 550291 | Mid and East Antrim | LA02/2019/0880/F | [5 empty] | 2019-11-20
| 7616 | 2020-06-30 | Lightsource BP | Down Barn Farm | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Down Barn Farm, Cholderton, Salisbury, Wiltshire | Wiltshire | South West | England | SP4 0EH | 422070 | 143863 | Wiltshire Council | 19/10890/FUL | [5 empty] | 2019-11-13 | [6 empty] | 2020-04-23 |  |  |  | 2023-04-23
| 7617 | 2019-12-20 | Elgin Energy | Ranksborough Farm (Resubmission) | Solar Photovoltaics | n/a | n/a | 28 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land At Ranksborough Farm, Melton Road, Langham, Oakham, Leicestershire | Leicestershire | East Midlands | England | LE15 7EJ | 483119 | 310941 | Rutland County Council | 2019/1249/MAF | [5 empty] | 2019-11-07
| 7618 | 2020-04-23 | Tesco Stores | Tesco Store Bishop Auckland | Solar Photovoltaics | n/a | n/a | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Extra, Abraham Enterprise Park, St. Helen Auckland, Bishop Auckland, County Durham | County Durham | North East | England | DL14 9AB | 419568 | 527338 | Durham County Council | DM/19/03613/PNS | [5 empty] | 2019-11-20 | [6 empty] | 2020-01-08
| 7619 | 2020-04-23 | Tesco Stores | Tesco Burnage Store | Solar Photovoltaics | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Burnage Store, Burnage Lane, Manchester, Greater Manchester | Greater Manchester | North West | England | M19 1TF | 386127 | 391485 | Manchester City Council | 125482/P14J/2019 | [5 empty] | 2019-11-20 | [6 empty] | 2020-01-15
| 7625 | 2020-04-23 | Tesco Stores | Tesco Store East Didsbury | Solar Photovoltaics | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco East Didsbury Store, Parrs Wood Lane, Manchester, Greater Manchester | Greater Manchester | North West | England | M20 5NP | 385499 | 390611 | Manchester City Council | 125481/P14J/2019 | [5 empty] | 2019-11-20 | [6 empty] | 2020-01-15
| 7626 | 2019-12-20 | Elgin Energy | Sparrow Lodge Farm | Solar Photovoltaics | n/a | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land at Sparrow Lodge Farm, Wicken Park Road, Wicken, Milton Keynes, Buckinghamshire | Northamptonshire | East Midlands | England | MK19 6BZ | 475390 | 238266 | South Northamptonshire Council | S/2019/2270/MAF | [5 empty] | 2019-11-08
| 7627 | 2019-12-20 | Fermanagh GAA | Lissan Lane | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | 60m N Of Sports Complex, 20 Lissan Lane, Lissan, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT74 4FQ | 38333 | 512035 | Fermanagh and Omagh | LA10/2019/1300/F | [5 empty] | 2019-11-12
| 7629 | 2020-03-31 | Hartlepool Borough Council | Redcar EfW | EfW Incineration | n/a | n/a | 40 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land East Of John Boyle Road, Tees Dock Road, And West Of, Grangetown Prairie Site, Middlesbrough, Cleveland | Cleveland | North East | England | TS6 6LU | 454736 | 521248 | Redcar and Cleveland Borough Council | R/2019/0767/OOM | [5 empty] | 2019-12-20
| 7630 | 2020-06-30 | AG Renewables | Burwell Solar Farm | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Site Noth Of Hightown Drove, Burwell, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB25 | 557261 | 267595 | East Cambridgeshire District Council | 20/00557/ESF | [5 empty] | 2020-05-01
| 7631 | 2020-02-25 | Solar Charging (Lark Energy) | Wittering Ford Road | Battery | Co-located with RE | 4956 | 3 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To The South Of, Wittering Ford Road, Stamford, Lincolnshire | Cambridgeshire | Eastern | England | PE9 3 | 506664 | 302641 | Peterborough City Council | 19/01261/FUL | [5 empty] | 2019-09-18 | [6 empty] | 2019-11-13 |  |  |  | 2022-11-13
| 7632 | 2020-03-31 | Arlington Energy | Gipsy Lane | Battery | Stand-alone Storage | n/a | 16 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Rear Of The Royal Toby Ho, Manchester Road, Rochdale, Greater Manchester | Greater Manchester | North West | England | OL11 3HF | 388277 | 411246 | Rochdale Borough Council | 19/01147/FUL | [5 empty] | 2019-11-05 | [6 empty] | 2020-03-20 |  |  |  | 2023-03-20
| 7633 | 2019-12-20 | Private Developer | Coa Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Lands 574m South-East Of, 233 Coa Road, Ballinamallard, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT94 2PB | 39283 | 513396 | Fermanagh and Omagh | LA10/2019/1285/F | [5 empty] | 2019-11-06
| 7634 | 2020-03-31 | S B Waste Management | Purbrook Road | EfW Incineration | n/a | n/a | 1.2 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | SB Waste Management and Recyclin, 26 Purbrook Road, Wolverhampton, West Midlands | West Midlands | West Midlands | England | WV1 2EJ | 393125 | 297912 | Wolverhampton City Council | 19/01242/FUL | [5 empty] | 2019-11-06 | [6 empty] | 2020-02-10 |  |  |  | 2023-02-10
| 7635 | 2019-12-20 | HCRS | Erganagh Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Lands 330m South Of, 29 Erganagh Road, Castlederg, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT81 7JQ | 42055 | 550155 | Derry City and Strabane District | LA11/2019/0936/F | [5 empty] | 2019-10-29
| 7638 | 2019-12-20 | Laird Brothers | Lochhead Steading Concrete Block Manufacturing Plant | Solar Photovoltaics | n/a | n/a | 0.57 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Lochhead Steading, Forfar, Tayside | Angus | Scotland | Scotland | DD8 2RL | 347503 | 750941 | Angus Council | 19/00712/FULL | [5 empty] | 2019-09-27 | [6 empty] | 2019-11-05 |  |  |  | 2022-11-05
| 7639 | 2019-12-20 | Private Developer | Derryallen Road | Wind Onshore | n/a | n/a | 0.5 | n/a |  |  |  | 0.5 | 1 | 45 | n/a | Planning Application Submitted | Application Submitted | Lands 200m South Of, 22 Derryallen Road, Trillick, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 3RZ | 41656 | 516551 | Fermanagh and Omagh | LA10/2019/1270/F | [5 empty] | 2019-11-01
| 7640 | 2019-12-20 | Brockaghboy Windfarm | Brockaghboy Wind Farm (Further Extension) | Wind Onshore | n/a | n/a | 10 | n/a |  |  |  | 2.5 | 4 | 125 | n/a | Planning Application Submitted | Application Submitted | Brockaghboy Wind Farm, 10A Drumbane Road, Garvagh, south east of Dowlin's Bridge, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 5DR | 97550 | 569675 | Mid Ulster | LA09/2019/1386/F | [5 empty] | 2019-10-14
| 7641 | 2020-03-26 | Reach South Academy Trust | Parkfield School | Solar Photovoltaics | n/a | n/a | 0.35 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Bournemouth International Airp, Christchurch, Dorset | Dorset | South West | England | BH23 6DF | 411890 | 97452 | Christchurch Borough Council | 8/19/1291/FUL | [5 empty] | 2019-10-24 | [6 empty] | 2019-12-17 |  |  |  | 2022-12-17
| 7642 | 2019-12-20 | East Herts District Council | Castle Weir | Small Hydro | n/a | n/a | 0.15 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Castle Weir On The River Lea,, The Wash, Hertford, Hertfordshire | Hertfordshire | Eastern | England | SG14 1PS | 212594 | 532468 | East Hertfordshire District Council | 3/19/2176/OUT | [5 empty] | 2019-10-24
| 7643 | 2019-12-20 | Private Developer | Windyhill Road | Wind Onshore | n/a | n/a | 0.15 | n/a |  |  |  | 0.15 | 1 | 50 | n/a | Planning Application Submitted | Application Submitted | Lands 187m South Of, 223 Windyhill Road, Macosquin, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 4JL | 95380 | 589373 | Causeway Coast and Glens | LA01/2019/1153/F | [5 empty] | 2019-10-18
| 7644 | 2020-06-30 | Arena Capital Partners | Kilsannagh Lane | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 70 | n/a | Planning Permission Granted | Awaiting Construction | Approximately 185m North West, 39 Kilsannagh Lane, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 1LR | 87189 | 512796 | Mid Ulster | LA09/2019/1396/F | [5 empty] | 2019-10-23 | [6 empty] | 2020-04-30 |  |  |  | 2025-04-29
| 7645 | 2020-06-30 | Arena Capital Partners | Legilly Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 70 | n/a | Planning Permission Granted | Awaiting Construction | Approximately 430m North West, 19 Legilly Road, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 1NZ | 87363 | 519973 | Mid Ulster | LA09/2019/1395/F | [5 empty] | 2019-10-23 | [6 empty] | 2020-04-30 |  |  |  | 2025-04-29
| 7646 | 2020-04-27 | Push Energy | Tesco Superstore Thetford Road | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Superstore, Thetford Road, Watton, Thetford, Norfolk | Norfolk | Eastern | England | IP25 6BQ | 591787 | 300656 | Breckland Council | 3PN/2019/0053/PV | [5 empty] | 2019-11-15 | [6 empty] | 2019-12-17
| 7647 | 2020-03-31 | Arena Capital Partners | Craighill Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 70 | n/a | Planning Permission Granted | Awaiting Construction | Approx. 280m NNE of, 11 Craighill Road, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 7PD | 63124 | 538845 | Fermanagh and Omagh | LA10/2019/1215/F | [5 empty] | 2019-10-15 | [6 empty] | 2020-02-21 |  |  |  | 2025-02-20
| 7649 | 2020-06-30 | Private Developer | Nutfield Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 65 | n/a | Planning Application Withdrawn | Application Withdrawn | 81 Nutfield Road, Lisnaskea, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT92 0QU | 45955 | 499435 | Fermanagh and Omagh | LA10/2019/1229/F | [5 empty] | 2019-10-17 | 2020-05-26
| 7650 | 2019-12-20 | Private Developer | Drumcor Road | Wind Onshore | n/a | n/a | 1 | n/a |  |  |  | 1 | 1 | 67 | n/a | Planning Application Submitted | Application Submitted | Lands 120m North East of, 14 Drumcor Road, Tempo, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT94 3FE | 49010 | 512288 | Fermanagh and Omagh | LA10/2019/1228/F | [5 empty] | 2019-10-17
| 7651 | 2020-03-31 | Private Developer | Omagh Road | Wind Onshore | n/a | n/a | 0.5 | n/a |  |  |  | 0.5 | 1 | 40 | n/a | Planning Permission Granted | Awaiting Construction | Lands approx. 350m South of, 174 Omagh Road, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 2AJ | 69528 | 521189 | Mid Ulster | LA09/2019/1344/F | [5 empty] | 2019-10-14 | [6 empty] | 2020-02-20 |  |  |  | 2025-02-19
| 7652 | 2020-04-27 | Push Energy | Church Road Tesco | Solar Photovoltaics | n/a | n/a | 0.229 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Superstore, 86 Church Road, Tiptree, Colchester, Essex | Essex | Eastern | England | CO5 0SU | 589765 | 215870 | Colchester Borough Council | 192576 | [5 empty] | 2019-10-07 | [6 empty] | 2019-11-15
| 7654 | 2020-03-31 | EnergieKontor UK | Cornharrow Wind Farm (Resubmission) | Wind Onshore | n/a | 7849 | 38.4 | n/a |  |  |  | 4.8 | 8 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Cornharrow Wind Farm, Land At Cornharrow, Dalry, Castle Douglas, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG7 3UG | 266701 | 592862 | Dumfries and Galloway Council | 20/0159/FUL | [5 empty] | 2020-02-19
| 7655 | 2019-12-20 | Graythorp Energy | Graythorpe Energy Centre | EfW Incineration | n/a | n/a | 49.5 |  |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land off, Tofts Road West, Hartlepool, Cleveland | Cleveland | North East | England | TS25 2DF | 451783 | 528147 | Hartlepool Borough Council | H/2019/0275 | [5 empty] | 2019-10-01
| 7656 | 2020-06-30 | Checkley Wood Energy | Double Arches Solar Array | Solar Photovoltaics | n/a | n/a | 1.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land At Double Arches Quarry, Watling Street, Heath And Reach, Leighton Buzzard, Bedfordshire | Bedfordshire | Eastern | England | LU7 9LD | 494027 | 229072 | Central Bedfordshire Council | CB/20/01505/FULL | [5 empty] | 2020-05-18
| 7657 | 2020-06-30 | BeBa Energy | Hampton Manor | Solar Photovoltaics | n/a | n/a | 0.32 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Refused | Application Refused | Solar Array Hampton Manor, Shadow Brook Lane, Hampton-in-Arden, Solihull, West Midlands | West Midlands | West Midlands | England | B92 0DG | 420040 | 281184 | Solihull Metropolitan Borough Council | PL/2019/02522/PPFL | [5 empty] | 2019-09-27 |  | 2020-04-15
| 7663 | 2020-06-30 | Aura Power | Feeder Road | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Adjacent To St Philip's Marsh, Feeder Road, Land Off, Bristol, Avon | Avon | South West | England | BS2 0TH | 360828 | 172208 | Bristol City Council | 19/04841/F | [5 empty] | 2019-10-03 | [6 empty] | 2020-05-27 |  |  |  | 2023-05-27
| 7664 | 2020-03-31 | Arena Capital Partners | Aughnagurgan Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 67 | n/a | Planning Permission Granted | Awaiting Construction | App 670m SW Of, 29 Aughnagurgan Road, Darkley, Armagh, Co Armagh | Co. Armagh | Northern Ireland | Northern Ireland | BT60 3DA | 96191 | 488066 | Armagh, Banbridge and Craigavon | LA08/2019/1328/F | [5 empty] | 2019-09-25 | [6 empty] | 2020-03-06 |  |  |  | 2025-03-05
| 7667 | 2019-12-20 | Moore Energy | Lislafferty Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Approximately 400M. South West, 20 Lislafferty Road, Newtownstewart, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 4NB | 48107 | 548589 | Derry City and Strabane District | LA11/2019/0796/F | [5 empty] | 2019-09-18
| 7668 | 2020-06-09 | Peel Environmental / Waste2tricity | Protos Plastics to Hydrogen Facility (Ince) | Advanced Conversion Technologies | n/a | n/a | 3.8 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Area 10B Ince Resource Recover, Grinsome Road, Chester, Cheshire | Cheshire | North West | England | CH2 | 346402 | 376573 | Cheshire West and Chester Council | 19/03489/FUL | [5 empty] | 2019-09-18 | [6 empty] | 2020-03-18 |  |  |  | 2023-03-18
| 7669 | 2019-12-20 | ScottishPower Renewables | Coal Clough Wind Farm (Co-located) | Solar Photovoltaics | n/a | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Coal Clough Windfarm, Long Causeway, Cliviger, Burnley, Lancashire | Lancashire | North West | England | BB10 4RR | 389945 | 428272 | Burnley Borough Council | FUL/2019/0470 | [5 empty] | 2019-09-24
| 7672 | 2020-03-27 | Hill Power | Tullyrain Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Appeal Lodged | Application Submitted | 285m East N/East Of, 41 Tullyrain Road, Banbridge, Co Down | Co. Down | Northern Ireland | Northern Ireland | BT32 4PR | 122447 | 507283 | Armagh, Banbridge and Craigavon | LA08/2019/1260/F | 2019/A0255 |  |  |  |  | 2019-09-16 |  |  | 2020-03-13
| 7673 | 2019-12-20 | Private Developer | Lislafferty Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | Approximately 470 M. South Wes, 20 Lislafferty Road, Newtownstewart, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 4NB | 48174 | 548446 | Fermanagh and Omagh | LA11/2019/0797/F | [5 empty] | 2019-09-18
| 7674 | 2020-03-31 | ScottishPower Renewables | East Ballochy (Resubmission) | Solar Photovoltaics | n/a | 7675 | 39.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Field 400M SE Of East Ballochy, East Ballochy, Montrose, Tayside | Angus | Scotland | Scotland | DD10 9LP | 367035 | 761826 | Angus Council | 20/00019/FULM | [5 empty] | 2020-01-27
| 7675 | 2020-03-31 | ScottishPower Renewables | East Ballochy | Battery | Co-located with RE | 7674 | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Field 400M SE Of East Ballochy, East Ballochy, Montrose, Tayside | Angus | Scotland | Scotland | DD10 9LP | 367035 | 761826 | Angus Council | 20/00019/FULM | [5 empty] | 2020-01-27
| 7676 | 2020-06-25 | ScottishPower Renewables | Coldham Estate Solar Farm | Solar Photovoltaics | n/a | 7677 | 10 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Solar Farm, March Road, Coldham, Wisbech, Cambridgeshire | Cambridgeshire | Eastern | England | PE14 0LY | 544453 | 301966 | Fenland District Council | F/YR19/0810/F | [5 empty] | 2019-09-17 | [6 empty] | 2019-12-17 |  |  |  | 2022-12-17
| 7677 | 2020-06-25 | ScottishPower Renewables | Coldham Estate Solar Farm | Battery | Co-located with RE | 7676 | 6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Solar Farm, March Road, Coldham, Wisbech, Cambridgeshire | Cambridgeshire | Eastern | England | PE14 0LY | 544453 | 301966 | Fenland District Council | F/YR19/0810/F | [5 empty] | 2019-09-17 | [6 empty] | 2017-03-31 |  |  |  | 2020-03-31
| 7678 | 2020-03-31 | Centrica Business Solutions | Osi Food Solutions Factory | Solar Photovoltaics | n/a | n/a | 0.67 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Osi Food Solutions Ltd, Luneberg Way, Scunthorpe, Humberside | Humberside | Yorkshire and Humber | England | DN15 8LP | 487613 | 412825 | North Lincolnshire Council | PA/2019/1461 | [5 empty] | 2019-09-11 | [6 empty] | 2019-12-17 |  |  |  | 2022-12-17
| 7679 | 2019-12-20 | T C Stewart and Sons Ltd | Draffanmarshill Farm | Wind Onshore | n/a | n/a | 4.2 | n/a |  |  |  | 4.2 | 1 | 180 | n/a | Planning Application Submitted | Application Submitted | Draffan Road, Draffanmarshill Farm, Lanark, Strathclyde | South Lanarkshire | Scotland | Scotland | ML11 9PW | 278551 | 645431 | South Lanarkshire Council | P/19/1258 | [5 empty] | 2019-09-10
| 7680 | 2020-06-30 | Private Developer | Rockstown Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 45 | n/a | Planning Permission Granted | Awaiting Construction | Approximately 420M North East, 124 Rockstown Road, Carrickmore, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT79 9BX | 76576 | 534545 | Fermanagh and Omagh | LA10/2019/1089/F | [5 empty] | 2019-09-12 | [6 empty] | 2020-06-09 |  |  |  | 2025-06-08
| 7682 | 2019-12-20 | Mullinamoot | Breagho Road | Wind Onshore | n/a | n/a | 0.5 | n/a |  |  |  | 0.5 | 1 | 54 | n/a | Planning Application Submitted | Application Submitted | 360m East North East of, 37 Breagho Road, Breagho, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT74 4DE | 37143 | 513290 | Fermanagh and Omagh | LA10/2019/1084/F | [5 empty] | 2019-09-11
| 7684 | 2020-04-29 | Infinite Energy Renewables | Energy Centre Royal Mint | Battery | Co-located with fossil fuel plant | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Royal Mint, Llantrisant, Pontyclun, Mid Glamorgan | Rhondda Cynon Taff | Wales | Wales | CF72 8YT | 303676 | 184935 | Rhondda Cynon Taff County Borough Council | 19/1007/10 | [5 empty] | 2019-09-23 | [6 empty] | 2019-12-09 |  |  |  | 2024-12-09
| 7686 | 2020-03-31 | Muirden Energy | Drum Hollistan Wind Farm (Resubmission) | Wind Onshore | n/a | n/a | 35 | n/a |  |  |  | 5 | 7 | 125 | n/a | Planning Application Submitted | Application Submitted | the Sandside Estate, Land 2215M SW Of Under Keepers, Sandside, Reay, Thurso | Highland | Scotland | Scotland | KW14 7RN | 293078 | 963740 | Highland Council | 20/00645/FUL | [5 empty] | 2020-02-17
| 7687 | 2020-06-30 | Wind 2 | Moorshield Wind Farm | Wind Onshore | n/a | n/a | 15 | n/a |  |  |  | 5 | 3 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Moor Road, Kirkhill, East Renfrewshire, Approximately 6km South West of Eaglesham and 10 km North of East Stewarton, East Ayrshire | East Renfrewshire | Scotland | Scotland | G76 0QG | 251966 | 649283 | East Renfrewshire Council | 2020/0217/TP | [5 empty] | 2020-05-04
| 7688 | 2020-04-29 | Harmony Energy | Holes Bay | Battery | Stand-alone Storage | n/a | 15 | n/a |  |  |  | n/a | n/a | n/a | n/a | Under Construction | Under Construction | Land at Sterte Avenue West, Poole | Dorset | South West | England | BH15 2AL | 400787 | 91856 | Poole Borough Council | APP/17/00186/F | [5 empty] | 2017-02-08 | [6 empty] | 2020-01-14 |  |  |  | 2023-01-14 | 2020-01-01
| 7689 | 2020-01-02 | Anglian Water | Jaywick Water Recycling Centre | Solar Photovoltaics | n/a | n/a | 0.89 | n/a |  |  |  | n/a | n/a | n/a | Ground | Operational | Operational | Jaywick Water Recycling Centre, Clacton-on-Sea | Essex | Eastern | England | CO15 2NY | 614280 | 214153 | Tendring District Council | 17/02045/CMTR | [5 empty] | 2017-11-24 | [6 empty] | 2017-12-18 |  |  |  |  | 2019-11-16 | 2019-12-16
| 7696 | 2020-07-06 | RPS Group / Thurrock Power | Thurrock Flexible Generation Plant | Battery | Co-located with fossil fuel plant | n/a | 150 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Thurrock Flexible Generation Plant Fort Road Tilbury Essex | Essex | Eastern | England | RM18 8UJ | 565711 | 175889 | The Planning Inspectorate - National Infrastructure | EN010092 | [5 empty] | 2020-06-10
| 7708 | 2020-06-25 | Infinergy | Limekiln Wind Farm (Extension) | Wind Onshore | n/a | n/a | 21 | n/a |  |  |  | 4.2 | 5 | 149.9 | n/a | Planning Application Submitted | Application Submitted | Broubster Estate, Acheveilan North Estate and Limekiln Estate, southeast of Reay, Caithness | Highland | Scotland | Scotland |  | 300298 | 961309 | Scottish Government (S36) | ECU00002070 | [5 empty] | 2020-05-14
| 7712 | 2020-03-31 | Oasis Community Learning / Eden Sustainable | Oasis Academy Wintringham | Solar Photovoltaics | n/a | n/a | 0.172 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Oasis Academy Wintringham, Weelsby Avenue, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN32 0AZ | 527273 | 407483 | North East Lincolnshire Council | DM/0895/19/PNSOL | [5 empty] | 2020-02-07 | [6 empty] | 2020-03-23
| 7713 | 2020-04-27 | Push Energy | Clannell Road Tesco (Northampton South) | Solar Photovoltaics | n/a | n/a | 0.388 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Superstore, Hunsbury Centre, Clannell Road, Northampton, Northamptonshire | Northamptonshire | East Midlands | England | NN4 0JF | 474481 | 258030 | Northampton Borough Council | N/2020/0027 | [5 empty] | 2020-01-28 | [6 empty] | 2020-03-23
| 7714 | 2020-03-31 | Public Power Solutions (PPS) | Rock Barracks Solar Farm | Solar Photovoltaics | n/a | n/a | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Rock Barracks, Babcock Dyncorp, Otley Road, Sutton Heath, Woodbridge, Suffolk | Suffolk | Eastern | England | IP12 3LZ | 632663 | 248682 | East Suffolk District Council | DC/20/1198/FUL | [5 empty] | 2020-03-16
| 7718 | 2020-06-30 | Private Developer | Lower Skilts Farm | Solar Photovoltaics | n/a | n/a | 0.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | Lower Skilts Farm, Henley Road, Outhill, Studley, Warwickshire | Warwickshire | West Midlands | England | B80 7DU | 409848 | 267032 | Stratford on Avon District Council | 19/03523/FUL | [5 empty] | 2020-03-18 | 2020-06-16
| 7719 | 2020-03-31 | BSI Wind | Mullan Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 52 | n/a | Planning Application Submitted | Application Submitted | Lands approx 455m NW of, 15 Mullan Road, Kilrea, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 5XA | 106608 | 573937 | Causeway Coast and Glens | LA01/2020/0321/F | [5 empty] | 2020-03-13
| 7723 | 2020-06-25 | Tesco Stores | Portman Road Tesco (Reading West) | Solar Photovoltaics | n/a | n/a | 0.211 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Superstore, Portman Road, Reading, Berkshire | Berkshire | South East | England | RG30 1AW | 469655 | 173765 | Reading Borough Council | 200146 | [5 empty] | 2020-02-20 | [6 empty] | 2020-05-22 |  |  |  | 2023-05-22
| 7724 | 2020-06-30 | Enzygo | Orrell Street Battery Energy Storage Facility | Battery | Stand-alone Storage | n/a |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Site Of Former Council Depot, Orrell Street, Wigan, Greater Manchester | Greater Manchester | North West | England | WN1 3AQ | 358715 | 405122 | Wigan Council | A/20/88858/MAJOR | [5 empty] | 2020-03-12 | [6 empty] | 2020-06-11 |  |  |  | 2023-06-11
| 7725 | 2020-06-30 | Bouygues Energies | Swales Moor Farm | Battery | Co-located with fossil fuel plant | n/a | 5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Swales Moor Farm, Swales Moor Road, Halifax, West Yorkshire | Greater Manchester | Yorkshire and Humber | England | HX3 6UF | 409049 | 427866 | Calderdale Metropolitan Borough Council | 20/00240/FUL | [5 empty] | 2020-03-13 | [6 empty] | 2020-06-18 |  |  |  | 2023-06-18
| 7726 | 2020-06-25 | Renewable Energy Systems (RES) | Churchtown Solar Farm Battery Storage | Battery | Co-located with RE |  | 18 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Churchtown Solar Farm, Nanterrow Lane, Connor Downs, Hayle, Cornwall | Cornwall | South West | England | TR27 5BP | 159964 | 40457 | Cornwall Council | PA19/09903 | [5 empty] | 2019-12-04 | [6 empty] | 2020-03-19 |  |  |  | 2023-03-19
| 7729 | 2020-06-30 | The Highland Council | Inverness Royal Academy | Solar Photovoltaics | n/a | n/a | 0.28 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Inverness Royal Academy, 192 Culduthel Road, Culduthel, Inverness, Highlands | Highland | Scotland | Scotland | IV2 6AD | 266626 | 842081 | Highland Council | 20/01072/FUL | [5 empty] | 2020-03-06 | [6 empty] | 2020-05-04 |  |  |  | 2023-05-04
| 7731 | 2020-03-31 | Push Energy | Tesco Superstore Wisemore | Solar Photovoltaics | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Application Submitted | Application Submitted | Tesco Superstore, Wisemore, Walsall, West Midlands | West Midlands | West Midlands | England | WS2 8EZ | 401212 | 298812 | Walsall Council | 20/0008 | [5 empty] | 2020-03-12
| 7733 | 2020-04-27 | Push Energy | Cromwell Road Tesco | Solar Photovoltaics | n/a | n/a | 0.775 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco, Cromwell Road, Wisbech, Cambridgeshire | Cambridgeshire | Eastern | England | PE14 0RG | 545009 | 308090 | Fenland District Council | F/YR20/0077/PNSOL | [5 empty] | 2020-01-28 | [6 empty] | 2020-03-17
| 7735 | 2020-03-31 | Next Distribution | Elmsall Way Warehouse | Solar Photovoltaics | n/a | n/a | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Elmsall Way Warehouse, Dale Lane, South Elmsall, Pontefract, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | WF9 2XT | 448358 | 411902 | Wakefield Council | 19/02744/FUL | [5 empty] | 2019-12-18 | [6 empty] | 2020-03-16 |  |  |  | 2023-03-16
| 7736 | 2020-06-30 | Suffolk County Council | University Of Suffolk Campus North | Battery | Co-located with RE | n/a |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | University Of Suffolk Campus N, New Street, Ipswich, Suffolk | Suffolk | Eastern | England | IP4 1BZ | 617121 | 244193 | Suffolk County Council | SCC/0013/20IP | [5 empty] | 2020-03-12 | [6 empty] | 2020-04-14 |  |  |  | 2023-04-14
| 7737 | 2020-06-30 | Harmony Energy Storage | Rye Common | Battery | Stand-alone Storage | n/a | 49.5 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Refused | Application Refused | Street Record, Rye Common Lane, Crondall, Farnham, Surrey | Hampshire | South East | England | GU10 5DD | 478485 | 150474 | Hart District Council | 20/00651/FUL | [5 empty] | 2020-03-12 |  | 2020-05-01
| 7738 | 2020-03-31 | Private Developer | Kenyon Way | Solar Photovoltaics | n/a | n/a | 1.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Site To The West Of, Kenyon Way, South Of The Worsley Trading E, Little Hulton, Manchester, Greater Manchester | Greater Manchester | North West | England | M38 0EP | 371073 | 403418 | Salford City Council | 20/74960/FUL | [5 empty] | 2020-03-05
| 7739 | 2020-06-30 | Banks Renewables | Hazlehead Wind Farm Battery | Battery | Co-located with RE | 3937 | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Hazlehead Battery, Wind Farm, Crow Edge, Hazlehead Wind Farm, Sheffield, South Yorkshire | South Yorkshire | Yorkshire and Humber | England | S36 4HJ | 417625 | 404115 | Barnsley Council | 2020/0242 | [5 empty] | 2020-03-12 | [6 empty] | 2020-06-10
| 7740 | 2020-06-04 | Arenko Cleantech | Lister Drive | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent to Lister Drive, Carnegie Road, Liverpool, Merseyside | Merseyside | North West | England | L13 7HY | 338451 | 391858 | Liverpool City Council | 20F/0335 | [5 empty] | 2020-01-28 | [6 empty] | 2020-03-13 |  |  |  | 2023-03-13
| 7741 | 2020-03-31 | Oldham Metropolitan Borough Council | Land at Wrigley Head | Solar Photovoltaics | n/a | n/a | 0.89 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land at, Wrigley Head, Failsworth, Manchester, Greater Manchester | Greater Manchester | North West | England | M35 | 389832 | 402182 | Oldham Council | PA/344623/20 | [5 empty] | 2020-03-05
| 7742 | 2020-06-30 | Glassenbury Battery Storage | Huggin's Hall (Extension) | Battery | Stand-alone Storage | n/a | 9.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Electricity Distribution Site, Glassenbury Road, Cranbrook, Kent | Kent | South East | England | TN17 2 | 575739 | 135688 | Tunbridge Wells Borough Council | 20/00389/FULL | [5 empty] | 2020-02-19 | [6 empty] | 2020-04-17 |  |  |  | 2023-04-17
| 7743 | 2020-03-31 | Hill Power | Upper Hightown Road | Wind Onshore | n/a | n/a | 0.2 | n/a |  |  |  | 0.2 | 1 | 100 | n/a | Planning Application Submitted | Application Submitted | 510m north/north west if, 33 Upper Hightown Road, Ballysillan, Belfast, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT14 8RR | 143772 | 535132 | Belfast City Council | LA04/2020/0595/F | [5 empty] | 2020-03-06
| 7744 | 2020-03-31 | Northern Farm Partnership | Shinny Road Macosquin | Solar Photovoltaics | n/a | n/a | 0.95 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | 400m NW of Northstone Croaghan, Shinny Road, Macosquin, Coleraine, Co Londonderry | Co. Derry / Londonderry | Northern Ireland | Northern Ireland | BT51 4PS | 97330 | 584053 | Causeway Coast and Glens | LA01/2020/0279/F | [5 empty] | 2020-03-06
| 7745 | 2020-06-30 | Private Developer | Howden Farm | Solar Photovoltaics | n/a | n/a | 0.186 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Field To The West Of Howden Wo, Gifford, Haddington, Lothian | East Lothian | Scotland | Scotland | EH41 4JS | 349610 | 667181 | East Lothian Council | 20/00238/P | [5 empty] | 2020-03-05 | [6 empty] | 2020-04-27 |  |  |  | 2023-04-27
| 7746 | 2020-04-29 | Eco-Economix | Basing Road | Battery | Stand-alone Storage | n/a | 21 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land At, Basing Road, Old Basing, Basingstoke, Hampshire | Hampshire | South East | England | RG24 7AL | 465530 | 152602 | Basingstoke and Deane Borough Council | 19/03097/FUL | [5 empty] | 2019-12-19 | [6 empty] | 2020-03-10 |  |  |  | 2023-03-10
| 7749 | 2020-06-30 | Eden Sustainable | Princess Yachts Ltd (5) | Solar Photovoltaics | n/a | n/a | 0.99 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 2 Newport Street, Plymouth, Devon | Devon | South West | England | PL1 3QG | 246096 | 54127 | Plymouth City Council | 20/00086/GPD | [5 empty] | 2020-03-05 | [6 empty] | 2020-04-30 |  |  |  | 2023-04-30
| 7750 | 2020-04-27 | Push Energy | Tesco Store The Forum Stevenage | Solar Photovoltaics | n/a | n/a | 0.426 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Stores Extra, 1 - 5 The Forum, Town Centre Stevenage, Herts, Stevenage, Hertfordshire | Hertfordshire | Eastern | England | SG1 1ES | 523632 | 224354 | Stevenage Borough Council | 20/00015/CPAS | [5 empty] | 2020-01-10 | [6 empty] | 2020-03-06
| 7751 | 2020-04-27 | Push Energy | Featherstall Road Tesco (Chadderton) | Solar Photovoltaics | n/a | n/a | 0.543 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Stores Ltd, Featherstall Road North, Oldham, Greater Manchester | Greater Manchester | North West | England | OL9 6BW | 391740 | 405450 | Oldham Council | PA/344401/20 | [5 empty] | 2020-01-09 | [6 empty] | 2020-03-05
| 7752 | 2020-06-30 | Eden Sustainable | Princess Yachts Ltd (1) | Solar Photovoltaics | n/a | n/a | 0.478 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Princess Yachts Ltd, Coypool Road, Plympton, Plymouth, Devon | Devon | South West | England | PL7 4NW | 251930 | 57371 | Plymouth City Council | 20/00161/GPD | [5 empty] | 2020-03-05 | [6 empty] | 2020-04-30 |  |  |  | 2023-04-30
| 7753 | 2020-06-30 | Eden Sustainable | Princess Yachts Ltd (2) | Solar Photovoltaics | n/a | n/a | 0.58 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Princess Yachts Ltd, Coypool Road, Plympton, Plymouth, Devon | Devon | South West | England | PL7 4NW | 251806 | 57209 | Plymouth City Council | 20/00165/GPD | [5 empty] | 2020-03-05 | [6 empty] | 2020-04-30 |  |  |  | 2023-04-30
| 7754 | 2020-06-30 | Eden Sustainable | Princess Yachts Ltd (3) | Solar Photovoltaics | n/a | n/a | 0.29 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Princess Yachts International, Coypool Road, Plympton, Plymouth, Devon | Devon | South West | England | PL7 4NW | 251880 | 57244 | Plymouth City Council | 20/00159/GPD | [5 empty] | 2020-03-05 | [6 empty] | 2020-04-30 |  |  |  | 2023-04-30
| 7755 | 2020-06-30 | Eden Sustainable | Princess Yachts Ltd (4) | Solar Photovoltaics | n/a | n/a | 0.22 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Princess Yachts Ltd, Coypool Road, Plympton, Plymouth, Devon | Devon | South West | England | PL7 4NW | 251901 | 57147 | Plymouth City Council | 20/00157/GPD | [5 empty] | 2020-03-05 | [6 empty] | 2020-04-30 |  |  |  | 2023-04-30
| 7757 | 2020-03-31 | EnergieKontor UK | Fell Wind Farm Battery | Battery | Co-located with RE | 7756 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Fell Wind Farm, Moniaive, Thornhill, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG3 | 272679 | 583776 | Dumfries and Galloway Council | 20/0148/FUL | [5 empty] | 2020-02-19
| 7758 | 2020-06-30 | Hutchesons Educational Trust / Intelligent Alternatives | Hutchesons Grammar School | Solar Photovoltaics | n/a | n/a | 0.175 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 21 Beaton Road, Glasgow, Strathclyde | Glasgow | Scotland | Scotland | G41 4NW | 257194 | 662717 | Glasgow City | 20/00578/FUL | [5 empty] | 2020-03-03 | [6 empty] | 2020-05-01 |  |  |  | 2023-05-01
| 7760 | 2020-03-31 | Greenheath Farming | Land North of Hill Farm | Solar Photovoltaics | n/a | n/a | 8.92 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land North Of Hill Farm, Hill Farm Lane, Duns Tew, Bicester, Oxfordshire | Oxfordshire | South East | England | OX25 | 446055 | 229953 | Cherwell District Council | 20/00574/F | [5 empty] | 2020-02-26
| 7762 | 2020-06-30 | Private Developer | Netherton | Wind Onshore | n/a | n/a | 0.9 | n/a |  |  |  | 0.9 | 1 | 78 | n/a | Planning Permission Granted | Awaiting Construction | Land At Netherton, Fisherford, Inverurie, Grampian | Aberdeenshire | Scotland | Scotland | AB51 8YS | 367378 | 836927 | Aberdeenshire Council | APP/2020/0293 | [5 empty] | 2020-03-02 | [6 empty] | 2020-04-28 |  |  |  | 2023-04-28
| 7763 | 2020-06-30 | Scottish Fire and Rescue Service | Claylands Road | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 21 Claylands Road, Newbridge, Lothian | Edinburgh | Scotland | Scotland | EH28 8LF | 312064 | 671748 | Edinburgh City Council | 20/00942/FUL | [5 empty] | 2020-02-26 | [6 empty] | 2020-04-23 |  |  |  | 2023-04-22
| 7764 | 2020-06-30 | Intelligent Land Investments (ILI) | Fordtown Energy Storage (Resubmission) | Battery | Stand-alone Storage | n/a | 29.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Fordtown, Kintore, Inverurie, Grampian | Aberdeenshire | Scotland | Scotland | AB51 0XJ | 377990 | 814576 | Aberdeenshire Council | ENQ/2020/0261 | [5 empty] | 2020-02-26 | [6 empty] | 2020-03-17
| 7765 | 2020-03-31 | Watt Energy Saver | Hollywood Bowl | Solar Photovoltaics | n/a | n/a | 0.15 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Hollywood Bowl, 3 Cardigan Fields Road, Leeds, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | LS4 2DG | 427629 | 434252 | Leeds City Council | 20/00203/DPD | [5 empty] | 2020-01-14 | [6 empty] | 2020-02-28
| 7766 | 2020-03-31 | Pattemores Transport (Crewkerne) | Pattemores Transport (Crewkern) | Solar Photovoltaics | n/a | n/a | 2.08 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Pattemores Transport (Crewkern, Mosterton Road, Misterton, Crewkerne, Somerset | Somerset | South West | England | TA18 8NT | 346361 | 107149 | South Somerset District Council | 20/00315/FUL | [5 empty] | 2020-02-14
| 7767 | 2020-03-31 | Scottish Power Renewables | Brigstock Solar Farm | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land North Of Old Head Wood, Grafton Road, Brigstock, Kettering, Northamptonshire | Northamptonshire | East Midlands | England | NN14 | 492168 | 283517 | East Northamptonshire Council | 20/00207/FUL | [5 empty] | 2020-02-19
| 7768 | 2020-03-31 | Brooklands Healthcare | Woodside Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 55 | n/a | Planning Permission Granted | Awaiting Construction | Lands 175m North West of, 90 Woodside Road, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT42 4HG | 129390 | 560546 | Mid and East Antrim | LA02/2019/0935/F | [5 empty] | 2019-12-11 | [6 empty] | 2020-02-25 |  |  |  | 2025-02-24
| 7771 | 2020-06-30 | Perkins Engines Company | Perkins Engines | Solar Photovoltaics | n/a | n/a | 1.166 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Perkins Engines, Frank Perkins Way, Peterborough, Cambridgeshire | Cambridgeshire | Eastern | England | PE1 5FQ | 521283 | 300052 | Peterborough City Council | 20/00163/FUL | [5 empty] | 2020-02-21 | [6 empty] | 2020-05-01 |  |  |  | 2023-05-01
| 7772 | 2020-06-30 | Statkraft UK | Liverpool Energy Management Facility | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To The South Of, Carnegie Road, Liverpool, Merseyside | Merseyside | North West | England | L13 7HY | 338451 | 391858 | Liverpool City Council | 20F/0550 | [5 empty] | 2020-02-21 | [6 empty] | 2020-06-17 |  |  |  | 2023-06-17
| 7773 | 2020-06-29 | Penso Power | Stonehill Energy Storage | Battery | Stand-alone Storage | n/a | 50 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent To Electricity S, Stonehill, Charlton, Malmesbury, Wiltshire | Wiltshire | South West | England | SN16 9RP | 399819 | 189611 | Wiltshire Council | 19/11460/FUL | [5 empty] | 2019-11-29 | [6 empty] | 2020-02-24
| 7776 | 2020-06-25 | Entrust Microgrid | Leiria Way Car Park | Battery | Stand-alone Storage | n/a |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Car Park Leiria Way, 13 High Street, Runcorn, Cheshire | Cheshire | North West | England | WA7 1AP | 351448 | 382977 | Halton Borough Council | 20/00079/FUL | [5 empty] | 2020-02-18 | [6 empty] | 2020-05-05 |  |  |  | 2023-05-05
| 7777 | 2020-03-31 | Private Developer | Killymittan Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 55 | n/a | Planning Application Submitted | Application Submitted | Land Approximately 300M SW Of, 37 Killymittan Road, Ballinamallard, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT94 2FW | 40120 | 516981 | Fermanagh and Omagh | LA10/2020/0168/F | [5 empty] | 2020-02-14
| 7778 | 2020-03-31 | Private Developer | Rockdale Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 55 | n/a | Planning Application Submitted | Application Submitted | Lands approximately 625m SE of, 71 Rockdale Road, Cookstown, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT80 9BA | 88927 | 532293 | Mid Ulster | LA09/2020/0232/F | [5 empty] | 2020-02-19
| 7779 | 2020-03-31 | Private Developer | Edenmore Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 55 | n/a | Planning Application Submitted | Application Submitted | Approximately 100M SE Of, 133 Edenmore Road, Carn, Tempo, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT94 3BP | 43675 | 514092 | Fermanagh and Omagh | LA10/2020/0160/F | [5 empty] | 2020-02-14
| 7780 | 2020-06-30 | Anesco | Newton Wood Farm | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Newton Wood Farm, Newtonwood Lane, Newton, Alfreton, Derbyshire | Derbyshire | East Midlands | England | DE55 5SG | 445457 | 360430 | Bolsover District Council | 20/00202/FUL | [5 empty] | 2020-05-27
| 7781 | 2020-03-31 | Solar South West | Two Post Lane | Solar Photovoltaics | n/a | 7847 | 12 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Two Post Lane, Spreyton, South Tawton, Crediton, Devon | Devon | South West | England | EX17 5AY | 267970 | 96660 | West Devon Borough Council | 0362/20/FUL | [5 empty] | 2020-02-04
| 7782 | 2020-06-30 | Electricity North West | ENWL Training Academy | Solar Photovoltaics | n/a | n/a | 0.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | 6 Dyneley Road, Blackburn, Lancashire | Lancashire | North West | England | BB1 3AB | 370231 | 428929 | Blackburn with Darwen Borough Council | 10/20/0091 | [5 empty] | 2020-02-12 | [6 empty] | 2020-04-08 |  |  |  | 2023-04-08
| 7783 | 2020-06-30 | Diodes Zetex Semiconductors | Bentfield Industrial Units | Battery | Co-located with fossil fuel plant | n/a | 0.25 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Bentfield Industrial Units, Stockfield Road, Chadderton, Oldham, Greater Manchester | Greater Manchester | North West | England | OL9 9LL | 391074 | 405015 | Oldham Council | PA/344529/20 | [5 empty] | 2020-02-13 | [6 empty] | 2020-05-05 |  |  |  | 2023-05-05
| 7784 | 2020-03-31 | Private Developer | Eden Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 53 | n/a | Planning Application Submitted | Application Submitted | 335m NW of, 43 Eden Road, Portglenone, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT44 8LS | 106473 | 561926 | Mid Ulster | LA09/2020/0203/F | [5 empty] | 2020-02-14
| 7785 | 2020-06-30 | Green Energy International | Patrickston Farm | Solar Photovoltaics | n/a | n/a | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land 800M SW of Patrickston Fa, Kippen, Gargunnock, Stirling, Central | Stirling | Scotland | Scotland | FK8 3JH | 269179 | 695851 | Stirling Council | 19/00915/FUL | [5 empty] | 2020-01-27 | [6 empty] | 2020-04-05 |  |  |  | 2023-04-05
| 7786 | 2020-03-31 | Elgin Energy EsCo | Wood Lane Solar Farm | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land North West And South Of F, Wood Lane, Sturton-le-Steeple, Retford, Nottinghamshire | Nottinghamshire | East Midlands | England | DN22 9HT | 476501 | 384053 | Bassetlaw District Council | 20/00117/FUL | [5 empty] | 2020-02-06
| 7792 | 2020-03-31 | Oakapple Renewable Energy | Chancerygate Way | Solar Photovoltaics | n/a | n/a | 0.27 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | 7 Chancerygate Way, Farnborough, Hampshire | Hampshire | South East | England | GU14 8FF | 486956 | 157685 | Rushmoor Borough Council | 20/00006/FUL | [5 empty] | 2020-01-06 | [6 empty] | 2020-02-07 |  |  |  | 2023-02-07
| 7793 | 2020-06-30 | Sunderland City Services | Evolve Business Centre | Solar Photovoltaics | n/a | 7794 | 0.28 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Evolve Business Centre, Cygnet Way, Houghton-Le-Spring, Tyne and Wear | Tyne and Wear | North East | England | DH4 5QY | 433344 | 548627 | Sunderland City Council | 20/00134/LP3 | [5 empty] | 2020-02-05 | [6 empty] | 2020-05-01 |  |  |  | 2025-05-01
| 7794 | 2020-06-30 | Sunderland City Services | Evolve Business Centre | Battery | Co-located with RE | 7793 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Evolve Business Centre, Cygnet Way, Houghton-Le-Spring, Tyne and Wear | Tyne and Wear | North East | England | DH4 5QY | 433344 | 548627 | Sunderland City Council | 20/00134/LP3 | [5 empty] | 2020-02-05 | [6 empty] | 2020-05-01 |  |  |  | 2025-05-01
| 7795 | 2020-06-05 | Yeo Valley Farms | Lag Farm | Solar Photovoltaics | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Lag Farm, Bath Road, Blagdon, Bristol, Avon | Somerset | South West | England | BS40 7SG | 351543 | 158644 | North Somerset Council | 19/P/3087/SJA | [5 empty] | 2019-12-11 | [6 empty] | 2020-02-05
| 7797 | 2020-04-27 | Push Energy | Tesco Quay Street | Solar Photovoltaics | n/a | n/a | 0.349 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Tesco Superstore, 1 - 2 Quay Street, Fareham, Hampshire | Hampshire | South East | England | PO16 0LE | 458020 | 106152 | Fareham Borough Council | P/20/0010/PA | [5 empty] | 2020-01-06 | [6 empty] | 2020-02-03
| 7800 | 2020-06-30 | Shaw Energy | Hawthorne Road | Battery | Stand-alone Storage | n/a | 40 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | 491 Linacre Lane, Bootle, Merseyside | Merseyside | North West | England | L20 5AL | 334606 | 396285 | Sefton Council | DC/2020/00085 | [5 empty] | 2020-01-29 | [6 empty] | 2020-04-14 |  |  |  | 2023-04-14
| 7801 | 2020-03-31 | Private Developer | Reservoir Road | Wind Onshore | n/a | n/a | 0.15 | n/a |  |  |  | 0.15 | 1 | 55 | n/a | Planning Application Submitted | Application Submitted | 200m East of, 15 Reservoir Road, Corkey, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT44 9JE | 126534 | 579631 | Mid and East Antrim | LA01/2020/0078/F | [5 empty] | 2020-01-21
| 7804 | 2020-03-31 | Scottish Power Renewables | Clauchrie Windfarm Battery | Battery | Co-located with RE | 7803 | 25 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Clauchrie Windfarm, 6KM North-East Of, Barhill, Newton Stewart, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG8 | 229552 | 588722 | Scottish Government (S36) | ECU00002001 | [5 empty] | 2019-12-18
| 7805 | 2020-03-31 | Private Developer | Shankill Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 75 | n/a | Planning Application Submitted | Application Submitted | 290m South East of, 65 Shankill Road, Magherahar, Cullen, Enniskillen, Co Fermanagh | Co. Fermanagh | Northern Ireland | Northern Ireland | BT93 7BW | 27250 | 516548 | Fermanagh and Omagh | LA10/2020/0081/F | [5 empty] | 2020-01-24
| 7806 | 2020-06-30 | Silberline | Banbeath Industrial Estate | Solar Photovoltaics | n/a | n/a | 0.15 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Unit 1, 8 Banbeath Industrial Estate, Banbeath place, Leven, Fife | Fife | Scotland | Scotland | KY8 5HD | 337110 | 701484 | Fife Council | 20/00026/FULL | [5 empty] | 2020-01-24 | [6 empty] | 2020-04-28 |  |  |  | 0
| 7808 | 2020-03-31 | Pennant Walters | Pant y Wal (Extension) | Wind Onshore | n/a | n/a | 5 | n/a |  |  |  | 2.5 | 2 | 125 | n/a | Planning Application Submitted | Application Submitted | Pant y Wal Wind Farm, Ogmore, Bridgend, Mid Glamorgan | Bridgend | Wales | Wales | CF35 6EG | 294041 | 190912 | Bridgend County Borough Council | P/20/42/FUL | [5 empty] | 2020-01-15
| 7809 | 2020-06-25 | Private Developer | Carmagrim Road | Wind Onshore | n/a | n/a | 0.15 | n/a |  |  |  | 0.15 | 1 | 65 | n/a | Planning Permission Granted | Awaiting Construction | 450m south east of, 29a Carmagrim Road, Portglenone, Ballymena, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT44 8DE | 115931 | 559236 | Mid and East Antrim | LA02/2020/0045/F | [5 empty] | 2020-01-20 | [6 empty] | 2020-04-06 |  |  |  | 2025-04-06
| 7810 | 2020-06-30 | Ellergreen Estate | James Cropper Effluent Plant | Solar Photovoltaics | n/a | n/a | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Withdrawn | Application Withdrawn | James Cropper Effluent Plant, Burneside, Kendal, Cumbria | Cumbria | North West | England | LA9 6PZ | 350603 | 495881 | South Lakeland District Council | SL/2019/1027 | [5 empty] | 2019-12-17 | 2020-01-21
| 7815 | 2020-03-31 | Spring Che | Rockbeare Hill | Solar Photovoltaics | n/a | n/a | 15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land To The South Of, Rockbeare Hill, Rockbeare, Exeter, Devon | Devon | South West | England | EX5 2EZ | 305402 | 93695 | East Devon District Council | 19/2832/MFUL | [5 empty] | 2020-01-10
| 7817 | 2020-03-31 | Voltalia UK | Higher Stockbridge Farm | Solar Photovoltaics | n/a | n/a | 35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Higher Stockbridge Farm, Stockbridge, Sherborne, Dorset | Dorset | South West | England | DT9 6EP | 363744 | 111132 | West Dorset District Council | WD/D/19/003181 | [5 empty] | 2019-12-23
| 7819 | 2020-06-30 | Lidl UK | Harborough Road Store | Solar Photovoltaics | n/a | n/a | 0.15 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Former Waitrose Ltd, 36 Harborough Road, Oadby, Leicester, Leicestershire | Leicestershire | East Midlands | England | LE2 4LA | 462395 | 300585 | Oadby and Wigston Borough Council | 19/00513/FUL | [5 empty] | 2019-12-20 | [6 empty] | 2020-04-16 |  |  |  | 2023-04-16
| 7820 | 2020-04-20 | Coriolis Energy | Manor Farm | Battery | Stand-alone Storage | n/a | 26 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Manor Farm, Newgate Lane, Londonthorpe, Grantham, Lincolnshire | Lincolnshire | East Midlands | England | NG31 9RY | 495062 | 337504 | South Kesteven District Council | S19/0181 | [5 empty] | 2019-01-28 | [6 empty] | 2019-06-04 |  |  |  | 2022-06-04
| 7823 | 2020-06-30 | Lightsource BP | Hulam Farm | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Hulam Farm, Castle Eden, Hartlepool, Cleveland | County Durham | North East | England | TS27 4SA | 443903 | 536669 | Durham County Council | DM/19/03959/FPA | [5 empty] | 2019-12-27 | [6 empty] | 2020-06-17 |  |  |  | 2023-06-17
| 7827 | 2020-03-31 | ENGIE Renewables | Mauxhall Farm | Battery | Co-located with RE | 7826 | 24 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Mauxhall Farm, Immingham Road, Stallingborough, Grimsby, Humberside | Humberside | Yorkshire and Humber | England | DN41 8BS | 519206 | 413210 | North East Lincolnshire Council | DM/1145/19/FUL | [5 empty] | 2019-12-17
| 7828 | 2020-03-31 | Balanced Grid Solutions | Titchfield Lane | Battery | Stand-alone Storage | n/a | 49 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land South Of Ash Farm, Titchfield Lane, Wickham, Fareham, Hampshire | Hampshire | South East | England | PO15 6DY | 455282 | 109603 | Winchester City Council | 19/02710/FUL | [5 empty] | 2019-12-04
| 7830 | 2020-03-31 | Cenin Renewables | Aerospace Business Park | Solar Photovoltaics | n/a | n/a | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Picketston, Picketston Village, Picketston, Barry, South Glamorgan | Vale of Glamorgan | Wales | Wales | CF62 4QN | 300077 | 169782 | Vale of Glamorgan Council | 2019/01314/FUL | [5 empty] | 2019-12-16 | [6 empty] | 2020-03-26 |  |  |  | 2025-03-26
| 7832 | 2020-06-25 | Noriker Power | Welkin Mill | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Withdrawn | Application Withdrawn | Welkin Mill, Welkin Road, Bredbury, Stockport, Greater Manchester | Greater Manchester | North West | England | SK6 2BH | 391076 | 391375 | Stockport Metropolitan Borough Council | DC/075050 | [5 empty] | 2019-12-23 | 2020-05-28
| 7833 | 2020-03-31 | Golan Wind | Rosnareen Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 85 | n/a | Planning Application Submitted | Application Submitted | 632m SE of, 69 Rosnareen Road, Trillick, Omagh, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT78 3SF | 45218 | 516695 | Fermanagh and Omagh | LA10/2019/1475/F | [5 empty] | 2019-12-20
| 7834 | 2020-03-31 | Stephenson Halliday | Crumps Yard Solar Farm | Solar Photovoltaics | n/a | n/a | 1.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Crumps Yard, Dock Road, Connah's Quay, Deeside, Clwyd | Flintshire | Wales | Wales | CH5 4DS | 329707 | 369690 | Flintshire County Council | 60765 | [5 empty] | 2019-12-10
| 7840 | 2020-03-31 | Croome Airfield Solar | Croome Airfield Solar Farm | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Defford Aerodrome, Rebecca Road, Besford, Worcester, Hereford and Worcester | Hereford and Worcester | West Midlands | England | WR8 9ES | 389440 | 243350 | Wychavon District Council | 19/02632/FUL | [5 empty] | 2019-12-10
| 7841 | 2020-06-25 | Private Developer | Rassau Industrial Estate | Battery | Stand-alone Storage | n/a | 6 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Unit 16, Rassau Industrial Estate, Rassau, Ebbw Vale, Gwent | Blaenau Gwent | Wales | Wales | NP23 5SD | 315062 | 212353 | Blaenau Gwent County Borough Council | C/2019/0326 | [5 empty] | 2019-11-25 | [6 empty] | 2020-01-22
| 7842 | 2020-03-31 | Shires Hamilton | Auchteraw Energy Storage | Battery | Stand-alone Storage | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land 280M Se Of Torrdhuin, Auchterawe, Fort Augustus, Highlands | Highland | Scotland | Scotland | PH32 4BT | 234761 | 807618 | Highland Council | 19/05385/FUL | [5 empty] | 2019-12-06
| 7846 | 2020-03-31 | CleanEarth | West Dykes | Wind Onshore | n/a | n/a | 3 | n/a |  |  |  | 3 | 1 | 150 | n/a | Planning Application Submitted | Application Submitted | West Dykes Farm, Strathaven South, Strathaven, Strathclyde | South Lanarkshire | Scotland | Scotland | ML10 6RH | 266058 | 639006 | South Lanarkshire Council | P/19/1829 | [5 empty] | 2019-12-19
| 7847 | 2020-03-31 | Solar South West | Two Post Lane | Battery | Co-located with RE | 7781 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Two Post Lane, Spreyton, South Tawton, Crediton, Devon | Devon | South West | England | EX17 5AY | 267970 | 96660 | West Devon Borough Council | 0362/20/FUL | [5 empty] | 2020-02-04
| 7849 | 2020-04-01 | EnergieKontor UK | Cornharrow Wind Farm Battery | Battery | Co-located with RE | 7761 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Cornharrow Wind Farm, Land At Cornharrow, Dalry, Castle Douglas, Dumfries and Galloway | Dumfries and Galloway | Scotland | Scotland | DG7 3UG | 266701 | 592862 | Dumfries and Galloway Council | 20/0159/FUL | [5 empty] | 2020-02-19
| 7851 | 2020-03-31 | Scottish Power Renewables | Kilgallioch Windfarm (Extension - Solar) | Solar Photovoltaics | n/a | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | High Eldrig, land 12 km NW of Kirkcowan, SE of Kilgallioch Windfarm | Dumfries and Galloway | Scotland | Scotland |  | 225000 | 570000 | Scottish Government (S36) | ECU00001996 | [5 empty] | 2019-12-16
| 7856 | 2020-07-06 | Cleve Hill Solar (Hive Energy/ Wirsol Energy) | Cleve Hill Solar Project | Battery | Co-located with RE | 6502 | 350 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Graveney, Whitstable | Kent | South East | England | ME13 9EE | 603057 | 163995 | The Planning Inspectorate - National Infrastructure | EN010085 | [5 empty] | 2018-11-16 | [6 empty] | 2020-05-28 |  |  |  | 2025-06-19
| 7857 | 2020-06-24 | Cory Riverside Energy | Riverside Energy Park (REP) | Solar Photovoltaics | n/a | 7036 | 1 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Norman Road, Bexley, London | London | South East | England | DA17 6JY | 549545 | 180595 | The Planning Inspectorate - National Infrastructure | EN010093 | [5 empty] | 2018-11-16 | [6 empty] | 2020-04-09
| 7882 | 2020-06-25 | ScottishPower Renewables | Arecleoch Wind Farm (extension) | Battery | Co-located with RE | 7881 | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land 2km south west of Barrhill, South Ayrshire | South Ayrshire | Scotland | Scotland | KA26 0PP | 221500 | 578500 | Scottish Government (S36) | ECU00001864 | [5 empty] | 2019-06-12
| 7883 | 2020-06-30 | Solar Advanced Systems (SAS Energy) | Brinsbury Campus Stane | Solar Photovoltaics | n/a | n/a | 0.2 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Permission Granted | Awaiting Construction | Land at Brinsbury Campus, North Heath, Pulborough, West Sussex | West Sussex | South East | England | RH20 1DL | 506544 | 122267 | Horsham District Council | DC/20/0629 | [5 empty] | 2020-03-27 | [6 empty] | 2020-06-23 |  |  |  | 2023-06-23
| 7892 | 2020-06-30 | Private Developer | Burton End | Solar Photovoltaics | n/a | n/a | 1.5 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land To The South East Of, Burton End, West Wickham, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB21 | 563073 | 250334 | South Cambridgeshire District Council | 20/01564/FUL | [5 empty] | 2020-06-08
| 7894 | 2020-06-30 | Awel Aman Tawe | Mynydd y Gwryhd Solar Farm | Battery | Co-located with RE | 7893 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land To The West Of, Cwmgors On Mynydd Uchaf, Adjoining Community Wind Turbi, Swansea, West Glamorgan | Neath Port Talbot | Wales | Wales | SA9 | 272720 | 210612 | Neath Port Talbot County Borough Council | P2020/0408 | [5 empty] | 2020-06-10
| 7896 | 2020-06-30 | Warwickshire Solar 1 | Harborough Fields Farm | Solar Photovoltaics | n/a | 7897 | 27 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Harborough Fields Farm, Churchover Lane, Churchover, Rugby, Warwickshire | Warwickshire | West Midlands | England | CV23 0ER | 450071 | 280647 | Rugby Borough Council | R20/0438 | [5 empty] | 2020-06-04
| 7897 | 2020-06-30 | Warwickshire Solar 1 | Harborough Fields Farm | Battery | Co-located with RE | 7896 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Harborough Fields Farm, Churchover Lane, Churchover, Rugby, Warwickshire | Warwickshire | West Midlands | England | CV23 0ER | 450071 | 280647 | Rugby Borough Council | R20/0438 | [5 empty] | 2020-06-04
| 7903 | 2020-06-30 | Lidl Northern Ireland | Lidl Nutts Corner | Solar Photovoltaics | n/a | n/a | 0.16 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Application Submitted | Application Submitted | Lidl Supermarket, 71 - 85 Roe Fold, Main Street, Limavady, Co Londonderry | Co. Londonderry | Northern Ireland | Northern Ireland | BT49 0EL | 84003 | 584307 | Causeway Coast and Glens | LA01/2020/0527/F | [5 empty] | 2020-06-03
| 7906 | 2020-06-30 | UK Power Networks | Reach Road | Battery | Co-located with RE | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Armtrac, 70 Reach Road, Burwell, Cambridge, Cambridgeshire | Cambridgeshire | Eastern | England | CB25 0AH | 558327 | 266047 | East Cambridgeshire District Council | 20/00655/SON | [5 empty] | 2020-05-20
| 7913 | 2020-06-30 | Endless Energy | Dalton Lane | Battery | Stand-alone Storage | n/a |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land At, Dalton Lane, Keighley, West Yorkshire | West Yorkshire | Yorkshire and Humber | England | BD21 4HT | 407472 | 441446 | Bradford Metropolitan District Council | 20/01511/MAR | [5 empty] | 2020-05-15
| 7914 | 2020-06-30 | Richard Thomas Associates | Morfa Pingett | Solar Photovoltaics | n/a | n/a | 1.6 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | MORFA PINGETT, Pinged, Burry Port, Dyfed | Carmarthenshire | Wales | Wales | SA16 0JE | 241320 | 205018 | Carmarthenshire County Council | S/40618 | [5 empty] | 2020-05-21
| 7915 | 2020-06-30 | Scottish Water | Perth Wastewater Treatment Works (Extension) | Solar Photovoltaics | n/a | 7916 | 0.3 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land 150 Metres South West Of, Rhynd, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH1 0AD | 314371 | 722017 | Perth and Kinross Council | 20/00540/FLL | [5 empty] | 2020-05-18
| 7916 | 2020-06-30 | Scottish Water | Perth Wastewater Treatment Works (Extension) | Battery | Co-located with RE | 7915 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land 150 Metres South West Of, Rhynd, Perth, Tayside | Perth and Kinross | Scotland | Scotland | PH1 0AD | 314371 | 722017 | Perth and Kinross Council | 20/00540/FLL | [5 empty] | 2020-05-18
| 7920 | 2020-06-30 | Arena Capital Partners | Terrydoo Road 1 | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 67 | n/a | Planning Application Submitted | Application Submitted | Approximately 654m East SE Of, 34 Terrydoo Road, Limavady, Co Londonderry | Co. Londonderry | Northern Ireland | Northern Ireland | BT49 0PF | 90516 | 581300 | Causeway Coast and Glens | LA01/2020/0483/F | [5 empty] | 2020-03-20
| 7928 | 2020-06-30 | Arcadis / Ministry of Justice | H M Prison Bure | Solar Photovoltaics | n/a | n/a | 0.19 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | H M Prison Bure, Jaguar Drive, Badersfield, Norwich, Norfolk | Norfolk | Eastern | England | NR10 5GB | 625937 | 323187 | North Norfolk District Council | PF/20/0712 | [5 empty] | 2020-04-30 | [6 empty] | 2020-06-25 |  |  |  | 2023-06-25
| 7929 | 2020-06-30 | Voltalia UK | Clifton Farm | Solar Photovoltaics | n/a | n/a | 35 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Clifton Farm, Clifton Farm Lane, Clifton Maybank, Weston-Super-Mare, Avon | Somerset | South West | England | BS22 | 357927 | 112190 | North Somerset Council | WD/D/20/001057 | [5 empty] | 2020-05-05
| 7930 | 2020-06-30 | Orchard Street Investment Management | Homebase Linden Park Road | Solar Photovoltaics | n/a | n/a | 0.24 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Homebase Ltd, Linden Park Road, Tunbridge Wells, Kent | Kent | South East | England | TN2 5QL | 557711 | 138397 | Tunbridge Wells Borough Council | 20/00920/PN14J | [5 empty] | 2020-03-25 | [6 empty] | 2020-05-15
| 7931 | 2020-06-30 | Private Developer | Stroan Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 77 | n/a | Planning Application Submitted | Application Submitted | Approximately 100m West Of, 37 Stroan Road, Dervock, Ballymoney, Co Antrim | Co. Antrim | Northern Ireland | Northern Ireland | BT53 8BZ | 115028 | 588873 | Causeway Coast and Glens | LA01/2020/0451/F | [5 empty] | 2020-05-06
| 7935 | 2020-06-30 | Arena Capital Partners | Terrydoo Road 2 | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 67 | n/a | Planning Application Submitted | Application Submitted | Approx 800m East South East Of, 34 Terrydoo Road, Limavady, Co Londonderry | Co. Londonderry | Northern Ireland | Northern Ireland | BT49 0PF | 90875 | 582002 | Causeway Coast and Glens | LA01/2020/0433/F | [5 empty] | 2020-03-12
| 7938 | 2020-06-30 | Conrad Energy | Philip Street Car Breakers | Battery | Stand-alone Storage | n/a | 7.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Philip Street Car Breakers, Philip Street, St. Philips Marsh, Bristol, Avon | Avon | South West | England | BS2 0TA | 360605 | 172276 | Bristol City Council | 20/01888/F | [5 empty] | 2020-05-04
| 7941 | 2020-06-30 | JBM Solar Project | Minety Substation | Solar Photovoltaics | n/a | 7942 | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land Near Minety Substation, Stonehill, Charlton, Malmesbury, Wiltshire | Wiltshire | South West | England | SN16 9DX | 399585 | 189182 | Wiltshire Council | 20/03528/FUL | [5 empty] | 2020-04-27
| 7942 | 2020-06-30 | JBM Solar Project | Minety Substation | Battery | Co-located with RE | 7941 | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land Near Minety Substation, Stonehill, Charlton, Malmesbury, Wiltshire | Wiltshire | South West | England | SN16 9DX | 399585 | 189182 | Wiltshire Council | 20/03528/FUL | [5 empty] | 2020-04-27
| 7943 | 2020-06-30 | Edinburgh Community Solar Co-op | City of Edinburgh Council Buildings | Solar Photovoltaics | n/a |  | 0.16 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Application Submitted | Application Submitted | Waverley Court, 4 East Market Street, Edinburgh, Lothian | Edinburgh | Scotland | Scotland | EH8 8BG | 326167 | 673824 | Edinburgh City Council | 20/01666/FUL | [5 empty] | 2020-04-23
| 7946 | 2020-06-30 | Gigabox Developments | Dundee Technology Park | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land At Technology Park, South Road, Dundee, Tayside | Dundee | Scotland | Scotland | DD2 4LX | 335237 | 731592 | Dundee City Council | 20/00239/FULL | [5 empty] | 2020-04-30
| 7950 | 2020-06-30 | Lightsource BP | Saputo Dairy UK | Battery | Co-located with RE | 7949 |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Land South West Of Sapulo Dair, Davidstow, Camelford, Cornwall | Cornwall | South West | England | PL32 | 213675 | 86266 | Cornwall Council | PA20/02612 | [5 empty] | 2020-04-29
| 7951 | 2020-06-30 | Aniron Renewables | Xtratherm UK | Solar Photovoltaics | n/a | n/a | 1.684 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Permission Granted | Awaiting Construction | Xtratherm, Park Road, Holmewood, Chesterfield, Derbyshire | Derbyshire | East Midlands | England | S42 5UY | 442491 | 366364 | North East Derbyshire District Council | 20/00256/FL | [5 empty] | 2020-03-10 | [6 empty] | 2020-05-01 |  |  |  | 2023-05-01
| 7953 | 2020-06-30 | Cadzow Brothers | Isle of Luing Wind Farm | Wind Onshore | n/a | n/a | 0.225 | n/a |  |  |  | 0.225 | 1 | 45 | n/a | Planning Application Submitted | Application Submitted | Land East Of Camas Nan Gall To, Isle Of Luing Argyll And Bute, Oban, Strathclyde | Argyll and Bute | Scotland | Scotland | PA34 4UF | 174143 | 707638 | Argyll and Bute Council | 20/00589/PP | [5 empty] | 2020-04-21
| 7954 | 2020-06-30 | Lightrock Power | Crick Road | Solar Photovoltaics | n/a | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Land at, Crick Road, Yelvertoft, Northampton, Northamptonshire | Northamptonshire | East Midlands | England | NN6 6NA | 458955 | 273857 | Daventry District Council | DA/2020/0200 | [5 empty] | 2020-04-08
| 7957 | 2020-06-30 | Hammars Hill Energy | Hammars Hill Wind Farm Extension | Wind Onshore | n/a | n/a | 8.4 | n/a |  |  |  | 4.2 | 2 | 150 | n/a | Planning Application Submitted | Application Submitted | Hammars Hill, Evie, Orkney, Orkney Isles | Orkney Islands | Scotland | Scotland | KW17 2NH | 337526 | 1022979 | Orkney Islands Council | 20/112/TPP | [5 empty] | 2020-04-02
| 7961 | 2020-06-30 | Pegasus Group | Woodington Solar Farm (Resubmission) | Solar Photovoltaics | n/a | n/a | 40 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Woodington Solar Farm, Woodington Road, Woodington Farm, East Wellow, Romsey, Hampshire | Hampshire | South East | England | SO51 6DQ | 430472 | 121002 | Test Valley Borough Council | 20/00814/FULLS | [5 empty] | 2020-04-14
| 7963 | 2020-06-30 | Private Developer | West Beacon Solar Park | Solar Photovoltaics | n/a | n/a | 0.82 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | West Beacon Farm, Deans Lane, Woodhouse Eaves, Loughborough, Leicestershire | Leicestershire | East Midlands | England | LE12 8TE | 450290 | 315294 | Charnwood Borough Council | P/20/0701/2 | [5 empty] | 2020-04-14
| 7964 | 2020-06-30 | Private Developer | Concess Road | Wind Onshore | n/a | n/a | 0.25 | n/a |  |  |  | 0.25 | 1 | 46 | n/a | Planning Application Submitted | Application Submitted | Land South Of, 26 Concess Road, Victoria Bridge, Strabane, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT82 9NA | 47855 | 554006 | Derry City and Strabane District | LA11/2020/0243/F | [5 empty] | 2020-03-19
| 7966 | 2020-06-30 | Noriker Power | Perserverance Road (Resubmission) | Battery | Co-located with fossil fuel | n/a | 20 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Old School Lane, Hereford, Hereford and Worcester | Hereford and Worcester | West Midlands | England | HR4 9BP | 351122 | 241621 | Herefordshire Council | P200967/F | [5 empty] | 2020-03-23
| 7968 | 2020-06-30 | Push Energy | Ricoh UK Products | Solar Photovoltaics | n/a | n/a | 1.21 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Ricoh Uk Products Ltd, Shifnal Road, Priorslee, Telford, Shropshire | Shropshire | West Midlands | England | TF2 9NS | 371831 | 309510 | Telford and Wrekin Council | TWC/2020/0293 | [5 empty] | 2020-03-31
| 7969 | 2020-06-30 | Elgin Energy | Hale Solar Farm | Solar Photovoltaics | n/a | n/a | 40 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Hale Farm, Hulcott, Aylesbury, Buckinghamshire | Buckinghamshire | South East | England | HP22 5AX | 485958 | 216460 | Aylesbury Vale District Council | 20/00779/APP | [5 empty] | 2020-03-26
| 7971 | 2020-06-30 | Livesey Brothers | Lower Fields Mushroom Farm | Solar Photovoltaics | n/a | n/a | 0.308 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Lower Fields Mushroom Farm, Normanton Road, Packington, Ashby-De-La-Zouch, Leicestershire | Leicestershire | East Midlands | England | LE65 1XA | 437043 | 313723 | North West Leicestershire District Council | 20/00504/FUL | [5 empty] | 2020-03-26
| 7972 | 2020-06-30 | Bird Brothers | Fairview Farm | Solar Photovoltaics | n/a | n/a | 0.15 | n/a |  |  |  | n/a | n/a | n/a | Ground | Planning Application Submitted | Application Submitted | Fairview Farm, St. Ives Road, Eltisley, St. Neots, Cambridgeshire | Cambridgeshire | Eastern | England | PE19 6TW | 527238 | 260862 | Huntingdonshire District Council | 20/00480/FUL | [5 empty] | 2020-03-24
| 7976 | 2020-06-30 | Plumbs | Brookhouse Mill | Solar Photovoltaics | n/a | n/a | 0.29 | n/a |  |  |  | n/a | n/a | n/a | Roof | Planning Application Submitted | Application Submitted | Brookhouse Mill, Old Lancaster Lane, Preston, Lancashire | Lancashire | North West | England | PR1 7PZ | 352606 | 430425 | Preston City Council | 06/2020/0270 | [5 empty] | 2020-03-18
| 7979 | 2020-06-30 | ENGIE Renewables | Gort Energy Storage (Resubmission) | Battery | Stand-alone Storage | n/a |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | South of Classic Marble Shower, 31 Garvaghy Bridge Road, Garvaghy, Dungannon, Co Tyrone | Co. Tyrone | Northern Ireland | Northern Ireland | BT70 2EW | 68925 | 522071 | Mid Ulster | LA10/2020/0206/F | [5 empty] | 2020-02-27
| 7980 | 2020-06-30 | Levington Developments | The Brick Bank | Battery | Stand-alone Storage | n/a | 7 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land, Malleable Way, Stockton-On-Tees, Cleveland | County Durham | North East | England | TS18 2QX | 445779 | 519695 | Stockton on Tees Borough Council | 18/1521/FUL | [5 empty] | 2018-07-12 | [6 empty] | 2019-01-08 |  |  |  | 2022-01-08
| 7981 | 2020-06-30 | Kingfisher / Solar Century | B and Q Distribution Centre Highworth Road | Battery | Stand-alone Storage | n/a |  | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Unit 1, B and Q Distribution Centre, Milne Way, Swindon, Wiltshire | Wiltshire | South West | England | SN3 4AJ | 417904 | 189004 | Swindon Borough Council | S/18/0856 | [5 empty] | 2018-06-29 | [6 empty] | 2018-08-21 |  |  |  | 2021-08-21
| 7982 | 2020-06-30 | Together Housing | Smithybrook View | Battery | Co-located with RE | n/a | 1.2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Unit 9, Smithybrook View, Market Street, Clay Cross, Chesterfield, Derbyshire | Derbyshire | East Midlands | England | S45 9PA | 439260 | 363303 | North East Derbyshire District Council | 18/00134/FL | [5 empty] | 2018-02-19 | [6 empty] | 2018-05-24 |  |  |  | 2021-05-24
| 7983 | 2020-06-30 | Eco-Economix | Park Farm | Battery | Stand-alone Storage | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Park Farm, Hook Street, Lydiard Tregoze, Swindon, Wiltshire | Wiltshire | South West | England | SN5 3NY | 410168 | 184116 | Wiltshire Council | 18/00952/FUL | [5 empty] | 2018-03-09 | [6 empty] | 2018-05-03 |  |  |  | 2021-05-03
| 7984 | 2020-06-30 | Volta Energy Storage | Mucklow Hill | Battery | Stand-alone Storage | n/a | 12 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Hayward Bridge, Mucklow Hill, Haulage Yard, Halesowen, West Midlands | West Midlands | West Midlands | England | B62 8DL | 397456 | 284053 | Dudley Metropolitan Borough Council | P17/1489 | [5 empty] | 2017-10-18 | [6 empty] | 2017-12-21 |  |  |  | 2020-12-21
| 7985 | 2020-06-30 | Amber Infrastructure Group | Unit 5 XL Business Park | Battery | Stand-alone Storage | n/a | 49.9 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Unit 5, X L Business Park, Statham Road, Skelmersdale, Lancashire | Lancashire | North West | England | WN8 8DY | 346649 | 407589 | West Lancashire Borough Council | 2017/0968/FUL | [5 empty] | 2017-09-13 | [6 empty] | 2017-12-18 |  |  |  | 2020-12-18
| 7986 | 2020-06-30 | Peel Energy | Britannia House | Battery | Co-located with fossil fuel | n/a | 10 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land Adjacent to Britannia Hou, Dock Road, Birkenhead, Merseyside | Merseyside | North West | England | CH41 1DF | 330400 | 390620 | Wirral Council | APP/17/01190 | [5 empty] | 2017-09-20 | [6 empty] | 2017-12-04 |  |  |  | 2020-12-04
| 7987 | 2020-06-30 | Green Hedge | Whitehouse Farm Energy Barn | Battery | Stand-alone Storage | n/a | 40 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Whitehouse Farm, Blakes Lane, Guarlford, Malvern, Hereford and Worcester | Hereford and Worcester | West Midlands | England | WR13 6NZ | 382225 | 245650 | Malvern Hills District Council | 17/01504/FUL | [5 empty] | 2017-10-03 | [6 empty] | 2017-11-29 |  |  |  | 2020-11-29
| 7988 | 2020-06-30 | Green Hedge | Catsbrain Farm | Battery | Stand-alone Storage | n/a | 30 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | N/o Kingsdown Road and W/o, Catsbrain Farm, Swindon, Wiltshire | Wiltshire | South West | England | SN3 | 417507 | 189131 | Swindon Borough Council | S/17/0979 | [5 empty] | 2017-06-19 | [6 empty] | 2017-11-03 |  |  |  | 2020-11-03
| 7989 | 2020-06-30 | Renewable Energy Systems (RES) | Roaring Hill (Resubmission) | Battery | Stand-alone Storage | n/a | 30 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | Land To East Of Balsillie Avenue And To The South Of The Limekilns Glenrothes Fife | Fife | Scotland | Scotland |  | 325451 | 702300 | Fife Council | 17/03318/FULL | [5 empty] | 2017-10-17 | [6 empty] | 2017-12-22 |  |  |  | 2020-12-22
| 7990 | 2020-07-03 | Veolia | Alton Materials Recovery Facility | EfW Incineration | n/a | n/a | 33 | Yes |  |  |  | n/a | n/a | n/a | n/a | Planning Application Submitted | Application Submitted | Alton Materials Recovery Facility, A31, Alton GU34 4JD, | Hampshire | South East | England | GU34 4JD | 474546 | 141537 | Hampshire County Council | 33619/007 | [5 empty] | 2020-05-26
| 7991 | 2020-07-06 | Wind Estate | Brownhill Farm (Resubmission) | Wind Onshore | n/a | n/a | 8.4 | n/a |  |  |  | 4.2 | 2 | 150 | n/a | Planning Application Submitted | Application Submitted | Brownhill Farm, West Benhar Road, Harthill, Shotts, Strathclyde | North Lanarkshire | Scotland | Scotland | ML7 5TG | 288880 | 662140 | North Lanarkshire Council | 20/00504/FUL | [5 empty] | 2020-05-12
| 7994 | 2020-07-06 | United Utilities | Clifton Marsh Waste Water Treatment Works | Battery | Co-located with RE | 6466 | 2 | n/a |  |  |  | n/a | n/a | n/a | n/a | Planning Permission Granted | Awaiting Construction | CLIFTON MARSH WASTE WATER TREATMENT WORKS, PRESTON NEW ROAD, FRECKLETON | Lancashire | North West | England |  | 345614 | 428877 | Lancashire County Council | LCC/2019/0045 | [5 empty] | 2019-08-01 | [6 empty] | 2019-08-28 |  |  |  | 2022-08-28